## Website
PROTECT
(D) - Application progress dependent on project indicated
updated: 10/16/2025
***Project details included in this Interconnections table reflect Level 4 applications under the MPUC Chapter 324 Rule as of August 2018 only. Generation requests and generators interconnected to the CMP network prior to 2018 (whether under MPUC Chapter 324 or previous interconnection procedures) are not captured in this table.*** | [11 empty] | Feasibility Study |  | Impact Study |  | Combined Study |  | ReStudy |  | Facility Study |  | IA | ReQueued Restudy
PRJ | ISO_QP | Queue Position | (D) PRJ | r'Qd | Date App Rec'd | Town | Substation | Circuit | Type of Generation | Total Size (kW) | Battery Size (kW) | Start | Completion | Start | Completion | Start | Completion | Start | Completion | Start | Completion | Fully Executed Interconnection Agreement | R`Qd One Start | R`Qd One Stop | R`Qd Two Start | R`Qd Two Stop | R`Qd Three Start | R`Qd Three Stop | R`Qd Four Start | R`Qd Four Stop | Estimated Commercial Operation Date | Application Status | Energized Status | 25% Payment | Cluster Area | 115 kV SS | T. Level 0=Screen NC=Non-Comp 3=Full | 1.3.9 Approval | i39: RC Approval | PROJECT STATUS
1 | 0 | 0 | 0 |  | 2018-08-06 | Fairfield | FAIRFIELD | 817D3 | Solar | 4320 | 0 |  |  |  |  | 2018-08-20 | 2018-10-04 |  |  |  |  | 2019-06-07 | [8 empty] | Q1 2021 | Fully Executed Interconnection Agreement | Yes | 2020-09-03 | Cluster 02 - Winslow-County Rd-Lakewood -1 | Winslow-County Rd | 0 | 2018-10-11 |  | EXECUTED/ENERGIZED
2 | 0 | 0 | 0 |  | 2018-08-29 | Oxford | OXFORD | 437D1 | Solar | 4600 | 0 |  |  |  |  | 2018-10-11 | 2018-12-17 |  |  |  |  | 2019-05-30 | [8 empty] | Q4 2020 | Fully Executed Interconnection Agreement | Yes | 2019-08-22 | Cluster 05 - Lewiston Loop - 1 | Norway | Individual | 2019-08-26 |  | EXECUTED/ENERGIZED
3 | 0 | 0 | 0 |  | 2018-08-29 | Oxford | OXFORD | 437D2 | Solar | 4600 | 0 |  |  |  |  | 2018-10-11 | 2018-12-17 |  |  |  |  | 2019-05-30 | [8 empty] | Q4 2020 | Fully Executed Interconnection Agreement | Yes | 2019-08-22 | Cluster 05 - Lewiston Loop - 1 | Norway | Individual | 2019-08-26 |  | EXECUTED/ENERGIZED
4 | 0 | 0 | 0 |  | 2018-10-15 | Augusta | BLAIR ROAD | 207D2 | Solar | 7200 | 0 |  |  |  |  | 2018-10-24 | 2019-01-04 |  |  |  |  | 2019-05-30 | [8 empty] | Q4 2020 | Fully Executed Interconnection Agreement | Yes | 2020-07-10 | Cluster 11 - Augusta E-Puddledock-Bowman St - 2 | Augusta E/Puddledock/Bowman St | Individual | 2019-08-26 |  | EXECUTED/ENERGIZED
5 | 0 | 0 | 0 |  | 2018-10-29 | Fairfield | SHAWMUT | 852D1 | Solar | 4990 | 0 |  |  |  |  | 2018-12-11 | 2019-02-13 |  |  |  |  | 2019-05-30 | [8 empty] | Q4 2020 | Fully Executed Interconnection Agreement | Yes | 2020-07-15 | Cluster 02 - Winslow-County Rd-Lakewood -1 | Lakewood | 0 | 2019-05-01 |  | EXECUTED/ENERGIZED
6 | 0 | 0 | 0 |  | 2018-11-19 | Winslow | WINSLOW | 870D2 | Solar | 6999 | 0 |  |  |  |  | 2019-02-08 | 2019-04-11 |  |  |  |  | 2019-06-07 | [8 empty] | Q4 2020 | Fully Executed Interconnection Agreement | Yes | 2020-09-01 | Cluster 02 - Winslow-County Rd-Lakewood -1 | Winslow-County Rd | Individual | 2020-07-27 |  | EXECUTED/ENERGIZED
7 | 0 | 0 | 0 |  | 2019-01-24 | Waterville | SOUTH WATERVILLE | 855D2 | Solar | 4920 | 0 |  |  |  |  | 2019-03-15 | 2019-05-16 |  |  |  |  | 2019-06-07 | [8 empty] | Q1 2021 | Fully Executed Interconnection Agreement | Yes | 2020-09-03 | Cluster 02 - Winslow-County Rd-Lakewood -1 | Winslow-County Rd | 0 | 2019-12-13 |  | EXECUTED/ENERGIZED
8 | 0 | 0 | 0 |  | 2019-02-04 | Rumford | RUMFORD INDUSTRIAL PARK | 466D1 | Battery | 4999 | 4999 |  |  |  |  | 2019-04-29 | 2019-07-02 |  |  |  |  | 2019-08-05 | [8 empty] | Q1 2021 | Fully Executed Interconnection Agreement | Yes | 2020-08-19 | Cluster 10 - Roxbury-Rumford-Woodstock - 1 | Rumford IP | 0 | 2020-04-10 |  | EXECUTED/ENERGIZED
9 | 0 | 0 | 0 |  | 2019-03-05 | Sanford | HIGH STREET | 626D1 | Solar | 4950 | 0 |  |  |  |  | 2019-07-11 | 2019-09-09 |  |  |  |  | 2020-02-19 | [8 empty] | Q4 2020 | Fully Executed Interconnection Agreement | Yes | 2020-08-12 | Cluster 04 - Sanford-Quaker Hill - 1 | Sanford | 0 | 2019-12-30 |  | EXECUTED/ENERGIZED
10 | 0 | 0 | 0 |  | 2019-03-11 | Fairfield | SHAWMUT | 852D1 | Solar | 650 | 0 |  |  |  |  | 2019-05-02 | 2019-07-01 |  |  |  |  | 2019-12-05 | [8 empty] | Q4 2019 | Fully Executed Interconnection Agreement | Yes | 2019-10-12 | Cluster 12 - Winslow-County Rd-Lakewood - 2 | Lakewood | 0 |  | Not Required | EXECUTED/ENERGIZED
11 | 0 | 0 | 0 |  | 2019-04-02 | Sanford | SANFORD INDUSTRIAL PARK | 656D3 | Battery | 4999 | 4999 |  |  |  |  | 2019-06-20 | 2019-08-23 |  |  |  |  | 2020-05-11 | [8 empty] | Q4 2020 | Fully Executed Interconnection Agreement | No | 2021-02-02 | Cluster 04 - Sanford-Quaker Hill - 1 | Sanford | NC | 2020-07-14 |  | EXECUTED
12 | 0 | 0 | 0 |  | 2019-04-25 | Dover | DOVER | 815D1 | Battery | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Guilford |  |  |  | WITHDRAWN
13 | 0 | 0 | 0 |  | 2019-05-02 | Manchester | PUDDLEDOCK ROAD | 262D1 | Battery | 0 | 0 | [10 empty] | 2020-05-15 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 01 - Augusta/ E_Puddledock/ BowmanSt - 1 | Augusta E/Puddledock/Bowman St | Individual |  | 2022-10-21 | EXECUTED-WITHDRAWN
14 | 0 | 0 | 0 |  | 2019-05-03 | Hartland | HARTLAND | 824D2 | Solar | 4000 | 0 |  |  |  |  | 2019-06-17 | 2019-08-20 |  |  |  |  | 2019-08-29 | [8 empty] | Q1 2021 | Fully Executed Interconnection Agreement | Yes | 2020-09-03 | Cluster 16 - Wyman Area - 1 | Hartland | 0 | 2019-12-13 |  | EXECUTED/ENERGIZED
15 | 0 | 0 | 0 |  | 2019-05-15 | South Portland | MUSSEY ROAD | 636D2 | Battery | 0 | 0 | [10 empty] | 2019-11-06 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 15 - Greater Portland - 1 | Mussey Road | Individual | 2023-05-31 |  | 0
16 | 0 | 0 | 0 |  | 2019-05-15 | Hartland | HARTLAND | 824D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Hartland |  |  |  | WITHDRAWN
17 | 0 | 0 | 0 |  | 2019-05-16 | Wells | PRATT & WHITNEY | 661D2 | Solar | 4800 | 0 |  |  |  |  | 2019-07-12 | 2019-09-16 |  |  |  |  | 2020-02-13 | [8 empty] | Q4 2020 | Fully Executed Interconnection Agreement | Yes | 2020-09-10 | Cluster 04 - Sanford-Quaker Hill - 1 | Pratt & Whitney | 0 | 2020-04-28 |  | EXECUTED/ENERGIZED
18 | 0 | 0 | 0 |  | 2019-05-21 | Sanford | SOUTH SANFORD | 667D1 | Solar | 4950 | 0 |  |  |  |  | 2019-07-12 | 2019-09-16 |  |  |  |  | 2020-02-18 | [8 empty] | Q4 2020 | Fully Executed Interconnection Agreement | Yes | 2020-09-22 | Cluster 04 - Sanford-Quaker Hill - 1 | Sanford | NC | 2020-04-28 |  | EXECUTED
19 | 0 | 0 | 0 |  | 2019-05-23 | Wells | PRATT & WHITNEY | 661D2 | Solar | 4950 | 0 |  |  |  |  | 2020-01-27 | 2020-03-30 |  |  |  |  | 2020-05-01 | [8 empty] | Q4 2020 | Fully Executed Interconnection Agreement | Yes | 2020-11-25 | Cluster 04 - Sanford-Quaker Hill - 1 | Pratt & Whitney | NC | 2020-07-30 |  | EXECUTED/ENERGIZED
20 | 0 | 0 | 0 |  | 2019-06-07 | Pittsfield | DETROIT | 812D1 | Solar | 4875 | 0 |  |  |  |  | 2019-07-16 | 2019-09-17 |  |  |  |  | 2019-10-02 | [8 empty] | Q4 2020 | Fully Executed Interconnection Agreement | Yes | 2020-09-01 | Cluster 06 - Detroit-Guilford-Belfast - 1 | Detroit | 0 | 2020-02-26 |  | EXECUTED/ENERGIZED
21 | 0 | 0 | 0 |  | 2019-06-13 | Unity | UNITY | 860D1 | Solar | 4980 | 0 |  |  |  |  | 2019-08-05 | 2019-10-07 |  |  |  |  | 2019-11-14 | [8 empty] | Q4 2020 | Fully Executed Interconnection Agreement | Yes | 2020-09-03 | Cluster 06 - Detroit-Guilford-Belfast - 1 | Belfast | 0 | 2019-12-13 |  | EXECUTED/ENERGIZED
22 | 0 | 0 | 0 |  | 2019-06-14 | Palmyra | NEWPORT | 837D1 | Solar | 4990 | 0 |  |  |  |  | 2019-07-24 | 2019-09-25 |  |  |  |  | 2020-02-13 | [8 empty] | Q2 2021 | Fully Executed Interconnection Agreement | Yes | 2020-09-15 | Cluster 06 - Detroit-Guilford-Belfast - 1 | Detroit | 0 | 2020-02-26 |  | EXECUTED/ENERGIZED
23 | 0 | 0 | 0 |  | 2019-06-17 | Poland | HOTEL ROAD | 420D4 | Solar | 4875 | 0 |  |  |  |  | 2019-08-14 | 2019-10-16 |  |  |  |  | 2019-12-05 | [8 empty] | Q3 2020 | Fully Executed Interconnection Agreement | Yes | 2020-05-21 | Cluster 05 - Lewiston Loop - 1 | Hotel Rd/Gulf/Middle St/Crowleys/Norway | 0 | 2020-02-26 |  | EXECUTED/ENERGIZED
24 | 0 | 0 | 0 |  | 2019-07-12 | Lewiston | DEER RIPS | 412D4 | Solar | 4900 | 0 |  |  |  |  | 2019-08-14 | 2019-10-16 |  |  |  |  | 2019-12-05 | [8 empty] | Q3 2020 | Fully Executed Interconnection Agreement | Yes | 2020-11-10 | Cluster 05 - Lewiston Loop - 1 | Hotel Rd/Gulf/Middle St/Crowleys/Norway | 0 | 2020-02-28 |  | EXECUTED/ENERGIZED
25 | 0 | 0 | 0 |  | 2019-07-18 | Madison | SKOWHEGAN NORTH SIDE | 853D1 | Solar | 4999 | 0 |  |  |  |  | 2019-10-01 | 2019-12-03 |  |  |  |  | 2020-02-06 | [8 empty] | Q4 2020 | Fully Executed Interconnection Agreement | Yes | 2020-05-21 | Cluster 02 - Winslow-County Rd-Lakewood -1 | Lakewood | NC | 2020-04-28 |  | EXECUTED/ENERGIZED
26 | 0 | 0 | 0 |  | 2019-07-31 | Madison | SKOWHEGAN NORTH SIDE | 853D1 | Solar/Battery | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 02 - Winslow-County Rd-Lakewood -1 | Lakewood | 3 |  |  | WITHDRAWN
27 | 0 | 0 | 0 |  | 2019-07-31 | Saco | DUNSTAN | 617D2 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Vallee Lane |  |  |  | WITHDRAWN
28 | 0 | 0 | 0 |  | 2019-08-06 | Auburn | HOTEL ROAD | 420D4 | Solar | 4990 | 0 |  |  |  |  | 2020-01-02 | 2020-03-05 |  |  |  |  | 2020-04-08 | 2022-06-28 | 2022-08-09 | 2023-01-10 |  | 2023-02-23 | 2023-04-03 |  |  | Q2 2021 | Fully Executed Interconnection Agreement | No | 2020-09-19 | Cluster 05 - Lewiston Loop - 1 | Hotel Rd/Gulf/Middle St/Crowleys/Norway | 3 | 2022-07-19 |  | RE_QUEUED_FullEx
29 | 0 |  | 28 |  | 2019-08-06 | Auburn | HOTEL ROAD | 420D4 | Solar | 4990 | 0 |  |  |  |  | 2020-04-29 | 2020-06-29 |  |  |  |  | 2020-08-26 | 2022-09-26 | 2022-11-09 | 2023-07-13 | 2023-08-24 |  |  |  |  | Q2 2021 | Fully Executed Interconnection Agreement | No | 2020-11-30 | Cluster 05 - Lewiston Loop - 1 | Hotel Rd/Gulf/Middle St/Crowleys/Norway | 3 | 2022-07-19 |  | RE_QUEUED_FullEx
30 | 0 | 0 | 0 |  | 2019-08-06 | Lewiston | DEER RIPS | 412D4 | Solar | 0 | 0 | [10 empty] | 2020-06-17 | [8 empty] | Q3 2020 | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 05 - Lewiston Loop - 1 | Hotel Rd/Gulf/Middle St/Crowleys/Norway | 3 | 2022-07-19 |  | RE_QUEUED_FullEx
31 | 0 | 0 | 0 |  | 2019-08-07 | Rumford | RUMFORD | 447D2 | Solar | 4990 | 0 |  |  |  |  | 2019-11-20 | 2020-01-29 |  |  |  |  | 2020-04-13 | [8 empty] | Q4 2020 | Fully Executed Interconnection Agreement | Yes | 2020-08-11 | Cluster 10 - Roxbury-Rumford-Woodstock - 1 | Rumford | 0 | 2020-06-25 |  | EXECUTED/ENERGIZED
32 | 0 | 0 | 0 |  | 2019-08-07 | Gorham | FORT HILL | 624D1 | Solar/Battery | 4990 | 3000 |  |  |  |  | 2019-11-20 | 2020-01-29 |  |  |  |  | 2020-04-15 | [8 empty] | Q4 2020 | Fully Executed Interconnection Agreement | Yes | 2020-08-27 | Cluster 07 - Raymond - 1 | Raymond | NC | 2020-07-14 |  | EXECUTED/ENERGIZED
33 | 0 | 0 | 0 |  | 2019-08-07 | Auburn | GREAT FALLS | 436D6 | Solar | 4990 | 0 |  |  |  |  | 2019-12-05 | 2020-02-04 |  |  |  |  | 2020-04-20 | [8 empty] | Q4 2020 | Fully Executed Interconnection Agreement | Yes | 2020-08-23 | Cluster 05 - Lewiston Loop - 1 | Hotel Rd/Gulf/Middle St/Crowleys/Norway | NC | 2020-07-14 |  | EXECUTED/ENERGIZED
34 | 0 |  | 0 |  | 2019-08-07 | Auburn | GREAT FALLS | 436D6 | Solar | 999 | 0 |  |  |  |  | 2020-07-13 | 2020-09-15 |  |  |  |  | 2020-11-08 | 2023-06-19 | 2023-08-09 | 2024-12-06 | 2025-02-13 |  |  |  |  | Q3 2028 | Fully Executed Interconnection Agreement | No | 2024-04-04 | Cluster 05 - Lewiston Loop - 1 | Hotel Rd/Gulf/Middle St/Crowleys/Norway | 3 | 2022-07-19 | Not Required | RE_QUEUED_FullEx
35 | 0 | 0 | 0 |  | 2019-08-07 | Woodstock | TRAP CORNER | 453D1 | Solar/Battery | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Woodstock |  |  |  | WITHDRAWN
36 | 0 | 0 | 0 |  | 2019-08-07 | South Thomaston | THOMASTON CREEK | 246D1 | Solar/Battery | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Highland/Park St |  |  |  | WITHDRAWN
37 | 0 | 0 | 0 |  | 2019-08-09 | Dayton | BIDDEFORD PUMP | 605D2 | Solar | 4990 | 0 | 2019-10-21 | 2019-11-20 | 2020-01-10 | 2020-02-11 | [6 empty] | 2020-04-02 | [8 empty] | Q4 2020 | Fully Executed Interconnection Agreement | Yes | 2020-06-26 | Cluster 14 - Louden-Biddeford IP - 1 | Louden | 0 | 2020-04-28 |  | EXECUTED
38 | 0 | 0 | 0 |  | 2019-08-09 | Dayton | BIDDEFORD PUMP | 605D1 | Solar/Battery | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Louden |  |  |  | WITHDRAWN
39 | 0 | 0 | 0 |  | 2019-08-09 | Dayton | BIDDEFORD PUMP | 605D1 | Solar/Battery | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Louden |  |  |  | WITHDRAWN
40 | 0 | 0 | 0 |  | 2019-08-09 | Scarborough | SCARBOROUGH | 693D1 | Solar | 4980 | 0 |  |  |  |  | 2019-12-05 | 2020-02-04 |  |  |  |  | 2020-04-10 | [8 empty] | Q4 2020 | Fully Executed Interconnection Agreement | Yes | 2020-06-26 | Cluster 15 - Greater Portland - 1 | Spring St | 0 | 2020-07-14 |  | EXECUTED/ENERGIZED
41 | 0 | 0 | 0 |  | 2019-08-09 | Buxton | BONNY EAGLE | 610D2 | Solar/Battery | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Kimball Road/Lovell |  |  |  | WITHDRAWN
42 | 0 | 0 | 0 |  | 2019-08-09 | Buxton | BONNY EAGLE | 610D2 | Solar/Battery | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Kimball Road/Lovell |  |  |  | WITHDRAWN
43 | 0 | 0 | 0 |  | 2019-08-12 | Harrison | KIMBALL ROAD | 423D1 | Solar/Battery | 4990 | 4990 |  |  |  |  | 2019-10-31 | 2020-01-10 |  |  |  |  | 2020-01-28 | [8 empty] | Q4 2020 | Fully Executed Interconnection Agreement | Yes | 2020-08-24 | Cluster 03 - Kimball Rd-Lovell - 1 | Kimball Road/Lovell | 0 | 2020-02-28 |  | EXECUTED/ENERGIZED
44 | 0 | 0 | 0 |  | 2019-08-12 | Saco | LOUDEN | 633D1 | Solar | 4800 | 0 | 2019-10-23 | 2019-11-27 | 2020-01-13 | 2020-02-11 |  |  | 2020-03-18 |  |  |  | 2020-04-03 | [8 empty] | Q4 2020 | Fully Executed Interconnection Agreement | Yes | 2020-06-15 | Cluster 14 - Louden-Biddeford IP - 1 | Louden | NC | 2020-04-28 |  | EXECUTED
45 | 0 | 0 | 0 |  | 2019-08-13 | Lewiston | CROWLEYS | 411D1 | Solar | 2000 | 0 |  |  |  |  | 2019-10-08 | 2019-12-11 |  |  |  |  | 2020-01-06 | [8 empty] | Q3 2020 | Fully Executed Interconnection Agreement | Yes | 2020-05-28 | Cluster 05 - Lewiston Loop - 1 | Hotel Rd/Gulf/Middle St/Crowleys/Norway | 0 | 2020-02-28 |  | EXECUTED/ENERGIZED
46 | 0 | 0 | 0 |  | 2019-08-15 | Winslow | WINSLOW | 870D2 | Solar | 4600 | 0 |  |  |  |  | 2019-10-08 | 2019-12-11 |  |  |  |  | 2020-07-01 | [8 empty] | Q4 2020 | Fully Executed Interconnection Agreement | Yes | 2022-03-24 | Cluster 02 - Winslow-County Rd-Lakewood -1 | Winslow-County Rd | NC | 2020-08-31 |  | EXECUTED
47 | 0 | 0 | 0 |  | 2019-08-15 | Biddeford | BIDDEFORD PUMP | 605D1 | Solar | 0 | 0 | [10 empty] | 2020-08-05 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 14 - Louden-Biddeford IP - 1 | Louden | NC | 2021-03-30 |  | EXECUTED-WITHDRAWN
48 | 0 | 0 | 0 |  | 2019-08-15 | Waterville | OAKLAND | 839D1 | Solar | 4600 | 0 |  |  |  |  | 2019-10-08 | 2019-12-11 |  |  |  |  | 2020-06-11 | [8 empty] | Q4 2020 | Fully Executed Interconnection Agreement | Yes | 2020-11-12 | Cluster 02 - Winslow-County Rd-Lakewood -1 | Winslow-County Rd | NC | 2020-07-14 |  | EXECUTED/ENERGIZED
49 | 0 | 0 | 0 |  | 2019-08-19 | Fryeburg | FRYEBURG TAP | 405D2 | Solar | 4900 | 0 |  |  |  |  | 2019-11-04 | 2020-01-14 |  |  |  |  | 2020-03-02 | [8 empty] | Q4 2020 | Fully Executed Interconnection Agreement | Yes | 2020-09-10 | Cluster 03 - Kimball Rd-Lovell - 1 | Kimball Road/Lovell | 0 | 2020-04-28 |  | EXECUTED/ENERGIZED
50 | 0 | 0 | 0 |  | 2019-08-21 | Naples | RAYMOND 115 KV | 445D2 | Solar | 2000 | 0 |  |  |  |  | 2019-11-05 | 2020-01-15 |  |  |  |  | 2020-04-20 | [8 empty] | Q1 2020 | Fully Executed Interconnection Agreement | Yes | 2020-08-11 | Cluster 07 - Raymond - 1 | Raymond | NC | 2020-07-14 |  | EXECUTED/ENERGIZED
51 | 0 | 0 | 0 |  | 2019-08-29 | Skowhegan | WESTON HYDRO | 866D1 | Solar | 2625 | 0 |  |  |  |  | 2019-10-07 | 2019-12-10 |  |  |  |  | 2020-01-15 | [8 empty] | Q4 2021 | Fully Executed Interconnection Agreement | Yes | 2020-06-06 | Cluster 02 - Winslow-County Rd-Lakewood -1 | Lakewood | NC | 2020-04-28 |  | EXECUTED/ENERGIZED
52 | 0 | 0 | 0 |  | 2019-08-29 | Lebanon | LEBANON | 695D2 | Solar/Battery | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Sanford |  |  |  | WITHDRAWN
53 | 0 | 0 | 0 |  | 2019-08-29 | Standish | SHAWS MILL ROAD | 660D1 | Solar | 4990 | 0 |  |  |  |  | 2019-10-01 | 2019-12-03 |  |  |  |  | 2020-02-06 | [8 empty] | Q4 2021 | Fully Executed Interconnection Agreement | Yes | 2020-09-10 | Cluster 07 - Raymond - 1 | Raymond | 0 | 2020-04-28 |  | EXECUTED/ENERGIZED
54 | 0 | 0 | 0 |  | 2019-08-29 | Auburn | HOTEL ROAD | 420D2 | Solar/Battery | 0 | 0 | [10 empty] | 2021-02-19 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 05 - Lewiston Loop - 1 | Hotel Rd/Gulf/Middle St/Crowleys/Norway | 3 | 2022-07-19 |  | EXECUTED-WITHDRAWN
55 | 0 | 0 | 0 |  | 2019-08-29 | Auburn | HOTEL ROAD | 420D2 | Solar/Battery | 0 | 0 |  |  |  |  | 2021-07-13 | 2021-09-13 | 2021-12-11 | 2022-01-18 | [12 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 18 - Lewiston Loop - 2 | Hotel Rd/Gulf/Middle St/Crowleys/Norway | 3 |  |  | WITHDRAWN
56 | 0 | 0 | 0 |  | 2019-08-29 | Auburn | HOTEL ROAD | 420D2 | Solar/Battery | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 18 - Lewiston Loop - 2 | Hotel Rd/Gulf/Middle St/Crowleys/Norway | 3 |  |  | Kelsey Haley
57 | 0 | 0 | 0 |  | 2019-08-29 | Bethel | BETHEL | 403D1 | Solar | 4800 | 0 |  |  |  |  | 2019-10-31 | 2020-01-10 |  |  |  |  | 2020-02-18 | [8 empty] | Q4 2020 | Fully Executed Interconnection Agreement | Yes | 2020-07-23 | Cluster 10 - Roxbury-Rumford-Woodstock - 1 | Woodstock | 0 | 2020-04-28 |  | EXECUTED/ENERGIZED
58 | 0 | 0 | 0 |  | 2019-08-30 | Auburn | HOTEL ROAD | 420D2 | Solar/Battery | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 18 - Lewiston Loop - 2 | Hotel Rd/Gulf/Middle St/Crowleys/Norway | 3 |  |  | WITHDRAWN
59 | 0 | 0 | 0 |  | 2019-08-30 | Buxton | BONNY EAGLE | 610D2 | Solar | 0 | 0 | [10 empty] | 2020-04-03 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 03 - Kimball Rd-Lovell - 1 | Kimball Road/Lovell | 3 | 2023-04-27 |  | EXECUTED-WITHDRAWN
60 | 0 | 0 | 0 |  | 2019-08-30 | Buxton | BONNY EAGLE | 610D2 | Solar/Battery | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Kimball Road/Lovell |  |  |  | WITHDRAWN
61 | 0 | 0 | 0 |  | 2019-09-03 | Winthrop | WINTHROP | 256D1 | Solar/Battery | 4990 | 5000 |  |  |  |  | 2019-10-31 | 2020-01-10 |  |  |  |  | 2020-04-02 | [8 empty] | Q2 2021 | Fully Executed Interconnection Agreement | Yes | 2020-10-08 | Cluster 11 - Augusta E-Puddledock-Bowman St - 2 | Augusta E/Puddledock/Bowman St | 0 | 2020-04-28 |  | EXECUTED/ENERGIZED
62 | 0 | 0 | 0 |  | 2019-09-03 | Rumford | RUMFORD INDUSTRIAL PARK | 466D1 | Solar | 4988 | 0 |  |  |  |  | 2019-10-03 | 2019-12-09 |  |  |  |  | 2020-01-16 | [8 empty] | Q4 2020 | Fully Executed Interconnection Agreement | Yes | 2020-08-12 | Cluster 10 - Roxbury-Rumford-Woodstock - 1 | Rumford IP | NC | 2020-07-14 |  | EXECUTED/ENERGIZED
63 | 0 | 0 | 0 |  | 2019-09-04 | Otisfield | CASCO TAP | 463D1 | Solar/Battery | 3880 | 4000 |  |  |  |  | 2019-10-07 | 2019-12-10 |  |  |  |  | 2020-06-19 | [8 empty] | Q4 2020 | Fully Executed Interconnection Agreement | Yes | 2020-10-19 | Cluster 07 - Raymond - 1 | Raymond | NC | 2020-07-14 |  | EXECUTED/ENERGIZED
64 | 0 | 0 | 0 |  | 2019-09-04 | Gray | GRAY | 416D2 | Solar | 4990 | 0 |  |  |  |  | 2019-10-03 | 2019-12-09 |  |  |  |  | 2020-03-26 | [8 empty] | Q4 2020 | Fully Executed Interconnection Agreement | Yes | 2020-09-13 | Cluster 15 - Greater Portland - 1 | Elm St | 0 | 2020-04-28 |  | EXECUTED/ENERGIZED
65 | 0 | 0 | 0 |  | 2019-09-05 | Turner | TURNER | 454D1 | Solar/Battery | 0 | 0 | [10 empty] | 2020-04-03 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 05 - Lewiston Loop - 1 | Hotel Rd/Gulf/Middle St/Crowleys/Norway | 3 | 2022-07-19 |  | EXECUTED-WITHDRAWN
66 | 0 | 0 | 0 |  | 2019-09-05 | Farmington | STURTEVANT | 858D3 | Solar | 4875 | 0 |  |  |  |  | 2019-10-02 | 2019-11-12 |  |  |  |  | 2019-11-20 | [8 empty] | Q4 2020 | Fully Executed Interconnection Agreement | Yes | 2020-09-03 | Cluster 08 - Sturtevant-Leeds-Livermore-Ludden-Riley - 1 | Sturtevant | 0 | 2019-12-30 |  | EXECUTED/ENERGIZED
67 | 0 | 0 | 0 |  | 2019-09-05 | Standish | BONNY EAGLE | 610D2 | Solar | 0 | 0 | [10 empty] | 2020-11-14 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 03 - Kimball Rd-Lovell - 1 | Kimball Road/Lovell | 3 | 2023-04-27 |  | RE_QUEUED_FullEx
68 | 0 | 0 | 0 |  | 2019-09-05 | Leeds | LEEDS | 471D2 | Solar | 20000 | 0 | 2019-12-04 | 2020-01-03 | 2020-01-28 | 2020-02-27 | [6 empty] | 2020-06-11 | [8 empty] | Q2 2021 | Fully Executed Interconnection Agreement | Yes | 2020-09-22 | Cluster 08 - Sturtevant-Leeds-Livermore-Ludden-Riley - 1 | Leeds | Individual | 2021-12-17 |  | EXECUTED
69 | 0 | 0 | 0 |  | 2019-09-06 | Turner | TURNER | 454D1 | Solar/Battery | 0 | 0 | [10 empty] | 2020-09-11 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 05 - Lewiston Loop - 1 | Hotel Rd/Gulf/Middle St/Crowleys/Norway | 3 |  | 2022-07-22 | EXECUTED-WITHDRAWN
70 | 0 | 0 | 0 |  | 2019-09-09 | Readfield | PUDDLEDOCK ROAD | 262D1 | Solar | 4950 | 0 |  |  |  |  | 2020-04-02 | 2020-06-08 |  |  |  |  | 2020-06-17 | 2023-07-14 |  |  | 2023-07-25 |  |  |  |  | Q4 2020 | Fully Executed Interconnection Agreement | Yes | 2021-08-19 | Cluster 01 - Augusta - 1 | Augusta E/Puddledock/Bowman St | 3 | 2021-01-04 |  | RE_QUEUED_FullEx/ENERGIZED
71 | 0 | 0 | 0 |  | 2019-09-09 | Readfield | PUDDLEDOCK ROAD | 262D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Augusta E/Puddledock/Bowman St |  |  |  | WITHDRAWN
72 | 0 | 0 | 0 |  | 2019-09-09 | Leeds | LEEDS | 471D2 | Solar | 0 | 0 | [10 empty] | 2020-08-07 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 08 - Sturtevant-Leeds-Livermore-Ludden-Riley - 1 | Leeds | 3 |  | 2023-12-15 | EXECUTED-WITHDRAWN
73 | 0 | 0 | 0 |  | 2019-09-09 | Leeds | LEEDS | 471D2 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Leeds |  |  |  | WITHDRAWN
74 | 0 | 0 | 0 |  | 2019-09-09 | Fryeburg | FRYEBURG | 415D2 | Solar | 0 | 0 |  |  |  |  | 2020-03-31 | 2020-06-05 |  |  |  |  | 2020-05-18 | [8 empty] | Q4 2021 | WITHDRAWN | WITHDRAWN |  | Cluster 03 - Kimball Rd-Lovell - 1 | Kimball Road/Lovell | 3 | 2023-04-27 |  | EXECUTED
75 | 0 | 0 | 0 |  | 2019-09-09 | Waterville | OAKLAND | 839D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 02 - Winslow-County Rd-Lakewood -1 | Winslow-County Rd | 3 |  |  | WITHDRAWN
76 | 0 | 0 | 0 |  | 2019-09-09 | Gorham | FORT HILL | 624D2 | Solar | 0 | 0 |  |  |  |  | 2020-06-24 | 2020-08-27 |  |  |  |  | 2020-09-23 | 2023-03-23 | 2023-05-05 | [7 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 07 - Raymond - 1 | Raymond | 3 | 2023-12-21 |  | EXECUTED-WITHDRAWN
77 | 0 | 0 | 0 |  | 2019-09-09 | Baldwin | BALDWIN | 691D1 | Solar | 4950 | 0 |  |  |  |  | 2019-10-18 | 2019-12-19 |  |  |  |  | 2020-04-29 | [8 empty] | Q4 2021 | Fully Executed Interconnection Agreement | Yes | 2020-09-16 | Cluster 03 - Kimball Rd-Lovell - 1 | Kimball Road/Lovell | NC | 2020-07-14 |  | EXECUTED/ENERGIZED
78 | 0 | 0 | 0 |  | 2019-09-10 | Saco | DUNSTAN | 617D2 | Solar/Battery | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Vallee Lane |  |  |  | WITHDRAWN
79 | 0 | 0 | 0 |  | 2019-09-10 | Parkman | GUILFORD | 821D1 | Solar | 4875 | 0 |  |  |  |  | 2019-10-11 | 2019-12-16 |  |  |  |  | 2020-01-15 | 2022-10-12 | 2022-11-23 | 2022-12-20 |  | 2023-10-12 | 2023-11-28 |  |  | Q1 2022 | Fully Executed Interconnection Agreement | Yes | 2020-07-02 | Cluster 06 - Detroit-Guilford-Belfast - 1 | Guilford | 0 | 2020-04-10 |  | RE_QUEUED_FullEx
80 | 0 | 0 | 0 |  | 2019-09-10 | Pittsfield | DETROIT | 812D1 | Solar | 4980 | 0 |  |  |  |  | 2019-10-09 | 2019-12-12 |  |  |  |  | 2020-05-11 | [8 empty] | Q4 2021 | Fully Executed Interconnection Agreement | Yes | 2020-05-18 | Cluster 06 - Detroit-Guilford-Belfast - 1 | Detroit | NC | 2020-06-25 |  | EXECUTED/ENERGIZED
81 | 0 | 0 | 0 |  | 2019-09-10 | Washington | STICKNEYS CORNER | 245D2 | Solar | 2000 | 0 |  |  |  |  | 2019-10-29 | 2019-12-24 |  |  |  |  | 2020-02-25 | [8 empty] | Q1 2021 | Fully Executed Interconnection Agreement | Yes | 2020-08-19 | Cluster 09 - Midcoast - 1 | Coopers Mills | 0 | 2020-04-28 |  | EXECUTED/ENERGIZED
82 | 0 | 0 | 0 |  | 2019-09-10 | Oakland | COUNTY RD (RICE RIPS) | 873D1 | Solar | 4990 | 0 |  |  |  |  | 2019-12-05 | 2020-02-04 |  |  |  |  | 2020-05-05 | [8 empty] | Q4 2021 | Fully Executed Interconnection Agreement | Yes | 2020-11-05 | Cluster 02 - Winslow-County Rd-Lakewood -1 | Winslow-County Rd | NC | 2020-06-25 |  | EXECUTED/ENERGIZED
83 | 0 | 0 | 0 |  | 2019-09-10 | Wilton | WILTON | 885D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Sturtevant |  |  |  | WITHDRAWN
84 | 0 | 0 | 0 |  | 2019-09-10 | North Bridgton | BRIDGTON | 406D1 | Solar | 4990 | 0 |  |  |  |  | 2019-12-05 | 2020-02-04 |  |  |  |  | 2020-03-26 | [8 empty] | Q4 2021 | Fully Executed Interconnection Agreement | Yes | 2020-09-10 | Cluster 03 - Kimball Rd-Lovell - 1 | Kimball Road/Lovell | NC | 2020-07-14 |  | EXECUTED/ENERGIZED
85 | 0 | 0 | 0 |  | 2019-09-10 | Baldwin | BALDWIN | 691D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 13 - Kimball Rd-Lovell - 2 | Kimball Road/Lovell | 3 |  |  | WITHDRAWN
86 | 0 | 0 | 0 |  | 2019-09-10 | Naples | BRIDGTON 34 KV | 406D4 | Solar | 0 | 0 | [10 empty] | 2020-07-24 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 03 - Kimball Rd-Lovell - 1 | Kimball Road/Lovell | 3 | 2023-04-27 |  | EXECUTED-WITHDRAWN
87 | 0 | 0 | 0 |  | 2019-09-11 | Hermon | BANGOR HYDRO (Versant) | 120D1 | Solar | 4990 | 0 |  |  |  |  | 2020-03-10 | 2020-05-13 | 2021-08-23 | 2021-09-16 |  |  | 2021-11-30 | [8 empty] | Q4 2021 | Fully Executed Interconnection Agreement | Yes | 2023-07-20 | N/A | Emera Transmission |  | 2022-08-17 |  | EXECUTED
88 | 0 | 0 | 0 |  | 2019-09-13 | Turner | TURNER TAP | 467D1 | Solar/Battery | 0 | 0 | [10 empty] | 2020-03-26 | [8 empty] | Q2 2021 | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 05 - Lewiston Loop - 1 | Hotel Rd/Gulf/Middle St/Crowleys/Norway | 3 | 2022-07-19 |  | EXECUTED
89 | 0 | 0 | 0 |  | 2019-09-13 | Monmouth | MONMOUTH | 457D1 | Solar | 4950 | 0 |  |  |  |  | 2019-10-29 | 2020-01-02 |  |  |  |  | 2020-03-23 | [9 empty] | Fully Executed Interconnection Agreement | Yes | 2020-09-28 | N/A | Monmouth | 0 | 2020-06-25 |  | EXECUTED/ENERGIZED
90 | 0 | 0 | 0 |  | 2019-09-16 | Harrison | KIMBALL ROAD | 423D1 | Solar | 0 | 0 | [10 empty] | 2020-04-14 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 03 - Kimball Rd-Lovell - 1 | Kimball Road/Lovell | 3 | 2023-04-27 |  | EXECUTED-WITHDRAWN
91 | 0 | 0 | 0 |  | 2019-09-16 | Standish | BONNY EAGLE | 610D2 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 03 - Kimball Rd-Lovell - 1 | Kimball Road/Lovell | 3 |  | 2023-04-22 | WITHDRAWN
92 | 0 | 1 - PDRD | 0 | RQP-1 | 2019-09-16 | Manchester | PUDDLEDOCK ROAD | 262D1 | Solar | 1990 | 4990 |  |  |  |  | 2020-09-17 | 2020-11-23 | 2023-11-30 | 2024-01-15 |  |  | 2021-01-12 | 2023-09-11 | 2023-10-24 | [6 empty] | Q3 2026 | Fully Executed Interconnection Agreement | No | 2024-09-18 | Cluster 11 - Augusta E-Puddledock-Bowman St - 2 | Augusta E/Puddledock/Bowman St | 3 | 2024-05-28 |  | RE_QUEUED_FullEx
93 | 0 | 0 | 0 |  | 2019-09-17 | Wiscasset | MAINE YANKEE | 274D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Maine Yankee | 0 |  |  | WITHDRAWN
94 | 0 | 0 | 0 |  | 2019-09-17 | Augusta | AUGUSTA K5 | 200D2 | Solar | 4988 | 0 |  |  |  |  | 2019-10-11 | 2019-12-16 |  |  |  |  | 2020-01-28 | [8 empty] | Q4 2020 | Fully Executed Interconnection Agreement | Yes | 2020-08-17 | Cluster 11 - Augusta E-Puddledock-Bowman St - 2 | Augusta E/Puddledock/Bowman St | 0 | 2020-04-28 |  | EXECUTED/ENERGIZED
95 | 0 | 0 | 0 |  | 2019-09-17 | Manchester | MANCHESTER | 233D1 | Solar | 4500 | 0 |  |  |  |  | 2020-01-30 | 2020-04-06 |  |  |  |  | 2020-04-14 | [8 empty] | Q4 2021 | Fully Executed Interconnection Agreement | Yes | 2021-05-26 | Cluster 01 - Augusta - 1 | Augusta E/Puddledock/Bowman St | 3 | 2021-01-04 |  | EXECUTED/ENERGIZED
96 | 0 | 0 | 0 |  | 2019-09-18 | Fryeburg | FRYEBURG TAP | 405D1 | Solar | 0 | 0 | [10 empty] | 2020-10-19 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 03 - Kimball Rd-Lovell - 1 | Kimball Road/Lovell | 3 | 2023-04-27 |  | EXECUTED
97 | 0 | 0 | 0 |  | 2019-09-18 | Lebanon | LEBANON | 695D2 | Solar | 2000 | 0 |  |  |  |  | 2020-04-08 | 2020-06-11 |  |  |  |  | 2020-07-01 | [8 empty] | Q2 2022 | Fully Executed Interconnection Agreement (combo PRJ 98) | Yes | 2020-08-11 | Cluster 04 - Sanford-Quaker Hill - 1 | Sanford | 3 | 2022-06-27 |  | EXECUTED
98 | 0 | 0 | 0 |  | 2019-09-18 | Lebanon | LEBANON | 695D2 | Solar | 1750 | 0 |  |  |  |  | 2020-04-08 | 2020-06-11 |  |  |  |  | 2020-07-01 | [8 empty] | Q2 2022 | Fully Executed Interconnection Agreement (combo PRJ 97) | Yes | 2020-08-11 | Cluster 04 - Sanford-Quaker Hill - 1 | Sanford | 3 | 2022-06-27 |  | EXECUTED
99 | 0 | 0 | 0 |  | 2019-09-19 | Turner | TURNER TAP | 467D1 | Solar | 0 | 0 | [10 empty] | 2020-08-07 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 05 - Lewiston Loop - 1 | Hotel Rd/Gulf/Middle St/Crowleys/Norway | 3 | 2022-07-19 |  | EXECUTED
100 | 0 | 0 | 0 |  | 2019-09-19 | Turner | TURNER TAP | 467D1 | Solar | 0 | 0 | [10 empty] | 2020-08-07 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 05 - Lewiston Loop - 1 | Hotel Rd/Gulf/Middle St/Crowleys/Norway | 3 | 2022-07-19 |  | EXECUTED
101 | 0 | 0 | 0 |  | 2019-09-19 | Limerick | LIMERICK | 632D1 | Solar | 2000 | 0 |  |  |  |  | 2020-02-10 | 2020-04-15 |  |  |  |  | 2020-05-06 | [8 empty] | Q1 2028 | Fully Executed Interconnection Agreement (combo PRJ 106) | No | 2020-08-12 | Cluster 03 - Kimball Rd-Lovell - 1 | Kimball Road/Lovell | 3 | 2023-04-27 |  | EXECUTED
102 | 0 | 0 | 0 |  | 2019-09-19 | Washington | STICKNEYS CORNER | 245D1 | Solar | 4000 | 0 |  |  |  |  | 2020-04-16 | 2020-06-18 |  |  |  |  | 2020-07-02 | [9 empty] | Fully Executed Interconnection Agreement | Yes | 2020-07-20 | Cluster 09 - Midcoast - 1 | Coopers Mills | NC | 2020-10-05 |  | EXECUTED/ENERGIZED
103 | 0 | 0 | 0 |  | 2019-09-19 | Saco | LOUDEN | 633D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Louden |  |  |  | WITHDRAWN
104 | 0 | 0 | 0 |  | 2019-09-19 | Old Orchard Beach | CROWLEYS | 411D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A |  |  |  |  | WITHDRAWN
105 | 0 | 0 | 0 |  | 2019-09-19 | Newport | NEWPORT | 837D2 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Detroit |  |  |  | WITHDRAWN
106 | 0 | 0 | 0 |  | 2019-09-19 | Limerick | LIMERICK | 632D1 | Solar | 2000 | 0 |  |  |  |  | 2020-02-10 | 2020-04-15 |  |  |  |  | 2020-05-06 | [8 empty] | Q1 2028 | Fully Executed Interconnection Agreement (combo PRJ 101) | No | 2020-08-12 | Cluster 03 - Kimball Rd-Lovell - 1 | Kimball Road/Lovell | 3 | 2023-04-27 |  | EXECUTED
107 | 0 | 0 | 0 |  | 2019-09-19 | Jay | LIVERMORE FALLS | 428D3 | Solar | 2000 | 0 |  |  |  |  | 2020-02-07 | 2020-04-14 |  |  |  |  | 2020-04-28 | [8 empty] | Q4 2021 | Fully Executed Interconnection Agreement (combo PRJ 108) | Yes | 2020-08-11 | Cluster 08 - Sturtevant-Leeds-Livermore-Ludden-Riley - 1 | Livermore Falls | 0 | 2020-06-25 |  | EXECUTED/ENERGIZED
108 | 0 | 0 | 0 |  | 2019-09-19 | Jay | LIVERMORE FALLS | 428D3 | Solar | 1250 | 0 |  |  |  |  | 2020-02-07 | 2020-04-14 |  |  |  |  | 2020-04-28 | [8 empty] | Q4 2021 | Fully Executed Interconnection Agreement (combo PRJ 107) | Yes | 2020-08-11 | Cluster 08 - Sturtevant-Leeds-Livermore-Ludden-Riley - 1 | Livermore Falls | 0 | 2020-06-25 |  | EXECUTED/ENERGIZED
109 | 0 | 0 | 0 |  | 2019-09-20 | Auburn | HOTEL ROAD | 420D6 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Hotel Rd/Gulf/Middle St/Crowleys |  |  |  | WITHDRAWN
110 | 0 | 0 | 0 |  | 2019-10-31 | North Berwick | BASSETT | 602D3 | Solar | 4950 | 0 |  |  |  |  | 2020-01-30 | 2020-04-06 |  |  |  |  | 2020-04-13 | [9 empty] | Fully Executed Interconnection Agreement | Yes | 2020-07-20 | Cluster 04 - Sanford-Quaker Hill - 1 | Quaker Hill | NC | 2020-07-14 |  | EXECUTED/ENERGIZED
111 | 0 | 0 | 0 |  | 2019-09-20 | Brunswick | BRUNSWICK WEST SIDE | 213D3 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Topsham |  |  |  | WITHDRAWN
112 | 0 | 0 | 0 |  | 2019-09-20 | Berwick | PRATT & WHITNEY | 661D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Pratt & Whitney |  |  |  | WITHDRAWN
113 | 0 | 0 | 0 |  | 2019-09-20 | Newport | NEWPORT | 837D2 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Detroit |  |  |  | WITHDRAWN
114 | 0 | 0 | 0 |  | 2019-09-20 | Sabattus | CROWLEYS | 411D1 | Solar | 2000 | 0 |  |  |  |  | 2020-02-18 | 2020-04-22 |  |  |  |  | 2020-04-14 | [8 empty] | Q2 2021 | Fully Executed Interconnection Agreement | Yes | 2020-08-19 | Cluster 05 - Lewiston Loop - 1 | Hotel Rd/Gulf/Middle St/Crowleys/Norway | 3 | 2022-07-19 |  | EXECUTED/ENERGIZED
115 | 0 | 0 | 0 |  | 2019-09-20 | Sabattus | FACTORY ISLAND | 621D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A |  |  |  |  | WITHDRAWN
116 | 0 | 0 | 0 |  | 2019-09-23 | Winthrop | WINTHROP | 256D3 | Solar | 2500 | 0 |  |  |  |  | 2020-04-29 | 2020-07-02 |  |  |  |  | 2020-09-29 | [8 empty] | Q3 2021 | Fully Executed Interconnection Agreement | Yes | 2021-02-17 | Cluster 01 - Augusta - 1 | Augusta E/Puddledock/Bowman St | 3 | 2021-01-04 |  | EXECUTED/ENERGIZED
117 | 0 | 0 | 0 |  | 2019-09-23 | Parkman | GUILFORD | 821D3 | Solar | 0 | 0 | [10 empty] | 2020-07-13 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 06 - Detroit-Guilford-Belfast - 1 | Guilford | 3 | 2023-08-31 |  | RE_QUEUED_FullEx
118 | 0 | 0 | 0 |  | 2019-09-23 | Bingham | WYMAN HYDRO | 872D1 | Solar | 4950 | 0 |  |  |  |  | 2019-11-18 | 2020-01-27 |  |  |  |  | 2020-03-26 | [8 empty] | Q3 2021 | Fully Executed Interconnection Agreement | Yes | 2021-01-22 | Cluster 16 - Wyman Area - 1 | Wyman Hydro | 0 | 2020-06-25 |  | EXECUTED/ENERGIZED
119 | 0 | 0 | 0 |  | 2019-09-23 | Orland | BUCKSPORT | 806D2 | Solar/Battery | 4990 | 4990 |  |  |  |  | 2019-11-18 | 2020-01-27 |  |  |  |  | 2020-03-02 | [8 empty] | Q2 2021 | Fully Executed Interconnection Agreement | Yes | 2020-09-13 | Cluster 06 - Detroit-Guilford-Belfast - 1 | Bucksport | 0 | 2020-04-28 |  | EXECUTED/ENERGIZED
120 | 0 | 0 | 0 |  | 2019-09-23 | Pittsfield | BURNHAM | 807D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Detroit | NC |  |  | WITHDRAWN
121 | 0 | 0 | 0 |  | 2019-09-24 | Harrison | KIMBALL ROAD | 423D1 | Solar/Battery | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 13 - Kimball Rd-Lovell - 2 | Kimball Road/Lovell | 3 |  |  | WITHDRAWN
122 | 0 | 0 | 0 |  | 2019-09-24 | Waldoboro | WALDOBORO | 252D2 | Solar | 2500 | 0 | 2019-11-12 | 2019-12-16 | 2020-02-27 |  |  |  | 2020-03-12 | 2020-04-27 |  |  | 2020-04-29 | [8 empty] | Q4 2020 | Fully Executed Interconnection Agreement | Yes | 2020-08-18 | Cluster 09 - Midcoast - 1 | Highland/Park St | 0 | 2020-06-25 |  | EXECUTED/ENERGIZED
123 | 0 | 0 | 0 |  | 2019-09-24 | Augusta | BLAIR ROAD | 207D2 | Solar/Battery | 3750 | 2000 | 2019-11-12 | 2019-12-16 | 2019-12-27 | 2020-01-28 |  |  | 2020-03-30 | 2020-05-12 |  |  | 2020-04-28 | [8 empty] | Q4 2020 | Fully Executed Interconnection Agreement | Yes | 2021-05-11 | Cluster 01 - Augusta - 1 | Augusta E/Puddledock/Bowman St | 3 | 2021-01-04 |  | EXECUTED/ENERGIZED
124 | 0 | 0 | 0 |  | 2019-09-24 | China | SOUTH CHINA | 244D1 | Solar | 4875 | 0 |  |  |  |  | 2019-11-12 | 2019-01-21 | 2020-03-30 | 2020-04-16 |  |  | 2020-04-23 | [8 empty] | Q4 2020 | Fully Executed Interconnection Agreement | Yes | 2020-08-18 | Cluster 11 - Augusta E-Puddledock-Bowman St - 2 | Augusta E/Puddledock/Bowman St | NC | 2020-06-25 |  | EXECUTED/ENERGIZED
125 | 0 | 0 | 0 |  | 2019-09-25 | Augusta | NORTH AUGUSTA | 272D6 | Solar | 2475 | 0 |  |  |  |  | 2019-10-31 | 2019-01-10 | 2020-04-09 | 2020-05-19 |  |  | 2020-06-04 | [8 empty] | Q2 2021 | Fully Executed Interconnection Agreement | Yes | 2020-08-31 | Cluster 11 - Augusta E-Puddledock-Bowman St - 2 | North Augusta | 0 | 2020-07-30 |  | EXECUTED/ENERGIZED
126 | 0 | 0 | 0 |  | 2019-09-26 | Warren | THOMASTON CREEK | 246D3 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A |  |  |  |  | WITHDRAWN
127 | 0 | 0 | 0 |  | 2019-09-26 | Windham | SWETT ROAD | 682D1/D2 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Raymond |  |  |  | WITHDRAWN
128 | 0 | 0 | 0 |  | 2019-09-26 | Richmond | RICHMOND | 240D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Augusta E/Puddledock/Bowman St |  |  |  | WITHDRAWN
129 | 0 | 0 | 0 |  | 2019-09-26 | Newport | NEWPORT | 837D2 | Solar | 0 | 0 | [10 empty] | 2020-07-16 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 06 - Detroit-Guilford-Belfast - 1 | Detroit | 3 | 2023-08-31 |  | EXECUTED-WITHDRAWN
130 | 0 | 0 | 0 |  | 2019-09-26 | Baldwin | BALDWIN | 691D1 | Solar | 0 | 0 | [10 empty] | 2021-05-24 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 03 - Kimball Rd-Lovell - 1 | Kimball Road/Lovell | 3 | 2023-04-27 |  | EXECUTED-WITHDRAWN
131 | 0 | 0 | 0 |  | 2019-09-26 | Belgrade | COUNTY RD (RICE RIPS) | 873D1 | Solar | 0 | 0 | [10 empty] | 2020-07-01 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 02 - Winslow-County Rd-Lakewood -1 | Winslow-County Rd | 3 | 2021-12-17 |  | EXECUTED-WITHDRAWN
132 | 0 | 0 | 0 |  | 2019-09-26 | Belgrade | COUNTY RD (RICE RIPS) | 873D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 02 - Winslow-County Rd-Lakewood -1 | Winslow-County Rd | 3 |  | 2021-12-21 | WITHDRAWN
133 | 0 | 0 | 0 |  | 2019-09-26 | Livermore Falls | LIVERMORE FALLS | 428D3 | Solar | 3892 | 0 |  |  |  |  | 2020-06-02 | 2020-08-04 |  |  |  |  | 2020-08-24 | [8 empty] | Q4 2020 | Fully Executed Interconnection Agreement | Yes | 2020-09-21 | Cluster 08 - Sturtevant-Leeds-Livermore-Ludden-Riley - 1 | Livermore Falls | NC | 2020-11-20 |  | EXECUTED/ENERGIZED
134 | 0 | 0 | 0 |  | 2019-09-26 | Wales | MONMOUTH | 457D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Monmouth |  |  |  | WITHDRAWN
135 | 0 | 0 | 0 |  | 2019-09-26 | Wales | MONMOUTH | 457D1 | Solar | 4500 | 0 |  |  |  |  | 2020-09-09 | 2020-11-12 |  |  |  |  | 2021-06-04 | [9 empty] | Fully Executed Interconnection Agreement | Yes | 2021-10-21 | N/A | Monmouth | NC | 2021-02-25 |  | EXECUTED
136 | 0 | 0 | 0 |  | 2019-09-26 | Wales | MONMOUTH | 457D1 | Solar | 0 | 0 | [10 empty] | 2021-11-05 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | N/A | Monmouth | NC | 2021-11-23 |  | RE_QUEUED_FullEx
137 | 0 | 0 | 0 |  | 2019-09-26 | Wales | MONMOUTH | 457D1 | Solar | 0 | 0 | [10 empty] | 2021-11-05 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | N/A | Monmouth | NC | 2021-11-23 | Not Required | EXECUTED-WITHDRAWN
138 | 0 | 0 | 0 |  | 2019-09-26 | Naples | BRIDGTON 34 KV | 406D4 | Solar | 0 | 0 | [10 empty] | 2020-11-10 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 03 - Kimball Rd-Lovell - 1 | Kimball Road/Lovell | 3 | 2023-04-27 |  | RE_QUEUED_FullEx
139 | 0 | 0 | 0 |  | 2019-09-27 | Limerick | LIMERICK | 632D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Kimball Road/Lovell |  |  |  | WITHDRAWN
140 | 0 |  | 0 |  | 2019-09-27 | Guilford | GUILFORD | 821D1 | Solar | 999 | 0 |  |  |  |  | 2020-08-05 | 2020-10-08 | 2021-01-04 | 2021-02-03 |  |  | 2021-07-09 | 2023-08-23 | 2024-07-29 | 2024-03-21 |  | 2024-05-22 |  |  |  | Q3 2025 | Fully Executed Interconnection Agreement | No | 2024-06-03 | Cluster 06 - Detroit-Guilford-Belfast - 1 | Guilford | 3 | 2023-08-31 | Not Required | RE_QUEUED_FullEx
141 | 0 | 0 | 0 |  | 2019-09-27 | China | SOUTH CHINA | 244D2 | Solar/Battery | 4478 | 2250 |  |  |  |  | 2020-05-01 | 2020-07-06 |  |  |  |  | 2020-07-24 | [8 empty] | Q4 2020 | Fully Executed Interconnection Agreement | Yes | 2021-05-24 | Cluster 01 - Augusta - 1 | Augusta E/Puddledock/Bowman St | 3 | 2021-01-04 |  | EXECUTED/ENERGIZED
142 | 0 | 0 | 0 |  | 2019-09-27 | Union | UNION | 251D1 | Solar | 4875 | 0 |  |  |  |  | 2019-11-05 | 2020-01-15 |  |  |  |  | 2020-05-11 | [8 empty] | Q4 2020 | Fully Executed Interconnection Agreement | Yes | 2020-10-08 | Cluster 09 - Midcoast - 1 | Coopers Mills | NC | 2020-07-14 |  | EXECUTED/ENERGIZED
143 | 0 | 0 | 0 |  | 2019-09-27 | Poland | HOTEL ROAD | 420D4 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Hotel Rd/Gulf/Middle St/Crowleys |  |  |  | WITHDRAWN
144 | 0 | 0 | 0 |  | 2019-10-01 | Union | UNION | 251D1 | Solar | 2000 | 0 |  |  |  |  | 2020-06-10 | 2020-08-13 |  |  |  |  | 2020-09-23 | 2022-11-10 | [7 empty] | Q4 2020 | Fully Executed Interconnection Agreement | Yes | 2022-09-16 | Cluster 09 - Midcoast - 1 | Coopers Mills | NC | 2021-03-30 |  | EXECUTED
145 | 0 | 0 | 0 |  | 2019-10-01 | Woodstock | BRYANT POND | 407D1 | Solar/Battery | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Woodstock |  |  |  | WITHDRAWN
146 | 0 | 0 | 0 |  | 2019-10-01 | Oxford | OXFORD | 437D1 | Solar/Battery | 4290 | 0 |  |  |  |  | 2019-11-14 | 2020-01-23 |  |  |  |  | 2020-02-13 | [8 empty] | Q4 2020 | Fully Executed Interconnection Agreement | Yes | 2020-09-10 | Cluster 05 - Lewiston Loop - 1 | Norway | 0 | 2020-07-14 |  | EXECUTED/ENERGIZED
147 | 0 | 0 | 0 |  | 2019-10-01 | Limington | NORTH LIMINGTON | 638D1 | Solar/Battery | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Kimball Road/Lovell |  |  |  | WITHDRAWN
148 | 0 | 0 | 0 |  | 2019-10-01 | Rockport | MEADOW ROAD | 270D1 | Solar | 2125 | 0 |  |  |  |  | 2019-12-05 | 2020-02-04 |  |  |  |  | 2020-02-18 | [8 empty] | Q3 2020 | Fully Executed Interconnection Agreement | Yes | 2020-09-13 | Cluster 09 - Midcoast - 1 | Meadow Road | 0 | 2020-04-28 |  | EXECUTED/ENERGIZED
149 | 0 | 0 | 0 |  | 2019-10-01 | Limington | NORTH LIMINGTON | 638D1 | Solar | 0 | 0 | [10 empty] | 2020-08-21 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 03 - Kimball Rd-Lovell - 1 | Kimball Road/Lovell | 3 | 2023-04-27 |  | EXECUTED-WITHDRAWN
150 | 0 | 0 | 0 |  | 2019-10-01 | Baldwin | HIRAM TAP | 692D1 | Solar | 4875 | 0 | 2019-11-14 | 2019-12-16 | 2019-12-27 | 2020-01-28 |  |  | 2020-03-31 | 2020-05-14 |  |  | 2020-05-05 | [8 empty] | Q4 2020 | Fully Executed Interconnection Agreement | Yes | 2020-08-10 | Cluster 03 - Kimball Rd-Lovell - 1 | Kimball Road/Lovell | NC | 2020-07-14 |  | EXECUTED/ENERGIZED
151 | 0 |  | 0 |  | 2019-10-01 | Harrison | KIMBALL ROAD | 423D2 | Solar | 999 | 0 |  |  |  |  | 2020-06-24 | 2020-08-27 | 2024-04-17 | 2024-05-30 |  |  | 2020-09-09 | 2023-08-28 | 2023-10-10 | 2024-01-12 | 2024-03-18 |  |  |  |  | Q4 2025 | Fully Executed Interconnection Agreement | No | 2023-12-11 | Cluster 03 - Kimball Rd-Lovell - 1 | Kimball Road/Lovell | 3 | Not Required | Not Required | RE_QUEUED_FullEx
152 | 0 | 0 | 0 |  | 2019-10-02 | Leeds | LEEDS | 471D2 | Solar | 4999 | 0 |  |  |  |  | 2020-09-29 | 2020-12-04 | 2021-10-01 | 2021-11-12 | 2021-08-10 |  | 2021-11-20 | [9 empty] | Fully Executed Interconnection Agreement | Yes | 2023-10-05 | Cluster 08 - Sturtevant-Leeds-Livermore-Ludden-Riley - 1 | Leeds | 3 | 2023-12-21 |  | EXECUTED
153 | 0 | 0 | 0 |  | 2019-10-02 | Norridgewock | SKOWHEGAN TAP | 864D1 | Solar | 4999 | 0 |  |  |  |  | 2019-12-10 | 2020-02-14 |  |  |  |  | 2020-03-26 | [8 empty] | Q1 2021 | Fully Executed Interconnection Agreement | Yes | 2020-07-22 | Cluster 02 - Winslow-County Rd-Lakewood -1 | Lakewood | NC | 2020-06-25 |  | EXECUTED/ENERGIZED
154 | 0 | 0 | 0 |  | 2019-10-02 | Norridgewock | SKOWHEGAN SOUTH SIDE | 854D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Lakewood |  |  |  | WITHDRAWN
155 | 0 | 0 | 0 |  | 2019-10-03 | Windham | GRAY | 416D3 | Solar/Battery | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Elm St |  |  |  | WITHDRAWN
156 | 0 | 0 | 0 |  | 2019-10-04 | Standish | SHAWS MILL ROAD | 660D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Raymond | NC |  |  | WITHDRAWN
157 | 0 | 0 | 0 |  | 2019-10-04 | Farmington | STURTEVANT | 858D1A | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Sturtevant |  |  |  | WITHDRAWN
158 | 0 | 0 | 0 |  | 2019-10-04 | Farmington | STURTEVANT | 858D1A | Solar | 0 | 0 | [10 empty] | 2021-05-17 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 08 - Sturtevant-Leeds-Livermore-Ludden-Riley - 1 | Sturtevant | 3 | 2023-12-21 |  | RE_QUEUED_FullEx/ENERGIZED
159 | 0 | 0 | 0 |  | 2019-10-04 | Plymouth | NEWPORT | 837D2 | Solar/Battery | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Detroit |  |  |  | WITHDRAWN
160 | 0 | 0 | 0 |  | 2019-10-04 | Plymouth | NEWPORT | 837D2 | Solar/Battery | 0 | 0 | [10 empty] | 2021-05-28 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 06 - Detroit-Guilford-Belfast - 1 | Detroit | 3 |  | 2023-08-23 | EXECUTED-WITHDRAWN
161 | 0 | 0 | 0 |  | 2019-10-07 | Biddeford | BIDDEFORD INDUSTRIAL PARK | 673D1 | Solar | 700 | 0 |  |  |  |  | 2020-04-02 | 2020-06-08 |  |  |  |  | 2020-06-16 | [8 empty] | Q4 2020 | Fully Executed Interconnection Agreement | Yes | 2020-08-17 | Cluster 14 - Louden-Biddeford IP - 1 | Biddeford IP | 0 |  | Not Required | EXECUTED/ENERGIZED
162 | 0 | 0 | 0 |  | 2019-10-07 | Washington | STICKNEYS CORNER | 245D2 | Solar/Battery | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Coopers Mills |  |  |  | WITHDRAWN
163 | 0 | 0 | 0 |  | 2019-10-07 | Windsor | COOPERS MILLS ROAD | 230D1 | Solar | 2000 | 0 |  |  |  |  | 2019-12-23 | 2020-02-27 |  |  |  |  | 2020-04-06 | [8 empty] | Q2 2021 | Fully Executed Interconnection Agreement | Yes | 2020-08-19 | Cluster 09 - Midcoast - 1 | Coopers Mills | NC | 2020-07-14 |  | EXECUTED/ENERGIZED
164 | 0 | 0 | 0 |  | 2019-10-08 | Ripley | DEXTER | 813D3 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Guilford |  |  |  | WITHDRAWN
165 | 0 | 0 | 0 |  | 2019-10-08 | Monmouth | MONMOUTH | 457D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Monmouth |  |  |  | WITHDRAWN
166 | 0 | 0 | 0 |  | 2019-10-08 | Standish | SHAWS MILL ROAD | 660D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Detroit |  |  |  | WITHDRAWN
167 | 0 | 0 | 0 |  | 2019-10-08 | Etna | CARMEL | 808D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Detroit | NC |  |  | WITHDRAWN
168 | 0 | 0 | 0 |  | 2019-10-08 | Topsham | TOPSHAM 34 KV | 250D2 | Solar/Battery | 4990 | 4990 |  |  |  |  | 2019-12-05 | 2020-02-04 |  |  |  |  | 2020-03-02 | [8 empty] | Q2 2021 | Fully Executed Interconnection Agreement | Yes | 2020-08-24 | Cluster 09 - Midcoast - 1 | Topsham | 0 | 2020-04-28 |  | EXECUTED/ENERGIZED
169 | 0 | 0 | 0 |  | 2019-10-09 | Etna | CARMEL | 808D1 | Solar | 0 | 0 | [10 empty] | 2021-05-07 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 06 - Detroit-Guilford-Belfast - 1 | Detroit | 3 |  | 2023-08-23 | EXECUTED-WITHDRAWN
170 | 0 | 0 | 0 |  | 2019-10-09 | South Paris | NORWAY | 435D3 | Solar | 4950 | 0 |  |  |  |  | 2019-11-14 | 2020-01-23 |  |  |  |  | 2020-04-07 | 2022-08-09 | 2022-09-20 | [6 empty] | Q4 2021 | Fully Executed Interconnection Agreement | Yes | 2022-11-28 | Cluster 05 - Lewiston Loop - 1 | Hotel Rd/Gulf/Middle St/Crowleys/Norway | 3 | 2022-07-19 |  | #REF!
171 | 0 | 0 | 0 |  | 2019-10-09 | Naples | BRIDGTON | 406D2 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Kimball Road/Lovell |  |  |  | WITHDRAWN
172 | 0 | 0 | 0 |  | 2019-10-15 | Acton | BUTLER'S CORNER | 612D2 | Solar | 3450 | 0 |  |  |  |  | 2019-12-18 | 2020-05-18 | 2020-04-09 |  |  |  | 2020-06-02 | [8 empty] | Q1 2021 | Fully Executed Interconnection Agreement | Yes | 2020-07-09 | Cluster 04 - Sanford-Quaker Hill - 1 | Sanford | NC | 2020-07-14 |  | #REF!
173 | 0 | 0 | 0 |  | 2019-10-15 | Benton | WINSLOW | 870D1 | Solar/Battery | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A |  |  |  |  | WITHDRAWN
174 | 0 | 0 | 0 |  | 2019-10-15 | Belfast | BELFAST WEST SIDE | 803D5 | Solar | 4750 | 3000 | 2019-11-25 | 2019-12-24 | 2020-01-09 | 2020-02-07 |  |  | 2020-03-31 | 2020-05-14 |  |  | 2020-04-30 | [8 empty] | Q4 2020 | Fully Executed Interconnection Agreement | Yes | 2020-07-23 | Cluster 06 - Detroit-Guilford-Belfast - 1 | Belfast | NC | 2020-06-25 |  | EXECUTED/ENERGIZED
175 | 0 | 0 | 0 |  | 2019-10-15 | Bowdoin | TOPSHAM 34 KV | 250D1 | Solar/Battery | 3638 | 2000 |  |  |  |  | 2020-03-24 | 2020-05-28 |  |  |  |  | 2020-06-19 | [8 empty] | Q4 2020 | Fully Executed Interconnection Agreement | Yes | 2020-10-08 | Cluster 09 - Midcoast - 1 | Topsham | NC | 2020-07-30 |  | EXECUTED/ENERGIZED
176 | 0 | 0 | 0 |  | 2019-10-15 | Gorham | SPRING STREET | 668D5 | Solar | 4875 | 0 |  |  |  |  | 2019-12-11 | 2020-02-17 |  |  |  |  | 2020-05-12 | [8 empty] | Q3 2020 | Fully Executed Interconnection Agreement | Yes | 2020-10-08 | Cluster 15 - Greater Portland - 1 | Spring St | NC | 2020-07-30 |  | EXECUTED/ENERGIZED
177 | 0 | 0 | 0 |  | 2019-10-15 | Carmel | CARMEL | 808D3 | Solar | 0 | 0 | [10 empty] | 2022-05-23 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 17 - Detroit Guilford Belfast - 2 | Detroit | 3 |  |  | EXECUTED-WITHDRAWN
178 | 0 | 0 | 0 |  | 2019-10-15 | Paris | NORWAY | 435D3 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 05 - Lewiston Loop - 1 | Hotel Rd/Gulf/Middle St/Crowleys/Norway | 3 |  | 2022-07-22 | WITHDRAWN
179 | 0 | 0 | 0 |  | 2019-10-15 | Leeds | MONMOUTH | 457D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Monmouth |  |  |  | WITHDRAWN
180 | 0 | 0 | 0 |  | 2019-10-15 | Buxton | BAR MILLS | 678D2 | Solar | 2400 | 0 |  |  |  |  | 2019-12-23 | 2020-02-27 |  |  |  |  | 2020-03-19 | [8 empty] | Q3 2020 | Fully Executed Interconnection Agreement | Yes | 2020-08-10 | Cluster 14 - Louden-Biddeford IP - 1 | West Buxton | 0 | 2020-04-28 |  | EXECUTED/ENERGIZED
181 | 0 | 0 | 0 |  | 2019-10-15 | Knox | UNITY | 860D2 | Solar | 1500 | 0 |  |  |  |  | 2020-02-20 | 2020-04-24 |  |  |  |  | 2020-06-17 | [8 empty] | Q4 2020 | Fully Executed Interconnection Agreement | Yes | 2020-07-06 | Cluster 06 - Detroit-Guilford-Belfast - 1 | Belfast | NC | 2020-07-30 |  | EXECUTED/ENERGIZED
182 | 0 | 0 | 0 |  | 2019-10-15 | Skowhegan | WESTON HYDRO | 866D2 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Lakewood |  |  |  | WITHDRAWN
183 | 0 | 0 | 0 |  | 2019-10-15 | Fairfield | FAIRFIELD | 817D1 | Solar | 4980 | 0 |  |  |  |  | 2019-12-11 | 2020-02-17 |  |  |  |  | 2020-04-16 | [8 empty] | Q3 2021 | Fully Executed Interconnection Agreement | Yes | 2022-01-05 | Cluster 02 - Winslow-County Rd-Lakewood -1 | Winslow-County Rd | 3 | 2021-12-17 |  | EXECUTED/ENERGIZED
184 | 0 | 0 | 0 |  | 2019-10-15 | Skowhegan | SKOWHEGAN TAP | 864D1 | Solar | 1453 | 0 |  |  |  |  | 2020-05-01 | 2020-07-07 | 2020-10-21 | 2020-12-18 | 2020-08-28 | 2020-09-02 | 2021-12-02 | [8 empty] | Q4 2021 | Fully Executed Interconnection Agreement | Yes | 2022-09-16 | Cluster 02 - Winslow-County Rd-Lakewood -1 | Lakewood | 3 | 2021-12-17 |  | EXECUTED
185 | 0 | 0 | 0 |  | 2019-10-15 | Skowhegan | SKOWHEGAN TAP | 864D1 | Solar | 996 | 0 |  |  |  |  | 2022-01-24 | 2022-03-28 |  |  |  |  | 2022-07-29 | [8 empty] | Q3 2025 | Fully Executed Interconnection Agreement | Yes | 2023-06-16 | Cluster XX - Winslow/ County Rd/ Lakewood - TBD | Lakewood | 3 |  | Not Required | EXECUTED
186 | 0 | 0 | 0 |  | 2019-10-15 | Wiscasset | MAINE YANKEE | 274D1 | Solar | 4950 | 0 |  |  |  |  | 2020-05-01 | 2020-07-06 | 2021-06-24 | 2021-07-12 |  |  | 2020-08-18 | [8 empty] | Q3 2020 | Fully Executed Interconnection Agreement | Yes | 2021-10-26 | Cluster 09 - Midcoast - 1 | Maine Yankee | NC | 2020-10-05 |  | EXECUTED/ENERGIZED
187 | 0 | 0 | 0 |  | 2019-10-15 | Farmington | STURTEVANT | 858D1A | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Sturtevant |  |  |  | WITHDRAWN
188 | 0 | 0 | 0 |  | 2019-10-17 | Naples | BRIDGTON 34 KV | 406D4 | Solar | 0 | 0 | [10 empty] | 2021-12-10 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 03 - Kimball Rd-Lovell - 1 | Kimball Road/Lovell | 3 | 2023-04-27 |  | EXECUTED-WITHDRAWN
189 | 0 | 0 | 0 |  | 2019-10-17 | Wiscasset | MESSINA | 238D1 | Solar | 4950 | 0 |  |  |  |  | 2020-04-02 | 2020-06-08 |  |  |  |  | 2020-07-23 | [8 empty] | Q4 2020 | Fully Executed Interconnection Agreement | Yes | 2021-08-19 | Cluster 09 - Midcoast - 1 | Mason | 0 | 2020-08-31 |  | EXECUTED/ENERGIZED
190 | 0 | 0 | 0 |  | 2019-10-17 | Pittsfield | PITTSFIELD | 842D1 | Solar | 0 | 0 | [10 empty] | 2020-07-23 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 06 - Detroit-Guilford-Belfast - 1 | Detroit | 3 | 2023-08-31 |  | EXECUTED
191 | 0 | 0 | 0 |  | 2019-10-17 | Waldoboro | WALDOBORO | 252D2 | Solar | 4950 | 0 |  |  |  |  | 2020-06-04 | 2020-08-07 |  |  |  |  | 2020-10-27 | [8 empty] | Q4 2020 | Fully Executed Interconnection Agreement | Yes | 2021-08-17 | Cluster 09 - Midcoast - 1 | Highland/Park St | NC | 2021-03-30 |  | EXECUTED/ENERGIZED
192 | 0 | 0 | 0 |  | 2019-10-17 | Dover-Foxcroft | DOVER | 815D2 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Guilford |  |  |  | WITHDRAWN
193 | 0 | 0 | 0 |  | 2019-10-17 | Monmouth | MONMOUTH | 457D2 | Solar/Battery | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Monmouth |  |  |  | WITHDRAWN
194 | 0 | 0 | 0 |  | 2019-10-18 | Starks | ANSON | 801D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Winslow/ County Rd/ Lakewood - TBD | Lakewood |  |  |  | WITHDRAWN
195 | 0 | 0 | 0 |  | 2019-10-18 | Augusta | BLAIR ROAD | 207D2 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Augusta E/Puddledock/Bowman St |  |  |  | WITHDRAWN
196 | 0 | 0 | 0 |  | 2019-10-18 | Skowhegan | WESTON HYDRO | 866D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Lakewood |  |  |  | WITHDRAWN
197 | 0 | 0 | 0 |  | 2019-10-18 | Skowhegan | WESTON HYDRO | 866D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Lakewood |  |  |  | WITHDRAWN
198 | 0 | 0 | 0 |  | 2019-10-21 | Lisbon | LISBON | 231D2 | Solar | 0 | 0 | [10 empty] | 2020-05-18 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 05 - Lewiston Loop - 1 | Hotel Rd/Gulf/Middle St/Crowleys/Norway | 3 | 2022-07-19 |  | EXECUTED
199 | 0 | 0 | 0 |  | 2019-10-21 | Oxford | OXFORD | 437D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Norway |  |  |  | WITHDRAWN
200 | 0 | 0 | 0 |  | 2019-10-21 | Livermore | LEEDS | 471D1 | Solar | 999 | 0 |  |  |  |  | 2022-01-04 | 2022-03-02 |  |  |  |  | 2022-03-21 |  |  | 2024-03-12 | 2024-05-16 | [5 empty] | Fully Executed Interconnection Agreement | No | 2025-03-24 | Cluster XX - Sturtevant/ Leeds/ Livermore/ Ludden/ Riley_TBD | Leeds | 3 |  | Not Required | RE_QUEUED_FullEx
201 | 0 | 0 | 0 |  | 2019-10-21 | Troy | UNITY | 860D1 | Solar | 995 | 0 |  |  |  |  | 2020-08-07 | 2020-10-13 | 2023-04-18 | 2023-06-01 | 2022-11-11 | 2023-02-09 | 2020-11-08 | 2022-07-19 | 2022-08-30 | 2023-04-19 | 2023-06-01 |  |  |  |  | Q2 2025 | Fully Executed Interconnection Agreement | Yes | 2023-06-20 | Cluster 06 - Detroit-Guilford-Belfast - 1 | Belfast | 3 |  | Not Required | RE_QUEUED_FullEx
202 | 0 | 0 | 0 |  | 2019-10-21 | Windham | SWETT ROAD | 682D2 | Solar/Battery | 4990 | [5 empty] | 2020-04-28 | 2020-06-29 |  |  |  |  | 2020-07-24 | [8 empty] | Q3 2021 | Fully Executed Interconnection Agreement | No | 2021-05-04 | Cluster 07 - Raymond - 1 | Raymond | 3 | 2023-12-21 |  | EXECUTED
203 | 0 | 0 | 0 |  | 2019-10-21 | Searsport | SEARSPORT | 850D1 | Solar/Battery | 4990 | 4990 |  |  |  |  | 2019-11-20 | 2020-01-29 |  |  |  |  | 2020-03-02 | [8 empty] | Q2 2021 | Fully Executed Interconnection Agreement | Yes | 2020-10-08 | Cluster 06 - Detroit-Guilford-Belfast - 1 | Belfast | NC | 2020-04-28 |  | EXECUTED/ENERGIZED
204 | 0 | 0 | 0 |  | 2019-10-22 | Farmington | STURTEVANT | 858D1A | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Sturtevant |  |  |  | WITHDRAWN
205 | 0 | 0 | 201 |  | 2019-10-22 | Thorndike | UNITY | 860D2 | Solar | 996 | [5 empty] | 2020-12-02 | 2021-02-08 |  |  |  |  | 2021-06-21 | 2023-06-21 |  | 2023-08-22 | [5 empty] | Q4 2021 | Fully Executed Interconnection Agreement | Yes | 2023-03-13 | Cluster 06 - Detroit-Guilford-Belfast - 1 | Belfast | 3 |  | Not Required | RE_QUEUED_FullEx
206 | 0 | 0 | 0 |  | 2019-10-22 | North Berwick | PRATT & WHITNEY | 661D1 | Solar | 4999 | 0 |  |  |  |  | 2020-05-18 | 2020-07-22 |  |  |  |  | 2020-08-04 | [8 empty] | Q3 2021 | Fully Executed Interconnection Agreement | Yes | 2021-03-15 | Cluster 04 - Sanford-Quaker Hill - 1 | Pratt & Whitney | NC | 2020-10-05 |  | EXECUTED/ENERGIZED
207 | 0 | 0 | 0 |  | 2019-10-23 | Athens | ATHENS | 827D2 | Solar | 4400 | 0 |  |  |  |  | 2020-02-03 | 2020-04-08 |  |  |  |  | 2020-04-13 | [8 empty] | Q4 2021 | Fully Executed Interconnection Agreement | Yes | 2020-07-22 | Cluster 16 - Wyman Area - 1 | Athens | 0 | 2020-06-25 |  | EXECUTED/ENERGIZED
208 | 0 | 0 | 0 |  | 2019-10-23 | Augusta | CONY ROAD | 216D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Augusta E/Puddledock/Bowman St |  |  |  | WITHDRAWN
209 | 0 | 0 | 0 |  | 2019-10-23 | Farmingdale | BROWNS CROSSING | 211D2 | Solar | 4850 | 0 |  |  |  |  | 2020-03-05 | 2020-05-08 |  |  |  |  | 2020-05-15 | [8 empty] | Q3 2020 | Fully Executed Interconnection Agreement | Yes | 2020-07-22 | Cluster 11 - Augusta E-Puddledock-Bowman St - 2 | Browns Crossing | 0 | 2020-07-14 |  | EXECUTED/ENERGIZED
210 | 0 | 0 | 0 |  | 2019-10-23 | Palmyra | DETROIT | 812D2 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Detroit |  |  |  | WITHDRAWN
211 | 0 | 0 | 0 |  | 2019-10-23 | Palmyra | NEWPORT | 837D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Detroit |  |  |  | WITHDRAWN
212 | 0 | 0 | 0 |  | 2019-10-23 | Augusta | BOND BROOK | 208D3 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Augusta E/Puddledock/Bowman St |  |  |  | WITHDRAWN
213 | 0 | 0 | 0 |  | 2019-10-23 | Randolph | BOWMAN STREET | 263D1 | Solar | 4990 | [5 empty] | 2019-12-05 | 2020-02-04 |  |  |  |  | 2020-02-13 | [9 empty] | Fully Executed Interconnection Agreement | Yes | 2021-05-05 | Cluster 01 - Augusta - 1 | Augusta E/Puddledock/Bowman St | 3 | 2021-01-04 |  | EXECUTED/ENERGIZED
214 | 0 | 0 | 0 |  | 2019-10-23 | Gardiner | GARDINER | 226D2 | Solar | 875 | 0 |  |  |  |  | 2019-11-25 | 2020-01-31 |  |  |  |  | 2020-03-02 | [8 empty] | Q4 2020 | Fully Executed Interconnection Agreement | Yes | 2020-09-17 | Cluster 11 - Augusta E-Puddledock-Bowman St - 2 | Augusta E/Puddledock/Bowman St | 0 |  | Not Required | EXECUTED/ENERGIZED
215 | 0 | 0 | 0 |  | 2019-10-25 | Durham | LISBON FALLS | 232D2 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Hotel Rd/Gulf/Middle St/Crowleys |  |  |  | WITHDRAWN
216 | 0 | 0 | 0 |  | 2019-10-25 | Vassalboro | MCCOYS | 237D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Augusta E/Puddledock/Bowman St |  |  |  | WITHDRAWN
217 | 0 | 0 | 0 |  | 2019-10-25 | Westbrook | SPRING STREET | 668D5 | Solar | 4990 | 0 |  |  |  |  | 2020-06-02 | 2020-08-04 |  |  |  |  | 2020-08-18 | [8 empty] | Q4 2021 | Fully Executed Interconnection Agreement | Yes | 2021-07-14 | Cluster 15 - Greater Portland - 1 | Spring St | NC | 2020-12-14 |  | EXECUTED
218 | 0 | 0 | 0 |  | 2019-10-25 | Jay | RILEY | 449D2 | Solar | 4950 | 0 |  |  |  |  | 2019-12-05 | 2020-02-04 |  |  |  |  | 2020-06-16 | [8 empty] | Q4 2020 | Fully Executed Interconnection Agreement | Yes | 2020-07-20 | Cluster 08 - Sturtevant-Leeds-Livermore-Ludden-Riley - 1 | Riley | 0 | 2020-07-14 |  | EXECUTED/ENERGIZED
219 | 0 | 0 | 0 |  | 2019-10-25 | Benton | CLINTON | 810D1 | Solar | 4450 | 0 |  |  |  |  | 2019-12-16 | 2020-02-20 |  |  |  |  | 2020-04-03 | [8 empty] | Q2 2021 | Fully Executed Interconnection Agreement | Yes | 2022-01-20 | Cluster 02 - Winslow-County Rd-Lakewood -1 | Winslow-County Rd | 3 | 2021-12-17 |  | EXECUTED/ENERGIZED
220 | 0 | 0 | 0 |  | 2019-10-25 | Warren | WARREN | 253D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Highland/Park St |  |  |  | WITHDRAWN
221 | 0 | 0 | 0 |  | 2019-10-28 | Gardiner | GARDINER | 226D2 | Solar | 3250 | 0 |  |  |  |  | 2020-02-12 | 2020-04-14 |  |  |  |  | 2020-04-27 | [8 empty] | Q4 2020 | Fully Executed Interconnection Agreement | Yes | 2021-05-26 | Cluster 01 - Augusta - 1 | Augusta E/Puddledock/Bowman St | 3 | 2021-01-04 |  | EXECUTED/ENERGIZED
222 | 0 | 0 | 0 |  | 2019-10-28 | Topsham | TOPSHAM 34 KV | 250D1 | Solar/Battery | 0 | 0 | [10 empty] | 2021-01-12 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 09 - Midcoast - 1 | Topsham | NC | 2021-03-30 |  | EXECUTED-WITHDRAWN
223 | 0 | 0 | 0 |  | 2019-10-28 | South Paris | PARIS TAP | 409D1 | Solar/Battery | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Woodstock |  |  |  | WITHDRAWN
224 | 0 | 0 | 0 |  | 2019-10-28 | West Paris | PARIS TAP | 409D1 | Solar/Battery | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Woodstock |  |  |  | WITHDRAWN
225 | 0 | 0 | 0 |  | 2019-10-28 | Mechanic Falls | MECHANIC FALLS | 431D3 | Solar | 0 | 0 | [10 empty] | 2020-04-08 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 05 - Lewiston Loop - 1 | Hotel Rd/Gulf/Middle St/Crowleys/Norway | 3 | 2022-07-19 |  | RE_QUEUED_FullEx
226 | 0 | 0 | 0 |  | 2019-10-28 | Minot | MECHANIC FALLS | 431D2 | Solar | 0 | 0 | [10 empty] | 2020-08-05 | [8 empty] | Q4 2020 | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 05 - Lewiston Loop - 1 | Hotel Rd/Gulf/Middle St/Crowleys/Norway | 3 | 2022-07-19 |  | RE_QUEUED_FullEx
227 | 0 | 0 | 0 |  | 2019-10-29 | Skowhegan | WESTON HYDRO | 866D1 | Solar | 4950 | 0 |  |  |  |  | 2020-03-20 | 2020-05-27 |  |  |  |  | 2020-06-19 | [8 empty] | Q4 2021 | Fully Executed Interconnection Agreement | Yes | 2020-07-17 | Cluster 02 - Winslow-County Rd-Lakewood -1 | Lakewood | 3 | 2021-12-17 |  | EXECUTED/ENERGIZED
228 | 0 | 0 | 0 |  | 2019-10-29 | Paris | PARIS TAP | 409D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Woodstock |  |  |  | WITHDRAWN
229 | 0 | 0 | 0 |  | 2019-10-29 | Madison | SKOWHEGAN NORTH SIDE | 853D1 | Solar | 4000 | 0 |  |  |  |  | 2020-08-14 | 2020-10-20 |  |  |  |  | 2020-10-29 | [9 empty] | Fully Executed Interconnection Agreement | Yes | 2022-01-19 | Cluster 02 - Winslow-County Rd-Lakewood -1 | Lakewood | 3 | 2021-12-17 |  | EXECUTED/ENERGIZED
230 | 0 | 0 | 0 |  | 2019-10-29 | Parkman | GUILFORD | 821D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 17 - Detroit Guilford Belfast - 2 | Guilford | 3 |  |  | WITHDRAWN
231 | 0 | 0 | 0 |  | 2019-10-31 | North Berwick | PRATT & WHITNEY | 661D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Pratt & Whitney |  |  |  | WITHDRAWN
232 | 0 | 0 | 0 |  | 2019-09-20 | Berwick | BASSETT | 602D3 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Quaker Hill |  |  |  | WITHDRAWN
233 | 0 | 0 | 0 |  | 2019-11-01 | Sweden | LOVELL | 430D1 | Solar/Battery | 0 | 0 | [10 empty] | 2020-11-03 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 03 - Kimball Rd-Lovell - 1 | Kimball Road/Lovell | 3 |  | 2023-04-22 | EXECUTED-WITHDRAWN
234 | 0 | 0 | 0 |  | 2019-11-01 | Sweden | LOVELL | 430D1 | Solar/Battery | 0 | 0 | [10 empty] | 2021-07-08 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 03 - Kimball Rd-Lovell - 1 | Kimball Road/Lovell | 3 |  | 2023-04-22 | EXECUTED-WITHDRAWN
235 | 0 | 0 | 0 |  | 2019-11-04 | West Paris | TRAP CORNER | 453D1 | Solar | 2500 | 0 |  |  |  |  | 2020-05-01 | 2020-07-06 |  |  |  |  | 2020-07-13 | [8 empty] | Q4 2021 | Fully Executed Interconnection Agreement | Yes | 2020-08-17 | Cluster 10 - Roxbury-Rumford-Woodstock - 1 | Woodstock | NC | 2020-10-05 |  | EXECUTED/ENERGIZED
236 | 0 | 0 | 0 |  | 2019-11-06 | Benton | WINSLOW | 870D1 | Solar/Battery | 873 | [5 empty] | 2020-07-28 | 2020-09-30 | 2020-11-17 | 2020-01-06 |  |  | 2021-01-19 | [8 empty] | Q4 2020 | Fully Executed Interconnection Agreement | Yes | 2021-06-09 | Cluster 02 - Winslow-County Rd-Lakewood -1 | Winslow-County Rd | 3 |  | Not Required | EXECUTED/ENERGIZED
237 | 0 | 0 | 0 |  | 2019-11-07 | Denmark | DENMARK | 413D1 | Solar/Battery | 0 | 0 | [10 empty] | 2020-05-27 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 03 - Kimball Rd-Lovell - 1 | Kimball Road/Lovell | 3 |  | 2023-04-22 | 0
238 | 0 | 0 | 0 |  | 2019-11-07 | Manchester | MANCHESTER | 233D1 | Solar/Battery | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Augusta E/Puddledock/Bowman St |  |  |  | WITHDRAWN
239 | 0 | 0 | 0 |  | 2019-11-07 | Cornish | HIRAM TAP | 692D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Kimball Road/Lovell |  |  |  | WITHDRAWN
240 | 0 | 0 | 0 |  | 2019-11-07 | Searsport | SEARSPORT | 850D2 | Solar/Battery | 0 | 0 | [10 empty] | 2020-06-16 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 06 - Detroit-Guilford-Belfast - 1 | Belfast | 3 |  | 2023-08-23 | EXECUTED-WITHDRAWN
241 | 0 | 0 | 0 |  | 2019-11-07 | Benton | WINSLOW | 870D1 | Solar | 0 | 0 | [10 empty] | 2021-07-13 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 12 - Winslow-County Rd-Lakewood - 2 | Winslow-County Rd | 3 | 2024-05-28 |  | EXECUTED-WITHDRAWN
242 | 0 | 0 | 0 |  | 2019-11-07 | Benton | WINSLOW | 870D1 | Solar | 0 | 0 | [10 empty] | 2021-07-13 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 12 - Winslow-County Rd-Lakewood - 2 | Winslow-County Rd | 3 | 2023-12-04 | Not Required | EXECUTED-WITHDRAWN
243 | 0 | 0 | 0 |  | 2019-11-07 | Benton | WINSLOW | 870D1 | Solar/Battery | 0 | 0 | [10 empty] | 2021-12-08 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster XX - Winslow/ County Rd/ Lakewood - TBD | Winslow-County Rd | 3 | 2023-12-04 |  | EXECUTED-WITHDRAWN
244 | 0 | 0 | 0 |  | 2019-11-07 | Searsport | SEARSPORT | 850D2 | Solar/Battery | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Belfast |  |  |  | WITHDRAWN
245 | 0 | 0 | 0 |  | 2019-11-07 | Starks | ANSON | 801D1 | Solar | 1800 | 0 |  |  |  |  | 2020-01-30 | 2020-04-01 | 2020-04-24 | 2020-06-04 |  |  | 2020-07-06 | [8 empty] | Q4 2021 | Fully Executed Interconnection Agreement | Yes | 2020-09-07 | Cluster 02 - Winslow-County Rd-Lakewood -1 | Lakewood | 3 | 2021-12-17 |  | EXECUTED/ENERGIZED
246 | 0 | 0 | 0 |  | 2019-11-07 | Dexter | DEXTER | 813D1 | Solar | 0 | 0 | [10 empty] | 2020-08-18 | [8 empty] | Q4 2021 | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 06 - Detroit-Guilford-Belfast - 1 | Guilford | 3 | 2023-08-31 |  | RE_QUEUED_STUDY
247 | 0 | 0 | 0 |  | 2019-11-07 | North Anson | NORTH ANSON | 838D2 | Solar | 2000 | 0 |  |  |  |  | 2020-02-03 | 2020-04-08 |  |  |  |  | 2020-06-04 | [8 empty] | Q4 2021 | Fully Executed Interconnection Agreement | Yes | 2022-05-10 | Cluster 02 - Winslow-County Rd-Lakewood -1 | Lakewood | 3 | 2021-12-17 |  | EXECUTED
248 | 0 | 0 | 0 |  | 2019-11-07 | Westbrook | SPRING STREET | 668D5 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Spring St |  |  |  | WITHDRAWN
249 | 0 | 0 | 0 |  | 2019-11-07 | Skowhegan | SKOWHEGAN NORTH SIDE | 853D2 | Solar | 0 | 0 | [10 empty] | 2021-09-16 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 12 - Winslow-County Rd-Lakewood - 2 | Lakewood | 3 | 2024-05-28 |  | EXECUTED-WITHDRAWN
250 | 0 | 0 | 0 |  | 2019-11-12 | Augusta | BOND BROOK | 208D3 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Augusta E/Puddledock/Bowman St |  |  |  | WITHDRAWN
251 | 0 | 0 | 0 |  | 2019-11-12 | Farmington | FARMINGTON FALLS | 818D2 | Solar | 0 | 0 | [10 empty] | 2020-03-20 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 08 - Sturtevant-Leeds-Livermore-Ludden-Riley - 1 | Sturtevant | NC | 2020-06-25 |  | EXECUTED-WITHDRAWN
252 | 0 | 0 | 0 |  | 2019-11-13 | Berwick | BERWICK | 603D2 | Solar | 3562 | 0 |  |  |  |  | 2019-12-05 | 2020-02-04 |  |  |  |  | 2020-03-24 | [8 empty] | Q4 2020 | Fully Executed Interconnection Agreement | Yes | 2020-08-12 | Cluster 04 - Sanford-Quaker Hill - 1 | Quaker Hill | 0 | 2020-06-25 |  | EXECUTED/ENERGIZED
253 | 0 | 0 | 0 |  | 2019-11-13 | Naples | RAYMOND 115 KV | 445D2 | Solar | 0 | 0 | [10 empty] | 2020-08-04 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 07 - Raymond - 1 | Raymond | 3 | 2023-12-21 |  | EXECUTED-WITHDRAWN
254 | 0 | 0 | 0 |  | 2019-11-13 | Sidney | SOUTH WATERVILLE | 855D2 | Solar | 1950 | 0 |  |  |  |  | 2020-01-27 | 2020-04-01 |  |  |  |  | 2020-05-20 | [8 empty] | Q4 2021 | Fully Executed Interconnection Agreement | Yes | 2020-06-30 | Cluster 02 - Winslow-County Rd-Lakewood -1 | Winslow-County Rd | 3 | 2021-12-17 |  | EXECUTED/ENERGIZED
255 | 0 | 0 | 0 |  | 2019-11-13 | Gorham | FORT HILL | 624D2 | Solar | 0 | 0 | [10 empty] | 2021-06-24 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 07 - Raymond - 1 | Raymond | 3 |  | 2023-12-15 | EXECUTED-WITHDRAWN
256 | 0 | 0 | 0 |  | 2019-11-13 | Rockport | MEADOW ROAD | 270D2 | Solar | 3550 | 0 |  |  |  |  | 2020-04-08 | 2020-06-11 |  |  |  |  | 2020-06-12 | [8 empty] | Q4 2020 | Fully Executed Interconnection Agreement | Yes | 2020-07-23 | Cluster 09 - Midcoast - 1 | Meadow Road | NC | 2020-08-31 |  | EXECUTED/ENERGIZED
257 | 0 | 0 | 0 |  | 2019-11-13 | Hallowell | MANCHESTER | 233D2 | Solar/Battery | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 01 - Augusta - 1 | Augusta E/Puddledock/Bowman St | 3 |  | December | WITHDRAWN
258 | 0 | 0 | 0 |  | 2019-11-13 | Sabattus | CROWLEYS | 411D1 | Solar | 4900 | 0 |  |  |  |  | 2020-03-26 | 2020-06-02 |  |  |  |  | 2020-06-19 | [9 empty] | Fully Executed Interconnection Agreement | Yes | 2020-07-22 | Cluster 05 - Lewiston Loop - 1 | Hotel Rd/Gulf/Middle St/Crowleys/Norway | 3 | 2022-07-19 |  | EXECUTED/ENERGIZED
259 | 0 | 0 | 0 |  | 2019-11-13 | St Albans | HARTLAND | 824D2 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Hartland | NC |  |  | WITHDRAWN
260 | 0 | 0 | 0 |  | 2019-11-14 | Parsonfield | HIRAM TAP | 692D1 | Solar | 0 | 0 | [10 empty] | 2020-09-11 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 03 - Kimball Rd-Lovell - 1 | Kimball Road/Lovell | 3 | 2023-04-27 |  | EXECUTED-WITHDRAWN
261 | 0 | 0 | 0 |  | 2019-11-14 | Eustis | STRATTON | 877D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Bigelow |  |  |  | WITHDRAWN
262 | 0 | 0 | 0 |  | 2019-11-18 | Jay | LIVERMORE FALLS | 428D1 | Solar | 0 | 0 | [10 empty] | 2021-03-10 | [8 empty] | Q3 2020 | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 08 - Sturtevant-Leeds-Livermore-Ludden-Riley - 1 | Livermore Falls | NC | 2021-07-15 |  | EXECUTED
263 | 0 | 0 | 0 |  | 2019-11-18 | Monmouth | MONMOUTH | 457D3 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Monmouth |  |  |  | WITHDRAWN
264 | 0 | 0 | 0 |  | 2019-11-18 | Strong | PHILLIPS/STRONG | 841D1 | Solar | 4990 | 0 |  |  |  |  | 2020-02-25 | 2020-04-29 |  |  |  |  | 2020-05-06 | [8 empty] | Q3 2021 | Fully Executed Interconnection Agreement | Yes | 2020-09-13 | Cluster 08 - Sturtevant-Leeds-Livermore-Ludden-Riley - 1 | Sturtevant | NC | 2020-08-31 |  | EXECUTED/ENERGIZED
265 | 0 | 0 | 0 |  | 2019-11-19 | Oakland | OAKLAND | 839D1 | Solar | 2375 | 0 |  |  |  |  | 2020-09-08 | 2020-11-11 |  |  |  |  | 2021-05-28 | 2022-10-13 | 2022-10-10 | [6 empty] | Q4 2020 | Fully Executed Interconnection Agreement | Yes | 2023-05-24 | Cluster 02 - Winslow-County Rd-Lakewood -1 | Winslow-County Rd | 3 | 2021-12-17 |  | EXECUTED
266 | 0 | 0 | 0 |  | 2019-11-19 | Newcastle | DAMARISCOTTA MILLS | 219D2 | Solar/Battery | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Newcastle |  |  |  | WITHDRAWN
267 | 0 | 0 | 0 |  | 2019-11-19 | Wales | MONMOUTH | 457D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Monmouth |  |  |  | WITHDRAWN
268 | 0 |  | 0 |  | 2019-11-19 | Corinna | CORINNA | 811D1 | Solar | 4950 | 0 |  |  |  |  | 2020-04-02 | 2020-06-08 |  |  |  | 2023-04-26 | 2020-07-23 | 2022-09-06 | 2022-10-18 | [6 empty] | Q4 2020 | Fully Executed Interconnection Agreement | No | 2024-10-24 | Cluster 06 - Detroit-Guilford-Belfast - 1 | Detroit | 3 | 2023-08-31 |  | RE_QUEUED_FullEx
269 | 0 | 0 | 0 |  | 2019-11-20 | Paris | NORWAY | 435D3 | Solar/Battery | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Norway |  |  |  | WITHDRAWN
270 | 0 | 0 | 0 |  | 2019-11-20 | Vassalboro | VASSALBORO | 861D8 | Solar | 3300 | 0 |  |  |  |  | 2020-01-27 | 2020-03-30 |  | 2022-07-19 |  |  | 2020-04-17 | 2022-07-11 | 2022-07-20 | 2022-10-18 | 2022-11-04 | 2023-05-01 | 2023-06-13 |  |  | Q1 2022 | Fully Executed Interconnection Agreement | Yes | 2020-09-28 | Cluster 02 - Winslow-County Rd-Lakewood -1 | Winslow-County Rd | 3 | 2021-12-17 |  | RE_QUEUED_FullEx/ENERGIZED
271 | 0 | 0 | 0 |  | 2019-11-21 | Sabattus | SABATTUS | 450D1 | Solar | 900 | 0 |  |  |  |  | 2020-01-07 | 2020-03-10 | 2020-05-01 | 2020-06-01 |  |  | 2020-06-16 | [9 empty] | Fully Executed Interconnection Agreement | Yes | 2020-08-04 | Cluster 05 - Lewiston Loop - 1 | Hotel Rd/Gulf/Middle St/Crowleys/Norway | 0 |  | Not Required | EXECUTED
272 | 0 | 0 | 0 |  | 2019-11-22 | Greenville | MONSON | 834D2 | Solar | 4250 | 0 |  |  |  |  | 2020-02-14 | 2020-04-20 |  |  |  |  | 2020-05-18 | [8 empty] | Q4 2021 | Fully Executed Interconnection Agreement | No | 2020-08-17 | Cluster 06 - Detroit-Guilford-Belfast - 1 | Guilford | 3 | 2023-08-31 |  | EXECUTED
273 | 0 | 0 | 0 |  | 2019-11-22 | Bethel | BETHEL | 403D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Woodstock |  |  |  | WITHDRAWN
274 | 0 | 0 | 0 |  | 2019-11-22 | Carmel | CARMEL | 808D2 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Detroit |  |  |  | WITHDRAWN
275 | 0 | 0 | 0 |  | 2019-11-25 | Sidney | SIDNEY | 242D1 | Solar | 2000 | 0 |  |  |  |  | 2020-02-21 | 2020-04-27 |  |  |  |  | 2020-06-18 | [8 empty] | Q4 2021 | Fully Executed Interconnection Agreement | Yes | 2020-06-06 | Cluster 01 - Augusta - 1 | Augusta E/Puddledock/Bowman St | 3 | 2021-01-04 |  | EXECUTED/ENERGIZED
276 | 0 | 0 | 0 |  | 2019-11-25 | Gorham | MOSHERS | 635D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Moshers |  |  |  | WITHDRAWN
277 | 0 | 0 | 0 |  | 2019-11-26 | China | SOUTH CHINA | 244D2 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Augusta E-Puddledock-Bowman St - TBD | Augusta E/Puddledock/Bowman St | 3 |  |  | WITHDRAWN
278 | 0 | 0 | 0 |  | 2019-11-26 | New Gloucester | HOTEL ROAD | 420D7 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Hotel Rd/Gulf/Middle St/Crowleys |  |  |  | WITHDRAWN
279 | 0 | 0 | 0 |  | 2019-11-26 | Unity | UNITY | 860D2 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Belfast |  |  |  | WITHDRAWN
280 | 0 | 0 | 0 |  | 2019-11-26 | Unity | UNITY | 860D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Belfast |  |  |  | WITHDRAWN
281 | 0 | 0 | 270 |  | 2019-11-26 | Winslow | VASSALBORO | 861D9 | Solar | 4125 | 0 |  |  |  |  | 2020-06-04 | 2020-08-07 | 2020-09-24 | 2020-11-10 |  |  | 2021-06-16 | 2022-08-10 | 2022-09-12 | 2022-11-15 | 2022-12-22 | 2023-08-04 | 2023-09-19 |  |  |  | Fully Executed Interconnection Agreement | Yes | 2022-08-17 | Cluster 02 - Winslow-County Rd-Lakewood -1 | Winslow-County Rd | 3 | 2021-12-17 |  | RE_QUEUED_FullEx
282 | 0 | 0 | 0 |  | 2019-11-26 | Harmony | ATHENS | 827D2 | Solar | 4910 | 0 |  |  |  |  | 2020-05-15 | 2020-07-15 |  |  |  |  | 2020-09-04 | [9 empty] | Fully Executed Interconnection Agreement | Yes | 2020-08-27 | Cluster 16 - Wyman Area - 1 | Athens | NC | 2020-10-05 |  | EXECUTED/ENERGIZED
283 | 0 | 0 | 0 |  | 2019-11-26 | Denmark | DENMARK | 413D2 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Kimball Road/Lovell |  |  |  | WITHDRAWN
284 | 0 | 0 | 0 |  | 2019-11-26 | Auburn | HOTEL ROAD | 420D4 | Solar/Battery | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 18 - Lewiston Loop - 2 | Hotel Rd/Gulf/Middle St/Crowleys/Norway | 3 |  |  | WITHDRAWN
285 | 0 | 0 | 0 |  | 2019-11-26 | Sanford | SOUTH SANFORD | 667D2 | Solar/Battery | 0 | 0 | [10 empty] | 2020-08-04 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 04 - Sanford-Quaker Hill - 1 | Sanford | 3 | 2022-10-19 |  | EXECUTED-WITHDRAWN
286 | 0 | 0 | 0 |  | 2019-12-02 | Winslow | WINSLOW | 870D1 | Solar/Battery | 0 | 0 | [10 empty] | 2022-03-25 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster XX - Winslow/ County Rd/ Lakewood - TBD | Winslow-County Rd | 3 |  |  | EXECUTED-WITHDRAWN
287 | 0 | 0 | 0 |  | 2019-12-02 | Oxford | NORWAY | 435D1 | Solar | 3000 | 0 |  |  |  |  | 2020-10-05 | 2020-12-10 |  |  |  |  | 2021-06-17 | 2023-01-10 | 2023-02-20 | [6 empty] | Q4 2021 | Fully Executed Interconnection Agreement | Yes | 2023-02-15 | Cluster 05 - Lewiston Loop - 1 | Hotel Rd/Gulf/Middle St/Crowleys/Norway | 3 | 2022-07-19 |  | RE_QUEUED_FullEx/ENERGIZED
288 | 0 | 0 | 0 |  | 2019-12-03 | Skowhegan | SKOWHEGAN NORTH SIDE | 853D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Winslow/ County Rd/ Lakewood - TBD | Lakewood | 3 |  |  | WITHDRAWN
289 | 0 | 0 | 0 |  | 2019-12-03 | Skowhegan | SKOWHEGAN NORTH SIDE | 853D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Winslow/ County Rd/ Lakewood - TBD | Lakewood | 3 |  |  | WITHDRAWN
290 | 0 | 0 | 0 |  | 2019-12-03 | Woolwich | WOOLWICH | 258D1 | Solar | 4999 | 0 |  |  |  |  | 2020-01-13 | 2020-03-16 |  |  |  |  | 2020-05-27 | [8 empty] | Q4 2020 | Fully Executed Interconnection Agreement | Yes | 2020-09-15 | Cluster 09 - Midcoast - 1 | Bath | 0 | 2020-07-14 |  | EXECUTED/ENERGIZED
291 | 0 | 0 | 0 |  | 2019-12-04 | Bridgton | BRIDGTON 34 KV | 406D4 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Kimball Road/Lovell |  |  |  | WITHDRAWN
292 | 0 | 0 | 0 |  | 2019-12-04 | Wells | PRATT & WHITNEY | 661D2 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Pratt & Whitney |  |  |  | WITHDRAWN
293 | 0 | 0 | 0 |  | 2019-12-12 | Berwick | BASSETT | 602D2 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Quaker Hill |  |  |  | WITHDRAWN
294 | 0 | 0 | 0 |  | 2019-12-12 | Leeds | LEEDS | 471D2 | Solar/Battery | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Leeds |  |  |  | WITHDRAWN
295 | 0 | 0 | 0 |  | 2019-12-20 | Waterford | PAPOOSE POND | 438D1 | Solar/Battery | 0 | 0 | [10 empty] | 2020-05-14 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 03 - Kimball Rd-Lovell - 1 | Kimball Road/Lovell | 3 |  | 2023-04-22 | EXECUTED-WITHDRAWN
296 | 0 | 0 | 0 |  | 2019-12-20 | Mechanic Falls | MECHANIC FALLS | 431D2 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Hotel Rd/Gulf/Middle St/Crowleys/Norway |  |  |  | WITHDRAWN
297 | 0 | 0 | 0 |  | 2019-12-20 | Waterboro | WATERBORO | 671D1 | Solar | 4875 | 0 |  |  |  |  | 2020-01-10 | 2020-03-17 |  |  |  |  | 2020-04-22 | [8 empty] | Q4 2021 | Fully Executed Interconnection Agreement | Yes | 2020-07-14 | Cluster 04 - Sanford-Quaker Hill - 1 | Waterboro | 0 | 2020-06-25 |  | EXECUTED/ENERGIZED
298 | 0 | 0 | 0 |  | 2019-12-20 | Norridgewock | SKOWHEGAN SOUTH SIDE | 854D1 | Solar | 4999 | 0 |  |  |  |  | 2020-03-02 | 2020-04-02 |  |  |  |  | 2020-05-14 | [8 empty] | Q4 2021 | Fully Executed Interconnection Agreement | Yes | 2021-10-21 | Cluster 02 - Winslow-County Rd-Lakewood -1 | Lakewood | 3 | 2021-12-17 |  | EXECUTED
299 | 0 | 0 | 0 |  | 2020-01-07 | Auburn | HOTEL ROAD | 420D4 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 18 - Lewiston Loop - 2 | Hotel Rd/Gulf/Middle St/Crowleys/Norway | 3 |  |  | WITHDRAWN
300 | 0 | 0 | 0 |  | 2020-01-07 | Palmyra | DETROIT | 812D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Detroit |  |  |  | WITHDRAWN
301 | 0 | 0 | 0 |  | 2020-01-07 | Chelsea | CONY ROAD | 216D2 | Solar | 4999 | 0 |  |  |  |  | 2020-03-02 | 2020-05-05 |  |  |  |  | 2020-05-12 | [8 empty] | Q3 2021 | Fully Executed Interconnection Agreement | Yes | 2020-09-13 | Cluster 01 - Augusta - 1 | Augusta E/Puddledock/Bowman St | 3 | 2021-01-04 |  | EXECUTED/ENERGIZED
302 | 0 | 0 | 0 |  | 2020-01-07 | Poland | MECHANIC FALLS | 431D3 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Norway |  |  |  | WITHDRAWN
303 | 0 | 0 | 0 |  | 2020-01-09 | Kingfield | STURTEVANT | 858D2 | Solar | 0 | 0 | [10 empty] | 2021-12-23 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster XX - Sturtevant/ Leeds/ Livermore/ Ludden/ Riley_TBD | Sturtevant | 3 |  |  | EXECUTED-WITHDRAWN
304 | 0 | 0 | 0 |  | 2020-01-09 | New Portland | STURTEVANT | 858D2 | Solar | 0 | 0 | [10 empty] | 2022-06-28 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster XX - Sturtevant/ Leeds/ Livermore/ Ludden/ Riley_TBD | Sturtevant | 3 |  | Not Required | RE_QUEUED_FullEx
305 | 0 | 0 | 0 |  | 2020-01-09 | Rangeley | RANGELEY | 875D2 | Solar | 3000 | 0 |  |  |  |  | 2020-04-09 | 2020-06-10 | 2021-03-05 |  |  |  | 2020-08-04 | [8 empty] | Q4 2021 | Fully Executed Interconnection Agreement | Yes | 2022-04-14 | Cluster 10 - Roxbury-Rumford-Woodstock - 1 | Roxbury | 0 | 2020-08-31 |  | EXECUTED
306 | 0 | 0 | 0 |  | 2020-01-09 | Corinna | CORINNA | 811D1 | Solar | 0 | 0 | [10 empty] | 2021-07-14 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 06 - Detroit-Guilford-Belfast - 1 | Detroit | 3 | 2023-08-31 |  | RE_QUEUED_FullEx
307 | 0 | 0 | 0 |  | 2020-01-10 | Livermore Falls | LIVERMORE FALLS | 428D2 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 08 - Sturtevant-Leeds-Livermore-Ludden-Riley - 1 | Livermore Falls | 3 |  | 2023-12-15 | WITHDRAWN
308 | 0 | 1 - DEXT | 0 | RQP-1 | 2020-01-15 | Dexter | DEXTER | 813D1 | Solar | 995 | 0 | 2020-09-09 | 2020-11-11 | 2020-12-08 | 2021-01-22 | [6 empty] | 2021-08-30 |  |  | 2024-11-22 | 2025-01-29 | 2025-08-20 |  |  |  | Q1 2025 | Fully Executed Interconnection Agreement | No | 2024-06-04 | Cluster 06 - Detroit-Guilford-Belfast - 1 | Guilford | 3 | 2023-08-31 |  | RE_QUEUED_FullEx
309 | 0 | 0 | 0 |  | 2020-01-15 | Dexter | DEXTER | 813D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 17 - Detroit Guilford Belfast - 2 | Guilford | 3 |  |  | WITHDRAWN
310 | 0 | 0 | 0 |  | 2020-01-17 | Winthrop | WINTHROP | 256D3 | Solar | 0 | 0 | [10 empty] | 2021-06-15 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 11 - Augusta E-Puddledock-Bowman St - 2 | Augusta E/Puddledock/Bowman St | 3 | 2024-05-28 |  | EXECUTED-WITHDRAWN
311 | 0 | 0 | 0 |  | 2020-01-17 | Whitefield | COOPERS MILLS ROAD | 230D2 | Solar | 990 | 0 |  |  |  |  | 2020-05-15 | 2020-07-20 | 2020-08-28 | 2020-10-09 |  |  | 2020-12-01 | [9 empty] | Fully Executed Interconnection Agreement | Yes | 2021-02-16 | Cluster 09 - Midcoast - 1 | Coopers Mills | NC |  | Not Required | EXECUTED/ENERGIZED
312 | 0 | 0 | 0 |  | 2020-01-17 | Naples | NAPLES TAP | 469D1 | Solar | 0 | 0 | [10 empty] | 2020-08-26 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 07 - Raymond - 1 | Raymond | 3 | 2023-12-21 |  | EXECUTED
313 | 0 | 0 | 0 |  | 2020-01-17 | Starks | ANSON | 801D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Winslow/ County Rd/ Lakewood - TBD | Lakewood |  |  |  | WITHDRAWN
314 | 0 | 0 | 0 |  | 2020-01-21 | Augusta | BLAIR ROAD | 207D2 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 01 - Augusta - 1 | Augusta E/Puddledock/Bowman St | 3 |  | 2022-03-21 | WITHDRAWN
315 | 0 | 0 | 0 |  | 2020-01-21 | Poland | MECHANIC FALLS | 431D3 | Solar/Battery | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 05 - Lewiston Loop - 1 | Hotel Rd/Gulf/Middle St/Crowleys/Norway | 3 |  | 2022-07-22 | WITHDRAWN
316 | 0 | 0 | 0 |  | 2020-01-21 | Augusta | NORTH AUGUSTA | 272D4 | Solar | 999 | 0 |  |  |  |  | 2020-07-27 | 2020-09-29 |  |  |  |  | 2020-11-03 | [9 empty] | Fully Executed Interconnection Agreement | Yes | 2021-07-01 | Cluster 11 - Augusta E-Puddledock-Bowman St - 2 | North Augusta | NC |  | Not Required | EXECUTED/ENERGIZED
317 | 0 | 0 | 0 |  | 2020-01-24 | Norway | NORWAY | 435D3 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Norway | 0 |  |  | WITHDRAWN
318 | 0 | 0 | 0 |  | 2020-01-24 | Monson | MONSON | 834D1 | Solar | 999 | 0 |  |  |  |  | 2020-06-10 | 2020-08-13 |  |  |  |  | 2020-10-05 | 2023-08-02 | 2023-09-18 | [6 empty] | Q3 2025 | Fully Executed Interconnection Agreement | No | 2024-02-13 | Cluster 06 - Detroit-Guilford-Belfast - 1 | Guilford | 3 |  | Not Required | RE_QUEUED_FullEx
319 | 0 | 0 | 0 |  | 2020-01-24 | Windham | RAYMOND 34 KV | 444D3 | Solar | 0 | 0 | [10 empty] | 2020-10-27 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 07 - Raymond - 1 | Raymond | 3 | 2023-12-21 |  | EXECUTED-WITHDRAWN
320 | 0 | 0 | 0 |  | 2020-01-24 | Kittery | BRAGDON COMMONS | 689D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Quaker Hill |  |  |  | WITHDRAWN
321 | 0 | 0 | 0 |  | 2020-01-24 | Waterboro | WATERBORO | 671D2 | Solar | 4998 | 0 |  |  |  |  | 2020-05-22 | 2020-07-28 |  |  |  |  | 2020-09-04 | [9 empty] | Fully Executed Interconnection Agreement | Yes | 2021-01-20 | Cluster 04 - Sanford-Quaker Hill - 1 | Waterboro | NC | 2020-10-05 |  | EXECUTED/ENERGIZED
322 | 0 | 0 | 0 |  | 2020-01-24 | Mercer | SKOWHEGAN TAP | 864D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Winslow/ County Rd/ Lakewood - TBD | Lakewood | 3 |  |  | WITHDRAWN
323 | 0 | 0 | 0 |  | 2020-01-24 | Hartland | HARTLAND | 824D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Hartland | NC |  |  | WITHDRAWN
324 | 0 | 0 | 0 |  | 2020-01-24 | Union | UNION | 251D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Coopers Mills |  |  |  | WITHDRAWN
325 | 0 | 0 | 0 |  | 2020-01-27 | Lewiston | DEER RIPS | 412D4 | Solar | 0 | 0 | [10 empty] | 2021-02-16 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 05 - Lewiston Loop - 1 | Hotel Rd/Gulf/Middle St/Crowleys/Norway | 3 | 2022-07-19 |  | EXECUTED-WITHDRAWN
326 | 0 | 0 | 0 |  | 2020-01-27 | Limington | NORTH LIMINGTON | 638D1 | Solar | 0 | 0 | [10 empty] | 2020-11-05 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 03 - Kimball Rd-Lovell - 1 | Kimball Road/Lovell | 3 | 2023-04-27 |  | Decision due 9/4
327 | 0 | 0 | 0 |  | 2020-01-27 | Gorham | SPRING STREET | 668D5 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Spring St |  |  |  | WITHDRAWN
328 | 0 | 0 | 0 |  | 2020-01-27 | Sanford | SANFORD INDUSTRIAL PARK | 656D3 | Solar | 4998 | 0 |  |  |  |  | 2020-06-23 | 2020-08-25 |  |  |  |  | 2020-09-29 | [9 empty] | Fully Executed Interconnection Agreement | Yes | 2021-07-16 | Cluster 04 - Sanford-Quaker Hill - 1 | Sanford | 3 | 2022-06-27 |  | EXECUTED/ENERGIZED
329 | 0 | 0 | 0 |  | 2020-01-27 | Auburn | DEER RIPS | 412D1 | Solar | 0 | 0 | [10 empty] | 2021-08-17 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 18 - Lewiston Loop - 2 | Hotel Rd/Gulf/Middle St/Crowleys/Norway | 3 |  |  | EXECUTED-WITHDRAWN
330 | 0 | 0 | 0 |  | 2020-01-27 | South Berwick | BASSETT | 602D3 | Solar | 4000 | 0 |  |  |  |  | 2020-06-09 | 2020-08-12 |  |  |  |  | 2020-09-11 | [9 empty] | Fully Executed Interconnection Agreement | Yes | 2020-10-21 | Cluster 04 - Sanford-Quaker Hill - 1 | Quaker Hill | NC | 2021-03-30 |  | EXECUTED/ENERGIZED
331 | 0 | 0 | 0 |  | 2020-01-28 | Skowhegan | WESTON HYDRO | 866D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Lakewood | NA |  |  | WITHDRAWN
332 | 0 | 0 | 0 |  | 2020-01-28 | Anson | NORTH ANSON | 838D2 | Solar | 4000 | 0 |  |  |  |  | 2020-07-06 | 2020-09-08 |  |  |  |  | 2020-10-19 | [8 empty] | Q2 2021 | Fully Executed Interconnection Agreement | Yes | 2022-03-09 | Cluster 02 - Winslow-County Rd-Lakewood -1 | Lakewood | 3 | 2021-12-17 |  | EXECUTED
333 | 0 | 0 | 0 |  | 2020-01-28 | Old Orchard Beach | GOOSEFARE | 630D4 | Solar | 4700 | 0 |  |  |  |  | 2020-05-05 | 2020-07-09 |  |  |  |  | 2020-07-16 | [8 empty] | Q3 2021 | Fully Executed Interconnection Agreement | Yes | 2020-08-04 | Cluster 14 - Louden-Biddeford IP - 1 | Louden | NC | 2021-03-30 |  | EXECUTED/ENERGIZED
334 | 0 | 0 | 0 |  | 2020-01-28 | Winslow | VASSALBORO | 861D9 | Solar | 0 | 0 | [10 empty] | 2021-10-26 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 12 - Winslow-County Rd-Lakewood - 2 | Winslow-County Rd | 3 | 2024-05-28 |  | EXECUTED-WITHDRAWN
335 | 0 | 0 | 0 |  | 2020-01-30 | Mercer | SKOWHEGAN TAP | 864D1 | Solar/Battery | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Winslow/ County Rd/ Lakewood - TBD | Lakewood | 3 |  |  | WITHDRAWN
336 | 0 | 0 | 0 |  | 2020-01-30 | Vassalboro | MCCOYS | 237D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Augusta E/Puddledock/Bowman St |  |  |  | WITHDRAWN
337 | 0 | 0 | 0 |  | 2020-01-30 | Vassalboro | MCCOYS | 237D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Augusta E/Puddledock/Bowman St |  |  |  | WITHDRAWN
338 | 0 | 0 | 0 |  | 2020-01-31 | Sandy River Plantation | SADDLEBACK | 876D1 | Solar | 4890 | 0 |  |  |  |  | 2020-04-23 | 2020-06-25 |  |  |  |  | 2020-09-16 | [8 empty] | Q4 2020 | Fully Executed Interconnection Agreement | Yes | 2020-09-25 | Cluster 10 - Roxbury-Rumford-Woodstock - 1 | Roxbury | NC | 2020-08-31 |  | EXECUTED/ENERGIZED
339 | 0 | 0 | 0 |  | 2020-02-03 | Dover-Foxcroft | DOVER | 815D2 | Solar | 0 | 0 | [10 empty] | 2020-09-02 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 06 - Detroit-Guilford-Belfast - 1 | Guilford | 3 | 2023-08-31 |  | EXECUTED
340 | 0 | 0 | 0 |  | 2020-02-03 | Farmington | STURTEVANT | 858D4 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Sturtevant/ Leeds/ Livermore/ Ludden/ Riley_TBD | Sturtevant | 3 |  |  | WITHDRAWN
341 | 0 | 0 | 0 |  | 2020-02-03 | Limington | NORTH LIMINGTON | 638D2 | Solar | 996 | 0 |  |  |  |  | 2020-12-14 | 2021-02-19 |  |  |  |  | 2021-05-26 | 2024-05-21 | 2024-07-26 | 2024-11-01 | 2025-01-29 |  |  |  |  | Q2 2025 | Fully Executed Interconnection Agreement | No | 2023-08-31 | Cluster 03 - Kimball Rd-Lovell - 1 | Kimball Road/Lovell | 3 | 2023-04-27 |  | RE_QUEUED_STUDY
342 | 0 | 0 | 0 |  | 2020-02-03 | Waterboro | WATERBORO | 671D2 | Solar | 4998 | 0 |  |  |  |  | 2020-10-23 | 2020-12-30 |  |  |  |  | 2021-06-14 | [9 empty] | Fully Executed Interconnection Agreement | Yes | 2022-04-07 | Cluster 04 - Sanford-Quaker Hill - 1 | Waterboro | 3 | 2022-06-27 |  | EXECUTED
343 | 0 | 0 | 0 |  | 2020-02-05 | Bristol | BRISTOL | 210D2 | Solar | 4899 | 0 |  |  |  |  | 2020-03-06 | 2020-05-11 |  |  |  |  | 2020-05-21 | [8 empty] | Q4 2021 | Fully Executed Interconnection Agreement | Yes | 2020-10-05 | Cluster 09 - Midcoast - 1 | Newcastle | NC | 2020-07-30 |  | EXECUTED/ENERGIZED
344 | 0 | 0 | 0 |  | 2020-02-05 | Embden | EMBDEN | 868D1 | Solar | 4999 | 0 |  |  |  |  | 2020-03-25 | 2020-05-29 |  |  |  |  | 2020-06-01 | [8 empty] | Q4 2021 | Fully Executed Interconnection Agreement | Yes | 2020-10-16 | Cluster 16 - Wyman Area - 1 | Embden | 0 | 2020-07-30 |  | EXECUTED/ENERGIZED
345 | 0 | 0 | 0 |  | 2020-02-05 | Orland | BUCKSPORT | 806D2 | Solar/Battery | 0 | 0 | [10 empty] | 2020-07-24 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 06 - Detroit-Guilford-Belfast - 1 | Bucksport | NC | 2020-10-05 |  | EXECUTED-WITHDRAWN
346 | 0 | 0 | 0 |  | 2020-02-06 | Winslow | VASSALBORO | 861D9 | Solar/Battery | 0 | 0 | [10 empty] | 2021-12-21 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster XX - Winslow/ County Rd/ Lakewood - TBD | Winslow-County Rd | 3 |  |  | EXECUTED-WITHDRAWN
347 | 0 | 0 | 0 |  | 2020-02-07 | Oxford | OXFORD | 437D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Norway |  |  |  | WITHDRAWN
348 | 0 | 0 | 0 |  | 2020-02-07 | Winthrop | WINTHROP | 256D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Augusta E-Puddledock-Bowman St - TBD | Augusta E/Puddledock/Bowman St |  |  |  | WITHDRAWN
349 | 0 | 0 | 0 |  | 2020-02-07 | Limerick | LIMERICK | 632D1 | Solar | 4998 | 0 |  |  |  |  | 2020-06-09 | 2020-08-11 |  |  |  |  | 2020-09-04 | [8 empty] | Q2 2021 | Fully Executed Interconnection Agreement | No | 2022-04-25 | Cluster 03 - Kimball Rd-Lovell - 1 | Kimball Road/Lovell | 3 | 2023-04-27 |  | EXECUTED
350 | 0 | 0 | 0 |  | 2020-02-12 | Winthrop | MANCHESTER | 233D2 | Solar | 995 | 0 |  |  |  |  | 2020-12-18 | 2021-06-11 | 2024-06-06 | 2024-07-24 |  | 2024-07-19 | 2021-11-24 | 2023-01-26 |  | 2023-06-14 | 2023-07-20 | 2023-10-27 | 2023-12-13 | 2024-02-14 | 2024-04-19 | Q4 2025 | Fully Executed Interconnection Agreement | No | 2024-11-18 | Cluster 11 - Augusta E-Puddledock-Bowman St - 2 | Augusta E/Puddledock/Bowman St | 3 | 2024-05-28 | Not Required | RE_QUEUED_RESULTS
351 | 0 | 0 | 0 |  | 2020-02-14 | Augusta | NORTH AUGUSTA | 272D4 | Solar | 0 | 0 | [10 empty] | 2021-07-01 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 11 - Augusta E-Puddledock-Bowman St - 2 | North Augusta | 3 | 2024-05-28 |  | EXECUTED
352 | 0 | 0 | 0 |  | 2020-02-14 | Windsor | COOPERS MILLS ROAD | 230D1 | Solar | 0 | 0 | [10 empty] | 2021-07-01 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 09 - Midcoast - 1 | Coopers Mills | 3 | 2023-12-21 |  | EXECUTED-WITHDRAWN
353 | 0 | 0 | 0 |  | 2020-02-14 | Sidney | SIDNEY | 242D1 | Solar | 1500 | 0 |  |  |  |  | 2020-07-06 | 2020-09-08 |  |  |  |  | 2020-12-08 | [8 empty] | Q1 2021 | Fully Executed Interconnection Agreement | Yes | 2022-04-01 | Cluster 01 - Augusta - 1 | Augusta E/Puddledock/Bowman St | 3 | 2021-01-04 |  | EXECUTED/ENERGIZED
354 | 0 | 0 | 0 |  | 2020-02-19 | Casco | RAYMOND 115 KV | 445D2 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Raymond |  |  |  | WITHDRAWN
355 | 0 | 0 | 0 |  | 2020-02-19 | Belfast | BELFAST 115 | 874D1 | Solar | 4999 | 0 |  |  |  |  | 2020-04-17 | 2020-06-19 |  |  |  |  | 2020-07-15 | 2022-08-23 | 2022-10-05 | [6 empty] | Q4 2021 | Fully Executed Interconnection Agreement | Yes | 2022-12-09 | Cluster 06 - Detroit-Guilford-Belfast - 1 | Belfast | 3 | 2023-05-31 |  | RE_QUEUED_FullEx
356 | 0 | 0 | 0 |  | 2020-02-19 | Farmington | STURTEVANT | 858D4 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Sturtevant/ Leeds/ Livermore/ Ludden/ Riley_TBD | Sturtevant | 3 |  |  | WITHDRAWN
357 | 0 | 0 | 0 |  | 2020-02-20 | Cumberland | ELM STREET | 620D1 | Solar/Battery | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Elm St |  |  |  | WITHDRAWN
358 | 0 | 0 | 0 |  | 2020-02-21 | Belfast | BELFAST WEST SIDE | 803D3 | Solar | 3500 | 0 |  |  |  |  | 2020-06-09 | 2020-08-12 | 2020-09-24 | 2020-11-09 |  |  | 2020-11-14 | [8 empty] | Q4 2020 | Fully Executed Interconnection Agreement | Yes | 2022-12-07 | Cluster 06 - Detroit-Guilford-Belfast - 1 | Belfast | 3 | 2023-05-31 |  | EXECUTED
359 | 0 | 0 | 0 |  | 2020-02-21 | Damariscotta | DAMARISCOTTA MILLS | 219D1 | Solar | 0 | 0 | [10 empty] | 2020-11-12 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 09 - Midcoast - 1 | Newcastle | 3 | 2023-12-21 |  | RE_QUEUED_FullEx
360 | 0 | 0 | 0 |  | 2020-02-24 | Waterville | SOUTH WATERVILLE | 855D2 | Solar | 3500 | [5 empty] | 2020-07-24 | 2020-09-28 |  |  |  |  | 2020-10-20 | [9 empty] | Fully Executed Interconnection Agreement | Yes | 2022-06-10 | Cluster 02 - Winslow-County Rd-Lakewood -1 | Winslow-County Rd | 3 | 2021-12-17 |  | EXECUTED/ENERGIZED
361 | 0 | 0 | 0 |  | 2020-02-24 | South Berwick | BASSETT | 602D3 | Solar/Battery | 0 | 0 | [10 empty] | 2021-02-18 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 04 - Sanford-Quaker Hill - 1 | Quaker Hill | 3 | 2022-06-27 |  | EXECUTED-WITHDRAWN
362 | 0 | 0 | 0 |  | 2020-02-25 | Waterboro | WATERBORO | 671D2 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Waterboro |  |  |  | WITHDRAWN
363 | 0 | 0 | 0 |  | 2020-02-25 | Windsor | COOPERS MILLS ROAD | 230D1 | Solar | 0 | 0 | [10 empty] | 2021-12-13 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster XX - Midcoast - TBD | Coopers Mills | 3 |  |  | EXECUTED-WITHDRAWN
364 | 0 | 0 | 0 |  | 2020-02-25 | Buxton | BONNY EAGLE | 610D2 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Kimball Rd/ Lovell - TBD | Kimball Road/Lovell | 3 |  |  | WITHDRAWN
365 | 0 | 0 | 0 |  | 2020-02-25 | Bethel | LOCKES MILLS | 429D1 | Solar | 2997 | 0 |  |  |  |  | 2020-04-15 | 2020-06-19 |  |  |  |  | 2020-07-01 | [8 empty] | Q4 2021 | Fully Executed Interconnection Agreement | Yes | 2020-08-25 | Cluster 10 - Roxbury-Rumford-Woodstock - 1 | Woodstock | NC | 2020-08-31 |  | EXECUTED/ENERGIZED
366 | 0 | 0 | 0 |  | 2020-02-28 | Edgecomb | EDGECOMB | 223D1 | Solar | 4950 | 0 |  |  |  |  | 2020-04-14 | 2020-06-18 |  |  |  |  | 2020-07-21 | [9 empty] | Fully Executed Interconnection Agreement | Yes | 2020-10-19 | Cluster 09 - Midcoast - 1 | Newcastle | NC | 2020-08-31 |  | EXECUTED/ENERGIZED
367 | 0 | 0 | 0 |  | 2020-02-28 | Belfast | BELFAST 115 | 874D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Belfast |  |  |  | WITHDRAWN
368 | 0 | 0 | 0 |  | 2020-02-28 | Belfast | BELFAST WEST SIDE | 803D6 | Solar | 2475 | 0 |  |  |  |  | 2021-01-15 | 2021-06-28 |  |  |  |  | 2021-07-07 | [8 empty] | Q3 2022 | Fully Executed Interconnection Agreement | Yes | 2022-11-29 | Cluster 06 - Detroit-Guilford-Belfast - 1 | Belfast | 3 | 2023-05-31 |  | EXECUTED
369 | 0 | 0 | 0 |  | 2020-02-28 | Belfast | BELFAST WEST SIDE | 803D6 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 17 - Detroit Guilford Belfast - 2 | Belfast | 3 |  |  | WITHDRAWN
370 | 0 | 0 | 0 |  | 2020-02-28 | Mechanic Falls | MECHANIC FALLS | 431D2 | Solar | 0 | 0 | [10 empty] | 2021-10-12 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 18 - Lewiston Loop - 2 | Hotel Rd/Gulf/Middle St/Crowleys/Norway | 3 |  |  | EXECUTED-WITHDRAWN
371 | 0 | 0 | 0 |  | 2020-02-28 | Vassalboro | VASSALBORO | 861D9 | Solar | 0 | 0 |  |  |  |  | 2022-02-14 | 2022-04-22 | 2022-05-31 | [13 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Winslow/ County Rd/ Lakewood - TBD | Winslow-County Rd | 3 |  |  | WITHDRAWN
372 | 0 | 0 | 0 |  | 2020-02-28 | Berwick | BERWICK | 603D2 | Solar | 1750 | 0 |  |  |  |  | 2020-04-13 | 2020-06-16 |  |  |  |  | 2020-07-16 | [8 empty] | Q4 2020 | Fully Executed Interconnection Agreement | Yes | 2020-11-30 | Cluster 04 - Sanford-Quaker Hill - 1 | Quaker Hill | NC | 2020-08-31 |  | EXECUTED/ENERGIZED
373 | 0 | 0 | 0 |  | 2020-02-28 | Livermore Falls | LIVERMORE FALLS | 428D3 | Solar | 0 | 0 | [10 empty] | 2021-12-27 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster XX - Sturtevant/ Leeds/ Livermore/ Ludden/ Riley_TBD | Livermore Falls | 3 |  |  | WITHDRAWN
374 | 0 | 0 | 0 |  | 2020-03-04 | Springvale | BUTLER'S CORNER | 612D1 | Solar | 0 | 0 | [10 empty] | 2020-10-06 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 04 - Sanford-Quaker Hill - 1 | Sanford | 3 | 2022-06-27 |  | EXECUTED-WITHDRAWN
375 | 0 | 0 | 0 |  | 2020-03-04 | Hampden | BANGOR HYDRO (Versant) | 120D1 | Solar | 0 | 0 | [10 empty] | 2023-01-03 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | N/A | Emera Transmission |  | 2024-03-21 |  | EXECUTED
376 | 0 | 0 | 0 |  | 2020-03-04 | Brunswick | BRUNSWICK WEST SIDE | 213D1 | Solar | 4999 | 0 |  |  |  |  | 2020-05-15 | 2020-07-21 |  |  |  |  | 2020-08-20 | [9 empty] | Fully Executed Interconnection Agreement | Yes | 2020-09-01 | Cluster 09 - Midcoast - 1 | Topsham | NC | 2020-10-05 |  | EXECUTED/ENERGIZED
377 | 0 | 0 | 0 |  | 2020-03-06 | Pittston | BOWMAN STREET | 263D1 | Solar | 4950 | 0 |  |  |  |  | 2020-04-23 | 2020-06-25 |  |  |  |  | 2020-09-29 | [8 empty] | Q3 2021 | Fully Executed Interconnection Agreement | Yes | 2021-03-31 | Cluster 01 - Augusta - 1 | Augusta E/Puddledock/Bowman St | 3 | 2021-01-04 |  | RE_QUEUED_FullEx/ENERGIZED
378 | 0 | 0 | 0 |  | 2020-03-06 | Biddeford | BIDDEFORD INDUSTRIAL PARK | 673D2 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Biddeford IP | NC |  |  | WITHDRAWN
379 | 0 | 0 | 0 |  | 2020-03-06 | Arundel | MAY STREET | 634D1 | Solar/Battery | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Biddeford IP |  |  |  | WITHDRAWN
380 | 0 | 0 | 0 |  | 2020-03-06 | Lewiston | CROWLEYS | 411D2 | Solar | 4999 | 0 |  |  |  |  | 2020-07-24 | 2020-09-28 |  |  |  |  | 2020-10-19 | [8 empty] | Q4 2021 | Fully Executed Interconnection Agreement | Yes | 2022-08-01 | Cluster 05 - Lewiston Loop - 1 | Hotel Rd/Gulf/Middle St/Crowleys/Norway | 3 | 2022-07-19 |  | EXECUTED
381 | 0 | 0 | 0 |  | 2020-03-10 | Belfast | BELFAST WEST SIDE | 803D6 | Solar | 0 | 0 | [10 empty] | 2022-05-10 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 17 - Detroit Guilford Belfast - 2 | Belfast | 3 |  |  | EXECUTED-WITHDRAWN
382 | 0 | 0 | 0 |  | 2020-03-10 | Gray | GRAY | 416D3 | Solar/Battery | 0 | 0 | [10 empty] | 2020-10-16 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 15 - Greater Portland - 1 | Elm St | NC | 2020-11-20 |  | EXECUTED-WITHDRAWN
383 | 0 | 0 | 0 |  | 2020-03-10 | Woodstock | BRYANT POND | 407D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Woodstock |  |  |  | WITHDRAWN
384 | 0 | 0 | 0 |  | 2020-03-10 | Acton | BUTLER'S CORNER | 612D2 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 04 - Sanford-Quaker Hill - 1 | Sanford | 3 |  | 2022-06-22 | WITHDRAWN
385 | 0 | 0 | 0 |  | 2020-03-10 | Gray | GRAY | 416D1 | Solar | 4999 | 0 |  |  |  |  | 2020-10-19 | 2020-12-23 |  |  |  |  | 2021-04-29 | [8 empty] | Q3 2021 | Fully Executed Interconnection Agreement | Yes | 2021-10-18 | Cluster 15 - Greater Portland - 1 | Elm St | NC | 2021-04-16 |  | RE_QUEUED_FullEx
386 | 0 | 0 | 0 |  | 2020-03-13 | Skowhegan | SKOWHEGAN SOUTH SIDE | 854D1 | Solar | 3199 | 0 |  |  |  |  | 2020-06-16 | 2020-08-18 |  |  |  |  | 2020-09-11 | [8 empty] | Q2 2022 | Fully Executed Interconnection Agreement | Yes | 2020-10-22 | Cluster 02 - Winslow-County Rd-Lakewood -1 | Lakewood | 3 | 2021-12-17 |  | EXECUTED/ENERGIZED
387 | 0 | 0 | 0 |  | 2020-03-13 | Augusta | NORTH AUGUSTA | 272D3 | Solar | 996 | 0 |  |  |  |  | 2021-09-15 | 2021-11-12 | 2021-12-10 | 2022-01-20 |  |  | 2022-01-28 | [8 empty] | Q3 2021 | Fully Executed Interconnection Agreement | Yes | 2022-09-09 | Cluster XX - Augusta E-Puddledock-Bowman St - TBD | North Augusta | 3 |  | Not Required | EXECUTED/ENERGIZED
388 | 0 | 0 | 0 |  | 2020-03-13 | Augusta | BOND BROOK | 208D1 | Solar | 4875 | 0 |  |  |  |  | 2020-04-15 | 2020-06-16 |  |  |  |  | 2020-08-24 | 2024-01-09 | 2024-03-05 | [7 empty] | Fully Executed Interconnection Agreement | Yes | 2022-11-04 | Cluster 01 - Augusta - 1 | Augusta E/Puddledock/Bowman St | 3 | 2021-01-04 |  | RE_QUEUED_FullEx
389 | 0 | 0 | 0 |  | 2020-03-20 | Manchester | PUDDLEDOCK ROAD | 262D1 | Solar | 0 | 0 |  |  |  |  | 2021-04-02 | 2021-07-06 | 2024-07-26 | 2024-09-09 |  |  | 2021-10-13 | 2024-04-15 | 2024-06-07 | [7 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 11 - Augusta E-Puddledock-Bowman St - 2 | Augusta E/Puddledock/Bowman St | 3 | 2024-05-28 |  | RE_QUEUED_RESTUDY
390 | 0 | 0 | 345 |  | 2020-03-20 | Bucksport | BUCKSPORT | 806D2 | Solar | 4980 | 0 |  |  |  |  | 2020-09-11 | 2020-11-17 |  |  |  |  | 2020-12-03 | 2022-08-30 | 2022-10-12 | 2022-12-07 | 2023-01-18 | [5 empty] | Fully Executed Interconnection Agreement | Yes | 2022-11-07 | Cluster 06 - Detroit-Guilford-Belfast - 1 | Bucksport | 3 | 2023-05-31 |  | RE_QUEUED_FullEx/ENERGIZED
391 | 0 | 0 | 0 |  | 2020-03-20 | Augusta | CAPITOL STREET | 215D2 | Solar | 500 | 0 |  |  |  |  | 2020-04-17 | 2020-06-16 |  |  |  |  | 2020-08-24 | [9 empty] | Fully Executed Interconnection Agreement | Yes | 2022-03-07 | Cluster 11 - Augusta E-Puddledock-Bowman St - 2 | Augusta E/Puddledock/Bowman St | 0 |  | Not Required | EXECUTED/ENERGIZED
392 | 0 | 0 | 0 |  | 2020-03-20 | Augusta | CAPITOL STREET | 215D3 | Solar | 1703 | 0 |  |  |  |  | 2020-04-17 | 2020-06-16 |  |  |  |  | 2020-08-24 | [9 empty] | Fully Executed Interconnection Agreement | Yes | 2022-03-07 | Cluster 01 - Augusta - 1 | Augusta E/Puddledock/Bowman St | 3 | 2021-01-04 |  | EXECUTED/ENERGIZED
393 | 0 | 0 | 0 |  | 2020-03-20 | Belmont | BELFAST WEST SIDE | 803D6 | Solar | 0 | 0 | [10 empty] | 2023-04-04 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 17 - Detroit Guilford Belfast - 2 | Belfast | 3 |  | Not Required | EXECUTED-WITHDRAWN
394 | 0 | 0 | 0 |  | 2020-03-20 | Lewiston | CROWLEYS | 411D1 | Solar | 0 | 0 | [10 empty] | 2021-02-18 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 05 - Lewiston Loop - 1 | Hotel Rd/Gulf/Middle St/Crowleys/Norway | 3 |  | Not Required | EXECUTED-WITHDRAWN
395 | 0 | 0 | 0 |  | 2020-03-20 | Prospect | PROSPECT | 846D1 | Solar | 0 | 0 | [10 empty] | 2020-08-04 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 06 - Detroit-Guilford-Belfast - 1 | Belfast | 3 |  | 2023-08-23 | EXECUTED-WITHDRAWN
396 | 0 | 0 | 0 |  | 2020-03-20 | Searsmont | BELFAST WEST SIDE | 803D6 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 17 - Detroit Guilford Belfast - 2 | Belfast | 3 |  |  | WITHDRAWN
397 | 0 | 0 | 0 |  | 2020-03-20 | Searsmont | BELFAST WEST SIDE | 803D6 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 17 - Detroit Guilford Belfast - 2 | Belfast | 3 |  |  | WITHDRAWN
398 | 0 | 0 | 0 |  | 2020-03-20 | Searsmont | BELFAST WEST SIDE | 803D6 | Solar | 0 | 0 | [10 empty] | 2023-08-21 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 17 - Detroit Guilford Belfast - 2 | Belfast | 3 |  | Not Required | EXECUTED-WITHDRAWN
399 | 0 | 0 | 0 |  | 2020-03-20 | Stockton Springs | SEARSPORT | 850D1 | Solar | 0 | 0 | [10 empty] | 2020-09-23 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 06 - Detroit-Guilford-Belfast - 1 | Belfast | 3 | 2023-08-31 |  | EXECUTED-WITHDRAWN
400 | 0 | 0 | 0 |  | 2020-03-20 | Prospect | PROSPECT | 846D1 | Solar | 4999 | 0 |  |  |  |  | 2020-04-24 | 2020-06-26 | 2021-07-20 | 2021-08-30 |  |  | 2020-08-04 | [9 empty] | Fully Executed Interconnection Agreement | Yes | 2020-12-09 | Cluster 06 - Detroit-Guilford-Belfast - 1 | Belfast | 3 | 2023-05-31 |  | EXECUTED
401 | 0 | 0 | 0 |  | 2020-03-20 | Carrabassett Valley | BIGELOW | 882D1 | Solar | 4995 | 0 |  |  |  |  | 2020-05-05 | 2020-07-09 |  |  |  |  | 2020-08-20 | [9 empty] | Fully Executed Interconnection Agreement | Yes | 2020-09-11 | Cluster 16 - Wyman Area - 1 | Bigelow | NC | 2020-10-05 |  | EXECUTED/ENERGIZED
402 | 0 | 0 | 0 |  | 2020-03-24 | Auburn | HOTEL ROAD | 420D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 18 - Lewiston Loop - 2 | Hotel Rd/Gulf/Middle St/Crowleys/Norway | 3 |  |  | WITHDRAWN
403 | 0 | 0 | 0 |  | 2020-03-23 | Casco | SAND ROAD TAP | 470D1 | Solar | 0 | 0 | [10 empty] | 2020-08-04 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 07 - Raymond - 1 | Raymond | 3 | 2023-12-21 |  | RE_QUEUED_FullEx
404 | 0 | 0 | 329 |  | 2020-03-26 | Auburn | DEER RIPS | 412D3 | Solar | 0 | 0 | [10 empty] | 2022-06-14 | [8 empty] | Q4 2025 | EXECUTED-WITHDRAWN | WITHDRAWN | 2024-06-06 | Cluster 18 - Lewiston Loop - 2 | Hotel Rd/Gulf/Middle St/Crowleys/Norway | 3 |  | Not Required | RE_QUEUED_RESULTS
405 | 0 | 0 | 0 |  | 2020-03-27 | Winterport | PROSPECT | 846D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 06 - Detroit-Guilford-Belfast - 1 | Belfast | 3 |  | 2023-08-23 | WITHDRAWN
406 | 0 | 0 | 0 |  | 2020-03-27 | Corinth | SKOWHEGAN NORTH SIDE | 853T1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A |  |  |  |  | WITHDRAWN
407 | 0 | 0 | 131 |  | 2020-03-27 | Waterville | COUNTY RD (RICE RIPS) | 873D2 | Solar | 4999 | 0 |  |  |  |  | 2021-01-04 | 2021-04-21 |  |  |  |  | 2021-07-07 | 2022-12-29 | 2024-11-11 | 2024-09-05 | [5 empty] | Q4 2021 | Fully Executed Interconnection Agreement | No | 2024-12-19 | Cluster 12 - Winslow-County Rd-Lakewood - 2 | Winslow-County Rd | 3 | 2024-05-28 |  | RE_QUEUED_STUDY
408 | 0 | 0 | 0 | RQP-5 | 2020-03-27 | South Paris | PARIS TAP | 409D1 | Solar | 3000 | 0 |  |  |  |  | 2020-05-06 | 2020-07-10 |  |  |  |  | 2020-07-27 | [8 empty] | Q3 2021 | Fully Executed Interconnection Agreement | Yes | 2022-01-21 | Cluster 10 - Roxbury-Rumford-Woodstock - 1 | Woodstock | NC | 2020-10-05 |  | EXECUTED
409 | 0 | 0 | 0 |  | 2020-03-27 | Athens | ATHENS | 827D1 | Solar | 2864 | 0 |  |  |  |  | 2020-09-08 | 2020-11-12 |  |  |  |  | 2020-12-08 | [9 empty] | Fully Executed Interconnection Agreement | Yes | 2021-08-10 | Cluster 16 - Wyman Area - 1 | Athens | NC | 2021-02-25 |  | EXECUTED/ENERGIZED
410 | 0 | 0 | 0 |  | 2020-03-30 | Lovell | LOVELL | 430D1 | Solar | 0 | 0 | [10 empty] | 2022-01-07 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 13 - Kimball Rd-Lovell - 2 | Kimball Road/Lovell | 3 |  | Not Required | EXECUTED-WITHDRAWN
411 | 0 | 0 | 0 |  | 2020-03-30 | South Thomaston | THOMASTON CREEK | 246D1 | Solar | 4000 | 0 |  |  |  |  | 2020-06-04 | 2020-08-07 | 2020-09-29 | 2020-11-16 |  |  | 2020-12-01 | [9 empty] | Fully Executed Interconnection Agreement | Yes | 2021-07-09 | Cluster 09 - Midcoast - 1 | Highland/Park St | NC | 2021-03-30 |  | EXECUTED/ENERGIZED
412 | 0 | 0 | 0 |  | 2020-03-30 | Dover-Foxcroft | DOVER | 815D1 | Solar | 0 | 0 | [10 empty] | 2021-07-27 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 06 - Detroit-Guilford-Belfast - 1 | Guilford | 3 | 2023-08-31 |  | RE_QUEUED_FullEx
413 | 0 | 0 | 0 |  | 2020-04-01 | Richmond | RICHMOND | 240D1 | Solar | 1750 | 0 |  |  |  |  | 2020-05-15 | 2020-07-15 |  |  |  |  | 2020-08-18 | [9 empty] | Fully Executed Interconnection Agreement | Yes | 2020-09-13 | Cluster 01 - Augusta - 1 | Augusta E/Puddledock/Bowman St | 3 | 2021-01-04 |  | EXECUTED/ENERGIZED
414 | 0 | 0 | 0 |  | 2020-04-01 | Lebanon | LEBANON | 695D2 | Solar | 1998 | 0 |  |  |  |  | 2020-08-14 | 2020-10-20 |  |  |  |  | 2020-11-12 | 2023-12-07 | 2024-03-01 | [7 empty] | Fully Executed Interconnection Agreement | Yes | 2023-07-13 | Cluster 04 - Sanford-Quaker Hill - 1 | Sanford | 3 | 2022-06-27 |  | RE_QUEUED_FullEx
415 | 0 | 0 | 0 |  | 2020-04-01 | Brooks | BROOKS | 805D1 | Solar | 4000 | 0 |  |  |  |  | 2020-05-15 | 2020-07-20 |  |  |  |  | 2020-08-18 | [9 empty] | Fully Executed Interconnection Agreement | Yes | 2020-10-23 | Cluster 06 - Detroit-Guilford-Belfast - 1 | Belfast | 3 | 2023-05-31 |  | EXECUTED
416 | 0 | 0 | 0 |  | 2020-04-01 | Lincolnville | LINCOLNVILLE | 800D1 | Solar | 4000 | 0 |  |  |  |  | 2020-04-24 | 2020-06-29 |  |  |  |  | 2020-07-13 | [9 empty] | Fully Executed Interconnection Agreement | Yes | 2020-07-24 | Cluster 09 - Midcoast - 1 | Lincolnville | 0 | 2020-08-31 |  | EXECUTED/ENERGIZED
417 | 0 | 0 | 0 |  | 2020-04-02 | Lewiston | CROWLEYS | 411D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 18 - Lewiston Loop - 2 | Hotel Rd/Gulf/Middle St/Crowleys/Norway | 3 |  |  | WITHDRAWN
418 | 0 |  | 0 |  | 2020-04-06 | Augusta | BOND BROOK | 208D2 | Solar | 0 | 0 | [10 empty] | 2021-06-16 | [8 empty] | Q4 2021 | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 11 - Augusta E-Puddledock-Bowman St - 2 | Augusta E/Puddledock/Bowman St | 3 | 2024-05-28 |  | RE_QUEUED_RESULTS
419 | 0 | 0 | 0 |  | 2020-04-06 | Athens | ATHENS | 827D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Athens |  |  |  | WITHDRAWN
420 | 0 | 0 | 0 |  | 2020-04-06 | Athens | ATHENS | 827D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Athens |  |  |  | WITHDRAWN
421 | 0 | 0 | 0 |  | 2020-04-06 | Athens | ATHENS | 827D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Athens |  |  |  | WITHDRAWN
422 | 0 | 0 | 0 |  | 2020-04-06 | Athens | ATHENS | 827D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Athens |  |  |  | WITHDRAWN
423 | 0 | 0 | 0 |  | 2020-04-06 | Athens | ATHENS | 827D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Athens |  |  |  | WITHDRAWN
424 | 0 | 0 | 0 |  | 2020-04-06 | Athens | ATHENS | 827D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Athens |  |  |  | WITHDRAWN
425 | 0 | 0 | 0 |  | 2020-04-06 | Athens | ATHENS | 827D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Athens |  |  |  | WITHDRAWN
426 | 0 | 0 | 0 |  | 2020-04-06 | Athens | ATHENS | 827D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Athens |  |  |  | WITHDRAWN
427 | 0 | 0 | 0 |  | 2020-04-13 | Stockton Springs | PROSPECT | 846D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Belfast |  |  |  | WITHDRAWN
428 | 0 | 0 | 0 |  | 2020-04-13 | Gardiner | GARDINER | 226D2 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 01 - Augusta - 1 | Augusta E/Puddledock/Bowman St | 3 |  | 2022-03-21 | WITHDRAWN
429 | 0 | 0 | 0 |  | 2020-04-13 | Gardiner | WEST STREET | 255D1 | Solar | 4000 | 0 |  |  |  |  | 2020-08-07 | 2020-10-13 |  |  |  |  | 2020-09-23 | [9 empty] | Fully Executed Interconnection Agreement | Yes | 2021-03-24 | Cluster 01 - Augusta - 1 | Augusta E/Puddledock/Bowman St | 3 | 2021-01-04 |  | EXECUTED/ENERGIZED
430 | 0 | 0 | 0 |  | 2020-04-13 | Brooks | BROOKS | 805D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 06 - Detroit-Guilford-Belfast - 1 | Belfast | 3 |  | 2023-08-23 | WITHDRAWN
431 | 0 | 0 | 0 |  | 2020-04-13 | Athens | ATHENS | 827D2 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Athens |  |  |  | WITHDRAWN
432 | 0 | 0 | 0 |  | 2020-04-17 | Farmington | STURTEVANT | 858D3 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Sturtevant/ Leeds/ Livermore/ Ludden/ Riley_TBD | Sturtevant | 3 |  |  | WITHDRAWN
433 | 0 | 0 | 0 |  | 2020-04-21 | Monroe | BROOKS | 805D1 | Solar | 0 | 0 |  |  |  |  | 2021-08-31 | [15 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 17 - Detroit Guilford Belfast - 2 | Belfast | 3 |  |  | WITHDRAWN
434 | 0 | 0 | 0 |  | 2020-04-21 | Belgrade | NORTH AUGUSTA | 272D6 | Solar | 0 | 0 | [10 empty] | 2022-07-28 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster XX - Augusta E-Puddledock-Bowman St - TBD | North Augusta | 3 |  |  | EXECUTED
435 | 0 | 0 | 0 |  | 2020-04-21 | Waterville | WEST WATERVILLE | 865D5 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 12 - Winslow-County Rd-Lakewood - 2 | Winslow-County Rd | 3 | 2024-05-28 |  | WITHDRAWN
436 | 0 | 0 | 0 |  | 2020-04-23 | Rumford | RUMFORD | 447D2 | Solar | 3984 | 0 |  |  |  |  | 2020-05-15 | 2020-07-21 |  |  |  |  | 2020-08-26 | [9 empty] | Fully Executed Interconnection Agreement | Yes | 2021-01-12 | Cluster 10 - Roxbury-Rumford-Woodstock - 1 | Rumford | NC | 2020-11-20 |  | EXECUTED/ENERGIZED
437 | 0 | 0 | 0 |  | 2020-04-23 | Gorham | WESTBROOK | 674D2 | Solar/Battery | 4990 | 0 |  |  |  |  | 2020-05-21 | 2020-07-27 |  |  |  |  | 2020-08-26 | [9 empty] | Fully Executed Interconnection Agreement | Yes | 2020-11-25 | Cluster 15 - Greater Portland - 1 | Moshers/Prides Corner | 0 | 2020-10-05 |  | EXECUTED/ENERGIZED
438 | 0 | 0 | 0 |  | 2020-04-23 | Thomaston | PARK STREET | 239D10 | Solar | 0 | 0 | [10 empty] | 2020-08-10 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 09 - Midcoast - 1 | Highland/Park St | NC | 2020-10-05 |  | EXECUTED
439 | 0 | 0 | 0 |  | 2020-04-23 | Turner | WATERBORO | 671T1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A |  |  |  |  | WITHDRAWN
440 | 0 | 0 | 0 |  | 2020-04-23 | Naples | NAPLES TAP | 469D1 | Solar | 0 | 0 | [10 empty] | 2021-06-10 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 07 - Raymond - 1 | Raymond | 3 | 2023-12-21 |  | EXECUTED-WITHDRAWN
441 | 0 | 0 | 0 |  | 2020-04-24 | Turner | DEER RIPS | 412D3 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 18 - Lewiston Loop - 2 | Hotel Rd/Gulf/Middle St/Crowleys/Norway | 3 |  |  | WITHDRAWN
442 | 0 | 0 | 0 |  | 2020-04-24 | Turner | DEER RIPS | 412D3 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 18 - Lewiston Loop - 2 | Hotel Rd/Gulf/Middle St/Crowleys/Norway | 3 |  |  | WITHDRAWN
443 | 0 | 0 | 0 |  | 2020-04-24 | Pownal | GRAY | 416D1 | Solar | 0 | 0 |  |  |  |  | 2021-06-03 | 2021-08-13 | 2021-10-12 | 2021-11-12 | [12 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 15 - Greater Portland - 1 | Elm St | 3 |  | 2024-03-19 | WITHDRAWN
444 | 0 | 0 | 0 |  | 2020-04-24 | York | BRAGDON COMMONS | 689D1 | Solar | 0 | 0 | [10 empty] | 2020-08-26 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 04 - Sanford-Quaker Hill - 1 | Quaker Hill | 3 | 2022-06-27 |  | EXECUTED-WITHDRAWN
445 | 0 | 0 | 0 |  | 2020-04-27 | Oxford | OXFORD | 437D1 | Solar | 1625 | 0 |  |  |  |  | 2020-07-09 | 2020-09-11 | 2020-11-10 | 2020-12-28 |  |  | 2021-06-03 | [9 empty] | Fully Executed Interconnection Agreement | Yes | 2022-12-02 | Cluster 05 - Lewiston Loop - 1 | Hotel Rd/Gulf/Middle St/Crowleys/Norway | 3 | 2022-07-19 |  | EXECUTED
446 | 0 | 0 | 0 |  | 2020-04-27 | Shapleigh | BUTLER'S CORNER | 612D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Sanford |  |  |  | WITHDRAWN
447 | 0 | 0 | 0 |  | 2020-04-29 | Chelsea | BOWMAN STREET | 263D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 11 - Augusta E-Puddledock-Bowman St - 2 | Augusta E/Puddledock/Bowman St | 3 | 2024-05-28 |  | WITHDRAWN
448 | 0 | 0 | 0 |  | 2020-04-30 | Berwick | BERWICK | 603D2 | Solar | 3450 | 0 |  |  |  |  | 2020-07-27 | 2020-09-29 |  |  |  |  | 2020-11-14 | [9 empty] | Fully Executed Interconnection Agreement | Yes | 2023-10-25 | Cluster 04 - Sanford-Quaker Hill - 1 | Quaker Hill | 3 | 2022-06-27 |  | EXECUTED
449 | 0 | 0 | 0 |  | 2020-04-30 | Richmond | RICHMOND | 240D1 | Solar | 0 | 0 | [10 empty] | 2020-11-12 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 11 - Augusta E-Puddledock-Bowman St - 2 | Augusta E/Puddledock/Bowman St | 3 | 2024-05-28 |  | EXECUTED-WITHDRAWN
450 | 0 | 0 | 0 |  | 2020-05-04 | Waterford | PAPOOSE POND | 438D1 | Solar/Battery | 0 | 0 | [10 empty] | 2020-08-20 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 03 - Kimball Rd-Lovell - 1 | Kimball Road/Lovell | 3 |  | 2023-04-22 | EXECUTED-WITHDRAWN
451 | 0 | 0 | 414 |  | 2020-05-04 | Lebanon | LEBANON | 695D1 | Solar | 1999 | 0 |  |  |  |  | 2020-12-08 | 2021-02-12 |  |  |  |  | 2021-06-21 | 2024-04-22 | 2024-05-17 | [6 empty] | Q4 2021 | Fully Executed Interconnection Agreement | Yes | 2023-10-17 | Cluster 04 - Sanford-Quaker Hill - 1 | Sanford | 3 | 2022-06-27 |  | RE_QUEUED_FullEx
452 | 0 | 0 | 0 |  | 2020-05-04 | Bowdoin | TOPSHAM 34 KV | 250D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Topsham |  |  |  | WITHDRAWN
453 | 0 | 0 | 0 |  | 2020-05-04 | South Portland | PLEASANT HILL | 644D2 | Solar | 2500 | 0 |  |  |  |  | 2020-07-02 | 2020-09-03 |  |  |  |  | 2020-10-15 | [9 empty] | Fully Executed Interconnection Agreement | Yes | 2021-03-04 | Cluster 15 - Greater Portland - 1 | Pleasant Hill | 0 | 2020-10-05 |  | EXECUTED/ENERGIZED
454 | 0 | 0 | 0 |  | 2020-05-05 | Kittery | PNSY | PNSY | CTG/Battery | 6800 | 1000 |  |  |  |  | 2021-12-17 | 2021-12-17 |  |  |  |  | 2021-12-17 | [9 empty] | Fully Executed Interconnection Agreement | Yes |  | N/A | N/A |  | N/A | N/A | EXECUTED
455 | 0 | 0 | 0 |  | 2020-05-07 | Augusta | CAPITOL STREET | 215D2 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 11 - Augusta E-Puddledock-Bowman St - 2 | Augusta E/Puddledock/Bowman St | 3 | 2024-05-28 |  | WITHDRAWN
456 | 0 | 0 | 0 |  | 2020-05-07 | Thomaston | THOMASTON CREEK | 246D3 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Highland/Park St |  |  |  | WITHDRAWN
457 | 0 | 0 | 0 |  | 2020-05-08 | York | SOUTH BERWICK | 663D2 | Solar | 0 | 0 | [10 empty] | 2020-10-28 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 04 - Sanford-Quaker Hill - 1 | Quaker Hill | 3 | 2022-06-27 |  | EXECUTED-WITHDRAWN
458 | 0 | 0 | 0 |  | 2020-05-08 | Norridgewock | SKOWHEGAN SOUTH SIDE | 854D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Lakewood |  |  |  | WITHDRAWN
459 | 0 | 0 | 0 |  | 2020-05-08 | Wilton | EAST WILTON | 816D1 | Solar | 3000 | 0 |  |  |  |  | 2020-06-17 | 2020-08-20 |  |  |  |  | 2020-09-16 | [9 empty] | Fully Executed Interconnection Agreement | Yes | 2020-10-23 | Cluster 08 - Sturtevant-Leeds-Livermore-Ludden-Riley - 1 | Sturtevant | NC | 2021-06-01 |  | EXECUTED/ENERGIZED
460 | 0 | 0 | 0 |  | 2020-05-11 | Dover-Foxcroft | DOVER | 815D2 | Solar | 0 | 0 |  |  |  |  | 2021-09-30 | [5 empty] | 2021-12-13 | 2023-04-05 | 2023-05-18 | [7 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 17 - Detroit Guilford Belfast - 2 | Guilford | 3 |  | Not Required | RE_QUEUED_FullEx
461 | 0 | 0 | 0 |  | 2020-05-11 | Wilton | WILTON | 885D1 | Solar | 0 | 0 | [10 empty] | 2021-08-30 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 08 - Sturtevant-Leeds-Livermore-Ludden-Riley - 1 | Sturtevant | 3 | 2023-12-21 |  | RE_QUEUED_FullEx
462 | 0 | 0 | 0 |  | 2020-05-11 | Augusta | NORTH AUGUSTA | 272D2 | Solar | 0 | 0 |  |  |  |  | 2022-09-29 | 2022-12-06 |  |  |  |  | 2023-01-13 | [9 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Augusta E-Puddledock-Bowman St - TBD | North Augusta | 3 |  |  | EXECUTED-WITHDRAWN
463 | 0 | 0 | 0 |  | 2020-05-13 | Farmington | STURTEVANT | 858D4 | Solar/Battery | 0 | 0 |  |  |  |  | 2024-06-10 | 2024-08-07 | [14 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Sturtevant/ Leeds/ Livermore/ Ludden/ Riley_TBD | Sturtevant | 3 |  | Not Required | RE_QUEUED_RESULTS
464 | 0 | 0 | 0 |  | 2020-05-13 | Windham | SWETT ROAD | 682D1 | Solar | 0 | 0 | [10 empty] | 2020-11-14 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 07 - Raymond - 1 | Raymond | 3 |  | 2023-12-15 | EXECUTED-WITHDRAWN
465 | 0 | 0 | 0 |  | 2020-05-13 | Waterford | PAPOOSE POND | 438D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 03 - Kimball Rd-Lovell - 1 | Kimball Road/Lovell | 3 |  | 2023-04-22 | WITHDRAWN
466 | 0 | 0 | 0 |  | 2020-05-13 | Sanford | HIGH STREET | 626D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A |  |  |  |  | WITHDRAWN
467 | 0 | 0 | 0 |  | 2020-05-14 | West Gardiner | WEST STREET | 255D2 | Solar | 0 | 0 | [10 empty] | 2021-01-18 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 11 - Augusta E-Puddledock-Bowman St - 2 | Augusta E/Puddledock/Bowman St | 3 | 2024-05-28 |  | EXECUTED-WITHDRAWN
468 | 0 | 0 | 0 |  | 2020-05-14 | Jay | RILEY | 449D2 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Riley | NC |  |  | WITHDRAWN
469 | 0 | 0 | 0 |  | 2020-05-18 | Sanford | SANFORD SWITCH | 657D4 | Solar | 0 | 0 | [10 empty] | 2020-09-09 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 04 - Sanford-Quaker Hill - 1 | Sanford | 3 | 2022-06-27 |  | EXECUTED-WITHDRAWN
470 | 0 | 0 | 0 |  | 2020-05-20 | Harmony | ATHENS | 827D2 | Solar | 0 | 0 | [10 empty] | 2021-10-26 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 16 - Wyman Area - 1 | Athens | 3 | 2023-04-27 |  | EXECUTED
471 | 0 | 0 | 0 |  | 2020-05-22 | South Thomaston | THOMASTON CREEK | 246D1 | Solar | 0 | 0 | [10 empty] | 2022-01-18 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 09 - Midcoast - 1 | Highland/Park St | 3 | 2023-12-21 |  | EXECUTED
472 | 0 | 0 | 0 |  | 2020-05-26 | Oakland | COUNTY RD (RICE RIPS) | 873D1 | Solar | 0 | 0 | [10 empty] | 2021-12-23 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 12 - Winslow-County Rd-Lakewood - 2 | Winslow-County Rd | 3 | 2024-05-28 |  | RE_QUEUED_FullEx
473 | 0 | 0 | 0 |  | 2020-05-26 | Pittsfield | BURNHAM | 807D1 | Solar | 0 | 0 | [10 empty] | 2020-09-18 | [8 empty] | Q4 2025 | EXECUTED-WITHDRAWN | WITHDRAWN | 2020-10-23 | Cluster 06 - Detroit-Guilford-Belfast - 1 | Detroit | 3 | 2023-08-31 |  | EXECUTED
474 | 0 | 0 | 0 |  | 2020-05-26 | New Sharon | FARMINGTON FALLS | 818D1 | Solar | 3750 | 0 |  |  |  |  | 2020-07-24 | 2020-09-28 | 2022-03-21 | 2022-04-29 |  |  | 2020-11-14 | [9 empty] | Fully Executed Interconnection Agreement | Yes | 2021-10-20 | Cluster 08 - Sturtevant-Leeds-Livermore-Ludden-Riley - 1 | Sturtevant | NC | 2021-06-01 |  | RE_QUEUED_FullEx/ENERGIZED
475 | 0 | 0 | 0 |  | 2020-05-26 | Fairfield | SHAWMUT | 852D1 | Solar | 1000 | 0 |  |  |  |  | 2020-07-17 | 2020-09-15 | 2021-09-16 | 2021-10-14 |  |  | 2020-09-23 | [9 empty] | Fully Executed Interconnection Agreement | Yes | 2022-02-02 | Cluster 02 - Winslow-County Rd-Lakewood -1 | Lakewood | 3 | 2021-12-17 |  | EXECUTED/ENERGIZED
476 | 0 | 0 | 0 |  | 2020-05-26 | Waterville | WEST WATERVILLE | 865D5 | Solar | 4950 | 0 |  |  |  |  | 2020-08-03 | 2020-10-06 |  |  |  |  | 2020-10-19 | [9 empty] | Fully Executed Interconnection Agreement | Yes | 2022-02-02 | Cluster 02 - Winslow-County Rd-Lakewood -1 | Winslow-County Rd | 3 | 2021-12-17 |  | EXECUTED/ENERGIZED
477 | 0 | 0 | 0 |  | 2020-05-27 | Andover | ANDOVER | 400D1 | Solar | 999 | 0 |  |  |  |  | 2020-07-24 | 2020-09-28 |  |  |  |  | 2020-11-10 | 2023-08-25 | 2023-10-09 | [6 empty] | Q4 2025 | Fully Executed Interconnection Agreement | No | 2023-11-20 | Cluster 10 - Roxbury-Rumford-Woodstock - 1 | Roxbury | 3 |  | Not Required | RE_QUEUED_FullEx
478 | 0 | 0 | 0 |  | 2020-05-28 | Augusta | AUGUSTA K5 | 200D3 | Solar | 2000 | 0 |  |  |  |  | 2020-07-27 | 2020-09-29 |  |  |  |  | 2020-10-26 | [9 empty] | Fully Executed Interconnection Agreement | Yes | 2021-05-04 | Cluster 01 - Augusta - 1 | Augusta E/Puddledock/Bowman St | 3 | 2021-01-04 |  | EXECUTED/ENERGIZED
479 | 0 | 0 | 0 |  | 2020-05-28 | Chelsea | CONY ROAD | 216D1 | Solar | 4999 | 0 | 2020-08-03 | 2020-09-08 | 2020-09-29 | 2020-11-12 | [6 empty] | 2020-11-24 | [9 empty] | Fully Executed Interconnection Agreement | Yes | 2021-12-31 | Cluster 01 - Augusta - 1 | Augusta E/Puddledock/Bowman St | 3 | 2021-01-04 |  | EXECUTED
480 | 0 | 0 | 0 |  | 2020-06-04 | Edgecomb | EDGECOMB | 223D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 09 - Midcoast - 1 | Newcastle | 3 |  | 2023-12-15 | WITHDRAWN
481 | 0 | 0 | 472 |  | 2020-06-04 | Oakland | COUNTY RD (RICE RIPS) | 873D1 | Solar | 999.6 | 0 |  |  |  |  | 2022-03-07 | 2022-05-10 | 2024-03-18 | 2024-04-26 |  |  | 2022-06-21 | 2023-08-22 | 2023-10-04 | 2025-02-05 | 2025-04-04 | [5 empty] | Fully Executed Interconnection Agreement | No | 2025-05-13 | Cluster XX - Winslow/ County Rd/ Lakewood - TBD | Winslow-County Rd | 3 |  | Not Required | RE_QUEUED_FullEx
482 | 0 | 0 | 0 |  | 2020-06-05 | Wilton | WILTON | 885D1 | Solar | 0 | 0 | [10 empty] | 2021-12-10 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster XX - Sturtevant/ Leeds/ Livermore/ Ludden/ Riley_TBD | Sturtevant | 3 |  |  | EXECUTED-WITHDRAWN
483 | 0 | 0 | 0 |  | 2020-06-08 | Shapleigh | SANFORD SWITCH | 657D3 | Solar | 0 | 0 | [10 empty] | 2021-01-26 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 04 - Sanford-Quaker Hill - 1 | Sanford | 3 | 2022-06-27 |  | EXECUTED-WITHDRAWN
484 | 0 | 0 | 0 |  | 2020-06-16 | Skowhegan | WESTON HYDRO | 866D2 | Solar | 0 | 0 | [10 empty] | 2021-03-01 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 12 - Winslow-County Rd-Lakewood - 2 | Lakewood | 3 | 2024-05-28 |  | EXECUTED-WITHDRAWN
485 | 0 | 0 | 0 |  | 2020-06-15 | Hollis | BAR MILLS | 678D1 | Solar | 4950 | 0 |  |  |  |  | 2020-08-03 | 2020-10-06 |  |  |  |  | 2020-10-19 | [9 empty] | Fully Executed Interconnection Agreement | Yes | 2021-09-23 | Cluster 14 - Louden-Biddeford IP - 1 | West Buxton | NC | 2021-09-03 |  | EXECUTED/ENERGIZED
486 | 0 | 0 | 0 |  | 2020-06-15 | North Anson | NORTH ANSON | 838D2 | Solar | 0 | 0 |  |  |  |  | 2020-11-12 | [15 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Lakewood |  |  |  | WITHDRAWN
487 | 0 | 0 | 0 |  | 2020-06-15 | Norridgewock | SKOWHEGAN SOUTH SIDE | 854D1 | Solar | 2318 | 0 |  |  |  |  | 2020-07-24 | 2020-09-28 | 2020-11-10 | 2020-12-28 |  |  | 2021-05-13 | [9 empty] | Fully Executed Interconnection Agreement | Yes | 2022-12-07 | Cluster 02 - Winslow-County Rd-Lakewood -1 | Lakewood | 3 | 2021-12-17 |  | EXECUTED
488 | 0 | 0 | 0 |  | 2020-06-15 | Owls Head | PARK STREET | 239D5 | Solar | 0 | 0 | [10 empty] | 2021-06-11 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 09 - Midcoast - 1 | Highland/Park St | 3 |  | 2023-12-15 | EXECUTED-WITHDRAWN
489 | 0 | 0 | 0 |  | 2020-06-15 | Fairfield | SHAWMUT | 852D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 12 - Winslow-County Rd-Lakewood - 2 | Lakewood | 3 | 2024-05-28 |  | WITHDRAWN
490 | 0 | 0 | 0 |  | 2020-06-16 | Palmyra | DETROIT | 812D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Detroit |  |  |  | WITHDRAWN
491 | 0 | 0 | 0 |  | 2020-06-16 | Bristol | BRISTOL | 210D2 | Solar | 3500 | 0 |  |  |  |  | 2020-08-05 | 2020-10-06 |  |  |  |  | 2020-11-04 | [9 empty] | Fully Executed Interconnection Agreement | Yes | 2023-03-02 | Cluster 09 - Midcoast - 1 | Newcastle | 3 | 2023-12-21 |  | EXECUTED
492 | 0 | 0 | 0 |  | 2020-06-22 | Limerick | LIMERICK | 632D2 | Solar | 0 | 0 |  |  |  |  | 2020-10-05 | 2020-12-15 | 2021-01-15 | 2021-06-11 |  |  | 2021-06-21 | [9 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 03 - Kimball Rd-Lovell - 1 | Kimball Road/Lovell | 3 | 2023-04-27 |  | EXECUTED
493 | 0 | 0 | 0 |  | 2020-06-23 | Gardiner | BROWNS CROSSING | 211D2 | Solar | 3875 | 0 |  |  |  |  | 2020-08-13 | 2020-10-19 | 2020-12-07 | 2021-01-19 |  |  | 2020-12-09 | [9 empty] | Fully Executed Interconnection Agreement | Yes | 2021-08-11 | Cluster 11 - Augusta E-Puddledock-Bowman St - 2 | Browns Crossing | NC | 2021-02-25 |  | EXECUTED/ENERGIZED
494 | 0 | 0 | 0 |  | 2020-06-23 | Gardiner | GARDINER | 226D2 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Augusta E/Puddledock/Bowman St |  |  |  | WITHDRAWN
495 | 0 | 0 | 0 |  | 2020-06-24 | Prospect | PROSPECT | 846D1 | Solar | 0 | 0 |  |  |  |  | 2021-03-10 | 2021-07-08 | 2021-11-04 | 2021-12-20 |  |  | 2022-09-15 | 2023-01-17 | 2023-02-21 | [7 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 17 - Detroit Guilford Belfast - 2 | Belfast | 3 |  |  | RE_QUEUED_FullEx
496 | 0 | 0 | 0 |  | 2020-06-24 | Monroe | BROOKS | 805D1 | Solar | 0 | 0 | 2022-03-30 | 2022-05-05 | 2022-09-08 | 2022-10-19 | [6 empty] | 2023-01-23 | [9 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 17 - Detroit Guilford Belfast - 2 | Belfast | 3 |  |  | EXECUTED
497 | 0 | 0 | 0 |  | 2020-06-24 | Casco | RAYMOND 115 KV | 445D2 | Solar | 0 | 0 | [10 empty] | 2021-01-19 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 07 - Raymond - 1 | Raymond | 3 | 2023-12-21 |  | EXECUTED-WITHDRAWN
498 | 0 | 0 | 0 |  | 2020-06-26 | Parkman | GUILFORD | 821D1 | Solar | 0 | 0 | [10 empty] | 2022-08-04 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 17 - Detroit Guilford Belfast - 2 | Guilford | 3 |  |  | RE_QUEUED_FullEx
499 | 0 | 0 | 0 |  | 2020-07-01 | Scarborough | SCARBOROUGH | 693D1 | Solar | 0 | 0 | [10 empty] | 2020-11-05 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 15 - Greater Portland - 1 | Spring St | 3 | 2024-02-22 |  | RE_QUEUED_FullEx
500 | 0 | 0 | 0 |  | 2020-07-01 | Farmington | STURTEVANT | 858D3 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Sturtevant/ Leeds/ Livermore/ Ludden/ Riley_TBD | Sturtevant | 3 |  |  | WITHDRAWN
501 | 0 | 0 | 0 |  | 2020-07-01 | Scarborough | SCARBOROUGH | 693D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Spring St |  |  |  | WITHDRAWN
502 | 0 | 0 | 0 |  | 2020-07-02 | Farmington | STURTEVANT | 858D1A | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Sturtevant/ Leeds/ Livermore/ Ludden/ Riley_TBD | Sturtevant | 3 |  |  | WITHDRAWN
503 | 0 | 0 | 0 |  | 2020-07-02 | Auburn | HOTEL ROAD | 420D4 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 18 - Lewiston Loop - 2 | Hotel Rd/Gulf/Middle St/Crowleys | 3 |  |  | WITHDRAWN
504 | 0 | 0 | 0 |  | 2020-07-08 | West Paris | TRAP CORNER | 453D1 | Solar | 0 | 0 | [10 empty] | 2021-05-06 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 10 - Roxbury-Rumford-Woodstock - 1 | Woodstock | 3 |  | Not Required | EXECUTED-WITHDRAWN
505 | 0 | 0 | 0 |  | 2020-07-09 | Brunswick | TOPHAM OLD | 249D1 | Solar | 0 | 0 | [10 empty] | 2020-12-01 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 09 - Midcoast - 1 | Topsham | 3 | 2023-12-21 |  | EXECUTED-WITHDRAWN
506 | 0 | 0 | 0 |  | 2020-07-09 | Canton | RUMFORD INDUSTRIAL PARK | 466D1 | Solar | 3000 | 0 |  |  |  |  | 2020-08-20 | 2020-10-26 |  |  |  |  | 2020-12-08 | [9 empty] | Fully Executed Interconnection Agreement | Yes | 2021-11-12 | Cluster 10 - Roxbury-Rumford-Woodstock - 1 | Rumford IP | NC | 2021-02-25 |  | EXECUTED/ENERGIZED
507 | 0 | 0 | 0 |  | 2020-07-13 | Scarborough | SCARBOROUGH | 693D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Spring St |  |  |  | WITHDRAWN
508 | 0 | 0 | 0 |  | 2020-07-13 | Arundel | BIDDEFORD INDUSTRIAL PARK | 673D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Biddeford IP |  |  |  | WITHDRAWN
509 | 0 | 0 | 0 |  | 2020-07-13 | Paris | PARIS TAP | 409D1 | Solar | 0 | 0 | [10 empty] | 2021-05-19 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 10 - Roxbury-Rumford-Woodstock - 1 | Woodstock | 3 | 2023-12-21 |  | EXECUTED-WITHDRAWN
510 | 0 | 0 | 0 |  | 2020-07-14 | New Portland | STURTEVANT | 858D2 | Solar/Battery | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Sturtevant/ Leeds/ Livermore/ Ludden/ Riley_TBD | Sturtevant | 3 |  |  | WITHDRAWN
511 | 0 | 0 | 0 |  | 2020-07-20 | Bristol | BRISTOL | 210D1 | Solar | 1999 | 0 |  |  |  |  | 2020-11-17 | 2021-01-26 | 2021-09-16 | 2021-10-27 |  |  | 2021-11-24 | [8 empty] | Q3 2026 | Fully Executed Interconnection Agreement | No | 2023-03-16 | Cluster 09 - Midcoast - 1 | Newcastle | 3 | 2023-12-21 |  | EXECUTED
512 | 0 | 0 | 0 |  | 2020-07-22 | Dover-Foxcroft | DOVER | 815D2 | Solar | 0 | 0 | 2022-03-02 | [10 empty] | 2023-08-28 | [8 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 17 - Detroit Guilford Belfast - 2 | Guilford | 3 |  |  | WITHDRAWN
513 | 0 | 0 | 0 |  | 2020-07-22 | Hollis | BAR MILLS | 678D1 | Solar | 0 | 0 | [10 empty] | 2021-07-06 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 14 - Louden-Biddeford IP - 1 | West Buxton | 3 |  | 2024-03-19 | EXECUTED-WITHDRAWN
514 | 0 | 0 | 0 |  | 2020-07-22 | Hermon | BANGOR HYDRO (Versant) | 120D1 | Solar/Battery | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Emera Transmission |  |  |  | WITHDRAWN
515 | 0 | 0 | 0 |  | 2020-07-22 | Rumford | RUMFORD | 447D2 | Solar/Battery | 0 | 0 | [10 empty] | 2021-02-02 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 10 - Roxbury-Rumford-Woodstock - 1 | Rumford | 3 |  | 2023-12-15 | EXECUTED-WITHDRAWN
516 | 0 | 0 | 0 |  | 2020-07-24 | Prospect | PROSPECT | 846D1 | Solar | 0 | 0 |  |  |  |  | 2023-04-26 | 2023-06-08 | [14 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 17 - Detroit Guilford Belfast - 2 | Belfast | 3 |  | Not Required | WITHDRAWN
517 | 0 | 0 | 0 |  | 2020-07-24 | Saco | LOUDEN | 633D1 | Solar/Battery | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Louden |  |  |  | WITHDRAWN
518 | 0 | 0 | 0 |  | 2020-07-24 | Fryeburg | FRYEBURG TAP | 405D1 | Hydro | 600 | 0 |  |  |  |  | 2020-11-13 | 2021-05-12 | 2021-07-19 | 2021-08-30 |  |  | 2021-10-06 | [9 empty] | Fully Executed Interconnection Agreement | Yes | 2022-04-11 | Cluster 03 - Kimball Rd-Lovell - 1 | Kimball Road/Lovell | 3 |  | Not Required | EXECUTED/ENERGIZED
519 | 0 | 0 | 0 |  | 2020-07-28 | Sabattus | SABATTUS | 450D1 | Solar | 4950 | 0 |  |  |  |  | 2020-08-20 | 2020-10-26 | 2023-11-22 | 2024-01-09 |  |  | 2020-11-10 | 2023-08-31 | 2023-10-16 | [7 empty] | Fully Executed Interconnection Agreement | Yes | 2022-09-26 | Cluster 05 - Lewiston Loop - 1 | Hotel Rd/Gulf/Middle St/Crowleys | 3 | 2022-07-19 |  | RE_QUEUED_FullEx
520 | 0 | 0 | 0 |  | 2020-07-28 | South Paris | NORWAY | 435D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Louden-Biddeford IP - TBD | Norway | 3 |  |  | WITHDRAWN
521 | 0 | 0 | 0 |  | 2020-07-29 | Plymouth | NEWPORT | 837D2 | Solar/Battery | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Detroit |  |  |  | WITHDRAWN
522 | 0 | 0 | 0 |  | 2020-07-30 | Newfield | LIMERICK | 632D2 | Solar | 0 | 0 |  |  |  |  | 2021-07-12 | [15 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 13 - Kimball Rd-Lovell - 2 | Kimball Road/Lovell | 3 |  |  | WITHDRAWN
523 | 0 | 0 | 0 |  | 2020-07-31 | Embden | EMBDEN | 868D1 | Solar | 1000 | 0 |  |  |  |  | 2020-08-28 | 2020-11-03 | 2021-08-31 |  |  |  | 2020-11-17 | [9 empty] | Fully Executed Interconnection Agreement | Yes | 2022-05-17 | Cluster 16 - Wyman Area - 1 | Embden | 3 | N/A |  | EXECUTED/ENERGIZED
524 | 0 | 0 | 0 |  | 2020-08-07 | Biddeford | BIDDEFORD PUMP | 605D1 | Solar | 840 | 0 |  |  |  |  | 2020-09-14 | 2020-11-17 | 2022-12-02 | 2021-09-14 |  |  | 2021-11-24 | 2022-12-02 | 2023-01-18 | [6 empty] | Q4 2025 | Fully Executed Interconnection Agreement | No | 2022-12-27 | Cluster 14 - Louden-Biddeford IP - 1 | Louden | 3 |  | Not Required | RE_QUEUED_FullEx
525 | 0 | 0 | 0 |  | 2020-08-07 | Leeds | LEEDS | 471D2 | Solar/Battery | 0 | 0 |  |  |  |  | 2022-04-06 | 2022-06-03 |  |  |  |  | 2022-10-31 | 2024-09-13 | 2024-11-19 | [7 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Sturtevant/ Leeds/ Livermore/ Ludden/ Riley_TBD | Leeds | 3 |  |  | RE_QUEUED_RESULTS
526 | 0 | 0 | 0 |  | 2020-08-10 | Greenville | MONSON | 834D2 | Solar | 0 | 0 | [10 empty] | 2021-07-21 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 06 - Detroit-Guilford-Belfast - 1 | Guilford | 3 | 2023-08-31 |  | EXECUTED-WITHDRAWN
527 | 0 | 0 | 0 |  | 2020-08-10 | Fairfield | SHAWMUT | 852D1 | Solar | 0 | 0 | 2022-01-05 | 2022-02-03 | [18 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Winslow/ County Rd/ Lakewood - TBD | Lakewood | 3 |  |  | WITHDRAWN
528 | 0 | 0 | 0 |  | 2020-08-10 | Denmark | DENMARK | 413D2 | Solar | 0 | 0 | [10 empty] | 2020-11-22 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 03 - Kimball Rd-Lovell - 1 | Kimball Road/Lovell | 3 | 2023-04-27 |  | EXECUTED-WITHDRAWN
529 | 0 | 0 | 0 |  | 2020-08-11 | New Gloucester | HOTEL ROAD | 420D7 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 18 - Lewiston Loop - 2 | Hotel Rd/Gulf/Middle St/Crowleys | 3 |  |  | WITHDRAWN
530 | 0 | 0 | 0 |  | 2020-08-11 | Sidney | NORTH AUGUSTA | 272D6 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Augusta E-Puddledock-Bowman St - TBD | North Augusta | 3 |  |  | WITHDRAWN
531 | 0 | 0 | 0 |  | 2020-08-12 | Bryant Pond | BRYANT POND | 407D1 | Solar | 0 | 0 | [10 empty] | 2021-05-05 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 10 - Roxbury-Rumford-Woodstock - 1 | Woodstock | 3 |  | 2023-12-15 | EXECUTED-WITHDRAWN
532 | 0 | 0 | 0 |  | 2020-08-13 | Detroit | DETROIT | 812D2 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Detroit |  |  |  | WITHDRAWN
533 | 0 | 0 | 0 |  | 2020-08-17 | Arundel | BIDDEFORD INDUSTRIAL PARK | 673D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 14 - Louden-Biddeford IP - 1 | Biddeford IP | 3 |  | 2024-03-19 | WITHDRAWN
534 | 0 | 0 | 0 |  | 2020-08-19 | Bingham | WYMAN HYDRO | 872D1 | Solar | 0 | 0 | [10 empty] | 2022-01-19 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 16 - Wyman Area - 1 | Wyman Hydro | 3 |  | Not Required | EXECUTED-WITHDRAWN
535 | 0 | 0 | 0 |  | 2020-08-19 | Buxton | BAR MILLS | 678D2 | Solar | 0 | 0 | [10 empty] | 2022-09-02 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 14 - Louden-Biddeford IP - 1 | West Buxton | 3 | 2024-02-22 |  | EXECUTED
536 | 0 | 0 | 0 |  | 2020-08-19 | Newport | NEWPORT | 837D2 | Solar | 0 | 0 | [10 empty] | 2022-06-14 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 17 - Detroit Guilford Belfast - 2 | Detroit | 3 |  |  | EXECUTED-WITHDRAWN
537 | 0 | 0 | 0 |  | 2020-08-21 | Fryeburg | FRYEBURG | 415D2 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 03 - Kimball Rd-Lovell - 1 | Kimball Road/Lovell | 3 |  | 2023-04-22 | WITHDRAWN
538 | 0 | 0 | 0 |  | 2020-08-21 | Auburn | GREAT FALLS | 436D6 | Solar | 0 | 0 |  |  |  |  | 2020-12-04 | 2021-02-10 | 2022-03-02 | 2022-04-15 |  | 2021-04-02 | [10 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 05 - Lewiston Loop - 1 | Hotel Rd/Gulf/Middle St/Crowleys | 3 |  | 2022-07-22 | WITHDRAWN
539 | 0 | 0 | 0 |  | 2020-08-31 | Monson | MONSON | 834D2 | Solar | 0 | 0 | [10 empty] | 2022-06-16 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 17 - Detroit Guilford Belfast - 2 | Guilford | 3 |  |  | EXECUTED-WITHDRAWN
540 | 0 | 0 | 0 |  | 2020-09-04 | Dixfield | LUDDEN LANE | 461D1 | Solar | 975 | 0 |  |  |  |  | 2021-01-08 | 2021-06-22 | 2021-08-19 | 2021-09-29 |  |  | 2021-11-08 | 2023-09-01 | 2023-10-17 | 2023-12-22 | 2024-02-26 |  |  |  |  | Q4 2025 | Fully Executed Interconnection Agreement | No | 2024-07-18 | Cluster 08 - Sturtevant-Leeds-Livermore-Ludden-Riley - 1 | Ludden Lane | 3 | 2023-12-21 | Not Required | RE_QUEUED_FullEx
541 | 0 | 0 | 0 |  | 2020-09-08 | Sanford | SANFORD INDUSTRIAL PARK | 656D2 | Solar | 0 | 0 | [10 empty] | 2021-07-01 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 04 - Sanford-Quaker Hill - 1 | Sanford | 3 | 2022-06-27 |  | EXECUTED-WITHDRAWN
542 | 0 | 0 | 0 |  | 2020-09-10 | Solon | EMBDEN | 868D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 16 - Wyman Area - 1 | Embden | 3 |  | 2023-05-15 07:38 | WITHDRAWN
543 | 0 | 0 | 0 |  | 2020-09-11 | York | YORK BEACH | 676D2 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Bolt Hill | 0 |  |  | WITHDRAWN
544 | 0 | 0 | 0 |  | 2020-09-11 | Pittsfield | DETROIT | 812D2 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Detroit |  |  |  | WITHDRAWN
545 | 0 | 0 | 0 |  | 2020-09-11 | Dover-Foxcroft | DOVER | 815D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 17 - Detroit Guilford Belfast - 2 | Guilford | 3 |  | Not Required | WITHDRAWN
546 | 0 | 0 | 0 |  | 2020-09-15 | Lincolnville | CAMDEN | 214D4 | Solar | 0 | 0 | [10 empty] | 2021-05-17 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 09 - Midcoast - 1 | Meadow Road | 3 |  | 2023-12-15 | EXECUTED-WITHDRAWN
547 | 0 | 0 | 0 |  | 2020-09-17 | Topsham | TOPHAM OLD | 249D1 | Solar | 0 | 0 |  |  |  |  | 2020-10-22 | 2020-12-29 |  |  |  |  | 2021-07-09 |  | 2022-12-08 | [7 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 09 - Midcoast - 1 | Topsham | 3 | 2023-12-21 |  | EXECUTED-WITHDRAWN
548 | 0 | 0 | 0 |  | 2020-09-24 | Vassalboro | MCCOYS | 237D1 | Solar | 0 | 0 | [10 empty] | 2021-09-01 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 11 - Augusta E-Puddledock-Bowman St - 2 | Augusta E/Puddledock/Bowman St | 3 | 2024-05-28 |  | EXECUTED-WITHDRAWN
549 | 0 | 0 | 0 |  | 2020-09-24 | Waterville | SOUTH WATERVILLE | 855D2 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 12 - Winslow-County Rd-Lakewood - 2 | Winslow-County Rd | 3 | 2024-05-28 |  | WITHDRAWN
550 | 0 | 0 | 0 |  | 2020-09-28 | Sanford | SANFORD INDUSTRIAL PARK | 656D2 | Solar | 0 | 0 | [10 empty] | 2021-12-08 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 19 - Sanford-Quaker Hill - 2 | Sanford | 3 |  |  | EXECUTED-WITHDRAWN
551 | 0 | 0 | 0 |  | 2020-09-28 | Lebanon | LEBANON | 695D2 | Solar | 0 | 0 | [10 empty] | 2021-12-21 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 19 - Sanford-Quaker Hill - 2 | Sanford | 3 |  |  | EXECUTED-WITHDRAWN
552 | 0 | 0 | 0 |  | 2020-09-29 | Warren | WARREN | 253D1 | Solar | 0 | 0 | [10 empty] | 2021-06-30 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 09 - Midcoast - 1 | Highland/Park St | 3 |  | 2023-12-15 | EXECUTED-WITHDRAWN
553 | 0 | 0 | 0 |  | 2020-09-29 | Carmel | CARMEL | 808D2 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 17 - Detroit Guilford Belfast - 2 | Detroit | 3 |  |  | WITHDRAWN
554 | 0 | 0 | 0 |  | 2020-09-30 | Freeport | FREEPORT | 225D4 | Solar | 0 | 0 | [10 empty] | 2021-05-05 | [8 empty] | Q2 2021 | EXECUTED-WITHDRAWN | WITHDRAWN | 2025-01-25 | Cluster 15 - Greater Portland - 1 | Elm St | 3 | 2024-02-22 |  | RE_QUEUED_FullEx
555 | 0 | 0 | 0 |  | 2020-09-30 | Thomaston | PARK STREET | 239D7 | Solar | 999 | 0 |  |  |  |  | 2021-07-15 | 2021-09-21 |  |  |  |  | 2021-10-26 | 2023-01-06 | 2023-02-15 | 2023-05-30 | 2023-07-10 | 2023-11-01 | 2023-12-22 | 2024-02-08 | 2024-04-16 | Q1 2026 | Fully Executed Interconnection Agreement | No | 2024-07-12 | Cluster XX - Midcoast - TBD | Highland/Park St | 3 |  | Not Required | RE_QUEUED_FullEx
556 | 0 | 0 | 0 |  | 2020-10-01 | Skowhegan | WESTON HYDRO | 866D2 | Solar | 0 | 0 | [10 empty] | 2021-11-24 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 12 - Winslow-County Rd-Lakewood - 2 | Lakewood | 3 | 2024-05-28 |  | EXECUTED-WITHDRAWN
557 | 0 | 0 | 0 |  | 2020-10-01 | Rockport | MEADOW ROAD | 270D2 | Solar | 0 | 0 | [10 empty] | 2021-08-02 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 09 - Midcoast - 1 | Meadow Road | 3 |  | 2023-12-15 | EXECUTED-WITHDRAWN
558 | 0 | 0 | 0 |  | 2020-10-05 | Lisbon | LISBON FALLS | 232D1 | Solar | 0 | 0 | [10 empty] | 2021-06-10 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 05 - Lewiston Loop - 1 | Hotel Rd/Gulf/Middle St/Crowleys | 3 | 2022-07-19 |  | EXECUTED-WITHDRAWN
559 | 0 | 0 | 0 |  | 2020-10-06 | Chelsea | CONY ROAD | 216D2 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Augusta E/Puddledock/Bowman St |  |  |  | WITHDRAWN
560 | 0 | 0 | 0 |  | 2020-10-06 | Raymond | RAYMOND 115 KV | 445D1 | Solar | 4990 | 0 |  |  |  |  | 2021-02-08 | 2021-06-29 |  |  |  |  | 2021-07-01 | 2023-05-03 |  | 2024-05-15 | 2024-07-19 |  |  |  |  | Q4 2025 | Fully Executed Interconnection Agreement | No | 2022-11-15 | Cluster 07 - Raymond - 1 | Raymond | 3 | 2023-12-21 |  | RE_QUEUED_FullEx
561 | 0 | 0 | 478 |  | 2020-10-13 | Augusta | AUGUSTA K5 | 200D2 | Solar | 1900 | 0 |  |  |  |  | 2020-12-14 | 2021-02-19 |  |  |  |  | 2021-07-13 | 2023-08-14 | 2023-09-28 | [6 empty] | Q2 2025 | Fully Executed Interconnection Agreement | No | 2023-04-11 | Cluster 11 - Augusta E-Puddledock-Bowman St - 2 | Augusta E/Puddledock/Bowman St | 3 | 2024-05-28 |  | RE_QUEUED_FullEx
562 | 0 | 0 | 0 |  | 2020-10-15 | Lisbon | LISBON | 231D1 | Solar/Battery | 0 | 0 | [10 empty] | 2021-10-14 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 05 - Lewiston Loop - 1 | Hotel Rd/Gulf/Middle St/Crowleys | 3 | 2022-07-19 |  | EXECUTED
563 | 0 | 0 | 0 |  | 2020-10-15 | Hartland | HARTLAND | 824D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Hartland |  |  |  | WITHDRAWN
564 | 0 | 0 | 0 |  | 2020-10-15 | Windsor | COOPERS MILLS ROAD | 230D2 | Solar/Battery | 0 | 0 | [10 empty] | 2022-05-23 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster XX - Midcoast - TBD | Coopers Mills | 3 |  |  | EXECUTED-WITHDRAWN
565 | 0 | 0 | 0 |  | 2020-10-15 | Windham | SWETT ROAD | 682D1 | Solar | 0 | 0 | [10 empty] | 2021-11-11 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 07 - Raymond - 1 | Raymond | 3 | 2023-12-21 |  | EXECUTED-WITHDRAWN
566 | 0 | 0 | 0 |  | 2020-10-15 | Dixfield | LUDDEN LANE | 461D1 | Solar/Battery | 2500 | 0 |  |  |  |  | 2020-11-23 | 2020-02-01 |  |  |  |  | 2021-03-01 | [8 empty] | Q4 2021 | Fully Executed Interconnection Agreement | Yes | 2021-11-04 | Cluster 08 - Sturtevant-Leeds-Livermore-Ludden-Riley - 1 | Ludden Lane | NC | 2021-07-15 |  | #REF!
567 | 0 | 0 | 0 |  | 2020-10-19 | Sanford | HIGH STREET | 626D5 | Solar | 0 | 0 | [10 empty] | 2021-09-23 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 04 - Sanford-Quaker Hill - 1 | Sanford | 3 | 2022-06-27 |  | EXECUTED-WITHDRAWN
568 | 0 | 0 | 0 |  | 2020-10-19 | South Berwick | SOUTH BERWICK | 663D2 | Solar | 0 | 0 | [10 empty] | 2021-10-22 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 04 - Sanford-Quaker Hill - 1 | Quaker Hill | 3 | 2022-06-27 |  | EXECUTED-WITHDRAWN
569 | 0 | 0 | 0 |  | 2020-10-19 | Pownal | GRAY | 416D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Elm St |  |  |  | WITHDRAWN
570 | 0 | 0 | 0 |  | 2020-10-21 | Strong | PHILLIPS/STRONG | 841D1 | Solar | 0 | 0 | [10 empty] | 2021-11-24 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 08 - Sturtevant-Leeds-Livermore-Ludden-Riley - 1 | Sturtevant | 3 | 2023-12-21 |  | EXECUTED-WITHDRAWN
571 | 0 | 0 | 0 |  | 2020-10-21 | Strong | PHILLIPS/STRONG | 841D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Sturtevant/ Leeds/ Livermore/ Ludden/ Riley_TBD | Sturtevant | 3 |  |  | WITHDRAWN
572 | 0 | 0 | 0 |  | 2020-10-29 | Monson | MONSON | 834D1 | Solar | 0 | 0 | [10 empty] | 2023-03-29 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 17 - Detroit Guilford Belfast - 2 | Guilford | 3 |  | Not Required | EXECUTED-WITHDRAWN
573 | 0 | 0 | 0 |  | 2020-10-30 | Searsmont | BELFAST WEST SIDE | 803D6 | Solar | 0 | 0 | [10 empty] | 2022-12-12 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 17 - Detroit Guilford Belfast - 2 | Belfast | 3 |  | Not Required | EXECUTED-WITHDRAWN
574 | 0 | 0 | 0 |  | 2020-11-03 | Pittsfield | DETROIT | 812D1 | Hydro | 0 | 0 | [10 empty] | 2021-08-26 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 06 - Detroit-Guilford-Belfast - 1 | Detroit | 3 |  | Not Required | EXECUTED-WITHDRAWN
575 | 0 | 0 | 0 |  | 2020-11-03 | New Sharon | FARMINGTON FALLS | 818D1 | Solar | 0 | 0 | [10 empty] | 2021-10-05 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 08 - Sturtevant-Leeds-Livermore-Ludden-Riley - 1 | Sturtevant | 3 |  | 2023-12-15 | EXECUTED-WITHDRAWN
576 | 0 | 0 | 0 |  | 2020-11-06 | Rumford | RUMFORD | 447D2 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 10 - Roxbury-Rumford-Woodstock - 1 | Rumford | 3 |  | 2023-12-15 | WITHDRAWN
577 | 0 | 0 | 481 |  | 2020-11-12 | Oakland | COUNTY RD (RICE RIPS) | 873D1 | Solar/Battery | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Winslow/ County Rd/ Lakewood - TBD | Winslow-County Rd | 3 |  |  | RE_QUEUED
578 | 0 | 0 | 0 |  | 2020-11-12 | Windham | SWETT ROAD | 682D1 | Solar | 0 | 0 | [10 empty] | 2023-07-05 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster XX - Raymond - TBD | Raymond | 3 |  |  | EXECUTED-WITHDRAWN
579 | 0 | 0 | 0 |  | 2020-11-12 | Bridgton | WEST BRIDGTON | 458D1 | Solar/Battery | 0 | 0 | [10 empty] | 2021-07-20 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 03 - Kimball Rd-Lovell - 1 | Kimball Road/Lovell | 3 |  | 2023-04-22 | EXECUTED-WITHDRAWN
580 | 0 | 0 | 0 |  | 2020-11-12 | Solon | EMBDEN | 868D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Embden |  |  |  | WITHDRAWN
581 | 0 | 0 | 0 |  | 2020-11-12 | Jay | RILEY | 449D2 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 08 - Sturtevant-Leeds-Livermore-Ludden-Riley - 1 | Riley | 3 |  | 2023-12-15 | WITHDRAWN
582 | 0 | 0 | 0 |  | 2020-11-12 | South Portland | PLEASANT HILL | 644D2 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 15 - Greater Portland - 1 | Pleasant Hill | 3 |  | 2024-03-19 | WITHDRAWN
583 | 0 | 0 | 0 |  | 2020-11-12 | Eliot | ELIOT | 687D1 | Solar | 0 | 0 | [10 empty] | 2021-09-09 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 19 - Sanford-Quaker Hill - 2 | Bolt Hill | NC | 2021-07-15 |  | EXECUTED-WITHDRAWN
584 | 0 | 0 | 0 |  | 2020-11-12 | Sebago | BALDWIN | 691D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 13 - Kimball Rd-Lovell - 2 | Kimball Road/Lovell | 3 |  |  | WITHDRAWN
585 | 0 | 0 | 0 |  | 2020-11-13 | Rockport | CAMDEN | 214D3 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Meadow Road |  |  |  | WITHDRAWN
586 | 0 | 0 | 0 |  | 2020-11-13 | Standish | SHAWS MILL ROAD | 660D2 | Solar | 0 | 0 | [10 empty] | 2021-10-22 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 07 - Raymond - 1 | Raymond | 3 | 2023-12-21 |  | EXECUTED
587 | 0 | 0 | 525 |  | 2020-11-13 | Livermore | LEEDS | 471D1 | Solar | 4998 | 0 |  |  |  |  | 2022-12-07 | 2023-02-07 |  |  |  |  | 2023-03-30 | 2025-01-22 | 2025-03-25 | [6 empty] | Q3 2021 | Fully Executed Interconnection Agreement | No |  | Cluster XX - Sturtevant/ Leeds/ Livermore/ Ludden/ Riley_TBD | Leeds | 3 |  |  | RE_QUEUED_FullEx
588 | 0 | 0 | 0 |  | 2020-11-19 | Berwick | BASSETT | 602D2 | Solar | 1999 | 0 |  |  |  |  | 2021-03-03 | 2021-06-25 | 2021-07-23 | 2021-09-03 |  |  | 2021-09-22 | 2022-12-19 | 2023-02-01 | [7 empty] | Fully Executed Interconnection Agreement | No |  | Cluster 19 - Sanford-Quaker Hill - 2 | Quaker Hill | 3 |  |  | RE_QUEUED_FullEx
589 | 0 | 0 | 0 |  | 2020-11-19 | Parkman | GUILFORD | 821D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 17 - Detroit Guilford Belfast - 2 | Guilford | 3 |  |  | RE_QUEUED
590 | 0 | 0 | 0 |  | 2020-11-24 | Carmel | CARMEL | 808D1 | Solar/Battery | 0 | 0 | [10 empty] | 2023-01-05 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 17 - Detroit Guilford Belfast - 2 | Detroit | 3 |  | Not Required | EXECUTED-WITHDRAWN
591 | 0 | 0 | 0 |  | 2020-11-24 | Eliot | ELIOT | 687D1 | Solar | 0 | 0 | [10 empty] | 2021-12-08 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 19 - Sanford-Quaker Hill - 2 | Bolt Hill | 3 |  |  | EXECUTED-WITHDRAWN
592 | 0 | 0 | 0 |  | 2020-11-30 | Fairfield | FAIRFIELD | 817D3 | Solar/DC BESS | 0 | 0 | [10 empty] | 2021-10-14 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 12 - Winslow-County Rd-Lakewood - 2 | Winslow-County Rd | 3 | 2024-05-28 |  | EXECUTED-WITHDRAWN
593 | 0 | 0 | 0 |  | 2020-12-08 | Parkman | GUILFORD | 821D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 17 - Detroit Guilford Belfast - 2 | Guilford | 3 |  |  | WITHDRAWN
594 | 0 | 0 | 0 |  | 2020-12-08 | Biddeford | MAY STREET | 634D1 | Solar | 0 | 0 | [10 empty] | 2021-06-07 | [8 empty] | Q3 2025 | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 14 - Louden-Biddeford IP - 1 | Biddeford IP | 3 | 2024-02-22 |  | RE_QUEUED_FullEx
595 | 0 | 0 | 0 |  | 2020-12-08 | Chelsea | BOWMAN STREET | 263D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Augusta E-Puddledock-Bowman St - TBD | Augusta E/Puddledock/Bowman St | 3 |  |  | WITHDRAWN
596 | 0 | 0 | 0 |  | 2020-12-08 | Cornish | HIRAM TAP | 692D1 | Solar | 0 | 0 | [10 empty] | 2021-08-18 | [8 empty] | Q2 2022 | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 13 - Kimball Rd-Lovell - 2 | Kimball Road/Lovell | 3 |  |  | RE_QUEUED_STUDY
597 | 0 | 0 | 0 |  | 2020-12-09 | Livermore Falls | LIVERMORE FALLS | 428D2 | Solar | 0 | 0 | [10 empty] | 2022-07-14 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster XX - Sturtevant/ Leeds/ Livermore/ Ludden/ Riley_TBD | Livermore Falls | 3 |  |  | WITHDRAWN
598 | 0 | 0 | 0 |  | 2020-12-09 | Belgrade | NORTH AUGUSTA | 272D6 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Augusta E-Puddledock-Bowman St - TBD | North Augusta | 3 |  |  | WITHDRAWN
599 | 0 | 0 | 0 |  | 2020-12-09 | Lewiston | CHALLENGER 12 KV | 421D2 | Solar | 1975 | 0 |  |  |  |  | 2021-01-12 | 2021-06-09 |  |  |  |  | 2021-07-07 | 2024-01-22 | 2024-03-22 | [6 empty] | Q1 2022 | Fully Executed Interconnection Agreement | Yes | 2023-11-09 | Cluster 05 - Lewiston Loop - 1 | Challenger Dr | 3 | 2022-07-19 |  | RE_QUEUED_FullEx
600 | 0 | 0 | 0 |  | 2020-12-09 | Westbrook | PRIDES CORNER | 647D1 | Solar | 0 | 0 | [10 empty] | 2021-07-08 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 15 - Greater Portland - 1 | Moshers/Prides Corner | 3 | 2024-02-22 |  | EXECUTED
601 | 0 | 0 | 0 |  | 2020-12-09 | Freeport | FREEPORT | 225D3 | Solar | 0 | 0 | [10 empty] | 2021-10-20 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 15 - Greater Portland - 1 | Elm St | 3 |  | 2024-03-19 | EXECUTED-WITHDRAWN
602 | 0 | 0 | 0 |  | 2020-12-14 | Andover | ANDOVER | 400D1 | Solar | 0 | 0 | [10 empty] | 2021-09-16 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 10 - Roxbury-Rumford-Woodstock - 1 | Roxbury | 3 |  | 2023-12-15 | EXECUTED-WITHDRAWN
603 | 0 | 0 | 0 |  | 2020-12-14 | Alna | SHEEPSCOT | 241D1 | Solar | 2875 | 0 |  |  |  |  | 2021-02-04 | 2021-05-12 |  |  |  |  | 2021-07-28 | [9 empty] | Fully Executed Interconnection Agreement | Yes | 2023-10-04 | Cluster 09 - Midcoast - 1 | Mason | 3 | 2023-12-21 |  | EXECUTED
604 | 0 | 0 | 0 |  | 2020-12-14 | Mechanic Falls | MECHANIC FALLS | 431D1 | Solar | 0 | 0 | [10 empty] | 2021-01-18 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 18 - Lewiston Loop - 2 | Norway | 3 |  |  | EXECUTED-WITHDRAWN
605 | 0 | 0 | 0 |  | 2020-12-15 | Wilton | EAST WILTON | 816D1 | Solar | 0 | 0 | [10 empty] | 2021-08-02 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 08 - Sturtevant-Leeds-Livermore-Ludden-Riley - 1 | Sturtevant | 3 | 2023-12-21 |  | EXECUTED-WITHDRAWN
606 | 0 | 0 | 0 |  | 2020-12-15 | Rumford | RUMFORD | 447D1 | Solar | 0 | 0 | [10 empty] | 2021-11-26 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster XX - Woodstock/ Roxbury/ Rumford - TBD | Rumford | 3 |  |  | EXECUTED-WITHDRAWN
607 | 0 | 0 | 0 |  | 2020-12-15 | Winthrop | WINTHROP | 256D2 | Solar | 0 | 0 |  |  |  |  | 2021-07-28 | 2021-09-22 |  |  |  |  | 2021-11-24 | [9 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Augusta E-Puddledock-Bowman St - TBD | Augusta E/Puddledock/Bowman St | 3 |  |  | EXECUTED-WITHDRAWN
608 | 0 | 0 | 0 |  | 2020-12-15 | Wiscasset | MESSINA | 238D1 | Solar | 975 | 0 |  |  |  |  | 2021-01-21 | 2021-06-17 | 2023-12-27 | 2024-02-08 |  | 2023-09-11 | 2021-08-02 | 2023-04-26 | 2023-06-07 | [6 empty] | Q4 2025 | Fully Executed Interconnection Agreement | No | 2024-09-09 | Cluster 09 - Midcoast - 1 | Mason | 3 | 2023-12-21 | Not Required | RE_QUEUED_FullEx
609 | 0 | 0 | 0 |  | 2020-12-15 | Waldoboro | WALDOBORO | 252D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 09 - Midcoast - 1 | Highland/Park St | 3 |  | 2023-12-15 | WITHDRAWN
610 | 0 | 0 | 0 |  | 2020-12-17 | Gorham | FORT HILL | 624D2 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Raymond - TBD | Raymond | 3 |  |  | WITHDRAWN
611 | 0 | 0 | 0 |  | 2020-12-17 | Turner | DEER RIPS | 412D3 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 18 - Lewiston Loop - 2 | Hotel Rd/Gulf/Middle St/Crowleys | 3 |  |  | WITHDRAWN
612 | 0 | 0 | 0 |  | 2020-12-17 | Farmington | STURTEVANT | 858D4 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Sturtevant/ Leeds/ Livermore/ Ludden/ Riley_TBD | Sturtevant | 3 |  |  | RE_QUEUED
613 | 0 | 0 | 0 |  | 2020-12-17 | North Berwick | PRATT & WHITNEY | 661D1 | Solar | 0 | 0 | [10 empty] | 2021-10-12 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 04 - Sanford-Quaker Hill - 1 | Pratt & Whitney | 3 | 2022-06-27 |  | EXECUTED-WITHDRAWN
614 | 0 | 0 | 0 |  | 2020-12-21 | Rockland | PARK STREET | 239D6 | Solar/DC BESS | 0 | 0 |  |  |  |  | 2021-12-13 | 2022-02-17 | [14 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Midcoast - TBD | Highland/Park St | 3 |  |  | WITHDRAWN
615 | 0 | 0 | 0 |  | 2020-12-21 | Hartland | HARTLAND | 824D1 | Solar/DC BESS | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Hartland |  |  |  | WITHDRAWN
616 | 0 | 0 | 0 |  | 2020-12-21 | Penobscot | BUCKSPORT | 806D2 | Solar/DC BESS | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Bucksport |  |  |  | WITHDRAWN
617 | 0 | 0 | 0 |  | 2020-12-21 | Lincolnville | LINCOLNVILLE | 800D1 | Solar | 0 | 0 | [10 empty] | 2021-01-18 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 09 - Midcoast - 1 | Lincolnville | 3 | 2023-12-21 |  | EXECUTED
618 | 0 | 0 | 0 |  | 2020-12-21 | Pittsfield | DETROIT | 812D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 17 - Detroit Guilford Belfast - 2 | Detroit | 3 |  | Not Required | WITHDRAWN
619 | 0 | 0 | 0 |  | 2020-12-21 | Westbrook | WESTBROOK | 674D2 | Solar | 0 | 0 | [10 empty] | 2022-05-26 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 15 - Greater Portland - 1 | Moshers/Prides Corner | 3 | 2024-02-22 |  | EXECUTED
620 | 0 |  | 600 |  | 2020-12-21 | Westbrook | PRIDES CORNER | 647D3 | Solar | 999 | 0 |  |  |  |  | 2022-09-23 | 2022-12-01 | 2023-02-09 | 2023-03-21 |  |  | 2023-05-01 | 2024-09-20 | 2024-11-26 | [6 empty] | Q4 2025 | Fully Executed Interconnection Agreement | No | 2023-10-13 | Cluster XX - Greater Portland - TBD | Moshers/Prides Corner | 3 |  | Not Required | RE_QUEUED_Fullex
621 | 0 | 0 | 0 |  | 2020-12-21 | New Vineyard | NEW VINEYARD | 836D1 | Solar | 0 | 0 | [10 empty] | 2021-10-12 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 08 - Sturtevant-Leeds-Livermore-Ludden-Riley - 1 | Sturtevant | 3 |  | 2023-12-15 | EXECUTED-WITHDRAWN
622 | 0 | 0 | 0 |  | 2020-12-23 | Waldoboro | MANKTOWN ROAD | 234D1 | Solar | 0 | 0 | [10 empty] | 2021-10-28 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 09 - Midcoast - 1 | Highland/Park St | 3 |  | 2023-12-15 | EXECUTED-WITHDRAWN
623 | 0 | 0 | 0 |  | 2020-12-29 | Livermore | LIVERMORE FALLS | 428D2 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Sturtevant/ Leeds/ Livermore/ Ludden/ Riley_TBD | Livermore Falls | 3 |  |  | WITHDRAWN
624 | 0 | 0 | 0 |  | 2020-12-29 | West Baldwin | HIRAM HYDRO | 419D1 | Solar | 0 | 0 | [10 empty] | 2021-12-03 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 13 - Kimball Rd-Lovell - 2 | Kimball Road/Lovell | 3 |  |  | EXECUTED
625 | 0 | 0 | 0 |  | 2021-01-05 | Belfast | BELFAST WEST SIDE | 803D6 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 17 - Detroit Guilford Belfast - 2 | Belfast | 3 |  |  | WITHDRAWN
626 | 0 | 0 | 0 |  | 2021-01-07 | Scarborough | DUNSTAN | 617D3 | Solar | 1950 | 0 |  |  |  |  | 2021-02-17 | 2021-06-29 |  |  |  |  | 2021-07-07 | 2023-08-10 | 2023-11-02 | [7 empty] | Fully Executed Interconnection Agreement | Yes | 2023-06-06 | Cluster 14 - Louden-Biddeford IP - 1 | Vallee Lane | NC | 2021-11-08 |  | RE_QUEUED_FullEx
627 | 0 | 0 | 0 |  | 2021-01-07 | Chelsea | CONY ROAD | 216D2 | Solar | 0 | 0 | [10 empty] | 2021-10-26 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 11 - Augusta E-Puddledock-Bowman St - 2 | Augusta E/Puddledock/Bowman St | 3 | 2024-05-28 |  | EXECUTED
628 | 0 | 0 | 0 |  | 2021-01-13 | Warren | THOMASTON CREEK | 246D3 | Solar | 0 | 0 | [10 empty] | 2022-07-14 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster XX - Midcoast - TBD | Highland/Park St | 3 |  |  | EXECUTED
629 | 0 | 0 | 0 |  | 2021-01-13 | Bridgton | BRIDGTON | 406D1 | Solar | 0 | 0 | [10 empty] | 2021-10-12 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 13 - Kimball Rd-Lovell - 2 | Kimball Road/Lovell | 3 |  |  | EXECUTED-WITHDRAWN
630 | 0 | 0 | 0 |  | 2021-01-25 | West Bath | BATH 34 | 261D3 | Solar | 0 | 0 | [10 empty] | 2021-10-28 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 09 - Midcoast - 1 | Bath | 3 | 2023-12-21 |  | EXECUTED-WITHDRAWN
631 | 0 | 0 | 0 | RQP-1 | 2021-01-25 | Scarborough | DUNSTAN | 617D2 | Solar | 999 | 0 |  |  |  |  | 2021-08-20 | 2021-10-26 |  |  |  |  | 2021-11-11 | 2024-09-10 | 2024-11-11 | [6 empty] | Q3 2026 | Fully Executed Interconnection Agreement | No | 2022-11-08 | Cluster 14 - Louden-Biddeford IP - 1 | Vallee Lane | 3 | 2024-02-22
632 | 0 | 0 | 0 |  | 2021-01-26 | Starks | ANSON | 801D1 | Solar | 0 | 0 | [10 empty] | 2021-09-01 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 12 - Winslow-County Rd-Lakewood - 2 | Lakewood | 3 | 2024-05-28 |  | RE_QUEUED_FullEx
633 | 0 | 0 | 0 |  | 2021-01-27 | Sanford | SANFORD SWITCH | 657D3 | Solar | 0 | 0 | [10 empty] | 2021-07-20 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 19 - Sanford-Quaker Hill - 2 | Sanford | 3 |  |  | EXECUTED-WITHDRAWN
634 | 0 | 0 | 0 |  | 2021-01-27 | Richmond | RICHMOND | 240D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Augusta E/Puddledock/Bowman St |  |  |  | WITHDRAWN
635 | 0 | 0 | 0 |  | 2021-01-29 | Avon | PHILLIPS/STRONG | 841D1 | Solar | 0 | 0 |  |  |  |  | 2022-03-07 | 2022-05-02 | 2022-07-15 |  |  |  |  | 2023-01-13 | [8 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Sturtevant/ Leeds/ Livermore/ Ludden/ Riley_TBD | Sturtevant | 3 |  | Not Required | WITHDRAWN
636 | 0 | 0 | 0 |  | 2021-02-02 | Windham | PRIDES CORNER | 647D2 | Solar | 0 | 0 |  |  |  |  | 2023-06-15 | 2023-08-23 | [14 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Greater Portland - TBD | Moshers/Prides Corner | 3 |  |  | WITHDRAWN
637 | 0 | 0 | 0 |  | 2021-02-02 | Cape Elizabeth | CAPE ELIZABETH | 613D1 | Solar | 900 | 0 |  |  |  |  | 2021-03-09 | 2021-06-29 |  |  |  |  | 2021-07-29 | [8 empty] | Q4 2025 | Fully Executed Interconnection Agreement | No | 2023-01-18 | Cluster 15 - Greater Portland - 1 | Pleasant Hill | 3 |  | Not Required | EXECUTED
638 | 0 | 0 | 0 |  | 2021-02-03 | Newport | NEWPORT | 837D1 | Solar | 0 | 0 |  |  |  |  | 2022-08-11 | 2022-10-13 | 2022-11-30 | 2023-01-12 |  |  |  | 2024-03-21 | 2024-05-17 | [7 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 17 - Detroit Guilford Belfast - 2 | Detroit | 3 |  |  | WITHDRAWN
639 | 0 | 0 | 0 |  | 2021-02-11 | Windham | NORTH WINDHAM | 639D2 | Solar | 0 | 0 | [10 empty] | 2021-10-20 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster XX - Raymond - TBD | Raymond | 3 |  |  | EXECUTED-WITHDRAWN
640 | 0 | 0 | 0 |  | 2021-02-12 | Durham | LISBON FALLS | 232D2 | Solar | 1990 | 0 |  |  |  |  | 2021-07-28 | 2021-09-29 | 2021-10-28 | 2021-12-10 |  |  | 2022-01-13 | 2023-05-04 | 2023-06-16 | [6 empty] | Q4 2022 | Fully Executed Interconnection Agreement | No |  | Cluster 18 - Lewiston Loop - 2 | Hotel Rd/Gulf/Middle St/Crowleys | 3 |  |  | RE_QUEUED_FullEx
641 | 0 | 0 | 0 |  | 2021-02-15 | Searsport | SEARSPORT | 850D2 | Solar | 0 | 0 | [10 empty] | 2021-12-21 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 17 - Detroit Guilford Belfast - 2 | Belfast | 3 |  |  | EXECUTED-WITHDRAWN
642 | 0 | 0 | 0 |  | 2021-02-15 | Newcastle | DAMARISCOTTA MILLS | 219D2 | Solar | 0 | 0 | [10 empty] | 2021-11-29 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 09 - Midcoast - 1 | Newcastle | 3 | 2023-12-21 |  | EXECUTED-WITHDRAWN
643 | 0 | 0 | 0 |  | 2021-02-15 | Topsham | LISBON FALLS | 232D2 | Solar | 0 | 0 |  |  |  |  | 2022-02-02 | 2022-04-14 |  |  |  | 2022-10-07 | 2022-11-17 | 2023-08-11 | 2023-09-26 | [7 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 18 - Lewiston Loop - 2 | Hotel Rd/Gulf/Middle St/Crowleys | 3 |  | Not Required | RE_QUEUED_FullEx
644 | 0 | 0 | 0 |  | 2021-02-16 | West Bath | BATH 34 | 261D3 | Solar | 0 | 0 |  |  |  |  | 2022-02-02 | 2022-04-14 | 2022-05-31 | 2022-07-11 |  |  | 2022-07-29 | 2023-10-24 | 2023-12-12 | 2024-08-08 | 2024-09-27 |  |  |  |  | Q4 2026 | WITHDRAWN | WITHDRAWN |  | Cluster XX - Midcoast - TBD | Bath | 3 |  | Not Required | RE_QUEUED_FullEx
645 | 0 | 0 | 0 |  | 2021-02-18 | Naples | NAPLES TAP | 469D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Raymond |  |  |  | WITHDRAWN
646 | 0 | 0 | 0 |  | 2021-02-18 | Skowhegan | SKOWHEGAN SOUTH SIDE | 854D2 | Solar | 0 | 0 | [10 empty] | 2022-08-10 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 12 - Winslow-County Rd-Lakewood - 2 | Lakewood | 3 | 2024-05-28 |  | EXECUTED-WITHDRAWN
647 | 0 | 0 | 0 |  | 2021-02-18 | Farmington | STURTEVANT | 858D3 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Sturtevant/ Leeds/ Livermore/ Ludden/ Riley_TBD | Sturtevant | 3 |  |  | RE_QUEUED
648 | 0 | 0 | 0 |  | 2021-02-24 | Winthrop | MANCHESTER | 233D2 | Solar | 0 | 0 | [10 empty] | 2022-07-06 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 11 - Augusta E-Puddledock-Bowman St - 2 | Augusta E/Puddledock/Bowman St | 3 |  | Not Required | RE_QUEUED_FullEx
649 | 0 | 0 | 0 |  | 2021-03-02 | Lewiston | SABATTUS | 450D2 | Solar | 0 | 0 | [10 empty] | 2022-01-31 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 18 - Lewiston Loop - 2 | Hotel Rd/Gulf/Middle St/Crowleys | 3 |  |  | RE_QUEUED_FullEx
650 | 0 | 0 | 0 |  | 2021-03-10 | Waterford | PAPOOSE POND | 438D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 13 - Kimball Rd-Lovell - 2 | Kimball Road/Lovell | 3 |  |  | WITHDRAWN
651 | 0 | 0 | 0 |  | 2021-03-15 | Kittery | KITTERY | 688D1 | Solar | 0 | 0 | [10 empty] | 2021-08-16 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 19 - Sanford-Quaker Hill - 2 | Bolt Hill | NC | 2021-11-23 |  | EXECUTED-WITHDRAWN
652 | 0 | 0 | 390 |  | 2021-03-24 | Bucksport | BUCKSPORT | 806D1 | Solar/Battery | 1990 | 0 |  |  |  |  | 2021-05-04 | 2021-07-12 | 2021-08-19 | 2021-10-01 |  |  | 2021-12-07 | 2023-03-02 | 2023-04-12 | [7 empty] | Fully Executed Interconnection Agreement | Yes | 2023-05-25 | Cluster 06 - Detroit-Guilford-Belfast - 1 | Bucksport | 3 | 2023-05-31 |  | RE_QUEUED_FullEx
653 | 0 | 0 | 0 |  | 2021-03-26 | Winthrop | WINTHROP | 256D2 | Solar | 975 | 0 |  |  |  |  | 2022-01-21 | 2022-03-04 |  |  |  | 2022-10-03 | 2022-11-21 | 2024-02-28 | 2024-04-29 | [6 empty] | Q3 2025 | Fully Executed Interconnection Agreement | No | 2024-10-04 | Cluster XX - Augusta E-Puddledock-Bowman St - TBD | Augusta E/Puddledock/Bowman St | 3 |  | Not Required | RE_QUEUED_FullEx
654 | 0 | 0 | 0 |  | 2021-03-26 | Roxbury | RUMFORD | 447D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Woodstock/ Roxbury/ Rumford - TBD | Rumford | 3 |  |  | WITHDRAWN
655 | 0 | 0 | 0 |  | 2021-03-29 | Orland | BUCKSPORT | 806D1 | Solar/Battery | 0 | 0 |  |  |  |  | 2022-02-04 | 2022-04-14 | [14 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 17 - Detroit Guilford Belfast - 2 | Bucksport | 3 |  |  | WITHDRAWN
656 | 0 | 0 | 0 |  | 2021-03-30 | Naples | RAYMOND 115 KV | 445D2 | Solar | 0 | 0 | [10 empty] | 2021-11-05 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster XX - Raymond - TBD | Raymond | 3 |  |  | EXECUTED-WITHDRAWN
657 | 0 | 2 - DEXT | 0 | RQP-2 | 2021-04-02 | Dexter | DEXTER | 813D3 | Solar/Battery | 1990 | 0 |  |  |  |  | 2021-11-23 | 2022-01-28 | 2022-03-30 | 2022-05-11 |  |  | 2022-07-06 | 2025-04-16 | 2025-06-18 | [7 empty] | Fully Executed Interconnection Agreement | No |  | Cluster 17 - Detroit Guilford Belfast - 2 | Guilford | 3 |  |  | RE_QUEUED_FullEx
658 | 0 | 0 | 0 |  | 2021-04-02 | South Berwick | SOUTH BERWICK | 663D2 | Solar | 0 | 0 |  |  |  |  | 2022-01-04 | 2022-03-11 | 2022-05-25 | 2022-07-15 |  |  | 2022-07-25 | 2023-04-20 | 2023-06-05 | 2023-07-21 | 2023-09-01 | 2023-12-22 | 2024-02-29 |  |  | Q3 2025 | WITHDRAWN | WITHDRAWN | 2023-11-27 | Cluster 19 - Sanford-Quaker Hill - 2 | Quaker Hill | 3 |  | Not Required | RE_QUEUED_FullEx
659 | 0 | 0 | 0 |  | 2021-04-12 | Monmouth | MONMOUTH | 457D2 | Solar/Battery | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Monmouth |  |  |  | WITHDRAWN
660 | 0 | 0 | 0 |  | 2021-04-15 | Brunswick | COOKS CORNER | 217D3 | Solar | 0 | 0 | [10 empty] | 2021-08-10 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster XX - Midcoast - TBD | Topsham | 3 |  |  | EXECUTED-WITHDRAWN
661 | 0 | 0 | 0 |  | 2021-04-22 | Sangerville | GUILFORD | 821D3 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 17 - Detroit Guilford Belfast - 2 | Guilford | 3 |  |  | RE_QUEUED
662 | 0 | 0 | 0 |  | 2021-04-22 | Bath | BATH NORTH END | 206D1 | Solar | 0 | 0 |  |  |  |  | 2021-06-16 | 2021-08-16 |  |  |  | 2022-01-06 | 2022-06-03 | [9 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Midcoast - TBD | Bath | 3 |  |  | EXECUTED
663 | 0 | 0 | 0 |  | 2021-04-22 | Skowhegan | SKOWHEGAN SOUTH SIDE | 854D2 | Solar | 0 | 0 |  |  |  |  | 2022-09-09 | 2022-11-08 |  |  |  | 2023-05-26 | [10 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Winslow/ County Rd/ Lakewood - TBD | Lakewood | 3 |  |  | WITHDRAWN
664 | 0 | 0 | 0 |  | 2021-04-30 | Bath | BATH 34 | 261D3 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Midcoast - TBD | Bath | 3 |  |  | WITHDRAWN
665 | 0 | 0 | 0 |  | 2021-04-30 | Raymond | RAYMOND 34 KV | 444D1 | Solar | 0 | 0 | [10 empty] | 2021-09-01 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster XX - Raymond - TBD | Raymond | 3 |  |  | EXECUTED-WITHDRAWN
666 | 0 | 0 | 0 |  | 2021-04-30 | Casco | MOSHERS | 635D2 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Moshers/Prides Corner |  |  |  | WITHDRAWN
667 | 0 | 0 | 0 |  | 2021-04-30 | Casco | NORTH WINDHAM | 639D2 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Raymond |  |  |  | WITHDRAWN
668 | 0 | 0 | 0 |  | 2021-04-30 | Casco | SAND ROAD TAP | 470D1 | Solar | 0 | 0 | [10 empty] | 2021-12-10 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster XX - Raymond - TBD | Raymond | 3 |  |  | EXECUTED-WITHDRAWN
669 | 0 | 0 | 648 |  | 2021-05-25 | Manchester | MANCHESTER | 233D1 | Solar | 975 | 0 |  |  |  |  | 2022-09-15 | 2022-11-21 |  |  |  |  | 2025-01-08 | 2024-10-18 | 2024-12-16 | [7 empty] | Fully Executed Interconnection Agreement | No | 2025-05-29 | Cluster XX - Augusta E-Puddledock-Bowman St - TBD | Augusta E/Puddledock/Bowman St | 3 |  | Not Required | RE_QUEUED
670 | 0 | 0 | 0 |  | 2021-05-28 | Thorndike | THORNDIKE TAP | 857D1 | Solar | 0 | 0 |  |  |  |  | 2021-07-28 | 2021-10-12 | 2021-12-02 | 2022-01-18 |  | 2022-04-22 | 2022-07-08 | [9 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 17 - Detroit Guilford Belfast - 2 | Belfast | 3 |  |  | EXECUTED
671 | 0 | 0 | 0 |  | 2021-05-28 | Richmond | RICHMOND | 240D1 | Solar | 0 | 0 | [10 empty] | 2022-02-04 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster XX - Augusta E-Puddledock-Bowman St - TBD | Augusta E/Puddledock/Bowman St | 3 |  |  | EXECUTED-WITHDRAWN
672 | 0 | 0 | 0 |  | 2021-06-21 | Newport | NEWPORT | 837D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 17 - Detroit Guilford Belfast - 2 | Detroit | 3 |  |  | WITHDRAWN
673 | 0 | 0 | 0 |  | 2021-06-21 | Gorham | MOSHERS | 635D2 | Hydro | 3990 | 0 |  |  |  |  | 2021-08-13 | 2021-10-19 |  |  |  |  | 2021-12-08 | [9 empty] | Fully Executed Interconnection Agreement | Yes | 2024-08-02 | Cluster 15 - Greater Portland - 1 | Moshers/Prides Corner | 3 | 2024-02-22 |  | EXECUTED
674 | 0 |  | 0 |  | 2021-06-21 | Standish | NORTH WINDHAM | 639D3 | Hydro | 4200 | 0 |  |  |  |  | 2021-12-21 | 2022-02-28 |  |  |  |  | 2022-03-25 | 2023-06-30 |  | 2024-04-25 | 2024-07-01 |  |  |  |  | Q4 2025 | Fully Executed Interconnection Agreement | No | 2024-08-20 | Cluster XX - Raymond - TBD | Raymond | 3 |  | Not Required | RE_QUEUED_FullEx
675 | 0 | 0 | 0 |  | 2021-07-02 | Boothbay | BOOTHBAY HARBOR | 209D3 | Solar | 0 | 0 | [10 empty] | 2021-10-26 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster XX - Midcoast - TBD | Mason | 3 |  |  | EXECUTED-WITHDRAWN
676 | 0 | 0 | 0 |  | 2021-07-02 | Lincolnville | LINCOLNVILLE | 800D1 | Solar | 0 | 0 |  |  |  |  | 2022-04-22 | 2022-05-23 | 2022-08-12 | 2022-09-22 |  |  | 2022-10-14 | 2024-10-31 | 2025-01-10 | [6 empty] | Q4 2025 | WITHDRAWN | WITHDRAWN |  | Cluster XX - Midcoast - TBD | Lincolnville | 3 |  |  | EXECUTED
677 | 0 | 0 | 0 |  | 2021-07-07 | Wales | MONMOUTH | 457D1 | Solar | 0 | 0 |  |  |  |  | 2022-04-06 | 2022-06-03 | 2022-07-27 |  |  |  |  | 2023-01-13 | 2023-02-27 | [7 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Augusta E-Puddledock-Bowman St - TBD | Monmouth | 3 |  | Not Required | WITHDRAWN
678 | 0 | 0 | 0 |  | 2021-07-16 | Acton | BUTLER'S CORNER | 612D2 | Solar | 0 | 0 | [10 empty] | 2021-12-08 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 19 - Sanford-Quaker Hill - 2 | Sanford | 3 |  |  | EXECUTED-WITHDRAWN
679 | 0 | 0 | 0 |  | 2021-07-20 | Buxton | BONNY EAGLE | 610D2 | Solar | 0 | 0 |  |  |  |  | 2022-06-06 | 2022-07-26 | [14 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 13 - Kimball Rd-Lovell - 2 | Kimball Road/Lovell | 3 |  |  | WITHDRAWN
680 | 0 | 0 | 0 |  | 2021-07-20 | Livermore Falls | LIVERMORE FALLS | 428D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Sturtevant/ Leeds/ Livermore/ Ludden/ Riley_TBD | Livermore Falls | 3 |  |  | WITHDRAWN
681 | 0 | 0 | 0 |  | 2021-07-22 | Arundel | KENNEBUNKPORT | 629D3 | Solar | 0 | 0 | 2021-11-24 | 2021-12-28 | [18 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 14 - Louden-Biddeford IP - 1 | Biddeford IP | 3 |  | 2024-03-19 | WITHDRAWN
682 | 0 | 0 | 0 |  | 2021-08-11 | Corinna | CORINNA | 811D1 | Solar | 0 | 0 |  |  |  |  | 2021-12-23 | [15 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 17 - Detroit Guilford Belfast - 2 | Detroit | 3 |  | Not Required | WITHDRAWN
683 | 0 | 0 | 0 |  | 2021-08-16 | Boothbay Harbor | BOOTHBAY HARBOR | 209D2 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Midcoast - TBD | Mason | 3 |  |  | WITHDRAWN
684 | 0 | 0 | 0 |  | 2021-08-16 | Clinton | CLINTON | 810D1 | Solar | 0 | 0 |  |  |  |  | 2021-10-15 | 2021-11-30 |  |  |  |  | 2022-01-03 | [9 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Winslow/ County Rd/ Lakewood - TBD | Winslow-County Rd | 3 |  |  | EXECUTED-WITHDRAWN
685 | 0 | 0 | 0 |  | 2021-08-24 | Yarmouth | ELM STREET | 620D2 | Solar | 0 | 0 |  |  |  |  | 2021-12-15 | 2022-02-22 |  |  |  |  | 2022-05-26 | 2023-04-19 | [8 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Greater Portland - TBD | Elm St | 3 |  |  | EXECUTED-WITHDRAWN
686 | 0 | 0 | 0 |  | 2021-09-14 | Windham | PRIDES CORNER | 647D3 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Greater Portland - TBD | Moshers/Prides Corner | 3 |  |  | WITHDRAWN
687 | 0 | 0 | 0 |  | 2021-10-19 | Embden | EMBDEN | 868D1 | Solar | 0 | 0 | [10 empty] | 2022-11-02 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster XX - Wyman Area - TBD | Embden | 3 |  |  | EXECUTED-WITHDRAWN
688 | 0 | 0 | 0 |  | 2021-10-25 | Windham | NORTH WINDHAM | 639D2 | Solar | 0 | 0 | [10 empty] | 2022-11-29 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster XX - Raymond - TBD | Raymond | 3 |  | Not Required | EXECUTED-WITHDRAWN
689 | 0 | 0 | 0 |  | 2021-11-30 | Lebanon | LEBANON | 695D2 | Solar | 0 | 0 | [10 empty] | 2022-08-12 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 19 - Sanford-Quaker Hill - 2 | Sanford | 3 |  |  | EXECUTED-WITHDRAWN
690 | 0 | 0 | 0 |  | 2021-11-30 | North Yarmouth | ELM STREET | 620D4 | Solar | 0 | 0 | [10 empty] | 2022-11-17 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster XX - Greater Portland - TBD | Elm St | 3 |  |  | EXECUTED-WITHDRAWN
691 | 0 | 0 | 0 |  | 2021-12-01 | Lewiston | SABATTUS | 450D1 | Solar | 0 | 0 | [10 empty] | 2022-06-14 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 18 - Lewiston Loop - 2 | Hotel Rd/Gulf/Middle St/Crowleys | 3 |  | Not Required | EXECUTED-WITHDRAWN
692 | 0 | 0 | 0 |  | 2021-12-13 | Readfield | PUDDLEDOCK ROAD | 262D1 | Solar | 0 | 0 |  |  |  |  | 2022-02-02 | 2022-03-29 |  |  |  | 2022-08-31 | 2022-11-17 | [9 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Augusta E-Puddledock-Bowman St - TBD | Augusta E/Puddledock/Bowman St | 3 |  |  | EXECUTED-WITHDRAWN
693 | 0 | 0 | 0 |  | 2021-12-21 | Waldoboro | WALDOBORO | 252D1 | Solar | 0 | 0 |  |  |  |  | 2022-02-16 | 2022-04-25 | [14 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 09 - Midcoast - 1 | Highland/Park St | 3 |  | 2023-12-15 | WITHDRAWN
694 | 0 | 0 | 0 |  | 2021-12-22 | Eustis | STRATTON | 877D1 | Solar/DC BESS | 0 | 0 | [10 empty] | 2022-08-08 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster XX - Wyman Area - TBD | Bigelow | 3 |  |  | EXECUTED
695 | 0 | 0 | 0 |  | 2022-01-07 | Skowhegan | WESTON HYDRO | 866D2 | Solar | 0 | 0 |  |  |  |  | 2022-02-14 | 2022-04-20 | 2022-06-28 |  |  |  |  | 2023-04-17 | [8 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Winslow/ County Rd/ Lakewood - TBD | Lakewood | 3 |  |  | WITHDRAWN
696 | 0 | 0 | 0 |  | 2022-01-12 | Eliot | ELIOT | 687D1 | Solar | 0 | 0 | 2022-03-21 | 2022-04-26 | 2022-06-28 | [17 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 19 - Sanford-Quaker Hill - 2 | Bolt Hill | 3 |  |  | WITHDRAWN
697 | 0 | 0 | 0 |  | 2022-01-24 | Athens | ATHENS | 827D1 | Solar | 0 | 0 | [10 empty] | 2022-06-14 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster XX - Wyman Area - TBD | Athens | 3 |  |  | EXECUTED-WITHDRAWN
698 | 0 | 0 | 265 |  | 2022-01-24 | Oakland | OAKLAND | 839D2 | Solar | 999 | 0 |  |  |  |  | 2023-02-06 | 2023-04-11 |  |  |  |  | 2023-05-03 | [8 empty] | Q2 2026 | Fully Executed Interconnection Agreement | No | 2023-11-22 | Cluster XX - Winslow/ County Rd/ Lakewood - TBD | Winslow-County Rd | 3 |  | Not Required | RE_QUEUED_FullEx
699 | 0 | 0 | 0 |  | 2022-01-24 | Oxford | OXFORD | 437D1 | Solar | 1999 | 0 |  |  |  |  | 2022-03-16 | 2022-05-18 |  |  |  |  | 2022-07-14 | [8 empty] | Q1 2026 | Fully Executed Interconnection Agreement | No | 2022-08-16 | Cluster 18 - Lewiston Loop - 2 | Norway | 3 |  |  | EXECUTED
700 | 0 | 0 | 0 |  | 2022-01-25 | Skowhegan | WESTON HYDRO | 866D1 | Solar | 0 | 0 |  |  |  |  | 2023-07-28 | 2023-10-04 | [14 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Winslow/ County Rd/ Lakewood - TBD | Lakewood | 3 |  |  | WITHDRAWN
701 | 0 | 0 | 611 |  | 2022-02-01 | Lewiston | DEER RIPS | 412D4 | Solar | 0 | 0 |  |  |  |  | 2024-09-23 | 2024-11-27 |  |  |  |  | 2025-02-05 | [8 empty] | Q4 2025 | WITHDRAWN | WITHDRAWN |  | Cluster 18 - Lewiston Loop - 2 | Hotel Rd/Gulf/Middle St/Crowleys/Norway | 3 |  |  | RE_QUEUED_SCOPING
702 | 0 | 0 | 655 |  | 2022-02-04 | Bucksport | BUCKSPORT | 806D2 | Solar | 4980 | [5 empty] | 2023-08-17 | 2023-10-23 |  |  |  |  | 2024-01-29 | [8 empty] | Q4 2024 | Fully Executed Interconnection Agreement | No |  | Cluster 17 - Detroit Guilford Belfast - 2 | Bucksport | 3 |  |  | RE_QUEUED_FullEx
703 | 0 | 0 | 0 |  | 2022-02-09 | Baldwin | BALDWIN | 691D1 | Solar | 0 | 0 | [10 empty] | 2022-05-18 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 13 - Kimball Rd-Lovell - 2 | Kimball Road/Lovell | 3 |  | Not Required | EXECUTED-WITHDRAWN
704 | 0 | 0 | 0 |  | 2022-02-16 | Bethel | LOCKES MILLS | 429D1 | Solar | 0 | 0 | [10 empty] | 2022-10-18 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster XX - Woodstock/ Roxbury/ Rumford - TBD | Woodstock | 3 |  |  | EXECUTED-WITHDRAWN
705 | 0 | 0 | 0 |  | 2022-02-17 | Peru | RUMFORD INDUSTRIAL PARK | 466D1 | Solar | 0 | 0 |  |  |  |  | 2022-03-30 | 2022-05-25 | [14 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Woodstock/ Roxbury/ Rumford - TBD | Rumford IP | 3 |  |  | WITHDRAWN
706 | 1151 | 0 | 0 |  | 2022-03-10 | Woodstock | BRYANT POND | 407D1 | Solar | 1968 | 0 |  |  |  |  | 2022-03-10 | 2022-05-11 |  |  |  |  | 2023-06-12 | [9 empty] | Fully Executed Interconnection Agreement | Yes | 2023-07-21 | N/A | Woodstock | 3 | N/A |  | EXECUTED
707 | 1169 |  | 606 |  | 2022-03-10 | Roxbury | RUMFORD | 447D1 | Solar | 1999 | 0 |  |  |  |  | 2022-03-10 | 2022-04-27 |  |  |  |  | 2025-08-05 | 2024-04-19 | 2024-06-18 | [7 empty] | Fully Executed Interconnection Agreement | No | 2023-11-13 | Cluster XX - Woodstock/ Roxbury/ Rumford - TBD | Rumford | 3 |  | Not Required | RE_QUEUED_RESULTS
708 | 0 | 0 | 0 |  | 2022-03-17 | Fryeburg | FRYEBURG TAP | 405D1 | Solar | 0 | 0 | [10 empty] | 2022-08-04 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 13 - Kimball Rd-Lovell - 2 | Kimball Road/Lovell | 3 |  |  | EXECUTED-WITHDRAWN
709 | 0 | 0 | 0 |  | 2022-03-18 | Woolwich | WOOLWICH | 258D1 | Solar | 0 | 0 | [10 empty] | 2022-08-04 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster XX - Midcoast - TBD | Bath | 3 |  |  | EXECUTED-WITHDRAWN
710 | 0 | 0 | 0 |  | 2022-03-31 | Topsham | TOPSHAM 34 KV | 250D1 | Solar | 0 | 0 | [10 empty] | 2022-09-08 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster XX - Midcoast - TBD | Topsham | 3 |  | Not Required | EXECUTED-WITHDRAWN
711 | 0 | 0 | 0 |  | 2022-04-07 | Casco | RAYMOND 115 KV | 445D1 | Solar | 0 | 0 | [10 empty] | 2022-09-09 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster XX - Raymond - TBD | Raymond | 3 |  |  | RE_QUEUED_FullEx
712 | 0 |  | 643 |  | 2022-04-07 | Lisbon | LISBON FALLS | 232D1 | Solar | 999 | 0 |  |  |  |  | 2023-01-13 | 2023-03-20 |  |  |  |  | 2024-05-28 | 2024-03-19 | 2024-05-23 | [6 empty] | Q3 2026 | Fully Executed Interconnection Agreement | No | 2024-09-26 | Cluster 18 - Lewiston Loop - 2 | Hotel Rd/Gulf/Middle St/Crowleys | 3 |  | Not Required | RE_QUEUED_FullEx
713 | 0 | 0 | 0 |  | 2022-04-20 | Auburn | GREAT FALLS | 436D6 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 18 - Lewiston Loop - 2 | Hotel Rd/Gulf/Middle St/Crowleys | 3 |  |  | WITHDRAWN
714 | 0 | 0 | 0 |  | 2022-04-28 | Skowhegan | SKOWHEGAN TAP | 864D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Winslow/ County Rd/ Lakewood - TBD | Lakewood | 3 |  |  | WITHDRAWN
715 | 0 | 0 | 0 |  | 2022-05-06 | Hartland | HARTLAND | 824D1 | Solar | 860 | 0 |  |  |  |  | 2022-06-17 | 2022-07-14 |  |  |  |  | 2022-09-08 | [9 empty] | Fully Executed Interconnection Agreement | Yes | 2023-01-19 | Cluster XX - Wyman Area - TBD | Hartland | 3 |  | Not Required | EXECUTED
716 | 0 | 0 | 0 |  | 2022-05-11 | Searsport | SEARSPORT | 850D1 | Solar | 0 | 0 | [10 empty] | 2022-11-01 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 17 - Detroit Guilford Belfast - 2 | Belfast | 3 |  |  | RE_QUEUED_FullEx
717 | 0 | 0 | 0 |  | 2022-05-13 | Biddeford | BIDDEFORD PUMP | 605D2 | Solar | 0 | 0 | [10 empty] | 2023-06-06 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster XX - Louden-Biddeford IP - TBD | Louden | 3 |  | TBD | EXECUTED-WITHDRAWN
718 | 0 |  | 0 |  | 2022-05-16 | Monmouth | MONMOUTH | 457D2 | Solar | 999 | 0 |  |  |  |  | 2023-05-04 | 2023-07-06 |  |  |  |  | 2023-08-22 |  | 2024-10-30 | [6 empty] | Q4 2025 | Fully Executed Interconnection Agreement | No | 2024-01-11 | Cluster XX - Augusta E-Puddledock-Bowman St - TBD | Monmouth | 3 |  | Not Required | RE_QUEUED_FullEx
719 | 0 | 0 | 0 |  | 2022-05-23 | Auburn | GREAT FALLS | 436D6 | Solar | 0 | 0 |  |  |  |  | 2022-08-04 | 2022-10-06 | [14 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 18 - Lewiston Loop - 2 | Hotel Rd/Gulf/Middle St/Crowleys | 3 |  | Not Required | WITHDRAWN
720 | 0 | 0 | 0 |  | 2022-05-31 | Winthrop | WINTHROP | 256D1 | Solar | 0 | 0 |  |  |  |  | 2023-01-12 | 2023-03-20 | [14 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Augusta E-Puddledock-Bowman St - TBD | Augusta E/Puddledock/Bowman St | 3 |  |  | WITHDRAWN
721 | 0 | 0 | 0 |  | 2022-05-31 | Starks | ANSON | 801D1 | Solar | 0 | 0 |  |  |  |  | 2022-08-25 | [15 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Winslow/ County Rd/ Lakewood - TBD | Lakewood | 3 |  |  | WITHDRAWN
722 | 0 | 0 | 0 |  | 2022-06-03 | Boothbay | BOOTHBAY HARBOR | 209D3 | Solar | 0 | 0 | [10 empty] | 2022-09-27 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster XX - Midcoast - TBD | Mason | 3 |  | Not Required | EXECUTED-WITHDRAWN
723 | 0 | 0 | 661 |  | 2022-06-08 | Parkman | GUILFORD | 821D1 | Solar | 0 | 0 |  |  |  |  | 2025-01-30 | 2024-04-04 | [13 empty] | Q4 2026 | WITHDRAWN | WITHDRAWN |  | Cluster 17 - Detroit Guilford Belfast - 2 | Guilford | 3 |  |  | RE_QUEUED
724 | 0 | 0 | 0 |  | 2022-06-08 | Fairfield | FAIRFIELD | 817D3 | Solar | 996 | 0 |  |  |  |  | 2022-07-25 | 2022-09-22 |  |  |  |  | 2022-09-27 | [8 empty] | Q3 2025 | Fully Executed Interconnection Agreement | No | 2022-10-14 | Cluster XX - Winslow/ County Rd/ Lakewood - TBD | Winslow-County Rd | 3 |  | Not Required | EXECUTED
725 | 0 | 0 | 0 |  | 2022-06-09 | South China | SOUTH CHINA | 244D2 | Solar | 975 | 0 | 2022-08-08 | 2022-09-14 | 2022-10-12 | 2022-11-09 | [6 empty] | 2023-01-09 | [8 empty] | Q4 2025 | Fully Executed Interconnection Agreement | No | 2023-10-03 | Cluster XX - Augusta E-Puddledock-Bowman St - TBD | Augusta E/Puddledock/Bowman St | 3 |  | Not Required | EXECUTED
726 | 0 | 0 | 0 |  | 2022-06-09 | Manchester | MANCHESTER | 233D2 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Augusta E-Puddledock-Bowman St - TBD | Augusta E/Puddledock/Bowman St | 3 |  |  | WITHDRAWN
727 | 0 | 0 | 0 |  | 2022-06-13 | Vassalboro | BLAIR ROAD | 207D1 | Solar | 0 | 0 |  |  |  |  | 2022-07-21 | 2022-09-21 | [14 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Augusta E-Puddledock-Bowman St - TBD | Augusta E/Puddledock/Bowman St | 3 |  |  | WITHDRAWN
728 | 0 | 0 | 0 |  | 2022-06-13 | Pittston | BOWMAN STREET | 263D1 | Solar | 975 | 0 |  |  |  |  | 2022-07-21 | 2022-09-22 |  |  |  |  | 2023-03-14 | 2023-01-21 | 2023-03-06 | 2023-12-07 | 2024-03-05 |  |  |  |  | Q4 2025 | Fully Executed Interconnection Agreement | No | 2023-10-25 | Cluster XX - Augusta E-Puddledock-Bowman St - TBD | Augusta E/Puddledock/Bowman St | 3 |  | Not Required | RE_QUEUED_FullEx
729 | 0 | 0 | 0 |  | 2022-06-20 | Readfield | PUDDLEDOCK ROAD | 262D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Augusta E-Puddledock-Bowman St - TBD | Augusta E/Puddledock/Bowman St | 3 |  |  | WITHDRAWN
730 | 0 | 0 | 0 |  | 2022-06-29 | Bristol | BRISTOL | 210D2 | Solar | 0 | 0 |  |  |  |  | 2022-08-08 | 2022-10-12 |  |  |  |  | 2022-11-14 | 2024-03-20 | 2024-05-22 | [6 empty] | Q4 2026 | WITHDRAWN | WITHDRAWN |  | Cluster XX - Midcoast - TBD | Newcastle | 3 |  | Not Required | RE_QUEUED_FullEx
731 | 0 | 1 - VASS | 371 | RQP-1 | 2022-07-11 | Vassalboro | VASSALBORO | 861D8 | Solar | 975 | 0 |  |  |  |  | 2024-01-08 | 2024-03-05 |  |  |  |  | 2024-03-27 | 2024-01-08 | 2024-03-05 | 2025-08-06 | 2025-10-07 |  |  |  |  | Q2 2026 | Fully Executed Interconnection Agreement | No | 2024-11-08 | Cluster XX - Winslow/ County Rd/ Lakewood - TBD | Winslow-County Rd | 3 |  | Not Required | RE_QUEUED_FullEx
732 | 0 | 1 - LVFA | 680 | RQP-1 | 2022-07-18 | Jay | LIVERMORE FALLS | 428D3 | Solar | 999 | 0 |  |  |  |  | 2022-11-15 | 2023-01-17 | 2023-03-06 | 2023-04-10 |  |  | 2023-04-19 | 2023-12-27 | 2024-03-04 | 2024-05-31 | 2024-08-02 | 2025-08-06 | 2025-10-08 |  |  | Q4 2025 | Fully Executed Interconnection Agreement | No | 2023-11-06 | Cluster XX - Sturtevant/ Leeds/ Livermore/ Ludden/ Riley_TBD | Livermore Falls | 3 |  |  | #REF!
733 | 0 | 0 | 0 |  | 2022-07-21 | Vassalboro | MCCOYS | 237D1 | Solar | 1000 | 0 |  |  |  |  | 2022-10-04 | 2022-12-12 |  |  |  |  | 2022-12-28 | [9 empty] | Fully Executed Interconnection Agreement | Yes | 2023-02-03 | Cluster XX - Augusta E-Puddledock-Bowman St - TBD | Augusta E/Puddledock/Bowman St | 3 |  |  | EXECUTED
734 | 0 | 0 | 0 |  | 2022-07-22 | Lewiston | MIDDLE STREET | 451D8 | Battery | 0 | 0 | [20 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 18 - Lewiston Loop - 2 | Middle Street | 3 |  |  | WITHDRAWN
735 | 0 | 0 | 0 |  | 2022-07-25 | Mechanic Falls | MECHANIC FALLS | 431D1 | Solar | 0 | 0 | [10 empty] | 2022-11-29 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 18 - Lewiston Loop - 2 | Norway | 3 |  | Not Required | EXECUTED-WITHDRAWN
736 | 0 | 0 | 0 |  | 2022-07-26 | Newcastle | DAMARISCOTTA MILLS | 219D2 | Solar/Battery | 0 | 0 |  |  |  |  | 2022-09-12 | 2022-11-09 |  |  |  |  | 2022-11-30 | [9 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Midcoast - TBD | Newcastle | 3 |  |  | EXECUTED-WITHDRAWN
737 | 0 | 0 | 0 |  | 2022-07-29 | Madison | SKOWHEGAN NORTH SIDE | 853D1 | Solar | 975 | 0 |  |  |  |  | 2022-08-24 | 2022-10-31 |  |  |  |  | 2023-01-09 | 2024-02-07 | 2024-04-11 | [6 empty] | Q3 2025 | Fully Executed Interconnection Agreement | No | 2023-10-03 | Cluster XX - Winslow/ County Rd/ Lakewood - TBD | Lakewood | 3 |  | Not Required | RE_QUEUED_FullEx
738 | 0 | 0 | 0 |  | 2022-08-09 | Andover | ANDOVER | 400D1 | Solar | 0 | 0 | [10 empty] | 2022-12-12 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster XX - Woodstock/ Roxbury/ Rumford - TBD | Roxbury | 3 |  | Not Required | EXECUTED-WITHDRAWN
739 | 0 | 0 | 0 |  | 2022-08-11 | Wiscasset | MESSINA | 238D1 | Solar/Battery | 0 | 0 |  |  |  |  | 2022-09-23 | 2022-12-01 | 2023-01-24 | 2023-03-07 | [12 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Midcoast - TBD | Mason | 3 |  | Not Required | WITHDRAWN
740 | 0 | 0 | 0 |  | 2022-08-18 | Raymond | RAYMOND 34 KV | 444D1 | Solar/Battery | 0 | 0 | [10 empty] | 2023-11-22 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster XX - Raymond - TBD | Raymond | 3 |  | Not Required | EXECUTED-WITHDRAWN
741 | 0 | 0 | 0 |  | 2022-08-18 | Mercer | SKOWHEGAN TAP | 864D1 | Solar | 999 | 0 |  |  |  |  | 2022-10-26 | 2023-01-05 | 2023-04-18 | 2023-05-30 |  |  | 2023-07-31 | [8 empty] | Q4 2025 | Fully Executed Interconnection Agreement | No | 2023-12-19 | Cluster XX - Winslow/ County Rd/ Lakewood - TBD | Lakewood | 3 |  |  | EXECUTED
742 | 0 | 0 | 0 |  | 2022-08-18 | Mercer | SKOWHEGAN TAP | 864D1 | Solar | 0 | 0 |  |  |  |  | 2023-12-12 | 2024-02-16 | [14 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Winslow/ County Rd/ Lakewood - TBD | Lakewood | 3 |  |  | WITHDRAWN
743 | 0 | 0 | 676 |  | 2022-08-26 | Northport | LINCOLNVILLE | 800D1 | Solar | 0 | 0 |  |  |  |  | 2022-11-11 | 2023-01-11 |  |  |  |  | 2023-02-24 | [8 empty] | Q4 2024 | WITHDRAWN | WITHDRAWN |  | Cluster XX - Midcoast - TBD | Lincolnville | 3 |  |  | EXECUTED
744 | 0 | 0 | 0 |  | 2022-08-30 | Windham | NORTH WINDHAM | 639D2 | Solar | 0 | 0 |  |  |  |  | 2023-01-09 | 2023-03-16 | [14 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Raymond - TBD | Raymond | 3 |  | Not Required | WITHDRAWN
745 | 0 | 0 | 725 |  | 2022-09-08 | South China | SOUTH CHINA | 244D1 | Solar | 975 | 0 |  |  |  |  | 2023-05-01 | 2023-07-07 |  |  |  |  | 2023-08-24 | [8 empty] | Q2 2025 | Fully Executed Interconnection Agreement | Yes | 2024-01-10 | Cluster XX - Augusta E-Puddledock-Bowman St - TBD | Augusta E/Puddledock/Bowman St | 3 |  | Not Required | EXECUTED
746 | 0 |  | 0 |  | 2022-09-08 | Fairfield | SHAWMUT | 852D1 | Solar | 500 | 0 |  |  |  |  | 2022-11-02 | 2023-01-10 |  |  |  |  | 2023-02-13 | 2024-03-25 | 2024-05-29 | [6 empty] | Q4 2025 | Fully Executed Interconnection Agreement | No | 2023-10-25 | Cluster XX - Winslow/ County Rd/ Lakewood - TBD | Lakewood | 3 |  | Not Required | RE_QUEUED_FullEx
747 | 0 | 0 | 0 |  | 2022-10-07 | Sweden | LOVELL | 430D1 | Solar | 0 | 0 | [10 empty] | 2023-09-15 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 13 - Kimball Rd-Lovell - 2 | Kimball Road/Lovell | 3 |  | Not Required | EXECUTED-WITHDRAWN
748 | 0 | 0 | 0 |  | 2022-10-07 | Sweden | LOVELL | 430D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 13 - Kimball Rd-Lovell - 2 | Kimball Road/Lovell | 3 |  | Not Required | WITHDRAWN
749 | 0 | 0 | 0 |  | 2022-10-07 | Sweden | LOVELL | 430D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 13 - Kimball Rd-Lovell - 2 | Kimball Road/Lovell | 3 |  | Not Required | WITHDRAWN
750 | 0 | 0 | 0 |  | 2022-10-12 | Levant | CARMEL | 808D3 | Solar | 0 | 0 | [10 empty] | 2024-04-11 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 17 - Detroit Guilford Belfast - 2 | Detroit | 3 |  | Not Required | RE_QUEUED_FullEx
751 | 0 |  | 700 |  | 2022-10-17 | Skowhegan | WESTON HYDRO | 866D2 | Solar | 500 | 0 |  |  |  |  | 2024-04-04 | 2024-06-05 |  |  |  |  | 2024-08-12 | [8 empty] | Q2 2025 | Fully Executed Interconnection Agreement | No | 2025-05-19 | Cluster XX - Winslow/ County Rd/ Lakewood - TBD | Lakewood | 3 |  | Not Required | RE_QUEUED_FullEx
752 | 0 | 0 | 0 |  | 2022-10-19 | Lewiston | DEER RIPS | 412D2 | Fuel Cell | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 18 - Lewiston Loop - 2 | Hotel Rd/Gulf/Middle St/Crowleys/Norway | 3 |  | Not Required | WITHDRAWN
753 | 0 | 0 | 0 |  | 2022-10-19 | Scarborough | PLEASANT HILL | 644D4 | Fuel Cell | 0 | 0 | [10 empty] | 2023-04-26 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster XX - Greater Portland - TBD | Pleasant Hill | 3 |  | Not Required | EXECUTED-WITHDRAWN
754 | 0 | 0 | 0 |  | 2022-10-19 | Biddeford | BIDDEFORD INDUSTRIAL PARK | 673D1 | Fuel Cell | 0 | 0 | [10 empty] | 2023-04-28 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster XX - Louden-Biddeford IP - TBD | Biddeford IP | 3 |  | Not Required | EXECUTED-WITHDRAWN
755 | 0 | 0 | 0 |  | 2022-10-19 | Sanford | SANFORD SWITCH | 657D4 | Fuel Cell | 0 | 0 |  |  |  |  | 2022-12-23 | 2023-02-27 | [14 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 19 - Sanford-Quaker Hill - 2 | Sanford | 3 |  | Not Required | WITHDRAWN
756 | 0 | 0 | 0 |  | 2022-10-19 | Augusta | CAPITOL STREET | 215D3 | Fuel Cell | 0 | 0 | [10 empty] | 2023-04-17 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster XX - Augusta E-Puddledock-Bowman St - TBD | Augusta E/Puddledock/Bowman St | 3 |  | Not Required | EXECUTED-WITHDRAWN
757 | 0 | 0 | 718 |  | 2022-12-12 | Monmouth | MONMOUTH | 457D2 | Solar | 0 | 0 | [10 empty] | 2024-02-12 | [8 empty] | Q3 2025 | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster XX - Augusta E-Puddledock-Bowman St - TBD | Monmouth | 3 |  | Not Required | RE_QUEUED_FullEx
758 | 0 | 0 | 0 |  | 2022-11-04 | Sanford | SANFORD INDUSTRIAL PARK | 656D2 | Solar | 990 | 0 |  |  |  |  | 2023-04-12 | 2023-06-16 |  |  |  |  | 2023-08-02 | [8 empty] | Q4 2025 | Fully Executed Interconnection Agreement | No | 2023-08-16 | Cluster 19 - Sanford-Quaker Hill - 2 | Sanford | 3 |  | Not Required | RE_QUEUED_FullEx
759 | 0 | 0 | 0 |  | 2022-11-04 | Portland | LAMBERT STREET | 631D1 | Fuel Cell | 0 | 0 |  |  |  |  | 2022-12-14 | 2023-02-21 | [14 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Greater Portland - TBD | Moshers/Prides Corner | 3 |  | Not Required | WITHDRAWN
760 | 0 | 0 | 0 |  | 2022-11-07 | Scarborough | MUSSEY ROAD | 636D2 | Fuel Cell | 0 | 0 |  |  |  |  | 2022-12-14 | [15 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Greater Portland - TBD | Mussey Road | 3 |  | Not Required | WITHDRAWN
761 | 0 | 0 | 0 |  | 2022-11-07 | Fairfield | FAIRFIELD | 817D2 | Fuel Cell | 0 | 0 | [10 empty] | 2023-06-06 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster XX - Winslow/ County Rd/ Lakewood - TBD | Winslow-County Rd | 3 |  | Not Required | EXECUTED-WITHDRAWN
762 | 0 | 0 | 0 |  | 2022-11-07 | Bucksport | BUCKSPORT | 806D1 | Fuel Cell | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 17 - Detroit Guilford Belfast - 2 | Bucksport | 3 |  | Not Required | WITHDRAWN
763 | 0 | 0 | 0 |  | 2022-11-17 | West Gardiner | WEST STREET | 255D2 | Solar | 0 | 0 | [10 empty] | 2023-08-24 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster XX - Augusta E-Puddledock-Bowman St - TBD | Augusta E/Puddledock/Bowman St | 3 |  | Not Required | EXECUTED-WITHDRAWN
764 | 0 | 0 | 0 |  | 2022-11-18 | Biddeford | BIDDEFORD PUMP | 605D2 | Solar | 0 | 0 | [10 empty] | 2024-04-09 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster XX - Louden-Biddeford IP - TBD | Louden | 3 |  | Not Required | RE_QUEUED_FullEx
765 | 0 | 0 | 0 |  | 2022-11-21 | Belfast | BELFAST 115 | 874D1 | Solar/Battery | 800 | 0 |  |  |  |  | 2023-01-24 | 2023-03-28 |  |  |  |  | 2023-03-30 | [8 empty] | Q4 2025 | Fully Executed Interconnection Agreement | No | 2024-06-07 | Cluster 17 - Detroit Guilford Belfast - 2 | Belfast | 3 |  | Not Required | RE_QUEUED_FullEx
766 | 0 | 0 | 0 |  | 2022-11-23 | Chelsea | CONY ROAD | 216D1 | Battery | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Withdrawn | Withdrawn | 3 |  | Not Required | WITHDRAWN
767 | 0 | 0 | 0 |  | 2022-11-29 | Saco | GOOSEFARE | 630D2 | Fuel Cell | 0 | 0 |  |  |  |  | 2023-02-03 | 2023-04-10 | [14 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Louden-Biddeford IP - TBD | Louden | 3 |  | Not Required | WITHDRAWN
768 | 0 |  | 0 |  | 2022-12-05 | Searsport | SEARSPORT | 850D1 | Solar | 999 | 0 |  |  |  |  | 2024-04-19 | 2024-06-17 |  |  |  |  | 2024-08-19 | 2024-12-10 | 2025-02-14 | [6 empty] | Q3 2026 | Fully Executed Interconnection Agreement | No | 2025-02-12 | Cluster 17 - Detroit Guilford Belfast - 2 | Belfast | 3 |  | Not Required | RE_QUEUED_FullEx
769 | 0 | 0 | 0 |  | 2022-12-20 | Augusta | NORTH AUGUSTA | 272D4 | Solar | 1875 | 0 |  |  |  |  | 2023-05-09 | 2023-07-10 |  |  |  |  | 2023-09-26 | 2024-05-10 | 2024-07-12 | 2024-12-27 | 2025-03-04 |  |  |  |  | Q2 2025 | Fully Executed Interconnection Agreement | No |  | Cluster XX - Augusta E-Puddledock-Bowman St - TBD | North Augusta | 3 |  |  | RE_QUEUED_RESULTS
770 | 0 | 0 | 0 |  | 2022-12-29 | Carrabassett Valley | BIGELOW | 882D2 | Solar/Battery | 12400 | 0 |  |  |  |  | 2023-03-27 | 2023-05-30 |  |  |  |  | 2023-08-24 | [9 empty] | Fully Executed Interconnection Agreement | No |  | Cluster XX - Wyman Area - TBD | Bigelow | 3 |  |  | EXECUTED
771 | 0 | 0 | 0 |  | 2023-01-04 | Bristol | BRISTOL | 210D1 | Solar | 0 | 0 | [10 empty] | 2023-04-25 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster XX - Midcoast - TBD | Newcastle | 3 |  | Not Required | EXECUTED-WITHDRAWN
772 | 0 | 0 | 761 |  | 2023-01-05 | Fairfield | FAIRFIELD | 817D3 | Solar | 0 | 0 |  |  |  |  | 2023-10-30 | 2024-01-08 |  |  |  |  | 2024-01-30 | [8 empty] | Q2 2026 | WITHDRAWN | WITHDRAWN |  | Cluster XX - Winslow/ County Rd/ Lakewood - TBD | Winslow-County Rd | 3 |  | Not Required | EXECUTED
773 | 0 | 0 | 0 |  | 2023-01-09 | Biddeford | MAY STREET | 634D1 | Fuel Cell | 0 | 0 |  |  |  |  | 2023-02-13 | 2023-04-19 | [14 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Louden-Biddeford IP - TBD | Biddeford IP | 3 |  | Not Required | WITHDRAWN
774 | 0 | 0 | 0 |  | 2023-01-11 | Boothbay | BOOTHBAY HARBOR | 209D3 | Solar | 0 | 0 | [10 empty] | 2023-05-04 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster XX - Midcoast - TBD | Mason | 3 |  | Not Required | EXECUTED-WITHDRAWN
775 | 0 | 0 | 0 |  | 2023-01-12 | Bath | BATH 34 | 261D4 | Fuel Cell | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Midcoast - TBD | Bath | 3 |  | Not Required | WITHDRAWN
776 | 0 | 0 | 0 |  | 2023-01-23 | Lewiston | CHALLENGER 12 KV | 421D2 | Fuel Cell | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 18 - Lewiston Loop - 2 | Challenger Dr | 3 |  | Not Required | WITHDRAWN
777 | 0 | 0 | 0 |  | 2023-01-24 | Mechanic Falls | MECHANIC FALLS | 431D1 | Solar | 0 | 0 |  |  |  |  | 2023-03-02 | 2023-05-02 |  |  |  |  | 2023-06-29 | [9 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 18 - Lewiston Loop - 2 | Norway | 3 |  | Not Required | EXECUTED-WITHDRAWN
778 | 0 | 0 | 0 |  | 2023-01-27 | Auburn | GREAT FALLS | 436D6 | Solar | 0 | 0 | [10 empty] | 2024-05-08 | [8 empty] | Q4 2025 | EXECUTED-WITHDRAWN | WITHDRAWN | 2024-08-19 | Cluster 18 - Lewiston Loop - 2 | Hotel Rd/Gulf/Middle St/Crowleys | 3 |  | Not Required | RE_QUEUED_FullEx
779 | 0 | 0 | 0 |  | 2023-01-31 | Monson | MONSON | 834D1 | Solar | 0 | 0 |  |  |  |  | 2023-04-27 | 2023-07-03 | [14 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 17 - Detroit Guilford Belfast - 2 | Guilford | 3 |  | Not Required | WITHDRAWN
780 | 0 | 0 | 0 |  | 2023-02-02 | Rockland | PARK STREET | 239D6 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Midcoast - TBD | Highland/Park St | 3 |  | Not Required | WITHDRAWN
781 | 0 | 2 - LVFA | 732 | RQP-2 | 2023-02-02 | Livermore Falls | LIVERMORE FALLS | 428D2 | Solar | 950 | 0 |  |  |  |  | 2023-05-05 | N/A |  |  |  |  | 2024-12-03 | 2024-09-16 | 2024-11-15 | 2024-12-16 | 2025-02-19 | [5 empty] | Fully Executed Interconnection Agreement | No | 2025-03-24 | Cluster XX - Sturtevant/ Leeds/ Livermore/ Ludden/ Riley_TBD | Livermore Falls | 3 |  | Not Required | RE_QUEUED
782 | 0 | 0 | 0 |  | 2023-02-07 | Peru | RUMFORD INDUSTRIAL PARK | 466D1 | Solar | 0 | 0 | [10 empty] | 2023-07-18 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster XX - Woodstock/ Roxbury/ Rumford - TBD | Rumford IP | 3 |  | Not Required | EXECUTED-WITHDRAWN
783 | 0 | 0 | 0 |  | 2023-02-09 | Biddeford | MAY STREET | 634D3 | Fuel Cell | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Louden-Biddeford IP - TBD | Biddeford IP | 3 |  | Not Required | WITHDRAWN
784 | 0 | 0 | 0 |  | 2023-02-10 | Lewiston | LEWISTON LOWER 115 | 424D5 | Fuel Cell | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 18 - Lewiston Loop - 2 | LEWISTON LOWER 115 KV | 3 |  | Not Required | WITHDRAWN
785 | 0 | 0 | 0 |  | 2023-02-10 | Kittery | BOLT HILL | 685D2 | Fuel Cell | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 19 - Sanford-Quaker Hill - 2 | Bolt Hill | 3 |  | Not Required | WITHDRAWN
786 | 0 | 0 | 0 |  | 2023-02-10 | Lewiston | SABATTUS | 450D2 | Fuel Cell | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 18 - Lewiston Loop - 2 | Hotel Rd/Gulf/Middle St/Crowleys | 3 |  | Not Required | WITHDRAWN
787 | 0 | 0 | 0 |  | 2023-02-10 | Lewiston | CHALLENGER 12 KV | 421D2 | Fuel Cell | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 18 - Lewiston Loop - 2 | Challenger Dr | 3 |  | Not Required | WITHDRAWN
788 | 0 | 0 | 0 |  | 2023-02-22 | West Bath | BATH 34 | 261D3 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Midcoast - TBD | Bath | 3 |  | Not Required | WITHDRAWN
789 | 0 | 0 | 0 |  | 2023-03-03 | Lisbon | LISBON FALLS | 232D1 | Fuel Cell | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 18 - Lewiston Loop - 2 | Hotel Rd/Gulf/Middle St/Crowleys | 3 |  | Not Required | WITHDRAWN
790 | 0 | 0 | 0 |  | 2023-03-03 | Carmel | CARMEL | 808D2 | Solar | 0 | 0 |  |  |  |  | 2024-05-31 | 2024-08-01 | 2024-11-20 |  |  |  |  | 2024-12-09 | [8 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 17 - Detroit Guilford Belfast - 2 | Detroit | 3 |  |  | RE_QUEUED_RESULTS
791 | 0 | 0 | 0 |  | 2023-03-03 | Minot | MECHANIC FALLS | 431D2 | Solar | 0 | 0 |  |  |  |  | 2024-06-18 | 2024-08-16 | [14 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 18 - Lewiston Loop - 2 | Norway | 3 |  |  | RE_QUEUED_RESULTS
792 | 0 | 0 | 0 |  | 2023-03-14 | Gray | GRAY | 416D3 | Solar | 0 | 0 | [10 empty] | 2023-07-31 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster XX - Greater Portland - TBD | Elm St | 3 |  | Not Required | EXECUTED-WITHDRAWN
793 | 0 | 0 | 0 |  | 2023-03-23 | Phippsburg | WASHINGTON ST (BATH) | 204D6 | Solar | 0 | 0 | [10 empty] | 2023-08-01 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster XX - Midcoast - TBD | Bath | 3 |  | Not Required | EXECUTED-WITHDRAWN
794 | 0 | 0 | 0 |  | 2023-03-27 | Topsham | TOPSHAM 34 KV | 250K3 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Midcoast - TBD | Topsham | 3 |  | Not Required | WITHDRAWN
795 | 0 | 0 | 0 |  | 2023-03-28 | Dixfield | LUDDEN LANE | 461D1 | Solar | 990 | 0 |  |  |  |  | 2023-05-19 | 2023-07-21 |  |  |  |  | 2024-05-29 | 2024-03-22 | 2024-05-17 | [6 empty] | Q1 2026 | Fully Executed Interconnection Agreement | No | 2024-09-30 | Cluster XX - Sturtevant/ Leeds/ Livermore/ Ludden/ Riley_TBD | Ludden Lane | 3 |  | Not Required | RE_QUEUED_FullEx
796 | 0 | 0 | 685 |  | 2023-03-28 | North Yarmouth | ELM STREET | 620D4 | Solar | 999 | 0 |  |  |  |  | 2023-05-22 | 2023-07-19 |  |  |  |  | 2023-09-15 | 2024-03-28 | 2024-06-03 | [6 empty] | Q2 2025 | Fully Executed Interconnection Agreement | Yes | 2024-04-11 | Cluster XX - Greater Portland - TBD | Elm St | 3 |  | Not Required | RE_QUEUED_FullEx
797 | 0 | 0 | 0 |  | 2023-03-29 | Bucksport | BUCKSPORT | 806D2 | Solar | 0 | 0 |  |  |  |  | 2024-03-07 | 2024-05-10 | [14 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 17 - Detroit Guilford Belfast - 2 | Bucksport | 3 |  | TBD | WITHDRAWN
798 | 0 | 0 | 796 |  | 2023-03-29 | North Yarmouth | ELM STREET | 620D4 | Solar | 999 | 0 |  |  |  |  | 2023-10-05 | 2023-12-13 |  |  |  |  | 2023-12-19 | 2024-07-10 | 2024-09-11 | [6 empty] | Q3 2025 | Fully Executed Interconnection Agreement | No | 2024-04-11 | Cluster XX - Greater Portland - TBD | Elm St | 3 |  | Not Required | RE_QUEUED_STUDY
799 | 0 | 0 | 0 |  | 2023-03-29 | Bucksport | BUCKSPORT | 806D2 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 17 - Detroit Guilford Belfast - 2 | Bucksport | 3 |  | TBD | WITHDRAWN
800 | 0 | 0 | 0 |  | 2023-04-12 | Lewiston | MIDDLE STREET | 451D8 | Battery | 9690 | 9690 |  |  |  |  | 2023-05-16 | 2023-06-28 |  |  |  | 2023-12-07 | 2024-01-10 | [9 empty] | Fully Executed Interconnection Agreement | No |  | Cluster 18 - Lewiston Loop - 2 | Middle Street | 3 |  |  | EXECUTED
801 | 0 | 0 | 0 |  | 2023-04-19 | South Sanford | PRATT & WHITNEY | 661D1 | Solar | 999 | 0 |  |  |  |  | 2023-06-12 | 2023-08-15 | 2023-10-10 |  |  |  | 2024-04-29 | 2023-12-14 | 2024-02-21 | [6 empty] | Q4 2026 | Fully Executed Interconnection Agreement | No | 2024-10-02 | Cluster 19 - Sanford-Quaker Hill - 2 | Pratt & Whitney | 3 |  | Not Required | RE_QUEUED_FullEx
802 | 0 | 0 | 0 |  | 2023-04-20 | Bridgton | BRIDGTON | 406D1 | Solar | 0 | 0 |  |  |  |  | 2023-07-12 | 2023-09-18 | [6 empty] | 2023-09-18 | [7 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 13 - Kimball Rd-Lovell - 2 | Kimball Road/Lovell | 3 |  | Not Required | WITHDRAWN
803 | 0 |  | 625 |  | 2023-04-21 | Belfast | BELFAST WEST SIDE | 803D4 | Solar | 999 | 0 |  |  |  |  | 2024-05-14 | 2024-07-17 |  |  |  |  | 2024-09-19 | 2024-09-03 | [7 empty] | Q4 2025 | Fully Executed Interconnection Agreement | No | 2025-01-23 | Cluster 17 - Detroit Guilford Belfast - 2 | Belfast | 3 |  | Not Required | RE_QUEUED_STUDY
804 | 0 | 0 | 0 |  | 2023-04-24 | Saco | GOOSEFARE | 630D4 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Louden-Biddeford IP - TBD | Louden | 3 |  | Not Required | WITHDRAWN
805 | 0 | 0 | 726 |  | 2023-04-25 | Manchester | MANCHESTER | 233D2 | Solar/Battery | 996 | 996 |  |  |  |  | 2025-02-19 | 2025-04-17 |  |  |  |  | 2025-07-25 | [9 empty] | Fully Executed Interconnection Agreement | No |  | Cluster XX - Augusta E-Puddledock-Bowman St - TBD | Augusta E/Puddledock/Bowman St | 3 |  | Not Required | RE_QUEUED
806 | 0 |  | 0 |  | 2023-04-27 | Newcastle | DAMARISCOTTA MILLS | 219D2 | Solar/Battery | 996 | 0 |  |  |  |  | 2023-06-13 | 2023-08-17 |  |  |  |  | 2023-12-11 | 2024-06-20 | 2024-08-21 | [6 empty] | Q4 2024 | Fully Executed Interconnection Agreement | No | 2025-03-17 | Cluster XX - Midcoast - TBD | Newcastle | 3 |  | Not Required | RE_QUEUED_STUDY
807 | 0 | 0 | 0 |  | 2023-05-03 | York | BRAGDON COMMONS | 689D1 | Solar | 0 | 0 | [10 empty] | 2024-01-29 | [8 empty] | Q4 2025 | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 19 - Sanford-Quaker Hill - 2 | Quaker Hill | 3 |  | Not Required | RE_QUEUED_FullEx
808 | 0 | 0 | 689 |  | 2023-05-04 | Lebanon | LEBANON | 695D2 | Solar | 975 | 0 |  |  |  |  | 2023-06-28 | 2023-08-31 |  |  |  |  | 2024-11-21 | 2024-07-17 | 2024-09-04 | [6 empty] | Q4 2024 | Fully Executed Interconnection Agreement | No | 2025-04-11 | Cluster 19 - Sanford-Quaker Hill - 2 | Sanford | 3 |  |  | RE_QUEUED_RESULTS
809 | 0 | 1 - MAST | 0 | RQP-1 | 2023-05-05 | Biddeford | MAY STREET | 634D4 | Solar/Battery | 999 | 0 |  |  |  |  | 2023-09-20 | 2023-11-28 |  |  |  |  | 2024-02-29 | 2025-08-28 | [7 empty] | Q2 2025 | Fully Executed Interconnection Agreement | No | 2024-10-17 | Cluster XX - Louden-Biddeford IP - TBD | Biddeford IP | 3 |  | Not Required | EXECUTED
810 | 0 | 0 | 0 |  | 2023-05-05 | Biddeford | MAY STREET | 634D4 | Solar/Battery | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Louden-Biddeford IP - TBD | Biddeford IP | 3 |  | Not Required | WITHDRAWN
811 | 0 | 0 | 798 |  | 2023-05-05 | Yarmouth | ELM STREET | 620D3 | Solar/Battery | 999 | 0 |  |  |  |  | 2024-02-23 | [5 empty] | 2025-03-25 | 2024-11-25 | 2025-02-11 | [6 empty] | Q4 2024 | Active | No |  | Cluster XX - Greater Portland - TBD | Elm St | 3 |  | Not Required | RE_QUEUED
812 | 0 | 0 | 0 |  | 2023-05-05 | South Portland | RIGBY | 650D4 | Solar/Battery | 999 | 0 |  |  |  |  | 2023-07-12 | 2023-09-14 |  |  |  |  | 2023-11-28 | [8 empty] | Q3 2026 | Fully Executed Interconnection Agreement | No | 2024-04-03 | Cluster XX - Greater Portland - TBD | Pleasant Hill | 3 |  | Not Required | EXECUTED
813 | 0 | 0 | 0 |  | 2023-05-05 | Sidney | SIDNEY | 242D1 | Solar/Battery | 996 | 0 |  |  |  |  | 2023-08-04 | 2023-10-09 |  |  |  |  | 2023-11-30 | [8 empty] | Q2 2026 | Fully Executed Interconnection Agreement | No | 2024-07-23 | Cluster XX - Augusta E-Puddledock-Bowman St - TBD | Augusta E/Puddledock/Bowman St | 3 |  | Not Required | EXECUTED
814 | 0 | 0 | 0 |  | 2023-05-08 | South Paris | NORWAY | 435D3 | Solar | 999 | 0 |  |  |  |  | 2023-07-18 | 2023-09-20 |  |  |  |  | 2023-11-20 | [8 empty] | Q4 2025 | Fully Executed Interconnection Agreement | No | 2024-03-07 | Cluster XX - Louden-Biddeford IP - TBD | Norway | 3 |  | Not Required | EXECUTED
815 | 0 | 1 - RUMF | 707 |  | 2023-05-09 | Rumford | RUMFORD | 447D2 | Solar | 2000 | 0 |  |  |  |  | 2025-09-09 | [15 empty] | Active | No |  | Cluster XX - Woodstock/ Roxbury/ Rumford - TBD | Rumford | 3 |  |  | RE_QUEUED
816 | 0 | 0 | 0 |  | 2023-05-10 | Baldwin | BALDWIN | 691D1 | Solar | 0 | 0 |  |  |  |  | 2023-06-30 | 2023-09-05 |  |  |  |  | 2023-10-16 | [8 empty] | Q4 2026 | WITHDRAWN | WITHDRAWN |  | Cluster 13 - Kimball Rd-Lovell - 2 | Kimball Road/Lovell | 3 |  | Not Required | RE_QUEUED_FullEx
817 | 0 |  | 757 |  | 2023-05-10 | Leeds | MONMOUTH | 457D2 | Solar | 999 | 0 |  |  |  |  | 2024-03-15 | N/A |  |  |  |  | 2025-06-27 | 2024-05-07 | 2024-07-12 | 2025-03-05 |  | 2025-04-24 | 2025-06-04 |  |  |  | Fully Executed Interconnection Agreement | No |  | Cluster XX - Augusta E-Puddledock-Bowman St - TBD | Monmouth | 3 |  | Not Required | RE_QUEUED
818 | 0 | 0 | 0 |  | 2023-05-11 | Buckfield | TURNER | 454D1 | Solar | 999 | 0 |  |  |  |  | 2023-07-18 | 2023-09-20 |  |  |  |  | 2023-11-20 | [8 empty] | Q4 2025 | Fully Executed Interconnection Agreement | No | 2023-12-15 | Cluster 18 - Lewiston Loop - 2 | Hotel Rd/Gulf/Middle St/Crowleys/Norway | 3 |  | Not Required | EXECUTED
819 | 0 | 1 - MONM | 817 | RQP-1 | 2023-05-11 | Monmouth | MONMOUTH | 457D2 | Solar | 999 | 0 |  |  |  |  | 2025-07-31 | 2025-10-01 | [13 empty] | Q4 2026 | Active | No |  | Cluster XX - Augusta E-Puddledock-Bowman St - TBD | Monmouth | 3 |  | Not Required | RE_QUEUED
820 | 0 | 0 | 0 |  | 2023-05-15 | Madison | SKOWHEGAN NORTH SIDE | 853D1 | Solar | 999 | 0 |  |  |  |  | 2023-07-26 | 2023-09-28 |  |  |  |  | 2023-12-13 | 2024-07-26 | 2024-09-30 | [6 empty] | Q2 2026 | Fully Executed Interconnection Agreement | No | 2024-04-25 | Cluster XX - Winslow/ County Rd/ Lakewood - TBD | Lakewood | 3 |  | Not Required | RE_QUEUED_STUDY
821 | 0 | 0 | 0 |  | 2023-05-15 | Vassalboro | MCCOYS | 237D1 | Solar | 999 | 0 |  |  |  |  | 2023-08-07 | 2023-10-11 | 2024-01-22 | 2024-03-05 |  |  | 2024-04-09 | [8 empty] | Q4 2025 | Fully Executed Interconnection Agreement | No | 2024-08-21 | Cluster XX - Augusta E-Puddledock-Bowman St - TBD | Augusta E/Puddledock/Bowman St | 3 |  | Not Required | EXECUTED
822 | 0 | 0 | 0 |  | 2023-05-19 | Carmel | CARMEL | 808D3 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 17 - Detroit Guilford Belfast - 2 | Detroit | 3 |  | Not Required | RE_QUEUED
823 | 0 | 0 | 782 |  | 2023-05-22 | Peru | RUMFORD INDUSTRIAL PARK | 466D1 | Solar | 999 | 0 |  |  |  |  | 2023-12-20 | 2024-02-27 |  |  |  |  | 2024-07-01 | [8 empty] | Q4 2025 | Fully Executed Interconnection Agreement | No | 2024-10-31 | Cluster XX - Woodstock/ Roxbury/ Rumford - TBD | Rumford IP | 3 |  | Not Required | #REF!
824 | 0 | 0 | 0 |  | 2023-05-24 | Rockland | PARK STREET | 239D7 | Solar/Battery | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Midcoast - TBD | Highland/Park St | 3 |  | Not Required | WITHDRAWN
825 | 0 | 0 | 0 |  | 2023-06-02 | Rockland | PARK STREET | 239D7 | Solar/DC BESS | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Midcoast - TBD | Highland/Park St | 3 |  | Not Required | WITHDRAWN
826 | 0 | 0 | 0 |  | 2023-06-05 | Athens | ATHENS | 827D1 | Solar | 0 | 0 | [10 empty] | 2023-12-28 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster XX - Wyman Area - TBD | Athens | 3 |  | Not Required | EXECUTED-WITHDRAWN
827 | 0 | 2 - MONM | 819 | RQP-2 | 2023-06-12 | Monmouth | MONMOUTH | 457D3 | Solar | 999 | 0 | [20 empty] | Active | No |  | Cluster XX - Augusta E-Puddledock-Bowman St - TBD | Monmouth | 3 |  | Not Required | RE_QUEUED
828 | 0 | 0 | 0 |  | 2023-06-15 | Brunswick | BRUNSWICK WEST SIDE | 213D3 | Solar | 0 | 0 |  |  |  |  | 2023-08-11 | 2023-10-20 | [5 empty] | 2024-04-22 | 2024-06-25 | 2024-08-01 |  | 2024-09-03 | 2024-11-01 |  |  |  | WITHDRAWN | WITHDRAWN |  | Cluster XX - Midcoast - TBD | Topsham | 3 |  | Not Required | RE_QUEUED_STUDY
829 | 0 | 0 | 0 |  | 2023-06-15 | Richmond | RICHMOND | 240D1 | Solar | 999 | 0 |  |  |  |  | 2023-08-23 | 2023-10-25 |  |  |  |  | 2024-02-15 | 2023-11-20 | 2023-01-05 | [6 empty] | Q1 2026 | Fully Executed Interconnection Agreement | No | 2024-09-26 | Cluster XX - Augusta E-Puddledock-Bowman St - TBD | Augusta E/Puddledock/Bowman St | 3 |  |  | RE_QUEUED_FullEx
830 | 0 | 0 | 0 |  | 2023-06-20 | Richmond | RICHMOND | 240D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Augusta E-Puddledock-Bowman St - TBD | Augusta E/Puddledock/Bowman St | 3 |  |  | WITHDRAWN
831 | 0 | 0 | 0 |  | 2023-06-20 | Lisbon | LISBON FALLS | 232D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 18 - Lewiston Loop - 2 | Hotel Rd/Gulf/Middle St/Crowleys | 3 |  |  | WITHDRAWN
832 | 0 | 0 | 0 |  | 2023-07-05 | Baldwin | BALDWIN | 691D1 | Solar | 0 | 0 |  |  |  |  | 2023-11-15 | 2024-01-25 |  |  |  |  | 2024-04-23 | [8 empty] | Q4 2024 | WITHDRAWN | WITHDRAWN |  | Cluster 13 - Kimball Rd-Lovell - 2 | Kimball Road/Lovell | 3 |  | Not Required | EXECUTED
833 | 0 | 0 | 0 |  | 2023-07-07 | Carmel | CARMEL | 808D3 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 17 - Detroit Guilford Belfast - 2 | Detroit | 3 |  | Not Required | RE_QUEUED
834 | 0 |  | 0 |  | 2023-07-20 | Fryeburg | FRYEBURG TAP | 405D1 | Solar | 999 | 0 |  |  |  |  | 2023-09-05 | 2023-11-08 |  |  |  |  | 2023-12-06 | 2024-10-22 | 2024-12-19 | [6 empty] | Q4 2025 | Fully Executed Interconnection Agreement | No | 2024-04-18 | Cluster 13 - Kimball Rd-Lovell - 2 | Kimball Road/Lovell | 3 |  | Not Required | EXECUTED
835 | 0 | 1 - LEED | 587 | RQP-1 | 2023-07-20 | Livermore | LEEDS | 471D1 | Solar/Battery | 4999 | 0 |  |  |  |  | 2023-09-15 | 2023-11-20 |  |  |  |  | 2024-01-04 | 2025-06-25 | 2025-08-28 | [6 empty] | Q1 2026 | Fully Executed Interconnection Agreement | No |  | Cluster XX - Sturtevant/ Leeds/ Livermore/ Ludden/ Riley_TBD | Leeds | 3 |  |  | RE_QUEUED_FullEx
836 | 0 | 0 | 0 |  | 2023-07-20 | Starks | ANSON | 801D1 | Solar | 0 | 0 | [10 empty] | 2024-04-29 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster XX - Winslow/ County Rd/ Lakewood - TBD | Lakewood | 3 |  | Not Required | EXECUTED
837 | 0 | 0 | 0 |  | 2023-07-20 | Starks | ANSON | 801D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Winslow/ County Rd/ Lakewood - TBD | Lakewood | 3 |  | Not Required | WITHDRAWN
838 | 0 | 1 - NOAU | 769 | RQP-1 | 2023-07-24 | Augusta | NORTH AUGUSTA | 272D2 | Solar/DC BESS | 996 | 0 |  |  |  |  | 2024-02-12 | [10 empty] | 2025-05-14 | 2025-07-21 |  |  | Q4 2024 | Active | No |  | Cluster XX - Augusta E-Puddledock-Bowman St - TBD | North Augusta | 3 |  | Not Required | RE_QUEUED
839 | 0 |  | 647 |  | 2023-07-26 | Strong | STURTEVANT | 858D1A | Solar | 0 | 0 | 2025-02-26 | 2025-04-02 | 2025-06-10 | 2025-07-25 | [15 empty] | Q3 2025 | WITHDRAWN | WITHDRAWN |  | Cluster XX - Sturtevant/ Leeds/ Livermore/ Ludden/ Riley_TBD | Sturtevant | 3 |  | Not Required | #REF!
840 | 0 | 0 | 0 |  | 2023-08-02 | Gray | GRAY | 416D3 | Solar | 0 | 0 |  |  |  |  | 2024-07-08 | 2024-09-09 | [14 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Greater Portland - TBD | Elm St | 3 |  | Not Required | STUDY
841 | 0 | 0 | 0 |  | 2023-08-09 | Bethel | LOCKES MILLS | 429D1 | Solar | 999 | 0 |  |  |  |  | 2023-10-06 | 2023-12-14 |  |  |  |  | 2024-02-14 | [8 empty] | Q1 2026 | Fully Executed Interconnection Agreement | No | 2024-06-27 | Cluster XX - Woodstock/ Roxbury/ Rumford - TBD | Woodstock | 3 |  | Not Required | EXECUTED
842 | 0 | 0 | 0 |  | 2023-08-10 | Bethel | LOCKES MILLS | 429D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Woodstock/ Roxbury/ Rumford - TBD | Woodstock | 3 |  | TBD | WITHDRAWN
843 | 0 | 0 | 0 |  | 2023-08-10 | Bridgton | BRIDGTON | 406D2 | Solar | 0 | 0 |  |  |  |  | 2024-02-16 | 2024-04-25 | [14 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 13 - Kimball Rd-Lovell - 2 | Kimball Road/Lovell | 3 |  | Not Required | WITHDRAWN
844 | 0 | 0 | 0 |  | 2023-08-23 | Bath | WASHINGTON ST (BATH) | 204D6 | Solar | 0 | 0 | [10 empty] | 2024-03-27 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster XX - Midcoast - TBD | Bath | 3 |  | Not Required | EXECUTED-WITHDRAWN
845 | 0 |  | 823 |  | 2023-08-25 | Peru | RUMFORD INDUSTRIAL PARK | 466D1 | Solar | 999 | 0 |  |  |  |  | 2024-08-16 | 2024-10-21 |  |  |  |  | 2024-11-20 | [8 empty] | Q4 2025 | Fully Executed Interconnection Agreement | No | 2025-03-24 | Cluster XX - Woodstock/ Roxbury/ Rumford - TBD | Rumford IP | 3 |  | Not Required | STUDY
846 | 0 | 0 | 839 | 0 | 2023-08-30 | Farmington | STURTEVANT | 858D1A | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Sturtevant/ Leeds/ Livermore/ Ludden/ Riley_TBD | Sturtevant | 3 |  | Not Required | RE_QUEUED
847 | 0 | 0 | 0 |  | 2023-08-30 | Skowhegan | SKOWHEGAN NORTH SIDE | 853D2 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Winslow/ County Rd/ Lakewood - TBD | Lakewood | 3 |  | Not Required | RE_QUEUED
848 | 0 | 0 | 0 |  | 2023-09-05 | Waldoboro | MANKTOWN ROAD | 234D1 | Solar | 999 | 0 |  |  |  |  | 2023-10-11 | 2023-12-15 |  |  |  |  | 2024-01-16 | [8 empty] | Q2 2025 | Fully Executed Interconnection Agreement | Yes | 2024-02-16 | Cluster XX - Midcoast - TBD | Highland/Park St | 3 |  | Not Required | EXECUTED
849 | 0 | 0 | 0 |  | 2023-09-26 | Turner | TURNER | 454D1 | Solar | 994 | 0 |  |  |  |  | 2024-01-10 | 2024-03-15 |  |  |  |  | 2024-04-15 | [8 empty] | Q4 2025 | Fully Executed Interconnection Agreement | No | 2024-08-08 | Cluster 18 - Lewiston Loop - 2 | Hotel Rd/Gulf/Middle St/Crowleys/Norway | 3 |  | Not Required | EXECUTED
850 | 0 | 0 | 0 |  | 2023-09-28 | Freedom | THORNDIKE TAP | 857D1 | Solar | 0 | 0 |  |  |  |  | 2023-10-25 | 2024-01-03 |  |  |  |  | 2024-02-09 | [9 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 17 - Detroit Guilford Belfast - 2 | Belfast | 3 |  | Not Required | #REF!
851 | 0 | 0 | 0 |  | 2023-10-02 | Damariscotta | DAMARISCOTTA MILLS | 219D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Midcoast - TBD | Newcastle | 3 |  | Not Required | RE_QUEUED
852 | 0 |  | 0 |  | 2023-10-17 | Poland | MECHANIC FALLS | 431D1 | Solar | 999 | 0 |  |  |  |  | 2025-02-06 | 2025-04-09 |  |  |  |  | 2025-04-09 | 2025-04-24 |  | 2025-06-25 | 2025-08-28 |  |  |  |  | Q2 2025 | Fully Executed Interconnection Agreement | No | 2025-08-12 | Cluster 18 - Lewiston Loop - 2 | Norway | 3 |  | Not Required | QUEUED
853 | 0 | 0 | 0 |  | 2023-11-01 | China | SOUTH CHINA | 244D2 | Solar/Battery | 0 | 0 | [10 empty] | 2024-06-26 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster XX - Augusta E-Puddledock-Bowman St - TBD | Augusta E/Puddledock/Bowman St | 3 |  | Not Required | EXECUTED
854 | 0 |  | 0 |  | 2023-11-28 | Bath | BATH NORTH END | 206D1 | Solar | 650 | 0 |  |  |  |  | 2024-01-31 | 2024-04-04 | 2024-05-07 | 2024-06-19 |  |  | 2024-08-20 | 2025-03-25 | 2025-05-27 | [6 empty] | Q3 2025 | Fully Executed Interconnection Agreement | No |  | Cluster XX - Midcoast - TBD | Bath | 3 |  | Not Required | EXECUTED
855 | 0 | 0 | 0 |  | 2023-12-07 | Embden | EMBDEN | 868D1 | Solar | 999 | 0 |  |  |  |  | 2024-02-16 | 2024-04-16 |  |  |  |  | 2024-05-13 | [8 empty] | Q1 2027 | Fully Executed Interconnection Agreement | No | 2024-11-14 | Cluster XX - Wyman Area - TBD | Embden | 3 |  | Not Required
856 | 0 | 0 | 0 |  | 2023-12-11 | Freeport | FREEPORT | 225D3 | Solar | 990 | 0 |  |  |  |  | 2024-07-03 | 2024-09-05 | 2024-11-14 | 2024-12-20 |  |  | 2025-01-23 | [8 empty] | Q3 2025 | Fully Executed Interconnection Agreement | No | 2025-05-28 | Cluster XX - Greater Portland - TBD | Elm St | 3
857 | 0 | 0 | 0 |  | 2023-12-11 | North Yarmouth | ELM STREET | 620D4 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Greater Portland - TBD | Elm St | 3 |  | Not Required
858 | 0 | 1 - GUIL | 723 | RQP-1 | 2023-12-28 | Parkman | GUILFORD | 821D1 | Solar | 4990 | 0 |  |  |  |  | 2025-05-08 | 2025-07-07 | 2025-09-18 | [13 empty] | Active | No |  | Cluster 17 - Detroit Guilford Belfast - 2 | Guilford | 3
859 | 0 | 0 | 0 |  | 2024-01-04 | West Paris | TRAP CORNER | 453D1 | Solar | 996 | 0 |  |  |  |  | 2024-02-02 | 2024-04-10 |  |  |  |  | 2024-04-23 | [8 empty] | Q2 2025 | Fully Executed Interconnection Agreement | Yes | 2024-05-10 | Cluster XX - Roxbury-Rumford-Woodstock - TBD | Woodstock | 3 |  | Not Required
860 | 0 | 0 | 0 |  | 2024-01-29 | Bristol | BRISTOL | 210D2 | Solar/Battery | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Midcoast - TBD | Newcastle | 3 |  | Not Required
861 | 0 | 0 | 0 |  | 2024-01-30 | Benton | WINSLOW | 870D1 | Solar | 0 | 0 |  |  |  |  | 2024-03-08 | 2024-05-10 | [14 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Winslow/ County Rd/ Lakewood - TBD | Winslow-County Rd | 3 |  | Not Required
862 | 0 | 0 | 0 |  | 2024-02-06 | Lebanon | LEBANON | 695D2 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 19 - Sanford-Quaker Hill - 2 | Sanford | 3 |  | Not Required
863 | 0 |  | 0 |  | 2024-02-06 | Lisbon | LISBON | 231D2 | Solar | 999 | 0 |  |  |  |  | 2024-03-28 | 2024-06-03 |  |  |  |  | 2024-07-19 | 2025-03-18 | 2025-05-19 | [6 empty] | Q2 2025 | Fully Executed Interconnection Agreement | No | 2025-01-23 | Cluster XX - Lewiston Loop - TBD | Hotel Rd/Gulf/Middle St/Crowleys | 3 |  | Not Required
864 | 0 | 0 | 0 |  | 2024-02-14 | Raymond | RAYMOND 34 KV | 444D3 | Solar | 996 | 0 |  |  |  |  | 2024-06-17 | 2024-08-21 |  |  |  |  | 2024-10-03 | [8 empty] | Q1 2026 | Fully Executed Interconnection Agreement | No | 2025-02-10 | Cluster XX - Raymond - TBD | Raymond | 3 |  | Not Required
865 | 0 |  | 0 |  | 2024-02-16 | West Bath | BATH 34 | 261D4 | Solar | 975 | 0 |  |  |  |  | 2024-04-09 | 2024-06-12 |  |  |  |  | 2024-07-05 | 2025-01-02 | 2025-03-10 | 2025-04-07 | 2025-06-10 |  |  |  |  | Q2 2026 | Fully Executed Interconnection Agreement | No | 2025-01-22 | Cluster XX - Midcoast - TBD | Bath | 3 |  | Not Required
866 | 0 |  | 857 |  | 2024-02-22 | Yarmouth | ELM STREET | 620D2 | Solar | 975 | 0 |  |  |  |  | 2025-05-05 | 2025-07-10 |  |  |  |  | 2025-08-13 | [8 empty] | Q1 2025 | Fully Executed Interconnection Agreement | No |  | Cluster XX - Greater Portland - TBD | Elm St | 3 |  | Not Required
867 | 0 | 0 | 866 |  | 2024-02-23 | Yarmouth | ELM STREET | 620D2 | Solar | 0 | 0 | [19 empty] | Q1 2025 | WITHDRAWN | WITHDRAWN |  | Cluster XX - Greater Portland - TBD | Elm St | 3 |  | Not Required
868 | 0 | 0 | 0 |  | 2024-02-28 | Sidney | SIDNEY | 242D1 | Solar | 0 | 0 | [10 empty] | 2024-09-12 | [8 empty] | Q2 2025 | EXECUTED-WITHDRAWN | WITHDRAWN | 2025-01-27 | Cluster XX - Augusta E-Puddledock-Bowman St - TBD | Augusta E/Puddledock/Bowman St | 3 |  | Not Required
869 | 0 | 0 | 0 |  | 2024-03-05 | Bath | BATH NORTH END | 206D1 | Solar/Battery | 0 | 0 |  |  |  |  | 2024-11-12 | 2025-01-21 | [14 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 19 - Sanford-Quaker Hill - 2 | Sanford | 3 |  | Not Required
870 | 0 |  | 0 |  | 2024-03-12 | Acton | BUTLER'S CORNER | 612D2 | Solar | 600 | 0 |  |  |  |  | 2024-04-23 | 2024-06-25 |  |  |  |  | 2024-08-16 | [8 empty] | Q4 2025 | Fully Executed Interconnection Agreement | No | 2024-12-23 | Cluster 19 - Sanford-Quaker Hill - 2 | Sanford | 3 |  | Not Required
871 | 0 | 0 | 0 |  | 2024-03-21 | Augusta | SIDNEY | 242D1 | Solar | 0 | 0 | [19 empty] | Q2 2025 | WITHDRAWN | WITHDRAWN |  | Cluster XX - Augusta E-Puddledock-Bowman St - TBD | Augusta E/Puddledock/Bowman St | 3 |  | Not Required
872 | 0 |  | 0 |  | 2024-03-21 | Swanville | BELFAST 115 | 874D1 | Solar | 2000 | 0 |  |  |  |  | 2024-05-17 | 2024-07-24 | 2024-09-13 | 2024-10-28 |  |  | 2025-03-10 | 2024-12-02 | 2025-02-06 | [6 empty] | Q3 2026 | Fully Executed Interconnection Agreement | No |  | Cluster 17 - Detroit Guilford Belfast - 2 | Belfast | 3
873 | 0 | 0 | 0 |  | 2024-03-27 | Hollis | BAR MILLS | 678D1 | Solar | 0 | 0 | [10 empty] | 2024-08-29 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster xx - Louden-Biddeford IP - TBD | West Buxton | 3 |  | Not Required
874 | 0 | 0 | 0 |  | 2024-05-10 | Fryeburg | FRYEBURG | 415D2 | Solar | 0 | 0 |  |  |  |  | 2024-06-26 | 2024-08-28 |  |  |  |  | 2024-11-07 | [8 empty] | Q3 2025 | WITHDRAWN | WITHDRAWN |  | Cluster XX - Kimball Rd-Lovell - TBD | Kimball Road/Lovell | 3 |  | Not Required
875 | 0 | 0 | 0 |  | 2024-05-13 | Athens | ATHENS | 827D2 | Solar | 0 | 0 | [10 empty] | 2024-11-01 | [8 empty] | Q3 2025 | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster XX - Wyman Area - TBD | Athens | 3 |  | Not Required
876 | 0 | 0 | 0 |  | 2024-05-23 | Sidney | SIDNEY | 242D2 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Augusta E-Puddledock-Bowman St - TBD | Augusta E/Puddledock/Bowman St | 3 |  | Not Required
877 | 0 | 2 - NOAU | 838 | RQP-2 | 2024-05-28 | Augusta | NORTH AUGUSTA | 272D6 | Solar | 950 | 0 | [19 empty] | Q3 2025 | Active | No |  | Cluster XX - Augusta E-Puddledock-Bowman St - TBD | North Augusta | 3 |  | Not Required
878 | 0 | 3 - NOAU | 877 | RQP-3 | 2024-05-28 | Augusta | NORTH AUGUSTA | 272D6 | Solar | 999 | 0 | [19 empty] | Q3 2025 | Active | No |  | Cluster XX - Augusta E-Puddledock-Bowman St - TBD | North Augusta | 3 |  | Not Required
879 | 0 | 2 - PDRD | 692 | RQP-2 | 2024-05-28 | Readfield | PUDDLEDOCK ROAD | 262D1 | Solar | 999 | 0 |  |  |  |  | 2024-11-26 | 2025-04-04 |  |  |  |  | 2025-07-21 | 2025-02-12 | 2025-04-04 | [6 empty] | Q3 2025 | Fully Executed Interconnection Agreement | No |  | Cluster XX - Augusta E-Puddledock-Bowman St - TBD | Augusta E/Puddledock/Bowman St | 3 |  | Not Required
880 | 0 |  | 0 |  | 2024-05-29 | Winterport | PROSPECT | 846D1 | Solar | 900 | 0 |  |  |  |  | 2024-06-28 | 2024-08-30 | 2024-10-21 | 2024-12-05 |  |  | 2024-12-20 | 2025-04-11 | 2025-06-13 | [6 empty] | Q4 2025 | Fully Executed Interconnection Agreement | No |  | Cluster 17 - Detroit Guilford Belfast - 2 | Belfast | 3 |  | Not Required
881 | 0 | 1 - MEFA | 0 | RQP-1 | 2024-05-29 | Mechanic Falls | MECHANIC FALLS | 431D3 | Solar | 999 | 0 | [19 empty] | Q4 2025 | Active | No |  | Cluster 18 - Lewiston Loop - 2 | Norway | 3 |  | Not Required
882 | 0 | 2 - MEFA | 0 | RQP-2 | 2024-05-29 | Poland | MECHANIC FALLS | 431D1 | Solar | 999 | 0 | [19 empty] | Q4 2025 | Active | No |  | Cluster 18 - Lewiston Loop - 2 | Norway | 3 |  | Not Required
883 | 0 | 0 | 0 |  | 2024-05-29 | Stockton Springs | PROSPECT | 846D1 | Solar | 0 | 0 |  |  |  |  | 2025-02-06 | 2025-09-12 | [5 empty] | 2025-07-18 | [7 empty] | Q4 2025 | WITHDRAWN | WITHDRAWN |  | Cluster 17 - Detroit Guilford Belfast - 2 | Belfast | 3 |  | Not Required
884 | 0 | 0 | 0 |  | 2024-05-29 | Winterport | PROSPECT | 846D1 | Solar | 0 | 0 | [19 empty] | Q4 2025 | WITHDRAWN | WITHDRAWN |  | Cluster 17 - Detroit Guilford Belfast - 2 | Belfast | 3 |  | Not Required
885 | 0 |  | 0 |  | 2024-06-04 | Limerick | LIMERICK | 632D1 | Solar | 0 | 0 | [10 empty] | 2025-04-14 | [8 empty] | Q4 2024 | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 13 - Kimball Rd-Lovell - 2 | Kimball Road/Lovell | 3 |  | Not Required
886 | 0 | 0 | 0 |  | 2024-06-17 | Jay | RILEY | 449D2 | Solar | 0 | 0 | [10 empty] | 2025-02-26 | [8 empty] | Q4 2024 | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster XX - Sturtevant-Leeds-Livermore-Ludden-Riley - TBD | Riley | 3 |  | Not Required
887 | 0 |  | 0 |  | 2024-06-18 | Andover | ANDOVER | 400D1 | Solar | 0 | 0 | [10 empty] | 2025-03-14 | [8 empty] | Q4 2024 | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster XX - Woodstock/ Roxbury/ Rumford - TBD | Roxbury | 3 |  | Not Required
888 | 0 | 0 | 0 |  | 2024-06-18 | Naples | BRIDGTON | 406D2 | Solar | 999 | 0 | 2024-08-13 | 2024-09-11 | 2024-11-11 | 2024-12-27 | [6 empty] | 2025-03-24 | [8 empty] | Q2 2026 | Fully Executed Interconnection Agreement | No |  | Cluster 13 - Kimball Rd-Lovell - 2 | Kimball Road/Lovell | 3 |  | Not Required
889 | 0 | 0 | 805 |  | 2024-06-26 | Manchester | MANCHESTER | 233D1 | Solar | 0 | 0 | [19 empty] | Q2 2024 | WITHDRAWN | WITHDRAWN |  | Cluster XX - Augusta E-Puddledock-Bowman St - TBD | Augusta E/Puddledock/Bowman St | 3 |  | Not Required
890 | 0 | 0 | 0 |  | 2024-07-02 | Skowhegan | SKOWHEGAN SOUTH SIDE | 854D2 | Solar | 600 | 0 |  |  |  |  | 2024-08-09 | 2024-10-08 |  |  |  |  | 2024-11-07 | [8 empty] | Q4 2024 | Fully Executed Interconnection Agreement | No | 2025-04-08 | Cluster XX - Augusta E-Puddledock-Bowman St - TBD | Augusta E/Puddledock/Bowman St | 3 |  | Not Required
891 | 0 | 0 | 0 |  | 2024-07-18 | South Portland | RIGBY | 650D4 | Battery | 0 | 0 |  |  |  |  | 2025-06-13 | 2025-08-19 | [13 empty] | Q4 2026 | WITHDRAWN | WITHDRAWN |  | Cluster XX - Winslow/ County Rd/ Lakewood - TBD | Lakewood | 3
892 | 0 | 0 | 0 |  | 2024-07-18 | Scarborough | PLEASANT HILL | 644D1 | Battery | 0 | 0 |  |  |  |  | 2025-06-13 | 2025-08-19 | [13 empty] | Q4 2026 | WITHDRAWN | WITHDRAWN |  | Cluster XX - Greater Portland - TBD | Pleasant Hill | 3
893 | 0 | 0 | 0 |  | 2024-07-18 | Westbrook | BRIGHTON AVE | 611D1 | Battery | 0 | 0 | [19 empty] | Q4 2026 | WITHDRAWN | WITHDRAWN |  | Cluster XX - Greater Portland - TBD | Pleasant Hill | 3
894 | 0 | 0 | 0 |  | 2024-07-18 | Westbrook | SPRING STREET | 668D1 | Battery | 0 | 0 |  |  |  |  | 2025-06-13 | 2025-08-19 | [13 empty] | Q4 2026 | WITHDRAWN | WITHDRAWN |  | Cluster XX - Greater Portland - TBD | Sewall St. | 3
895 | 0 |  | 0 |  | 2024-07-18 | South Paris | NORWAY | 435D1 | Solar/Battery | 1990 | 1818 |  |  |  |  | 2024-08-29 | 2024-11-04 |  |  |  |  | 2025-01-03 | [8 empty] | Q4 2026 | Fully Executed Interconnection Agreement | No |  | Cluster XX - Greater Portland - TBD | Spring St | 3
896 | 0 | 0 | 0 |  | 2024-07-24 | Pittsfield | PITTSFIELD | 842D1 | Solar | 0 | 0 | [10 empty] | 2025-01-22 | [8 empty] | Q3 2025 | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster XX - Louden-Biddeford IP - TBD | Norway | 3
897 | 0 | 0 | 0 |  | 2024-07-25 | Freeport | FREEPORT | 225D4 | Battery | 0 | 0 | [19 empty] | Q4 2026 | WITHDRAWN | WITHDRAWN |  | Cluster XX - Detroit-Guilford-Belfast - TBD | Detroit | 3
898 | 0 | 0 | 0 |  | 2024-08-01 | Gorham | MOSHERS | 635D2 | Battery | 0 | 0 | [19 empty] | Q4 2026 | WITHDRAWN | WITHDRAWN |  | Cluster XX - Greater Portland - TBD | Elm St | 3
899 | 0 | 3 - DEXT | 0 | RQP-3 | 2024-08-26 | Dexter | DEXTER | 813D3 | Solar | 999 | 0 | [20 empty] | Active | No |  | Cluster XX - Greater Portland - TBD | Elm St | 3
900 | 0 |  | 0 |  | 2024-09-03 | Warren | THOMASTON CREEK | 246D3 | Solar | 0 | 0 |  |  |  |  | 2024-11-15 | 2025-01-15 | [5 empty] | 2025-02-21 | 2025-04-23 | [6 empty] | Q4 2026 | WITHDRAWN | WITHDRAWN |  | Cluster XX - Midcoast - TBD | Highland/Park St | 3
901 | 0 |  | 0 |  | 2024-09-03 | Clinton | CLINTON | 810D1 | Solar | 975 | 0 |  |  |  |  | 2024-10-04 | 2024-12-09 |  |  |  |  | 2025-01-08 | [8 empty] | Q4 2026 | Fully Executed Interconnection Agreement | No | 2025-05-15 | Cluster XX - Midcoast - TBD | Park St. | 3 |  | Not Required
902 | 0 |  | 895 |  | 2024-09-05 | South Paris | NORWAY | 435D1 | Solar | 999 | 0 |  |  |  |  | 2025-02-12 | 2025-04-16 |  |  |  |  | 2025-04-24 | [8 empty] | Q4 2025 | Active | No | 2025-08-26 | Cluster XX - Winslow/ County Rd/ Lakewood - TBD | Detroit | 3 |  | Not Required
903 | 0 |  | 0 |  | 2024-09-06 | Hollis | BONNY EAGLE | 610D1 | Solar | 999 | 0 |  |  |  |  | 2024-10-25 | 2025-01-03 |  |  |  |  | 2025-04-01 | [8 empty] | Q4 2025 | Fully Executed Interconnection Agreement | No | 2025-07-22 | Cluster 18 - Lewiston Loop - 2 | Norway | 3 |  | Not Required
904 | 0 | 0 | 0 |  | 2024-09-09 | Richmond | RICHMOND | 240D1 | Solar | 0 | 0 |  |  |  |  | 2024-10-18 | 2024-12-16 |  |  |  |  | 2025-02-13 | [8 empty] | Q4 2026 | WITHDRAWN | WITHDRAWN |  | Cluster XX - Augusta E-Puddledock-Bowman St - TBD | Augusta E/Puddledock/Bowman St | 3
905 | 0 | 0 | 0 |  | 2024-09-10 | Cornish | HIRAM TAP | 692D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 13 - Kimball Rd-Lovell - 2 | Kimball Road/Lovell | 3
906 | 0 | 0 | 0 |  | 2024-09-11 | Corinna | CORINNA | 811D1 | Solar | 0 | 0 | 2024-11-11 |  |  |  | 2024-11-11 | [15 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 17 - Detroit Guilford Belfast - 2 | Detroit | 3
907 | 0 | 0 |  |  | 2024-09-11 | Starks | ANSON | 801D1 | Solar | 0 | 0 |  |  |  |  | 2024-11-12 | 2024-03-10 | [6 empty] | N/A | 2025-01-08 | [5 empty] | Q4 2026 | WITHDRAWN | WITHDRAWN |  | Cluster XX - Winslow/ County Rd/ Lakewood - TBD | Lakewood | 3
908 | 0 | 0 | 0 |  | 2024-09-12 | Penobscot | BUCKSPORT | 806D2 | Solar | 999 | 0 | 2024-11-18 | 2024-12-26 | 2025-01-23 | 2025-03-06 | [6 empty] | 2025-04-09 | [8 empty] | Q1 2026 | Fully Executed Interconnection Agreement | No |  | Cluster 17 - Detroit Guilford Belfast - 2 | Bucksport | 3 |  | Not Required
909 | 0 | 0 | 0 |  | 2024-09-12 | Carmel | CARMEL | 808D2 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 17 - Detroit Guilford Belfast - 2 | Detroit | 3
910 | 0 | 0 | 909 |  | 2024-09-12 | Levant | CARMEL | 808D3 | Solar | 0 | 0 | 2025-03-31 | 2025-04-28 | [17 empty] | Q1 2026 | WITHDRAWN | WITHDRAWN |  | Cluster 17 - Detroit Guilford Belfast - 2 | Detroit | 3
911 | 0 | 1 - CARM | 910 | RQP-1 | 2024-09-12 | Levant | CARMEL | 808D3 | Solar | 999 | 0 |  |  |  |  | 2025-08-08 | 2025-10-14 | [14 empty] | Active | No |  | Cluster 17 - Detroit Guilford Belfast - 2 | Detroit | 3
912 | 0 |  | 0 |  | 2024-09-12 | Dover-Foxcroft | DOVER | 815D2 | Solar | 0 | 0 | 2025-02-18 | 2025-03-25 | [17 empty] | Q4 2025 | WITHDRAWN | WITHDRAWN |  | Cluster 17 - Detroit Guilford Belfast - 2 | Guilford | 3
913 | 0 | 2 - RUMF | 815 |  | 2024-10-08 | Mexico | RUMFORD | 447D4 | Solar | 4999 | 0 | [19 empty] | Q4 2026 | Active | No |  | Cluster XX - Woodstock/ Roxbury/ Rumford - TBD | Rumford | 3
914 | 0 | 3 - MONM | 827 | RQP-3 | 2024-10-08 | Monmouth | MONMOUTH | 457D2 | Solar | 4999 | 0 | [19 empty] | Q4 2026 | Active | No |  | Cluster XX - Augusta E-Puddledock-Bowman St - TBD | Monmouth | 3
915 | 0 | 0 | 0 |  | 2024-10-08 | Wilton | WILTON | 885D1 | Solar | 0 | 0 |  |  |  |  | 2024-11-25 | [15 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Sturtevant/ Leeds/ Livermore/ Ludden/ Riley_TBD | Sturtevant | 3
916 | 0 |  | 0 |  | 2024-10-16 | Baldwin | BALDWIN | 691D1 | Solar | 0 | 0 | 2024-12-16 | 2025-01-22 | 2025-03-18 | [16 empty] | Q4 2025 | WITHDRAWN | WITHDRAWN |  | Cluster 13 - Kimball Rd-Lovell - 2 | Kimball Road/Lovell | 3
917 | 0 | 1 - BUCK | 0 |  | 2024-10-16 | Penobscot | BUCKSPORT | 806D2 | Solar | 999 | 0 | 2025-06-16 | 2025-07-22 | 2025-08-19 | 2025-09-30 | [15 empty] | Q4 2025 | Active | No |  | Cluster 17 - Detroit Guilford Belfast - 2 | Bucksport | 3
918 | 0 | 0 | 0 |  | 2024-11-06 | Springvale | BUTLER'S CORNER | 612D1 | Solar | 0 | 0 |  |  |  |  | 2024-12-24 | 2025-03-03 | [13 empty] | Q1 2026 | WITHDRAWN | WITHDRAWN |  | Cluster 19 - Sanford-Quaker Hill - 2 | Sanford | 3
919 | 0 | 0 | 0 |  | 2024-11-14 | Searsport | SEARSPORT | 850D2 | Solar | 0 | 0 | [19 empty] | Q1 2026 | WITHDRAWN | WITHDRAWN |  | Cluster 17 - Detroit Guilford Belfast - 2 | Belfast | 3
920 | 0 |  | 0 |  | 2024-11-18 | Biddeford | BIDDEFORD PUMP | 605D2 | Solar | 0 | 0 | [10 empty] | 2025-04-09 | [8 empty] | Q2 2027 | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster XX - Louden-Biddeford IP - TBD | Louden | 3
921 | 0 |  | 0 |  | 2024-12-03 | Arundel | MAY STREET | 634D1 | Solar | 0 | 0 |  |  |  |  | 2025-01-13 | 2025-03-19 |  |  |  |  | 2025-04-07 | [8 empty] | Q4 2026 | WITHDRAWN | WITHDRAWN |  | Cluster XX - Louden-Biddeford IP - TBD | Louden | 3
922 | 0 | 2 - LEED | 835 |  | 2024-12-03 | Leeds | LEEDS | 471D2 | Solar | 450 | 0 | [19 empty] | Q3 2026 | Fully Executed Interconnection Agreement | No |  | Cluster XX - Sturtevant-Leeds-Livermore-Ludden-Riley - TBD | Leeds | 3
923 | 0 | 0 | 907 |  | 2024-12-06 | Starks | ANSON | 801D1 | Solar | 0 | 0 | [19 empty] | Q1 2026 | WITHDRAWN | WITHDRAWN |  | Cluster XX - Winslow-County Rd-Lakewood - TBD | Lakewood | 3
924 | 0 |  | 0 | RQP-1 | 2024-12-10 | Dover-Foxcroft | DOVER | 815D1 | Solar | 975 | 0 |  |  |  |  | 2025-07-11 | 2025-09-05 |  |  |  |  | 2025-09-25 | [8 empty] | Q3 2025 | Fully Executed Interconnection Agreement | No |  | Cluster 17 - Detroit Guilford Belfast - 2 | Guilford | 3
925 | 0 | 0 | 888 |  | 2024-12-13 | Bridgton | BRIDGTON | 406D2 | Solar | 0 | 0 | [19 empty] | Q3 2026 | WITHDRAWN | WITHDRAWN |  | Cluster XX - Kimball Rd-Lovell - TBD | Kimball Road/Lovell | 3
926 | 0 | 1 - NORW | 902 | RQP-1 | 2025-01-15 | South Paris | NORWAY | 435D1 | Solar/Battery | 4999 | 4999 |  |  |  |  | 2025-06-25 | [6 empty] | 2025-07-14 | [7 empty] | Q2 2026 | Active | No |  | Cluster 18 - Lewiston Loop - 2 | Norway | 3
927 | 0 |  | 0 |  | 2025-01-24 | Standish | SHAWS MILL ROAD | 660D2 | Solar | 990 | 0 |  |  |  |  | 2025-03-12 | 2025-05-09 |  |  |  |  | 2025-06-04 | [8 empty] | Q4 2025 | Fully Executed Interconnection Agreement | No | 2025-10-07 | Cluster XX - Raymond - TBD | Raymond | 3 |  | Not Required
928 | 0 | 0 | 925 |  | 2025-02-13 | Bridgton | BRIDGTON | 406D2 | Battery | 0 | 0 |  |  |  |  | 2025-06-04 | 2025-08-08 | [13 empty] | Q3 2026 | WITHDRAWN | WITHDRAWN |  | Cluster XX - Kimball Rd-Lovell - TBD | Kimball Road/Lovell | 3
929 | 0 | 0 | 0 |  | 2025-02-26 | South Portland | PLEASANT HILL | 644D1 | Battery | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Greater Portland - TBD | Pleasant Hill | 3
930 | 0 | 0 | 0 |  | 2025-02-26 | Cape Elizabeth | CAPE ELIZABETH | 613D1 | Battery | 0 | 0 |  |  |  |  | 2025-06-26 | [15 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Greater Portland - TBD | Pleasant Hill | 3
931 | 0 | 0 | 0 |  | 2025-02-26 | South Portland | HINCKLEY POND | 690D1 | Battery | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Greater Portland - TBD | Pleasant Hill | 3
932 | 0 | 1 - UNIT | 0 |  | 2025-03-07 | Dixmont | UNITY | 860D1 | Solar | 999 | 0 | 2025-06-18 | 2025-07-24 | 2025-08-18 | 2025-09-30 | [16 empty] | Active | No
933 | 0 | 1 - DOVE | 924 |  | 2025-03-21 | Dover-Foxcroft | DOVER | 815D2 | Solar | 999 | 0 | [20 empty] | Active | No
934 | 0 | 1 - NOLI | 0 |  | 2025-07-07 | Limington | NORTH LIMINGTON | 638D2 | Solar | 999 | 0 |  |  |  |  | 2025-09-08 | [15 empty] | Active | No
935 | 0 | 1 - BRID | 928 |  | 2025-07-16 | Bridgton | BRIDGTON | 406D2 | Solar | 999 | 0 | [20 empty] | Active | No
936 | 0 | 2 - CARM | 911 |  | 2025-07-16 | Levant | CARMEL | 808D3 | Solar | 999 | 0 | [20 empty] | Active | No
937 | 0 | 1 - BASS | 0 |  | 2025-07-16 | BERWICK | BASSETT | 602D2 | Solar | 999 | 0 |  |  |  |  | 2025-08-22 | [15 empty] | Active | No
938 | 0 | 1 - FAFA | 0 |  | 2025-07-16 | NEW SHARON | FARMINGTON FALLS | 818D1 | Solar | 999 | 0 |  |  |  |  | 2025-08-18 | [15 empty] | Active | No
939 | 0 | 2 - NOLI | 0 |  | 2025-07-16 | LIMINGTON | NORTH LIMINGTON | 638D1 | Solar | 999 | 0 | [20 empty] | Active | No
940 | 0 | 2 - BUCK | 0 |  | 2025-07-16 | PENOBSCOT | BUCKSPORT | 806D2 | Solar | 999 | 0 | [20 empty] | Active | No
941 | 0 | 1 - RILE | 0 |  | 2025-07-16 | JAY | RILEY | 449D2 | Solar | 999 | 0 |  |  |  |  | 2025-08-22 | [15 empty] | Active | No
942 | 0 | 1 - LOVE | 0 |  | 2025-07-16 | FRYEBURG | LOVELL | 430D1 | Solar | 999 | 0 |  |  |  |  | 2025-08-22 | [15 empty] | Active | No
943 | 0 | 2 - BASS | 937 |  | 2025-07-16 | BERWICK | BASSETT | 602D2 | Solar | 999 | 0 | [20 empty] | Active | No
944 | 0 | 2 - LOVE | 0 |  | 2025-07-25 | FRYEBURG | LOVELL | 430D1 | Solar | 999 | 0 | [20 empty] | Active | No
945 | 0 | 1 - WILT | 0 |  | 2025-07-28 | Wilton | WILTON | 885D1 | Solar | 999 | 0 |  |  |  |  | 2025-10-03 | [15 empty] | Active | No
946 | 0 | 1 - CORI | 0 |  | 2025-09-12 | Corinna | CORINNA | 811D1 | Solar | 999 | 0 | [19 empty] | Q32026
947 | 0 | 1 - LULA | 0 |  | 2025-09-22 | Dixfield | LUDDEN LANE | 461D1 | Solar | 4500 | 0
948 | 0 | 2 - DOVE | 933 |  | 2025-09-26 | DOVER FOXCROFT | DOVER | 815D2 | Solar | 999 | 0
949 | 0 | 1 - FOHI | 0 |  | 2025-10-06 | Gorham | FORT HILL | 624D1 | Solar | 975 | 0
950 | 0 | 1 - BURN | 0 |  | 2025-10-15 | Pittsfield | BURNHAM | 807D1 | Solar | 975 | 0
Formulas:
Date App Rec'd = '[1]Level 4 Applications'!E2
Combined Study = IF(OR([Application Status]="EXECUTED-WITHDRAWN"),"",IF('[1]Level 4 Applications'!EG2=0,"",'[1]Level 4 Applications'!EG2))
Completion = IF(OR([Application Status]="EXECUTED-WITHDRAWN"),"",IF('[1]Level 4 Applications'!EZ2=0,"",'[1]Level 4 Applications'!EZ2))
Completion = IF(OR([Application Status]="EXECUTED-WITHDRAWN"),"",IF('[1]Level 4 Applications'!EX38=0,"",'[1]Level 4 Applications'!EX38))
IA = +IF('[1]Level 4 Applications'!HG2=0,"",'[1]Level 4 Applications'!HG2)
ReQueued Restudy = IF(OR([Application Status]="EXECUTED-WITHDRAWN"),"",IF('[1]Level 4 Applications'!EJ29=0,"",'[1]Level 4 Applications'!EJ29))
R`Qd One Stop = IF(OR([Application Status]="EXECUTED-WITHDRAWN"),"",IF('[1]Level 4 Applications'!FC29=0,"",'[1]Level 4 Applications'!FC29))
R`Qd Two Start = IF(OR([Application Status]="EXECUTED-WITHDRAWN"),"",IF('[1]Level 4 Applications'!EK29=0,"",'[1]Level 4 Applications'!EK29))
R`Qd Three Start = IF(OR([Application Status]="EXECUTED-WITHDRAWN"),"",IF('[1]Level 4 Applications'!EL29=0,"",'[1]Level 4 Applications'!EL29))
R`Qd Three Stop = IF(OR([Application Status]="EXECUTED-WITHDRAWN"),"",IF('[1]Level 4 Applications'!FE29=0,"",'[1]Level 4 Applications'!FE29))
R`Qd Two Stop = IF(OR([Application Status]="EXECUTED-WITHDRAWN"),"",IF('[1]Level 4 Applications'!FD30=0,"",'[1]Level 4 Applications'!FD30))
Feasibility Study = IF(OR([Application Status]="EXECUTED-WITHDRAWN"),"",IF('[1]Level 4 Applications'!EE38=0,"",'[1]Level 4 Applications'!EE38))
Feasibility Study = IF(OR([Application Status]="EXECUTED-WITHDRAWN"),"",IF('[1]Level 4 Applications'!EG907=0,"",'[1]Level 4 Applications'!EG907))
Impact Study = IF(OR([Application Status]="EXECUTED-WITHDRAWN"),"",IF('[1]Level 4 Applications'!EF38=0,"",'[1]Level 4 Applications'!EF38))
ReStudy = IF(OR([Application Status]="EXECUTED-WITHDRAWN"),"",IF('[1]Level 4 Applications'!EH45=0,"",'[1]Level 4 Applications'!EH45))
Facility Study = IF(OR([Application Status]="EXECUTED-WITHDRAWN"),"",IF('[1]Level 4 Applications'!EI153=0,"",'[1]Level 4 Applications'!EI153))
R`Qd Four Start = IF(OR([Application Status]="EXECUTED-WITHDRAWN"),"",IF('[1]Level 4 Applications'!EM351=0,"",'[1]Level 4 Applications'!EM351))
R`Qd Four Stop = IF(OR([Application Status]="EXECUTED-WITHDRAWN"),"",IF('[1]Level 4 Applications'!FF351=0,"",'[1]Level 4 Applications'!FF351))
r'Qd = '[1]Level 4 Applications'!$AG847