## Level 2 Online Report
Project # | App Received | Customer Notified Application Complete | Facility Type | AC kW | Circuit | Substation | Substation Transformer | Tech Screen Completed | Tech Screen Results | ESA Results | ESA Completed | Withdrawn
108719 | 2025-09-29 | 2025-10-03 | Solar | 975 | 438D1 | PAPOOSE POND | Tap off of Transmission Line |  | Pending
108721 | 2025-09-29 | 2025-10-01 | Solar | 975 | 824D1 | HARTLAND | 824T1 |  | Pending
108723 | 2025-09-29 | 2025-10-01 | Solar | 975 | 824D2 | HARTLAND | 824T1 |  | Pending
108725 | 2025-09-29 | 2025-10-01 | Solar | 999 | 818D1 | FARMINGTON FALLS | 818T1 |  | Pending
108726 | 2025-09-29 | 2025-10-03 | Solar | 999 | 210D1 | BRISTOL | 210T1 |  | Pending
108691 | 2025-09-26 | 2025-09-30 | Solar | 375 | 810D1 | CLINTON | 810T1 |  | Pending
108639 | 2025-09-25 | 2025-09-29 | Solar | 995 | 815D2 | DOVER | 815T2 |  | Pending
108641 | 2025-09-25 | 2025-09-29 | Solar | 375 | 210D2 | BRISTOL | 210T1 |  | Pending
108651 | 2025-09-25 | 2025-09-30 | Solar | 975 | 624D1 | FORT HILL | 624T1 |  | Pending
108655 | 2025-09-25 | 2025-09-29 | Solar | 500 | 632D2 | LIMERICK | 632T1 |  | Pending
108610 | 2025-09-23 | 2025-09-29 | Solar | 975 | 428D2 | LIVERMORE FALLS | 428T1 |  | Pending
108582 | 2025-09-22 | 2025-10-03 | Solar | 167 | 244D2 | SOUTH CHINA | 244T1 |  | Pending |  |  | No
108583 | 2025-09-22 | 2025-10-03 | Solar | 167 | 244D2 | SOUTH CHINA | 244T1 |  | Pending |  |  | No
108584 | 2025-09-22 | 2025-10-03 | Solar | 167 | 244D2 | SOUTH CHINA | 244T1 |  | Pending |  |  | No
108587 | 2025-09-22 | 2025-09-25 | Solar | 995 | 671D1 | WATERBORO | 671T1 |  | Pending
108600 | 2025-09-22 | 2025-09-29 | Solar | 975 | 866D2 | WESTON | 866T2 |  | Pending
108564 | 2025-09-18 | 2025-09-25 | Solar | 152.16 | 225D3 | FREEPORT | 225T2 |  | Pending
108422 | 2025-09-09 | 2025-09-19 | Solar | 220 | 412D1 | DEER RIPS | 412T2 | 2025-10-01 | Fail |  |  | No
108396 | 2025-09-08 | 2025-09-11 | Solar | 975 | 837D2 | NEWPORT | 837T2 | 2025-10-01 | Fail | Pending |  | No
108355 | 2025-09-05 | 2025-09-10 | Solar | 999 | 885D1 | WILTON | 885T1 | 2025-09-23 | Fail | Pending |  | No
108345 | 2025-09-04 | 2025-09-08 | Solar | 995 | 457D3 | MONMOUTH | 457T2 | 2025-09-16 | Fail | Pending |  | No
108348 | 2025-09-04 | 2025-09-11 | Solar | 150 | 250D1 | TOPSHAM | 250T2 | 2025-10-01 | Fail | Pending |  | No
108297 | 2025-09-02 | 2025-10-03 | Solar | 167 | 400D1 | ANDOVER | 400T1 |  | Pending
108305 | 2025-09-02 | 2025-10-03 | Solar | 167 | 400D1 | ANDOVER | 400T1 |  | Pending
108240 | 2025-08-28 | 2025-09-08 | Solar | 995 | 827D2 | ATHENS | 827T1 | 2025-09-16 | Fail | Pending
108275 | 2025-08-28 | 2025-09-10 | Solar | 996 | 461D1 | LUDDEN LANE | 461T1 | 2025-09-23 | Fail
108223 | 2025-08-27 | 2025-09-26 | Solar | 167 | 250D2 | TOPSHAM | 250T2 |  | Pending
108150 | 2025-08-21 | 2025-09-05 | Solar | 996 | 813D3 | DEXTER | 813T2 | 2025-09-19 | Fail | Pending
108039 | 2025-08-15 | 2025-09-05 | Solar | 996 | 419D1 | HIRAM HYDRO | 419T3 | 2025-09-22 | Fail
107972 | 2025-08-11 | 2025-08-29 | Solar | 150 | 438D1 | PAPOOSE POND | Tap off of Transmission Line | 2025-09-22 | Fail | Pending
107976 | 2025-08-11 | 2025-09-04 | Solar | 150 | 438D1 | PAPOOSE POND | Tap off of Transmission Line | 2025-09-23 | Fail | Pending
107945 | 2025-08-08 | 2025-09-09 | Solar | 975 | 617D2 | DUNSTAN | 617T1 | 2025-09-24 | Fail | Pending
107656 | 2025-07-25 | 2025-08-14 | Solar | 999 | 626D5 | HIGH STREET | 626T2 | 2025-09-03 | Fail | Pending
107549 | 2025-07-20 | 2025-07-25 | Solar | 995 | 691D1 | BALDWIN | 691T1 | 2025-08-15 | Fail | Pending
107430 | 2025-07-15 | 2025-07-23 | Solar | 150 | 437D2 | OXFORD | 437T1 | 2025-08-12 | Fail | Fail | 2025-09-26 | Yes
107431 | 2025-07-15 | 2025-07-21 | Solar | 150 | 435D4 | NORWAY | 435T2 | 2025-08-19 | Fail | Pending
107434 | 2025-07-15 | 2025-07-22 | Solar | 150 | 435D3 | NORWAY | 435T2 | 2025-08-12 | Fail | Pass | 2025-09-04
107347 | 2025-07-10 | 2025-07-16 | Solar | 975 | 262D1 | PUDDLEDOCK ROAD | 34 kV BUS 1 | 2025-07-30 | Fail | Pass | 2025-09-02
107361 | 2025-07-10 | 2025-08-06 | Solar | 998.9 | 256D1 | WINTHROP | 256T2 | 2025-08-25 | Fail | Pending
107304 | 2025-07-08 | 2025-07-15 | Solar | 233 | 225D4 | FREEPORT | 225T1 | 2025-07-23 | Fail | Pending
107262 | 2025-07-04 | 2025-08-28 | Solar | 999 | 272D6 | NORTH AUGUSTA | 272T2 | 2025-09-18 | Fail | Pending
107163 | 2025-06-26 | 2025-07-01 | Solar | 300 | 424D2 | LEWISTON LOWER | 424T1 | 2025-07-23 | Pass
107146 | 2025-06-24 | 2025-07-17 | Solar | 900 | 461D1 | LUDDEN LANE | 461T1 | 2025-08-05 | Fail |  |  | Yes
107059 | 2025-06-18 | 2025-06-19 | Solar | 150 | 855D1 | SOUTH WATERVILLE | 855T1 | 2025-07-01 | Fail | Fail | 2025-09-12 | Yes
107068 | 2025-06-18 | 2025-06-30 | Solar | 150 | 400D1 | ANDOVER | 400T1 | 2025-07-21 | Fail | Fail | 2025-08-28 | Yes
107032 | 2025-06-17 | 2025-08-26 | Solar | 125.4 | 421D2 | CHALLENGER | 421T1 | 2025-09-16 | Fail | Pending
106959 | 2025-06-11 | 2025-06-17 | Solar | 150 | 400D1 | ANDOVER | 400T1 | 2025-06-25 | Fail | Fail | 2025-08-06 | Yes
106867 | 2025-06-04 | 2025-06-09 | Solar | 999 | 885D1 | WILTON | 885T1 | 2025-06-20 | Fail | Fail | 2025-07-14 | Yes
106789 | 2025-05-29 | 2025-06-03 | Solar | 999 | 632D2 | LIMERICK | 632T1 | 2025-06-24 | Fail | Fail | 2025-08-28 | Yes
106772 | 2025-05-27 | 2025-06-05 | Solar | 996 | 272D2 | NORTH AUGUSTA | 272T1 | 2025-06-20 | Fail | Pass | 2025-08-07
106698 | 2025-05-22 | 2025-05-30 | Solar | 975 | 435D3 | NORWAY | 435T2 | 2025-06-09 | Fail | Pass | 2025-07-11
106654 | 2025-05-20 | 2025-06-03 | Solar | 999 | 415D2 | FRYEBURG | 415T1 | 2025-06-09 | Fail | Pass | 2025-07-25
106484 | 2025-05-07 | 2025-05-21 | Solar | 975 | 857D1 | THORNDIKE TAP | 857T1 | 2025-06-04 | Fail | Pass | 2025-08-05
106392 | 2025-04-30 | 2025-05-09 | Solar | 300 | 800D1 | LINCOLNVILLE | 800T1 | 2025-06-02 | Fail | Pass | 2025-08-27
106395 | 2025-04-30 | 2025-05-09 | Solar | 840 | 817D3 | FAIRFIELD | 817T1 | 2025-05-28 | Fail |  |  | Yes
106396 | 2025-04-30 | 2025-05-09 | Solar | 440 | 416D3 | GRAY | 416T1 | 2025-06-02 | Fail | Pass | 2025-08-26
106397 | 2025-04-30 | 2025-05-09 | Solar | 320 | 431D3 | MECHANIC FALLS | 431T2 | 2025-06-02 | Pass
106391 | 2025-04-29 | 2025-05-09 | Solar | 360 | 803D6 | BELFAST WEST SIDE | 34.5 kV Bus | 2025-06-02 | Fail | Pass | 2025-08-26
106272 | 2025-04-22 | 2025-05-01 | Solar | 152 | 423D2 | KIMBALL ROAD | 423T2 | 2025-05-20 | Fail | Pending |  | Yes
106220 | 2025-04-18 | 2025-04-24 | Solar | 440 | 246D3 | THOMASTON CREEK | 246T1 | 2025-05-13 | Fail | Fail | 2025-08-26 | Yes
106226 | 2025-04-18 | 2025-04-24 | Solar | 160 | 803D6 | BELFAST WEST SIDE | 34.5 kV Bus | 2025-05-13 | Fail | Pass | 2025-08-14
106231 | 2025-04-18 | 2025-04-24 | Solar | 320 | 678D2 | BAR MILLS | 678T4 | 2025-05-14 | Fail | Pending |  | Yes
106234 | 2025-04-18 | 2025-04-24 | Solar | 160 | 873D1 | COUNTY RD (RICE RIPS) | 873T1 | 2025-05-13 | Fail |  |  | Yes
106242 | 2025-04-18 | 2025-04-23 | Solar | 995 | 692D1 | HIRAM TAP | 692T1 | 2025-05-06 | Fail | Pass | 2025-07-07
106244 | 2025-04-18 | 2025-04-24 | Solar | 995 | 857D1 | THORNDIKE TAP | 857T1 | 2025-05-13 | Fail | Pass | 2025-07-07
106179 | 2025-04-16 | 2025-04-21 | Solar | 152 | 409D1 | PARIS TAP | 409T1 | 2025-05-05 | Fail | Pass | 2025-06-27
106128 | 2025-04-14 | 2025-04-17 | Solar | 875 | 428D3 | LIVERMORE FALLS | 428T1 | 2025-05-05 | Fail | Fail | 2025-07-02 | Yes
106048 | 2025-04-08 | 2025-04-15 | Solar | 153.6 | 208D2 | BOND BROOK | 208T1 | 2025-04-21 | Fail | Pass | 2025-06-04
105982 | 2025-04-03 | 2025-05-02 | Solar | 999 | 610D2 | BONNY EAGLE | 610T4 | 2025-05-16 | Fail | Pass | 2025-07-02
105997 | 2025-04-03 | 2025-04-17 | Solar | 136.8 | 219D2 | DAMARISCOTTA MILLS | 219T1 | 2025-05-05 | Fail | Pass | 2025-06-26
105865 | 2025-03-26 | 2025-03-31 | Solar | 999 | 885D1 | WILTON | 885T1 | 2025-04-04 | Fail | Fail | 2025-05-13 | Yes
105830 | 2025-03-24 | 2025-03-27 | Solar | 999 | 449D2 | RILEY | 449T1 | 2025-03-28 | Fail | Pass | 2025-06-20
105827 | 2025-03-21 | 2025-03-28 | Solar | 150 | 435D4 | NORWAY | 435T2 | 2025-04-04 | Fail | Pass | 2025-05-13
105796 | 2025-03-19 | 2025-03-27 | Solar | 999 | 238D1 | MESSINA | 238T1 | 2025-03-28 | Fail |  |  | Yes
105773 | 2025-03-17 | 2025-03-19 | Solar | 999 | 860D1 | UNITY | 860T1 | 2025-03-25 | Fail |  |  | Yes
105711 | 2025-03-12 | 2025-03-19 | Solar | 999 | 853D1 | SKOWHEGAN NORTH SIDE | 853T1 | 2025-03-25 | Fail |  |  | Yes
105681 | 2025-03-11 | 2025-03-19 | Solar | 999 | 467D1 | TURNER TAP | Tap off of Transmission Line | 2025-03-25 | Fail | Pass | 2025-04-23
105660 | 2025-03-07 | 2025-03-17 | Solar | 995 | 806D1 | BUCKSPORT | 806T5 | 2025-03-18 | Fail | Pass | 2025-04-04
105641 | 2025-03-06 | 2025-03-17 | Solar | 995 | 837D2 | NEWPORT | 837T2 | 2025-03-18 | Fail | Pass | 2025-04-03
105649 | 2025-03-06 |  | Solar | 990 | [7 empty] | Yes
105547 | 2025-02-25 | 2025-03-11 | Solar | 999 | 815D2 | DOVER | 815T2 |  | Fail |  |  | Yes
105548 | 2025-02-25 | 2025-03-12 | Solar | 999 | 638D1 | NORTH LIMINGTON | 638T1 | 2025-03-12 | Fail |  |  | Yes
105549 | 2025-02-25 | 2025-03-12 | Solar | 999 | 602D2 | BASSETT | 602T1 | 2025-03-12 | Fail |  |  | Yes
105550 | 2025-02-25 | 2025-03-11 | Solar | 999 | 602D2 | BASSETT | 602T1 | 2025-03-11 | Fail |  |  | Yes
105551 | 2025-02-25 | 2025-03-11 | Solar | 999 | 818D1 | FARMINGTON FALLS | 818T1 | 2025-03-11 | Fail |  |  | Yes
105521 | 2025-02-21 | 2025-03-07 | Solar | 999 | 842D1 | PITTSFIELD | 842T1 | 2025-03-11 | Fail | Pass | 2025-04-24
105523 | 2025-02-21 | 2025-03-07 | Solar | 999 | 885D1 | WILTON | 885T1 | 2025-03-11 | Fail | Fail | 2025-05-28 | Yes
105500 | 2025-02-19 | 2025-02-24 | Solar | 975 | 431D1 | MECHANIC FALLS | 431T2 | 2025-02-28 | Fail | Pass | 2025-04-18 | Yes
105454 | 2025-02-14 | 2025-02-18 | Solar | 969.4 | 813D1 | DEXTER | 813T1 | 2025-02-21 | Fail | Fail | 2025-03-20 | Yes
105424 | 2025-02-13 | 2025-02-17 | Solar | 200 | 810D1 | CLINTON | 810T1 | 2025-02-21 | Fail | Fail | 2025-03-13 | Yes
105405 | 2025-02-11 | 2025-02-12 | Solar | 995 | 431D1 | MECHANIC FALLS | 431T2 | 2025-02-14 | Fail | Pass | 2025-04-16
105215 | 2025-01-24 | 2025-01-28 | Solar | 152 | 423D2 | KIMBALL ROAD | 423T2 | 2025-01-31 | Fail | Fail | 2025-02-27 | Yes
105216 | 2025-01-24 | 2025-02-04 | Solar | 999 | 860D1 | UNITY | 860T1 | 2025-02-06 | Fail |  |  | Yes
105198 | 2025-01-23 | 2025-02-11 | Solar | 999 | 808D3 | CARMEL TAP | 808T1 | 2025-02-18 | Fail |  |  | Yes
105204 | 2025-01-23 | 2025-01-27 | Solar | 996 | 813D1 | DEXTER | 813T1 | 2025-01-31 | Fail | Fail | 2025-02-20 | Yes
105158 | 2025-01-16 | 2025-01-20 | Solar | 995 | 850D1 | SEARSPORT | 850T1 | 2025-01-24 | Fail | Pass | 2025-02-14
105134 | 2025-01-15 | 2025-01-23 | Solar | 200 | 675D2 | WESTERN AVENUE | 675T1 | 2025-01-24 | Pass
105120 | 2025-01-14 | 2025-01-20 | Solar | 141.84 | 253D1 | WARREN | 253T1 | 2025-01-24 | Fail | Fail | 2025-03-17 | Yes
105126 | 2025-01-14 | 2025-02-03 | Solar | 975 | 272D4 | NORTH AUGUSTA | 272T1 | 2025-02-06 | Fail | Pass | 2025-03-20
105055 | 2025-01-08 | 2025-01-27 | Solar | 975 | 873D1 | COUNTY RD (RICE RIPS) | 873T1 | 2025-02-03 | Fail |  |  | Yes
104989 | 2025-01-02 | 2025-01-03 | Solar | 152 | 409D1 | PARIS TAP | 409T1 | 2025-01-03 | Fail | Fail | 2025-01-24 | Yes
104942 | 2024-12-20 |  | Solar | 152 | [7 empty] | Yes
104944 | 2024-12-20 | 2024-12-23 | Solar | 152 | 423D2 | KIMBALL ROAD | 423T2 | 2024-12-30 | Fail | Pass | 2025-01-22
104916 | 2024-12-18 | 2024-12-31 | Solar | 220 | 239D7 | PARK STREET | 239T2 | 2025-01-03 | Fail | Pass | 2025-01-30
104902 | 2024-12-17 | 2024-12-31 | Solar | 200 | 246D3 | THOMASTON CREEK | 246T1 | 2025-01-03 | Fail | Pass | 2025-02-11
104903 | 2024-12-17 | 2024-12-24 | Solar | 240 | 239D6 | PARK STREET | 239T2 | 2025-01-03 | Fail | Pass | 2025-02-19
104904 | 2024-12-17 | 2024-12-31 | Solar | 100 | 239D5 | PARK STREET | 239T4 | 2025-01-03 | Fail | Pass | 2025-01-29
104822 | 2024-12-10 | 2024-12-12 | Solar | 995 | 467D1 | TURNER TAP | Tap off of Transmission Line | 2024-12-18 | Fail | Pass | 2025-01-14
104658 | 2024-11-22 | 2024-12-13 | Solar | 680 | 674D1 | WESTBROOK | 674T1 | 2024-12-16 | Fail | Fail | 2025-02-06
104659 | 2024-11-22 | 2024-12-13 | Solar | 400 | 674D1 | WESTBROOK | 674T1 | 2024-12-16 | Fail | Pass | 2025-05-29
104661 | 2024-11-22 | 2024-12-17 | Solar | 600 | 232D2 | LISBON FALLS | 232T2 | 2024-12-18 | Fail | Pass | 2025-01-06
104636 | 2024-11-21 | 2024-12-13 | Solar | 150 | 647D2 | PRIDES CORNER | 647T2 | 2024-12-16 | Pass
104638 | 2024-11-21 | 2024-12-13 | Solar | 240 | 674D2 | WESTBROOK | 674T1 | 2024-12-16 | Fail | Pass | 2025-02-06
104609 | 2024-11-20 | 2024-11-25 | Solar | 995 | 813D1 | DEXTER | 813T1 | 2024-11-26 | Fail |  |  | Yes
104613 | 2024-11-20 | 2024-11-25 | Solar | 999 | 431D1 | MECHANIC FALLS | 431T2 | 2024-11-26 | Fail | Fail | 2025-01-02 | Yes
104553 | 2024-11-15 | 2024-12-03 | Solar | 990 | 603D2 | BERWICK | 603T1 | 2024-12-03 | Fail | Pass | 2025-04-08
104517 | 2024-11-13 | 2024-11-21 | Solar | 999 | 428D2 | LIVERMORE FALLS | 428T1 | 2024-11-21 | Fail | Pass | 2024-12-09
104498 | 2024-11-12 |  | Solar | 265.05 | [7 empty] | Yes
104424 | 2024-11-05 | 2024-11-13 | Solar | 995 | 885D1 | WILTON | 885T1 | 2024-11-13 | Fail | Pass | 2025-01-23
104271 | 2024-10-23 | 2024-10-24 | Solar | 984.85 | 874D1 | BELFAST 115 | 874T2 | 2024-10-25 | Fail | Pass | 2024-11-12
104273 | 2024-10-23 | 2024-10-24 | Solar | 995 | 858D3 | STURTEVANT | 858T2 | 2024-10-25 | Fail | Pass | 2024-11-12
104262 | 2024-10-22 | 2024-11-05 | Solar | 999 | 850D2 | SEARSPORT | 850T1 | 2024-11-06 | Fail |  |  | Yes
104264 | 2024-10-22 | 2024-11-26 | Solar | 999 | 815D2 | DOVER | 815T2 | 2024-11-26 | Fail |  |  | Yes
104167 | 2024-10-15 | 2024-10-21 | Solar | 990 | 208D1 | BOND BROOK | 208T1 | 2024-10-22 | Fail | Pass | 2024-11-04
103912 | 2024-09-25 | 2024-09-25 | Solar | 153.6 | 219D2 | DAMARISCOTTA MILLS | 219T1 | 2024-09-26 | Fail | Pass | 2024-10-28
103885 | 2024-09-23 | 2024-10-01 | Solar | 975 | 624D2 | FORT HILL | 624T1 | 2024-10-02 | Fail |  |  | Yes
103844 | 2024-09-19 | 2024-09-24 | Solar | 975 | 272D4 | NORTH AUGUSTA | 272T1 | 2024-09-24 | Fail | Pass | 2024-10-17 | Yes
103677 | 2024-09-05 | 2024-09-05 | Solar | 100 | 803D6 | BELFAST WEST SIDE | 34.5 kV Bus | 2024-09-10 | Fail | Pass | 2024-10-15
103608 | 2024-08-30 |  | Solar | 4999 | [7 empty] | Yes
103599 | 2024-08-29 | 2024-09-16 | Solar | 999.6 | 842D1 | PITTSFIELD | 842T1 | 2024-09-16 | Fail | Pass | 2024-10-11
103367 | 2024-08-14 | 2024-08-15 | Solar | 995 | 242D1 | SIDNEY | 242T1 | 2024-08-16 | Fail | Pass | 2024-09-25
103285 | 2024-08-06 | 2024-08-13 | Solar | 540 | 647D1 | PRIDES CORNER | 647T2 | 2024-08-13 | Fail | Pass | 2024-09-12
103291 | 2024-08-06 | 2024-08-16 | Solar | 125 | 647D1 | PRIDES CORNER | 647T2 | 2024-08-22 | Fail | Pass | 2024-09-16
103293 | 2024-08-06 | 2024-08-16 | Solar | 150 | 647D1 | PRIDES CORNER | 647T2 | 2024-08-22 | Fail | Pass | 2024-09-16
103125 | 2024-07-30 | 2024-08-06 | Solar | 994 | 454D1 | TURNER | 454T1 | 2024-08-07 | Fail | Pass | 2024-09-16
103042 | 2024-07-24 | 2024-08-12 | Solar | 975 | 207D2 | BLAIR ROAD | 207T1 | 2024-08-13 | Fail | Fail | 2024-09-30 | Yes
103022 | 2024-07-23 |  | Solar | 480 | [7 empty] | Yes
103024 | 2024-07-23 | 2024-07-26 | Solar | 480 | 437D1 | OXFORD | 437T1 | 2024-07-29 | Fail | Fail | 2024-08-12 | Yes
103027 | 2024-07-23 |  | Solar | 150 | 437D1 | OXFORD | 437T1 |  |  |  |  | Yes
103030 | 2024-07-23 | 2024-07-26 | Solar | 420 | 216D2 | CONY ROAD | 216T1 | 2024-07-29 | Fail | Fail | 2024-08-23 | Yes
102896 | 2024-07-12 | 2024-07-30 | Solar | 975 | 634D1 | MAY STREET | 634T1 | 2024-08-16 | Fail | Fail | 2024-10-02 | Yes
102852 | 2024-07-11 | 2024-07-18 | Solar | 390 | 605D1 | BIDDEFORD PUMPING STATION | 605T1 | 2024-07-26 | Fail | Pass | 2024-08-28
102789 | 2024-07-08 | 2024-07-08 | Solar | 145.152 | 685D1 | BOLT HILL | 685T1 | 2024-07-10 | Pass
102756 | 2024-07-02 | 2024-07-10 | Solar | 995 | 874D1 | BELFAST 115 | 874T2 | 2024-07-12 | Fail | Fail | 2024-09-03 | Yes
102732 | 2024-07-01 | 2024-07-02 | Solar | 150 | 239D6 | PARK STREET | 239T2 | 2024-07-09 | Fail | Pass | 2024-08-05
102742 | 2024-07-01 | 2024-07-02 | Solar | 200 | 630D2 | GOOSEFARE | 630T1 | 2024-07-03 | Fail | Pass | 2024-08-06
102659 | 2024-06-25 | 2024-06-26 | Solar | 975 | 810D1 | CLINTON | 810T1 | 2024-06-27 | Fail | Fail | 2024-08-12 | Yes
102613 | 2024-06-24 | 2024-06-26 | Solar | 720 | 656D1 | SANFORD INDUSTRIAL PARK | 656T1 | 2024-07-12 | Fail | Pass | 2024-08-28
102614 | 2024-06-24 | 2024-06-26 | Solar | 360 | 644D1 | PLEASANT HILL | 644T2 | 2024-06-28 | Pass
102616 | 2024-06-24 | 2024-06-28 | Solar | 660 | 635D2 | MOSHERS | 635T2 | 2024-07-02 | Fail | Pass | 2024-08-01
102617 | 2024-06-24 | 2024-06-28 | Solar | 100 | 693D2 | SCARBOROUGH | 693T1 | 2024-07-02 | Pass
102619 | 2024-06-24 | 2024-06-28 | Solar | 200 | 693D2 | SCARBOROUGH | 693T1 | 2024-07-02 | Pass
102622 | 2024-06-24 | 2024-06-28 | Solar | 150 | 630D1 | GOOSEFARE | 630T1 | 2024-07-02 | Pass
102492 | 2024-06-13 |  | Solar | 996 | [7 empty] | Yes
102439 | 2024-06-10 | 2024-06-13 | Solar | 280 | 213D3 | BRUNSWICK WEST SIDE | 213T1 | 2024-06-24 | Pass
102340 | 2024-06-04 | 2024-07-10 | Solar | 160 | 213D3 | BRUNSWICK WEST SIDE | 213T1 | 2024-07-12 | Fail | Pass | 2024-08-09
102272 | 2024-05-30 | 2024-06-12 | Solar | 975 | 450D1 | SABATTUS | 450T1 | 2024-06-13 | Pass | Pass | 2024-07-15 | Yes
102178 | 2024-05-23 | 2024-05-29 | Solar/Battery | 996 | 444D3 | RAYMOND 34 KV | 444T1 | 2024-06-03 | Fail |  |  | Yes
102153 | 2024-05-22 | 2024-06-04 | Solar | 600 | 854D2 | SKOWHEGAN SOUTH SIDE | 854T1 | 2024-06-07 | Fail |  |  | Yes
102149 | 2024-05-21 | 2024-05-21 | Solar | 152 | 435D4 | NORWAY | 435T2 | 2024-05-22 | Fail | Pass | 2024-07-10
102000 | 2024-05-10 | 2024-05-22 | Wind | 225 | 806D2 | BUCKSPORT | 806T3 | 2024-05-31 | Fail | Pass | 2024-07-09
102005 | 2024-05-10 | 2024-05-23 | Solar | 999 | 263D1 | BOWMAN STREET | 34kV BUS 2 | 2024-05-29 | Fail |  |  | Yes
101765 | 2024-04-23 | 2024-05-15 | Solar | 999 | 821D3 | GUILFORD | 821T2 | 2024-05-28 | Fail | Pass | 2024-07-10
101713 | 2024-04-18 | 2024-05-07 | Solar | 975 | 674D2 | WESTBROOK | 674T1 | 2024-05-17 | Fail |  |  | Yes
101717 | 2024-04-18 | 2024-04-19 | Solar | 975 | 226D2 | GARDINER | 226T1 | 2024-04-22 | Fail | Pass | 2024-05-20
101658 | 2024-04-12 | 2024-04-18 | Solar | 153.6 | 219D2 | DAMARISCOTTA MILLS | 219T1 | 2024-05-08 | Fail |  |  | Yes
101603 | 2024-04-08 | 2024-04-17 | Solar | 250 | 412D4 | DEER RIPS | 412T4 | 2024-04-25 | Fail | Pass | 2024-06-24
101569 | 2024-04-04 | 2024-04-23 | Solar | 999 | 602D3 | BASSETT | 602T1 | 2024-05-09 | Fail | Pass | 2024-06-28
101528 | 2024-04-01 | 2024-04-12 | Solar | 999 | 431D1 | MECHANIC FALLS | 431T2 | 2024-04-22 | Fail | Fail | 2024-06-19 | Yes
101504 | 2024-03-28 | 2024-04-02 | Solar | 999 | 252D1 | WALDOBORO | 252T1 | 2024-04-05 | Fail | Fail | 2024-05-21 | Yes
101353 | 2024-03-18 | 2024-03-25 | Solar | 120 | 630D1 | GOOSEFARE | 630T1 | 2024-04-12 | Pass
101333 | 2024-03-14 |  | Solar | 150 | 403D1 | BETHEL | 403T1 |  |  |  |  | Yes
101334 | 2024-03-14 |  | Solar | 200 | 858D2 | STURTEVANT | 858T1 |  |  |  |  | Yes
101262 | 2024-03-08 | 2024-03-14 | Solar | 152 | 423D2 | KIMBALL ROAD | 423T2 | 2024-03-18 | Fail | Pass | 2024-04-30
101251 | 2024-03-07 | 2024-03-08 | Solar | 780 | 612D1 | BUTLER'S CORNER | 612T1 | 2024-03-27 | Fail | Fail | 2024-05-21 | Yes
101145 | 2024-02-27 | 2024-02-28 | Solar | 999 | 457D2 | MONMOUTH | 457T2 | 2024-03-01 | Fail | Pass | 2024-04-23
101131 | 2024-02-26 | 2024-02-29 | Solar | 999 | 447D4 | RUMFORD | 447T3 | 2024-03-01 | Fail | Fail | 2024-05-01 | Yes
101137 | 2024-02-26 | 2024-03-08 | Solar | 975 | 230D2 | COOPERS MILLS ROAD | 230T2 | 2024-03-08 | Fail | Pass | 2024-05-01
101067 | 2024-02-21 | 2024-02-23 | Solar | 125 | 865D1 | WEST WATERVILLE | 865T1 | 2024-02-26 | Pass |  |  | Yes
101037 | 2024-02-19 |  | Solar | 100 | 415D2 | FRYEBURG | 415T1 |  |  |  |  | Yes
100989 | 2024-02-13 |  | Solar | 996 | [7 empty] | Yes
100963 | 2024-02-09 | 2024-02-12 | Solar | 115.2 | 216D3 | CONY ROAD | 216T1 | 2024-02-13 | Pass
100873 | 2024-02-01 | 2024-02-13 | Solar | 995 | 667D2 | SOUTH SANFORD | 667T2 | 2024-03-07 | Fail | Fail | 2024-05-06 | Yes
100862 | 2024-01-31 | 2024-02-08 | Solar | 150 | 233D1 | MANCHESTER | 233T1 | 2024-02-09 | Fail | Pass | 2024-03-25
100863 | 2024-01-31 | 2024-02-09 | Solar | 600 | 415D2 | FRYEBURG | 415T1 | 2024-02-16 | Fail | Fail | 2024-04-12 | Yes
100846 | 2024-01-30 | 2024-02-19 | Solar | 999 | 272D2 | NORTH AUGUSTA | 272T1 | 2024-02-20 | Fail | Pass | 2024-04-11
100821 | 2024-01-26 | 2024-03-04 | Solar | 999 | 632D1 | LIMERICK | 632T1 | 2024-03-07 | Fail | Fail | 2024-05-12 | Yes
100803 | 2024-01-25 | 2024-02-02 | Solar | 999 | 246D3 | THOMASTON CREEK | 246T1 | 2024-02-21 | Fail | Fail | 2024-05-07 | Yes
100814 | 2024-01-25 | 2024-02-07 | Solar | 233.3 | 620D4 | ELM STREET | 620T2 | 2024-02-09 | Fail | Pass | 2024-04-02
100792 | 2024-01-24 | 2024-02-23 | Solar | 999 | 467D1 | TURNER TAP | Tap off of Transmission Line | 2024-02-26 | Fail | Pass | 2024-04-24
100687 | 2024-01-12 | 2024-01-18 | Solar | 500 | 256D2 | WINTHROP | 256T1 | 2024-01-19 | Fail |  |  | Yes
100680 | 2024-01-11 | 2024-01-22 | Solar | 380 | 668D3 | SPRING STREET | 668T2 | 2024-02-05 | Pass
100681 | 2024-01-11 | 2024-01-22 | Solar | 999 | 685D2 | BOLT HILL | 685T1 | 2024-02-13 | Fail | Pass | 2024-04-12
100682 | 2024-01-11 | 2024-01-22 | Solar | 999 | 603D3 | BERWICK | 603T1 | 2024-02-22 | Fail | Fail | 2024-04-26 | Yes
100620 | 2024-01-05 | 2024-01-05 | Solar | 400 | 412D1 | DEER RIPS | 412T2 | 2024-01-09 | Fail | Pass | 2024-03-18
100623 | 2024-01-05 | 2024-01-08 | Solar | 720 | 412D1 | DEER RIPS | 412T2 | 2024-01-09 | Fail | Pass | 2024-03-11
100571 | 2023-12-29 | 2024-01-16 | Solar | 750 | 200D3 | AUGUSTA K5 | 200T1 | 2024-01-16 | Fail | Pass | 2024-03-20
100520 | 2023-12-22 | 2024-01-09 | Solar | 500 | 660D2 | SHAWS MILL ROAD | 660T1 | 2024-01-13 | Fail | Pass | 2024-02-15
100461 | 2023-12-15 | 2024-01-10 | Solar | 999 | 818D2 | FARMINGTON FALLS | 818T1 | 2024-01-17 | Fail | Pass | 2024-04-11 | Yes
100388 | 2023-12-11 | 2023-12-15 | Solar | 350 | 421D2 | CHALLENGER | 421T1 | 2024-01-03 | Fail | Pass | 2024-02-21
100360 | 2023-12-08 |  | Solar | 999 | [7 empty] | Yes
100368 | 2023-12-08 | 2023-12-14 | Solar | 330 | 841D1 | PHILLIPS/STRONG | 841T1 | 2024-01-03 | Fail |  |  | Yes
100376 | 2023-12-08 | 2023-12-15 | Solar | 999 | 855D2 | SOUTH WATERVILLE | 855T1 | 2023-12-18 | Fail | Fail | 2024-02-08 | Yes
100379 | 2023-12-08 |  | Solar | 1000 | [7 empty] | Yes
100340 | 2023-12-07 | 2023-12-11 | Solar | 360 | 215D2 | CAPITOL STREET | 215T2 | 2023-12-11 | Fail | Pass | 2024-02-09
100354 | 2023-12-07 | 2024-01-08 | Solar | 999 | 632D1 | LIMERICK | 632T1 | 2024-02-01 | Fail | Fail | 2024-04-09 | Yes
100324 | 2023-12-06 | 2023-12-12 | Solar | 360 | 273D5 | BRUNSWICK HYDRO | 273T2 | 2024-01-02 | Pass
100307 | 2023-12-05 | 2023-12-06 | Solar | 540 | 249D2 | TOPSHAM OLD | 249T1 | 2023-12-27 | Fail | Pass | 2024-03-11
100263 | 2023-12-01 | 2024-01-10 | Solar | 900 | 818D1 | FARMINGTON FALLS | 818T1 | 2024-01-17 | Fail | Pass | 2024-03-18 | Yes
100265 | 2023-12-01 | 2023-12-06 | Solar | 240 | 865D1 | WEST WATERVILLE | 865T1 | 2023-12-06 | Fail | Pass | 2024-01-29
100266 | 2023-12-01 | 2023-12-06 | Solar | 400 | 639D2 | NORTH WINDHAM | 639T2 | 2023-12-11 | Fail | Pass | 2024-03-08
100267 | 2023-12-01 | 2023-12-06 | Solar | 240 | 681D3 | BRANCH BROOK | 681T3 | 2023-12-27 | Pass
100268 | 2023-12-01 | 2023-12-06 | Solar | 500 | 681D3 | BRANCH BROOK | 681T3 | 2023-12-26 | Pass
100245 | 2023-11-30 | 2023-12-07 | Solar | 120 | 249D1 | TOPSHAM OLD | 249T1 | 2023-12-29 | Fail | Pass | 2024-02-22
100251 | 2023-11-30 | 2023-12-07 | Solar | 100 | 249D1 | TOPSHAM OLD | 249T1 | 2024-01-02 | Fail | Pass | 2024-02-19
100252 | 2023-11-30 | 2024-01-17 | Solar | 1020 | 471D1 | LEEDS | 471T1 | 2024-01-23 | Fail | Fail | 2024-04-29 | Yes
100255 | 2023-11-30 | 2023-12-15 | Solar | 1020 | 873D1 | COUNTY RD (RICE RIPS) | 873T1 | 2023-12-18 | Fail |  |  | Yes
100222 | 2023-11-29 | 2023-11-30 | Solar | 996 | 678D1 | BAR MILLS | 678T4 | 2023-12-26 | Fail | Fail | 2024-03-21 | Yes
100227 | 2023-11-29 | 2023-12-12 | Solar | 1020 | 450D2 | SABATTUS | 450T1 | 2023-12-26 | Fail | Fail | 2024-03-11 | Yes
100140 | 2023-11-27 | 2023-12-07 | Solar | 360 | 668D3 | SPRING STREET | 668T2 | 2023-12-11 | Pass
100119 | 2023-11-22 | 2023-11-29 | Solar | 996 | 453D1 | TRAP CORNER | 453T1 | 2023-12-05 | Fail |  |  | Yes
100126 | 2023-11-22 | 2023-12-06 | Solar | 360 | 233D1 | MANCHESTER | 233T1 | 2023-12-06 | Fail | Fail | 2024-02-20 | Yes
100128 | 2023-11-22 | 2023-12-07 | Solar | 420 | 213D4 | BRUNSWICK WEST SIDE | 213T2 | 2023-12-29 | Pass |  |  | Yes
100129 | 2023-11-22 | 2023-12-06 | Solar | 480 | 668D3 | SPRING STREET | 668T2 | 2023-12-11 | Fail |  |  | Yes
100091 | 2023-11-17 | 2023-11-27 | Solar | 975 | 461D1 | LUDDEN LANE | 461T1 | 2023-12-11 | Fail | Pass | 2024-02-12
100056 | 2023-11-16 | 2023-11-27 | Solar | 120 | 208D1 | BOND BROOK | 208T1 | 2023-11-27 | Fail |  |  | Yes
100057 | 2023-11-16 | 2023-11-27 | Solar | 120 | 453D1 | TRAP CORNER | 453T1 | 2023-11-28 | Fail |  |  | Yes
100000 | 2023-11-15 | 2023-11-27 | Solar | 994 | 210D1 | BRISTOL | 210T1 | 2023-12-18 | Fail | Pass | 2024-01-25
100001 | 2023-11-15 | 2023-11-27 | Solar | 700 | 870D1 | WINSLOW | 870T4 | 2023-11-28 | Fail | Fail | 2024-01-02 | Yes
100002 | 2023-11-15 | 2023-11-22 | Solar | 994 | 454D1 | TURNER | 454T1 | 2023-11-28 | Fail | Fail | 2024-01-25 | Yes
100049 | 2023-11-15 | 2024-01-04 | Solar | 1020 | 858D2 | STURTEVANT | 858T1 | 2024-01-05 | Fail |  |  | Yes
85879 | 2023-11-13 | 2023-11-20 | Solar | 999 | 695D2 | LEBANON | 695T1 | 2023-12-13 | Fail | Fail | 2024-02-14 | Yes
85877 | 2023-11-10 | 2023-11-13 | Solar | 995 | 842D1 | PITTSFIELD | 842T1 | 2023-11-14 | Fail | Pass | 2023-12-08
85876 | 2023-11-09 | 2023-12-06 | Solar | 100 | 803D5 | BELFAST WEST SIDE | 803T1 | 2023-12-29 | Fail | Pass | 2024-02-21
85862 | 2023-11-08 | 2023-11-15 | Solar | 150 | 233D1 | MANCHESTER | 233T1 | 2023-11-15 | Fail | Pass | 2024-01-02
85875 | 2023-11-08 | 2023-12-11 | Solar | 999 | 837D2 | NEWPORT | 837T2 | 2023-12-11 | Fail | Pass | 2024-01-17 | Yes
85805 | 2023-11-03 | 2023-11-09 | Solar | 999 | 813D1 | DEXTER | 813T1 | 2023-11-17 | Fail | Pass | 2024-01-02
85807 | 2023-11-03 | 2023-11-09 | Solar | 999 | 256D2 | WINTHROP | 256T1 | 2023-11-10 | Fail | Pass | 2023-12-06
85736 | 2023-11-02 | 2023-11-02 | Solar | 999 | 471D2 | LEEDS | 471T1 | 2023-11-08 | Fail | Pass | 2024-01-02
85743 | 2023-11-02 | 2023-11-14 | Solar | 560 | 412D1 | DEER RIPS | 412T2 | 2023-11-17 | Fail | Pass | 2024-01-11 | Yes
85721 | 2023-11-01 | 2023-11-13 | Solar | 970 | 239D6 | PARK STREET | 239T2 | 2023-11-14 | Fail | Pass | 2024-01-17
85727 | 2023-11-01 | 2023-11-13 | Solar | 625 | 230D1 | COOPERS MILLS ROAD | 230T2 | 2023-11-13 | Fail | Pass | 2024-01-25
85695 | 2023-10-31 | 2023-11-13 | Solar | 300 | 865D5 | WEST WATERVILLE | 865T2 | 2023-11-14 | Fail | Pass | 2024-01-29
85703 | 2023-10-31 | 2023-11-03 | Solar | 975 | 421D2 | CHALLENGER | 421T1 | 2023-11-09 | Fail | Pass | 2023-12-06 | Yes
85663 | 2023-10-27 | 2023-11-03 | Solar | 600 | 612D2 | BUTLER'S CORNER | 612T1 | 2023-11-28 | Fail | Fail | 2024-02-14 | Yes
85622 | 2023-10-24 | 2023-11-13 | Solar | 152 | 423D2 | KIMBALL ROAD | 423T2 | 2023-11-14 | Fail | Pass | 2024-01-11
85588 | 2023-10-18 | 2023-10-24 | Solar | 600 | 865D1 | WEST WATERVILLE | 865T1 | 2023-10-25 | Pass
85484 | 2023-10-13 | 2023-10-18 | Solar | 975 | 447D1 | RUMFORD | 447T3 | 2023-10-30 | Pass
85488 | 2023-10-13 | 2023-10-19 | Solar | 500 | 208D1 | BOND BROOK | 208T1 | 2023-10-19 | Fail | Pass | 2023-11-27
85228 | 2023-09-28 | 2023-10-04 | Solar | 975 | 261D4 | BATH 34 | 261T2 | 2023-10-26 | Fail | Fail | 2023-11-10 | Yes
85186 | 2023-09-26 | 2023-10-17 | Solar | 900 | 667D3 | SOUTH SANFORD | 667T1 | 2023-11-14 | Fail | Pass | 2024-01-24
85197 | 2023-09-26 | 2023-10-02 | Solar | 480 | 423D1 | KIMBALL ROAD | 423T2 | 2023-10-05 | Fail | Pass | 2023-11-10
85173 | 2023-09-25 | 2023-09-28 | Solar | 250 | 673D1 | BIDDEFORD INDUSTRIAL PARK | 673T2 | 2023-10-23 | Pass
85069 | 2023-09-15 | 2023-10-04 | Solar | 975 | 466D1 | RUMFORD INDUSTRIAL PARK | 466T1 | 2023-10-06 | Fail | Fail | 2023-11-10 | Yes
85041 | 2023-09-13 | 2023-09-27 | Solar | 994 | 263D1 | BOWMAN STREET | 34kV BUS 2 | 2023-09-28 | Fail | Pass | 2023-10-25
85031 | 2023-09-12 | 2023-10-12 | Solar | 1999 | 225D3 | FREEPORT | 225T2 | 2023-10-26 | Fail |  |  | Yes
85012 | 2023-09-11 | 2023-09-18 | Solar | 1050 | 207D1 | BLAIR ROAD | 207T1 | 2023-09-19 | Fail | Fail | 2023-10-25 | Yes
84974 | 2023-09-08 | 2023-09-13 | Solar | 975 | 233D1 | MANCHESTER | 233T1 | 2023-09-13 | Fail | Pass | 2023-09-29
84979 | 2023-09-08 | 2023-09-13 | Solar | 975 | 219D2 | DAMARISCOTTA MILLS | 219T1 | 2023-09-19 | Fail | Pass | 2023-10-12
84902 | 2023-09-05 | 2023-09-12 | Other | 100 | 855D1 | SOUTH WATERVILLE | 855T1 | 2023-09-06 | Fail | Pass | 2023-10-12
84904 | 2023-09-05 | 2023-09-11 | Solar | 150 | 252D2 | WALDOBORO | 252T1 | 2023-09-15 | Fail | Pass | 2023-10-12
84764 | 2023-08-23 | 2023-09-19 | Solar | 500 | 210D2 | BRISTOL | 210T1 | 2023-10-11 | Fail | Fail | 2023-12-08 | Yes
84691 | 2023-08-17 | 2023-08-25 | Solar | 144.48 | 667D1 | SOUTH SANFORD | 667T2 | 2023-08-31 | Fail | Pass | 2023-10-12
84683 | 2023-08-14 |  | Solar | 799.98 | 874D1 | BELFAST 115 | 874T2 |  |  |  |  | Yes
84684 | 2023-08-14 | 2023-08-28 | Solar | 100 | 239D7 | PARK STREET | 239T2 | 2023-08-31 | Pass
84618 | 2023-08-09 | 2023-08-10 | Solar | 999 | 412D1 | DEER RIPS | 412T2 | 2023-08-11 | Fail | Pass | 2023-09-28
84619 | 2023-08-09 | 2023-08-10 | Solar | 996 | 870D1 | WINSLOW | 870T4 | 2023-08-11 | Fail | Fail | 2023-09-14 | Yes
84757 | 2023-08-09 | 2023-09-08 | Solar | 999.6 | 808D3 | CARMEL TAP | 808T1 | 2023-09-26 | Pass
84609 | 2023-08-08 | 2023-08-21 | Solar | 999 | 821D1 | GUILFORD | 821T1 | 2023-08-22 | Fail | Pass | 2023-12-01
84547 | 2023-08-01 | 2023-08-04 | Solar | 999 | 412D4 | DEER RIPS | 412T4 | 2023-08-07 | Fail | Fail | 2023-10-25 | Yes
84553 | 2023-08-01 | 2023-08-04 | Solar | 999 | 412D4 | DEER RIPS | 412T4 | 2023-08-07 | Fail | Fail | 2023-10-25 | Yes
84450 | 2023-07-25 | 2023-07-27 | Solar | 996 | 695D2 | LEBANON | 695T1 | 2023-08-24 | Fail | Pass | 2023-10-12
84451 | 2023-07-25 | 2023-07-27 | Solar | 996 | 663D2 | SOUTH BERWICK | 663T1 | 2023-08-24 | Fail | Fail | 2023-10-12 | Yes
84452 | 2023-07-25 | 2023-07-27 | Solar | 996 | 225D4 | FREEPORT | 225T1 | 2023-08-17 | Fail | Fail | 2023-10-03 | Yes
84411 | 2023-07-20 | 2023-08-07 | Solar | 999 | 632D2 | LIMERICK | 632T1 | 2023-08-31 | Fail |  |  | Yes
84416 | 2023-07-20 | 2023-08-07 | Solar | 999 | 632D2 | LIMERICK | 632T1 | 2023-08-31 | Fail |  |  | Yes
84392 | 2023-07-18 | 2023-08-21 | Solar | 200 | 607D1 | BISHOP STREET | 607T1 | 2023-09-08 | Pass |  |  | Yes
84389 | 2023-07-17 | 2023-07-26 | Solar | 975 | 232D2 | LISBON FALLS | 232T2 | 2023-08-11 | Fail | Fail | 2023-09-20 | Yes
84338 | 2023-07-13 | 2023-07-19 | Solar | 975 | 244D1 | SOUTH CHINA | 244T1 | 2023-07-19 | Fail | Fail | 2023-08-16 | Yes
84350 | 2023-07-13 | 2023-07-19 | Solar | 975 | 255D2 | WEST STREET | 255T1 | 2023-07-19 | Fail | Pass | 2023-08-23
84304 | 2023-07-10 | 2023-07-10 | Solar | 750 | 858D2 | STURTEVANT | 858T1 | 2023-07-13 | Pass
84290 | 2023-07-06 | 2023-07-10 | Solar | 975 | 808D1 | CARMEL | 808T1 | 2023-07-14 | Fail | Pass | 2023-08-31 | Yes
84276 | 2023-07-05 | 2023-07-21 | Solar | 999 | 837D1 | NEWPORT | 837T1 | 2023-07-24 | Fail | Pass | 2023-08-11
84277 | 2023-07-05 | 2023-07-21 | Solar | 999 | 837D1 | NEWPORT | 837T1 | 2023-07-24 | Fail | Pass | 2023-09-06
84278 | 2023-07-05 | 2023-07-21 | Solar | 999 | 837D1 | NEWPORT | 837T1 | 2023-07-24 | Fail | Pass | 2023-09-06
84279 | 2023-07-05 | 2023-07-21 | Solar | 999 | 837D1 | NEWPORT | 837T1 | 2023-07-24 | Fail | Fail | 2023-09-06 | Yes
84280 | 2023-07-05 | 2023-07-21 | Solar | 999 | 837D1 | NEWPORT | 837T1 | 2023-07-24 | Fail | Fail | 2023-09-06 | Yes
84272 | 2023-06-30 | 2023-07-05 | Solar | 825 | 253D1 | WARREN | 253T1 | 2023-07-06 | Fail | Pass | 2023-08-01
84231 | 2023-06-29 | 2023-07-10 | Solar | 996 | 461D1 | LUDDEN LANE | 461T1 | 2023-07-13 | Fail | Pass | 2023-08-11
84228 | 2023-06-28 | 2023-06-30 | Solar | 999 | 860D1 | UNITY | 860T1 | 2023-07-10 | Fail | Fail | 2023-08-30 | Yes
84222 | 2023-06-27 | 2023-07-05 | Solar | 120 | 678D1 | BAR MILLS | 678T4 | 2023-07-26 | Fail | Pass | 2023-09-11
84188 | 2023-06-23 | 2023-06-28 | Solar | 975 | 238D1 | MESSINA | 238T1 | 2023-07-20 | Fail | Fail | 2023-08-16 | Yes
84211 | 2023-06-23 | 2023-07-07 | Solar | 160 | 689D1 | BRAGDON COMMONS | 689T1 | 2023-07-26 | Fail | Pass | 2023-09-20
84117 | 2023-06-16 | 2023-06-21 | Solar | 975 | 858D1B | STURTEVANT | 858T2 | 2023-07-06 | Fail | Pass | 2023-09-25
84104 | 2023-06-14 | 2023-07-05 | Solar | 1000 | 815D2 | DOVER | 815T2 | 2023-07-06 | Fail |  |  | Yes
84107 | 2023-06-14 | 2023-06-15 | Solar | 999 | 636D1 | MUSSEY ROAD | 636T1 | 2023-06-30 | Fail | Pass | 2023-08-08 | Yes
84070 | 2023-06-12 | 2023-06-15 | Solar | 975 | 860D2 | UNITY | 860T1 | 2023-06-29 | Fail | Pass | 2023-07-27
84071 | 2023-06-12 | 2023-06-14 | Solar | 975 | 858D1A | STURTEVANT | 858T1 | 2023-06-15 | Fail | Pass | 2023-07-18 | Yes
84066 | 2023-06-09 | 2023-06-12 | Solar | 995 | 471D1 | LEEDS | 471T1 | 2023-06-15 | Fail | Fail | 2023-07-10 | Yes
84068 | 2023-06-09 | 2023-06-13 | Solar | 875 | 253D1 | WARREN | 253T1 | 2023-06-28 | Fail |  |  | Yes
84024 | 2023-06-07 | 2023-06-13 | Solar | 975 | 431D1 | MECHANIC FALLS | 431T2 | 2023-06-15 | Fail | Pass | 2023-07-18
83991 | 2023-06-02 | 2023-06-08 | Solar | 160 | 852D1 | SHAWMUT | 852T3 | 2023-06-09 | Fail | Pass | 2023-07-25
84004 | 2023-06-02 | 2023-06-21 | Solar | 999 | 256D1 | WINTHROP | 256T2 | 2023-06-27 | Fail | Pass | 2023-08-16
83944 | 2023-05-26 | 2023-06-01 | Solar | 975 | 639D2 | NORTH WINDHAM | 639T2 | 2023-06-07 | Fail | Pass | 2023-07-12 | Yes
83909 | 2023-05-24 | 2023-06-05 | Solar | 999 | 813D1 | DEXTER | 813T1 | 2023-06-07 | Fail | Fail | 2023-07-14 | Yes
83914 | 2023-05-24 | 2023-06-05 | Solar | 999 | 885D1 | WILTON | 885T1 | 2023-06-07 | Fail | Pass | 2023-07-14
83916 | 2023-05-24 | 2023-06-05 | Solar | 999 | 885D1 | WILTON | 885T1 | 2023-06-07 | Fail | Fail | 2023-07-14 | Yes
83894 | 2023-05-22 | 2023-05-25 | Solar | 900 | 691D1 | BALDWIN | 691T1 | 2023-05-25 | Fail | Fail | 2023-06-21 | Yes
83856 | 2023-05-17 | 2023-05-22 | Solar | 154 | 274D1 | MAINE YANKEE | 274T2 | 2023-05-23 | Fail | Pass | 2023-07-20
83838 | 2023-05-16 | 2023-05-22 | Solar | 200 | 239D7 | PARK STREET | 239T2 | 2023-05-23 | Pass
83837 | 2023-05-15 | 2023-05-17 | Solar | 720 | 428D2 | LIVERMORE FALLS | 428T1 | 2023-05-18 | Pass
83829 | 2023-05-12 | 2023-05-15 | Solar | 995 | 412D3 | DEER RIPS | 412T4 | 2023-05-18 | Fail | Pass | 2023-06-06
83793 | 2023-05-09 | 2023-05-11 | Solar | 975 | 400D1 | ANDOVER | 400T1 | 2023-05-12 | Fail | Pass | 2023-06-20
83777 | 2023-05-08 | 2023-05-09 | Solar | 999 | 805D1 | BROOKS | 805T1 | 2023-05-10 | Fail | Fail | 2023-08-08 | Yes
83779 | 2023-05-08 | 2023-05-10 | Solar | 996 | 813D3 | DEXTER | 813T2 | 2023-05-12 | Fail | Fail | 2023-08-08 | Yes
83787 | 2023-05-08 | 2023-05-10 | Solar | 996 | 406D2 | BRIDGTON | 406T1 | 2023-05-17 | Fail | Fail | 2023-07-26 | Yes
83769 | 2023-05-05 | 2023-05-08 | Solar | 240 | 630D4 | GOOSEFARE | 630T1 | 2023-05-17 | Fail | Pass | 2023-06-22
83738 | 2023-05-04 | 2023-05-11 | Solar | 975 | 466D1 | RUMFORD INDUSTRIAL PARK | 466T1 | 2023-05-12 | Fail | Pass | 2023-06-01 | Yes
83720 | 2023-05-03 | 2023-05-25 | Solar | 1000 | 834D1 | MONSON | 834T1 | 2023-05-30 | Fail | Fail | 2023-06-22 | Yes
83685 | 2023-04-28 | 2023-05-01 | Solar | 324 | 858D1A | STURTEVANT | 858T1 | 2023-05-01 | Fail | Pass | 2023-05-03
83664 | 2023-04-27 | 2023-05-01 | Solar | 700 | 816D1 | EAST WILTON | 816T1 | 2023-05-02 | Fail | Pass | 2023-06-01
83668 | 2023-04-27 | 2023-05-01 | Solar | 975 | 233D2 | MANCHESTER | 233T1 | 2023-05-03 | Fail | Pass | 2023-05-11 | Yes
83670 | 2023-04-27 | 2023-05-01 | Solar | 975 | 262D1 | PUDDLEDOCK ROAD | 34 kV BUS 1 | 2023-05-09 | Fail | Pass | 2023-06-16
83611 | 2023-04-24 | 2023-05-03 | Solar | 120 | 617D3 | DUNSTAN | 617T1 | 2023-05-15 | Pass
83605 | 2023-04-21 | 2023-04-27 | Solar | 975 | 431D1 | MECHANIC FALLS | 431T2 | 2023-04-27 | Fail | Pass | 2023-06-05
83600 | 2023-04-20 | 2023-04-21 | Solar | 850 | 450D1 | SABATTUS | 450T1 | 2023-04-24 | Fail | Pass | 2023-06-21
83601 | 2023-04-20 | 2023-04-25 | Solar | 700 | 256D2 | WINTHROP | 256T1 | 2023-04-25 | Fail | Pass | 2023-05-11
83526 | 2023-04-12 | 2023-05-01 | Solar | 1000 | 821D3 | GUILFORD | 821T2 | 2023-05-02 | Fail | Fail | 2023-05-18 | Yes
83507 | 2023-04-11 | 2023-04-14 | Solar | 975 | 639D2 | NORTH WINDHAM | 639T2 | 2023-05-02 | Fail | Pass | 2023-05-23
83514 | 2023-04-11 | 2023-04-13 | Solar | 995 | 858D3 | STURTEVANT | 858T2 | 2023-04-18 | Fail | Pass | 2023-05-01
83474 | 2023-04-05 | 2023-04-07 | Solar | 999 | 605D1 | BIDDEFORD PUMPING STATION | 605T1 | 2023-05-03 | Pass | Pass | 2023-06-26
83455 | 2023-04-03 | 2023-04-18 | Solar | 999 | 602D3 | BASSETT | 602T1 | 2023-05-03 | Fail | Pass | 2023-06-23
83453 | 2023-03-31 | 2023-04-05 | Solar | 975 | 858D1A | STURTEVANT | 858T1 | 2023-04-05 | Fail | Fail | 2023-04-24 | Yes
83437 | 2023-03-28 | 2023-04-06 | Solar | 120 | 634D4 | MAY STREET | 634T1 | 2023-05-03 | Pass
83403 | 2023-03-27 | 2023-04-03 | Solar | 125 | 693D1 | SCARBOROUGH | 693T1 | 2023-04-05 | Pass |  |  | Yes
83401 | 2023-03-24 | 2023-03-29 | Solar | 250 | 436D6 | GREAT FALLS | 436T1 | 2023-03-30 | Fail | Pass | 2023-04-24 | Yes
83384 | 2023-03-23 | 2023-03-29 | Solar | 600 | 673D1 | BIDDEFORD INDUSTRIAL PARK | 673T2 | 2023-04-19 | Fail | Pass | 2023-06-02
83361 | 2023-03-21 | 2023-03-24 | Solar/Battery | 996 | 834D1 | MONSON | 834T1 | 2023-03-28 | Fail | Pass | 2023-05-16
83350 | 2023-03-20 | 2023-03-23 | Solar | 999 | 253D1 | WARREN | 253T1 | 2023-04-12 | Fail | Fail | 2023-05-11 | Yes
83328 | 2023-03-16 | 2023-03-20 | Solar | 720 | 653D5 | FORE RIVER | 653T1 | 2023-04-03 | Fail | Pass | 2023-05-01
83307 | 2023-03-14 | 2023-03-21 | Solar/Battery | 996 | 813D1 | DEXTER | 813T1 | 2023-03-22 | Fail | Pass | 2023-07-07
83298 | 2023-03-13 | 2023-03-16 | Solar | 120 | 200D1 | AUGUSTA K5 | 200T1 | 2023-03-16 | Pass
83253 | 2023-03-06 | 2023-03-15 | Solar | 120 | 656D1 | SANFORD INDUSTRIAL PARK | 656T1 | 2023-04-04 | Pass
83260 | 2023-03-06 | 2023-03-10 | Solar | 400 | 211D1 | BROWNS CROSSING | 211T1 | 2023-03-13 | Pass
83231 | 2023-03-02 | 2023-03-20 | Solar | 150 | 232D2 | LISBON FALLS | 232T2 | 2023-03-29 | Pass
83235 | 2023-03-02 | 2023-03-06 | Fuel Cell | 930 | 688D1 | KITTERY | 688T1 | 2023-03-28 | Pass |  |  | Yes
83229 | 2023-03-01 | 2023-03-03 | Fuel Cell | 600 | 420D1 | HOTEL ROAD | 420T2 | 2023-03-14 | Pass
83208 | 2023-02-24 | 2023-03-03 | Solar | 999 | 447D2 | RUMFORD | 447T4 | 2023-03-14 | Fail | Pass | 2023-04-18
83189 | 2023-02-22 | 2023-02-22 | Solar | 1500 | 612D1 | BUTLER'S CORNER | 612T1 | 2023-03-21 | Fail |  |  | Yes
83186 | 2023-02-21 | 2023-02-23 | Solar | 995 | 256D2 | WINTHROP | 256T1 | 2023-02-24 | Fail | Pass | 2023-03-23
83158 | 2023-02-16 | 2023-03-13 | Solar | 160 | 690D1 | HINCKLEY POND | 690T1 | 2023-03-23 | Pass |  |  | Yes
83159 | 2023-02-16 | 2023-03-01 | Solar | 120 | 255D2 | WEST STREET | 255T1 | 2023-03-23 | Fail |  |  | Yes
83131 | 2023-02-14 | 2023-02-21 | Solar | 240 | 621D2 | FACTORY ISLAND | 621T2 | 2023-03-07 | Pass
83095 | 2023-02-13 | 2023-02-24 | Solar | 300 | 239D7 | PARK STREET | 239T2 | 2023-03-16 | Pass
83116 | 2023-02-13 | 2023-02-22 | Solar | 133.2 | 650D4 | RIGBY | 650T2 | 2023-03-01 | Pass
83066 | 2023-02-09 | 2023-02-13 | Solar | 160 | 629D3 | KENNEBUNKPORT | 629T2 | 2023-03-07 | Pass
83040 | 2023-02-08 | 2023-02-23 | Solar | 999 | 837D2 | NEWPORT | 837T2 | 2023-03-07 | Fail | Pass | 2023-04-05
83025 | 2023-02-07 | 2023-02-09 | Solar | 995 | 256D2 | WINTHROP | 256T1 | 2023-02-23 | Fail | Pass | 2023-03-22
83038 | 2023-02-07 | 2023-02-09 | Solar | 100 | 447D4 | RUMFORD | 447T3 | 2023-02-24 | Pass
83018 | 2023-02-03 | 2023-02-09 | Solar | 300 | 620D1 | ELM STREET | 620T2 | 2023-02-28 | Fail | Pass | 2023-04-03
83014 | 2023-02-02 | 2023-02-13 | Solar | 200 | 630D2 | GOOSEFARE | 630T1 | 2023-03-07 | Pass
83016 | 2023-02-02 | 2023-03-03 | Solar | 240 | 630D4 | GOOSEFARE | 630T1 | 2023-04-04 | Fail |  |  | Yes
82985 | 2023-01-30 | 2023-02-09 | Solar | 200 | 656D2 | SANFORD INDUSTRIAL PARK | 656T1 | 2023-02-21 | Pass
82971 | 2023-01-27 | 2023-02-01 | Solar | 100 | 634D4 | MAY STREET | 634T1 | 2023-02-22 | Pass
82924 | 2023-01-20 | 2023-01-23 | Fuel Cell | 975 | 636D2 | MUSSEY ROAD | 636T1 | 2023-03-03 | Pass
82927 | 2023-01-20 | 2023-01-24 | Solar | 500 | 447D4 | RUMFORD | 447T3 | 2023-02-14 | Pass
82862 | 2023-01-06 | 2023-01-10 | Solar | 400 | 813D3 | DEXTER | 813T2 | 2023-01-13 | Pass |  |  | Yes
82873 | 2023-01-06 | 2023-01-11 | Solar | 360 | 650D4 | RIGBY | 650T2 | 2023-02-06 | Pass
82874 | 2023-01-06 | 2023-02-06 | Solar | 999 | 821D1 | GUILFORD | 821T1 | 2023-02-07 | Fail | Fail | 2023-03-02 | Yes
82822 | 2023-01-05 | 2023-01-09 | Solar | 145.92 | 251D1 | UNION | 251T1 | 2023-01-26 | Fail | Pass | 2023-02-01
82781 | 2022-12-28 | 2023-01-18 | Fuel Cell | 975 | 630D1 | GOOSEFARE | 630T1 | 2023-01-26 | Pass |  |  | Yes
82771 | 2022-12-22 | 2023-01-06 | Solar | 996 | 657D4 | SANFORD SWITCH | 657T1 | 2023-01-30 | Fail | Pass | 2023-04-18
82708 | 2022-12-14 | 2023-01-09 | Solar | 500 | 238D1 | MESSINA | 238T1 | 2023-01-11 | Fail | Pass | 2023-03-27
82709 | 2022-12-14 |  |  | 999 | 610D2 | BONNY EAGLE | 610T4 |  |  |  |  | Yes
82674 | 2022-12-13 | 2023-01-03 | Solar | 999 | 821D1 | GUILFORD | 821T1 | 2023-01-03 | Fail |  |  | Yes
82683 | 2022-12-13 | 2023-01-11 | Solar | 700 | 624D2 | FORT HILL | 624T1 | 2023-02-07 | Pass
82671 | 2022-12-08 | 2022-12-12 | Fuel Cell | 650 | 420D3 | HOTEL ROAD | 420T2 | 2023-01-16 | Pass
82669 | 2022-12-06 | 2022-12-23 | Solar | 975 | 239D7 | PARK STREET | 239T2 | 2023-01-12 | Fail | Fail | 2023-02-22 | Yes
82584 | 2022-11-29 | 2022-12-12 | Solar | 890 | 420D6 | HOTEL ROAD | 420T1 | 2022-12-13 | Fail | Pass | 2023-02-23 | Yes
82564 | 2022-11-23 | 2022-12-12 | Solar | 1950 | 693D1 | SCARBOROUGH | 693T1 | 2023-02-13 | Fail |  |  | Yes
82547 | 2022-11-21 | 2022-11-30 | Fuel Cell | 975 | 421D2 | CHALLENGER | 421T1 |  | Fail |  |  | Yes
82518 | 2022-11-16 | 2022-11-29 | Fuel Cell | 975 | 424D4 | LEWISTON LOWER | 424T3 | 2023-01-13 | Pass
82496 | 2022-11-14 | 2022-11-18 | Fuel Cell | 975 | 688D1 | KITTERY | 688T1 | 2023-01-15 | Fail |  |  | Yes
82499 | 2022-11-14 | 2022-11-29 | Solar | 500 | 233D2 | MANCHESTER | 233T1 | 2022-11-30 | Fail | Pass | 2023-05-01
82486 | 2022-11-07 | 2022-11-30 | Fuel Cell | 975 | 630D2 | GOOSEFARE | 630T1 | 2023-01-06 | Pass
82485 | 2022-11-05 | 2022-11-30 | Fuel Cell | 975 | 420D6 | HOTEL ROAD | 420T1 | 2023-01-09 | Pass
82455 | 2022-11-03 | 2022-12-05 | Solar | 100 | 250D2 | TOPSHAM | 250T2 | 2023-05-10 | Pass | Pass | 2023-02-13
82439 | 2022-11-01 | 2022-11-01 | Solar | 950 | 858D4 | STURTEVANT | 858T2 | 2022-11-01 | Pass
82404 | 2022-10-26 | 2022-11-15 | Solar | 750 | 445D1 | RAYMOND 115 KV | 445T1 | 2022-11-17 | Fail |  | 2023-06-21 | Yes
82373 | 2022-10-21 | 2022-11-01 | Solar | 104.16 | 245D2 | STICKNEYS CORNER | 245T1 | 2022-11-02 | Fail | Pass | 2023-02-01
82363 | 2022-10-20 | 2022-11-16 | Fuel Cell | 975 | 636D2 | MUSSEY ROAD | 636T1 | 2022-12-27 | Fail |  |  | Yes
82366 | 2022-10-20 | 2022-10-24 | Solar | 996 | 657D4 | SANFORD SWITCH | 657T1 | 2022-12-27 | Fail | Pass | 2023-04-18
82339 | 2022-10-18 | 2022-11-14 | Solar | 975 | 841D1 | PHILLIPS/STRONG | 841T1 | 2023-01-25 | Fail | Pass | 2023-02-23
82340 | 2022-10-18 | 2022-12-02 | Solar | 975 | 839D2 | OAKLAND | 839T1 | 2022-12-02 | Fail | Fail | 2023-03-30 | Yes
82322 | 2022-10-17 | 2022-10-19 | Solar | 995 | 667D1 | SOUTH SANFORD | 667T2 | 2022-12-01 | Fail | Pass | 2023-03-22 | Yes
82324 | 2022-10-17 | 2022-10-17 | Solar | 975 | 450D1 | SABATTUS | 450T1 | 2022-11-22 | Fail | Fail | 2023-01-23 | Yes
82261 | 2022-10-05 | 2022-11-01 | Solar | 950 | 858D4 | STURTEVANT | 858T2 | 2022-11-02 | Pass
82255 | 2022-10-04 | 2022-10-04 | Solar | 975 | 821D1 | GUILFORD | 821T1 | 2022-10-14 | Fail | Pass | 2023-02-07
82233 | 2022-09-27 | 2022-10-04 | Solar | 100 | 659D9 | SEWALL STREET | 659T2 | 2022-10-12 | Pass
82226 | 2022-09-23 | 2022-09-27 | Solar | 349.998 | 813D1 | DEXTER | 813T1 | 2022-09-28 | Pass |  |  | Yes
82201 | 2022-09-20 | 2022-09-30 | Solar | 390 | 261D3 | BATH 34 | 261T2 | 2022-10-06 | Fail | Pass | 2022-11-30
82202 | 2022-09-20 | 2022-12-02 | Solar | 996 | 407D1 | BRYANT POND | 407T1 | 2022-12-05 | Fail |  |  | Yes
82186 | 2022-09-15 | 2022-10-03 | Solar | 348 | 250D1 | TOPSHAM | 250T2 | 2022-10-03 | Fail |  |  | Yes
82151 | 2022-09-09 | 2022-09-09 | Solar | 160 | 213D3 | BRUNSWICK WEST SIDE | 213T1 | 2022-09-23 | Pass
82152 | 2022-09-09 | 2022-09-12 | Solar | 260 | 273D4 | BRUNSWICK HYDRO | 273T2 | 2022-10-04 | Fail | Pass | 2023-01-23
82143 | 2022-09-08 | 2022-09-30 | Solar | 228 | 860D1 | UNITY | 860T1 | 2023-03-09 | Fail |  |  | Yes
82084 | 2022-08-29 | 2022-09-09 | Solar | 1000 | 416D1 | GRAY | 416T2 | 2022-10-07 | Fail | Fail |  | Yes
82055 | 2022-08-25 | 2022-12-01 | Solar | 275 | 823D2 | HARRIS | 823T5 | 2023-02-24 | Pass
82053 | 2022-08-23 | 2022-08-23 | Solar | 1000 | 846D1 | PROSPECT | 846T1 | 2022-09-02 | Fail | Pass | 2022-11-11
82010 | 2022-08-15 | 2022-08-18 | Solar/Battery | 996 | 445D1 | RAYMOND 115 KV | 445T1 | 2022-08-22 | Fail | Fail | 2022-09-21 | Yes
82007 | 2022-08-12 | 2022-08-30 | Solar | 1875 | 272D4 | NORTH AUGUSTA | 272T1 | 2022-09-14 | Fail | Fail | 2022-11-08 | Yes
81972 | 2022-08-10 | 2022-08-17 | Solar | 975 | 246D2 | THOMASTON CREEK | 246T1 | 2022-09-09 | Fail | Fail | 2022-10-21 | Yes
81959 | 2022-08-08 | 2022-09-14 | Solar | 2000 | 431D2 | MECHANIC FALLS | 431T1 | 2022-09-13 | Fail | Fail |  | Yes
81960 | 2022-08-08 | 2022-09-28 | Solar | 749 | 860D2 | UNITY | 860T1 | 2022-10-05 | Fail | Fail | 2022-11-21 | Yes
81961 | 2022-08-08 | 2022-09-28 | Solar | 749 | 209D3 | BOOTHBAY HARBOR | 209T1 | 2022-09-30 |  |  |  | Yes
81963 | 2022-08-08 | 2022-08-08 | Solar | 749 | 250D1 | TOPSHAM | 250T2 | 2022-09-02 | Fail | Pass | 2022-11-02
81964 | 2022-08-08 | 2022-09-28 | Solar | 749 | 817D3 | FAIRFIELD | 817T1 | 2022-09-30 |  |  |  | Yes
81965 | 2022-08-08 | 2022-08-15 | Solar | 749 | 438D1 | PAPOOSE POND | Tap off of Transmission Line | 2022-09-12 | Fail | Pass | 2022-12-12
81966 | 2022-08-08 | 2022-08-15 | Solar | 749 | 850D2 | SEARSPORT | 850T1 | 2022-09-14 | Fail | Pass | 2022-12-13
81967 | 2022-08-08 | 2022-08-15 | Solar | 749 | 837D2 | NEWPORT | 837T2 | 2022-08-29 | Fail | Fail | 2023-01-16 | Yes
81968 | 2022-08-08 | 2022-08-15 | Solar | 749 | 861D9 | VASSALBORO | 861T1 | 2022-09-13 | Fail | Fail | 2022-11-06 | Yes
81956 | 2022-08-05 | 2022-08-11 | Solar | 725 | 412D3 | DEER RIPS | 412T4 | 2022-09-13 | Pass
81957 | 2022-08-05 | 2022-08-11 | Solar | 725 | 412D3 | DEER RIPS | 412T4 | 2022-09-26 | Fail | Fail | 2022-11-21 | Yes
81958 | 2022-08-05 | 2022-08-12 | Solar | 2000 | 602D2 | BASSETT | 602T1 | 2022-08-29 | Fail | Pass | 2022-11-02 | Yes
81947 | 2022-08-04 | 2022-08-15 | Solar | 153.6 | 251D1 | UNION | 251T1 | 2022-08-29 | Fail |  | 2022-10-10 | Yes
81955 | 2022-08-04 | 2022-08-11 | Solar | 450 | 811D1 | CORINNA | 811T1 | 2022-08-30 | Pass |  |  | Yes
81945 | 2022-08-03 | 2022-08-08 | Solar | 500 | 866D2 | WESTON | 866T2 | 2022-10-04 | Pass |  |  | Yes
81942 | 2022-08-02 | 2022-08-08 | Solar | 996 | 470D1 | SAND ROAD TAP | 470T1 | 2022-08-09 | Fail | Pass | 2022-09-27
81911 | 2022-07-29 | 2022-08-05 | Solar | 530 | 861D9 | VASSALBORO | 861T1 | 2022-08-31 | Fail | Pass | 2022-10-12 | Yes
81910 | 2022-07-27 | 2022-08-04 | Solar | 996 | 861D9 | VASSALBORO | 861T1 | 2022-08-11 | Fail | Fail | 2022-10-05 | Yes
81908 | 2022-07-26 | 2022-08-04 | Solar | 165 | 252D2 | WALDOBORO | 252T1 |  |  |  |  | Yes
81909 | 2022-07-26 | 2022-08-04 | Solar | 996 | 837D2 | NEWPORT | 837T2 | 2022-08-29 | Fail |  | 2022-10-03 | Yes
81849 | 2022-07-25 | 2022-08-01 | Solar | 996 | 438D1 | PAPOOSE POND | Tap off of Transmission Line | 2022-08-24 | Fail | Fail | 2022-10-10 | Yes
81850 | 2022-07-25 | 2022-08-12 | Solar | 996 | 850D2 | SEARSPORT | 850T1 | 2022-09-06 | Fail | Fail | 2022-10-17 | Yes
81851 | 2022-07-25 | 2022-08-25 | Solar | 2000 | 667D1 | SOUTH SANFORD | 667T2 | 2022-10-12 | Fail |  |  | Yes
81852 | 2022-07-25 |  | Solar | 1700 | 626D1 | HIGH STREET | 626T1 |  |  |  |  | Yes
81894 | 2022-07-25 | 2022-08-15 | Solar | 999 | 866D2 | WESTON | 866T2 | 2022-08-29 | Fail | Fail | 2022-09-21 | Yes
81895 | 2022-07-25 | 2022-08-15 | Solar | 400 | 454D2 | TURNER | 454T1 | 2022-08-25 | Pass
81896 | 2022-07-25 | 2022-08-01 | Solar | 730 | 412D3 | DEER RIPS | 412T4 | 2022-08-01 | Fail |  |  | Yes
81847 | 2022-07-21 |  |  | 210 | 638D2 | NORTH LIMINGTON | 638T1 |  |  |  |  | Yes
81848 | 2022-07-21 | 2022-07-21 | Solar | 850 | 412D3 | DEER RIPS | 412T4 | 2022-08-29 | Fail | Fail | 2022-10-17 | Yes
81817 | 2022-07-20 | 2022-07-27 | Solar | 1000 | 837D2 | NEWPORT | 837T2 | 2022-08-29 | Fail | Fail | 2022-10-10 | Yes
81819 | 2022-07-20 | 2022-07-27 | Solar | 999 | 821D3 | GUILFORD | 821T2 | 2022-09-13 | Fail | Pass | 2022-11-02
81816 | 2022-07-19 | 2022-07-25 | Solar | 996 | 860D2 | UNITY | 860T1 | 2022-08-02 | Fail |  | 2022-09-02 | Yes
81815 | 2022-07-18 | 2022-08-02 | Solar | 124 | 225D4 | FREEPORT | 225T1 | 2022-08-16 | Fail |  |  | Yes
81810 | 2022-07-15 | 2022-07-22 | Solar | 996 | 209D3 | BOOTHBAY HARBOR | 209T1 | 2022-08-18 | Fail | Pass | 2022-10-05
81811 | 2022-07-15 | 2022-07-22 | Solar | 996 | 250D1 | TOPSHAM | 250T2 | 2022-08-18 | Fail |  |  | Yes
81812 | 2022-07-15 | 2022-07-22 | Solar | 996 | 817D3 | FAIRFIELD | 817T1 | 2022-08-18 | Fail |  | 2022-09-07 | Yes
81754 | 2022-07-08 | 2022-07-12 | Solar | 190 | 457D2 | MONMOUTH | 457T2 | 2022-07-27 | Pass |  |  | Yes
81752 | 2022-07-01 | 2022-07-12 | Solar | 540 | 250D2 | TOPSHAM | 250T2 | 2022-07-25 | Fail | Pass | 2022-09-13
81680 | 2022-06-24 | 2022-07-08 | Solar | 466 | 255D2 | WEST STREET | 255T1 | 2022-08-01 | Pass
81653 | 2022-06-21 | 2022-06-27 | Solar | 115.2 | 470D1 | SAND ROAD TAP | 470T1 | 2022-07-08 | Pass
81675 | 2022-06-21 | 2022-06-27 | Solar | 990 | 431D1 | MECHANIC FALLS | 431T2 | 2022-07-08 | Fail |  |  | Yes
81676 | 2022-06-21 | 2022-06-29 | Solar | 875 | 412D3 | DEER RIPS | 412T4 | 2022-07-27 | Fail |  |  | Yes
81677 | 2022-06-21 | 2022-06-29 | Solar | 875 | 412D3 | DEER RIPS | 412T4 | 2022-07-27 | Fail |  |  | Yes
81678 | 2022-06-21 | 2022-06-29 | Solar | 1000 | 858D4 | STURTEVANT | 858T2 | 2022-08-01 | Fail |  |  | Yes
81679 | 2022-06-21 | 2022-06-29 | Solar | 1000 | 858D4 | STURTEVANT | 858T2 | 2022-08-01 | Fail |  |  | Yes
81628 | 2022-06-17 | 2022-06-24 | Solar | 244 | 839D2 | OAKLAND | 839T1 | 2022-07-09 | Pass |  |  | Yes
81512 | 2022-06-02 | 2022-06-08 | Solar | 975 | 852D1 | SHAWMUT | 852T3 | 2022-06-15 | Fail | Fail |  | Yes
81513 | 2022-06-02 | 2022-06-08 | Solar | 975 | 873D1 | COUNTY RD (RICE RIPS) | 873T1 | 2022-06-15 | Fail | Pass | 2022-09-01
81515 | 2022-06-02 | 2022-06-08 | Solar | 975 | 873D1 | COUNTY RD (RICE RIPS) | 873T1 | 2022-06-27 | Fail |  |  | Yes
81516 | 2022-06-02 | 2022-06-08 | Solar | 975 | 454D2 | TURNER | 454T1 | 2022-06-15 | Fail |  |  | Yes
81506 | 2022-05-31 | 2022-06-06 | Solar | 975 | 870D1 | WINSLOW | 870T4 | 2022-07-06 | Fail |  | 2022-10-11 | Yes
81508 | 2022-05-31 | 2022-06-06 | Solar | 975 | 853D1 | SKOWHEGAN NORTH SIDE | 853T1 | 2022-06-15 | Fail |  |  | Yes
81509 | 2022-05-31 | 2022-06-06 | Solar | 975 | 853D1 | SKOWHEGAN NORTH SIDE | 853T1 | 2022-06-15 | Fail |  |  | Yes
81511 | 2022-05-31 | 2022-06-06 | Solar | 350 | 866D2 | WESTON | 866T2 | 2022-07-19 | Pass
81489 | 2022-05-27 | 2022-05-31 | Solar | 475 | 412D3 | DEER RIPS | 412T4 | 2022-06-08 | Pass
81435 | 2022-05-26 | 2022-06-01 | Solar | 975 | 412D3 | DEER RIPS | 412T4 | 2022-06-08 | Fail |  |  | Yes
81465 | 2022-05-26 | 2022-06-01 | Solar | 900 | 255D2 | WEST STREET | 255T1 | 2022-06-15 | Fail |  |  | Yes
81413 | 2022-05-23 | 2022-05-24 | Solar | 975 | 870D1 | WINSLOW | 870T4 | 2022-06-08 | Fail |  |  | Yes
81409 | 2022-05-20 | 2022-05-27 | Solar | 200 | 237D1 | MCCOYS | 237T1 | 2022-06-17 | Pass |  |  | Yes
81396 | 2022-05-19 | 2022-05-23 | Solar | 337.5 | 603D2 | BERWICK | 603T1 | 2022-08-11 | Fail | Pass | 2022-10-31
81395 | 2022-05-17 | 2022-06-06 | Solar | 975 | 457D2 | MONMOUTH | 457T2 | 2022-06-08 | Fail |  |  | Yes
81393 | 2022-05-16 | 2022-05-31 | Solar | 125 | 647D1 | PRIDES CORNER | 647T2 | 2022-06-14 | Pass
81394 | 2022-05-16 | 2022-05-23 | Solar | 975 | 457D2 | MONMOUTH | 457T2 | 2022-06-10 | Fail | Pass | 2022-07-29
81270 | 2022-05-09 | 2022-05-13 | Solar | 104.1 | 430D1 | LOVELL | 430T1 |  |  |  |  | Yes
81265 | 2022-05-03 | 2022-05-09 | Solar | 975 | 839D2 | OAKLAND | 839T1 | 2022-05-26 | Fail |  |  | Yes
81267 | 2022-05-03 | 2022-07-14 | Solar | 975 | 839D2 | OAKLAND | 839T1 | 2022-05-26 | Fail |  |  | Yes
81262 | 2022-05-02 | 2022-05-09 | Solar | 975 | 663D2 | SOUTH BERWICK | 663T1 | 2022-06-22 | Fail |  |  | Yes
81264 | 2022-05-02 | 2022-05-09 | Solar | 150 | 821D1 | GUILFORD | 821T1 | 2022-08-30 | Pass
81490 | 2022-04-30 | 2022-05-05 | Solar | 800 | 263D1 | BOWMAN STREET | 34kV BUS 2 | 2022-06-15 | Pass | Pass | 2022-08-16
81259 | 2022-04-29 | 2022-04-29 | Solar | 975 | 638D2 | NORTH LIMINGTON | 638T1 | 2022-07-06 | Fail |  |  | Yes
81260 | 2022-04-29 | 2022-05-05 | Solar | 650 | 861D9 | VASSALBORO | 861T1 | 2022-06-02 | Pass |  |  | Yes
81257 | 2022-04-28 | 2022-05-05 | Solar | 999 | 638D1 | NORTH LIMINGTON | 638T1 |  |  |  |  | Yes
81258 | 2022-04-28 | 2022-05-16 | Solar | 975 | 638D2 | NORTH LIMINGTON | 638T1 | 2022-07-06 | Fail |  |  | Yes
81223 | 2022-04-25 | 2022-04-25 | Other | 350 | 435D1 | NORWAY | 435T2 | 2022-07-21 | Pass
81222 | 2022-04-21 | 2022-04-29 | Solar | 975 | 663D2 | SOUTH BERWICK | 663T1 | 2022-07-06 | Fail |  |  | Yes
81170 | 2022-04-20 | 2022-04-27 | Solar | 750 | 695D2 | LEBANON | 695T1 | 2022-05-05 | Fail |  |  | Yes
81171 | 2022-04-20 | 2022-04-25 | Solar | 850 | 631D1 | LAMBERT STREET | 631T1 | 2022-07-08 | Fail | Pass | 2022-08-18
81179 | 2022-04-20 | 2022-04-27 | Solar | 750 | 695D2 | LEBANON | 695T1 | 2022-05-26 | Fail |  |  | Yes
81200 | 2022-04-20 | 2022-04-27 | Solar | 975 | 841D1 | PHILLIPS/STRONG | 841T1 | 2022-05-19 | Fail | Pass | 2022-07-21
81201 | 2022-04-20 | 2022-04-27 | Solar | 975 | 457D1 | MONMOUTH | 457T1 | 2022-05-17 | Fail | Pass | 2022-08-02
81203 | 2022-04-20 | 2022-04-27 | Solar | 975 | 841D1 | PHILLIPS/STRONG | 841T1 | 2022-05-18 | Fail |  |  | Yes
81132 | 2022-04-13 | 2022-04-15 | Solar | 172 | 874D1 | BELFAST 115 | 874T2 | 2022-05-27 | Pass |  |  | Yes
81130 | 2022-04-03 | 2022-04-15 | Solar | 975 | 225D4 | FREEPORT | 225T1 | 2022-06-02 | Fail | Pass | 2022-08-03 | Yes
81019 | 2022-03-30 | 2022-04-07 | Solar | 975 | 225D4 | FREEPORT | 225T1 | 2022-04-08 | Fail |  |  | Yes
81015 | 2022-03-29 | 2022-04-04 | Solar | 650 | 861D9 | VASSALBORO | 861T1 | 2022-04-28 | Fail |  |  | Yes
81016 | 2022-03-29 | 2022-04-04 | Solar | 280 | 865D5 | WEST WATERVILLE | 865T2 | 2022-05-17 | Fail | Pass | 2022-06-27
81017 | 2022-03-29 | 2022-04-07 | Solar | 500 | 444D2 | RAYMOND 34 KV | 444T1 | 2022-04-25 | Fail | Pass | 2022-08-12 | Yes
81006 | 2022-03-25 | 2022-04-21 | Solar | 475 | 239D10 | PARK STREET | 239T5 | 2022-05-19 | Pass |  |  | Yes
80962 | 2022-03-22 | 2022-03-22 | Solar | 975 | 244D2 | SOUTH CHINA | 244T1 | 2022-04-19 | Fail |  |  | Yes
80971 | 2022-03-22 | 2022-03-29 | Solar | 975 | 244D2 | SOUTH CHINA | 244T1 | 2022-04-29 | Fail | Pass | 2022-07-29 | Yes
80892 | 2022-03-21 | 2022-03-25 | Solar | 975 | 239D10 | PARK STREET | 239T5 | 2022-05-17 | Pass
80977 | 2022-03-21 | 2022-03-31 | Solar | 2000 | 457D2 | MONMOUTH | 457T2 | 2022-04-21 | Fail |  |  | Yes
80842 | 2022-03-02 | 2022-03-17 | Solar | 975 | 450D1 | SABATTUS | 450T1 | 2022-04-15 | Fail |  |  | Yes
80841 | 2022-03-01 | 2022-03-08 | Solar | 1990 | 801D1 | ANSON | 801T1 | 2022-03-29 | Fail |  |  | Yes
80838 | 2022-02-28 | 2022-03-17 | Solar | 1992 | 806D2 | BUCKSPORT | 806T3 | 2022-03-30 | Fail | Pass | 2022-06-25 | Yes
80825 | 2022-02-24 | 2022-03-09 | Solar | 1999 | 233D2 | MANCHESTER | 233T1 | 2022-03-30 | Fail | Fail | 2022-05-17 | Yes
80807 | 2022-02-16 | 2022-02-23 | Solar | 975 | 817D3 | FAIRFIELD | 817T1 | 2022-03-03 | Fail |  |  | Yes
80808 | 2022-02-16 | 2022-02-23 | Solar | 975 | 861D8 | VASSALBORO | 861T1 | 2022-03-29 | Fail | Fail | 2022-05-19 | Yes
80726 | 2022-02-04 | 2022-02-09 | Solar | 975 | 853D1 | SKOWHEGAN NORTH SIDE | 853T1 | 2022-03-28 | Fail |  |  | Yes
80727 | 2022-02-04 | 2022-02-09 | Solar | 975 | 874D1 | BELFAST 115 | 874T2 | 2022-03-07 | Fail |  |  | Yes
80728 | 2022-02-04 | 2022-02-10 | Solar | 975 | 428D3 | LIVERMORE FALLS | 428T1 | 2022-03-04 | Fail | Fail | 2022-06-03 | Yes
80736 | 2022-02-04 | 2022-02-10 | Solar | 975 | 420D7 | HOTEL ROAD | 420T1 | 2022-03-28 | Pass
80737 | 2022-02-04 | 2022-02-09 | Solar | 975 | 420D4 | HOTEL ROAD | 420T1 | 2022-03-03 | Fail |  |  | Yes
80725 | 2022-02-03 | 2022-02-09 | Solar | 975 | 866D2 | WESTON | 866T2 | 2022-02-11 | Fail |  |  | Yes
80701 | 2022-01-31 | 2022-02-04 | Solar | 1750 | 850D1 | SEARSPORT | 850T1 | 2022-02-10 | Fail | Fail | 2022-04-18 | Yes
80677 | 2022-01-26 | 2022-02-02 | Solar | 200 | 693D2 | SCARBOROUGH | 693T1 | 2022-04-06 | Fail | Pass | 2022-05-23
80667 | 2022-01-25 | 2022-02-01 | Solar | 499 | 420D7 | HOTEL ROAD | 420T1 | 2022-02-10 | Pass
80656 | 2022-01-20 | 2022-01-27 | Solar | 200 | 650D1 | RIGBY | 650T1 | 2022-02-17 | Pass |  |  | Yes
80658 | 2022-01-20 | 2022-01-27 | Solar | 436 | 650D1 | RIGBY | 650T1 | 2022-02-10 | Fail | Pass | 2022-06-06 | Yes
80659 | 2022-01-20 | 2022-01-27 | Solar | 516 | 650D1 | RIGBY | 650T1 | 2022-02-17 | Pass
80609 | 2022-01-13 | 2022-01-20 | Solar | 1999 | 263D1 | BOWMAN STREET | 34kV BUS 2 | 2022-01-21 | Fail | Pass | 2022-05-16 | Yes
80605 | 2022-01-12 | 2022-01-31 | Solar | 1500 | 412D4 | DEER RIPS | 412T4 | 2022-02-10 | Fail | Fail | 2022-05-12 | Yes
80585 | 2022-01-04 | 2022-01-11 | Solar | 1000 | 861D9 | VASSALBORO | 861T1 | 2022-01-21 | Fail | Pass | 2022-06-20 | Yes

## Comments
Row 4 | 0000002201 $4 refund draft for 108726 and 108725 over payment | Kaiya Hoogkamp | 10/02/25 8:16 AM
Row 15 | Derek will be out of office from 10/01 until 10/15 | Denise Baker | 09/25/25 12:54 PM
Row 23 | Customer changed size of project after refund was issued. Total application fee is $434.00 received check # 0214233428 for addtion $30.00 manual invoice # 910287897/920312010 | Denise Baker | 09/24/25 9:51 AM
Row 23 | Refunded $2736.00 due to overpayment of app fee. Customer entered incorrect project size. Correct size was $404.00 app fee, but customer paid $3140.00 | Thomas Blanchard | 09/18/25 10:32 AM
Row 24 | Customer changed size of project after refund was issued. Total application fee is $434.00 received check # 0214233428 for addtion $30.00 manual invoice invoice # 910287899/920312008 | Denise Baker | 09/24/25 9:54 AM
Row 28 | ESA performed by Dante | Kaiya Hoogkamp | 09/25/25 2:01 PM
Row 39 | Dante & Elisha are doing the ESA | Kaiya Hoogkamp | 09/24/25 12:07 PM
Row 46 | 0000001962 refund draft for $91.20 app fee overpayment | Kaiya Hoogkamp | 08/28/25 9:10 AM
Row 46 | 910283033 app invoice adjusted for $350.80 | Kaiya Hoogkamp | 08/26/25 3:08 PM
Row 46 | App is actually for 125.4 kW AC, not 171, refund of $91.20 is due | Kaiya Hoogkamp | 08/26/25 7:52 AM
Row 46 | Followed up on 7/7/2025 | Andrew Jackson | 07/07/25 2:44 PM
Row 53 | 120007677 duplicate contract made in the portal, cancelled (7/1/2025). | Kaiya Hoogkamp | 07/01/25 10:02 AM
Row 53 | Followed up on AOR(Incomplete) 5/16/2025 | Andrew Jackson | 05/16/25 10:58 AM
Row 74 | 4/17/2025 Withdrawn | Kaiya Hoogkamp | 04/17/25 10:31 AM
Row 75 | 4/17/2025 Withdrawn | Kaiya Hoogkamp | 04/17/25 10:32 AM
Row 76 | 105711 | Kaiya Hoogkamp | 04/17/25 10:32 AM
Row 76 | Additional invoice created for remaining application payment balance, $1996.00 | Kaiya Hoogkamp | 03/18/25 9:23 AM
Row 77 | Additional invoice created for remaining application payment balance, $1996.00 | Kaiya Hoogkamp | 03/18/25 9:23 AM
Row 80 | Draft 0000001119 refund issued via ACH on 5/2/2025 | Kaiya Hoogkamp | 05/02/25 8:37 AM
Row 80 | Adjusted Ombudsman fee invoice to $0.00 910265697 | Kaiya Hoogkamp | 05/01/25 9:28 AM
Row 80 | Adjusted app invoice to $0.00 910264462 | Kaiya Hoogkamp | 04/22/25 4:06 PM
Row 80 | 4/2/25 app withdrawn. | Kaiya Hoogkamp | 04/02/25 3:06 PM
Row 81 | 3/19/25 Application withdrawn. Failed technical screen and will fail and ESA. Advised to proceed with level 4. | Kaiya Hoogkamp | 03/19/25 1:12 PM
Row 82 | DO NOT EXECUTE IA OR COC UNTIL OMBUDSMAN FEE IS PAID | Kaiya Hoogkamp | 05/07/25 11:45 AM
Row 83 | DO NOT EXECUTE IA OR COC UNTIL OMBUDSMAN FEE IS PAID | Kaiya Hoogkamp | 05/07/25 11:46 AM
Row 84 | 3/19/25 Application withdrawn. Failed technical screen and will fail and ESA. Advised to proceed with level 4. | Kaiya Hoogkamp | 03/19/25 12:55 PM
Row 85 | 3/19/25 Application withdrawn. Failed technical screen and will fail and ESA. Advised to proceed with level 4. | Kaiya Hoogkamp | 03/19/25 1:03 PM
Row 89 | 2/26/25 emailed template to apply $1500 from previous ESA to this new PIA invoice | Kaiya Hoogkamp | 02/26/25 4:09 PM
Row 89 | If they go forward with the ESA we need to zero out previous ESA invoice and move funds to this new ESA | Kaiya Hoogkamp | 02/21/25 12:07 PM
Row 89 | Adjusted to $0.00 invoice 910253996 | Kaiya Hoogkamp | 02/18/25 1:12 PM
Row 89 | App fee is waived, previous project, 104609, could not be completed due to a level 4 study. We waived app fee and ESA fee (move fee from previous project to new project). | Kaiya Hoogkamp | 02/17/25 10:33 AM
Row 93 | 2/13/25 customer submitted payment and it was received. Opening the project up instead of reapplication. | Kaiya Hoogkamp | 02/13/25 8:20 AM
Row 93 | 2/11/25 project withdrawn, failure to pay application fee and unresponsive to outreach. | Kaiya Hoogkamp | 02/11/25 9:15 AM
Row 94 | Application late past AOR complete date due to developer delay sending application payment. | Kaiya Hoogkamp | 02/11/25 3:05 PM
Row 94 | Developer provided documentation of wire that was sent on 2/10/2025, reopened the application. | Kaiya Hoogkamp | 02/11/25 2:59 PM
Row 94 | 2/11/25 project withdrawn, failure to pay application fee and unresponsive to outreach. | Kaiya Hoogkamp | 02/11/25 9:14 AM
Row 99 | 1/29/25 offered one time extention to 2/5/2025 waiting for wire payment. | Kaiya Hoogkamp | 01/29/25 3:52 PM
Row 100 | $48 refunded, they overpaid the application fee. Draft:0000001583 | Kaiya Hoogkamp | 07/02/25 2:13 PM
Row 100 | 0000000189 is the draft refund | Kaiya Hoogkamp | 05/16/25 9:31 AM
Row 100 | 4/16/25 application withdrawn. Project unresponsive to outreach after technical screen failure. | Kaiya Hoogkamp | 04/16/25 8:16 AM
Row 102 | The developer advised this project was submitted in error and is withdrawn. | Kaiya Hoogkamp | 12/23/24 11:49 AM
Row 106 | $187.64 invoice 910266466/920289826 | Kaiya Hoogkamp | 05/07/25 9:24 AM
Row 106 | Additional $187.64 invoice received. Sent to workf flow 5/6/25. Per Dante "Project 104903 – the additional two hours were for a peer review. Its dated near the start of the month and on the other its dated at the end of the month so it must have been missed because it was split between the two invoices. " | Kaiya Hoogkamp | 05/06/25 10:21 AM
Row 106 | Original IA for incorrect $2500 910250371/ 920272691 Updated PIA to $1500 910250593/920272951 | Kaiya Hoogkamp | 01/21/25 3:17 PM
Row 109 | Developer is proposing a utility owned 750 kVA Pad mounted transformer. This will exceed the $30,000 Level 2 Threshold and will need to go to a level 4 study. | Nathan Lawrence | 12/17/24 1:56 PM
Row 109 | AOR complete delayed due to customer, waiting for payment to be received. | Kaiya Hoogkamp | 12/13/24 10:41 AM
Row 110 | TS Failed due to costs for proposed upgrades. | Nathan Lawrence | 01/08/25 10:10 AM
Row 110 | AOR complete delayed due to customer, waiting for payment to be received. | Kaiya Hoogkamp | 12/13/24 10:42 AM
Row 111 | AOR complete delayed due to customer, waiting for payment to be received. | Kaiya Hoogkamp | 12/13/24 10:42 AM
Row 112 | AOR complete delayed due to customer, waiting for payment to be received. | Kaiya Hoogkamp | 12/13/24 10:41 AM
Row 113 | AOR complete delayed due to customer, waiting for payment to be received. | Kaiya Hoogkamp | 12/13/24 10:41 AM
Row 114 | ESA original amount deposit due was $1500 | Kaiya Hoogkamp | 06/04/25 12:19 PM
Row 114 | 12/4/2024 informed developer we needed to terminate ESA and withdraw project due to level 4 PRJ 308 being in study. | Kaiya Hoogkamp | 05/14/25 9:11 AM
Row 114 | terminated contract on 3/11/25 | Kaiya Hoogkamp | 03/11/25 1:21 PM
Row 115 | Withdrawn on 1/2/2025 | Kaiya Hoogkamp | 01/27/25 8:32 AM
Row 118 | 12/2/2024 customer requested to withdraw, as they have not finalized the SLD. | Kaiya Hoogkamp | 12/02/24 11:47 AM
Row 122 | 11/7/24 application failed technical screen and was advised it would fail addtional screening. Application withdrew and will reapply as a level 4. | Kaiya Hoogkamp | 11/07/24 11:13 AM
Row 123 | 12/4/2024 customer has withdrawn and will apply as a level 4 | Kaiya Hoogkamp | 12/04/24 12:19 PM
Row 125 | Application Fee waived, this is a resubmission for original application 101658 | Kaiya Hoogkamp | 09/25/24 12:11 PM
Row 128 | Holding COC due to problems with the phone line. CMP cannot connect to the meter. | Nathan Lawrence | 03/11/25 1:32 PM
Row 129 | 9/3/2024 app withdrawn, it incorrectly applied as a level 2, it needs to be a level 4. Customer advised of this. | Kaiya Hoogkamp | 09/03/24 9:54 AM
Row 131 | MANUAL PORTAL APPLICATION | Kaiya Hoogkamp | 09/23/24 12:15 PM
Row 132 | Original projects 103022 ($1060) and 103021 ($200). $1060+$200 = $1260. The NEW app total is $1180. $1180 - $1260 = -$80 is due to the customer as a refund. | Kaiya Hoogkamp | 08/07/24 3:02 PM
Row 133 | Original projects 103019 ($250 payment valid) and 103017 (project went to tech screen). App total is $350. Minus the $250 availible = $100 due | Kaiya Hoogkamp | 08/07/24 2:54 PM
Row 134 | Original projects 103016 & 103014, both projects went through tech screen, so full app total of $400 is due | Kaiya Hoogkamp | 08/07/24 2:39 PM
Row 136 | 9/30/2024 ESA failed, project withdrawn | Kaiya Hoogkamp | 10/31/24 10:37 AM
Row 136 | 8/23/24 resent ESA for new signatures, with a date line added next to customer signature | Kaiya Hoogkamp | 08/23/24 11:41 AM
Row 137 | 8/6/24 withdrawn, project being combined. | Kaiya Hoogkamp | 08/06/24 3:13 PM
Row 138 | 8/12/2024 failed ESA, project withdrawn | Kaiya Hoogkamp | 08/12/24 3:17 PM
Row 139 | 8/6/24 withdrawn, project being combined. | Kaiya Hoogkamp | 08/12/24 3:19 PM
Row 140 | 8/23/2024 project withdrawn after failing ESA | Kaiya Hoogkamp | 10/15/24 1:48 PM
Row 141 | 10/2/2024 ESA failed and project withdrawn. | Kaiya Hoogkamp | 10/15/24 1:54 PM
Row 141 | 7/30 invoice adjustment to make it $2050, funds are on debtor. Need to wait for adjustment invoice before entering IT ticket to clear. 910231855 | Kaiya Hoogkamp | 09/12/24 3:21 PM
Row 142 | 8/28/2024 ESA failed, project withdrawn. | Kaiya Hoogkamp | 10/15/24 1:56 PM
Row 144 | 9/3/2024 ESA failed, project withdrawn. | Kaiya Hoogkamp | 10/15/24 1:57 PM
Row 145 | Kaiya Hoogkamp 4/7/25 email for IA sent. 30 BD 5/20/2025 | Kaiya Hoogkamp | 04/07/25 8:43 AM
Row 147 | 8/12/2024 project withdrawn, failed ESA | Kaiya Hoogkamp | 08/13/24 3:18 PM
Row 154 | 6/14/2024 customer advsied they are withdrawing and reapplying as a level 4. They did not mean to apply as a level 2. | Kaiya Hoogkamp | 06/14/24 10:33 AM
Row 156 | Application delayed AOR complete due to customer waiting for PE stamp on their SLD | Kaiya Hoogkamp | 07/10/24 2:09 PM
Row 158 | 6/18/2024 customer confirmed they are withdrawing after failing technical screen and reapplying as a level 4. | Kaiya Hoogkamp | 06/18/24 10:22 AM
Row 159 | 6/10/24 customer failed technical screen and requested to withdraw | Kaiya Hoogkamp | 06/10/24 10:34 AM
Row 160 | kWh, No on-site load | Nathan Lawrence | 08/01/24 1:18 PM
Row 162 | 7/16/2024 project emailed to confirm withdrawn after failing technical screen | Kaiya Hoogkamp | 07/17/24 8:25 AM
Row 164 | 6/5/2024 project failed tech screen and requested to withdraw and reapply as level 4. | Kaiya Hoogkamp | 10/15/24 2:11 PM
Row 166 | 120006528 terminated contract, ESA was never performed. | Kaiya Hoogkamp | 03/10/25 1:51 PM
Row 166 | 7/16/2024 application withdrawn as we cannot perform the level 2 ESA at this time. Refund has been issued. 0000001479 | Kaiya Hoogkamp | 07/16/24 3:34 PM
Row 167 | Additional ESA Invoice 910265922/920289270 for $656.73, additional study charges that were initially missed from Dante due to being out at the time. | Kaiya Hoogkamp | 05/02/25 11:49 AM
Row 169 | 6/28/2024 ESA failed, project withdrawn. | Kaiya Hoogkamp | 10/15/24 2:14 PM
Row 170 | 5/23/2024 ESA failed, project withdrawn. | Kaiya Hoogkamp | 10/15/24 2:15 PM
Row 172 | Withdrawn 4/5/2024 Customer did not respond to multiple outreach attempts to provide required documents and payment to deem application complete. | Kaiya Hoogkamp | 04/05/24 10:13 AM
Row 173 | Withdrawn 4/5/2024 Customer did not respond to multiple outreach attempts to provide required documents and payment to deem application complete. | Kaiya Hoogkamp | 04/05/24 10:18 AM
Row 174 | No on-site load | Nathan Lawrence | 08/19/24 12:46 PM
Row 175 | Debit memo to offset Credit memo: 910265865/920289224 | Kaiya Hoogkamp | 05/02/25 9:46 AM
Row 175 | credit memo created to offset invoice 910263066/920286135. Credit Memo is 910264738/920288363 | Kaiya Hoogkamp | 04/24/25 10:48 AM
Row 175 | 5/21/2024 ESA failed, project withdrawn. | Kaiya Hoogkamp | 10/15/24 2:18 PM
Row 176 | Refunded thru credit of 811.24 given to Level4 PRJ 820 per Tyler | Thomas Blanchard | 03/06/25 8:32 AM
Row 177 | 5/1/2024 project failed ESA and withdrawn. | Kaiya Hoogkamp | 10/15/24 2:20 PM
Row 179 | 4/5/2024 Refund processed in SAP. | Kaiya Hoogkamp | 04/05/24 10:55 AM
Row 179 | INC3492935 entered to open up refund for $1500 ESA payment. The developer paid for an ESA even though they passed technical screen. | Kaiya Hoogkamp | 04/05/24 10:44 AM
Row 179 | 4/3/24 Customer has withdrawn due to construction issues. | Kaiya Hoogkamp | 04/03/24 11:07 AM
Row 180 | adjusted invoice 910253799 to $0.00 on 2/17/2025 | Kaiya Hoogkamp | 02/17/25 1:37 PM
Row 180 | 3/5/24 customer is withdrawing due to developer being no longer in business. Customer will apply again in the future with a new developer. | Kaiya Hoogkamp | 03/05/24 1:23 PM
Row 180 | 3/4/2024 emailed requesting update as today is day 10 | Kaiya Hoogkamp | 03/04/24 1:55 PM
Row 181 | 2/28/24 customer requested to withdraw and have refund issued, project did not go to technical screen and refund will be issued. | Kaiya Hoogkamp | 02/29/24 9:29 AM
Row 183 | 5/7/2024 project failed ESA and withdrawn. | Kaiya Hoogkamp | 10/15/24 2:26 PM
Row 185 | project withdrawn as it failed ESA on 4/12/2024 | Kaiya Hoogkamp | 04/29/24 9:10 AM
Row 187 | 5/16/2024 project withdrew and reapplied as level 4. | Kaiya Hoogkamp | 09/13/24 3:21 PM
Row 187 | 3/4 application complete delayed by customer - applied for 1000 kW AC then informed us it was 999 kW AC. Required updated SLD & Site plan with the change. Requested updated documents on 2/23/24 and received them 3/4/2024 | Kaiya Hoogkamp | 03/04/24 3:09 PM
Row 187 | currently missing required deration letter. CANNOT issue IA without this documentation 3/4/2024 | Kaiya Hoogkamp | 03/04/24 2:28 PM
Row 188 | Refund used as credit towards a Level4 invoice (PRJ820) per Tyler | Thomas Blanchard | 03/06/25 8:21 AM
Row 188 | 2/7/25 duplicate application fee of $2098 has been refunded. | Kaiya Hoogkamp | 02/07/25 8:22 AM
Row 188 | 5/7/2024 failed ESA, project withdrawn | Kaiya Hoogkamp | 08/26/24 2:39 PM
Row 190 | currently missing required deration letter. CANNOT issue IA without this documentation 3/4/2024 | Kaiya Hoogkamp | 03/04/24 1:27 PM
Row 191 | Refund request number: 0000001051 | Kaiya Hoogkamp | 05/14/25 8:51 AM
Row 191 | 4/19/2024 application withdrawn. | Kaiya Hoogkamp | 08/20/24 1:05 PM
Row 191 | 4/30/2024 refund reissued for $1152. Original amount to be refunded $1500 for ESA. However, there was an outstanding invoice for $348 on invoice 910212016/920232028. That has now been paid. | Kaiya Hoogkamp | 04/30/24 3:10 PM
Row 191 | 4/23 Refund updated to JUST the ESA fee of $1500. We will waive app fee if they reapply in the future. | Kaiya Hoogkamp | 04/23/24 12:31 PM
Row 191 | project withdrawn, cannot process ESA due to level 4 studies. | Kaiya Hoogkamp | 04/19/24 2:30 PM
Row 191 | 4/18/24 processed refuned for $2600 | Kaiya Hoogkamp | 04/18/24 3:28 PM
Row 191 | 910219227 invoice adjustment to adjust invoice to $0 in order to issue refund. We are refunding application and ESA fee due to project being unable to move forward due to level 4 applications. | Kaiya Hoogkamp | 04/16/24 3:26 PM
Row 191 | waiting to receive W-9 or email confirmation of financial responsiblity for the ESA before creating contract. Create the ESA in the portal | Kaiya Hoogkamp | 02/06/24 11:26 AM
Row 194 | 4/26/24 withdrawn after failing ESA | Kaiya Hoogkamp | 08/20/24 12:36 PM
Row 200 | portal contract 120006228 PIA 910212543 / 920232559. Created and cancelled 2/23/24. Portal contract and "old way" contract both made. | Kaiya Hoogkamp | 02/23/24 2:04 PM
Row 201 | 1/3/24 withdrawn after not responding within the 10 business day deadline | Kaiya Hoogkamp | 03/21/24 12:51 PM
Row 202 | 5/17/2024 project failed technical screen and withdrew. | Kaiya Hoogkamp | 10/15/24 2:39 PM
Row 203 | 2/9/2024 project failed ESA and withdrawn. | Kaiya Hoogkamp | 10/15/24 2:38 PM
Row 204 | Withdrawn 1/3/2024 after customer did not provide required documentation within the required 10 days and after an extention was granted. | Kaiya Hoogkamp | 03/21/24 11:39 AM
Row 206 | 4/9/2024 project withdrawn as it failed ESA. | Kaiya Hoogkamp | 04/29/24 9:07 AM
Row 209 | 6/7/2024 project withdrew | Kaiya Hoogkamp | 06/07/24 3:25 PM
Row 209 | 2/6 emailed customer asking for W-9 for New Sharon Community Solar or an email confirming Genie Solar Energy is financially responsible for ESA before we can create contract and PIA | Kaiya Hoogkamp | 02/06/24 10:41 AM
Row 212 | Rick tech screen, originally on time, but, contained wrong project size in TS, delay from Rick for updated TS with correct project size caused delay sent to customer | Kaiya Hoogkamp | 09/09/24 1:49 PM
Row 216 | 4/29/2024 failed ESA, project withdrawn | Kaiya Hoogkamp | 06/18/24 3:02 PM
Row 216 | Developer submitted 4 applications for same size all at once during transition to new portal, payments and additional documents were not all submitted at the same time. There was numerous back and forth with customer to ensure we received payments, export control and new account creation caused delays with the customer. Developer has worked in good faith to keep us informed as they worked to get all required documentation and payment. | Kaiya Hoogkamp | 01/24/24 2:50 PM
Row 217 | Refund draft: 0000000989 | Kaiya Hoogkamp | 05/14/25 8:47 AM
Row 217 | 4/24/2024 withdrawn | Kaiya Hoogkamp | 10/22/24 11:52 AM
Row 217 | 4/23 Refund updated to JUST the ESA fee of $2500. We will waive app fee if they reapply in the future. | Kaiya Hoogkamp | 04/23/24 12:21 PM
Row 217 | project withdrawn as it cannot go through ESA due to level 4 studies. | Kaiya Hoogkamp | 04/19/24 2:20 PM
Row 217 | $4640 refund issued for app fee and ESA. Project withdrawn | Kaiya Hoogkamp | 04/19/24 2:20 PM
Row 217 | 910219232 invoice adjustment to adjust invoice to $0 in order to issue refund. We are refunding application and ESA fee due to project being unable to move forward due to level 4 applications. | Kaiya Hoogkamp | 04/16/24 3:20 PM
Row 218 | Withdrawn 3/22 due to failing ESA | Kaiya Hoogkamp | 04/30/24 10:27 AM
Row 219 | 3/12/2024 project failed ESA and was withdrawn. | Kaiya Hoogkamp | 10/15/24 2:32 PM
Row 221 | 1/22/24 customer requested to withdraw project. | Kaiya Hoogkamp | 02/27/24 12:00 PM
Row 222 | 2/22/2024 failed ESA | Kaiya Hoogkamp | 07/23/24 3:18 PM
Row 224 | 1/11/2024 customer withdrew after technical screen. | Kaiya Hoogkamp | 07/23/24 2:52 PM
Row 226 | Customer requested to withdraw on 1/4/2024 | Kaiya Hoogkamp | 05/07/24 10:57 AM
Row 226 | Refund issued in SAP | Kaiya Hoogkamp | 01/22/24 1:48 PM
Row 226 | Original contract 120005879 cancelled on 1/18/2024, customer withdrawn without doing ESA and PIA $1500 refunded. | Kaiya Hoogkamp | 01/18/24 11:33 AM
Row 226 | Duplicate contract 12000085887 created by Nate Lawrence was cancelled. No payment attached. | Kaiya Hoogkamp | 01/18/24 11:32 AM
Row 227 | 1/7/2024 customer requested to withdraw | Kaiya Hoogkamp | 05/22/24 9:09 AM
Row 229 | 1/2/2024 ESA failed, project withdrawn. | Kaiya Hoogkamp | 10/15/24 2:54 PM
Row 230 | 1/26/2024 project withdrawn after failing ESA | Kaiya Hoogkamp | 07/23/24 3:32 PM
Row 231 | 1/24/2024 customer has decided to withdraw the project. | Kaiya Hoogkamp | 02/27/24 1:21 PM
Row 232 | 2/20/2024 project failed ESA and withdrawn. | Kaiya Hoogkamp | 10/15/24 2:55 PM
Row 235 | No task 24 in SAP | Kaiya Hoogkamp | 12/17/24 2:40 PM
Row 236 | 5/16/2024 project requested to be withdrawn, project no longer viable. | Kaiya Hoogkamp | 10/15/24 2:57 PM
Row 240 | $0.00 invoice 910269585 | Kaiya Hoogkamp | 05/30/25 8:05 AM
Row 240 | Zeroed out ESA invoice, we are waiving the cost, as the customer asked to hold off on study and never confirmed they wanted to continue with ESA. They did not send the deposit. | Kaiya Hoogkamp | 05/30/25 7:58 AM
Row 240 | 5/15/25 project withdrawn due to site feasibility | Kaiya Hoogkamp | 05/19/25 10:05 AM
Row 240 | 4/4/25 email for IA sent. 30 BD 5/19/2025 | Kaiya Hoogkamp | 04/04/25 3:43 PM
Row 240 | Customer has not paid ESA deposit. DO NOT issue COC until we receive payment | Kaiya Hoogkamp | 03/07/25 11:33 AM
Row 242 | original PIA 910202573/920222068 cancelled due to incorrect project name entered in description. Ticket INC3254016 entered to cancel. | Kaiya Hoogkamp | 12/05/23 1:45 PM
Row 244 | 1211/24 project requested to withdraw in favor of their level 4 project 599 | Kaiya Hoogkamp | 12/11/24 8:44 AM
Row 245 | 2/22/2024 project failed ESA and withdrew. | Kaiya Hoogkamp | 10/15/24 3:05 PM
Row 250 | 1/31/2024 project failed ESA and withdrew. | Kaiya Hoogkamp | 10/15/24 3:09 PM
Row 252 | "Install 500 kVA Pad Mount Transformer." listed under "Estimated Cost to Interconnect". | Nathan Lawrence | 09/03/24 2:31 PM
Row 254 | 11/13/2023 project failed ESA and withdrew. | Kaiya Hoogkamp | 10/15/24 3:10 PM
Row 256 | 11/6/2023 project failed tech screen and withdrew. | Kaiya Hoogkamp | 10/15/24 3:17 PM
Row 257 | 10/25/2023 project failed ESA and withdrew. | Kaiya Hoogkamp | 10/15/24 3:18 PM
Row 259 | 910265923/920289271 paid on 5/29/25 | Kaiya Hoogkamp | 05/30/25 1:40 PM
Row 259 | additional ESA invioice: 910265923/920289271 | Kaiya Hoogkamp | 05/02/25 11:52 AM
Row 262 | 12/8/2023 application failed ESA. Project withdrawn. | Kaiya Hoogkamp | 06/24/24 11:53 AM
Row 264 | 9/8/2023 project unresponsive to outreach and withdrawn after 10 bd deadline. | Kaiya Hoogkamp | 10/15/24 3:48 PM
Row 265 | Has a related noti 10300727127 for customer building construction per Gary Ham | Nathan Lawrence | 07/30/24 8:36 AM
Row 267 | 9/14/2023 project failed ESA and project withdrawn. | Kaiya Hoogkamp | 10/16/24 7:40 AM
Row 270 | 1/24/2024 customer withdrew project. | Kaiya Hoogkamp | 10/16/24 7:43 AM
Row 271 | 11/3/2023 project withdrew. | Kaiya Hoogkamp | 10/16/24 7:42 AM
Row 272 | Original PIA 910191401/920210205 was never cleared w/ payment and sales admin cleared 3/26/2024. Created new PIA 910223778/920244513 on 5/23/2024 to apply payment to. | Thomas Blanchard | 05/28/24 2:44 PM
Row 273 | 10/12/2023 project failed ESA and withdrew. | Kaiya Hoogkamp | 10/16/24 8:21 AM
Row 274 | 10/3/2023 project failed ESA and withdrew. | Kaiya Hoogkamp | 10/16/24 8:19 AM
Row 275 | Contract cancelled. | Kaiya Hoogkamp | 03/10/25 1:27 PM
Row 275 | 10/26/2023 project requested to withdraw | Kaiya Hoogkamp | 10/22/24 12:01 PM
Row 276 | ESA Cancelled | Kaiya Hoogkamp | 03/10/25 1:28 PM
Row 276 | 10/26/2023 customer withdrew project. | Kaiya Hoogkamp | 10/16/24 8:28 AM
Row 277 | 4/4/25 email for IA sent. 30 BD 5/19/2025 | Kaiya Hoogkamp | 04/04/25 3:28 PM
Row 278 | 9/20/2023 project failed ESA and withdrew. | Kaiya Hoogkamp | 10/16/24 8:30 AM
Row 279 | 8/16/23 withdrawn after project failed ESA | Kaiya Hoogkamp | 10/07/24 10:53 AM
Row 280 | 5/6/25 Sent additional ESA for study work | Kaiya Hoogkamp | 05/06/25 1:15 PM
Row 280 | Additional PIA for restudy work done Spring 2024 910266050/920289412 $140.73 | Kaiya Hoogkamp | 05/05/25 9:56 AM
Row 280 | Original developer Perennial Renewables LLC, sold to Madison Energy Infrastructure | Kaiya Hoogkamp | 11/26/24 12:58 PM
Row 282 | 1/21/2025 customer withdrew | Kaiya Hoogkamp | 01/22/25 7:37 AM
Row 286 | 9/6/2023 project failed ESA and withdrew. | Kaiya Hoogkamp | 10/16/24 8:35 AM
Row 287 | 9/6/2023 project failed ESA and withdrew. | Kaiya Hoogkamp | 10/16/24 8:35 AM
Row 290 | 8/30/2023 project failed ESA and withdrew. | Kaiya Hoogkamp | 10/16/24 8:36 AM
Row 292 | 8/16/2023 project failed ESA and withdrew. | Kaiya Hoogkamp | 10/16/24 8:37 AM
Row 295 | 9/2/2023 application withdrawn | Kaiya Hoogkamp | 10/18/24 11:48 AM
Row 299 | 7/30/2023 app failed ESA and withdrew | Kaiya Hoogkamp | 10/18/24 11:54 AM
Row 299 | TIN has been used for Acadia Energy, can I use that # | Jessie Ladaga | 06/16/23 12:55 PM
Row 300 | 6/30/2023 application withdrawn | Kaiya Hoogkamp | 10/18/24 11:49 AM
Row 301 | Can I use the Green Lantern #; emailed Christy | Jessie Ladaga | 06/16/23 12:45 PM
Row 302 | Debtor # extended | Jessie Ladaga | 06/16/23 10:45 AM
Row 303 | DEBTOR # CREATED | Jessie Ladaga | 06/29/23 12:52 PM
Row 304 | noti is on debtor 932463 | Kaiya Hoogkamp | 08/28/25 9:54 AM
Row 305 | 9/21/2023 application withdrawn | Kaiya Hoogkamp | 10/18/24 12:01 PM
Row 306 | Invoice for NOTI 10301049886 paid 10/31/24 | Nathan Lawrence | 12/10/24 12:25 PM
Row 307 | 7/14/2023 app failed ESA and project withdrawn | Kaiya Hoogkamp | 10/18/24 12:00 PM
Row 308 | 6/25/2023 application withdrawn | Kaiya Hoogkamp | 10/18/24 12:02 PM
Row 308 | NH Solar Garden payment - confirmed via email - see email? is there a debtor #? is there a w9? | Jessie Ladaga | 06/14/23 5:34 PM
Row 309 | this project failed tech screen in error and needs to be refunded the ESA charge- after rescreen on tech screen they passed. | William Dawe | 07/11/23 8:54 AM
Row 309 | this is on RE # - can i use 1289121? | Jessie Ladaga | 06/14/23 5:20 PM
Row 312 | additional charges found and billable per Portal | Staci Pellegrini | 03/13/24 1:05 PM
| Added charges of $246.68 to invoice on 3/20/24 | Thomas Blanchard | 03/21/24 7:38 AM
Row 312 | no debtor # created. Can i use 929103? W9 is lacking address. Sent email. | Jessie Ladaga | 06/14/23 4:31 PM
Row 312 | debtor # created | Jessie Ladaga | 06/14/23 4:23 PM
Row 312 | email sent requesting w9 | Jessie Ladaga | 05/19/23 11:33 AM
Row 313 | Original developer GREEN LANTERN DEVELOPMENT LLC, sold to Madison Energy Infrastructure | Kaiya Hoogkamp | 11/26/24 12:55 PM
Row 313 | Created new paid 910206445/920226265 ticket sent xfer 2500.00 to correct debtor | Staci Pellegrini | 01/08/24 12:32 PM
Row 313 | pia 910183424/920201756 was canceled by sales admin | Staci Pellegrini | 01/05/24 9:35 AM
Row 313 | Pia was cancel because the payment was on the original payee debtor 924257 / set itnow ticket move to 932591 and will xfer contract to me and then set up new pia to clear. | Staci Pellegrini | 01/05/24 9:33 AM
Row 313 | found debtor # = 932591 | Jessie Ladaga | 06/14/23 2:39 PM
Row 313 | requested w9 | Jessie Ladaga | 06/14/23 2:30 PM
Row 314 | 8/14/2023 application withdrawn | Kaiya Hoogkamp | 10/18/24 12:09 PM
Row 314 | w9 reques sent | Jessie Ladaga | 05/31/23 2:44 PM
Row 314 | Request for w9 was sent out by front end analysis on 5/12/2023 | Jessie Ladaga | 05/12/23 2:48 PM
Row 315 | 8/8/2023 app failed ESA and withdrew | Kaiya Hoogkamp | 10/18/24 12:05 PM
Row 315 | w9 request sent | Jessie Ladaga | 05/31/23 2:48 PM
Row 315 | w9 request sent on 5/12 with ESA | Jessie Ladaga | 05/12/23 2:49 PM
Row 316 | 7/26/23 project failed ESA and withdrawn. | Kaiya Hoogkamp | 09/05/24 10:25 AM
Row 317 | NO W9 REC;D THIS HAS A NOTI # 1508679 | Jessie Ladaga | 06/30/23 3:22 PM
Row 317 | sent a follow up email requesting w9 | Jessie Ladaga | 06/14/23 2:17 PM
Row 317 | w9 email request sent | Jessie Ladaga | 05/31/23 2:26 PM
Row 318 | 5/20/2024 project has withdrawn. | Kaiya Hoogkamp | 05/20/24 3:30 PM
Row 318 | has credit willo need to apply to balance on 83453 email sent to Kiaya | Staci Pellegrini | 01/04/24 2:52 PM
Row 318 | email sent requesting .pdf PIA (study about to kick off) | Jessie Ladaga | 05/12/23 1:49 PM
Row 319 | 6/22/2023 ESA failed, application withdrawn | Kaiya Hoogkamp | 10/18/24 12:15 PM
Row 319 | THIS WAS EXTENDED BY STACI | Jessie Ladaga | 06/14/23 3:49 PM
Row 319 | 1416460 = noti / can this be extended to use? | Jessie Ladaga | 06/14/23 2:07 PM
Row 320 | sent IT ticket | Jessie Ladaga | 05/11/23 9:34 AM
Row 321 | FBL5N review; ? | Jessie Ladaga | 05/17/23 3:00 PM
Row 321 | Sent IT | Jessie Ladaga | 05/15/23 9:20 AM
Row 322 | 10/19/2023 The project listed 83668 is in fact a cancelled project per conversation with developer just now- Ryan Darlow. | Kaiya Hoogkamp | 10/18/24 12:20 PM
Row 322 | to have contract 120005075 reassigned to me then closed out .incorrect debtor | Staci Pellegrini | 03/05/24 4:37 PM
Row 322 | Duplicate contract Pia created for Prj 83668 contract 120005075 debtor 928950 910179620/920197672 incorrect debtor payment 5/5 pa 8400015200 will need to be moved debtor 929226 and applied invoice 920198765 contract 120005124. sent email jess. | Staci Pellegrini | 06/14/23 2:46 PM
Row 322 | sent IT | Jessie Ladaga | 05/15/23 8:44 AM
Row 322 | cutomer has sent in confirmation of ESA payment | Jessie Ladaga | 05/10/23 4:23 PM
Row 322 | have w9 and debtor #, need signed ESA | Jessie Ladaga | 05/10/23 1:06 PM
Row 322 | W9 requested | Jessie Ladaga | 05/10/23 12:59 PM
Row 323 | Payment refund 896..58 was taken from prj 83670 and applied to level 4 prj balance prj 692 1/17/2024 | Staci Pellegrini | 04/26/24 11:30 AM
Row 325 | Credit memo: 910266673 for $19.92 refund that is due | Kaiya Hoogkamp | 05/08/25 9:16 AM
Row 325 | 5/7/25 Sent contract to work flow | Kaiya Hoogkamp | 05/07/25 8:21 AM
Row 325 | New PIA 910266262/920289612 | Kaiya Hoogkamp | 05/06/25 9:42 AM
Row 325 | New Contract: 120007536 released on 5/6/25 | Kaiya Hoogkamp | 05/06/25 9:35 AM
Row 325 | Per Michelle and Brian and sales admin, because we cannot get the PIA to show on the contract, we need to cancel the contract and PIA and start over. 120005031 has been terminated | Kaiya Hoogkamp | 05/06/25 9:10 AM
Row 325 | 910266160/920289513 - new PIA created per Michelle in Sales Admin | Kaiya Hoogkamp | 05/05/25 3:04 PM
Row 325 | Original developer MECHANIC FALLS GLC SOLAR LLC, sold to Madison Energy Infrastructure | Kaiya Hoogkamp | 11/26/24 12:57 PM
Row 325 | INC3162470 ticket requesting payment | Kaiya Hoogkamp | 10/24/23 10:24 AM
Row 325 | Original PIA 910179625/920197692 was never cleared w/ payment and sales admin cleared 9/28/2023. Created new PIA 910199075/920218318 on 10/24/2023 to apply payment to. | Kaiya Hoogkamp | 10/24/23 10:19 AM
Row 326 | katie to create debtor # | Jessie Ladaga | 04/28/23 10:10 AM
Row 327 | old PIA that closed out 910178292/920196202 | Kaiya Hoogkamp | 11/01/23 3:11 PM
Row 327 | sent IT ticket | Jessie Ladaga | 05/12/23 4:07 PM
Row 327 | rec'd W9; found debtor; sent to Christy to fix spelling in SAP and confirm TIN's match | Jessie Ladaga | 04/26/23 12:14 PM
Row 328 | PAID IN FULL with PRJ 339 DG refund 1313.42 and a $290 open credit from prj 81817, (see emails) | Thomas Blanchard | 06/05/25 10:35 AM
Row 328 | 5/17/2023 app failed ESA and withdrawn | Kaiya Hoogkamp | 10/18/24 12:21 PM
Row 328 | pia was created by jess/ pia got cancelled due to no pmt being applied / found no confirmation of payment from the customerr via portal. I sent email to customer 11/11 to confirm if paid or not before we invoice | Staci Pellegrini | 01/11/24 11:36 AM
Row 328 | sent email to Sales Admin to have address updated Debtor # 923285 - office moved; sent W9 and IA for backup documentaiton | Jessie Ladaga | 06/14/23 12:22 PM
Row 328 | need to send email to update address-- speak with staci | Jessie Ladaga | 05/31/23 1:39 PM
Row 328 | debtor # reuqest sent | Jessie Ladaga | 05/10/23 12:52 PM
Row 329 | Original developer GREEN LANTERN DEVELOPMENT LLC, sold to Madison Energy Infrastructure | Kaiya Hoogkamp | 11/26/24 12:56 PM
Row 329 | Debtor creation requested | Jessie Ladaga | 05/09/23 2:38 PM
Row 330 | Kiaya created credit memo | Staci Pellegrini | 11/08/23 5:44 PM
Row 330 | sent email for OCR to place 2500 on 9003006 | Jessie Ladaga | 04/28/23 11:18 AM
Row 330 | sent KK a request to create debtor # | Jessie Ladaga | 04/26/23 1:13 PM
Row 331 | Charges waived, contract closed on 5/7/2024 | Thomas Blanchard | 05/07/24 11:48 AM
Row 331 | PIA Had been preivously cancelled. Contract completed on 10/20/2023. We will not be billing the contractor charges as it was a pass. | Kaiya Hoogkamp | 10/20/23 11:11 AM
Row 331 | This was a tech screen fail in error, it was in fact a PASS but ESA was billed out. | Kaiya Hoogkamp | 10/20/23 11:08 AM
Row 332 | debtor # created | Jessie Ladaga | 05/15/23 2:24 PM
Row 332 | email sent requesting w9 | Jessie Ladaga | 05/10/23 10:52 AM
Row 333 | 4/27/2023 project failed ESA and withdrew | Kaiya Hoogkamp | 09/23/24 2:19 PM
Row 333 | sent request to KK to have # created | Jessie Ladaga | 04/26/23 1:38 PM
Row 335 | 4/23/2023 app withdrawn | Kaiya Hoogkamp | 10/18/24 12:23 PM
Row 336 | April 3, 2024 developer requested withdraw | Kaiya Hoogkamp | 07/11/24 3:55 PM
Row 336 | completed refund 1/17/24 | Staci Pellegrini | 02/20/24 9:02 AM
Row 336 | sent invoices to customer 1/4/2024 this is credit back to the customer no other outstanding projects owed so i requested refund 0000000086 1/17/24 sap | Staci Pellegrini | 01/17/24 9:30 AM
Row 336 | Issue with customer name | Kristina Waterhouse | 04/03/23 2:39 PM
Row 337 | $ is still open on open cash draw as of 5/26 sent ITNOW ticket | Staci Pellegrini | 05/26/23 1:48 PM
Row 337 | 5/16/23 follow up email sent in RE of W9 | Jessie Ladaga | 05/17/23 4:39 PM
Row 337 | Put $2500 (paid on 5/15/2023) ESA fee on debtor 1568046, pending W-9 with Arundel Solar | Kaiya Hoogkamp | 05/16/23 2:44 PM
Row 337 | need w9 with ESA name, email request sent | Jessie Ladaga | 05/12/23 2:38 PM
Row 338 | Refund used towards outstanding novel invoice. | Kaiya Hoogkamp | 06/04/25 9:33 AM
Row 338 | debtor # request sent/ email attached | Jessie Ladaga | 05/10/23 6:23 PM
Row 338 | there is a fully exectued ESA | Jessie Ladaga | 05/10/23 10:22 AM
Row 338 | debtor # creation requested | Jessie Ladaga | 05/10/23 10:21 AM
Row 338 | No ESA - email sent requesting signed Agreement | Jessie Ladaga | 04/26/23 2:15 PM
Row 338 | Requested W9 4/4 | Kristina Waterhouse | 04/04/23 1:28 PM
Row 339 | 6/9/2023 application withdrew | Kaiya Hoogkamp | 10/22/24 12:10 PM
Row 339 | Chase Warren payment on 1289121; sent IT | Jessie Ladaga | 05/12/23 4:46 PM
Row 339 | After researching the project number was over written in error making info look incorrect. | Kristina Waterhouse | 05/04/23 1:52 PM
Row 339 | wrong project details on this ROW- updated cor | William Dawe | 05/04/23 9:54 AM
Row 339 | PIA sent to customer/developer (ReVision) | Jessie Ladaga | 04/26/23 2:51 PM
Row 339 | ESA uploaded; waiting on Christy to release from workfolow to release Contract | Jessie Ladaga | 04/24/23 1:26 PM
Row 339 | need CMP to sign ESA | Jessie Ladaga | 04/24/23 10:43 AM
Row 339 | reuqested katie to create debtor # | Jessie Ladaga | 04/17/23 12:27 PM
Row 340 | 120005064 completed on 2/27/2024 | Kaiya Hoogkamp | 02/27/24 12:33 PM
Row 340 | original contract 120005064 (created incorrectly on Revisions debtor) | Kaiya Hoogkamp | 10/24/23 9:39 AM
Row 340 | sent needed US mailing addy to Katie for # creation | Jessie Ladaga | 04/26/23 3:15 PM
Row 340 | katie to create debtor # | Jessie Ladaga | 04/17/23 12:31 PM
Row 341 | Additinal noti amount of $4547.11 was paid on 7/1/2025 | Kaiya Hoogkamp | 07/16/25 8:07 AM
Row 341 | Noti has additional invoice Follow up invoice sent 5/14/25 $4547.11 | Kaiya Hoogkamp | 06/30/25 10:16 AM
Row 341 | i can create the contract and not release | Jessie Ladaga | 05/10/23 4:25 PM
Row 341 | no signed ESA | Jessie Ladaga | 05/10/23 10:13 AM
Row 341 | Sent email requesting w9 | Jessie Ladaga | 05/09/23 12:16 PM
Row 342 | 4/4/25 email for IA sent. 30 BD 5/19/2025 | Kaiya Hoogkamp | 04/04/25 2:37 PM
Row 346 | 9/26/25 Spoke with Peter on the phone, he confirmed to withdraw the project ((207)754-5025) | Kaiya Hoogkamp | 09/26/25 10:56 AM
Row 346 | 4/4/25 email for IA sent. 30 BD 5/19/2025 | Kaiya Hoogkamp | 04/04/25 2:46 PM
Row 348 | completed refund 1/17/24 sjp | Staci Pellegrini | 02/20/24 9:03 AM
Row 348 | sent invoices to customer 1/4/2024 this is credit back to the customer no other outstanding projects owed so i requested refund 0000000086 1/17/24 sap | Staci Pellegrini | 01/17/24 9:29 AM
Row 349 | Withdraw request from customer 3/21/23 after failed TS. | Nathan Lawrence | 10/15/24 3:28 PM
Row 350 | PIF | Thomas Blanchard | 05/29/24 11:06 AM
Row 350 | Moved 103.42 from Acadia refunded projects to this Acadia balance due. OK'd by Glenn Walker | Thomas Blanchard | 05/29/24 11:03 AM
Row 351 | 4/7/2025 app withdrawn | Kaiya Hoogkamp | 04/07/25 8:54 AM
Row 351 | 4/4/25 email for IA sent. 30 BD 5/19/2025 | Kaiya Hoogkamp | 04/04/25 2:44 PM
Row 352 | no documentation verifying withdrawal | Kaiya Hoogkamp | 10/22/24 12:13 PM
Row 355 | Noti 10300899161 CANC | Nathan Lawrence | 01/30/25 12:45 PM
Row 357 | cleared SAP | Jessie Ladaga | 05/11/23 1:08 PM
Row 357 | need to change/update name in contract, add ESA then release | Jessie Ladaga | 04/24/23 10:34 AM
Row 357 | Requested Katie created debtor | Jessie Ladaga | 04/17/23 12:17 PM
Row 357 | Requested debtor | Kristina Waterhouse | 04/04/23 1:20 PM
Row 358 | Moved 596.78 from Acadia refunded projects to this Acadia balance due. OK'd by Glenn Walker. PIF | Thomas Blanchard | 05/29/24 11:05 AM
Row 360 | contract reassigned to me | Staci Pellegrini | 09/26/23 2:15 PM
Row 360 | charges 1480.08/ 1500.00 will need to refund 19.92. | Staci Pellegrini | 09/26/23 2:03 PM
Row 360 | Created USM1 debtor | Kristina Waterhouse | 04/03/23 3:02 PM
Row 360 | Requested W9 4/3 | Kristina Waterhouse | 04/03/23 12:02 PM
Row 362 | Customer confirmed withdrawal 4/11/2023, resubmitted as a L4. | Nathan Lawrence | 10/15/24 6:07 PM
Row 367 | 12/5/2023 project withdrew due to wetlands and being unable to develop the land. | Kaiya Hoogkamp | 07/09/24 12:53 PM
Row 369 | 3/4/2024 the project failed ESA and is withdrawn. | Kaiya Hoogkamp | 07/09/24 1:00 PM
Row 369 | INC2871444 to move and clear PIA | Kristina Waterhouse | 05/31/23 2:19 PM
Row 369 | Requested debtor in SAP | Kristina Waterhouse | 04/26/23 11:30 AM
Row 369 | Emailed again for W9 request | Kristina Waterhouse | 04/25/23 1:51 PM
Row 369 | Requested W9 | Kristina Waterhouse | 04/04/23 2:22 PM
Row 370 | ESA amount 986.72, study fee was waived. | Kaiya Hoogkamp | 06/25/25 9:23 AM
Row 370 | ESA Fees waived! | Kristina Waterhouse | 04/05/23 2:59 PM
Row 371 | 8/23/2023 application withdrew | Kaiya Hoogkamp | 10/22/24 12:46 PM
Row 372 | Requested debtor in SAP | Kristina Waterhouse | 04/06/23 10:36 AM
Row 372 | Requested W9 | Kristina Waterhouse | 04/05/23 8:26 AM
Row 374 | Customer requested withdrawal 1/4/2023, downsized and resubmitted. | Nathan Lawrence | 10/15/24 6:02 PM
Row 375 | 2/1/2023 customer confirmed they wanted to withdraw | Kaiya Hoogkamp | 06/12/24 10:47 AM
Row 378 | Wthdrawal requested by customer 2/27/2023. | Nathan Lawrence | 10/15/24 5:56 PM
Row 378 | Submitted INC2876458 to open CM for refund | Kristina Waterhouse | 06/02/23 10:15 AM
Row 378 | Sent email requesting they confirm refund information | Kristina Waterhouse | 05/23/23 11:31 AM
Row 378 | Created debtor in SAP | Kristina Waterhouse | 05/04/23 10:02 AM
Row 378 | Followed up on W9 request | Kristina Waterhouse | 04/25/23 1:55 PM
Row 378 | W9 requested 4/3 | Kristina Waterhouse | 04/03/23 1:48 PM
Row 379 | Also terminated contract 120004858 | Kristina Waterhouse | 06/13/23 8:44 AM
Row 379 | Submitted INC2895073 to cancell PIA | Kristina Waterhouse | 06/13/23 8:44 AM
Row 379 | Waived per Nate 4/12/2023 | Kristina Waterhouse | 04/13/23 6:25 AM
Row 380 | no documentation confirming withdrawal | Kaiya Hoogkamp | 10/22/24 11:45 AM
Row 381 | Customer confirmed withdrawal 2/15/2023 after failed TS, resubmitted as L4. | Nathan Lawrence | 10/15/24 5:52 PM
Row 383 | no documentation confirming withdrawal | Kaiya Hoogkamp | 10/22/24 11:44 AM
Row 384 | Project sold to Perennial September 2024. New IA sent 10/2/24. Awaiting letter of intent and updated assignement sheet - NAL 10/2/24. | Nathan Lawrence | 10/02/24 10:37 AM
Row 384 | sent IT ticket | Jessie Ladaga | 05/11/23 9:59 AM
Row 387 | paid 07-06-2023 | Helen Markham | 01/11/24 10:40 AM
Row 387 | reopend aplication due to the POI incorrect during screenings awaiting on DE for updated results | William Dawe | 05/08/23 10:41 AM
Row 387 | Might be waiving second set of ESA Charges?????? | Kristina Waterhouse | 05/08/23 10:27 AM
Row 387 | Requested USM1 debtor in SAP | Kristina Waterhouse | 05/08/23 10:19 AM
Row 387 | They replied that Goodwin Motors was not a valid DBA for "FRG, Inc"... responded that we need customer name to match on W9 | Kristina Waterhouse | 04/25/23 12:15 PM
Row 387 | Followed up on W9 request | Kristina Waterhouse | 04/12/23 7:20 AM
Row 387 | Requested W9 | Kristina Waterhouse | 04/07/23 1:13 PM
Row 389 | Customer withdraw request 6/13/2023. | Nathan Lawrence | 10/15/24 5:42 PM
Row 389 | contract completed | Staci Pellegrini | 02/27/24 8:12 AM
Row 389 | INC3066209 entered ticket to cancel PIA | Kaiya Hoogkamp | 09/05/23 11:14 AM
Row 389 | released contract 9/5/2023 & Informed Christy prj is withdrawn, she will cancel | Kaiya Hoogkamp | 09/05/23 10:59 AM
Row 389 | Found that this should not have been invoiced per Will dated 6/13/23 This project 82404 withdrew before ESA. Contract and PIA will need to be canceled. | Staci Pellegrini | 06/14/23 11:54 AM
Row 389 | invoice sent to customer | Jessie Ladaga | 05/15/23 9:31 AM
Row 389 | waiting on invoice; then need to sent to developer | Jessie Ladaga | 05/11/23 12:49 PM
Row 389 | esa agreement sent on 5/8/2023 waiting on dev and signature | William Dawe | 05/08/23 2:32 PM
Row 389 | need to send invoice. no signed ESA as of 4/24/2023 | Jessie Ladaga | 04/24/23 2:46 PM
Row 390 | INC2889448 to clear payment | Kristina Waterhouse | 06/09/23 9:06 AM
Row 390 | INC2770901 to clear PIA | Kristina Waterhouse | 04/12/23 12:47 PM
Row 390 | Requested debtor in SAP | Kristina Waterhouse | 04/11/23 1:56 PM
Row 390 | Requested W9 | Kristina Waterhouse | 04/07/23 1:35 PM
Row 391 | Customer confirmed PRJ withdrawn 2/23/23. Replaced w/ 82924. | Nathan Lawrence | 10/15/24 4:00 PM
Row 392 | 1233.40 | Staci Pellegrini | 08/16/23 11:32 AM
Row 392 | Extended debtor to 90/90 | Kristina Waterhouse | 04/06/23 10:21 AM
Row 392 | Requested W9 | Kristina Waterhouse | 04/05/23 8:36 AM
Row 393 | Submitted INC2807753 to open CM 910178007 for refund | Kristina Waterhouse | 05/01/23 9:40 AM
Row 394 | Project withdrawn 5/11/23, failed ESA. | Nathan Lawrence | 10/15/24 3:57 PM
Row 394 | Submitted INC2770359 to move/clear PIA | Kristina Waterhouse | 04/12/23 10:17 AM
Row 394 | Katherine used this PIA for project 82255 | Kristina Waterhouse | 04/12/23 8:42 AM
Row 394 | Found PIA confirmation but don't see payment? | Kristina Waterhouse | 04/11/23 2:34 PM
Row 394 | Created debtor | Kristina Waterhouse | 04/07/23 2:05 PM
Row 394 | Requested W9 4/3 | Kristina Waterhouse | 04/03/23 12:11 PM
Row 395 | 4/10/2024 project withdrawn per customer request. They cannot receive permits required to build. | Kaiya Hoogkamp | 04/10/24 3:15 PM
Row 395 | remaining credit will need to be refunded | Staci Pellegrini | 10/06/23 8:45 AM
Row 395 | invoice created 3/9/2023 sjp | Staci Pellegrini | 03/09/23 11:31 AM
Row 396 | The invoice was paid using a bulk refund from other Level2 Novel projects that were owed a refund. (see attachment) | Thomas Blanchard | 06/17/25 10:06 AM
Row 396 | 1/26/2023 failed esa and withdrew | Kaiya Hoogkamp | 10/22/24 11:42 AM
Row 396 | can't find deposit | Kristina Waterhouse | 04/13/23 10:07 AM
Row 396 | extended debtor in SAP | Kristina Waterhouse | 04/11/23 2:41 PM
Row 398 | Submitted INC2836191 to clear old milestone. Changed contract amount and released. | Kristina Waterhouse | 05/15/23 11:51 AM
Row 398 | Sumbitted CM 910179847 to clear incorrect invoice. Then need to redo milestone. New PIA #1 910179850/920197922 INC2832601 to move money from old PIA New PIA #2 910179851/ INC2832623 to move money | Kristina Waterhouse | 05/12/23 9:27 AM
Row 398 | Katherine used the wrong PIA payment and dollar amount.... This project only had a PIA of $500. Submitted INC270359 to cancel PIA 910173793/920191452 | Kristina Waterhouse | 04/12/23 9:56 AM
Row 400 | 10/21/2024 project requested withdrawal | Kaiya Hoogkamp | 10/22/24 11:41 AM
Row 401 | INC2873394 to clear payment | Kristina Waterhouse | 06/01/23 8:55 AM
Row 401 | INC2773312 to clear PIA | Kristina Waterhouse | 04/13/23 10:35 AM
Row 401 | Extended debtor in SAP | Kristina Waterhouse | 04/12/23 11:22 AM
Row 402 | Customer withdraw request 2/9/23 after failed TS. | Nathan Lawrence | 10/15/24 3:49 PM
Row 403 | 5/22/2023 customer confirmed withdrawing project | Kaiya Hoogkamp | 06/20/24 8:32 AM
Row 405 | Submitted INC2807736 to open credit memo for refund | Kristina Waterhouse | 05/01/23 9:32 AM
Row 405 | INC2773476 to clear PIA | Kristina Waterhouse | 04/13/23 11:31 AM
Row 405 | Emailed Christy.... debtors don't match W9 | Kristina Waterhouse | 04/12/23 11:39 AM
Row 406 | no documentation confirming withdrawal | Kaiya Hoogkamp | 10/22/24 11:40 AM
Row 407 | 2/22/2023 project failed ESA and withdrew. | Kaiya Hoogkamp | 10/16/24 8:42 AM
Row 407 | Can't find fully executed ESA | Kristina Waterhouse | 04/13/23 11:54 AM
Row 407 | Extended debtor in SAP | Kristina Waterhouse | 04/12/23 11:52 AM
Row 408 | IA for Tenant Change sent 10/3/24. Changed from "Moose River Lumber Co" to "Boundary Co". | Nathan Lawrence | 10/03/24 12:53 PM
Row 409 | Per Staci we have reassignment, new W9 and new IA so we are billing under Propspect Solar One LLC.... Extended USM1 in SAP | Kristina Waterhouse | 04/13/23 12:09 PM
Row 409 | The ESA is under VCP but customer is now Prospect Solar One LLC.... | Kristina Waterhouse | 04/12/23 12:09 PM
Row 410 | 2/9/2023 application withdrew | Kaiya Hoogkamp | 10/16/24 2:09 PM
Row 411 | 11/8/2022 project failed ESA and withdrew. | Kaiya Hoogkamp | 10/16/24 2:12 PM
Row 411 | Sent follow up email on refund info | Kristina Waterhouse | 06/02/23 10:58 AM
Row 411 | Sent follow up email for refund info. | Kristina Waterhouse | 05/22/23 7:40 AM
Row 411 | INC2836420 to open funds for refund and emailed customer for refund info | Kristina Waterhouse | 05/15/23 1:26 PM
Row 411 | Refund on straight invoice | Kristina Waterhouse | 04/13/23 1:41 PM
Row 412 | 11/16/2022 project requested to withdraw. | Kaiya Hoogkamp | 10/16/24 2:13 PM
Row 412 | Emailed again for status on where the payment was moved | Kristina Waterhouse | 05/22/23 1:28 PM
Row 412 | This projects deposit was cleared to PRJ 81513. PRJ 81513's deposit went to consumption. Emailed Sales admin. | Kristina Waterhouse | 04/14/23 11:53 AM
Row 412 | Created debtor in SAP | Kristina Waterhouse | 04/13/23 2:22 PM
Row 412 | Requested W9 4/3 | Kristina Waterhouse | 04/03/23 1:47 PM
Row 413 | 4/14/2023 project withdrawn | Kaiya Hoogkamp | 10/16/24 2:23 PM
Row 413 | Submitted INC2871126 to clear PIA | Kristina Waterhouse | 05/31/23 12:24 PM
Row 413 | PRJ 81958's deposit is missing. PRJ 81959's deposit was cleared to 81958. Sent email to sales admin to track down payment. There is an uncleared 500 on debtor 931931 but it's just a bank recon and I can't find anything else tied to the doc #. | Kristina Waterhouse | 05/18/23 2:03 PM
| Treasurey was able to find the payment and release it to sundry. | Kristina Waterhouse | 05/25/23 2:03 PM
Row 413 | Requested debtor in SAP | Kristina Waterhouse | 05/04/23 10:59 AM
Row 413 | Requested W9 | Kristina Waterhouse | 04/14/23 1:04 PM
Row 414 | 12/7/2022 project failed ESA and withdrew. | Kaiya Hoogkamp | 10/16/24 2:22 PM
Row 415 | 10/13/2022 project withdrawn. | Kaiya Hoogkamp | 10/16/24 2:21 PM
Row 417 | 2/21/2023 application withdrawn. | Kaiya Hoogkamp | 10/16/24 2:20 PM
Row 418 | Invoice for NOTI 10300952863 paid 11/11/2024 | Nathan Lawrence | 12/10/24 12:26 PM
Row 418 | Updated ESA name to Rewild per ESA agreement | Kristina Waterhouse | 03/20/23 12:48 PM
Row 420 | 1/26/2023 failed ESA and project withdrew. | Kaiya Hoogkamp | 10/16/24 2:17 PM
Row 420 | INC2803382 to cancel Katherines old PIA 910174793, it was never paid | Kristina Waterhouse | 04/27/23 1:24 PM
Row 421 | ESA total Amount $3206.84, we waived the study fee due to original tech screen pass and then failure | Kaiya Hoogkamp | 06/25/25 2:46 PM
Row 421 | 9/6/2022 project failed ESA and withdrew. | Kaiya Hoogkamp | 10/16/24 2:15 PM
Row 423 | ESA Amount: $500, was paid 1/18/2023 | Kaiya Hoogkamp | 06/25/25 11:31 AM
Row 423 | ESA total Billed: $1850.1, ESA was waived due to original tech screen was a pass, when it should have failed. | Kaiya Hoogkamp | 06/25/25 11:29 AM
Row 423 | 11/21/2022 project failed ESA and withdrew. | Kaiya Hoogkamp | 10/16/24 2:29 PM
Row 423 | the PIA was refunded customer not charged because of mis communication and email accidentially sent stating it was Pass when it was not ... | Staci Pellegrini | 01/11/24 12:30 PM
Row 423 | PIA was refunded! | Kristina Waterhouse | 05/04/23 11:21 AM
Row 423 | Found my deposit but it's cleared to a DC?? | Kristina Waterhouse | 04/14/23 1:39 PM
Row 424 | 6/17/2025 Remaining balance is $555.23 | Kaiya Hoogkamp | 06/17/25 11:24 AM
Row 424 | Correct Debtor is 933090 | Kaiya Hoogkamp | 04/16/25 9:06 AM
Row 424 | ESA Contract 120007418 INVOICE: 910262401 | Kaiya Hoogkamp | 04/09/25 9:03 AM
Row 424 | Coordination Study Contract 12007402 INVOICE: 910262399 | Kaiya Hoogkamp | 04/09/25 8:55 AM
Row 424 | NEW $500 contract: 120007418 PIA 910258361/920281370 | Kaiya Hoogkamp | 03/18/25 10:20 AM
Row 424 | Credit memo created 3/11/25: 910256926/920280771 & released | Kaiya Hoogkamp | 03/11/25 1:46 PM
Row 424 | Second contract for coordination study ($3200): 120007402. PIA: 910256233/920279200 | Kaiya Hoogkamp | 03/05/25 3:56 PM
Row 424 | 4/11/2023 project withdrew. | Kaiya Hoogkamp | 10/16/24 2:25 PM
Row 424 | Helen followed up on outstanding bal 2/14/24 | Staci Pellegrini | 02/28/24 4:24 PM
Row 424 | invoice 910197050 created for $500.00 ESA this correct debtor. | Staci Pellegrini | 10/06/23 9:35 AM
Row 424 | Need to lower the contract amount... this is the one that's cleared to a straight invoice | Kristina Waterhouse | 05/25/23 2:16 PM
| because of this kristina's invoice will need to be cancel and rebilled correctly with a PIA | Staci Pellegrini | 09/20/23 10:39 AM
Row 424 | PRJ 81958's deposit is missing. PRJ 819589's deposit was cleared to 81958. Sent email to sales admin to track down payment. There is an uncleared 500 on debtor 931931 but it's just a bank recon and I can't find anything else tied to the doc #. | Kristina Waterhouse | 05/18/23 2:03 PM
| this 500.00 is actual on debtor 931931, had to cancel invoice on 931931 and have $500.00 pmt mvd 933090 | Staci Pellegrini | 09/20/23 10:39 AM
Row 424 | i canceled the straight invoice last week ( smartsheets down) uner 931931 910160414/920176842 (adj 0.00) and asked for money to be moved over 933090. | Staci Pellegrini | 09/20/23 10:37 AM
Row 424 | email sent to Kaiya and straight invoice will need to be canceled. and contract reset from no guarantee to a guarantee. | Staci Pellegrini | 08/22/23 4:38 PM
Row 424 | PIA payment is pa 8400040065 11/15/2022 500.00 sitting on 931931 and needs to be moved to 933090. | Staci Pellegrini | 08/22/23 4:37 PM
Row 424 | INC2871110 to cancel PIA... paid with straight invoice | Kristina Waterhouse | 05/31/23 12:25 PM
Row 424 | Requested debtor in SAP | Kristina Waterhouse | 05/04/23 11:00 AM
Row 425 | 10/19/2022 project failed ESA and withdrew. | Kaiya Hoogkamp | 10/16/24 2:31 PM
Row 425 | Sent follow up email on refund info. | Kristina Waterhouse | 05/22/23 7:36 AM
Row 425 | Sent email to confirm refund info | Kristina Waterhouse | 05/15/23 12:58 PM
Row 425 | Submitted INC2836298 to clear invoice and open 766.60 for refund | Kristina Waterhouse | 05/15/23 12:52 PM
Row 425 | Exteded debtor in SAP | Kristina Waterhouse | 05/04/23 11:45 AM
Row 426 | NEW invoice on debtor 924030. Invoice: 910267874/920291265 | Kaiya Hoogkamp | 05/15/25 9:28 AM
Row 426 | Invoice adjustment to $0, 910267871 | Kaiya Hoogkamp | 05/15/25 9:06 AM
Row 426 | The correct debtor is 924030 | Kaiya Hoogkamp | 05/15/25 8:23 AM
Row 426 | UPDATED Invoice for $1000: 910262692/920285786 | Kaiya Hoogkamp | 04/10/25 1:34 PM
Row 426 | 4/10/25 app invoice adjustment to $0.00 910262686 | Kaiya Hoogkamp | 04/10/25 1:27 PM
Row 427 | 10/10/2022 project failed ESA and withdrew. | Kaiya Hoogkamp | 10/16/24 2:32 PM
Row 428 | sent email Sachin 4/11 for W-9 | Staci Pellegrini | 04/11/23 9:57 AM
Row 429 | Original ESA Amount that was waived was $1850.10 | Kaiya Hoogkamp | 06/04/25 9:50 AM
Row 429 | ESA fee waived per Nate P 9/7/2022 due to tech screen actually being a failure, not a pass, and the ESA was required to be done. | Kaiya Hoogkamp | 06/04/25 9:48 AM
Row 430 | 9/28/2022 project failed ESA and withdrew | Kaiya Hoogkamp | 10/16/24 2:49 PM
Row 431 | 3/3/2023 application withdrawn. | Kaiya Hoogkamp | 10/16/24 2:59 PM
Row 432 | 10/10/2022 project failed ESA and withdrew | Kaiya Hoogkamp | 10/16/24 2:57 PM
Row 433 | 10/19/2023 failed ESA, application withdrew. | Kaiya Hoogkamp | 10/17/24 10:55 AM
Row 433 | Canceled Katherine's PIA - INC2802646 | Kristina Waterhouse | 04/27/23 9:33 AM
Row 433 | Cancelled Katherine's contract, cannot find PIA and this needs to be released. | Kristina Waterhouse | 04/25/23 9:38 AM
Row 434 | 10/19/2022 project failed ESA and withdrew. | Kaiya Hoogkamp | 10/17/24 10:51 AM
Row 435 | 2/9/2023 application withdrew. | Kaiya Hoogkamp | 10/17/24 10:50 AM
Row 436 | 2/9/2023 application withdrew. | Kaiya Hoogkamp | 10/17/24 10:36 AM
Row 437 | 7/15/2025 sent follow up for ESA invoice payment | Kaiya Hoogkamp | 07/15/25 8:43 AM
Row 437 | 9/23/2022 project failed ESA and withdrew. | Kaiya Hoogkamp | 10/17/24 10:29 AM
Row 437 | sent reminder email for payment 1/10/2024 | Helen Markham | 01/10/24 2:52 PM
Row 437 | No deposit required | Kristina Waterhouse | 05/04/23 11:29 AM
Row 439 | 9/26/2022 application withdrawn. | Kaiya Hoogkamp | 10/16/24 3:02 PM
Row 440 | 8/3/2022 application withdrew. | Kaiya Hoogkamp | 10/17/24 11:07 AM
Row 441 | 10/19/2022 failed ESA and withdrew. | Kaiya Hoogkamp | 10/17/24 10:59 AM
Row 441 | The Payment 500.00 Kristina used originated 922312 clearing doc 2200003472 | Staci Pellegrini | 01/10/24 1:29 PM
Row 441 | per Portal & SAP $500.00 was invoiced under 910160407 10/21/2022 and cleared. for 81848 | Staci Pellegrini | 10/17/23 8:01 AM
| debtor 922331 | Staci Pellegrini | 10/17/23 11:54 AM
Row 441 | INC2855649 to move payment and clear PIA | Kristina Waterhouse | 05/24/23 9:03 AM
Row 441 | Submitted INC2855572 to clear adjusted invoice | Kristina Waterhouse | 05/24/23 8:45 AM
Row 441 | Released CM.... will do milestone after so it doesn't get stuck in my WF | Kristina Waterhouse | 05/23/23 11:15 AM
Row 441 | CM 910180038 to clear incorrect invoice | Kristina Waterhouse | 05/15/23 11:59 AM
Row 441 | I found a deposit when I was about to send this out to the customer..... need to adjust invoice and redo with PIA. | Kristina Waterhouse | 05/15/23 10:18 AM
Row 442 | 1/17/2023 failed ESA, application withdrawn. | Kaiya Hoogkamp | 10/17/24 11:19 AM
Row 442 | INC2856078 to clear random HA/HT pair | Kristina Waterhouse | 05/24/23 10:42 AM
Row 442 | 910181237 to clear Katherine's incorrect invoice | Kristina Waterhouse | 05/24/23 10:18 AM
Row 442 | Submitted ticket # INC2807808 to clear PIA | Kristina Waterhouse | 05/01/23 10:36 AM
Row 442 | Submitted ticket INC2807806 to cancel hx invoice 910165985 which never had a payment cleared to it. | Kristina Waterhouse | 05/01/23 10:31 AM
Row 443 | Ticket to cancel old PIA was closed but never done.... submitted INC2932865 | Kristina Waterhouse | 06/30/23 10:11 AM
Row 443 | Emailed front end.... I don't think a deposit was paid on this one. | Kristina Waterhouse | 05/09/23 12:16 PM
Row 443 | Submitted ticket INC2807815 to cancel PIA INC2807815, it was never paid so we'll bill total charges on milestone | Kristina Waterhouse | 05/01/23 10:40 AM
Row 444 | 9/28/2022 failed ESA and withdrew | Kaiya Hoogkamp | 10/17/24 11:28 AM
Row 444 | Extended debtor in SAP | Kristina Waterhouse | 04/27/23 12:05 PM
Row 444 | Cancelled Katherine's old contract | Kristina Waterhouse | 04/25/23 9:41 AM
Row 445 | 8/8/2022 failed tech screen, no formal email requesting withdraw. | Kaiya Hoogkamp | 10/17/24 11:45 AM
Row 447 | 9/12/2022 project withdrew | Kaiya Hoogkamp | 10/17/24 11:55 AM
Row 447 | Confirmed project never went to ESA | Kristina Waterhouse | 04/27/23 8:49 AM
Row 447 | Doesn't look like the ESA on this one was ever actually executed, project was withdrawn the same day the agreement was issued to the customer. | Kristina Waterhouse | 04/27/23 8:11 AM
Row 447 | Application was withdrawn 9/12/22.... we need to verify the study was not aleady started. | Kristina Waterhouse | 04/05/23 7:27 AM
Row 448 | 9/28/2022 failed ESA and withdrew. | Kaiya Hoogkamp | 10/17/24 11:49 AM
Row 448 | Submitted INC2802599 to cancel Katherine's old PIA | Kristina Waterhouse | 04/27/23 9:25 AM
Row 449 | 9/1/2022 application withdrawn. | Kaiya Hoogkamp | 10/17/24 12:22 PM
Row 450 | 500.00 Pia created ... need to bill remaining | Staci Pellegrini | 06/20/23 4:26 PM
Row 450 | 120004855 - cancelled contract | Kristina Waterhouse | 05/26/23 12:06 PM
Row 450 | Brian is going to cancel the PIA that katherine created on Revision ... as this needs to go on Oceanview instead. | Staci Pellegrini | 05/24/23 3:56 PM
Row 453 | 7/25/2022 application withdrawn. | Kaiya Hoogkamp | 10/17/24 12:51 PM
Row 454 | 8/3/2022 application withdrawn | Kaiya Hoogkamp | 10/17/24 12:50 PM
Row 455 | no documentation verifying withdrawal. | Kaiya Hoogkamp | 10/17/24 12:39 PM
Row 456 | 2/10/2023 application withdrew | Kaiya Hoogkamp | 10/17/24 12:24 PM
Row 457 | 2/10/2023 application withdrawn. | Kaiya Hoogkamp | 10/17/24 12:23 PM
Row 458 | 12/6/2022 application withdrawn. | Kaiya Hoogkamp | 10/17/24 12:54 PM
Row 459 | 8/10/2022 application withdrawn. | Kaiya Hoogkamp | 10/17/24 12:57 PM
Row 459 | Created USS1 under NES | Kristina Waterhouse | 05/31/23 1:51 PM
Row 459 | Requested W9 | Kristina Waterhouse | 05/30/23 12:07 PM
Row 460 | Requested W9 | Kristina Waterhouse | 05/30/23 12:11 PM
Row 460 | This project used deposit meant for project 81972. Deposit meant for this project was sent to consumption.... emailed sales admin. | Kristina Waterhouse | 04/14/23 11:53 AM
Row 461 | 3/3/2023 application withdrawn | Kaiya Hoogkamp | 10/17/24 12:56 PM
Row 462 | 6/21/2022 application withdrawn | Kaiya Hoogkamp | 10/17/24 12:55 PM
Row 463 | 10/19/2022 application withdrawn | Kaiya Hoogkamp | 10/17/24 1:08 PM
Row 463 | Created USS1 under NES | Kristina Waterhouse | 05/31/23 1:51 PM
Row 463 | Requested W9 | Kristina Waterhouse | 05/30/23 12:04 PM
Row 464 | 6/17/2022 application withdrawn. | Kaiya Hoogkamp | 10/17/24 12:59 PM
Row 465 | 6/17/2022 application withdrawn | Kaiya Hoogkamp | 10/17/24 12:58 PM
Row 468 | 6/30/2022 application withdrawn | Kaiya Hoogkamp | 10/17/24 1:10 PM
Row 469 | 6/15/2022 application withdrawn | Kaiya Hoogkamp | 10/17/24 1:09 PM
Row 470 | 6/8/2022 application withdrawn | Kaiya Hoogkamp | 10/17/24 1:27 PM
Row 471 | 6/27/2022 application withdrawn | Kaiya Hoogkamp | 10/17/24 1:28 PM
Row 472 | Extended debtor in SAP | Kristina Waterhouse | 06/02/23 12:29 PM
Row 472 | Receiced W9 naming Outlook Farm LLC as a DBA for Great Works Properties. There is a blocked debtor in SAP that matches by TIN. Submitted INC2876682 to have it unblocked. | Kristina Waterhouse | 06/02/23 12:09 PM
Row 472 | Emailed for updated assigment information and W9.... name in portal and on CMP account has been updated to Great Works Property Inc | Kristina Waterhouse | 05/31/23 11:19 AM
Row 473 | 6/8/2022 application withdrawn | Kaiya Hoogkamp | 10/17/24 1:30 PM
Row 474 | Old Account# 30013836017 | Nathan Lawrence | 07/25/24 3:42 PM
Row 475 | Ticket INC2812351 to clear payment | Kristina Waterhouse | 05/03/23 7:07 AM
Row 476 | no documentation confirming the withdrawal date | Kaiya Hoogkamp | 10/17/24 1:57 PM
Row 477 | no documentation confirming the project is withdrawn | Kaiya Hoogkamp | 10/17/24 2:33 PM
Row 478 | 6/30/2022 application withdrawn | Kaiya Hoogkamp | 10/17/24 2:16 PM
Row 479 | 4/9/2022 failed ESA and withdrew | Kaiya Hoogkamp | 10/17/24 2:39 PM
Row 479 | Adj invoicefrom 2994.64 to 2007.92 910207125 | Staci Pellegrini | 01/12/24 10:38 AM
Row 479 | Kristina has over billed 81262 she billed part of Auburn Penley Corner to this one invoice needs to be adj | Staci Pellegrini | 01/12/24 9:50 AM
Row 479 | They replied that they will update the name on the account to Novel... still has not been done. Sent follow up email. | Kristina Waterhouse | 05/30/23 12:00 PM
Row 479 | Requested W9 | Kristina Waterhouse | 05/24/23 1:09 PM
Row 480 | 8/30/2022 4:17:31 PM Jessie Roderick (U341040) ESA not needed. TS passed. DE revised. | Kristina Waterhouse | 03/21/23 12:32 PM
Row 481 | Charges in 12/22 but study was completed 8/22 | Kristina Waterhouse | 05/24/23 1:45 PM
Row 482 | 7/19/2022 application withdrawn | Kaiya Hoogkamp | 10/17/24 2:47 PM
Row 483 | no documentation for withdrawal | Kaiya Hoogkamp | 10/17/24 2:45 PM
Row 484 | no documentation regarding withdrawal | Kaiya Hoogkamp | 10/17/24 2:58 PM
Row 484 | cleared by doubtful debt | Kaiya Hoogkamp | 04/17/23 8:57 AM
Row 485 | no documentation about withdrawal | Kaiya Hoogkamp | 10/17/24 2:55 PM
Row 487 | 2/9/2023 application withdrawn | Kaiya Hoogkamp | 10/17/24 3:03 PM
Row 488 | 8/9/2022 application withdrawn | Kaiya Hoogkamp | 10/17/24 3:16 PM
Row 489 | Per W9 refund needs to be issued on USM1 debtor 929912. Submitted INC2879510 to move payment to correct debtor. | Kristina Waterhouse | 06/05/23 7:51 AM
Row 489 | Sent follow up email | Kristina Waterhouse | 06/02/23 10:35 AM
Row 489 | Sent follow up email for refund info. | Kristina Waterhouse | 05/22/23 7:33 AM
Row 489 | Sent email requesting W9 and to confirm refund info | Kristina Waterhouse | 05/15/23 12:49 PM
Row 489 | Submitted INC2836270 to clear adjusted invoice and open funds for refund. | Kristina Waterhouse | 05/15/23 12:43 PM
Row 490 | 8/9/2022 application withdrawn. | Kaiya Hoogkamp | 10/17/24 3:12 PM
Row 491 | INC2812351 to clear payment | Kristina Waterhouse | 05/03/23 7:07 AM
Row 493 | no documentation confirming withdrawal | Kaiya Hoogkamp | 10/17/24 3:10 PM
Row 494 | 8/17/2022 customer withdrew project | Kaiya Hoogkamp | 05/22/24 9:53 AM
Row 495 | The invoice was paid using a bulk refund from other Level2 Novel projects that were owed a refund (see attachment) | Thomas Blanchard | 06/17/25 10:01 AM
Row 495 | 8/8/2022 application withdrew | Kaiya Hoogkamp | 10/17/24 3:19 PM
Row 495 | sent reminder email for payment 1/10/2024 | Helen Markham | 01/10/24 2:52 PM
Row 496 | no documentation on withdrawal | Kaiya Hoogkamp | 10/17/24 3:23 PM
Row 497 | 8/2/2022 application withdrawn | Kaiya Hoogkamp | 10/17/24 3:30 PM
Row 498 | 2000.00 910154560 | Staci Pellegrini | 01/08/24 4:58 PM
Row 498 | revision 1289121 | Staci Pellegrini | 01/08/24 4:55 PM
Row 498 | $2000.00 esa deposit paid by revision 1489121.. remaining balance Kristina billed under 933140 | Staci Pellegrini | 01/08/24 4:54 PM
Row 498 | Requested debtor in SAP | Kristina Waterhouse | 05/12/23 1:26 PM
Row 499 | no documentation verifying withdrawal. | Kaiya Hoogkamp | 10/17/24 3:29 PM
Row 499 | Converted NOTI to USM1 and exteneded to 90/90 | Kristina Waterhouse | 05/30/23 1:14 PM
Row 499 | Followed up on W9 request | Kristina Waterhouse | 05/24/23 12:52 PM
Row 499 | Requested W9 | Kristina Waterhouse | 05/12/23 1:37 PM
Row 500 | 9/27/2022 application withdrawn | Kaiya Hoogkamp | 10/17/24 3:32 PM
Row 501 | 9/28/2022 application moved to level 4 and withdrawn as level 2. | Kaiya Hoogkamp | 10/17/24 3:42 PM
Row 502 | 10/10/2022 application withdrawn | Kaiya Hoogkamp | 10/17/24 3:41 PM
Row 502 | Submitted INC2833148 to clear adjusted invoice and open for refund | Kristina Waterhouse | 05/12/23 1:17 PM
Row 504 | 4/26/2022 application withdrew | Kaiya Hoogkamp | 10/17/24 3:39 PM
Row 505 | 5/26/2022 application moved to level 4 and withdrawn as level 2. | Kaiya Hoogkamp | 10/17/24 3:44 PM
Row 506 | no documentation verifying withdrawal. | Kaiya Hoogkamp | 10/17/24 3:45 PM
Row 507 | no documentation confirming withdrawal | Kaiya Hoogkamp | 10/17/24 3:52 PM
Row 507 | paid 06/26/2023 | Helen Markham | 01/11/24 10:27 AM
Row 507 | sent itnow ticket to clear dd with credit memo | Staci Pellegrini | 01/08/24 4:43 PM
Row 507 | Original invoice is with doubtful debt, need to identify the process | Kristina Waterhouse | 07/03/23 9:36 AM
Row 507 | Requested extension to 90/90 in SAP | Kristina Waterhouse | 06/05/23 12:31 PM
Row 507 | Customer replied that they are in the process of this project changing from Penobscot Narrow Solar to Penobscot Narrow Solar I. Asked estimated time frame | Kristina Waterhouse | 05/23/23 1:37 PM
Row 507 | Requested W9 | Kristina Waterhouse | 05/12/23 12:23 PM
Row 508 | 5/26/2022 project failed ESA and withdrew | Kaiya Hoogkamp | 10/17/24 3:56 PM
Row 509 | 12/6/2022 application withdrawn | Kaiya Hoogkamp | 10/18/24 11:18 AM
Row 510 | 6/8/2022 application withdrawn | Kaiya Hoogkamp | 10/18/24 11:15 AM
Row 510 | sent reminder email for payment 1/10/2024 | Helen Markham | 01/10/24 2:53 PM
Row 510 | Sent email for charge clarification. Katherine had labeled some June charges for this project but the study had already been completed in May. Novel had multiple projects during this time period. | Kristina Waterhouse | 05/30/23 11:53 AM
Row 511 | 6/20/2022 application withdrawn | Kaiya Hoogkamp | 10/18/24 11:23 AM
Row 512 | 5/26/2022 application withdrawn | Kaiya Hoogkamp | 10/18/24 11:22 AM
Row 513 | 6/30/2022 application withdrawn. | Kaiya Hoogkamp | 10/18/24 11:21 AM
Row 515 | 4/5/2022 application withdrawn | Kaiya Hoogkamp | 10/18/24 11:20 AM
Row 516 | 9/14/2022 application withdrawn | Kaiya Hoogkamp | 10/18/24 11:25 AM
Row 517 | Project in default, not paid | Thomas Blanchard | 06/17/25 12:44 PM
Row 517 | 4/25/2022 app failed ESA and withdrawn | Kaiya Hoogkamp | 10/18/24 11:28 AM
Row 517 | sent email to dante to ask why charges are 6475.35 when est being 500.00 | Staci Pellegrini | 01/08/24 3:05 PM
Row 517 | We charged 500.00 flat fee 7/7/2022 910150282/920166049 | Staci Pellegrini | 01/08/24 1:12 PM
Row 517 | W-9 Received | Kaiya Hoogkamp | 10/10/23 7:41 AM
Row 517 | Emailed requesting W-9 in order to create final invoice | Kaiya Hoogkamp | 10/02/23 1:41 PM
Row 517 | Followed up on W9 request | Kristina Waterhouse | 06/21/23 8:24 AM
Row 517 | Requested W9 | Kristina Waterhouse | 06/05/23 11:42 AM
Row 517 | Requested W9 | Kristina Waterhouse | 05/26/23 9:18 AM
Row 518 | Sent email confirming refund information | Kristina Waterhouse | 05/23/23 8:46 AM
Row 518 | 910152320 920169118 7/28/2022 CREATED / ADJ 3/17/2023 920191690 2000.00 | Staci Pellegrini | 04/18/23 3:50 PM
Row 518 | REFUND NEEDED | Staci Pellegrini | 04/18/23 3:26 PM
Row 521 | orig inovice 2000.00 910155488 920171646 4/28/2022 debtor 910795 has been adj 0.00 910232840 due to inv kristina created listed here | Staci Pellegrini | 08/07/24 11:23 AM
Row 521 | Paid 07/28/2023 | Helen Markham | 01/11/24 10:29 AM
Row 521 | The hx invoice is with doubtful debt. Submitted INC2936503 to determine the correct process for adjusting this invoice | Kristina Waterhouse | 07/03/23 9:21 AM
Row 521 | Extended debtor in SAP | Kristina Waterhouse | 06/05/23 9:12 AM
Row 521 | Followed up again on W9 request | Kristina Waterhouse | 05/31/23 11:26 AM
Row 521 | Followed up on W9 request | Kristina Waterhouse | 05/23/23 1:13 PM
Row 521 | Requested W9 | Kristina Waterhouse | 05/11/23 1:59 PM
Row 523 | 6/3/2022 application withdrawn | Kaiya Hoogkamp | 10/18/24 11:31 AM
Row 523 | Prior invoice 0.00 due to pia found 2000.00 from 10/11/2022 6000.00 group pmt, Tom created new PIA NEW CONTRACT 120006275/ | Staci Pellegrini | 03/15/24 9:53 AM
Row 523 | 910185191 to clear Katherines old invoice | Kristina Waterhouse | 06/30/23 12:15 PM
Row 524 | Additional $164.45 was billed and paid by bulk payment on 7/7/2025. | Thomas Blanchard | 07/07/25 3:00 PM
Row 524 | The invoice was paid using a bulk refund from other Level2 Novel projects that were owed a refund (see attachment) | Thomas Blanchard | 06/17/25 9:58 AM
Row 524 | 5/18/2022 application failed ESA and withdrew | Kaiya Hoogkamp | 10/18/24 11:31 AM
Row 524 | New contract 120006269, PIA 910213705 | Thomas Blanchard | 03/06/24 9:46 AM
Row 524 | 120005192 prior contract from Kristina did not have 500.00 pai this has been canceled and 0.00 TOm to create an new contract and pia and invoice 3/5/24 | Staci Pellegrini | 03/05/24 11:33 AM
Row 524 | prior invoice 2096..78 has been 0.00 Helen located 500.00 pia that belongs to this contract this needs to be reinvoiced under a new contract. Details in project backup file | Staci Pellegrini | 03/05/24 11:25 AM
Row 524 | sent reminder email for payment 1/10/2024 | Helen Markham | 01/10/24 2:53 PM
Row 524 | I had already tried to adjust this.... verified all old invoices are correctly cleared and only invoice that is outstanding is the one for 2096.78 | Kristina Waterhouse | 06/30/23 12:10 PM
Row 524 | ORIGINAL INVOICE WAS AMENDED SO CREDIT CREDIT INVOICE WAS CREATED 910184660 | Staci Pellegrini | 06/26/23 12:46 PM
Row 524 | 6/26/2023 0.00 invoice created 9/15/2022 910156432/920172671 930085 was replaced w 120005192 invoice920200848 910182481 | Staci Pellegrini | 06/26/23 11:59 AM
Row 524 | 910183703 to clear Katherines unpaid straight invoice | Kristina Waterhouse | 06/16/23 12:11 PM
Row 525 | 9/30/2024 project withdrawn. | Kaiya Hoogkamp | 09/30/24 11:51 AM
Row 525 | sent reminder email for payment 1/10/2024 | Helen Markham | 01/10/24 2:54 PM