## Level 2 Online Report
Project # | App Received | Customer Notified Application Complete | Facility Type | AC kW | Circuit | Substation | Substation Transformer | Tech Screen Completed | Tech Screen Results | ESA Results | ESA Completed | Withdrawn
106698 | 2025-05-22 | 2025-05-30 | Solar | 975
106654 | 2025-05-20 |  | Solar | 999
106484 | 2025-05-07 | 2025-05-21 | Solar | 975 |  |  |  |  | Pending
106392 | 2025-04-30 | 2025-05-09 | Solar | 300 | 800D1 | LINCOLNVILLE | 800T1 |  | Pending
106395 | 2025-04-30 | 2025-05-09 | Solar | 840 | 817D3 | FAIRFIELD | 817T1 | 2025-05-28 | Fail
106396 | 2025-04-30 | 2025-05-09 | Solar | 440 | 416D3 | GRAY | 416T1 |  | Pending
106397 | 2025-04-30 | 2025-05-09 | Solar | 320 | 431D3 | MECHANIC FALLS | 431T2 |  | Pending
106391 | 2025-04-29 | 2025-05-09 | Solar | 360 | 803D6 | BELFAST WEST SIDE | 34.5 kV Bus |  | Pending
106272 | 2025-04-22 | 2025-05-01 | Solar | 152 | 423D2 | KIMBALL ROAD | 423T2 | 2025-05-20 | Fail
106220 | 2025-04-18 | 2025-04-24 | Solar | 440 | 246D3 | THOMASTON CREEK | 246T1 | 2025-05-13 | Fail
106226 | 2025-04-18 | 2025-04-24 | Solar | 160 | 803D6 | BELFAST WEST SIDE | 34.5 kV Bus | 2025-05-13 | Fail
106231 | 2025-04-18 | 2025-04-24 | Solar | 320 | 678D2 | BAR MILLS | 678T4 | 2025-05-14 | Fail
106234 | 2025-04-18 | 2025-04-24 | Solar | 160 | 873D1 | COUNTY RD (RICE RIPS) | 873T1 | 2025-05-13 | Fail
106242 | 2025-04-18 | 2025-04-23 | Solar | 995 | 692D1 | HIRAM TAP | 692T1 | 2025-05-06 | Fail | Pending
106244 | 2025-04-18 | 2025-04-24 | Solar | 995 | 857D1 | THORNDIKE TAP | 857T1 | 2025-05-13 | Fail | Pending
106179 | 2025-04-16 | 2025-04-21 | Solar | 152 | 409D1 | PARIS TAP | 409T1 | 2025-05-05 | Fail
106128 | 2025-04-14 | 2025-04-17 | Solar | 875 | 428D3 | LIVERMORE FALLS | 428T1 | 2025-05-05 | Fail | Pending
106048 | 2025-04-08 | 2025-04-15 | Solar | 153.6 | 208D2 | BOND BROOK | 208T1 | 2025-04-21 | Fail | Pending
105982 | 2025-04-03 | 2025-05-02 | Solar | 999 | 610D2 | BONNY EAGLE | 610T4 | 2025-05-16 | Fail | Pending
105997 | 2025-04-03 | 2025-04-17 | Solar | 136.8 | 219D2 | DAMARISCOTTA MILLS | 219T1 | 2025-05-05 | Fail | Pending
105865 | 2025-03-26 | 2025-03-31 | Solar | 999 | 885D1 | WILTON | 885T1 | 2025-04-04 | Fail | Fail | 2025-05-13 | Yes
105830 | 2025-03-24 | 2025-03-27 | Solar | 999 | 449D2 | RILEY | 449T1 | 2025-03-28 | Fail | Pending
105827 | 2025-03-21 | 2025-03-28 | Solar | 150 | 435D4 | NORWAY | 435T2 | 2025-04-04 | Fail | Pass | 2025-05-13
105796 | 2025-03-19 | 2025-03-27 | Solar | 999 | 238D1 | MESSINA | 238T1 | 2025-03-28 | Fail |  |  | Yes
105773 | 2025-03-17 | 2025-03-19 | Solar | 999 | 860D1 | UNITY | 860T1 | 2025-03-25 | Fail |  |  | Yes
105711 | 2025-03-12 | 2025-03-19 | Solar | 999 | 853D1 | SKOWHEGAN NORTH SIDE | 853T1 | 2025-03-25 | Fail |  |  | Yes
105681 | 2025-03-11 | 2025-03-19 | Solar | 999 | 467D1 | TURNER TAP | Tap off of Transmission Line | 2025-03-25 | Fail | Pass | 2025-04-23
105660 | 2025-03-07 | 2025-03-17 | Solar | 995 | 806D1 | BUCKSPORT | 806T5 | 2025-03-18 | Fail | Pass | 2025-04-04
105641 | 2025-03-06 | 2025-03-17 | Solar | 995 | 837D2 | NEWPORT | 837T2 | 2025-03-18 | Fail | Pass | 2025-04-03
105649 | 2025-03-06 |  | Solar | 990 | [7 empty] | Yes
105547 | 2025-02-25 | 2025-03-11 | Solar | 999 | 815D2 | DOVER | 815T2 |  | Fail |  |  | Yes
105548 | 2025-02-25 | 2025-03-12 | Solar | 999 | 638D1 | NORTH LIMINGTON | 638T1 | 2025-03-12 | Fail
105549 | 2025-02-25 | 2025-03-12 | Solar | 999 | 602D2 | BASSETT | 602T1 | 2025-03-12 | Fail
105550 | 2025-02-25 | 2025-03-11 | Solar | 999 | 602D2 | BASSETT | 602T1 | 2025-03-11 | Fail |  |  | Yes
105551 | 2025-02-25 | 2025-03-11 | Solar | 999 | 818D1 | FARMINGTON FALLS | 818T1 | 2025-03-11 | Fail |  |  | Yes
105521 | 2025-02-21 | 2025-03-07 | Solar | 999 | 842D1 | PITTSFIELD | 842T1 | 2025-03-11 | Fail | Pass | 2025-04-24
105523 | 2025-02-21 | 2025-03-07 | Solar | 999 | 885D1 | WILTON | 885T1 | 2025-03-11 | Fail | Fail | 2025-05-28 | Yes
105500 | 2025-02-19 | 2025-02-24 | Solar | 975 | 431D1 | MECHANIC FALLS | 431T2 | 2025-02-28 | Fail | Pass | 2025-04-18
105454 | 2025-02-14 | 2025-02-18 | Solar | 969.4 | 813D1 | DEXTER | 813T1 | 2025-02-21 | Fail | Fail | 2025-03-20 | Yes
105424 | 2025-02-13 | 2025-02-17 | Solar | 200 | 810D1 | CLINTON | 810T1 | 2025-02-21 | Fail | Fail | 2025-03-13 | Yes
105405 | 2025-02-11 | 2025-02-12 | Solar | 995 | 431D1 | MECHANIC FALLS | 431T2 | 2025-02-14 | Fail | Pass | 2025-04-16
105215 | 2025-01-24 | 2025-01-28 | Solar | 152 | 423D2 | KIMBALL ROAD | 423T2 | 2025-01-31 | Fail | Fail | 2025-02-27 | Yes
105216 | 2025-01-24 | 2025-02-04 | Solar | 999 | 860D1 | UNITY | 860T1 | 2025-02-06 | Fail |  |  | Yes
105198 | 2025-01-23 | 2025-02-11 | Solar | 999 | 808D3 | CARMEL TAP | 808T1 | 2025-02-18 | Fail |  |  | Yes
105204 | 2025-01-23 | 2025-01-27 | Solar | 996 | 813D1 | DEXTER | 813T1 | 2025-01-31 | Fail | Fail | 2025-02-20 | Yes
105158 | 2025-01-16 | 2025-01-20 | Solar | 995 | 850D1 | SEARSPORT | 850T1 | 2025-01-24 | Fail | Pass | 2025-02-14
105134 | 2025-01-15 | 2025-01-23 | Solar | 200 | 675D2 | WESTERN AVENUE | 675T1 | 2025-01-24 | Pass
105120 | 2025-01-14 | 2025-01-20 | Solar | 141.84 | 253D1 | WARREN | 253T1 | 2025-01-24 | Fail | Fail | 2025-03-17 | Yes
105126 | 2025-01-14 | 2025-02-03 | Solar | 975 | 272D4 | NORTH AUGUSTA | 272T1 | 2025-02-06 | Fail | Pass | 2025-03-20
105055 | 2025-01-08 | 2025-01-27 | Solar | 975 | 873D1 | COUNTY RD (RICE RIPS) | 873T1 | 2025-02-03 | Fail |  |  | Yes
104989 | 2025-01-02 | 2025-01-03 | Solar | 152 | 409D1 | PARIS TAP | 409T1 | 2025-01-03 | Fail | Fail | 2025-01-24 | Yes
104942 | 2024-12-20 |  | Solar | 152 | [7 empty] | Yes
104944 | 2024-12-20 | 2024-12-23 | Solar | 152 | 423D2 | KIMBALL ROAD | 423T2 | 2024-12-30 | Fail | Pass | 2025-01-22
104916 | 2024-12-18 | 2024-12-31 | Solar | 220 | 239D7 | PARK STREET | 239T2 | 2025-01-03 | Fail | Pass | 2025-01-30
104902 | 2024-12-17 | 2024-12-31 | Solar | 200 | 246D3 | THOMASTON CREEK | 246T1 | 2025-01-03 | Fail | Pass | 2025-02-11
104903 | 2024-12-17 | 2024-12-24 | Solar | 240 | 239D6 | PARK STREET | 239T2 | 2025-01-03 | Fail | Pass | 2025-02-19
104904 | 2024-12-17 | 2024-12-31 | Solar | 100 | 239D5 | PARK STREET | 239T4 | 2025-01-03 | Fail | Pass | 2025-01-29
104822 | 2024-12-10 | 2024-12-12 | Solar | 995 | 467D1 | TURNER TAP | Tap off of Transmission Line | 2024-12-18 | Fail | Pass | 2025-01-14
104658 | 2024-11-22 | 2024-12-13 | Solar | 680 | 674D1 | WESTBROOK | 674T1 | 2024-12-16 | Fail | Fail | 2025-02-06
104659 | 2024-11-22 | 2024-12-13 | Solar | 400 | 674D1 | WESTBROOK | 674T1 | 2024-12-16 | Fail | Pass | 2025-05-29
104661 | 2024-11-22 | 2024-12-17 | Solar | 600 | 232D2 | LISBON FALLS | 232T2 | 2024-12-18 | Fail | Pass | 2025-01-06
104636 | 2024-11-21 | 2024-12-13 | Solar | 150 | 647D2 | PRIDES CORNER | 647T2 | 2024-12-16 | Pass
104638 | 2024-11-21 | 2024-12-13 | Solar | 240 | 674D2 | WESTBROOK | 674T1 | 2024-12-16 | Fail | Pass | 2025-02-06
104609 | 2024-11-20 | 2024-11-25 | Solar | 995 | 813D1 | DEXTER | 813T1 | 2024-11-26 | Fail |  |  | Yes
104613 | 2024-11-20 | 2024-11-25 | Solar | 999 | 431D1 | MECHANIC FALLS | 431T2 | 2024-11-26 | Fail | Fail | 2025-01-02 | Yes
104553 | 2024-11-15 | 2024-12-03 | Solar | 990 | 603D2 | BERWICK | 603T1 | 2024-12-03 | Fail | Pass | 2025-04-08
104517 | 2024-11-13 | 2024-11-21 | Solar | 999 | 428D2 | LIVERMORE FALLS | 428T1 | 2024-11-21 | Fail | Pass | 2024-12-09
104498 | 2024-11-12 |  | Solar | 265.05 | [7 empty] | Yes
104424 | 2024-11-05 | 2024-11-13 | Solar | 995 | 885D1 | WILTON | 885T1 | 2024-11-13 | Fail | Pass | 2025-01-23
104271 | 2024-10-23 | 2024-10-24 | Solar | 984.85 | 874D1 | BELFAST 115 | 874T2 | 2024-10-25 | Fail | Pass | 2024-11-12
104273 | 2024-10-23 | 2024-10-24 | Solar | 995 | 858D3 | STURTEVANT | 858T2 | 2024-10-25 | Fail | Pass | 2024-11-12
104262 | 2024-10-22 | 2024-11-05 | Solar | 999 | 850D2 | SEARSPORT | 850T1 | 2024-11-06 | Fail |  |  | Yes
104264 | 2024-10-22 | 2024-11-26 | Solar | 999 | 815D2 | DOVER | 815T2 | 2024-11-26 | Fail |  |  | Yes
104167 | 2024-10-15 | 2024-10-21 | Solar | 990 | 208D1 | BOND BROOK | 208T1 | 2024-10-22 | Fail | Pass | 2024-11-04
103912 | 2024-09-25 | 2024-09-25 | Solar | 153.6 | 219D2 | DAMARISCOTTA MILLS | 219T1 | 2024-09-26 | Fail | Pass | 2024-10-28
103885 | 2024-09-23 | 2024-10-01 | Solar | 975 | 624D2 | FORT HILL | 624T1 | 2024-10-02 | Fail |  |  | Yes
103844 | 2024-09-19 | 2024-09-24 | Solar | 975 | 272D4 | NORTH AUGUSTA | 272T1 | 2024-09-24 | Fail | Pass | 2024-10-17 | Yes
103677 | 2024-09-05 | 2024-09-05 | Solar | 100 | 803D6 | BELFAST WEST SIDE | 34.5 kV Bus | 2024-09-10 | Fail | Pass | 2024-10-15
103608 | 2024-08-30 |  | Solar | 4999 | [7 empty] | Yes
103599 | 2024-08-29 | 2024-09-16 | Solar | 999.6 | 842D1 | PITTSFIELD | 842T1 | 2024-09-16 | Fail | Pass | 2024-10-11
103367 | 2024-08-14 | 2024-08-15 | Solar | 995 | 242D1 | SIDNEY | 242T1 | 2024-08-16 | Fail | Pass | 2024-09-25
103285 | 2024-08-06 | 2024-08-13 | Solar | 540 | 647D1 | PRIDES CORNER | 647T2 | 2024-08-13 | Fail | Pass | 2024-09-12
103291 | 2024-08-06 | 2024-08-16 | Solar | 125 | 647D1 | PRIDES CORNER | 647T2 | 2024-08-22 | Fail | Pass | 2024-09-16
103293 | 2024-08-06 | 2024-08-16 | Solar | 150 | 647D1 | PRIDES CORNER | 647T2 | 2024-08-22 | Fail | Pass | 2024-09-16
103125 | 2024-07-30 | 2024-08-06 | Solar | 994 | 454D1 | TURNER | 454T1 | 2024-08-07 | Fail | Pass | 2024-09-16
103042 | 2024-07-24 | 2024-08-12 | Solar | 975 | 207D2 | BLAIR ROAD | 207T1 | 2024-08-13 | Fail | Fail | 2024-09-30 | Yes
103022 | 2024-07-23 |  | Solar | 480 | [7 empty] | Yes
103024 | 2024-07-23 | 2024-07-26 | Solar | 480 | 437D1 | OXFORD | 437T1 | 2024-07-29 | Fail | Fail | 2024-08-12 | Yes
103027 | 2024-07-23 |  | Solar | 150 | 437D1 | OXFORD | 437T1 |  |  |  |  | Yes
103030 | 2024-07-23 | 2024-07-26 | Solar | 420 | 216D2 | CONY ROAD | 216T1 | 2024-07-29 | Fail | Fail | 2024-08-23 | Yes
102896 | 2024-07-12 | 2024-07-30 | Solar | 975 | 634D1 | MAY STREET | 634T1 | 2024-08-16 | Fail | Fail | 2024-10-02 | Yes
102852 | 2024-07-11 | 2024-07-18 | Solar | 390 | 605D1 | BIDDEFORD PUMPING STATION | 605T1 | 2024-07-26 | Fail | Pass | 2024-08-28
102789 | 2024-07-08 | 2024-07-08 | Solar | 145.152 | 685D1 | BOLT HILL | 685T1 | 2024-07-10 | Pass
102756 | 2024-07-02 | 2024-07-10 | Solar | 995 | 874D1 | BELFAST 115 | 874T2 | 2024-07-12 | Fail | Fail | 2024-09-03 | Yes
102732 | 2024-07-01 | 2024-07-02 | Solar | 150 | 239D6 | PARK STREET | 239T2 | 2024-07-09 | Fail | Pass | 2024-08-05
102742 | 2024-07-01 | 2024-07-02 | Solar | 200 | 630D2 | GOOSEFARE | 630T1 | 2024-07-03 | Fail | Pass | 2024-08-06
102659 | 2024-06-25 | 2024-06-26 | Solar | 975 | 810D1 | CLINTON | 810T1 | 2024-06-27 | Fail | Fail | 2024-08-12 | Yes
102613 | 2024-06-24 | 2024-06-26 | Solar | 720 | 656D1 | SANFORD INDUSTRIAL PARK | 656T1 | 2024-07-12 | Fail | Pass | 2024-08-28
102614 | 2024-06-24 | 2024-06-26 | Solar | 360 | 644D1 | PLEASANT HILL | 644T2 | 2024-06-28 | Pass
102616 | 2024-06-24 | 2024-06-28 | Solar | 660 | 635D2 | MOSHERS | 635T2 | 2024-07-02 | Fail | Pass | 2024-08-01
102617 | 2024-06-24 | 2024-06-28 | Solar | 100 | 693D2 | SCARBOROUGH | 693T1 | 2024-07-02 | Pass
102619 | 2024-06-24 | 2024-06-28 | Solar | 200 | 693D2 | SCARBOROUGH | 693T1 | 2024-07-02 | Pass
102622 | 2024-06-24 | 2024-06-28 | Solar | 150 | 630D1 | GOOSEFARE | 630T1 | 2024-07-02 | Pass
102492 | 2024-06-13 |  | Solar | 996 | [7 empty] | Yes
102439 | 2024-06-10 | 2024-06-13 | Solar | 280 | 213D3 | BRUNSWICK WEST SIDE | 213T1 | 2024-06-24 | Pass
102340 | 2024-06-04 | 2024-07-10 | Solar | 160 | 213D3 | BRUNSWICK WEST SIDE | 213T1 | 2024-07-12 | Fail | Pass | 2024-08-09
102272 | 2024-05-30 | 2024-06-12 | Solar | 975 | 450D1 | SABATTUS | 450T1 | 2024-06-13 | Pass | Pass | 2024-07-15
102178 | 2024-05-23 | 2024-05-29 | Solar/Battery | 996 | 444D3 | RAYMOND 34 KV | 444T1 | 2024-06-03 | Fail |  |  | Yes
102153 | 2024-05-22 | 2024-06-04 | Solar | 600 | 854D2 | SKOWHEGAN SOUTH SIDE | 854T1 | 2024-06-07 | Fail |  |  | Yes
102149 | 2024-05-21 | 2024-05-21 | Solar | 152 | 435D4 | NORWAY | 435T2 | 2024-05-22 | Fail | Pass | 2024-07-10
102000 | 2024-05-10 | 2024-05-22 | Wind | 225 | 806D2 | BUCKSPORT | 806T3 | 2024-05-31 | Fail | Pass | 2024-07-09
102005 | 2024-05-10 | 2024-05-23 | Solar | 999 | 263D1 | BOWMAN STREET | 34kV BUS 2 | 2024-05-29 | Fail |  |  | Yes
101765 | 2024-04-23 | 2024-05-15 | Solar | 999 | 821D3 | GUILFORD | 821T2 | 2024-05-28 | Fail | Pass | 2024-07-10
101713 | 2024-04-18 | 2024-05-07 | Solar | 975 | 674D2 | WESTBROOK | 674T1 | 2024-05-17 | Fail |  |  | Yes
101717 | 2024-04-18 | 2024-04-19 | Solar | 975 | 226D2 | GARDINER | 226T1 | 2024-04-22 | Fail | Pass | 2024-05-20
101658 | 2024-04-12 | 2024-04-18 | Solar | 153.6 | 219D2 | DAMARISCOTTA MILLS | 219T1 | 2024-05-08 | Fail |  |  | Yes
101603 | 2024-04-08 | 2024-04-17 | Solar | 250 | 412D4 | DEER RIPS | 412T4 | 2024-04-25 | Fail | Pass | 2024-06-24
101569 | 2024-04-04 | 2024-04-23 | Solar | 999 | 602D3 | BASSETT | 602T1 | 2024-05-09 | Fail | Pass | 2024-06-28
101528 | 2024-04-01 | 2024-04-12 | Solar | 999 | 431D1 | MECHANIC FALLS | 431T2 | 2024-04-22 | Fail | Fail | 2024-06-19 | Yes
101504 | 2024-03-28 | 2024-04-02 | Solar | 999 | 252D1 | WALDOBORO | 252T1 | 2024-04-05 | Fail | Fail | 2024-05-21 | Yes
101353 | 2024-03-18 | 2024-03-25 | Solar | 120 | 630D1 | GOOSEFARE | 630T1 | 2024-04-12 | Pass
101333 | 2024-03-14 |  | Solar | 150 | 403D1 | BETHEL | 403T1 |  |  |  |  | Yes
101334 | 2024-03-14 |  | Solar | 200 | 858D2 | STURTEVANT | 858T1 |  |  |  |  | Yes
101262 | 2024-03-08 | 2024-03-14 | Solar | 152 | 423D2 | KIMBALL ROAD | 423T2 | 2024-03-18 | Fail | Pass | 2024-04-30
101251 | 2024-03-07 | 2024-03-08 | Solar | 780 | 612D1 | BUTLER'S CORNER | 612T1 | 2024-03-27 | Fail | Fail | 2024-05-21 | Yes
101145 | 2024-02-27 | 2024-02-28 | Solar | 999 | 457D2 | MONMOUTH | 457T2 | 2024-03-01 | Fail | Pass | 2024-04-23
101131 | 2024-02-26 | 2024-02-29 | Solar | 999 | 447D4 | RUMFORD | 447T3 | 2024-03-01 | Fail | Fail | 2024-05-01 | Yes
101137 | 2024-02-26 | 2024-03-08 | Solar | 975 | 230D2 | COOPERS MILLS ROAD | 230T2 | 2024-03-08 | Fail | Pass | 2024-05-01
101067 | 2024-02-21 | 2024-02-23 | Solar | 125 | 865D1 | WEST WATERVILLE | 865T1 | 2024-02-26 | Pass |  |  | Yes
101037 | 2024-02-19 |  | Solar | 100 | 415D2 | FRYEBURG | 415T1 |  |  |  |  | Yes
100989 | 2024-02-13 |  | Solar | 996 | [7 empty] | Yes
100963 | 2024-02-09 | 2024-02-12 | Solar | 115.2 | 216D3 | CONY ROAD | 216T1 | 2024-02-13 | Pass
100873 | 2024-02-01 | 2024-02-13 | Solar | 995 | 667D2 | SOUTH SANFORD | 667T2 | 2024-03-07 | Fail | Fail | 2024-05-06 | Yes
100862 | 2024-01-31 | 2024-02-08 | Solar | 150 | 233D1 | MANCHESTER | 233T1 | 2024-02-09 | Fail | Pass | 2024-03-25
100863 | 2024-01-31 | 2024-02-09 | Solar | 600 | 415D2 | FRYEBURG | 415T1 | 2024-02-16 | Fail | Fail | 2024-04-12 | Yes
100846 | 2024-01-30 | 2024-02-19 | Solar | 999 | 272D2 | NORTH AUGUSTA | 272T1 | 2024-02-20 | Fail | Pass | 2024-04-11
100821 | 2024-01-26 | 2024-03-04 | Solar | 999 | 632D1 | LIMERICK | 632T1 | 2024-03-07 | Fail | Fail | 2024-05-12 | Yes
100803 | 2024-01-25 | 2024-02-02 | Solar | 999 | 246D3 | THOMASTON CREEK | 246T1 | 2024-02-21 | Fail | Fail | 2024-05-07 | Yes
100814 | 2024-01-25 | 2024-02-07 | Solar | 233.3 | 620D4 | ELM STREET | 620T2 | 2024-02-09 | Fail | Pass | 2024-04-02
100792 | 2024-01-24 | 2024-02-23 | Solar | 999 | 467D1 | TURNER TAP | Tap off of Transmission Line | 2024-02-26 | Fail | Pass | 2024-04-24
100687 | 2024-01-12 | 2024-01-18 | Solar | 500 | 256D2 | WINTHROP | 256T1 | 2024-01-19 | Fail |  |  | Yes
100680 | 2024-01-11 | 2024-01-22 | Solar | 380 | 668D3 | SPRING STREET | 668T2 | 2024-02-05 | Pass
100681 | 2024-01-11 | 2024-01-22 | Solar | 999 | 685D2 | BOLT HILL | 685T1 | 2024-02-13 | Fail | Pass | 2024-04-12
100682 | 2024-01-11 | 2024-01-22 | Solar | 999 | 603D3 | BERWICK | 603T1 | 2024-02-22 | Fail | Fail | 2024-04-26 | Yes
100620 | 2024-01-05 | 2024-01-05 | Solar | 400 | 412D1 | DEER RIPS | 412T2 | 2024-01-09 | Fail | Pass | 2024-03-18
100623 | 2024-01-05 | 2024-01-08 | Solar | 720 | 412D1 | DEER RIPS | 412T2 | 2024-01-09 | Fail | Pass | 2024-03-11
100571 | 2023-12-29 | 2024-01-16 | Solar | 750 | 200D3 | AUGUSTA K5 | 200T1 | 2024-01-16 | Fail | Pass | 2024-03-20
100520 | 2023-12-22 | 2024-01-09 | Solar | 500 | 660D2 | SHAWS MILL ROAD | 660T1 | 2024-01-13 | Fail | Pass | 2024-02-15
100461 | 2023-12-15 | 2024-01-10 | Solar | 999 | 818D2 | FARMINGTON FALLS | 818T1 | 2024-01-17 | Fail | Pass | 2024-04-11
100388 | 2023-12-11 | 2023-12-15 | Solar | 350 | 421D2 | CHALLENGER | 421T1 | 2024-01-03 | Fail | Pass | 2024-02-21
100360 | 2023-12-08 |  | Solar | 999 | [7 empty] | Yes
100368 | 2023-12-08 | 2023-12-14 | Solar | 330 | 841D1 | PHILLIPS/STRONG | 841T1 | 2024-01-03 | Fail |  |  | Yes
100376 | 2023-12-08 | 2023-12-15 | Solar | 999 | 855D2 | SOUTH WATERVILLE | 855T1 | 2023-12-18 | Fail | Fail | 2024-02-08 | Yes
100379 | 2023-12-08 |  | Solar | 1000 | [7 empty] | Yes
100340 | 2023-12-07 | 2023-12-11 | Solar | 360 | 215D2 | CAPITOL STREET | 215T2 | 2023-12-11 | Fail | Pass | 2024-02-09
100354 | 2023-12-07 | 2024-01-08 | Solar | 999 | 632D1 | LIMERICK | 632T1 | 2024-02-01 | Fail | Fail | 2024-04-09 | Yes
100324 | 2023-12-06 | 2023-12-12 | Solar | 360 | 273D5 | BRUNSWICK HYDRO | 273T2 | 2024-01-02 | Pass
100307 | 2023-12-05 | 2023-12-06 | Solar | 540 | 249D2 | TOPSHAM OLD | 249T1 | 2023-12-27 | Fail | Pass | 2024-03-11
100263 | 2023-12-01 | 2024-01-10 | Solar | 900 | 818D1 | FARMINGTON FALLS | 818T1 | 2024-01-17 | Fail | Pass | 2024-03-18 | Yes
100265 | 2023-12-01 | 2023-12-06 | Solar | 240 | 865D1 | WEST WATERVILLE | 865T1 | 2023-12-06 | Fail | Pass | 2024-01-29
100266 | 2023-12-01 | 2023-12-06 | Solar | 400 | 639D2 | NORTH WINDHAM | 639T2 | 2023-12-11 | Fail | Pass | 2024-03-08
100267 | 2023-12-01 | 2023-12-06 | Solar | 240 | 681D3 | BRANCH BROOK | 681T3 | 2023-12-27 | Pass
100268 | 2023-12-01 | 2023-12-06 | Solar | 500 | 681D3 | BRANCH BROOK | 681T3 | 2023-12-26 | Pass
100245 | 2023-11-30 | 2023-12-07 | Solar | 120 | 249D1 | TOPSHAM OLD | 249T1 | 2023-12-29 | Fail | Pass | 2024-02-22
100251 | 2023-11-30 | 2023-12-07 | Solar | 100 | 249D1 | TOPSHAM OLD | 249T1 | 2024-01-02 | Fail | Pass | 2024-02-19
100252 | 2023-11-30 | 2024-01-17 | Solar | 1020 | 471D1 | LEEDS | 471T1 | 2024-01-23 | Fail | Fail | 2024-04-29 | Yes
100255 | 2023-11-30 | 2023-12-15 | Solar | 1020 | 873D1 | COUNTY RD (RICE RIPS) | 873T1 | 2023-12-18 | Fail |  |  | Yes
100222 | 2023-11-29 | 2023-11-30 | Solar | 996 | 678D1 | BAR MILLS | 678T4 | 2023-12-26 | Fail | Fail | 2024-03-21 | Yes
100227 | 2023-11-29 | 2023-12-12 | Solar | 1020 | 450D2 | SABATTUS | 450T1 | 2023-12-26 | Fail | Fail | 2024-03-11 | Yes
100140 | 2023-11-27 | 2023-12-07 | Solar | 360 | 668D3 | SPRING STREET | 668T2 | 2023-12-11 | Pass
100119 | 2023-11-22 | 2023-11-29 | Solar | 996 | 453D1 | TRAP CORNER | 453T1 | 2023-12-05 | Fail |  |  | Yes
100126 | 2023-11-22 | 2023-12-06 | Solar | 360 | 233D1 | MANCHESTER | 233T1 | 2023-12-06 | Fail | Fail | 2024-02-20 | Yes
100128 | 2023-11-22 | 2023-12-07 | Solar | 420 | 213D4 | BRUNSWICK WEST SIDE | 213T2 | 2023-12-29 | Pass
100129 | 2023-11-22 | 2023-12-06 | Solar | 480 | 668D3 | SPRING STREET | 668T2 | 2023-12-11 | Fail |  |  | Yes
100091 | 2023-11-17 | 2023-11-27 | Solar | 975 | 461D1 | LUDDEN LANE | 461T1 | 2023-12-11 | Fail | Pass | 2024-02-12
100056 | 2023-11-16 | 2023-11-27 | Solar | 120 | 208D1 | BOND BROOK | 208T1 | 2023-11-27 | Fail |  |  | Yes
100057 | 2023-11-16 | 2023-11-27 | Solar | 120 | 453D1 | TRAP CORNER | 453T1 | 2023-11-28 | Fail |  |  | Yes
100000 | 2023-11-15 | 2023-11-27 | Solar | 994 | 210D1 | BRISTOL | 210T1 | 2023-12-18 | Fail | Pass | 2024-01-25
100001 | 2023-11-15 | 2023-11-27 | Solar | 700 | 870D1 | WINSLOW | 870T4 | 2023-11-28 | Fail | Fail | 2024-01-02 | Yes
100002 | 2023-11-15 | 2023-11-22 | Solar | 994 | 454D1 | TURNER | 454T1 | 2023-11-28 | Fail | Fail | 2024-01-25 | Yes
100049 | 2023-11-15 | 2024-01-04 | Solar | 1020 | 858D2 | STURTEVANT | 858T1 | 2024-01-05 | Fail |  |  | Yes
85879 | 2023-11-13 | 2023-11-20 | Solar | 999 | 695D2 | LEBANON | 695T1 | 2023-12-13 | Fail | Fail | 2024-02-14 | Yes
85877 | 2023-11-10 | 2023-11-13 | Solar | 995 | 842D1 | PITTSFIELD | 842T1 | 2023-11-14 | Fail | Pass | 2023-12-08
85876 | 2023-11-09 | 2023-12-06 | Solar | 100 | 803D5 | BELFAST WEST SIDE | 803T1 | 2023-12-29 | Fail | Pass | 2024-02-21
85862 | 2023-11-08 | 2023-11-15 | Solar | 150 | 233D1 | MANCHESTER | 233T1 | 2023-11-15 | Fail | Pass | 2024-01-02
85875 | 2023-11-08 | 2023-12-11 | Solar | 999 | 837D2 | NEWPORT | 837T2 | 2023-12-11 | Fail | Pass | 2024-01-17 | Yes
85805 | 2023-11-03 | 2023-11-09 | Solar | 999 | 813D1 | DEXTER | 813T1 | 2023-11-17 | Fail | Pass | 2024-01-02
85807 | 2023-11-03 | 2023-11-09 | Solar | 999 | 256D2 | WINTHROP | 256T1 | 2023-11-10 | Fail | Pass | 2023-12-06
85736 | 2023-11-02 | 2023-11-02 | Solar | 999 | 471D2 | LEEDS | 471T1 | 2023-11-08 | Fail | Pass | 2024-01-02
85743 | 2023-11-02 | 2023-11-14 | Solar | 560 | 412D1 | DEER RIPS | 412T2 | 2023-11-17 | Fail | Pass | 2024-01-11 | Yes
85721 | 2023-11-01 | 2023-11-13 | Solar | 970 | 239D6 | PARK STREET | 239T2 | 2023-11-14 | Fail | Pass | 2024-01-17
85727 | 2023-11-01 | 2023-11-13 | Solar | 625 | 230D1 | COOPERS MILLS ROAD | 230T2 | 2023-11-13 | Fail | Pass | 2024-01-25
85695 | 2023-10-31 | 2023-11-13 | Solar | 300 | 865D5 | WEST WATERVILLE | 865T2 | 2023-11-14 | Fail | Pass | 2024-01-29
85703 | 2023-10-31 | 2023-11-03 | Solar | 975 | 421D2 | CHALLENGER | 421T1 | 2023-11-09 | Fail | Pass | 2023-12-06 | Yes
85663 | 2023-10-27 | 2023-11-03 | Solar | 600 | 612D2 | BUTLER'S CORNER | 612T1 | 2023-11-28 | Fail | Fail | 2024-02-14 | Yes
85622 | 2023-10-24 | 2023-11-13 | Solar | 152 | 423D2 | KIMBALL ROAD | 423T2 | 2023-11-14 | Fail | Pass | 2024-01-11
85588 | 2023-10-18 | 2023-10-24 | Solar | 600 | 865D1 | WEST WATERVILLE | 865T1 | 2023-10-25 | Pass
85484 | 2023-10-13 | 2023-10-18 | Solar | 975 | 447D1 | RUMFORD | 447T3 | 2023-10-30 | Pass
85488 | 2023-10-13 | 2023-10-19 | Solar | 500 | 208D1 | BOND BROOK | 208T1 | 2023-10-19 | Fail | Pass | 2023-11-27
85228 | 2023-09-28 | 2023-10-04 | Solar | 975 | 261D4 | BATH 34 | 261T2 | 2023-10-26 | Fail | Fail | 2023-11-10 | Yes
85186 | 2023-09-26 | 2023-10-17 | Solar | 900 | 667D3 | SOUTH SANFORD | 667T1 | 2023-11-14 | Fail | Pass | 2024-01-24
85197 | 2023-09-26 | 2023-10-02 | Solar | 480 | 423D1 | KIMBALL ROAD | 423T2 | 2023-10-05 | Fail | Pass | 2023-11-10
85173 | 2023-09-25 | 2023-09-28 | Solar | 250 | 673D1 | BIDDEFORD INDUSTRIAL PARK | 673T2 | 2023-10-23 | Pass
85069 | 2023-09-15 | 2023-10-04 | Solar | 975 | 466D1 | RUMFORD INDUSTRIAL PARK | 466T1 | 2023-10-06 | Fail | Fail | 2023-11-10 | Yes
85041 | 2023-09-13 | 2023-09-27 | Solar | 994 | 263D1 | BOWMAN STREET | 34kV BUS 2 | 2023-09-28 | Fail | Pass | 2023-10-25
85031 | 2023-09-12 | 2023-10-12 | Solar | 1999 | 225D3 | FREEPORT | 225T2 | 2023-10-26 | Fail |  |  | Yes
85012 | 2023-09-11 | 2023-09-18 | Solar | 1050 | 207D1 | BLAIR ROAD | 207T1 | 2023-09-19 | Fail | Fail | 2023-10-25 | Yes
84974 | 2023-09-08 | 2023-09-13 | Solar | 975 | 233D1 | MANCHESTER | 233T1 | 2023-09-13 | Fail | Pass | 2023-09-29
84979 | 2023-09-08 | 2023-09-13 | Solar | 975 | 219D2 | DAMARISCOTTA MILLS | 219T1 | 2023-09-19 | Fail | Pass | 2023-10-12
84902 | 2023-09-05 | 2023-09-12 | Other | 100 | 855D1 | SOUTH WATERVILLE | 855T1 | 2023-09-06 | Fail | Pass | 2023-10-12
84904 | 2023-09-05 | 2023-09-11 | Solar | 150 | 252D2 | WALDOBORO | 252T1 | 2023-09-15 | Fail | Pass | 2023-10-12
84764 | 2023-08-23 | 2023-09-19 | Solar | 500 | 210D2 | BRISTOL | 210T1 | 2023-10-11 | Fail | Fail | 2023-12-08 | Yes
84691 | 2023-08-17 | 2023-08-25 | Solar | 144.48 | 667D1 | SOUTH SANFORD | 667T2 | 2023-08-31 | Fail | Pass | 2023-10-12
84683 | 2023-08-14 |  | Solar | 799.98 | 874D1 | BELFAST 115 | 874T2 |  |  |  |  | Yes
84684 | 2023-08-14 | 2023-08-28 | Solar | 100 | 239D7 | PARK STREET | 239T2 | 2023-08-31 | Pass
84618 | 2023-08-09 | 2023-08-10 | Solar | 999 | 412D1 | DEER RIPS | 412T2 | 2023-08-11 | Fail | Pass | 2023-09-28
84619 | 2023-08-09 | 2023-08-10 | Solar | 996 | 870D1 | WINSLOW | 870T4 | 2023-08-11 | Fail | Fail | 2023-09-14 | Yes
84757 | 2023-08-09 | 2023-09-08 | Solar | 999.6 | 808D3 | CARMEL TAP | 808T1 | 2023-09-26 | Pass
84609 | 2023-08-08 | 2023-08-21 | Solar | 999 | 821D1 | GUILFORD | 821T1 | 2023-08-22 | Fail | Pass | 2023-12-01
84547 | 2023-08-01 | 2023-08-04 | Solar | 999 | 412D4 | DEER RIPS | 412T4 | 2023-08-07 | Fail | Fail | 2023-10-25 | Yes
84553 | 2023-08-01 | 2023-08-04 | Solar | 999 | 412D4 | DEER RIPS | 412T4 | 2023-08-07 | Fail | Fail | 2023-10-25 | Yes
84450 | 2023-07-25 | 2023-07-27 | Solar | 996 | 695D2 | LEBANON | 695T1 | 2023-08-24 | Fail | Pass | 2023-10-12
84451 | 2023-07-25 | 2023-07-27 | Solar | 996 | 663D2 | SOUTH BERWICK | 663T1 | 2023-08-24 | Fail | Fail | 2023-10-12 | Yes
84452 | 2023-07-25 | 2023-07-27 | Solar | 996 | 225D4 | FREEPORT | 225T1 | 2023-08-17 | Fail | Fail | 2023-10-03 | Yes
84411 | 2023-07-20 | 2023-08-07 | Solar | 999 | 632D2 | LIMERICK | 632T1 | 2023-08-31 | Fail |  |  | Yes
84416 | 2023-07-20 | 2023-08-07 | Solar | 999 | 632D2 | LIMERICK | 632T1 | 2023-08-31 | Fail |  |  | Yes
84392 | 2023-07-18 | 2023-08-21 | Solar | 200 | 607D1 | BISHOP STREET | 607T1 | 2023-09-08 | Pass
84389 | 2023-07-17 | 2023-07-26 | Solar | 975 | 232D2 | LISBON FALLS | 232T2 | 2023-08-11 | Fail | Fail | 2023-09-20 | Yes
84338 | 2023-07-13 | 2023-07-19 | Solar | 975 | 244D1 | SOUTH CHINA | 244T1 | 2023-07-19 | Fail | Fail | 2023-08-16 | Yes
84350 | 2023-07-13 | 2023-07-19 | Solar | 975 | 255D2 | WEST STREET | 255T1 | 2023-07-19 | Fail | Pass | 2023-08-23
84304 | 2023-07-10 | 2023-07-10 | Solar | 750 | 858D2 | STURTEVANT | 858T1 | 2023-07-13 | Pass
84290 | 2023-07-06 | 2023-07-10 | Solar | 975 | 808D1 | CARMEL | 808T1 | 2023-07-14 | Fail | Pass | 2023-08-31 | Yes
84276 | 2023-07-05 | 2023-07-21 | Solar | 999 | 837D1 | NEWPORT | 837T1 | 2023-07-24 | Fail | Pass | 2023-08-11
84277 | 2023-07-05 | 2023-07-21 | Solar | 999 | 837D1 | NEWPORT | 837T1 | 2023-07-24 | Fail | Pass | 2023-09-06
84278 | 2023-07-05 | 2023-07-21 | Solar | 999 | 837D1 | NEWPORT | 837T1 | 2023-07-24 | Fail | Pass | 2023-09-06
84279 | 2023-07-05 | 2023-07-21 | Solar | 999 | 837D1 | NEWPORT | 837T1 | 2023-07-24 | Fail | Fail | 2023-09-06 | Yes
84280 | 2023-07-05 | 2023-07-21 | Solar | 999 | 837D1 | NEWPORT | 837T1 | 2023-07-24 | Fail | Fail | 2023-09-06 | Yes
84272 | 2023-06-30 | 2023-07-05 | Solar | 825 | 253D1 | WARREN | 253T1 | 2023-07-06 | Fail | Pass | 2023-08-01
84231 | 2023-06-29 | 2023-07-10 | Solar | 996 | 461D1 | LUDDEN LANE | 461T1 | 2023-07-13 | Fail | Pass | 2023-08-11
84228 | 2023-06-28 | 2023-06-30 | Solar | 999 | 860D1 | UNITY | 860T1 | 2023-07-10 | Fail | Fail | 2023-08-30 | Yes
84222 | 2023-06-27 | 2023-07-05 | Solar | 120 | 678D1 | BAR MILLS | 678T4 | 2023-07-26 | Fail | Pass | 2023-09-11
84188 | 2023-06-23 | 2023-06-28 | Solar | 975 | 238D1 | MESSINA | 238T1 | 2023-07-20 | Fail | Fail | 2023-08-16 | Yes
84211 | 2023-06-23 | 2023-07-07 | Solar | 160 | 689D1 | BRAGDON COMMONS | 689T1 | 2023-07-26 | Fail | Pass | 2023-09-20
84117 | 2023-06-16 | 2023-06-21 | Solar | 975 | 858D1B | STURTEVANT | 858T2 | 2023-07-06 | Fail | Pass | 2023-09-25
84104 | 2023-06-14 | 2023-07-05 | Solar | 1000 | 815D2 | DOVER | 815T2 | 2023-07-06 | Fail |  |  | Yes
84107 | 2023-06-14 | 2023-06-15 | Solar | 999 | 636D1 | MUSSEY ROAD | 636T1 | 2023-06-30 | Fail | Pass | 2023-08-08 | Yes
84070 | 2023-06-12 | 2023-06-15 | Solar | 975 | 860D2 | UNITY | 860T1 | 2023-06-29 | Fail | Pass | 2023-07-27
84071 | 2023-06-12 | 2023-06-14 | Solar | 975 | 858D1A | STURTEVANT | 858T1 | 2023-06-15 | Fail | Pass | 2023-07-18 | Yes
84066 | 2023-06-09 | 2023-06-12 | Solar | 995 | 471D1 | LEEDS | 471T1 | 2023-06-15 | Fail | Fail | 2023-07-10 | Yes
84068 | 2023-06-09 | 2023-06-13 | Solar | 875 | 253D1 | WARREN | 253T1 | 2023-06-28 | Fail |  |  | Yes
84024 | 2023-06-07 | 2023-06-13 | Solar | 975 | 431D1 | MECHANIC FALLS | 431T2 | 2023-06-15 | Fail | Pass | 2023-07-18
83991 | 2023-06-02 | 2023-06-08 | Solar | 160 | 852D1 | SHAWMUT | 852T3 | 2023-06-09 | Fail | Pass | 2023-07-25
84004 | 2023-06-02 | 2023-06-21 | Solar | 999 | 256D1 | WINTHROP | 256T2 | 2023-06-27 | Fail | Pass | 2023-08-16
83944 | 2023-05-26 | 2023-06-01 | Solar | 975 | 639D2 | NORTH WINDHAM | 639T2 | 2023-06-07 | Fail | Pass | 2023-07-12
83909 | 2023-05-24 | 2023-06-05 | Solar | 999 | 813D1 | DEXTER | 813T1 | 2023-06-07 | Fail | Fail | 2023-07-14 | Yes
83914 | 2023-05-24 | 2023-06-05 | Solar | 999 | 885D1 | WILTON | 885T1 | 2023-06-07 | Fail | Pass | 2023-07-14
83916 | 2023-05-24 | 2023-06-05 | Solar | 999 | 885D1 | WILTON | 885T1 | 2023-06-07 | Fail | Fail | 2023-07-14 | Yes
83894 | 2023-05-22 | 2023-05-25 | Solar | 900 | 691D1 | BALDWIN | 691T1 | 2023-05-25 | Fail | Fail | 2023-06-21 | Yes
83856 | 2023-05-17 | 2023-05-22 | Solar | 154 | 274D1 | MAINE YANKEE | 274T2 | 2023-05-23 | Fail | Pass | 2023-07-20
83838 | 2023-05-16 | 2023-05-22 | Solar | 200 | 239D7 | PARK STREET | 239T2 | 2023-05-23 | Pass
83837 | 2023-05-15 | 2023-05-17 | Solar | 720 | 428D2 | LIVERMORE FALLS | 428T1 | 2023-05-18 | Pass
83829 | 2023-05-12 | 2023-05-15 | Solar | 995 | 412D3 | DEER RIPS | 412T4 | 2023-05-18 | Fail | Pass | 2023-06-06
83793 | 2023-05-09 | 2023-05-11 | Solar | 975 | 400D1 | ANDOVER | 400T1 | 2023-05-12 | Fail | Pass | 2023-06-20
83777 | 2023-05-08 | 2023-05-09 | Solar | 999 | 805D1 | BROOKS | 805T1 | 2023-05-10 | Fail | Fail | 2023-08-08 | Yes
83779 | 2023-05-08 | 2023-05-10 | Solar | 996 | 813D3 | DEXTER | 813T2 | 2023-05-12 | Fail | Fail | 2023-08-08 | Yes
83787 | 2023-05-08 | 2023-05-10 | Solar | 996 | 406D2 | BRIDGTON | 406T1 | 2023-05-17 | Fail | Fail | 2023-07-26 | Yes
83769 | 2023-05-05 | 2023-05-08 | Solar | 240 | 630D4 | GOOSEFARE | 630T1 | 2023-05-17 | Fail | Pass | 2023-06-22
83738 | 2023-05-04 | 2023-05-11 | Solar | 975 | 466D1 | RUMFORD INDUSTRIAL PARK | 466T1 | 2023-05-12 | Fail | Pass | 2023-06-01 | Yes
83720 | 2023-05-03 | 2023-05-25 | Solar | 1000 | 834D1 | MONSON | 834T1 | 2023-05-30 | Fail | Fail | 2023-06-22 | Yes
83685 | 2023-04-28 | 2023-05-01 | Solar | 324 | 858D1A | STURTEVANT | 858T1 | 2023-05-01 | Fail | Pass | 2023-05-03
83664 | 2023-04-27 | 2023-05-01 | Solar | 700 | 816D1 | EAST WILTON | 816T1 | 2023-05-02 | Fail | Pass | 2023-06-01
83668 | 2023-04-27 | 2023-05-01 | Solar | 975 | 233D2 | MANCHESTER | 233T1 | 2023-05-03 | Fail | Pass | 2023-05-11 | Yes
83670 | 2023-04-27 | 2023-05-01 | Solar | 975 | 262D1 | PUDDLEDOCK ROAD | 34 kV BUS 1 | 2023-05-09 | Fail | Pass | 2023-06-16
83611 | 2023-04-24 | 2023-05-03 | Solar | 120 | 617D3 | DUNSTAN | 617T1 | 2023-05-15 | Pass
83605 | 2023-04-21 | 2023-04-27 | Solar | 975 | 431D1 | MECHANIC FALLS | 431T2 | 2023-04-27 | Fail | Pass | 2023-06-05
83600 | 2023-04-20 | 2023-04-21 | Solar | 850 | 450D1 | SABATTUS | 450T1 | 2023-04-24 | Fail | Pass | 2023-06-21
83601 | 2023-04-20 | 2023-04-25 | Solar | 700 | 256D2 | WINTHROP | 256T1 | 2023-04-25 | Fail | Pass | 2023-05-11
83526 | 2023-04-12 | 2023-05-01 | Solar | 1000 | 821D3 | GUILFORD | 821T2 | 2023-05-02 | Fail | Fail | 2023-05-18 | Yes
83507 | 2023-04-11 | 2023-04-14 | Solar | 975 | 639D2 | NORTH WINDHAM | 639T2 | 2023-05-02 | Fail | Pass | 2023-05-23
83514 | 2023-04-11 | 2023-04-13 | Solar | 995 | 858D3 | STURTEVANT | 858T2 | 2023-04-18 | Fail | Pass | 2023-05-01
83474 | 2023-04-05 | 2023-04-07 | Solar | 999 | 605D1 | BIDDEFORD PUMPING STATION | 605T1 | 2023-05-03 | Pass | Pass | 2023-06-26
83455 | 2023-04-03 | 2023-04-18 | Solar | 999 | 602D3 | BASSETT | 602T1 | 2023-05-03 | Fail | Pass | 2023-06-23
83453 | 2023-03-31 | 2023-04-05 | Solar | 975 | 858D1A | STURTEVANT | 858T1 | 2023-04-05 | Fail | Fail | 2023-04-24 | Yes
83437 | 2023-03-28 | 2023-04-06 | Solar | 120 | 634D4 | MAY STREET | 634T1 | 2023-05-03 | Pass
83403 | 2023-03-27 | 2023-04-03 | Solar | 125 | 693D1 | SCARBOROUGH | 693T1 | 2023-04-05 | Pass |  |  | Yes
83401 | 2023-03-24 | 2023-03-29 | Solar | 250 | 436D6 | GREAT FALLS | 436T1 | 2023-03-30 | Fail | Pass | 2023-04-24 | Yes
83384 | 2023-03-23 | 2023-03-29 | Solar | 600 | 673D1 | BIDDEFORD INDUSTRIAL PARK | 673T2 | 2023-04-19 | Fail | Pass | 2023-06-02
83361 | 2023-03-21 | 2023-03-24 | Solar/Battery | 996 | 834D1 | MONSON | 834T1 | 2023-03-28 | Fail | Pass | 2023-05-16
83350 | 2023-03-20 | 2023-03-23 | Solar | 999 | 253D1 | WARREN | 253T1 | 2023-04-12 | Fail | Fail | 2023-05-11 | Yes
83328 | 2023-03-16 | 2023-03-20 | Solar | 720 | 653D5 | FORE RIVER | 653T1 | 2023-04-03 | Fail | Pass | 2023-05-01
83307 | 2023-03-14 | 2023-03-21 | Solar/Battery | 996 | 813D1 | DEXTER | 813T1 | 2023-03-22 | Fail | Pass | 2023-07-07
83298 | 2023-03-13 | 2023-03-16 | Solar | 120 | 200D1 | AUGUSTA K5 | 200T1 | 2023-03-16 | Pass
83253 | 2023-03-06 | 2023-03-15 | Solar | 120 | 656D1 | SANFORD INDUSTRIAL PARK | 656T1 | 2023-04-04 | Pass
83260 | 2023-03-06 | 2023-03-10 | Solar | 400 | 211D1 | BROWNS CROSSING | 211T1 | 2023-03-13 | Pass
83231 | 2023-03-02 | 2023-03-20 | Solar | 150 | 232D2 | LISBON FALLS | 232T2 | 2023-03-29 | Pass
83235 | 2023-03-02 | 2023-03-06 | Fuel Cell | 930 | 688D1 | KITTERY | 688T1 | 2023-03-28 | Pass
83229 | 2023-03-01 | 2023-03-03 | Fuel Cell | 600 | 420D1 | HOTEL ROAD | 420T2 | 2023-03-14 | Pass
83208 | 2023-02-24 | 2023-03-03 | Solar | 999 | 447D2 | RUMFORD | 447T4 | 2023-03-14 | Fail | Pass | 2023-04-18
83189 | 2023-02-22 | 2023-02-22 | Solar | 1500 | 612D1 | BUTLER'S CORNER | 612T1 | 2023-03-21 | Fail |  |  | Yes
83186 | 2023-02-21 | 2023-02-23 | Solar | 995 | 256D2 | WINTHROP | 256T1 | 2023-02-24 | Fail | Pass | 2023-03-23
83158 | 2023-02-16 | 2023-03-13 | Solar | 160 | 690D1 | HINCKLEY POND | 690T1 | 2023-03-23 | Pass |  |  | Yes
83159 | 2023-02-16 | 2023-03-01 | Solar | 120 | 255D2 | WEST STREET | 255T1 | 2023-03-23 | Fail |  |  | Yes
83131 | 2023-02-14 | 2023-02-21 | Solar | 240 | 621D2 | FACTORY ISLAND | 621T2 | 2023-03-07 | Pass
83095 | 2023-02-13 | 2023-02-24 | Solar | 300 | 239D7 | PARK STREET | 239T2 | 2023-03-16 | Pass
83116 | 2023-02-13 | 2023-02-22 | Solar | 133.2 | 650D4 | RIGBY | 650T2 | 2023-03-01 | Pass
83066 | 2023-02-09 | 2023-02-13 | Solar | 160 | 629D3 | KENNEBUNKPORT | 629T2 | 2023-03-07 | Pass
83040 | 2023-02-08 | 2023-02-23 | Solar | 999 | 837D2 | NEWPORT | 837T2 | 2023-03-07 | Fail | Pass | 2023-04-05
83025 | 2023-02-07 | 2023-02-09 | Solar | 995 | 256D2 | WINTHROP | 256T1 | 2023-02-23 | Fail | Pass | 2023-03-22
83038 | 2023-02-07 | 2023-02-09 | Solar | 100 | 447D4 | RUMFORD | 447T3 | 2023-02-24 | Pass
83018 | 2023-02-03 | 2023-02-09 | Solar | 300 | 620D1 | ELM STREET | 620T2 | 2023-02-28 | Fail | Pass | 2023-04-03
83014 | 2023-02-02 | 2023-02-13 | Solar | 200 | 630D2 | GOOSEFARE | 630T1 | 2023-03-07 | Pass
83016 | 2023-02-02 | 2023-03-03 | Solar | 240 | 630D4 | GOOSEFARE | 630T1 | 2023-04-04 | Fail |  |  | Yes
82985 | 2023-01-30 | 2023-02-09 | Solar | 200 | 656D2 | SANFORD INDUSTRIAL PARK | 656T1 | 2023-02-21 | Pass
82971 | 2023-01-27 | 2023-02-01 | Solar | 100 | 634D4 | MAY STREET | 634T1 | 2023-02-22 | Pass
82924 | 2023-01-20 | 2023-01-23 | Fuel Cell | 975 | 636D2 | MUSSEY ROAD | 636T1 | 2023-03-03 | Pass
82927 | 2023-01-20 | 2023-01-24 | Solar | 500 | 447D4 | RUMFORD | 447T3 | 2023-02-14 | Pass
82862 | 2023-01-06 | 2023-01-10 | Solar | 400 | 813D3 | DEXTER | 813T2 | 2023-01-13 | Pass |  |  | Yes
82873 | 2023-01-06 | 2023-01-11 | Solar | 360 | 650D4 | RIGBY | 650T2 | 2023-02-06 | Pass
82874 | 2023-01-06 | 2023-02-06 | Solar | 999 | 821D1 | GUILFORD | 821T1 | 2023-02-07 | Fail | Fail | 2023-03-02 | Yes
82822 | 2023-01-05 | 2023-01-09 | Solar | 145.92 | 251D1 | UNION | 251T1 | 2023-01-26 | Fail | Pass | 2023-02-01
82781 | 2022-12-28 | 2023-01-18 | Fuel Cell | 975 | 630D1 | GOOSEFARE | 630T1 | 2023-01-26 | Pass |  |  | Yes
82771 | 2022-12-22 | 2023-01-06 | Solar | 996 | 657D4 | SANFORD SWITCH | 657T1 | 2023-01-30 | Fail | Pass | 2023-04-18
82708 | 2022-12-14 | 2023-01-09 | Solar | 500 | 238D1 | MESSINA | 238T1 | 2023-01-11 | Fail | Pass | 2023-03-27
82709 | 2022-12-14 |  |  | 999 | 610D2 | BONNY EAGLE | 610T4 |  |  |  |  | Yes
82674 | 2022-12-13 | 2023-01-03 | Solar | 999 | 821D1 | GUILFORD | 821T1 | 2023-01-03 | Fail |  |  | Yes
82683 | 2022-12-13 | 2023-01-11 | Solar | 700 | 624D2 | FORT HILL | 624T1 | 2023-02-07 | Pass
82671 | 2022-12-08 | 2022-12-12 | Fuel Cell | 650 | 420D3 | HOTEL ROAD | 420T2 | 2023-01-16 | Pass
82669 | 2022-12-06 | 2022-12-23 | Solar | 975 | 239D7 | PARK STREET | 239T2 | 2023-01-12 | Fail | Fail | 2023-02-22 | Yes
82584 | 2022-11-29 | 2022-12-12 | Solar | 890 | 420D6 | HOTEL ROAD | 420T1 | 2022-12-13 | Fail | Pass | 2023-02-23
82564 | 2022-11-23 | 2022-12-12 | Solar | 1950 | 693D1 | SCARBOROUGH | 693T1 | 2023-02-13 | Fail |  |  | Yes
82547 | 2022-11-21 | 2022-11-30 | Fuel Cell | 975 | 421D2 | CHALLENGER | 421T1 |  | Fail |  |  | Yes
82518 | 2022-11-16 | 2022-11-29 | Fuel Cell | 975 | 424D4 | LEWISTON LOWER | 424T3 | 2023-01-13 | Pass
82496 | 2022-11-14 | 2022-11-18 | Fuel Cell | 975 | 688D1 | KITTERY | 688T1 | 2023-01-15 | Fail |  |  | Yes
82499 | 2022-11-14 | 2022-11-29 | Solar | 500 | 233D2 | MANCHESTER | 233T1 | 2022-11-30 | Fail | Pass | 2023-05-01
82486 | 2022-11-07 | 2022-11-30 | Fuel Cell | 975 | 630D2 | GOOSEFARE | 630T1 | 2023-01-06 | Pass
82485 | 2022-11-05 | 2022-11-30 | Fuel Cell | 975 | 420D6 | HOTEL ROAD | 420T1 | 2023-01-09 | Pass
82455 | 2022-11-03 | 2022-12-05 | Solar | 100 | 250D2 | TOPSHAM | 250T2 | 2023-05-10 | Pass | Pass | 2023-02-13
82439 | 2022-11-01 | 2022-11-01 | Solar | 950 | 858D4 | STURTEVANT | 858T2 | 2022-11-01 | Pass
82404 | 2022-10-26 | 2022-11-15 | Solar | 750 | 445D1 | RAYMOND 115 KV | 445T1 | 2022-11-17 | Fail |  | 2023-06-21 | Yes
82373 | 2022-10-21 | 2022-11-01 | Solar | 104.16 | 245D2 | STICKNEYS CORNER | 245T1 | 2022-11-02 | Fail | Pass | 2023-02-01
82363 | 2022-10-20 | 2022-11-16 | Fuel Cell | 975 | 636D2 | MUSSEY ROAD | 636T1 | 2022-12-27 | Fail |  |  | Yes
82366 | 2022-10-20 | 2022-10-24 | Solar | 996 | 657D4 | SANFORD SWITCH | 657T1 | 2022-12-27 | Fail | Pass | 2023-04-18
82339 | 2022-10-18 | 2022-11-14 | Solar | 975 | 841D1 | PHILLIPS/STRONG | 841T1 | 2023-01-25 | Fail | Pass | 2023-02-23
82340 | 2022-10-18 | 2022-12-02 | Solar | 975 | 839D2 | OAKLAND | 839T1 | 2022-12-02 | Fail | Fail | 2023-03-30 | Yes
82322 | 2022-10-17 | 2022-10-19 | Solar | 995 | 667D1 | SOUTH SANFORD | 667T2 | 2022-12-01 | Fail | Pass | 2023-03-22 | Yes
82324 | 2022-10-17 | 2022-10-17 | Solar | 975 | 450D1 | SABATTUS | 450T1 | 2022-11-22 | Fail | Fail | 2023-01-23 | Yes
82261 | 2022-10-05 | 2022-11-01 | Solar | 950 | 858D4 | STURTEVANT | 858T2 | 2022-11-02 | Pass
82255 | 2022-10-04 | 2022-10-04 | Solar | 975 | 821D1 | GUILFORD | 821T1 | 2022-10-14 | Fail | Pass | 2023-02-07
82233 | 2022-09-27 | 2022-10-04 | Solar | 100 | 659D9 | SEWALL STREET | 659T2 | 2022-10-12 | Pass
82226 | 2022-09-23 | 2022-09-27 | Solar | 349.998 | 813D1 | DEXTER | 813T1 | 2022-09-28 | Pass |  |  | Yes
82201 | 2022-09-20 | 2022-09-30 | Solar | 390 | 261D3 | BATH 34 | 261T2 | 2022-10-06 | Fail | Pass | 2022-11-30
82202 | 2022-09-20 | 2022-12-02 | Solar | 996 | 407D1 | BRYANT POND | 407T1 | 2022-12-05 | Fail |  |  | Yes
82186 | 2022-09-15 | 2022-10-03 | Solar | 348 | 250D1 | TOPSHAM | 250T2 | 2022-10-03 | Fail |  |  | Yes
82151 | 2022-09-09 | 2022-09-09 | Solar | 160 | 213D3 | BRUNSWICK WEST SIDE | 213T1 | 2022-09-23 | Pass
82152 | 2022-09-09 | 2022-09-12 | Solar | 260 | 273D4 | BRUNSWICK HYDRO | 273T2 | 2022-10-04 | Fail | Pass | 2023-01-23
82143 | 2022-09-08 | 2022-09-30 | Solar | 228 | 860D1 | UNITY | 860T1 | 2023-03-09 | Fail |  |  | Yes
82084 | 2022-08-29 | 2022-09-09 | Solar | 1000 | 416D1 | GRAY | 416T2 | 2022-10-07 | Fail | Fail |  | Yes
82055 | 2022-08-25 | 2022-12-01 | Solar | 275 | 823D2 | HARRIS | 823T5 | 2023-02-24 | Pass
82053 | 2022-08-23 | 2022-08-23 | Solar | 1000 | 846D1 | PROSPECT | 846T1 | 2022-09-02 | Fail | Pass | 2022-11-11
82010 | 2022-08-15 | 2022-08-18 | Solar/Battery | 996 | 445D1 | RAYMOND 115 KV | 445T1 | 2022-08-22 | Fail | Fail | 2022-09-21 | Yes
82007 | 2022-08-12 | 2022-08-30 | Solar | 1875 | 272D4 | NORTH AUGUSTA | 272T1 | 2022-09-14 | Fail | Fail | 2022-11-08 | Yes
81972 | 2022-08-10 | 2022-08-17 | Solar | 975 | 246D2 | THOMASTON CREEK | 246T1 | 2022-09-09 | Fail | Fail | 2022-10-21 | Yes
81959 | 2022-08-08 | 2022-09-14 | Solar | 2000 | 431D2 | MECHANIC FALLS | 431T1 | 2022-09-13 | Fail | Fail |  | Yes
81960 | 2022-08-08 | 2022-09-28 | Solar | 749 | 860D2 | UNITY | 860T1 | 2022-10-05 | Fail | Fail | 2022-11-21 | Yes
81961 | 2022-08-08 | 2022-09-28 | Solar | 749 | 209D3 | BOOTHBAY HARBOR | 209T1 | 2022-09-30 |  |  |  | Yes
81963 | 2022-08-08 | 2022-08-08 | Solar | 749 | 250D1 | TOPSHAM | 250T2 | 2022-09-02 | Fail | Pass | 2022-11-02
81964 | 2022-08-08 | 2022-09-28 | Solar | 749 | 817D3 | FAIRFIELD | 817T1 | 2022-09-30 |  |  |  | Yes
81965 | 2022-08-08 | 2022-08-15 | Solar | 749 | 438D1 | PAPOOSE POND | Tap off of Transmission Line | 2022-09-12 | Fail | Pass | 2022-12-12
81966 | 2022-08-08 | 2022-08-15 | Solar | 749 | 850D2 | SEARSPORT | 850T1 | 2022-09-14 | Fail | Pass | 2022-12-13
81967 | 2022-08-08 | 2022-08-15 | Solar | 749 | 837D2 | NEWPORT | 837T2 | 2022-08-29 | Fail | Fail | 2023-01-16 | Yes
81968 | 2022-08-08 | 2022-08-15 | Solar | 749 | 861D9 | VASSALBORO | 861T1 | 2022-09-13 | Fail | Fail | 2022-11-06 | Yes
81956 | 2022-08-05 | 2022-08-11 | Solar | 725 | 412D3 | DEER RIPS | 412T4 | 2022-09-13 | Pass
81957 | 2022-08-05 | 2022-08-11 | Solar | 725 | 412D3 | DEER RIPS | 412T4 | 2022-09-26 | Fail | Fail | 2022-11-21 | Yes
81958 | 2022-08-05 | 2022-08-12 | Solar | 2000 | 602D2 | BASSETT | 602T1 | 2022-08-29 | Fail | Pass | 2022-11-02 | Yes
81947 | 2022-08-04 | 2022-08-15 | Solar | 153.6 | 251D1 | UNION | 251T1 | 2022-08-29 | Fail |  | 2022-10-10 | Yes
81955 | 2022-08-04 | 2022-08-11 | Solar | 450 | 811D1 | CORINNA | 811T1 | 2022-08-30 | Pass |  |  | Yes
81945 | 2022-08-03 | 2022-08-08 | Solar | 500 | 866D2 | WESTON | 866T2 | 2022-10-04 | Pass |  |  | Yes
81942 | 2022-08-02 | 2022-08-08 | Solar | 996 | 470D1 | SAND ROAD TAP | 470T1 | 2022-08-09 | Fail | Pass | 2022-09-27
81911 | 2022-07-29 | 2022-08-05 | Solar | 530 | 861D9 | VASSALBORO | 861T1 | 2022-08-31 | Fail | Pass | 2022-10-12
81910 | 2022-07-27 | 2022-08-04 | Solar | 996 | 861D9 | VASSALBORO | 861T1 | 2022-08-11 | Fail | Fail | 2022-10-05 | Yes
81908 | 2022-07-26 | 2022-08-04 | Solar | 165 | 252D2 | WALDOBORO | 252T1 |  |  |  |  | Yes
81909 | 2022-07-26 | 2022-08-04 | Solar | 996 | 837D2 | NEWPORT | 837T2 | 2022-08-29 | Fail |  | 2022-10-03 | Yes
81849 | 2022-07-25 | 2022-08-01 | Solar | 996 | 438D1 | PAPOOSE POND | Tap off of Transmission Line | 2022-08-24 | Fail | Fail | 2022-10-10 | Yes
81850 | 2022-07-25 | 2022-08-12 | Solar | 996 | 850D2 | SEARSPORT | 850T1 | 2022-09-06 | Fail | Fail | 2022-10-17 | Yes
81851 | 2022-07-25 | 2022-08-25 | Solar | 2000 | 667D1 | SOUTH SANFORD | 667T2 | 2022-10-12 | Fail |  |  | Yes
81852 | 2022-07-25 |  | Solar | 1700 | 626D1 | HIGH STREET | 626T1 |  |  |  |  | Yes
81894 | 2022-07-25 | 2022-08-15 | Solar | 999 | 866D2 | WESTON | 866T2 | 2022-08-29 | Fail | Fail | 2022-09-21 | Yes
81895 | 2022-07-25 | 2022-08-15 | Solar | 400 | 454D2 | TURNER | 454T1 | 2022-08-25 | Pass
81896 | 2022-07-25 | 2022-08-01 | Solar | 730 | 412D3 | DEER RIPS | 412T4 | 2022-08-01 | Fail |  |  | Yes
81847 | 2022-07-21 |  |  | 210 | 638D2 | NORTH LIMINGTON | 638T1 |  |  |  |  | Yes
81848 | 2022-07-21 | 2022-07-21 | Solar | 850 | 412D3 | DEER RIPS | 412T4 | 2022-08-29 | Fail | Fail | 2022-10-17 | Yes
81817 | 2022-07-20 | 2022-07-27 | Solar | 1000 | 837D2 | NEWPORT | 837T2 | 2022-08-29 | Fail | Fail | 2022-10-10 | Yes
81819 | 2022-07-20 | 2022-07-27 | Solar | 999 | 821D3 | GUILFORD | 821T2 | 2022-09-13 | Fail | Pass | 2022-11-02
81816 | 2022-07-19 | 2022-07-25 | Solar | 996 | 860D2 | UNITY | 860T1 | 2022-08-02 | Fail |  | 2022-09-02 | Yes
81815 | 2022-07-18 | 2022-08-02 | Solar | 124 | 225D4 | FREEPORT | 225T1 | 2022-08-16 | Fail |  |  | Yes
81810 | 2022-07-15 | 2022-07-22 | Solar | 996 | 209D3 | BOOTHBAY HARBOR | 209T1 | 2022-08-18 | Fail | Pass | 2022-10-05
81811 | 2022-07-15 | 2022-07-22 | Solar | 996 | 250D1 | TOPSHAM | 250T2 | 2022-08-18 | Fail |  |  | Yes
81812 | 2022-07-15 | 2022-07-22 | Solar | 996 | 817D3 | FAIRFIELD | 817T1 | 2022-08-18 | Fail |  | 2022-09-07 | Yes
81754 | 2022-07-08 | 2022-07-12 | Solar | 190 | 457D2 | MONMOUTH | 457T2 | 2022-07-27 | Pass |  |  | Yes
81752 | 2022-07-01 | 2022-07-12 | Solar | 540 | 250D2 | TOPSHAM | 250T2 | 2022-07-25 | Fail | Pass | 2022-09-13
81680 | 2022-06-24 | 2022-07-08 | Solar | 466 | 255D2 | WEST STREET | 255T1 | 2022-08-01 | Pass
81653 | 2022-06-21 | 2022-06-27 | Solar | 115.2 | 470D1 | SAND ROAD TAP | 470T1 | 2022-07-08 | Pass
81675 | 2022-06-21 | 2022-06-27 | Solar | 990 | 431D1 | MECHANIC FALLS | 431T2 | 2022-07-08 | Fail |  |  | Yes
81676 | 2022-06-21 | 2022-06-29 | Solar | 875 | 412D3 | DEER RIPS | 412T4 | 2022-07-27 | Fail |  |  | Yes
81677 | 2022-06-21 | 2022-06-29 | Solar | 875 | 412D3 | DEER RIPS | 412T4 | 2022-07-27 | Fail |  |  | Yes
81678 | 2022-06-21 | 2022-06-29 | Solar | 1000 | 858D4 | STURTEVANT | 858T2 | 2022-08-01 | Fail |  |  | Yes
81679 | 2022-06-21 | 2022-06-29 | Solar | 1000 | 858D4 | STURTEVANT | 858T2 | 2022-08-01 | Fail |  |  | Yes
81628 | 2022-06-17 | 2022-06-24 | Solar | 244 | 839D2 | OAKLAND | 839T1 | 2022-07-09 | Pass |  |  | Yes
81512 | 2022-06-02 | 2022-06-08 | Solar | 975 | 852D1 | SHAWMUT | 852T3 | 2022-06-15 | Fail | Fail |  | Yes
81513 | 2022-06-02 | 2022-06-08 | Solar | 975 | 873D1 | COUNTY RD (RICE RIPS) | 873T1 | 2022-06-15 | Fail | Pass | 2022-09-01
81515 | 2022-06-02 | 2022-06-08 | Solar | 975 | 873D1 | COUNTY RD (RICE RIPS) | 873T1 | 2022-06-27 | Fail |  |  | Yes
81516 | 2022-06-02 | 2022-06-08 | Solar | 975 | 454D2 | TURNER | 454T1 | 2022-06-15 | Fail |  |  | Yes
81506 | 2022-05-31 | 2022-06-06 | Solar | 975 | 870D1 | WINSLOW | 870T4 | 2022-07-06 | Fail |  | 2022-10-11 | Yes
81508 | 2022-05-31 | 2022-06-06 | Solar | 975 | 853D1 | SKOWHEGAN NORTH SIDE | 853T1 | 2022-06-15 | Fail |  |  | Yes
81509 | 2022-05-31 | 2022-06-06 | Solar | 975 | 853D1 | SKOWHEGAN NORTH SIDE | 853T1 | 2022-06-15 | Fail |  |  | Yes
81511 | 2022-05-31 | 2022-06-06 | Solar | 350 | 866D2 | WESTON | 866T2 | 2022-07-19 | Pass
81489 | 2022-05-27 | 2022-05-31 | Solar | 475 | 412D3 | DEER RIPS | 412T4 | 2022-06-08 | Pass
81435 | 2022-05-26 | 2022-06-01 | Solar | 975 | 412D3 | DEER RIPS | 412T4 | 2022-06-08 | Fail |  |  | Yes
81465 | 2022-05-26 | 2022-06-01 | Solar | 900 | 255D2 | WEST STREET | 255T1 | 2022-06-15 | Fail |  |  | Yes
81413 | 2022-05-23 | 2022-05-24 | Solar | 975 | 870D1 | WINSLOW | 870T4 | 2022-06-08 | Fail |  |  | Yes
81409 | 2022-05-20 | 2022-05-27 | Solar | 200 | 237D1 | MCCOYS | 237T1 | 2022-06-17 | Pass |  |  | Yes
81396 | 2022-05-19 | 2022-05-23 | Solar | 337.5 | 603D2 | BERWICK | 603T1 | 2022-08-11 | Fail | Pass | 2022-10-31
81395 | 2022-05-17 | 2022-06-06 | Solar | 975 | 457D2 | MONMOUTH | 457T2 | 2022-06-08 | Fail |  |  | Yes
81393 | 2022-05-16 | 2022-05-31 | Solar | 125 | 647D1 | PRIDES CORNER | 647T2 | 2022-06-14 | Pass
81394 | 2022-05-16 | 2022-05-23 | Solar | 975 | 457D2 | MONMOUTH | 457T2 | 2022-06-10 | Fail | Pass | 2022-07-29
81270 | 2022-05-09 | 2022-05-13 | Solar | 104.1 | 430D1 | LOVELL | 430T1 |  |  |  |  | Yes
81265 | 2022-05-03 | 2022-05-09 | Solar | 975 | 839D2 | OAKLAND | 839T1 | 2022-05-26 | Fail |  |  | Yes
81267 | 2022-05-03 | 2022-07-14 | Solar | 975 | 839D2 | OAKLAND | 839T1 | 2022-05-26 | Fail |  |  | Yes
81262 | 2022-05-02 | 2022-05-09 | Solar | 975 | 663D2 | SOUTH BERWICK | 663T1 | 2022-06-22 | Fail |  |  | Yes
81264 | 2022-05-02 | 2022-05-09 | Solar | 150 | 821D1 | GUILFORD | 821T1 | 2022-08-30 | Pass
81490 | 2022-04-30 | 2022-05-05 | Solar | 800 | 263D1 | BOWMAN STREET | 34kV BUS 2 | 2022-06-15 | Pass | Pass | 2022-08-16
81259 | 2022-04-29 | 2022-04-29 | Solar | 975 | 638D2 | NORTH LIMINGTON | 638T1 | 2022-07-06 | Fail |  |  | Yes
81260 | 2022-04-29 | 2022-05-05 | Solar | 650 | 861D9 | VASSALBORO | 861T1 | 2022-06-02 | Pass |  |  | Yes
81257 | 2022-04-28 | 2022-05-05 | Solar | 999 | 638D1 | NORTH LIMINGTON | 638T1 |  |  |  |  | Yes
81258 | 2022-04-28 | 2022-05-16 | Solar | 975 | 638D2 | NORTH LIMINGTON | 638T1 | 2022-07-06 | Fail |  |  | Yes
81223 | 2022-04-25 | 2022-04-25 | Other | 350 | 435D1 | NORWAY | 435T2 | 2022-07-21 | Pass
81222 | 2022-04-21 | 2022-04-29 | Solar | 975 | 663D2 | SOUTH BERWICK | 663T1 | 2022-07-06 | Fail |  |  | Yes
81170 | 2022-04-20 | 2022-04-27 | Solar | 750 | 695D2 | LEBANON | 695T1 | 2022-05-05 | Fail |  |  | Yes
81171 | 2022-04-20 | 2022-04-25 | Solar | 850 | 631D1 | LAMBERT STREET | 631T1 | 2022-07-08 | Fail | Pass | 2022-08-18
81179 | 2022-04-20 | 2022-04-27 | Solar | 750 | 695D2 | LEBANON | 695T1 | 2022-05-26 | Fail |  |  | Yes
81200 | 2022-04-20 | 2022-04-27 | Solar | 975 | 841D1 | PHILLIPS/STRONG | 841T1 | 2022-05-19 | Fail | Pass | 2022-07-21
81201 | 2022-04-20 | 2022-04-27 | Solar | 975 | 457D1 | MONMOUTH | 457T1 | 2022-05-17 | Fail | Pass | 2022-08-02
81203 | 2022-04-20 | 2022-04-27 | Solar | 975 | 841D1 | PHILLIPS/STRONG | 841T1 | 2022-05-18 | Fail |  |  | Yes
81132 | 2022-04-13 | 2022-04-15 | Solar | 172 | 874D1 | BELFAST 115 | 874T2 | 2022-05-27 | Pass |  |  | Yes
81130 | 2022-04-03 | 2022-04-15 | Solar | 975 | 225D4 | FREEPORT | 225T1 | 2022-06-02 | Fail | Pass | 2022-08-03 | Yes
81019 | 2022-03-30 | 2022-04-07 | Solar | 975 | 225D4 | FREEPORT | 225T1 | 2022-04-08 | Fail |  |  | Yes
81015 | 2022-03-29 | 2022-04-04 | Solar | 650 | 861D9 | VASSALBORO | 861T1 | 2022-04-28 | Fail |  |  | Yes
81016 | 2022-03-29 | 2022-04-04 | Solar | 280 | 865D5 | WEST WATERVILLE | 865T2 | 2022-05-17 | Fail | Pass | 2022-06-27
81017 | 2022-03-29 | 2022-04-07 | Solar | 500 | 444D2 | RAYMOND 34 KV | 444T1 | 2022-04-25 | Fail | Pass | 2022-08-12 | Yes
81006 | 2022-03-25 | 2022-04-21 | Solar | 475 | 239D10 | PARK STREET | 239T5 | 2022-05-19 | Pass |  |  | Yes
80962 | 2022-03-22 | 2022-03-22 | Solar | 975 | 244D2 | SOUTH CHINA | 244T1 | 2022-04-19 | Fail |  |  | Yes
80971 | 2022-03-22 | 2022-03-29 | Solar | 975 | 244D2 | SOUTH CHINA | 244T1 | 2022-04-29 | Fail | Pass | 2022-07-29 | Yes
80892 | 2022-03-21 | 2022-03-25 | Solar | 975 | 239D10 | PARK STREET | 239T5 | 2022-05-17 | Pass
80977 | 2022-03-21 | 2022-03-31 | Solar | 2000 | 457D2 | MONMOUTH | 457T2 | 2022-04-21 | Fail |  |  | Yes
80842 | 2022-03-02 | 2022-03-17 | Solar | 975 | 450D1 | SABATTUS | 450T1 | 2022-04-15 | Fail |  |  | Yes
80841 | 2022-03-01 | 2022-03-08 | Solar | 1990 | 801D1 | ANSON | 801T1 | 2022-03-29 | Fail |  |  | Yes
80838 | 2022-02-28 | 2022-03-17 | Solar | 1992 | 806D2 | BUCKSPORT | 806T3 | 2022-03-30 | Fail | Pass | 2022-06-25 | Yes
80825 | 2022-02-24 | 2022-03-09 | Solar | 1999 | 233D2 | MANCHESTER | 233T1 | 2022-03-30 | Fail | Fail | 2022-05-17 | Yes
80807 | 2022-02-16 | 2022-02-23 | Solar | 975 | 817D3 | FAIRFIELD | 817T1 | 2022-03-03 | Fail |  |  | Yes
80808 | 2022-02-16 | 2022-02-23 | Solar | 975 | 861D8 | VASSALBORO | 861T1 | 2022-03-29 | Fail | Fail | 2022-05-19 | Yes
80726 | 2022-02-04 | 2022-02-09 | Solar | 975 | 853D1 | SKOWHEGAN NORTH SIDE | 853T1 | 2022-03-28 | Fail |  |  | Yes
80727 | 2022-02-04 | 2022-02-09 | Solar | 975 | 874D1 | BELFAST 115 | 874T2 | 2022-03-07 | Fail |  |  | Yes
80728 | 2022-02-04 | 2022-02-10 | Solar | 975 | 428D3 | LIVERMORE FALLS | 428T1 | 2022-03-04 | Fail | Fail | 2022-06-03 | Yes
80736 | 2022-02-04 | 2022-02-10 | Solar | 975 | 420D7 | HOTEL ROAD | 420T1 | 2022-03-28 | Pass
80737 | 2022-02-04 | 2022-02-09 | Solar | 975 | 420D4 | HOTEL ROAD | 420T1 | 2022-03-03 | Fail |  |  | Yes
80725 | 2022-02-03 | 2022-02-09 | Solar | 975 | 866D2 | WESTON | 866T2 | 2022-02-11 | Fail |  |  | Yes
80701 | 2022-01-31 | 2022-02-04 | Solar | 1750 | 850D1 | SEARSPORT | 850T1 | 2022-02-10 | Fail | Fail | 2022-04-18 | Yes
80677 | 2022-01-26 | 2022-02-02 | Solar | 200 | 693D2 | SCARBOROUGH | 693T1 | 2022-04-06 | Fail | Pass | 2022-05-23
80667 | 2022-01-25 | 2022-02-01 | Solar | 499 | 420D7 | HOTEL ROAD | 420T1 | 2022-02-10 | Pass
80656 | 2022-01-20 | 2022-01-27 | Solar | 200 | 650D1 | RIGBY | 650T1 | 2022-02-17 | Pass
80658 | 2022-01-20 | 2022-01-27 | Solar | 436 | 650D1 | RIGBY | 650T1 | 2022-02-10 | Fail | Pass | 2022-06-06 | Yes
80659 | 2022-01-20 | 2022-01-27 | Solar | 516 | 650D1 | RIGBY | 650T1 | 2022-02-17 | Pass
80609 | 2022-01-13 | 2022-01-20 | Solar | 1999 | 263D1 | BOWMAN STREET | 34kV BUS 2 | 2022-01-21 | Fail | Pass | 2022-05-16 | Yes
80605 | 2022-01-12 | 2022-01-31 | Solar | 1500 | 412D4 | DEER RIPS | 412T4 | 2022-02-10 | Fail | Fail | 2022-05-12 | Yes
80585 | 2022-01-04 | 2022-01-11 | Solar | 1000 | 861D9 | VASSALBORO | 861T1 | 2022-01-21 | Fail | Pass | 2022-06-20 | Yes

## Comments
Row 3 | Followed up on AOR(Incomplete) 5/16/2025 | Andrew Jackson | 05/16/25 10:58 AM
Row 24 | 4/17/2025 Withdrawn | Kaiya Hoogkamp | 04/17/25 10:31 AM
Row 25 | 4/17/2025 Withdrawn | Kaiya Hoogkamp | 04/17/25 10:32 AM
Row 26 | 105711 | Kaiya Hoogkamp | 04/17/25 10:32 AM
Row 26 | Additional invoice created for remaining application payment balance, $1996.00 | Kaiya Hoogkamp | 03/18/25 9:23 AM
Row 27 | Additional invoice created for remaining application payment balance, $1996.00 | Kaiya Hoogkamp | 03/18/25 9:23 AM
Row 30 | Draft 0000001119 refund issued via ACH on 5/2/2025 | Kaiya Hoogkamp | 05/02/25 8:37 AM
Row 30 | Adjusted Ombudsman fee invoice to $0.00 910265697 | Kaiya Hoogkamp | 05/01/25 9:28 AM
Row 30 | Adjusted app invoice to $0.00 910264462 | Kaiya Hoogkamp | 04/22/25 4:06 PM
Row 30 | 4/2/25 app withdrawn. | Kaiya Hoogkamp | 04/02/25 3:06 PM
Row 31 | 3/19/25 Application withdrawn. Failed technical screen and will fail and ESA. Advised to proceed with level 4. | Kaiya Hoogkamp | 03/19/25 1:12 PM
Row 32 | DO NOT EXECUTE IA OR COC UNTIL OMBUDSMAN FEE IS PAID | Kaiya Hoogkamp | 05/07/25 11:45 AM
Row 33 | DO NOT EXECUTE IA OR COC UNTIL OMBUDSMAN FEE IS PAID | Kaiya Hoogkamp | 05/07/25 11:46 AM
Row 34 | 3/19/25 Application withdrawn. Failed technical screen and will fail and ESA. Advised to proceed with level 4. | Kaiya Hoogkamp | 03/19/25 12:55 PM
Row 35 | 3/19/25 Application withdrawn. Failed technical screen and will fail and ESA. Advised to proceed with level 4. | Kaiya Hoogkamp | 03/19/25 1:03 PM
Row 39 | 2/26/25 emailed template to apply $1500 from previous ESA to this new PIA invoice | Kaiya Hoogkamp | 02/26/25 4:09 PM
Row 39 | If they go forward with the ESA we need to zero out previous ESA invoice and move funds to this new ESA | Kaiya Hoogkamp | 02/21/25 12:07 PM
Row 39 | Adjusted to $0.00 invoice 910253996 | Kaiya Hoogkamp | 02/18/25 1:12 PM
Row 39 | App fee is waived, previous project, 104609, could not be completed due to a level 4 study. We waived app fee and ESA fee (move fee from previous project to new project). | Kaiya Hoogkamp | 02/17/25 10:33 AM
Row 43 | 2/13/25 customer submitted payment and it was received. Opening the project up instead of reapplication. | Kaiya Hoogkamp | 02/13/25 8:20 AM
Row 43 | 2/11/25 project withdrawn, failure to pay application fee and unresponsive to outreach. | Kaiya Hoogkamp | 02/11/25 9:15 AM
Row 44 | Application late past AOR complete date due to developer delay sending application payment. | Kaiya Hoogkamp | 02/11/25 3:05 PM
Row 44 | Developer provided documentation of wire that was sent on 2/10/2025, reopened the application. | Kaiya Hoogkamp | 02/11/25 2:59 PM
Row 44 | 2/11/25 project withdrawn, failure to pay application fee and unresponsive to outreach. | Kaiya Hoogkamp | 02/11/25 9:14 AM
Row 49 | 1/29/25 offered one time extention to 2/5/2025 waiting for wire payment. | Kaiya Hoogkamp | 01/29/25 3:52 PM
Row 50 | 0000000189 is the draft refund | Kaiya Hoogkamp | 05/16/25 9:31 AM
Row 50 | 4/16/25 application withdrawn. Project unresponsive to outreach after technical screen failure. | Kaiya Hoogkamp | 04/16/25 8:16 AM
Row 52 | The developer advised this project was submitted in error and is withdrawn. | Kaiya Hoogkamp | 12/23/24 11:49 AM
Row 56 | $187.64 invoice 910266466/920289826 | Kaiya Hoogkamp | 05/07/25 9:24 AM
Row 56 | Additional $187.64 invoice received. Sent to workf flow 5/6/25. Per Dante "Project 104903 – the additional two hours were for a peer review. Its dated near the start of the month and on the other its dated at the end of the month so it must have been missed because it was split between the two invoices. " | Kaiya Hoogkamp | 05/06/25 10:21 AM
Row 56 | Original IA for incorrect $2500 910250371/ 920272691 Updated PIA to $1500 910250593/920272951 | Kaiya Hoogkamp | 01/21/25 3:17 PM
Row 59 | Developer is proposing a utility owned 750 kVA Pad mounted transformer. This will exceed the $30,000 Level 2 Threshold and will need to go to a level 4 study. | Nathan Lawrence | 12/17/24 1:56 PM
Row 59 | AOR complete delayed due to customer, waiting for payment to be received. | Kaiya Hoogkamp | 12/13/24 10:41 AM
Row 60 | TS Failed due to costs for proposed upgrades. | Nathan Lawrence | 01/08/25 10:10 AM
Row 60 | AOR complete delayed due to customer, waiting for payment to be received. | Kaiya Hoogkamp | 12/13/24 10:42 AM
Row 61 | AOR complete delayed due to customer, waiting for payment to be received. | Kaiya Hoogkamp | 12/13/24 10:42 AM
Row 62 | AOR complete delayed due to customer, waiting for payment to be received. | Kaiya Hoogkamp | 12/13/24 10:41 AM
Row 63 | AOR complete delayed due to customer, waiting for payment to be received. | Kaiya Hoogkamp | 12/13/24 10:41 AM
Row 64 | 12/4/2024 informed developer we needed to terminate ESA and withdraw project due to level 4 PRJ 308 being in study. | Kaiya Hoogkamp | 05/14/25 9:11 AM
Row 64 | terminated contract on 3/11/25 | Kaiya Hoogkamp | 03/11/25 1:21 PM
Row 65 | Withdrawn on 1/2/2025 | Kaiya Hoogkamp | 01/27/25 8:32 AM
Row 68 | 12/2/2024 customer requested to withdraw, as they have not finalized the SLD. | Kaiya Hoogkamp | 12/02/24 11:47 AM
Row 72 | 11/7/24 application failed technical screen and was advised it would fail addtional screening. Application withdrew and will reapply as a level 4. | Kaiya Hoogkamp | 11/07/24 11:13 AM
Row 73 | 12/4/2024 customer has withdrawn and will apply as a level 4 | Kaiya Hoogkamp | 12/04/24 12:19 PM
Row 75 | Application Fee waived, this is a resubmission for original application 101658 | Kaiya Hoogkamp | 09/25/24 12:11 PM
Row 78 | Holding COC due to problems with the phone line. CMP cannot connect to the meter. | Nathan Lawrence | 03/11/25 1:32 PM
Row 79 | 9/3/2024 app withdrawn, it incorrectly applied as a level 2, it needs to be a level 4. Customer advised of this. | Kaiya Hoogkamp | 09/03/24 9:54 AM
Row 81 | MANUAL PORTAL APPLICATION | Kaiya Hoogkamp | 09/23/24 12:15 PM
Row 82 | Original projects 103022 ($1060) and 103021 ($200). $1060+$200 = $1260. The NEW app total is $1180. $1180 - $1260 = -$80 is due to the customer as a refund. | Kaiya Hoogkamp | 08/07/24 3:02 PM
Row 83 | Original projects 103019 ($250 payment valid) and 103017 (project went to tech screen). App total is $350. Minus the $250 availible = $100 due | Kaiya Hoogkamp | 08/07/24 2:54 PM
Row 84 | Original projects 103016 & 103014, both projects went through tech screen, so full app total of $400 is due | Kaiya Hoogkamp | 08/07/24 2:39 PM
Row 86 | 9/30/2024 ESA failed, project withdrawn | Kaiya Hoogkamp | 10/31/24 10:37 AM
Row 86 | 8/23/24 resent ESA for new signatures, with a date line added next to customer signature | Kaiya Hoogkamp | 08/23/24 11:41 AM
Row 87 | 8/6/24 withdrawn, project being combined. | Kaiya Hoogkamp | 08/06/24 3:13 PM
Row 88 | 8/12/2024 failed ESA, project withdrawn | Kaiya Hoogkamp | 08/12/24 3:17 PM
Row 89 | 8/6/24 withdrawn, project being combined. | Kaiya Hoogkamp | 08/12/24 3:19 PM
Row 90 | 8/23/2024 project withdrawn after failing ESA | Kaiya Hoogkamp | 10/15/24 1:48 PM
Row 91 | 10/2/2024 ESA failed and project withdrawn. | Kaiya Hoogkamp | 10/15/24 1:54 PM
Row 91 | 7/30 invoice adjustment to make it $2050, funds are on debtor. Need to wait for adjustment invoice before entering IT ticket to clear. 910231855 | Kaiya Hoogkamp | 09/12/24 3:21 PM
Row 92 | 8/28/2024 ESA failed, project withdrawn. | Kaiya Hoogkamp | 10/15/24 1:56 PM
Row 94 | 9/3/2024 ESA failed, project withdrawn. | Kaiya Hoogkamp | 10/15/24 1:57 PM
Row 95 | Kaiya Hoogkamp 4/7/25 email for IA sent. 30 BD 5/20/2025 | Kaiya Hoogkamp | 04/07/25 8:43 AM
Row 97 | 8/12/2024 project withdrawn, failed ESA | Kaiya Hoogkamp | 08/13/24 3:18 PM
Row 104 | 6/14/2024 customer advsied they are withdrawing and reapplying as a level 4. They did not mean to apply as a level 2. | Kaiya Hoogkamp | 06/14/24 10:33 AM
Row 106 | Application delayed AOR complete due to customer waiting for PE stamp on their SLD | Kaiya Hoogkamp | 07/10/24 2:09 PM
Row 108 | 6/18/2024 customer confirmed they are withdrawing after failing technical screen and reapplying as a level 4. | Kaiya Hoogkamp | 06/18/24 10:22 AM
Row 109 | 6/10/24 customer failed technical screen and requested to withdraw | Kaiya Hoogkamp | 06/10/24 10:34 AM
Row 110 | kWh, No on-site load | Nathan Lawrence | 08/01/24 1:18 PM
Row 112 | 7/16/2024 project emailed to confirm withdrawn after failing technical screen | Kaiya Hoogkamp | 07/17/24 8:25 AM
Row 114 | 6/5/2024 project failed tech screen and requested to withdraw and reapply as level 4. | Kaiya Hoogkamp | 10/15/24 2:11 PM
Row 116 | 120006528 terminated contract, ESA was never performed. | Kaiya Hoogkamp | 03/10/25 1:51 PM
Row 116 | 7/16/2024 application withdrawn as we cannot perform the level 2 ESA at this time. Refund has been issued. 0000001479 | Kaiya Hoogkamp | 07/16/24 3:34 PM
Row 117 | Additional ESA Invoice 910265922/920289270 for $656.73, additional study charges that were initially missed from Dante due to being out at the time. | Kaiya Hoogkamp | 05/02/25 11:49 AM
Row 119 | 6/28/2024 ESA failed, project withdrawn. | Kaiya Hoogkamp | 10/15/24 2:14 PM
Row 120 | 5/23/2024 ESA failed, project withdrawn. | Kaiya Hoogkamp | 10/15/24 2:15 PM
Row 122 | Withdrawn 4/5/2024 Customer did not respond to multiple outreach attempts to provide required documents and payment to deem application complete. | Kaiya Hoogkamp | 04/05/24 10:13 AM
Row 123 | Withdrawn 4/5/2024 Customer did not respond to multiple outreach attempts to provide required documents and payment to deem application complete. | Kaiya Hoogkamp | 04/05/24 10:18 AM
Row 124 | No on-site load | Nathan Lawrence | 08/19/24 12:46 PM
Row 125 | Debit memo to offset Credit memo: 910265865/920289224 | Kaiya Hoogkamp | 05/02/25 9:46 AM
Row 125 | credit memo created to offset invoice 910263066/920286135. Credit Memo is 910264738/920288363 | Kaiya Hoogkamp | 04/24/25 10:48 AM
Row 125 | 5/21/2024 ESA failed, project withdrawn. | Kaiya Hoogkamp | 10/15/24 2:18 PM
Row 126 | Refunded thru credit of 811.24 given to Level4 PRJ 820 per Tyler | Thomas Blanchard | 03/06/25 8:32 AM
Row 127 | 5/1/2024 project failed ESA and withdrawn. | Kaiya Hoogkamp | 10/15/24 2:20 PM
Row 129 | 4/5/2024 Refund processed in SAP. | Kaiya Hoogkamp | 04/05/24 10:55 AM
Row 129 | INC3492935 entered to open up refund for $1500 ESA payment. The developer paid for an ESA even though they passed technical screen. | Kaiya Hoogkamp | 04/05/24 10:44 AM
Row 129 | 4/3/24 Customer has withdrawn due to construction issues. | Kaiya Hoogkamp | 04/03/24 11:07 AM
Row 130 | adjusted invoice 910253799 to $0.00 on 2/17/2025 | Kaiya Hoogkamp | 02/17/25 1:37 PM
Row 130 | 3/5/24 customer is withdrawing due to developer being no longer in business. Customer will apply again in the future with a new developer. | Kaiya Hoogkamp | 03/05/24 1:23 PM
Row 130 | 3/4/2024 emailed requesting update as today is day 10 | Kaiya Hoogkamp | 03/04/24 1:55 PM
Row 131 | 2/28/24 customer requested to withdraw and have refund issued, project did not go to technical screen and refund will be issued. | Kaiya Hoogkamp | 02/29/24 9:29 AM
Row 133 | 5/7/2024 project failed ESA and withdrawn. | Kaiya Hoogkamp | 10/15/24 2:26 PM
Row 135 | project withdrawn as it failed ESA on 4/12/2024 | Kaiya Hoogkamp | 04/29/24 9:10 AM
Row 137 | 5/16/2024 project withdrew and reapplied as level 4. | Kaiya Hoogkamp | 09/13/24 3:21 PM
Row 137 | 3/4 application complete delayed by customer - applied for 1000 kW AC then informed us it was 999 kW AC. Required updated SLD & Site plan with the change. Requested updated documents on 2/23/24 and received them 3/4/2024 | Kaiya Hoogkamp | 03/04/24 3:09 PM
Row 137 | currently missing required deration letter. CANNOT issue IA without this documentation 3/4/2024 | Kaiya Hoogkamp | 03/04/24 2:28 PM
Row 138 | Refund used as credit towards a Level4 invoice (PRJ820) per Tyler | Thomas Blanchard | 03/06/25 8:21 AM
Row 138 | 2/7/25 duplicate application fee of $2098 has been refunded. | Kaiya Hoogkamp | 02/07/25 8:22 AM
Row 138 | 5/7/2024 failed ESA, project withdrawn | Kaiya Hoogkamp | 08/26/24 2:39 PM
Row 140 | currently missing required deration letter. CANNOT issue IA without this documentation 3/4/2024 | Kaiya Hoogkamp | 03/04/24 1:27 PM
Row 141 | Refund request number: 0000001051 | Kaiya Hoogkamp | 05/14/25 8:51 AM
Row 141 | 4/19/2024 application withdrawn. | Kaiya Hoogkamp | 08/20/24 1:05 PM
Row 141 | 4/30/2024 refund reissued for $1152. Original amount to be refunded $1500 for ESA. However, there was an outstanding invoice for $348 on invoice 910212016/920232028. That has now been paid. | Kaiya Hoogkamp | 04/30/24 3:10 PM
Row 141 | 4/23 Refund updated to JUST the ESA fee of $1500. We will waive app fee if they reapply in the future. | Kaiya Hoogkamp | 04/23/24 12:31 PM
Row 141 | project withdrawn, cannot process ESA due to level 4 studies. | Kaiya Hoogkamp | 04/19/24 2:30 PM
Row 141 | 4/18/24 processed refuned for $2600 | Kaiya Hoogkamp | 04/18/24 3:28 PM
Row 141 | 910219227 invoice adjustment to adjust invoice to $0 in order to issue refund. We are refunding application and ESA fee due to project being unable to move forward due to level 4 applications. | Kaiya Hoogkamp | 04/16/24 3:26 PM
Row 141 | waiting to receive W-9 or email confirmation of financial responsiblity for the ESA before creating contract. Create the ESA in the portal | Kaiya Hoogkamp | 02/06/24 11:26 AM
Row 144 | 4/26/24 withdrawn after failing ESA | Kaiya Hoogkamp | 08/20/24 12:36 PM
Row 150 | portal contract 120006228 PIA 910212543 / 920232559. Created and cancelled 2/23/24. Portal contract and "old way" contract both made. | Kaiya Hoogkamp | 02/23/24 2:04 PM
Row 151 | 1/3/24 withdrawn after not responding within the 10 business day deadline | Kaiya Hoogkamp | 03/21/24 12:51 PM
Row 152 | 5/17/2024 project failed technical screen and withdrew. | Kaiya Hoogkamp | 10/15/24 2:39 PM
Row 153 | 2/9/2024 project failed ESA and withdrawn. | Kaiya Hoogkamp | 10/15/24 2:38 PM
Row 154 | Withdrawn 1/3/2024 after customer did not provide required documentation within the required 10 days and after an extention was granted. | Kaiya Hoogkamp | 03/21/24 11:39 AM
Row 156 | 4/9/2024 project withdrawn as it failed ESA. | Kaiya Hoogkamp | 04/29/24 9:07 AM
Row 159 | 6/7/2024 project withdrew | Kaiya Hoogkamp | 06/07/24 3:25 PM
Row 159 | 2/6 emailed customer asking for W-9 for New Sharon Community Solar or an email confirming Genie Solar Energy is financially responsible for ESA before we can create contract and PIA | Kaiya Hoogkamp | 02/06/24 10:41 AM
Row 162 | Rick tech screen, originally on time, but, contained wrong project size in TS, delay from Rick for updated TS with correct project size caused delay sent to customer | Kaiya Hoogkamp | 09/09/24 1:49 PM
Row 166 | 4/29/2024 failed ESA, project withdrawn | Kaiya Hoogkamp | 06/18/24 3:02 PM
Row 166 | Developer submitted 4 applications for same size all at once during transition to new portal, payments and additional documents were not all submitted at the same time. There was numerous back and forth with customer to ensure we received payments, export control and new account creation caused delays with the customer. Developer has worked in good faith to keep us informed as they worked to get all required documentation and payment. | Kaiya Hoogkamp | 01/24/24 2:50 PM
Row 167 | Refund draft: 0000000989 | Kaiya Hoogkamp | 05/14/25 8:47 AM
Row 167 | 4/24/2024 withdrawn | Kaiya Hoogkamp | 10/22/24 11:52 AM
Row 167 | 4/23 Refund updated to JUST the ESA fee of $2500. We will waive app fee if they reapply in the future. | Kaiya Hoogkamp | 04/23/24 12:21 PM
Row 167 | project withdrawn as it cannot go through ESA due to level 4 studies. | Kaiya Hoogkamp | 04/19/24 2:20 PM
Row 167 | $4640 refund issued for app fee and ESA. Project withdrawn | Kaiya Hoogkamp | 04/19/24 2:20 PM
Row 167 | 910219232 invoice adjustment to adjust invoice to $0 in order to issue refund. We are refunding application and ESA fee due to project being unable to move forward due to level 4 applications. | Kaiya Hoogkamp | 04/16/24 3:20 PM
Row 168 | Withdrawn 3/22 due to failing ESA | Kaiya Hoogkamp | 04/30/24 10:27 AM
Row 169 | 3/12/2024 project failed ESA and was withdrawn. | Kaiya Hoogkamp | 10/15/24 2:32 PM
Row 171 | 1/22/24 customer requested to withdraw project. | Kaiya Hoogkamp | 02/27/24 12:00 PM
Row 172 | 2/22/2024 failed ESA | Kaiya Hoogkamp | 07/23/24 3:18 PM
Row 174 | 1/11/2024 customer withdrew after technical screen. | Kaiya Hoogkamp | 07/23/24 2:52 PM
Row 176 | Customer requested to withdraw on 1/4/2024 | Kaiya Hoogkamp | 05/07/24 10:57 AM
Row 176 | Refund issued in SAP | Kaiya Hoogkamp | 01/22/24 1:48 PM
Row 176 | Original contract 120005879 cancelled on 1/18/2024, customer withdrawn without doing ESA and PIA $1500 refunded. | Kaiya Hoogkamp | 01/18/24 11:33 AM
Row 176 | Duplicate contract 12000085887 created by Nate Lawrence was cancelled. No payment attached. | Kaiya Hoogkamp | 01/18/24 11:32 AM
Row 177 | 1/7/2024 customer requested to withdraw | Kaiya Hoogkamp | 05/22/24 9:09 AM
Row 179 | 1/2/2024 ESA failed, project withdrawn. | Kaiya Hoogkamp | 10/15/24 2:54 PM
Row 180 | 1/26/2024 project withdrawn after failing ESA | Kaiya Hoogkamp | 07/23/24 3:32 PM
Row 181 | 1/24/2024 customer has decided to withdraw the project. | Kaiya Hoogkamp | 02/27/24 1:21 PM
Row 182 | 2/20/2024 project failed ESA and withdrawn. | Kaiya Hoogkamp | 10/15/24 2:55 PM
Row 185 | No task 24 in SAP | Kaiya Hoogkamp | 12/17/24 2:40 PM
Row 186 | 5/16/2024 project requested to be withdrawn, project no longer viable. | Kaiya Hoogkamp | 10/15/24 2:57 PM
Row 190 | $0.00 invoice 910269585 | Kaiya Hoogkamp | 05/30/25 8:05 AM
Row 190 | Zeroed out ESA invoice, we are waiving the cost, as the customer asked to hold off on study and never confirmed they wanted to continue with ESA. They did not send the deposit. | Kaiya Hoogkamp | 05/30/25 7:58 AM
Row 190 | 5/15/25 project withdrawn due to site feasibility | Kaiya Hoogkamp | 05/19/25 10:05 AM
Row 190 | 4/4/25 email for IA sent. 30 BD 5/19/2025 | Kaiya Hoogkamp | 04/04/25 3:43 PM
Row 190 | Customer has not paid ESA deposit. DO NOT issue COC until we receive payment | Kaiya Hoogkamp | 03/07/25 11:33 AM
Row 192 | original PIA 910202573/920222068 cancelled due to incorrect project name entered in description. Ticket INC3254016 entered to cancel. | Kaiya Hoogkamp | 12/05/23 1:45 PM
Row 194 | 1211/24 project requested to withdraw in favor of their level 4 project 599 | Kaiya Hoogkamp | 12/11/24 8:44 AM
Row 195 | 2/22/2024 project failed ESA and withdrew. | Kaiya Hoogkamp | 10/15/24 3:05 PM
Row 200 | 1/31/2024 project failed ESA and withdrew. | Kaiya Hoogkamp | 10/15/24 3:09 PM
Row 202 | "Install 500 kVA Pad Mount Transformer." listed under "Estimated Cost to Interconnect". | Nathan Lawrence | 09/03/24 2:31 PM
Row 204 | 11/13/2023 project failed ESA and withdrew. | Kaiya Hoogkamp | 10/15/24 3:10 PM
Row 206 | 11/6/2023 project failed tech screen and withdrew. | Kaiya Hoogkamp | 10/15/24 3:17 PM
Row 207 | 10/25/2023 project failed ESA and withdrew. | Kaiya Hoogkamp | 10/15/24 3:18 PM
Row 209 | additional ESA invioice: 910265923/920289271 | Kaiya Hoogkamp | 05/02/25 11:52 AM
Row 212 | 12/8/2023 application failed ESA. Project withdrawn. | Kaiya Hoogkamp | 06/24/24 11:53 AM
Row 214 | 9/8/2023 project unresponsive to outreach and withdrawn after 10 bd deadline. | Kaiya Hoogkamp | 10/15/24 3:48 PM
Row 215 | Has a related noti 10300727127 for customer building construction per Gary Ham | Nathan Lawrence | 07/30/24 8:36 AM
Row 217 | 9/14/2023 project failed ESA and project withdrawn. | Kaiya Hoogkamp | 10/16/24 7:40 AM
Row 220 | 1/24/2024 customer withdrew project. | Kaiya Hoogkamp | 10/16/24 7:43 AM
Row 221 | 11/3/2023 project withdrew. | Kaiya Hoogkamp | 10/16/24 7:42 AM
Row 222 | Original PIA 910191401/920210205 was never cleared w/ payment and sales admin cleared 3/26/2024. Created new PIA 910223778/920244513 on 5/23/2024 to apply payment to. | Thomas Blanchard | 05/28/24 2:44 PM
Row 223 | 10/12/2023 project failed ESA and withdrew. | Kaiya Hoogkamp | 10/16/24 8:21 AM
Row 224 | 10/3/2023 project failed ESA and withdrew. | Kaiya Hoogkamp | 10/16/24 8:19 AM
Row 225 | Contract cancelled. | Kaiya Hoogkamp | 03/10/25 1:27 PM
Row 225 | 10/26/2023 project requested to withdraw | Kaiya Hoogkamp | 10/22/24 12:01 PM
Row 226 | ESA Cancelled | Kaiya Hoogkamp | 03/10/25 1:28 PM
Row 226 | 10/26/2023 customer withdrew project. | Kaiya Hoogkamp | 10/16/24 8:28 AM
Row 227 | 4/4/25 email for IA sent. 30 BD 5/19/2025 | Kaiya Hoogkamp | 04/04/25 3:28 PM
Row 228 | 9/20/2023 project failed ESA and withdrew. | Kaiya Hoogkamp | 10/16/24 8:30 AM
Row 229 | 8/16/23 withdrawn after project failed ESA | Kaiya Hoogkamp | 10/07/24 10:53 AM
Row 230 | 5/6/25 Sent additional ESA for study work | Kaiya Hoogkamp | 05/06/25 1:15 PM
Row 230 | Additional PIA for restudy work done Spring 2024 910266050/920289412 $140.73 | Kaiya Hoogkamp | 05/05/25 9:56 AM
Row 230 | Original developer Perennial Renewables LLC, sold to Madison Energy Infrastructure | Kaiya Hoogkamp | 11/26/24 12:58 PM
Row 232 | 1/21/2025 customer withdrew | Kaiya Hoogkamp | 01/22/25 7:37 AM
Row 236 | 9/6/2023 project failed ESA and withdrew. | Kaiya Hoogkamp | 10/16/24 8:35 AM
Row 237 | 9/6/2023 project failed ESA and withdrew. | Kaiya Hoogkamp | 10/16/24 8:35 AM
Row 240 | 8/30/2023 project failed ESA and withdrew. | Kaiya Hoogkamp | 10/16/24 8:36 AM
Row 242 | 8/16/2023 project failed ESA and withdrew. | Kaiya Hoogkamp | 10/16/24 8:37 AM
Row 245 | 9/2/2023 application withdrawn | Kaiya Hoogkamp | 10/18/24 11:48 AM
Row 249 | 7/30/2023 app failed ESA and withdrew | Kaiya Hoogkamp | 10/18/24 11:54 AM
Row 249 | TIN has been used for Acadia Energy, can I use that # | Jessie Ladaga | 06/16/23 12:55 PM
Row 250 | 6/30/2023 application withdrawn | Kaiya Hoogkamp | 10/18/24 11:49 AM
Row 251 | Can I use the Green Lantern #; emailed Christy | Jessie Ladaga | 06/16/23 12:45 PM
Row 252 | Debtor # extended | Jessie Ladaga | 06/16/23 10:45 AM
Row 253 | DEBTOR # CREATED | Jessie Ladaga | 06/29/23 12:52 PM
Row 255 | 9/21/2023 application withdrawn | Kaiya Hoogkamp | 10/18/24 12:01 PM
Row 256 | Invoice for NOTI 10301049886 paid 10/31/24 | Nathan Lawrence | 12/10/24 12:25 PM
Row 257 | 7/14/2023 app failed ESA and project withdrawn | Kaiya Hoogkamp | 10/18/24 12:00 PM
Row 258 | 6/25/2023 application withdrawn | Kaiya Hoogkamp | 10/18/24 12:02 PM
Row 258 | NH Solar Garden payment - confirmed via email - see email? is there a debtor #? is there a w9? | Jessie Ladaga | 06/14/23 5:34 PM
Row 259 | this project failed tech screen in error and needs to be refunded the ESA charge- after rescreen on tech screen they passed. | William Dawe | 07/11/23 8:54 AM
Row 259 | this is on RE # - can i use 1289121? | Jessie Ladaga | 06/14/23 5:20 PM
Row 262 | additional charges found and billable per Portal | Staci Pellegrini | 03/13/24 1:05 PM
| Added charges of $246.68 to invoice on 3/20/24 | Thomas Blanchard | 03/21/24 7:38 AM
Row 262 | no debtor # created. Can i use 929103? W9 is lacking address. Sent email. | Jessie Ladaga | 06/14/23 4:31 PM
Row 262 | debtor # created | Jessie Ladaga | 06/14/23 4:23 PM
Row 262 | email sent requesting w9 | Jessie Ladaga | 05/19/23 11:33 AM
Row 263 | Original developer GREEN LANTERN DEVELOPMENT LLC, sold to Madison Energy Infrastructure | Kaiya Hoogkamp | 11/26/24 12:55 PM
Row 263 | Created new paid 910206445/920226265 ticket sent xfer 2500.00 to correct debtor | Staci Pellegrini | 01/08/24 12:32 PM
Row 263 | pia 910183424/920201756 was canceled by sales admin | Staci Pellegrini | 01/05/24 9:35 AM
Row 263 | Pia was cancel because the payment was on the original payee debtor 924257 / set itnow ticket move to 932591 and will xfer contract to me and then set up new pia to clear. | Staci Pellegrini | 01/05/24 9:33 AM
Row 263 | found debtor # = 932591 | Jessie Ladaga | 06/14/23 2:39 PM
Row 263 | requested w9 | Jessie Ladaga | 06/14/23 2:30 PM
Row 264 | 8/14/2023 application withdrawn | Kaiya Hoogkamp | 10/18/24 12:09 PM
Row 264 | w9 reques sent | Jessie Ladaga | 05/31/23 2:44 PM
Row 264 | Request for w9 was sent out by front end analysis on 5/12/2023 | Jessie Ladaga | 05/12/23 2:48 PM
Row 265 | 8/8/2023 app failed ESA and withdrew | Kaiya Hoogkamp | 10/18/24 12:05 PM
Row 265 | w9 request sent | Jessie Ladaga | 05/31/23 2:48 PM
Row 265 | w9 request sent on 5/12 with ESA | Jessie Ladaga | 05/12/23 2:49 PM
Row 266 | 7/26/23 project failed ESA and withdrawn. | Kaiya Hoogkamp | 09/05/24 10:25 AM
Row 267 | NO W9 REC;D THIS HAS A NOTI # 1508679 | Jessie Ladaga | 06/30/23 3:22 PM
Row 267 | sent a follow up email requesting w9 | Jessie Ladaga | 06/14/23 2:17 PM
Row 267 | w9 email request sent | Jessie Ladaga | 05/31/23 2:26 PM
Row 268 | 5/20/2024 project has withdrawn. | Kaiya Hoogkamp | 05/20/24 3:30 PM
Row 268 | has credit willo need to apply to balance on 83453 email sent to Kiaya | Staci Pellegrini | 01/04/24 2:52 PM
Row 268 | email sent requesting .pdf PIA (study about to kick off) | Jessie Ladaga | 05/12/23 1:49 PM
Row 269 | 6/22/2023 ESA failed, application withdrawn | Kaiya Hoogkamp | 10/18/24 12:15 PM
Row 269 | THIS WAS EXTENDED BY STACI | Jessie Ladaga | 06/14/23 3:49 PM
Row 269 | 1416460 = noti / can this be extended to use? | Jessie Ladaga | 06/14/23 2:07 PM
Row 270 | sent IT ticket | Jessie Ladaga | 05/11/23 9:34 AM
Row 271 | FBL5N review; ? | Jessie Ladaga | 05/17/23 3:00 PM
Row 271 | Sent IT | Jessie Ladaga | 05/15/23 9:20 AM
Row 272 | 10/19/2023 The project listed 83668 is in fact a cancelled project per conversation with developer just now- Ryan Darlow. | Kaiya Hoogkamp | 10/18/24 12:20 PM
Row 272 | to have contract 120005075 reassigned to me then closed out .incorrect debtor | Staci Pellegrini | 03/05/24 4:37 PM
Row 272 | Duplicate contract Pia created for Prj 83668 contract 120005075 debtor 928950 910179620/920197672 incorrect debtor payment 5/5 pa 8400015200 will need to be moved debtor 929226 and applied invoice 920198765 contract 120005124. sent email jess. | Staci Pellegrini | 06/14/23 2:46 PM
Row 272 | sent IT | Jessie Ladaga | 05/15/23 8:44 AM
Row 272 | cutomer has sent in confirmation of ESA payment | Jessie Ladaga | 05/10/23 4:23 PM
Row 272 | have w9 and debtor #, need signed ESA | Jessie Ladaga | 05/10/23 1:06 PM
Row 272 | W9 requested | Jessie Ladaga | 05/10/23 12:59 PM
Row 273 | Payment refund 896..58 was taken from prj 83670 and applied to level 4 prj balance prj 692 1/17/2024 | Staci Pellegrini | 04/26/24 11:30 AM
Row 275 | Credit memo: 910266673 for $19.92 refund that is due | Kaiya Hoogkamp | 05/08/25 9:16 AM
Row 275 | 5/7/25 Sent contract to work flow | Kaiya Hoogkamp | 05/07/25 8:21 AM
Row 275 | New PIA 910266262/920289612 | Kaiya Hoogkamp | 05/06/25 9:42 AM
Row 275 | New Contract: 120007536 released on 5/6/25 | Kaiya Hoogkamp | 05/06/25 9:35 AM
Row 275 | Per Michelle and Brian and sales admin, because we cannot get the PIA to show on the contract, we need to cancel the contract and PIA and start over. 120005031 has been terminated | Kaiya Hoogkamp | 05/06/25 9:10 AM
Row 275 | 910266160/920289513 - new PIA created per Michelle in Sales Admin | Kaiya Hoogkamp | 05/05/25 3:04 PM
Row 275 | Original developer MECHANIC FALLS GLC SOLAR LLC, sold to Madison Energy Infrastructure | Kaiya Hoogkamp | 11/26/24 12:57 PM
Row 275 | INC3162470 ticket requesting payment | Kaiya Hoogkamp | 10/24/23 10:24 AM
Row 275 | Original PIA 910179625/920197692 was never cleared w/ payment and sales admin cleared 9/28/2023. Created new PIA 910199075/920218318 on 10/24/2023 to apply payment to. | Kaiya Hoogkamp | 10/24/23 10:19 AM
Row 276 | katie to create debtor # | Jessie Ladaga | 04/28/23 10:10 AM
Row 277 | old PIA that closed out 910178292/920196202 | Kaiya Hoogkamp | 11/01/23 3:11 PM
Row 277 | sent IT ticket | Jessie Ladaga | 05/12/23 4:07 PM
Row 277 | rec'd W9; found debtor; sent to Christy to fix spelling in SAP and confirm TIN's match | Jessie Ladaga | 04/26/23 12:14 PM
Row 278 | 5/17/2023 app failed ESA and withdrawn | Kaiya Hoogkamp | 10/18/24 12:21 PM
Row 278 | pia was created by jess/ pia got cancelled due to no pmt being applied / found no confirmation of payment from the customerr via portal. I sent email to customer 11/11 to confirm if paid or not before we invoice | Staci Pellegrini | 01/11/24 11:36 AM
Row 278 | sent email to Sales Admin to have address updated Debtor # 923285 - office moved; sent W9 and IA for backup documentaiton | Jessie Ladaga | 06/14/23 12:22 PM
Row 278 | need to send email to update address-- speak with staci | Jessie Ladaga | 05/31/23 1:39 PM
Row 278 | debtor # reuqest sent | Jessie Ladaga | 05/10/23 12:52 PM
Row 279 | Original developer GREEN LANTERN DEVELOPMENT LLC, sold to Madison Energy Infrastructure | Kaiya Hoogkamp | 11/26/24 12:56 PM
Row 279 | Debtor creation requested | Jessie Ladaga | 05/09/23 2:38 PM
Row 280 | Kiaya created credit memo | Staci Pellegrini | 11/08/23 5:44 PM
Row 280 | sent email for OCR to place 2500 on 9003006 | Jessie Ladaga | 04/28/23 11:18 AM
Row 280 | sent KK a request to create debtor # | Jessie Ladaga | 04/26/23 1:13 PM
Row 281 | Charges waived, contract closed on 5/7/2024 | Thomas Blanchard | 05/07/24 11:48 AM
Row 281 | PIA Had been preivously cancelled. Contract completed on 10/20/2023. We will not be billing the contractor charges as it was a pass. | Kaiya Hoogkamp | 10/20/23 11:11 AM
Row 281 | This was a tech screen fail in error, it was in fact a PASS but ESA was billed out. | Kaiya Hoogkamp | 10/20/23 11:08 AM
Row 282 | debtor # created | Jessie Ladaga | 05/15/23 2:24 PM
Row 282 | email sent requesting w9 | Jessie Ladaga | 05/10/23 10:52 AM
Row 283 | 4/27/2023 project failed ESA and withdrew | Kaiya Hoogkamp | 09/23/24 2:19 PM
Row 283 | sent request to KK to have # created | Jessie Ladaga | 04/26/23 1:38 PM
Row 285 | 4/23/2023 app withdrawn | Kaiya Hoogkamp | 10/18/24 12:23 PM
Row 286 | April 3, 2024 developer requested withdraw | Kaiya Hoogkamp | 07/11/24 3:55 PM
Row 286 | completed refund 1/17/24 | Staci Pellegrini | 02/20/24 9:02 AM
Row 286 | sent invoices to customer 1/4/2024 this is credit back to the customer no other outstanding projects owed so i requested refund 0000000086 1/17/24 sap | Staci Pellegrini | 01/17/24 9:30 AM
Row 286 | Issue with customer name | Kristina Waterhouse | 04/03/23 2:39 PM
Row 287 | $ is still open on open cash draw as of 5/26 sent ITNOW ticket | Staci Pellegrini | 05/26/23 1:48 PM
Row 287 | 5/16/23 follow up email sent in RE of W9 | Jessie Ladaga | 05/17/23 4:39 PM
Row 287 | Put $2500 (paid on 5/15/2023) ESA fee on debtor 1568046, pending W-9 with Arundel Solar | Kaiya Hoogkamp | 05/16/23 2:44 PM
Row 287 | need w9 with ESA name, email request sent | Jessie Ladaga | 05/12/23 2:38 PM
Row 288 | debtor # request sent/ email attached | Jessie Ladaga | 05/10/23 6:23 PM
Row 288 | there is a fully exectued ESA | Jessie Ladaga | 05/10/23 10:22 AM
Row 288 | debtor # creation requested | Jessie Ladaga | 05/10/23 10:21 AM
Row 288 | No ESA - email sent requesting signed Agreement | Jessie Ladaga | 04/26/23 2:15 PM
Row 288 | Requested W9 4/4 | Kristina Waterhouse | 04/04/23 1:28 PM
Row 289 | 6/9/2023 application withdrew | Kaiya Hoogkamp | 10/22/24 12:10 PM
Row 289 | Chase Warren payment on 1289121; sent IT | Jessie Ladaga | 05/12/23 4:46 PM
Row 289 | After researching the project number was over written in error making info look incorrect. | Kristina Waterhouse | 05/04/23 1:52 PM
Row 289 | wrong project details on this ROW- updated cor | William Dawe | 05/04/23 9:54 AM
Row 289 | PIA sent to customer/developer (ReVision) | Jessie Ladaga | 04/26/23 2:51 PM
Row 289 | ESA uploaded; waiting on Christy to release from workfolow to release Contract | Jessie Ladaga | 04/24/23 1:26 PM
Row 289 | need CMP to sign ESA | Jessie Ladaga | 04/24/23 10:43 AM
Row 289 | reuqested katie to create debtor # | Jessie Ladaga | 04/17/23 12:27 PM
Row 290 | 120005064 completed on 2/27/2024 | Kaiya Hoogkamp | 02/27/24 12:33 PM
Row 290 | original contract 120005064 (created incorrectly on Revisions debtor) | Kaiya Hoogkamp | 10/24/23 9:39 AM
Row 290 | sent needed US mailing addy to Katie for # creation | Jessie Ladaga | 04/26/23 3:15 PM
Row 290 | katie to create debtor # | Jessie Ladaga | 04/17/23 12:31 PM
Row 291 | i can create the contract and not release | Jessie Ladaga | 05/10/23 4:25 PM
Row 291 | no signed ESA | Jessie Ladaga | 05/10/23 10:13 AM
Row 291 | Sent email requesting w9 | Jessie Ladaga | 05/09/23 12:16 PM
Row 292 | 4/4/25 email for IA sent. 30 BD 5/19/2025 | Kaiya Hoogkamp | 04/04/25 2:37 PM
Row 296 | 4/4/25 email for IA sent. 30 BD 5/19/2025 | Kaiya Hoogkamp | 04/04/25 2:46 PM
Row 298 | completed refund 1/17/24 sjp | Staci Pellegrini | 02/20/24 9:03 AM
Row 298 | sent invoices to customer 1/4/2024 this is credit back to the customer no other outstanding projects owed so i requested refund 0000000086 1/17/24 sap | Staci Pellegrini | 01/17/24 9:29 AM
Row 299 | Withdraw request from customer 3/21/23 after failed TS. | Nathan Lawrence | 10/15/24 3:28 PM
Row 300 | PIF | Thomas Blanchard | 05/29/24 11:06 AM
Row 300 | Moved 103.42 from Acadia refunded projects to this Acadia balance due. OK'd by Glenn Walker | Thomas Blanchard | 05/29/24 11:03 AM
Row 301 | 4/7/2025 app withdrawn | Kaiya Hoogkamp | 04/07/25 8:54 AM
Row 301 | 4/4/25 email for IA sent. 30 BD 5/19/2025 | Kaiya Hoogkamp | 04/04/25 2:44 PM
Row 302 | no documentation verifying withdrawal | Kaiya Hoogkamp | 10/22/24 12:13 PM
Row 305 | Noti 10300899161 CANC | Nathan Lawrence | 01/30/25 12:45 PM
Row 307 | cleared SAP | Jessie Ladaga | 05/11/23 1:08 PM
Row 307 | need to change/update name in contract, add ESA then release | Jessie Ladaga | 04/24/23 10:34 AM
Row 307 | Requested Katie created debtor | Jessie Ladaga | 04/17/23 12:17 PM
Row 307 | Requested debtor | Kristina Waterhouse | 04/04/23 1:20 PM
Row 308 | Moved 596.78 from Acadia refunded projects to this Acadia balance due. OK'd by Glenn Walker. PIF | Thomas Blanchard | 05/29/24 11:05 AM
Row 310 | contract reassigned to me | Staci Pellegrini | 09/26/23 2:15 PM
Row 310 | charges 1480.08/ 1500.00 will need to refund 19.92. | Staci Pellegrini | 09/26/23 2:03 PM
Row 310 | Created USM1 debtor | Kristina Waterhouse | 04/03/23 3:02 PM
Row 310 | Requested W9 4/3 | Kristina Waterhouse | 04/03/23 12:02 PM
Row 312 | Customer confirmed withdrawal 4/11/2023, resubmitted as a L4. | Nathan Lawrence | 10/15/24 6:07 PM
Row 317 | 12/5/2023 project withdrew due to wetlands and being unable to develop the land. | Kaiya Hoogkamp | 07/09/24 12:53 PM
Row 319 | 3/4/2024 the project failed ESA and is withdrawn. | Kaiya Hoogkamp | 07/09/24 1:00 PM
Row 319 | INC2871444 to move and clear PIA | Kristina Waterhouse | 05/31/23 2:19 PM
Row 319 | Requested debtor in SAP | Kristina Waterhouse | 04/26/23 11:30 AM
Row 319 | Emailed again for W9 request | Kristina Waterhouse | 04/25/23 1:51 PM
Row 319 | Requested W9 | Kristina Waterhouse | 04/04/23 2:22 PM
Row 320 | ESA Fees waived! | Kristina Waterhouse | 04/05/23 2:59 PM
Row 321 | 8/23/2023 application withdrew | Kaiya Hoogkamp | 10/22/24 12:46 PM
Row 322 | Requested debtor in SAP | Kristina Waterhouse | 04/06/23 10:36 AM
Row 322 | Requested W9 | Kristina Waterhouse | 04/05/23 8:26 AM
Row 324 | Customer requested withdrawal 1/4/2023, downsized and resubmitted. | Nathan Lawrence | 10/15/24 6:02 PM
Row 325 | 2/1/2023 customer confirmed they wanted to withdraw | Kaiya Hoogkamp | 06/12/24 10:47 AM
Row 328 | Wthdrawal requested by customer 2/27/2023. | Nathan Lawrence | 10/15/24 5:56 PM
Row 328 | Submitted INC2876458 to open CM for refund | Kristina Waterhouse | 06/02/23 10:15 AM
Row 328 | Sent email requesting they confirm refund information | Kristina Waterhouse | 05/23/23 11:31 AM
Row 328 | Created debtor in SAP | Kristina Waterhouse | 05/04/23 10:02 AM
Row 328 | Followed up on W9 request | Kristina Waterhouse | 04/25/23 1:55 PM
Row 328 | W9 requested 4/3 | Kristina Waterhouse | 04/03/23 1:48 PM
Row 329 | Also terminated contract 120004858 | Kristina Waterhouse | 06/13/23 8:44 AM
Row 329 | Submitted INC2895073 to cancell PIA | Kristina Waterhouse | 06/13/23 8:44 AM
Row 329 | Waived per Nate 4/12/2023 | Kristina Waterhouse | 04/13/23 6:25 AM
Row 330 | no documentation confirming withdrawal | Kaiya Hoogkamp | 10/22/24 11:45 AM
Row 331 | Customer confirmed withdrawal 2/15/2023 after failed TS, resubmitted as L4. | Nathan Lawrence | 10/15/24 5:52 PM
Row 333 | no documentation confirming withdrawal | Kaiya Hoogkamp | 10/22/24 11:44 AM
Row 334 | Project sold to Perennial September 2024. New IA sent 10/2/24. Awaiting letter of intent and updated assignement sheet - NAL 10/2/24. | Nathan Lawrence | 10/02/24 10:37 AM
Row 334 | sent IT ticket | Jessie Ladaga | 05/11/23 9:59 AM
Row 337 | paid 07-06-2023 | Helen Markham | 01/11/24 10:40 AM
Row 337 | reopend aplication due to the POI incorrect during screenings awaiting on DE for updated results | William Dawe | 05/08/23 10:41 AM
Row 337 | Might be waiving second set of ESA Charges?????? | Kristina Waterhouse | 05/08/23 10:27 AM
Row 337 | Requested USM1 debtor in SAP | Kristina Waterhouse | 05/08/23 10:19 AM
Row 337 | They replied that Goodwin Motors was not a valid DBA for "FRG, Inc"... responded that we need customer name to match on W9 | Kristina Waterhouse | 04/25/23 12:15 PM
Row 337 | Followed up on W9 request | Kristina Waterhouse | 04/12/23 7:20 AM
Row 337 | Requested W9 | Kristina Waterhouse | 04/07/23 1:13 PM
Row 339 | Customer withdraw request 6/13/2023. | Nathan Lawrence | 10/15/24 5:42 PM
Row 339 | contract completed | Staci Pellegrini | 02/27/24 8:12 AM
Row 339 | INC3066209 entered ticket to cancel PIA | Kaiya Hoogkamp | 09/05/23 11:14 AM
Row 339 | released contract 9/5/2023 & Informed Christy prj is withdrawn, she will cancel | Kaiya Hoogkamp | 09/05/23 10:59 AM
Row 339 | Found that this should not have been invoiced per Will dated 6/13/23 This project 82404 withdrew before ESA. Contract and PIA will need to be canceled. | Staci Pellegrini | 06/14/23 11:54 AM
Row 339 | invoice sent to customer | Jessie Ladaga | 05/15/23 9:31 AM
Row 339 | waiting on invoice; then need to sent to developer | Jessie Ladaga | 05/11/23 12:49 PM
Row 339 | esa agreement sent on 5/8/2023 waiting on dev and signature | William Dawe | 05/08/23 2:32 PM
Row 339 | need to send invoice. no signed ESA as of 4/24/2023 | Jessie Ladaga | 04/24/23 2:46 PM
Row 340 | INC2889448 to clear payment | Kristina Waterhouse | 06/09/23 9:06 AM
Row 340 | INC2770901 to clear PIA | Kristina Waterhouse | 04/12/23 12:47 PM
Row 340 | Requested debtor in SAP | Kristina Waterhouse | 04/11/23 1:56 PM
Row 340 | Requested W9 | Kristina Waterhouse | 04/07/23 1:35 PM
Row 341 | Customer confirmed PRJ withdrawn 2/23/23. Replaced w/ 82924. | Nathan Lawrence | 10/15/24 4:00 PM
Row 342 | 1233.40 | Staci Pellegrini | 08/16/23 11:32 AM
Row 342 | Extended debtor to 90/90 | Kristina Waterhouse | 04/06/23 10:21 AM
Row 342 | Requested W9 | Kristina Waterhouse | 04/05/23 8:36 AM
Row 343 | Submitted INC2807753 to open CM 910178007 for refund | Kristina Waterhouse | 05/01/23 9:40 AM
Row 344 | Project withdrawn 5/11/23, failed ESA. | Nathan Lawrence | 10/15/24 3:57 PM
Row 344 | Submitted INC2770359 to move/clear PIA | Kristina Waterhouse | 04/12/23 10:17 AM
Row 344 | Katherine used this PIA for project 82255 | Kristina Waterhouse | 04/12/23 8:42 AM
Row 344 | Found PIA confirmation but don't see payment? | Kristina Waterhouse | 04/11/23 2:34 PM
Row 344 | Created debtor | Kristina Waterhouse | 04/07/23 2:05 PM
Row 344 | Requested W9 4/3 | Kristina Waterhouse | 04/03/23 12:11 PM
Row 345 | 4/10/2024 project withdrawn per customer request. They cannot receive permits required to build. | Kaiya Hoogkamp | 04/10/24 3:15 PM
Row 345 | remaining credit will need to be refunded | Staci Pellegrini | 10/06/23 8:45 AM
Row 345 | invoice created 3/9/2023 sjp | Staci Pellegrini | 03/09/23 11:31 AM
Row 346 | 1/26/2023 failed esa and withdrew | Kaiya Hoogkamp | 10/22/24 11:42 AM
Row 346 | can't find deposit | Kristina Waterhouse | 04/13/23 10:07 AM
Row 346 | extended debtor in SAP | Kristina Waterhouse | 04/11/23 2:41 PM
Row 348 | Submitted INC2836191 to clear old milestone. Changed contract amount and released. | Kristina Waterhouse | 05/15/23 11:51 AM
Row 348 | Sumbitted CM 910179847 to clear incorrect invoice. Then need to redo milestone. New PIA #1 910179850/920197922 INC2832601 to move money from old PIA New PIA #2 910179851/ INC2832623 to move money | Kristina Waterhouse | 05/12/23 9:27 AM
Row 348 | Katherine used the wrong PIA payment and dollar amount.... This project only had a PIA of $500. Submitted INC270359 to cancel PIA 910173793/920191452 | Kristina Waterhouse | 04/12/23 9:56 AM
Row 350 | 10/21/2024 project requested withdrawal | Kaiya Hoogkamp | 10/22/24 11:41 AM
Row 351 | INC2873394 to clear payment | Kristina Waterhouse | 06/01/23 8:55 AM
Row 351 | INC2773312 to clear PIA | Kristina Waterhouse | 04/13/23 10:35 AM
Row 351 | Extended debtor in SAP | Kristina Waterhouse | 04/12/23 11:22 AM
Row 352 | Customer withdraw request 2/9/23 after failed TS. | Nathan Lawrence | 10/15/24 3:49 PM
Row 353 | 5/22/2023 customer confirmed withdrawing project | Kaiya Hoogkamp | 06/20/24 8:32 AM
Row 355 | Submitted INC2807736 to open credit memo for refund | Kristina Waterhouse | 05/01/23 9:32 AM
Row 355 | INC2773476 to clear PIA | Kristina Waterhouse | 04/13/23 11:31 AM
Row 355 | Emailed Christy.... debtors don't match W9 | Kristina Waterhouse | 04/12/23 11:39 AM
Row 356 | no documentation confirming withdrawal | Kaiya Hoogkamp | 10/22/24 11:40 AM
Row 357 | 2/22/2023 project failed ESA and withdrew. | Kaiya Hoogkamp | 10/16/24 8:42 AM
Row 357 | Can't find fully executed ESA | Kristina Waterhouse | 04/13/23 11:54 AM
Row 357 | Extended debtor in SAP | Kristina Waterhouse | 04/12/23 11:52 AM
Row 358 | IA for Tenant Change sent 10/3/24. Changed from "Moose River Lumber Co" to "Boundary Co". | Nathan Lawrence | 10/03/24 12:53 PM
Row 359 | Per Staci we have reassignment, new W9 and new IA so we are billing under Propspect Solar One LLC.... Extended USM1 in SAP | Kristina Waterhouse | 04/13/23 12:09 PM
Row 359 | The ESA is under VCP but customer is now Prospect Solar One LLC.... | Kristina Waterhouse | 04/12/23 12:09 PM
Row 360 | 2/9/2023 application withdrew | Kaiya Hoogkamp | 10/16/24 2:09 PM
Row 361 | 11/8/2022 project failed ESA and withdrew. | Kaiya Hoogkamp | 10/16/24 2:12 PM
Row 361 | Sent follow up email on refund info | Kristina Waterhouse | 06/02/23 10:58 AM
Row 361 | Sent follow up email for refund info. | Kristina Waterhouse | 05/22/23 7:40 AM
Row 361 | INC2836420 to open funds for refund and emailed customer for refund info | Kristina Waterhouse | 05/15/23 1:26 PM
Row 361 | Refund on straight invoice | Kristina Waterhouse | 04/13/23 1:41 PM
Row 362 | 11/16/2022 project requested to withdraw. | Kaiya Hoogkamp | 10/16/24 2:13 PM
Row 362 | Emailed again for status on where the payment was moved | Kristina Waterhouse | 05/22/23 1:28 PM
Row 362 | This projects deposit was cleared to PRJ 81513. PRJ 81513's deposit went to consumption. Emailed Sales admin. | Kristina Waterhouse | 04/14/23 11:53 AM
Row 362 | Created debtor in SAP | Kristina Waterhouse | 04/13/23 2:22 PM
Row 362 | Requested W9 4/3 | Kristina Waterhouse | 04/03/23 1:47 PM
Row 363 | 4/14/2023 project withdrawn | Kaiya Hoogkamp | 10/16/24 2:23 PM
Row 363 | Submitted INC2871126 to clear PIA | Kristina Waterhouse | 05/31/23 12:24 PM
Row 363 | PRJ 81958's deposit is missing. PRJ 81959's deposit was cleared to 81958. Sent email to sales admin to track down payment. There is an uncleared 500 on debtor 931931 but it's just a bank recon and I can't find anything else tied to the doc #. | Kristina Waterhouse | 05/18/23 2:03 PM
| Treasurey was able to find the payment and release it to sundry. | Kristina Waterhouse | 05/25/23 2:03 PM
Row 363 | Requested debtor in SAP | Kristina Waterhouse | 05/04/23 10:59 AM
Row 363 | Requested W9 | Kristina Waterhouse | 04/14/23 1:04 PM
Row 364 | 12/7/2022 project failed ESA and withdrew. | Kaiya Hoogkamp | 10/16/24 2:22 PM
Row 365 | 10/13/2022 project withdrawn. | Kaiya Hoogkamp | 10/16/24 2:21 PM
Row 367 | 2/21/2023 application withdrawn. | Kaiya Hoogkamp | 10/16/24 2:20 PM
Row 368 | Invoice for NOTI 10300952863 paid 11/11/2024 | Nathan Lawrence | 12/10/24 12:26 PM
Row 368 | Updated ESA name to Rewild per ESA agreement | Kristina Waterhouse | 03/20/23 12:48 PM
Row 370 | 1/26/2023 failed ESA and project withdrew. | Kaiya Hoogkamp | 10/16/24 2:17 PM
Row 370 | INC2803382 to cancel Katherines old PIA 910174793, it was never paid | Kristina Waterhouse | 04/27/23 1:24 PM
Row 371 | 9/6/2022 project failed ESA and withdrew. | Kaiya Hoogkamp | 10/16/24 2:15 PM
Row 373 | 11/21/2022 project failed ESA and withdrew. | Kaiya Hoogkamp | 10/16/24 2:29 PM
Row 373 | the PIA was refunded customer not charged because of mis communication and email accidentially sent stating it was Pass when it was not ... | Staci Pellegrini | 01/11/24 12:30 PM
Row 373 | PIA was refunded! | Kristina Waterhouse | 05/04/23 11:21 AM
Row 373 | Found my deposit but it's cleared to a DC?? | Kristina Waterhouse | 04/14/23 1:39 PM
Row 374 | Correct Debtor is 933090 | Kaiya Hoogkamp | 04/16/25 9:06 AM
Row 374 | ESA Contract 120007418 INVOICE: 910262401 | Kaiya Hoogkamp | 04/09/25 9:03 AM
Row 374 | Coordination Study Contract 12007402 INVOICE: 910262399 | Kaiya Hoogkamp | 04/09/25 8:55 AM
Row 374 | NEW $500 contract: 120007418 PIA 910258361/920281370 | Kaiya Hoogkamp | 03/18/25 10:20 AM
Row 374 | Credit memo created 3/11/25: 910256926/920280771 & released | Kaiya Hoogkamp | 03/11/25 1:46 PM
Row 374 | Second contract for coordination study ($3200): 120007402. PIA: 910256233/920279200 | Kaiya Hoogkamp | 03/05/25 3:56 PM
Row 374 | 4/11/2023 project withdrew. | Kaiya Hoogkamp | 10/16/24 2:25 PM
Row 374 | Helen followed up on outstanding bal 2/14/24 | Staci Pellegrini | 02/28/24 4:24 PM
Row 374 | invoice 910197050 created for $500.00 ESA this correct debtor. | Staci Pellegrini | 10/06/23 9:35 AM
Row 374 | Need to lower the contract amount... this is the one that's cleared to a straight invoice | Kristina Waterhouse | 05/25/23 2:16 PM
| because of this kristina's invoice will need to be cancel and rebilled correctly with a PIA | Staci Pellegrini | 09/20/23 10:39 AM
Row 374 | PRJ 81958's deposit is missing. PRJ 819589's deposit was cleared to 81958. Sent email to sales admin to track down payment. There is an uncleared 500 on debtor 931931 but it's just a bank recon and I can't find anything else tied to the doc #. | Kristina Waterhouse | 05/18/23 2:03 PM
| this 500.00 is actual on debtor 931931, had to cancel invoice on 931931 and have $500.00 pmt mvd 933090 | Staci Pellegrini | 09/20/23 10:39 AM
Row 374 | i canceled the straight invoice last week ( smartsheets down) uner 931931 910160414/920176842 (adj 0.00) and asked for money to be moved over 933090. | Staci Pellegrini | 09/20/23 10:37 AM
Row 374 | email sent to Kaiya and straight invoice will need to be canceled. and contract reset from no guarantee to a guarantee. | Staci Pellegrini | 08/22/23 4:38 PM
Row 374 | PIA payment is pa 8400040065 11/15/2022 500.00 sitting on 931931 and needs to be moved to 933090. | Staci Pellegrini | 08/22/23 4:37 PM
Row 374 | INC2871110 to cancel PIA... paid with straight invoice | Kristina Waterhouse | 05/31/23 12:25 PM
Row 374 | Requested debtor in SAP | Kristina Waterhouse | 05/04/23 11:00 AM
Row 375 | 10/19/2022 project failed ESA and withdrew. | Kaiya Hoogkamp | 10/16/24 2:31 PM
Row 375 | Sent follow up email on refund info. | Kristina Waterhouse | 05/22/23 7:36 AM
Row 375 | Sent email to confirm refund info | Kristina Waterhouse | 05/15/23 12:58 PM
Row 375 | Submitted INC2836298 to clear invoice and open 766.60 for refund | Kristina Waterhouse | 05/15/23 12:52 PM
Row 375 | Exteded debtor in SAP | Kristina Waterhouse | 05/04/23 11:45 AM
Row 376 | NEW invoice on debtor 924030. Invoice: 910267874/920291265 | Kaiya Hoogkamp | 05/15/25 9:28 AM
Row 376 | Invoice adjustment to $0, 910267871 | Kaiya Hoogkamp | 05/15/25 9:06 AM
Row 376 | The correct debtor is 924030 | Kaiya Hoogkamp | 05/15/25 8:23 AM
Row 376 | UPDATED Invoice for $1000: 910262692/920285786 | Kaiya Hoogkamp | 04/10/25 1:34 PM
Row 376 | 4/10/25 app invoice adjustment to $0.00 910262686 | Kaiya Hoogkamp | 04/10/25 1:27 PM
Row 377 | 10/10/2022 project failed ESA and withdrew. | Kaiya Hoogkamp | 10/16/24 2:32 PM
Row 378 | sent email Sachin 4/11 for W-9 | Staci Pellegrini | 04/11/23 9:57 AM
Row 380 | 9/28/2022 project failed ESA and withdrew | Kaiya Hoogkamp | 10/16/24 2:49 PM
Row 381 | 3/3/2023 application withdrawn. | Kaiya Hoogkamp | 10/16/24 2:59 PM
Row 382 | 10/10/2022 project failed ESA and withdrew | Kaiya Hoogkamp | 10/16/24 2:57 PM
Row 383 | 10/19/2023 failed ESA, application withdrew. | Kaiya Hoogkamp | 10/17/24 10:55 AM
Row 383 | Canceled Katherine's PIA - INC2802646 | Kristina Waterhouse | 04/27/23 9:33 AM
Row 383 | Cancelled Katherine's contract, cannot find PIA and this needs to be released. | Kristina Waterhouse | 04/25/23 9:38 AM
Row 384 | 10/19/2022 project failed ESA and withdrew. | Kaiya Hoogkamp | 10/17/24 10:51 AM
Row 385 | 2/9/2023 application withdrew. | Kaiya Hoogkamp | 10/17/24 10:50 AM
Row 386 | 2/9/2023 application withdrew. | Kaiya Hoogkamp | 10/17/24 10:36 AM
Row 387 | 9/23/2022 project failed ESA and withdrew. | Kaiya Hoogkamp | 10/17/24 10:29 AM
Row 387 | sent reminder email for payment 1/10/2024 | Helen Markham | 01/10/24 2:52 PM
Row 387 | No deposit required | Kristina Waterhouse | 05/04/23 11:29 AM
Row 389 | 9/26/2022 application withdrawn. | Kaiya Hoogkamp | 10/16/24 3:02 PM
Row 390 | 8/3/2022 application withdrew. | Kaiya Hoogkamp | 10/17/24 11:07 AM
Row 391 | 10/19/2022 failed ESA and withdrew. | Kaiya Hoogkamp | 10/17/24 10:59 AM
Row 391 | The Payment 500.00 Kristina used originated 922312 clearing doc 2200003472 | Staci Pellegrini | 01/10/24 1:29 PM
Row 391 | per Portal & SAP $500.00 was invoiced under 910160407 10/21/2022 and cleared. for 81848 | Staci Pellegrini | 10/17/23 8:01 AM
| debtor 922331 | Staci Pellegrini | 10/17/23 11:54 AM
Row 391 | INC2855649 to move payment and clear PIA | Kristina Waterhouse | 05/24/23 9:03 AM
Row 391 | Submitted INC2855572 to clear adjusted invoice | Kristina Waterhouse | 05/24/23 8:45 AM
Row 391 | Released CM.... will do milestone after so it doesn't get stuck in my WF | Kristina Waterhouse | 05/23/23 11:15 AM
Row 391 | CM 910180038 to clear incorrect invoice | Kristina Waterhouse | 05/15/23 11:59 AM
Row 391 | I found a deposit when I was about to send this out to the customer..... need to adjust invoice and redo with PIA. | Kristina Waterhouse | 05/15/23 10:18 AM
Row 392 | 1/17/2023 failed ESA, application withdrawn. | Kaiya Hoogkamp | 10/17/24 11:19 AM
Row 392 | INC2856078 to clear random HA/HT pair | Kristina Waterhouse | 05/24/23 10:42 AM
Row 392 | 910181237 to clear Katherine's incorrect invoice | Kristina Waterhouse | 05/24/23 10:18 AM
Row 392 | Submitted ticket # INC2807808 to clear PIA | Kristina Waterhouse | 05/01/23 10:36 AM
Row 392 | Submitted ticket INC2807806 to cancel hx invoice 910165985 which never had a payment cleared to it. | Kristina Waterhouse | 05/01/23 10:31 AM
Row 393 | Ticket to cancel old PIA was closed but never done.... submitted INC2932865 | Kristina Waterhouse | 06/30/23 10:11 AM
Row 393 | Emailed front end.... I don't think a deposit was paid on this one. | Kristina Waterhouse | 05/09/23 12:16 PM
Row 393 | Submitted ticket INC2807815 to cancel PIA INC2807815, it was never paid so we'll bill total charges on milestone | Kristina Waterhouse | 05/01/23 10:40 AM
Row 394 | 9/28/2022 failed ESA and withdrew | Kaiya Hoogkamp | 10/17/24 11:28 AM
Row 394 | Extended debtor in SAP | Kristina Waterhouse | 04/27/23 12:05 PM
Row 394 | Cancelled Katherine's old contract | Kristina Waterhouse | 04/25/23 9:41 AM
Row 395 | 8/8/2022 failed tech screen, no formal email requesting withdraw. | Kaiya Hoogkamp | 10/17/24 11:45 AM
Row 397 | 9/12/2022 project withdrew | Kaiya Hoogkamp | 10/17/24 11:55 AM
Row 397 | Confirmed project never went to ESA | Kristina Waterhouse | 04/27/23 8:49 AM
Row 397 | Doesn't look like the ESA on this one was ever actually executed, project was withdrawn the same day the agreement was issued to the customer. | Kristina Waterhouse | 04/27/23 8:11 AM
Row 397 | Application was withdrawn 9/12/22.... we need to verify the study was not aleady started. | Kristina Waterhouse | 04/05/23 7:27 AM
Row 398 | 9/28/2022 failed ESA and withdrew. | Kaiya Hoogkamp | 10/17/24 11:49 AM
Row 398 | Submitted INC2802599 to cancel Katherine's old PIA | Kristina Waterhouse | 04/27/23 9:25 AM
Row 399 | 9/1/2022 application withdrawn. | Kaiya Hoogkamp | 10/17/24 12:22 PM
Row 400 | 500.00 Pia created ... need to bill remaining | Staci Pellegrini | 06/20/23 4:26 PM
Row 400 | 120004855 - cancelled contract | Kristina Waterhouse | 05/26/23 12:06 PM
Row 400 | Brian is going to cancel the PIA that katherine created on Revision ... as this needs to go on Oceanview instead. | Staci Pellegrini | 05/24/23 3:56 PM
Row 403 | 7/25/2022 application withdrawn. | Kaiya Hoogkamp | 10/17/24 12:51 PM
Row 404 | 8/3/2022 application withdrawn | Kaiya Hoogkamp | 10/17/24 12:50 PM
Row 405 | no documentation verifying withdrawal. | Kaiya Hoogkamp | 10/17/24 12:39 PM
Row 406 | 2/10/2023 application withdrew | Kaiya Hoogkamp | 10/17/24 12:24 PM
Row 407 | 2/10/2023 application withdrawn. | Kaiya Hoogkamp | 10/17/24 12:23 PM
Row 408 | 12/6/2022 application withdrawn. | Kaiya Hoogkamp | 10/17/24 12:54 PM
Row 409 | 8/10/2022 application withdrawn. | Kaiya Hoogkamp | 10/17/24 12:57 PM
Row 409 | Created USS1 under NES | Kristina Waterhouse | 05/31/23 1:51 PM
Row 409 | Requested W9 | Kristina Waterhouse | 05/30/23 12:07 PM
Row 410 | Requested W9 | Kristina Waterhouse | 05/30/23 12:11 PM
Row 410 | This project used deposit meant for project 81972. Deposit meant for this project was sent to consumption.... emailed sales admin. | Kristina Waterhouse | 04/14/23 11:53 AM
Row 411 | 3/3/2023 application withdrawn | Kaiya Hoogkamp | 10/17/24 12:56 PM
Row 412 | 6/21/2022 application withdrawn | Kaiya Hoogkamp | 10/17/24 12:55 PM
Row 413 | 10/19/2022 application withdrawn | Kaiya Hoogkamp | 10/17/24 1:08 PM
Row 413 | Created USS1 under NES | Kristina Waterhouse | 05/31/23 1:51 PM
Row 413 | Requested W9 | Kristina Waterhouse | 05/30/23 12:04 PM
Row 414 | 6/17/2022 application withdrawn. | Kaiya Hoogkamp | 10/17/24 12:59 PM
Row 415 | 6/17/2022 application withdrawn | Kaiya Hoogkamp | 10/17/24 12:58 PM
Row 418 | 6/30/2022 application withdrawn | Kaiya Hoogkamp | 10/17/24 1:10 PM
Row 419 | 6/15/2022 application withdrawn | Kaiya Hoogkamp | 10/17/24 1:09 PM
Row 420 | 6/8/2022 application withdrawn | Kaiya Hoogkamp | 10/17/24 1:27 PM
Row 421 | 6/27/2022 application withdrawn | Kaiya Hoogkamp | 10/17/24 1:28 PM
Row 422 | Extended debtor in SAP | Kristina Waterhouse | 06/02/23 12:29 PM
Row 422 | Receiced W9 naming Outlook Farm LLC as a DBA for Great Works Properties. There is a blocked debtor in SAP that matches by TIN. Submitted INC2876682 to have it unblocked. | Kristina Waterhouse | 06/02/23 12:09 PM
Row 422 | Emailed for updated assigment information and W9.... name in portal and on CMP account has been updated to Great Works Property Inc | Kristina Waterhouse | 05/31/23 11:19 AM
Row 423 | 6/8/2022 application withdrawn | Kaiya Hoogkamp | 10/17/24 1:30 PM
Row 424 | Old Account# 30013836017 | Nathan Lawrence | 07/25/24 3:42 PM
Row 425 | Ticket INC2812351 to clear payment | Kristina Waterhouse | 05/03/23 7:07 AM
Row 426 | no documentation confirming the withdrawal date | Kaiya Hoogkamp | 10/17/24 1:57 PM
Row 427 | no documentation confirming the project is withdrawn | Kaiya Hoogkamp | 10/17/24 2:33 PM
Row 428 | 6/30/2022 application withdrawn | Kaiya Hoogkamp | 10/17/24 2:16 PM
Row 429 | 4/9/2022 failed ESA and withdrew | Kaiya Hoogkamp | 10/17/24 2:39 PM
Row 429 | Adj invoicefrom 2994.64 to 2007.92 910207125 | Staci Pellegrini | 01/12/24 10:38 AM
Row 429 | Kristina has over billed 81262 she billed part of Auburn Penley Corner to this one invoice needs to be adj | Staci Pellegrini | 01/12/24 9:50 AM
Row 429 | They replied that they will update the name on the account to Novel... still has not been done. Sent follow up email. | Kristina Waterhouse | 05/30/23 12:00 PM
Row 429 | Requested W9 | Kristina Waterhouse | 05/24/23 1:09 PM
Row 430 | 8/30/2022 4:17:31 PM Jessie Roderick (U341040) ESA not needed. TS passed. DE revised. | Kristina Waterhouse | 03/21/23 12:32 PM
Row 431 | Charges in 12/22 but study was completed 8/22 | Kristina Waterhouse | 05/24/23 1:45 PM
Row 432 | 7/19/2022 application withdrawn | Kaiya Hoogkamp | 10/17/24 2:47 PM
Row 433 | no documentation for withdrawal | Kaiya Hoogkamp | 10/17/24 2:45 PM
Row 434 | no documentation regarding withdrawal | Kaiya Hoogkamp | 10/17/24 2:58 PM
Row 434 | cleared by doubtful debt | Kaiya Hoogkamp | 04/17/23 8:57 AM
Row 435 | no documentation about withdrawal | Kaiya Hoogkamp | 10/17/24 2:55 PM
Row 437 | 2/9/2023 application withdrawn | Kaiya Hoogkamp | 10/17/24 3:03 PM
Row 438 | 8/9/2022 application withdrawn | Kaiya Hoogkamp | 10/17/24 3:16 PM
Row 439 | Per W9 refund needs to be issued on USM1 debtor 929912. Submitted INC2879510 to move payment to correct debtor. | Kristina Waterhouse | 06/05/23 7:51 AM
Row 439 | Sent follow up email | Kristina Waterhouse | 06/02/23 10:35 AM
Row 439 | Sent follow up email for refund info. | Kristina Waterhouse | 05/22/23 7:33 AM
Row 439 | Sent email requesting W9 and to confirm refund info | Kristina Waterhouse | 05/15/23 12:49 PM
Row 439 | Submitted INC2836270 to clear adjusted invoice and open funds for refund. | Kristina Waterhouse | 05/15/23 12:43 PM
Row 440 | 8/9/2022 application withdrawn. | Kaiya Hoogkamp | 10/17/24 3:12 PM
Row 441 | INC2812351 to clear payment | Kristina Waterhouse | 05/03/23 7:07 AM
Row 443 | no documentation confirming withdrawal | Kaiya Hoogkamp | 10/17/24 3:10 PM
Row 444 | 8/17/2022 customer withdrew project | Kaiya Hoogkamp | 05/22/24 9:53 AM
Row 445 | 8/8/2022 application withdrew | Kaiya Hoogkamp | 10/17/24 3:19 PM
Row 445 | sent reminder email for payment 1/10/2024 | Helen Markham | 01/10/24 2:52 PM
Row 446 | no documentation on withdrawal | Kaiya Hoogkamp | 10/17/24 3:23 PM
Row 447 | 8/2/2022 application withdrawn | Kaiya Hoogkamp | 10/17/24 3:30 PM
Row 448 | 2000.00 910154560 | Staci Pellegrini | 01/08/24 4:58 PM
Row 448 | revision 1289121 | Staci Pellegrini | 01/08/24 4:55 PM
Row 448 | $2000.00 esa deposit paid by revision 1489121.. remaining balance Kristina billed under 933140 | Staci Pellegrini | 01/08/24 4:54 PM
Row 448 | Requested debtor in SAP | Kristina Waterhouse | 05/12/23 1:26 PM
Row 449 | no documentation verifying withdrawal. | Kaiya Hoogkamp | 10/17/24 3:29 PM
Row 449 | Converted NOTI to USM1 and exteneded to 90/90 | Kristina Waterhouse | 05/30/23 1:14 PM
Row 449 | Followed up on W9 request | Kristina Waterhouse | 05/24/23 12:52 PM
Row 449 | Requested W9 | Kristina Waterhouse | 05/12/23 1:37 PM
Row 450 | 9/27/2022 application withdrawn | Kaiya Hoogkamp | 10/17/24 3:32 PM
Row 451 | 9/28/2022 application moved to level 4 and withdrawn as level 2. | Kaiya Hoogkamp | 10/17/24 3:42 PM
Row 452 | 10/10/2022 application withdrawn | Kaiya Hoogkamp | 10/17/24 3:41 PM
Row 452 | Submitted INC2833148 to clear adjusted invoice and open for refund | Kristina Waterhouse | 05/12/23 1:17 PM
Row 454 | 4/26/2022 application withdrew | Kaiya Hoogkamp | 10/17/24 3:39 PM
Row 455 | 5/26/2022 application moved to level 4 and withdrawn as level 2. | Kaiya Hoogkamp | 10/17/24 3:44 PM
Row 456 | no documentation verifying withdrawal. | Kaiya Hoogkamp | 10/17/24 3:45 PM
Row 457 | no documentation confirming withdrawal | Kaiya Hoogkamp | 10/17/24 3:52 PM
Row 457 | paid 06/26/2023 | Helen Markham | 01/11/24 10:27 AM
Row 457 | sent itnow ticket to clear dd with credit memo | Staci Pellegrini | 01/08/24 4:43 PM
Row 457 | Original invoice is with doubtful debt, need to identify the process | Kristina Waterhouse | 07/03/23 9:36 AM
Row 457 | Requested extension to 90/90 in SAP | Kristina Waterhouse | 06/05/23 12:31 PM
Row 457 | Customer replied that they are in the process of this project changing from Penobscot Narrow Solar to Penobscot Narrow Solar I. Asked estimated time frame | Kristina Waterhouse | 05/23/23 1:37 PM
Row 457 | Requested W9 | Kristina Waterhouse | 05/12/23 12:23 PM
Row 458 | 5/26/2022 project failed ESA and withdrew | Kaiya Hoogkamp | 10/17/24 3:56 PM
Row 459 | 12/6/2022 application withdrawn | Kaiya Hoogkamp | 10/18/24 11:18 AM
Row 460 | 6/8/2022 application withdrawn | Kaiya Hoogkamp | 10/18/24 11:15 AM
Row 460 | sent reminder email for payment 1/10/2024 | Helen Markham | 01/10/24 2:53 PM
Row 460 | Sent email for charge clarification. Katherine had labeled some June charges for this project but the study had already been completed in May. Novel had multiple projects during this time period. | Kristina Waterhouse | 05/30/23 11:53 AM
Row 461 | 6/20/2022 application withdrawn | Kaiya Hoogkamp | 10/18/24 11:23 AM
Row 462 | 5/26/2022 application withdrawn | Kaiya Hoogkamp | 10/18/24 11:22 AM
Row 463 | 6/30/2022 application withdrawn. | Kaiya Hoogkamp | 10/18/24 11:21 AM
Row 465 | 4/5/2022 application withdrawn | Kaiya Hoogkamp | 10/18/24 11:20 AM
Row 466 | 9/14/2022 application withdrawn | Kaiya Hoogkamp | 10/18/24 11:25 AM
Row 467 | 4/25/2022 app failed ESA and withdrawn | Kaiya Hoogkamp | 10/18/24 11:28 AM
Row 467 | sent email to dante to ask why charges are 6475.35 when est being 500.00 | Staci Pellegrini | 01/08/24 3:05 PM
Row 467 | We charged 500.00 flat fee 7/7/2022 910150282/920166049 | Staci Pellegrini | 01/08/24 1:12 PM
Row 467 | W-9 Received | Kaiya Hoogkamp | 10/10/23 7:41 AM
Row 467 | Emailed requesting W-9 in order to create final invoice | Kaiya Hoogkamp | 10/02/23 1:41 PM
Row 467 | Followed up on W9 request | Kristina Waterhouse | 06/21/23 8:24 AM
Row 467 | Requested W9 | Kristina Waterhouse | 06/05/23 11:42 AM
Row 467 | Requested W9 | Kristina Waterhouse | 05/26/23 9:18 AM
Row 468 | Sent email confirming refund information | Kristina Waterhouse | 05/23/23 8:46 AM
Row 468 | 910152320 920169118 7/28/2022 CREATED / ADJ 3/17/2023 920191690 2000.00 | Staci Pellegrini | 04/18/23 3:50 PM
Row 468 | REFUND NEEDED | Staci Pellegrini | 04/18/23 3:26 PM
Row 471 | orig inovice 2000.00 910155488 920171646 4/28/2022 debtor 910795 has been adj 0.00 910232840 due to inv kristina created listed here | Staci Pellegrini | 08/07/24 11:23 AM
Row 471 | Paid 07/28/2023 | Helen Markham | 01/11/24 10:29 AM
Row 471 | The hx invoice is with doubtful debt. Submitted INC2936503 to determine the correct process for adjusting this invoice | Kristina Waterhouse | 07/03/23 9:21 AM
Row 471 | Extended debtor in SAP | Kristina Waterhouse | 06/05/23 9:12 AM
Row 471 | Followed up again on W9 request | Kristina Waterhouse | 05/31/23 11:26 AM
Row 471 | Followed up on W9 request | Kristina Waterhouse | 05/23/23 1:13 PM
Row 471 | Requested W9 | Kristina Waterhouse | 05/11/23 1:59 PM
Row 473 | 6/3/2022 application withdrawn | Kaiya Hoogkamp | 10/18/24 11:31 AM
Row 473 | Prior invoice 0.00 due to pia found 2000.00 from 10/11/2022 6000.00 group pmt, Tom created new PIA NEW CONTRACT 120006275/ | Staci Pellegrini | 03/15/24 9:53 AM
Row 473 | 910185191 to clear Katherines old invoice | Kristina Waterhouse | 06/30/23 12:15 PM
Row 474 | 5/18/2022 application failed ESA and withdrew | Kaiya Hoogkamp | 10/18/24 11:31 AM
Row 474 | New contract 120006269, PIA 910213705 | Thomas Blanchard | 03/06/24 9:46 AM
Row 474 | 120005192 prior contract from Kristina did not have 500.00 pai this has been canceled and 0.00 TOm to create an new contract and pia and invoice 3/5/24 | Staci Pellegrini | 03/05/24 11:33 AM
Row 474 | prior invoice 2096..78 has been 0.00 Helen located 500.00 pia that belongs to this contract this needs to be reinvoiced under a new contract. Details in project backup file | Staci Pellegrini | 03/05/24 11:25 AM
Row 474 | sent reminder email for payment 1/10/2024 | Helen Markham | 01/10/24 2:53 PM
Row 474 | I had already tried to adjust this.... verified all old invoices are correctly cleared and only invoice that is outstanding is the one for 2096.78 | Kristina Waterhouse | 06/30/23 12:10 PM
Row 474 | ORIGINAL INVOICE WAS AMENDED SO CREDIT CREDIT INVOICE WAS CREATED 910184660 | Staci Pellegrini | 06/26/23 12:46 PM
Row 474 | 6/26/2023 0.00 invoice created 9/15/2022 910156432/920172671 930085 was replaced w 120005192 invoice920200848 910182481 | Staci Pellegrini | 06/26/23 11:59 AM
Row 474 | 910183703 to clear Katherines unpaid straight invoice | Kristina Waterhouse | 06/16/23 12:11 PM
Row 475 | 9/30/2024 project withdrawn. | Kaiya Hoogkamp | 09/30/24 11:51 AM
Row 475 | sent reminder email for payment 1/10/2024 | Helen Markham | 01/10/24 2:54 PM