## Level 2 Online Report
Project # | App Received | Customer Notified Application Complete | Facility Type | AC kW | Circuit | Substation | Substation Transformer | Tech Screen Completed | Tech Screen Results | ESA Results | ESA Completed | Withdrawn
106484 | 2025-05-07 |  | Solar | 975 | 860D2 | UNITY | 860T1
106392 | 2025-04-30 | 2025-05-09 | Solar | 300 | 800D1 | LINCOLNVILLE | 800T1 |  | Pending
106395 | 2025-04-30 | 2025-05-09 | Solar | 840 | 817D3 | FAIRFIELD | 817T1 |  | Pending
106396 | 2025-04-30 | 2025-05-09 | Solar | 440 | 416D3 | GRAY | 416T1 |  | Pending
106397 | 2025-04-30 | 2025-05-09 | Solar | 320 | 431D3 | MECHANIC FALLS | 431T2 |  | Pending
106391 | 2025-04-29 | 2025-05-09 | Solar | 360 | 803D6 | BELFAST WEST SIDE | 34.5 kV Bus |  | Pending
106272 | 2025-04-22 | 2025-05-01 | Solar | 152 | 423D2 | KIMBALL ROAD | 423T2 |  | Pending
106220 | 2025-04-18 | 2025-04-24 | Solar | 440 | 246D3 | THOMASTON CREEK | 246T1 | 2025-05-13 | Fail
106226 | 2025-04-18 | 2025-04-24 | Solar | 160 | 803D6 | BELFAST WEST SIDE | 34.5 kV Bus | 2025-05-13 | Fail
106231 | 2025-04-18 | 2025-04-24 | Solar | 320 | 678D2 | BAR MILLS | 678T4 | 2025-05-14 | Fail
106234 | 2025-04-18 | 2025-04-24 | Solar | 160 | 873D1 | COUNTY RD (RICE RIPS) | 873T1 | 2025-05-13 | Fail
106242 | 2025-04-18 | 2025-04-23 | Solar | 995 | 692D1 | HIRAM TAP | 692T1 | 2025-05-06 | Fail
106244 | 2025-04-18 | 2025-04-24 | Solar | 995 | 857D1 | THORNDIKE TAP | 857T1 | 2025-05-13 | Fail
106179 | 2025-04-16 | 2025-04-21 | Solar | 152 | 409D1 | PARIS TAP | 409T1 | 2025-05-05 | Fail
106128 | 2025-04-14 | 2025-04-17 | Solar | 875 | 428D3 | LIVERMORE FALLS | 428T1 | 2025-05-05 | Fail
106048 | 2025-04-08 | 2025-04-15 | Solar | 153.6 | 208D2 | BOND BROOK | 208T1 | 2025-04-21 | Fail | Pending
105982 | 2025-04-03 | 2025-05-02 | Solar | 999 | 610D2 | BONNY EAGLE | 610T4 | 2025-05-16 | Fail
105997 | 2025-04-03 | 2025-04-17 | Solar | 136.8 | 219D2 | DAMARISCOTTA MILLS | 219T1 | 2025-05-05 | Fail
105865 | 2025-03-26 | 2025-03-31 | Solar | 999 | 885D1 | WILTON | 885T1 | 2025-04-04 | Fail | Fail | 2025-05-13 | Yes
105830 | 2025-03-24 | 2025-03-27 | Solar | 999 | 449D2 | RILEY | 449T1 | 2025-03-28 | Fail | Pending
105827 | 2025-03-21 | 2025-03-28 | Solar | 150 | 435D4 | NORWAY | 435T2 | 2025-04-04 | Fail | Pass | 2025-05-13
105796 | 2025-03-19 | 2025-03-27 | Solar | 999 | 238D1 | MESSINA | 238T1 | 2025-03-28 | Fail |  |  | Yes
105773 | 2025-03-17 | 2025-03-19 | Solar | 999 | 860D1 | UNITY | 860T1 | 2025-03-25 | Fail |  |  | Yes
105711 | 2025-03-12 | 2025-03-19 | Solar | 999 | 853D1 | SKOWHEGAN NORTH SIDE | 853T1 | 2025-03-25 | Fail |  |  | Yes
105681 | 2025-03-11 | 2025-03-19 | Solar | 999 | 467D1 | TURNER TAP | Tap off of Transmission Line | 2025-03-25 | Fail | Pass | 2025-04-23
105660 | 2025-03-07 | 2025-03-17 | Solar | 995 | 806D1 | BUCKSPORT | 806T5 | 2025-03-18 | Fail | Pass | 2025-04-04
105641 | 2025-03-06 | 2025-03-17 | Solar | 995 | 837D2 | NEWPORT | 837T2 | 2025-03-18 | Fail | Pass | 2025-04-03
105649 | 2025-03-06 |  | Solar | 990 | [7 empty] | Yes
105547 | 2025-02-25 | 2025-03-11 | Solar | 999 | 815D2 | DOVER | 815T2 |  | Fail |  |  | Yes
105548 | 2025-02-25 | 2025-03-12 | Solar | 999 | 638D1 | NORTH LIMINGTON | 638T1 | 2025-03-12 | Fail
105549 | 2025-02-25 | 2025-03-12 | Solar | 999 | 602D2 | BASSETT | 602T1 | 2025-03-12 | Fail
105550 | 2025-02-25 | 2025-03-11 | Solar | 999 | 602D2 | BASSETT | 602T1 | 2025-03-11 | Fail |  |  | Yes
105551 | 2025-02-25 | 2025-03-11 | Solar | 999 | 818D1 | FARMINGTON FALLS | 818T1 | 2025-03-11 | Fail |  |  | Yes
105521 | 2025-02-21 | 2025-03-07 | Solar | 999 | 842D1 | PITTSFIELD | 842T1 | 2025-03-11 | Fail | Pass | 2025-04-24
105523 | 2025-02-21 | 2025-03-07 | Solar | 999 | 885D1 | WILTON | 885T1 | 2025-03-11 | Fail
105500 | 2025-02-19 | 2025-02-24 | Solar | 975 | 431D1 | MECHANIC FALLS | 431T2 | 2025-02-28 | Fail | Pass | 2025-04-18
105454 | 2025-02-14 | 2025-02-18 | Solar | 969.4 | 813D1 | DEXTER | 813T1 | 2025-02-21 | Fail | Fail | 2025-03-20 | Yes
105424 | 2025-02-13 | 2025-02-17 | Solar | 200 | 810D1 | CLINTON | 810T1 | 2025-02-21 | Fail | Fail | 2025-03-13 | Yes
105405 | 2025-02-11 | 2025-02-12 | Solar | 995 | 431D1 | MECHANIC FALLS | 431T2 | 2025-02-14 | Fail | Pass | 2025-04-16
105215 | 2025-01-24 | 2025-01-28 | Solar | 152 | 423D2 | KIMBALL ROAD | 423T2 | 2025-01-31 | Fail | Fail | 2025-02-27 | Yes
105216 | 2025-01-24 | 2025-02-04 | Solar | 999 | 860D1 | UNITY | 860T1 | 2025-02-06 | Fail |  |  | Yes
105198 | 2025-01-23 | 2025-02-11 | Solar | 999 | 808D3 | CARMEL TAP | 808T1 | 2025-02-18 | Fail |  |  | Yes
105204 | 2025-01-23 | 2025-01-27 | Solar | 996 | 813D1 | DEXTER | 813T1 | 2025-01-31 | Fail | Fail | 2025-02-20 | Yes
105158 | 2025-01-16 | 2025-01-20 | Solar | 995 | 850D1 | SEARSPORT | 850T1 | 2025-01-24 | Fail | Pass | 2025-02-14
105134 | 2025-01-15 | 2025-01-23 | Solar | 200 | 675D2 | WESTERN AVENUE | 675T1 | 2025-01-24 | Pass
105120 | 2025-01-14 | 2025-01-20 | Solar | 141.84 | 253D1 | WARREN | 253T1 | 2025-01-24 | Fail | Fail | 2025-03-17 | Yes
105126 | 2025-01-14 | 2025-02-03 | Solar | 975 | 272D4 | NORTH AUGUSTA | 272T1 | 2025-02-06 | Fail | Pass | 2025-03-20
105055 | 2025-01-08 | 2025-01-27 | Solar | 975 | 873D1 | COUNTY RD (RICE RIPS) | 873T1 | 2025-02-03 | Fail |  |  | Yes
104989 | 2025-01-02 | 2025-01-03 | Solar | 152 | 409D1 | PARIS TAP | 409T1 | 2025-01-03 | Fail | Fail | 2025-01-24 | Yes
104942 | 2024-12-20 |  | Solar | 152 | [7 empty] | Yes
104944 | 2024-12-20 | 2024-12-23 | Solar | 152 | 423D2 | KIMBALL ROAD | 423T2 | 2024-12-30 | Fail | Pass | 2025-01-22
104916 | 2024-12-18 | 2024-12-31 | Solar | 220 | 239D7 | PARK STREET | 239T2 | 2025-01-03 | Fail | Pass | 2025-01-30
104902 | 2024-12-17 | 2024-12-31 | Solar | 200 | 246D3 | THOMASTON CREEK | 246T1 | 2025-01-03 | Fail | Pass | 2025-02-11
104903 | 2024-12-17 | 2024-12-24 | Solar | 240 | 239D6 | PARK STREET | 239T2 | 2025-01-03 | Fail | Pass | 2025-02-19
104904 | 2024-12-17 | 2024-12-31 | Solar | 100 | 239D5 | PARK STREET | 239T4 | 2025-01-03 | Fail | Pass | 2025-01-29
104822 | 2024-12-10 | 2024-12-12 | Solar | 995 | 467D1 | TURNER TAP | Tap off of Transmission Line | 2024-12-18 | Fail | Pass | 2025-01-14
104658 | 2024-11-22 | 2024-12-13 | Solar | 680 | 674D1 | WESTBROOK | 674T1 | 2024-12-16 | Fail | Fail | 2025-02-06
104659 | 2024-11-22 | 2024-12-13 | Solar | 400 | 674D1 | WESTBROOK | 674T1 | 2024-12-16 | Fail | Pending
104661 | 2024-11-22 | 2024-12-17 | Solar | 600 | 232D2 | LISBON FALLS | 232T2 | 2024-12-18 | Fail | Pass | 2025-01-06
104636 | 2024-11-21 | 2024-12-13 | Solar | 150 | 647D2 | PRIDES CORNER | 647T2 | 2024-12-16 | Pass
104638 | 2024-11-21 | 2024-12-13 | Solar | 240 | 674D2 | WESTBROOK | 674T1 | 2024-12-16 | Fail | Pass | 2025-02-06
104609 | 2024-11-20 | 2024-11-25 | Solar | 995 | 813D1 | DEXTER | 813T1 | 2024-11-26 | Fail |  |  | Yes
104613 | 2024-11-20 | 2024-11-25 | Solar | 999 | 431D1 | MECHANIC FALLS | 431T2 | 2024-11-26 | Fail | Fail | 2025-01-02 | Yes
104553 | 2024-11-15 | 2024-12-03 | Solar | 990 | 603D2 | BERWICK | 603T1 | 2024-12-03 | Fail | Pass | 2025-04-08
104517 | 2024-11-13 | 2024-11-21 | Solar | 999 | 428D2 | LIVERMORE FALLS | 428T1 | 2024-11-21 | Fail | Pass | 2024-12-09
104498 | 2024-11-12 |  | Solar | 265.05 | [7 empty] | Yes
104424 | 2024-11-05 | 2024-11-13 | Solar | 995 | 885D1 | WILTON | 885T1 | 2024-11-13 | Fail | Pass | 2025-01-23
104271 | 2024-10-23 | 2024-10-24 | Solar | 984.85 | 874D1 | BELFAST 115 | 874T2 | 2024-10-25 | Fail | Pass | 2024-11-12
104273 | 2024-10-23 | 2024-10-24 | Solar | 995 | 858D3 | STURTEVANT | 858T2 | 2024-10-25 | Fail | Pass | 2024-11-12
104262 | 2024-10-22 | 2024-11-05 | Solar | 999 | 850D2 | SEARSPORT | 850T1 | 2024-11-06 | Fail |  |  | Yes
104264 | 2024-10-22 | 2024-11-26 | Solar | 999 | 815D2 | DOVER | 815T2 | 2024-11-26 | Fail |  |  | Yes
104167 | 2024-10-15 | 2024-10-21 | Solar | 990 | 208D1 | BOND BROOK | 208T1 | 2024-10-22 | Fail | Pass | 2024-11-04
103912 | 2024-09-25 | 2024-09-25 | Solar | 153.6 | 219D2 | DAMARISCOTTA MILLS | 219T1 | 2024-09-26 | Fail | Pass | 2024-10-28
103885 | 2024-09-23 | 2024-10-01 | Solar | 975 | 624D2 | FORT HILL | 624T1 | 2024-10-02 | Fail |  |  | Yes
103844 | 2024-09-19 | 2024-09-24 | Solar | 975 | 272D4 | NORTH AUGUSTA | 272T1 | 2024-09-24 | Fail | Pass | 2024-10-17 | Yes
103677 | 2024-09-05 | 2024-09-05 | Solar | 100 | 803D6 | BELFAST WEST SIDE | 34.5 kV Bus | 2024-09-10 | Fail | Pass | 2024-10-15
103608 | 2024-08-30 |  | Solar | 4999 | [7 empty] | Yes
103599 | 2024-08-29 | 2024-09-16 | Solar | 999.6 | 842D1 | PITTSFIELD | 842T1 | 2024-09-16 | Fail | Pass | 2024-10-11
103367 | 2024-08-14 | 2024-08-15 | Solar | 995 | 242D1 | SIDNEY | 242T1 | 2024-08-16 | Fail | Pass | 2024-09-25
103285 | 2024-08-06 | 2024-08-13 | Solar | 540 | 647D1 | PRIDES CORNER | 647T2 | 2024-08-13 | Fail | Pass | 2024-09-12
103291 | 2024-08-06 | 2024-08-16 | Solar | 125 | 647D1 | PRIDES CORNER | 647T2 | 2024-08-22 | Fail | Pass | 2024-09-16
103293 | 2024-08-06 | 2024-08-16 | Solar | 150 | 647D1 | PRIDES CORNER | 647T2 | 2024-08-22 | Fail | Pass | 2024-09-16
103125 | 2024-07-30 | 2024-08-06 | Solar | 994 | 454D1 | TURNER | 454T1 | 2024-08-07 | Fail | Pass | 2024-09-16
103042 | 2024-07-24 | 2024-08-12 | Solar | 975 | 207D2 | BLAIR ROAD | 207T1 | 2024-08-13 | Fail | Fail | 2024-09-30 | Yes
103022 | 2024-07-23 |  | Solar | 480 | [7 empty] | Yes
103024 | 2024-07-23 | 2024-07-26 | Solar | 480 | 437D1 | OXFORD | 437T1 | 2024-07-29 | Fail | Fail | 2024-08-12 | Yes
103027 | 2024-07-23 |  | Solar | 150 | 437D1 | OXFORD | 437T1 |  |  |  |  | Yes
103030 | 2024-07-23 | 2024-07-26 | Solar | 420 | 216D2 | CONY ROAD | 216T1 | 2024-07-29 | Fail | Fail | 2024-08-23 | Yes
102896 | 2024-07-12 | 2024-07-30 | Solar | 975 | 634D1 | MAY STREET | 634T1 | 2024-08-16 | Fail | Fail | 2024-10-02 | Yes
102852 | 2024-07-11 | 2024-07-18 | Solar | 390 | 605D1 | BIDDEFORD PUMPING STATION | 605T1 | 2024-07-26 | Fail | Pass | 2024-08-28
102789 | 2024-07-08 | 2024-07-08 | Solar | 145.152 | 685D1 | BOLT HILL | 685T1 | 2024-07-10 | Pass
102756 | 2024-07-02 | 2024-07-10 | Solar | 995 | 874D1 | BELFAST 115 | 874T2 | 2024-07-12 | Fail | Fail | 2024-09-03 | Yes
102732 | 2024-07-01 | 2024-07-02 | Solar | 150 | 239D6 | PARK STREET | 239T2 | 2024-07-09 | Fail | Pass | 2024-08-05
102742 | 2024-07-01 | 2024-07-02 | Solar | 200 | 630D2 | GOOSEFARE | 630T1 | 2024-07-03 | Fail | Pass | 2024-08-06
102659 | 2024-06-25 | 2024-06-26 | Solar | 975 | 810D1 | CLINTON | 810T1 | 2024-06-27 | Fail | Fail | 2024-08-12 | Yes
102613 | 2024-06-24 | 2024-06-26 | Solar | 720 | 656D1 | SANFORD INDUSTRIAL PARK | 656T1 | 2024-07-12 | Fail | Pass | 2024-08-28
102614 | 2024-06-24 | 2024-06-26 | Solar | 360 | 644D1 | PLEASANT HILL | 644T2 | 2024-06-28 | Pass
102616 | 2024-06-24 | 2024-06-28 | Solar | 660 | 635D2 | MOSHERS | 635T2 | 2024-07-02 | Fail | Pass | 2024-08-01
102617 | 2024-06-24 | 2024-06-28 | Solar | 100 | 693D2 | SCARBOROUGH | 693T1 | 2024-07-02 | Pass
102619 | 2024-06-24 | 2024-06-28 | Solar | 200 | 693D2 | SCARBOROUGH | 693T1 | 2024-07-02 | Pass
102622 | 2024-06-24 | 2024-06-28 | Solar | 150 | 630D1 | GOOSEFARE | 630T1 | 2024-07-02 | Pass
102492 | 2024-06-13 |  | Solar | 996 | [7 empty] | Yes
102439 | 2024-06-10 | 2024-06-13 | Solar | 280 | 213D3 | BRUNSWICK WEST SIDE | 213T1 | 2024-06-24 | Pass
102340 | 2024-06-04 | 2024-07-10 | Solar | 160 | 213D3 | BRUNSWICK WEST SIDE | 213T1 | 2024-07-12 | Fail | Pass | 2024-08-09
102272 | 2024-05-30 | 2024-06-12 | Solar | 975 | 450D1 | SABATTUS | 450T1 | 2024-06-13 | Pass | Pass | 2024-07-15
102178 | 2024-05-23 | 2024-05-29 | Solar/Battery | 996 | 444D3 | RAYMOND 34 KV | 444T1 | 2024-06-03 | Fail |  |  | Yes
102153 | 2024-05-22 | 2024-06-04 | Solar | 600 | 854D2 | SKOWHEGAN SOUTH SIDE | 854T1 | 2024-06-07 | Fail |  |  | Yes
102149 | 2024-05-21 | 2024-05-21 | Solar | 152 | 435D4 | NORWAY | 435T2 | 2024-05-22 | Fail | Pass | 2024-07-10
102000 | 2024-05-10 | 2024-05-22 | Wind | 225 | 806D2 | BUCKSPORT | 806T3 | 2024-05-31 | Fail | Pass | 2024-07-09
102005 | 2024-05-10 | 2024-05-23 | Solar | 999 | 263D1 | BOWMAN STREET | 34kV BUS 2 | 2024-05-29 | Fail |  |  | Yes
101765 | 2024-04-23 | 2024-05-15 | Solar | 999 | 821D3 | GUILFORD | 821T2 | 2024-05-28 | Fail | Pass | 2024-07-10
101713 | 2024-04-18 | 2024-05-07 | Solar | 975 | 674D2 | WESTBROOK | 674T1 | 2024-05-17 | Fail |  |  | Yes
101717 | 2024-04-18 | 2024-04-19 | Solar | 975 | 226D2 | GARDINER | 226T1 | 2024-04-22 | Fail | Pass | 2024-05-20
101658 | 2024-04-12 | 2024-04-18 | Solar | 153.6 | 219D2 | DAMARISCOTTA MILLS | 219T1 | 2024-05-08 | Fail |  |  | Yes
101603 | 2024-04-08 | 2024-04-17 | Solar | 250 | 412D4 | DEER RIPS | 412T4 | 2024-04-25 | Fail | Pass | 2024-06-24
101569 | 2024-04-04 | 2024-04-23 | Solar | 999 | 602D3 | BASSETT | 602T1 | 2024-05-09 | Fail | Pass | 2024-06-28
101528 | 2024-04-01 | 2024-04-12 | Solar | 999 | 431D1 | MECHANIC FALLS | 431T2 | 2024-04-22 | Fail | Fail | 2024-06-19 | Yes
101504 | 2024-03-28 | 2024-04-02 | Solar | 999 | 252D1 | WALDOBORO | 252T1 | 2024-04-05 | Fail | Fail | 2024-05-21 | Yes
101353 | 2024-03-18 | 2024-03-25 | Solar | 120 | 630D1 | GOOSEFARE | 630T1 | 2024-04-12 | Pass
101333 | 2024-03-14 |  | Solar | 150 | 403D1 | BETHEL | 403T1 |  |  |  |  | Yes
101334 | 2024-03-14 |  | Solar | 200 | 858D2 | STURTEVANT | 858T1 |  |  |  |  | Yes
101262 | 2024-03-08 | 2024-03-14 | Solar | 152 | 423D2 | KIMBALL ROAD | 423T2 | 2024-03-18 | Fail | Pass | 2024-04-30
101251 | 2024-03-07 | 2024-03-08 | Solar | 780 | 612D1 | BUTLER'S CORNER | 612T1 | 2024-03-27 | Fail | Fail | 2024-05-21 | Yes
101145 | 2024-02-27 | 2024-02-28 | Solar | 999 | 457D2 | MONMOUTH | 457T2 | 2024-03-01 | Fail | Pass | 2024-04-23
101131 | 2024-02-26 | 2024-02-29 | Solar | 999 | 447D4 | RUMFORD | 447T3 | 2024-03-01 | Fail | Fail | 2024-05-01 | Yes
101137 | 2024-02-26 | 2024-03-08 | Solar | 975 | 230D2 | COOPERS MILLS ROAD | 230T2 | 2024-03-08 | Fail | Pass | 2024-05-01
101067 | 2024-02-21 | 2024-02-23 | Solar | 125 | 865D1 | WEST WATERVILLE | 865T1 | 2024-02-26 | Pass |  |  | Yes
101037 | 2024-02-19 |  | Solar | 100 | 415D2 | FRYEBURG | 415T1 |  |  |  |  | Yes
100989 | 2024-02-13 |  | Solar | 996 | [7 empty] | Yes
100963 | 2024-02-09 | 2024-02-12 | Solar | 115.2 | 216D3 | CONY ROAD | 216T1 | 2024-02-13 | Pass
100873 | 2024-02-01 | 2024-02-13 | Solar | 995 | 667D2 | SOUTH SANFORD | 667T2 | 2024-03-07 | Fail | Fail | 2024-05-06 | Yes
100862 | 2024-01-31 | 2024-02-08 | Solar | 150 | 233D1 | MANCHESTER | 233T1 | 2024-02-09 | Fail | Pass | 2024-03-25
100863 | 2024-01-31 | 2024-02-09 | Solar | 600 | 415D2 | FRYEBURG | 415T1 | 2024-02-16 | Fail | Fail | 2024-04-12 | Yes
100846 | 2024-01-30 | 2024-02-19 | Solar | 999 | 272D2 | NORTH AUGUSTA | 272T1 | 2024-02-20 | Fail | Pass | 2024-04-11
100821 | 2024-01-26 | 2024-03-04 | Solar | 999 | 632D1 | LIMERICK | 632T1 | 2024-03-07 | Fail | Fail | 2024-05-12 | Yes
100803 | 2024-01-25 | 2024-02-02 | Solar | 999 | 246D3 | THOMASTON CREEK | 246T1 | 2024-02-21 | Fail | Fail | 2024-05-07 | Yes
100814 | 2024-01-25 | 2024-02-07 | Solar | 233.3 | 620D4 | ELM STREET | 620T2 | 2024-02-09 | Fail | Pass | 2024-04-02
100792 | 2024-01-24 | 2024-02-23 | Solar | 999 | 467D1 | TURNER TAP | Tap off of Transmission Line | 2024-02-26 | Fail | Pass | 2024-04-24
100687 | 2024-01-12 | 2024-01-18 | Solar | 500 | 256D2 | WINTHROP | 256T1 | 2024-01-19 | Fail |  |  | Yes
100680 | 2024-01-11 | 2024-01-22 | Solar | 380 | 668D3 | SPRING STREET | 668T2 | 2024-02-05 | Pass
100681 | 2024-01-11 | 2024-01-22 | Solar | 999 | 685D2 | BOLT HILL | 685T1 | 2024-02-13 | Fail | Pass | 2024-04-12
100682 | 2024-01-11 | 2024-01-22 | Solar | 999 | 603D3 | BERWICK | 603T1 | 2024-02-22 | Fail | Fail | 2024-04-26 | Yes
100620 | 2024-01-05 | 2024-01-05 | Solar | 400 | 412D1 | DEER RIPS | 412T2 | 2024-01-09 | Fail | Pass | 2024-03-18
100623 | 2024-01-05 | 2024-01-08 | Solar | 720 | 412D1 | DEER RIPS | 412T2 | 2024-01-09 | Fail | Pass | 2024-03-11
100571 | 2023-12-29 | 2024-01-16 | Solar | 750 | 200D3 | AUGUSTA K5 | 200T1 | 2024-01-16 | Fail | Pass | 2024-03-20
100520 | 2023-12-22 | 2024-01-09 | Solar | 500 | 660D2 | SHAWS MILL ROAD | 660T1 | 2024-01-13 | Fail | Pass | 2024-02-15
100461 | 2023-12-15 | 2024-01-10 | Solar | 999 | 818D2 | FARMINGTON FALLS | 818T1 | 2024-01-17 | Fail | Pass | 2024-04-11
100388 | 2023-12-11 | 2023-12-15 | Solar | 350 | 421D2 | CHALLENGER | 421T1 | 2024-01-03 | Fail | Pass | 2024-02-21
100360 | 2023-12-08 |  | Solar | 999 | [7 empty] | Yes
100368 | 2023-12-08 | 2023-12-14 | Solar | 330 | 841D1 | PHILLIPS/STRONG | 841T1 | 2024-01-03 | Fail |  |  | Yes
100376 | 2023-12-08 | 2023-12-15 | Solar | 999 | 855D2 | SOUTH WATERVILLE | 855T1 | 2023-12-18 | Fail | Fail | 2024-02-08 | Yes
100379 | 2023-12-08 |  | Solar | 1000 | [7 empty] | Yes
100340 | 2023-12-07 | 2023-12-11 | Solar | 360 | 215D2 | CAPITOL STREET | 215T2 | 2023-12-11 | Fail | Pass | 2024-02-09
100354 | 2023-12-07 | 2024-01-08 | Solar | 999 | 632D1 | LIMERICK | 632T1 | 2024-02-01 | Fail | Fail | 2024-04-09 | Yes
100324 | 2023-12-06 | 2023-12-12 | Solar | 360 | 273D5 | BRUNSWICK HYDRO | 273T2 | 2024-01-02 | Pass
100307 | 2023-12-05 | 2023-12-06 | Solar | 540 | 249D2 | TOPSHAM OLD | 249T1 | 2023-12-27 | Fail | Pass | 2024-03-11
100263 | 2023-12-01 | 2024-01-10 | Solar | 900 | 818D1 | FARMINGTON FALLS | 818T1 | 2024-01-17 | Fail | Pass | 2024-03-18 | Yes
100265 | 2023-12-01 | 2023-12-06 | Solar | 240 | 865D1 | WEST WATERVILLE | 865T1 | 2023-12-06 | Fail | Pass | 2024-01-29
100266 | 2023-12-01 | 2023-12-06 | Solar | 400 | 639D2 | NORTH WINDHAM | 639T2 | 2023-12-11 | Fail | Pass | 2024-03-08
100267 | 2023-12-01 | 2023-12-06 | Solar | 240 | 681D3 | BRANCH BROOK | 681T3 | 2023-12-27 | Pass
100268 | 2023-12-01 | 2023-12-06 | Solar | 500 | 681D3 | BRANCH BROOK | 681T3 | 2023-12-26 | Pass
100245 | 2023-11-30 | 2023-12-07 | Solar | 120 | 249D1 | TOPSHAM OLD | 249T1 | 2023-12-29 | Fail | Pass | 2024-02-22
100251 | 2023-11-30 | 2023-12-07 | Solar | 100 | 249D1 | TOPSHAM OLD | 249T1 | 2024-01-02 | Fail | Pass | 2024-02-19
100252 | 2023-11-30 | 2024-01-17 | Solar | 1020 | 471D1 | LEEDS | 471T1 | 2024-01-23 | Fail | Fail | 2024-04-29 | Yes
100255 | 2023-11-30 | 2023-12-15 | Solar | 1020 | 873D1 | COUNTY RD (RICE RIPS) | 873T1 | 2023-12-18 | Fail |  |  | Yes
100222 | 2023-11-29 | 2023-11-30 | Solar | 996 | 678D1 | BAR MILLS | 678T4 | 2023-12-26 | Fail | Fail | 2024-03-21 | Yes
100227 | 2023-11-29 | 2023-12-12 | Solar | 1020 | 450D2 | SABATTUS | 450T1 | 2023-12-26 | Fail | Fail | 2024-03-11 | Yes
100140 | 2023-11-27 | 2023-12-07 | Solar | 360 | 668D3 | SPRING STREET | 668T2 | 2023-12-11 | Pass
100119 | 2023-11-22 | 2023-11-29 | Solar | 996 | 453D1 | TRAP CORNER | 453T1 | 2023-12-05 | Fail |  |  | Yes
100126 | 2023-11-22 | 2023-12-06 | Solar | 360 | 233D1 | MANCHESTER | 233T1 | 2023-12-06 | Fail | Fail | 2024-02-20 | Yes
100128 | 2023-11-22 | 2023-12-07 | Solar | 420 | 213D4 | BRUNSWICK WEST SIDE | 213T2 | 2023-12-29 | Pass
100129 | 2023-11-22 | 2023-12-06 | Solar | 480 | 668D3 | SPRING STREET | 668T2 | 2023-12-11 | Fail |  |  | Yes
100091 | 2023-11-17 | 2023-11-27 | Solar | 975 | 461D1 | LUDDEN LANE | 461T1 | 2023-12-11 | Fail | Pass | 2024-02-12
100056 | 2023-11-16 | 2023-11-27 | Solar | 120 | 208D1 | BOND BROOK | 208T1 | 2023-11-27 | Fail |  |  | Yes
100057 | 2023-11-16 | 2023-11-27 | Solar | 120 | 453D1 | TRAP CORNER | 453T1 | 2023-11-28 | Fail |  |  | Yes
100000 | 2023-11-15 | 2023-11-27 | Solar | 994 | 210D1 | BRISTOL | 210T1 | 2023-12-18 | Fail | Pass | 2024-01-25
100001 | 2023-11-15 | 2023-11-27 | Solar | 700 | 870D1 | WINSLOW | 870T4 | 2023-11-28 | Fail | Fail | 2024-01-02 | Yes
100002 | 2023-11-15 | 2023-11-22 | Solar | 994 | 454D1 | TURNER | 454T1 | 2023-11-28 | Fail | Fail | 2024-01-25 | Yes
100049 | 2023-11-15 | 2024-01-04 | Solar | 1020 | 858D2 | STURTEVANT | 858T1 | 2024-01-05 | Fail |  |  | Yes
85879 | 2023-11-13 | 2023-11-20 | Solar | 999 | 695D2 | LEBANON | 695T1 | 2023-12-13 | Fail | Fail | 2024-02-14 | Yes
85877 | 2023-11-10 | 2023-11-13 | Solar | 995 | 842D1 | PITTSFIELD | 842T1 | 2023-11-14 | Fail | Pass | 2023-12-08
85876 | 2023-11-09 | 2023-12-06 | Solar | 100 | 803D5 | BELFAST WEST SIDE | 803T1 | 2023-12-29 | Fail | Pass | 2024-02-21
85862 | 2023-11-08 | 2023-11-15 | Solar | 150 | 233D1 | MANCHESTER | 233T1 | 2023-11-15 | Fail | Pass | 2024-01-02
85875 | 2023-11-08 | 2023-12-11 | Solar | 999 | 837D2 | NEWPORT | 837T2 | 2023-12-11 | Fail | Pass | 2024-01-17 | Yes
85805 | 2023-11-03 | 2023-11-09 | Solar | 999 | 813D1 | DEXTER | 813T1 | 2023-11-17 | Fail | Pass | 2024-01-02
85807 | 2023-11-03 | 2023-11-09 | Solar | 999 | 256D2 | WINTHROP | 256T1 | 2023-11-10 | Fail | Pass | 2023-12-06
85736 | 2023-11-02 | 2023-11-02 | Solar | 999 | 471D2 | LEEDS | 471T1 | 2023-11-08 | Fail | Pass | 2024-01-02
85743 | 2023-11-02 | 2023-11-14 | Solar | 560 | 412D1 | DEER RIPS | 412T2 | 2023-11-17 | Fail | Pass | 2024-01-11
85721 | 2023-11-01 | 2023-11-13 | Solar | 970 | 239D6 | PARK STREET | 239T2 | 2023-11-14 | Fail | Pass | 2024-01-17
85727 | 2023-11-01 | 2023-11-13 | Solar | 625 | 230D1 | COOPERS MILLS ROAD | 230T2 | 2023-11-13 | Fail | Pass | 2024-01-25
85695 | 2023-10-31 | 2023-11-13 | Solar | 300 | 865D5 | WEST WATERVILLE | 865T2 | 2023-11-14 | Fail | Pass | 2024-01-29
85703 | 2023-10-31 | 2023-11-03 | Solar | 975 | 421D2 | CHALLENGER | 421T1 | 2023-11-09 | Fail | Pass | 2023-12-06 | Yes
85663 | 2023-10-27 | 2023-11-03 | Solar | 600 | 612D2 | BUTLER'S CORNER | 612T1 | 2023-11-28 | Fail | Fail | 2024-02-14 | Yes
85622 | 2023-10-24 | 2023-11-13 | Solar | 152 | 423D2 | KIMBALL ROAD | 423T2 | 2023-11-14 | Fail | Pass | 2024-01-11
85588 | 2023-10-18 | 2023-10-24 | Solar | 600 | 865D1 | WEST WATERVILLE | 865T1 | 2023-10-25 | Pass
85484 | 2023-10-13 | 2023-10-18 | Solar | 975 | 447D1 | RUMFORD | 447T3 | 2023-10-30 | Pass
85488 | 2023-10-13 | 2023-10-19 | Solar | 500 | 208D1 | BOND BROOK | 208T1 | 2023-10-19 | Fail | Pass | 2023-11-27
85228 | 2023-09-28 | 2023-10-04 | Solar | 975 | 261D4 | BATH 34 | 261T2 | 2023-10-26 | Fail | Fail | 2023-11-10 | Yes
85186 | 2023-09-26 | 2023-10-17 | Solar | 900 | 667D3 | SOUTH SANFORD | 667T1 | 2023-11-14 | Fail | Pass | 2024-01-24
85197 | 2023-09-26 | 2023-10-02 | Solar | 480 | 423D1 | KIMBALL ROAD | 423T2 | 2023-10-05 | Fail | Pass | 2023-11-10
85173 | 2023-09-25 | 2023-09-28 | Solar | 250 | 673D1 | BIDDEFORD INDUSTRIAL PARK | 673T2 | 2023-10-23 | Pass
85069 | 2023-09-15 | 2023-10-04 | Solar | 975 | 466D1 | RUMFORD INDUSTRIAL PARK | 466T1 | 2023-10-06 | Fail | Fail | 2023-11-10 | Yes
85041 | 2023-09-13 | 2023-09-27 | Solar | 994 | 263D1 | BOWMAN STREET | 34kV BUS 2 | 2023-09-28 | Fail | Pass | 2023-10-25
85031 | 2023-09-12 | 2023-10-12 | Solar | 1999 | 225D3 | FREEPORT | 225T2 | 2023-10-26 | Fail |  |  | Yes
85012 | 2023-09-11 | 2023-09-18 | Solar | 1050 | 207D1 | BLAIR ROAD | 207T1 | 2023-09-19 | Fail | Fail | 2023-10-25 | Yes
84974 | 2023-09-08 | 2023-09-13 | Solar | 975 | 233D1 | MANCHESTER | 233T1 | 2023-09-13 | Fail | Pass | 2023-09-29
84979 | 2023-09-08 | 2023-09-13 | Solar | 975 | 219D2 | DAMARISCOTTA MILLS | 219T1 | 2023-09-19 | Fail | Pass | 2023-10-12
84902 | 2023-09-05 | 2023-09-12 | Other | 100 | 855D1 | SOUTH WATERVILLE | 855T1 | 2023-09-06 | Fail | Pass | 2023-10-12
84904 | 2023-09-05 | 2023-09-11 | Solar | 150 | 252D2 | WALDOBORO | 252T1 | 2023-09-15 | Fail | Pass | 2023-10-12
84764 | 2023-08-23 | 2023-09-19 | Solar | 500 | 210D2 | BRISTOL | 210T1 | 2023-10-11 | Fail | Fail | 2023-12-08 | Yes
84691 | 2023-08-17 | 2023-08-25 | Solar | 144.48 | 667D1 | SOUTH SANFORD | 667T2 | 2023-08-31 | Fail | Pass | 2023-10-12
84683 | 2023-08-14 |  | Solar | 799.98 | 874D1 | BELFAST 115 | 874T2 |  |  |  |  | Yes
84684 | 2023-08-14 | 2023-08-28 | Solar | 100 | 239D7 | PARK STREET | 239T2 | 2023-08-31 | Pass
84618 | 2023-08-09 | 2023-08-10 | Solar | 999 | 412D1 | DEER RIPS | 412T2 | 2023-08-11 | Fail | Pass | 2023-09-28
84619 | 2023-08-09 | 2023-08-10 | Solar | 996 | 870D1 | WINSLOW | 870T4 | 2023-08-11 | Fail | Fail | 2023-09-14 | Yes
84757 | 2023-08-09 | 2023-09-08 | Solar | 999.6 | 808D3 | CARMEL TAP | 808T1 | 2023-09-26 | Pass
84609 | 2023-08-08 | 2023-08-21 | Solar | 999 | 821D1 | GUILFORD | 821T1 | 2023-08-22 | Fail | Pass | 2023-12-01
84547 | 2023-08-01 | 2023-08-04 | Solar | 999 | 412D4 | DEER RIPS | 412T4 | 2023-08-07 | Fail | Fail | 2023-10-25 | Yes
84553 | 2023-08-01 | 2023-08-04 | Solar | 999 | 412D4 | DEER RIPS | 412T4 | 2023-08-07 | Fail | Fail | 2023-10-25 | Yes
84450 | 2023-07-25 | 2023-07-27 | Solar | 996 | 695D2 | LEBANON | 695T1 | 2023-08-24 | Fail | Pass | 2023-10-12
84451 | 2023-07-25 | 2023-07-27 | Solar | 996 | 663D2 | SOUTH BERWICK | 663T1 | 2023-08-24 | Fail | Fail | 2023-10-12 | Yes
84452 | 2023-07-25 | 2023-07-27 | Solar | 996 | 225D4 | FREEPORT | 225T1 | 2023-08-17 | Fail | Fail | 2023-10-03 | Yes
84411 | 2023-07-20 | 2023-08-07 | Solar | 999 | 632D2 | LIMERICK | 632T1 | 2023-08-31 | Fail |  |  | Yes
84416 | 2023-07-20 | 2023-08-07 | Solar | 999 | 632D2 | LIMERICK | 632T1 | 2023-08-31 | Fail |  |  | Yes
84392 | 2023-07-18 | 2023-08-21 | Solar | 200 | 607D1 | BISHOP STREET | 607T1 | 2023-09-08 | Pass
84389 | 2023-07-17 | 2023-07-26 | Solar | 975 | 232D2 | LISBON FALLS | 232T2 | 2023-08-11 | Fail | Fail | 2023-09-20 | Yes
84338 | 2023-07-13 | 2023-07-19 | Solar | 975 | 244D1 | SOUTH CHINA | 244T1 | 2023-07-19 | Fail | Fail | 2023-08-16 | Yes
84350 | 2023-07-13 | 2023-07-19 | Solar | 975 | 255D2 | WEST STREET | 255T1 | 2023-07-19 | Fail | Pass | 2023-08-23
84304 | 2023-07-10 | 2023-07-10 | Solar | 750 | 858D2 | STURTEVANT | 858T1 | 2023-07-13 | Pass
84290 | 2023-07-06 | 2023-07-10 | Solar | 975 | 808D1 | CARMEL | 808T1 | 2023-07-14 | Fail | Pass | 2023-08-31 | Yes
84276 | 2023-07-05 | 2023-07-21 | Solar | 999 | 837D1 | NEWPORT | 837T1 | 2023-07-24 | Fail | Pass | 2023-08-11
84277 | 2023-07-05 | 2023-07-21 | Solar | 999 | 837D1 | NEWPORT | 837T1 | 2023-07-24 | Fail | Pass | 2023-09-06
84278 | 2023-07-05 | 2023-07-21 | Solar | 999 | 837D1 | NEWPORT | 837T1 | 2023-07-24 | Fail | Pass | 2023-09-06
84279 | 2023-07-05 | 2023-07-21 | Solar | 999 | 837D1 | NEWPORT | 837T1 | 2023-07-24 | Fail | Fail | 2023-09-06 | Yes
84280 | 2023-07-05 | 2023-07-21 | Solar | 999 | 837D1 | NEWPORT | 837T1 | 2023-07-24 | Fail | Fail | 2023-09-06 | Yes
84272 | 2023-06-30 | 2023-07-05 | Solar | 825 | 253D1 | WARREN | 253T1 | 2023-07-06 | Fail | Pass | 2023-08-01
84231 | 2023-06-29 | 2023-07-10 | Solar | 996 | 461D1 | LUDDEN LANE | 461T1 | 2023-07-13 | Fail | Pass | 2023-08-11
84228 | 2023-06-28 | 2023-06-30 | Solar | 999 | 860D1 | UNITY | 860T1 | 2023-07-10 | Fail | Fail | 2023-08-30 | Yes
84222 | 2023-06-27 | 2023-07-05 | Solar | 120 | 678D1 | BAR MILLS | 678T4 | 2023-07-26 | Fail | Pass | 2023-09-11
84188 | 2023-06-23 | 2023-06-28 | Solar | 975 | 238D1 | MESSINA | 238T1 | 2023-07-20 | Fail | Fail | 2023-08-16 | Yes
84211 | 2023-06-23 | 2023-07-07 | Solar | 160 | 689D1 | BRAGDON COMMONS | 689T1 | 2023-07-26 | Fail | Pass | 2023-09-20
84117 | 2023-06-16 | 2023-06-21 | Solar | 975 | 858D1B | STURTEVANT | 858T2 | 2023-07-06 | Fail | Pass | 2023-09-25
84104 | 2023-06-14 | 2023-07-05 | Solar | 1000 | 815D2 | DOVER | 815T2 | 2023-07-06 | Fail |  |  | Yes
84107 | 2023-06-14 | 2023-06-15 | Solar | 999 | 636D1 | MUSSEY ROAD | 636T1 | 2023-06-30 | Fail | Pass | 2023-08-08 | Yes
84070 | 2023-06-12 | 2023-06-15 | Solar | 975 | 860D2 | UNITY | 860T1 | 2023-06-29 | Fail | Pass | 2023-07-27
84071 | 2023-06-12 | 2023-06-14 | Solar | 975 | 858D1A | STURTEVANT | 858T1 | 2023-06-15 | Fail | Pass | 2023-07-18 | Yes
84066 | 2023-06-09 | 2023-06-12 | Solar | 995 | 471D1 | LEEDS | 471T1 | 2023-06-15 | Fail | Fail | 2023-07-10 | Yes
84068 | 2023-06-09 | 2023-06-13 | Solar | 875 | 253D1 | WARREN | 253T1 | 2023-06-28 | Fail |  |  | Yes
84024 | 2023-06-07 | 2023-06-13 | Solar | 975 | 431D1 | MECHANIC FALLS | 431T2 | 2023-06-15 | Fail | Pass | 2023-07-18
83991 | 2023-06-02 | 2023-06-08 | Solar | 160 | 852D1 | SHAWMUT | 852T3 | 2023-06-09 | Fail | Pass | 2023-07-25
84004 | 2023-06-02 | 2023-06-21 | Solar | 999 | 256D1 | WINTHROP | 256T2 | 2023-06-27 | Fail | Pass | 2023-08-16
83944 | 2023-05-26 | 2023-06-01 | Solar | 975 | 639D2 | NORTH WINDHAM | 639T2 | 2023-06-07 | Fail | Pass | 2023-07-12
83909 | 2023-05-24 | 2023-06-05 | Solar | 999 | 813D1 | DEXTER | 813T1 | 2023-06-07 | Fail | Fail | 2023-07-14 | Yes
83914 | 2023-05-24 | 2023-06-05 | Solar | 999 | 885D1 | WILTON | 885T1 | 2023-06-07 | Fail | Pass | 2023-07-14
83916 | 2023-05-24 | 2023-06-05 | Solar | 999 | 885D1 | WILTON | 885T1 | 2023-06-07 | Fail | Fail | 2023-07-14 | Yes
83894 | 2023-05-22 | 2023-05-25 | Solar | 900 | 691D1 | BALDWIN | 691T1 | 2023-05-25 | Fail | Fail | 2023-06-21 | Yes
83856 | 2023-05-17 | 2023-05-22 | Solar | 154 | 274D1 | MAINE YANKEE | 274T2 | 2023-05-23 | Fail | Pass | 2023-07-20
83838 | 2023-05-16 | 2023-05-22 | Solar | 200 | 239D7 | PARK STREET | 239T2 | 2023-05-23 | Pass
83837 | 2023-05-15 | 2023-05-17 | Solar | 720 | 428D2 | LIVERMORE FALLS | 428T1 | 2023-05-18 | Pass
83829 | 2023-05-12 | 2023-05-15 | Solar | 995 | 412D3 | DEER RIPS | 412T4 | 2023-05-18 | Fail | Pass | 2023-06-06
83793 | 2023-05-09 | 2023-05-11 | Solar | 975 | 400D1 | ANDOVER | 400T1 | 2023-05-12 | Fail | Pass | 2023-06-20
83777 | 2023-05-08 | 2023-05-09 | Solar | 999 | 805D1 | BROOKS | 805T1 | 2023-05-10 | Fail | Fail | 2023-08-08 | Yes
83779 | 2023-05-08 | 2023-05-10 | Solar | 996 | 813D3 | DEXTER | 813T2 | 2023-05-12 | Fail | Fail | 2023-08-08 | Yes
83787 | 2023-05-08 | 2023-05-10 | Solar | 996 | 406D2 | BRIDGTON | 406T1 | 2023-05-17 | Fail | Fail | 2023-07-26 | Yes
83769 | 2023-05-05 | 2023-05-08 | Solar | 240 | 630D4 | GOOSEFARE | 630T1 | 2023-05-17 | Fail | Pass | 2023-06-22
83738 | 2023-05-04 | 2023-05-11 | Solar | 975 | 466D1 | RUMFORD INDUSTRIAL PARK | 466T1 | 2023-05-12 | Fail | Pass | 2023-06-01 | Yes
83720 | 2023-05-03 | 2023-05-25 | Solar | 1000 | 834D1 | MONSON | 834T1 | 2023-05-30 | Fail | Fail | 2023-06-22 | Yes
83685 | 2023-04-28 | 2023-05-01 | Solar | 324 | 858D1A | STURTEVANT | 858T1 | 2023-05-01 | Fail | Pass | 2023-05-03
83664 | 2023-04-27 | 2023-05-01 | Solar | 700 | 816D1 | EAST WILTON | 816T1 | 2023-05-02 | Fail | Pass | 2023-06-01
83668 | 2023-04-27 | 2023-05-01 | Solar | 975 | 233D2 | MANCHESTER | 233T1 | 2023-05-03 | Fail | Pass | 2023-05-11 | Yes
83670 | 2023-04-27 | 2023-05-01 | Solar | 975 | 262D1 | PUDDLEDOCK ROAD | 34 kV BUS 1 | 2023-05-09 | Fail | Pass | 2023-06-16
83611 | 2023-04-24 | 2023-05-03 | Solar | 120 | 617D3 | DUNSTAN | 617T1 | 2023-05-15 | Pass
83605 | 2023-04-21 | 2023-04-27 | Solar | 975 | 431D1 | MECHANIC FALLS | 431T2 | 2023-04-27 | Fail | Pass | 2023-06-05
83600 | 2023-04-20 | 2023-04-21 | Solar | 850 | 450D1 | SABATTUS | 450T1 | 2023-04-24 | Fail | Pass | 2023-06-21
83601 | 2023-04-20 | 2023-04-25 | Solar | 700 | 256D2 | WINTHROP | 256T1 | 2023-04-25 | Fail | Pass | 2023-05-11
83526 | 2023-04-12 | 2023-05-01 | Solar | 1000 | 821D3 | GUILFORD | 821T2 | 2023-05-02 | Fail | Fail | 2023-05-18 | Yes
83507 | 2023-04-11 | 2023-04-14 | Solar | 975 | 639D2 | NORTH WINDHAM | 639T2 | 2023-05-02 | Fail | Pass | 2023-05-23
83514 | 2023-04-11 | 2023-04-13 | Solar | 995 | 858D3 | STURTEVANT | 858T2 | 2023-04-18 | Fail | Pass | 2023-05-01
83474 | 2023-04-05 | 2023-04-07 | Solar | 999 | 605D1 | BIDDEFORD PUMPING STATION | 605T1 | 2023-05-03 | Pass | Pass | 2023-06-26
83455 | 2023-04-03 | 2023-04-18 | Solar | 999 | 602D3 | BASSETT | 602T1 | 2023-05-03 | Fail | Pass | 2023-06-23
83453 | 2023-03-31 | 2023-04-05 | Solar | 975 | 858D1A | STURTEVANT | 858T1 | 2023-04-05 | Fail | Fail | 2023-04-24 | Yes
83437 | 2023-03-28 | 2023-04-06 | Solar | 120 | 634D4 | MAY STREET | 634T1 | 2023-05-03 | Pass
83403 | 2023-03-27 | 2023-04-03 | Solar | 125 | 693D1 | SCARBOROUGH | 693T1 | 2023-04-05 | Pass |  |  | Yes
83401 | 2023-03-24 | 2023-03-29 | Solar | 250 | 436D6 | GREAT FALLS | 436T1 | 2023-03-30 | Fail | Pass | 2023-04-24 | Yes
83384 | 2023-03-23 | 2023-03-29 | Solar | 600 | 673D1 | BIDDEFORD INDUSTRIAL PARK | 673T2 | 2023-04-19 | Fail | Pass | 2023-06-02
83361 | 2023-03-21 | 2023-03-24 | Solar/Battery | 996 | 834D1 | MONSON | 834T1 | 2023-03-28 | Fail | Pass | 2023-05-16
83350 | 2023-03-20 | 2023-03-23 | Solar | 999 | 253D1 | WARREN | 253T1 | 2023-04-12 | Fail | Fail | 2023-05-11 | Yes
83328 | 2023-03-16 | 2023-03-20 | Solar | 720 | 653D5 | FORE RIVER | 653T1 | 2023-04-03 | Fail | Pass | 2023-05-01
83307 | 2023-03-14 | 2023-03-21 | Solar/Battery | 996 | 813D1 | DEXTER | 813T1 | 2023-03-22 | Fail | Pass | 2023-07-07
83298 | 2023-03-13 | 2023-03-16 | Solar | 120 | 200D1 | AUGUSTA K5 | 200T1 | 2023-03-16 | Pass
83253 | 2023-03-06 | 2023-03-15 | Solar | 120 | 656D1 | SANFORD INDUSTRIAL PARK | 656T1 | 2023-04-04 | Pass
83260 | 2023-03-06 | 2023-03-10 | Solar | 400 | 211D1 | BROWNS CROSSING | 211T1 | 2023-03-13 | Pass
83231 | 2023-03-02 | 2023-03-20 | Solar | 150 | 232D2 | LISBON FALLS | 232T2 | 2023-03-29 | Pass
83235 | 2023-03-02 | 2023-03-06 | Fuel Cell | 930 | 688D1 | KITTERY | 688T1 | 2023-03-28 | Pass
83229 | 2023-03-01 | 2023-03-03 | Fuel Cell | 600 | 420D1 | HOTEL ROAD | 420T2 | 2023-03-14 | Pass
83208 | 2023-02-24 | 2023-03-03 | Solar | 999 | 447D2 | RUMFORD | 447T4 | 2023-03-14 | Fail | Pass | 2023-04-18
83189 | 2023-02-22 | 2023-02-22 | Solar | 1500 | 612D1 | BUTLER'S CORNER | 612T1 | 2023-03-21 | Fail |  |  | Yes
83186 | 2023-02-21 | 2023-02-23 | Solar | 995 | 256D2 | WINTHROP | 256T1 | 2023-02-24 | Fail | Pass | 2023-03-23
83158 | 2023-02-16 | 2023-03-13 | Solar | 160 | 690D1 | HINCKLEY POND | 690T1 | 2023-03-23 | Pass |  |  | Yes
83159 | 2023-02-16 | 2023-03-01 | Solar | 120 | 255D2 | WEST STREET | 255T1 | 2023-03-23 | Fail |  |  | Yes
83131 | 2023-02-14 | 2023-02-21 | Solar | 240 | 621D2 | FACTORY ISLAND | 621T2 | 2023-03-07 | Pass
83095 | 2023-02-13 | 2023-02-24 | Solar | 300 | 239D7 | PARK STREET | 239T2 | 2023-03-16 | Pass
83116 | 2023-02-13 | 2023-02-22 | Solar | 133.2 | 650D4 | RIGBY | 650T2 | 2023-03-01 | Pass
83066 | 2023-02-09 | 2023-02-13 | Solar | 160 | 629D3 | KENNEBUNKPORT | 629T2 | 2023-03-07 | Pass
83040 | 2023-02-08 | 2023-02-23 | Solar | 999 | 837D2 | NEWPORT | 837T2 | 2023-03-07 | Fail | Pass | 2023-04-05
83025 | 2023-02-07 | 2023-02-09 | Solar | 995 | 256D2 | WINTHROP | 256T1 | 2023-02-23 | Fail | Pass | 2023-03-22
83038 | 2023-02-07 | 2023-02-09 | Solar | 100 | 447D4 | RUMFORD | 447T3 | 2023-02-24 | Pass
83018 | 2023-02-03 | 2023-02-09 | Solar | 300 | 620D1 | ELM STREET | 620T2 | 2023-02-28 | Fail | Pass | 2023-04-03
83014 | 2023-02-02 | 2023-02-13 | Solar | 200 | 630D2 | GOOSEFARE | 630T1 | 2023-03-07 | Pass
83016 | 2023-02-02 | 2023-03-03 | Solar | 240 | 630D4 | GOOSEFARE | 630T1 | 2023-04-04 | Fail |  |  | Yes
82985 | 2023-01-30 | 2023-02-09 | Solar | 200 | 656D2 | SANFORD INDUSTRIAL PARK | 656T1 | 2023-02-21 | Pass
82971 | 2023-01-27 | 2023-02-01 | Solar | 100 | 634D4 | MAY STREET | 634T1 | 2023-02-22 | Pass
82924 | 2023-01-20 | 2023-01-23 | Fuel Cell | 975 | 636D2 | MUSSEY ROAD | 636T1 | 2023-03-03 | Pass
82927 | 2023-01-20 | 2023-01-24 | Solar | 500 | 447D4 | RUMFORD | 447T3 | 2023-02-14 | Pass
82862 | 2023-01-06 | 2023-01-10 | Solar | 400 | 813D3 | DEXTER | 813T2 | 2023-01-13 | Pass |  |  | Yes
82873 | 2023-01-06 | 2023-01-11 | Solar | 360 | 650D4 | RIGBY | 650T2 | 2023-02-06 | Pass
82874 | 2023-01-06 | 2023-02-06 | Solar | 999 | 821D1 | GUILFORD | 821T1 | 2023-02-07 | Fail | Fail | 2023-03-02 | Yes
82822 | 2023-01-05 | 2023-01-09 | Solar | 145.92 | 251D1 | UNION | 251T1 | 2023-01-26 | Fail | Pass | 2023-02-01
82781 | 2022-12-28 | 2023-01-18 | Fuel Cell | 975 | 630D1 | GOOSEFARE | 630T1 | 2023-01-26 | Pass |  |  | Yes
82771 | 2022-12-22 | 2023-01-06 | Solar | 996 | 657D4 | SANFORD SWITCH | 657T1 | 2023-01-30 | Fail | Pass | 2023-04-18
82708 | 2022-12-14 | 2023-01-09 | Solar | 500 | 238D1 | MESSINA | 238T1 | 2023-01-11 | Fail | Pass | 2023-03-27
82709 | 2022-12-14 |  |  | 999 | 610D2 | BONNY EAGLE | 610T4 |  |  |  |  | Yes
82674 | 2022-12-13 | 2023-01-03 | Solar | 999 | 821D1 | GUILFORD | 821T1 | 2023-01-03 | Fail |  |  | Yes
82683 | 2022-12-13 | 2023-01-11 | Solar | 700 | 624D2 | FORT HILL | 624T1 | 2023-02-07 | Pass
82671 | 2022-12-08 | 2022-12-12 | Fuel Cell | 650 | 420D3 | HOTEL ROAD | 420T2 | 2023-01-16 | Pass
82669 | 2022-12-06 | 2022-12-23 | Solar | 975 | 239D7 | PARK STREET | 239T2 | 2023-01-12 | Fail | Fail | 2023-02-22 | Yes
82584 | 2022-11-29 | 2022-12-12 | Solar | 890 | 420D6 | HOTEL ROAD | 420T1 | 2022-12-13 | Fail | Pass | 2023-02-23
82564 | 2022-11-23 | 2022-12-12 | Solar | 1950 | 693D1 | SCARBOROUGH | 693T1 | 2023-02-13 | Fail |  |  | Yes
82547 | 2022-11-21 | 2022-11-30 | Fuel Cell | 975 | 421D2 | CHALLENGER | 421T1 |  | Fail |  |  | Yes
82518 | 2022-11-16 | 2022-11-29 | Fuel Cell | 975 | 424D4 | LEWISTON LOWER | 424T3 | 2023-01-13 | Pass
82496 | 2022-11-14 | 2022-11-18 | Fuel Cell | 975 | 688D1 | KITTERY | 688T1 | 2023-01-15 | Fail |  |  | Yes
82499 | 2022-11-14 | 2022-11-29 | Solar | 500 | 233D2 | MANCHESTER | 233T1 | 2022-11-30 | Fail | Pass | 2023-05-01
82486 | 2022-11-07 | 2022-11-30 | Fuel Cell | 975 | 630D2 | GOOSEFARE | 630T1 | 2023-01-06 | Pass
82485 | 2022-11-05 | 2022-11-30 | Fuel Cell | 975 | 420D6 | HOTEL ROAD | 420T1 | 2023-01-09 | Pass
82455 | 2022-11-03 | 2022-12-05 | Solar | 100 | 250D2 | TOPSHAM | 250T2 | 2023-05-10 | Pass | Pass | 2023-02-13
82439 | 2022-11-01 | 2022-11-01 | Solar | 950 | 858D4 | STURTEVANT | 858T2 | 2022-11-01 | Pass
82404 | 2022-10-26 | 2022-11-15 | Solar | 750 | 445D1 | RAYMOND 115 KV | 445T1 | 2022-11-17 | Fail |  | 2023-06-21 | Yes
82373 | 2022-10-21 | 2022-11-01 | Solar | 104.16 | 245D2 | STICKNEYS CORNER | 245T1 | 2022-11-02 | Fail | Pass | 2023-02-01
82363 | 2022-10-20 | 2022-11-16 | Fuel Cell | 975 | 636D2 | MUSSEY ROAD | 636T1 | 2022-12-27 | Fail |  |  | Yes
82366 | 2022-10-20 | 2022-10-24 | Solar | 996 | 657D4 | SANFORD SWITCH | 657T1 | 2022-12-27 | Fail | Pass | 2023-04-18
82339 | 2022-10-18 | 2022-11-14 | Solar | 975 | 841D1 | PHILLIPS/STRONG | 841T1 | 2023-01-25 | Fail | Pass | 2023-02-23
82340 | 2022-10-18 | 2022-12-02 | Solar | 975 | 839D2 | OAKLAND | 839T1 | 2022-12-02 | Fail | Fail | 2023-03-30 | Yes
82322 | 2022-10-17 | 2022-10-19 | Solar | 995 | 667D1 | SOUTH SANFORD | 667T2 | 2022-12-01 | Fail | Pass | 2023-03-22 | Yes
82324 | 2022-10-17 | 2022-10-17 | Solar | 975 | 450D1 | SABATTUS | 450T1 | 2022-11-22 | Fail | Fail | 2023-01-23 | Yes
82261 | 2022-10-05 | 2022-11-01 | Solar | 950 | 858D4 | STURTEVANT | 858T2 | 2022-11-02 | Pass
82255 | 2022-10-04 | 2022-10-04 | Solar | 975 | 821D1 | GUILFORD | 821T1 | 2022-10-14 | Fail | Pass | 2023-02-07
82233 | 2022-09-27 | 2022-10-04 | Solar | 100 | 659D9 | SEWALL STREET | 659T2 | 2022-10-12 | Pass
82226 | 2022-09-23 | 2022-09-27 | Solar | 349.998 | 813D1 | DEXTER | 813T1 | 2022-09-28 | Pass |  |  | Yes
82201 | 2022-09-20 | 2022-09-30 | Solar | 390 | 261D3 | BATH 34 | 261T2 | 2022-10-06 | Fail | Pass | 2022-11-30
82202 | 2022-09-20 | 2022-12-02 | Solar | 996 | 407D1 | BRYANT POND | 407T1 | 2022-12-05 | Fail |  |  | Yes
82186 | 2022-09-15 | 2022-10-03 | Solar | 348 | 250D1 | TOPSHAM | 250T2 | 2022-10-03 | Fail |  |  | Yes
82151 | 2022-09-09 | 2022-09-09 | Solar | 160 | 213D3 | BRUNSWICK WEST SIDE | 213T1 | 2022-09-23 | Pass
82152 | 2022-09-09 | 2022-09-12 | Solar | 260 | 273D4 | BRUNSWICK HYDRO | 273T2 | 2022-10-04 | Fail | Pass | 2023-01-23
82143 | 2022-09-08 | 2022-09-30 | Solar | 228 | 860D1 | UNITY | 860T1 | 2023-03-09 | Fail |  |  | Yes
82084 | 2022-08-29 | 2022-09-09 | Solar | 1000 | 416D1 | GRAY | 416T2 | 2022-10-07 | Fail | Fail |  | Yes
82055 | 2022-08-25 | 2022-12-01 | Solar | 275 | 823D2 | HARRIS | 823T5 | 2023-02-24 | Pass
82053 | 2022-08-23 | 2022-08-23 | Solar | 1000 | 846D1 | PROSPECT | 846T1 | 2022-09-02 | Fail | Pass | 2022-11-11
82010 | 2022-08-15 | 2022-08-18 | Solar/Battery | 996 | 445D1 | RAYMOND 115 KV | 445T1 | 2022-08-22 | Fail | Fail | 2022-09-21 | Yes
82007 | 2022-08-12 | 2022-08-30 | Solar | 1875 | 272D4 | NORTH AUGUSTA | 272T1 | 2022-09-14 | Fail | Fail | 2022-11-08 | Yes
81972 | 2022-08-10 | 2022-08-17 | Solar | 975 | 246D2 | THOMASTON CREEK | 246T1 | 2022-09-09 | Fail | Fail | 2022-10-21 | Yes
81959 | 2022-08-08 | 2022-09-14 | Solar | 2000 | 431D2 | MECHANIC FALLS | 431T1 | 2022-09-13 | Fail | Fail |  | Yes
81960 | 2022-08-08 | 2022-09-28 | Solar | 749 | 860D2 | UNITY | 860T1 | 2022-10-05 | Fail | Fail | 2022-11-21 | Yes
81961 | 2022-08-08 | 2022-09-28 | Solar | 749 | 209D3 | BOOTHBAY HARBOR | 209T1 | 2022-09-30 |  |  |  | Yes
81963 | 2022-08-08 | 2022-08-08 | Solar | 749 | 250D1 | TOPSHAM | 250T2 | 2022-09-02 | Fail | Pass | 2022-11-02
81964 | 2022-08-08 | 2022-09-28 | Solar | 749 | 817D3 | FAIRFIELD | 817T1 | 2022-09-30 |  |  |  | Yes
81965 | 2022-08-08 | 2022-08-15 | Solar | 749 | 438D1 | PAPOOSE POND | Tap off of Transmission Line | 2022-09-12 | Fail | Pass | 2022-12-12
81966 | 2022-08-08 | 2022-08-15 | Solar | 749 | 850D2 | SEARSPORT | 850T1 | 2022-09-14 | Fail | Pass | 2022-12-13
81967 | 2022-08-08 | 2022-08-15 | Solar | 749 | 837D2 | NEWPORT | 837T2 | 2022-08-29 | Fail | Fail | 2023-01-16 | Yes
81968 | 2022-08-08 | 2022-08-15 | Solar | 749 | 861D9 | VASSALBORO | 861T1 | 2022-09-13 | Fail | Fail | 2022-11-06 | Yes
81956 | 2022-08-05 | 2022-08-11 | Solar | 725 | 412D3 | DEER RIPS | 412T4 | 2022-09-13 | Pass
81957 | 2022-08-05 | 2022-08-11 | Solar | 725 | 412D3 | DEER RIPS | 412T4 | 2022-09-26 | Fail | Fail | 2022-11-21 | Yes
81958 | 2022-08-05 | 2022-08-12 | Solar | 2000 | 602D2 | BASSETT | 602T1 | 2022-08-29 | Fail | Pass | 2022-11-02 | Yes
81947 | 2022-08-04 | 2022-08-15 | Solar | 153.6 | 251D1 | UNION | 251T1 | 2022-08-29 | Fail |  | 2022-10-10 | Yes
81955 | 2022-08-04 | 2022-08-11 | Solar | 450 | 811D1 | CORINNA | 811T1 | 2022-08-30 | Pass |  |  | Yes
81945 | 2022-08-03 | 2022-08-08 | Solar | 500 | 866D2 | WESTON | 866T2 | 2022-10-04 | Pass |  |  | Yes
81942 | 2022-08-02 | 2022-08-08 | Solar | 996 | 470D1 | SAND ROAD TAP | 470T1 | 2022-08-09 | Fail | Pass | 2022-09-27
81911 | 2022-07-29 | 2022-08-05 | Solar | 530 | 861D9 | VASSALBORO | 861T1 | 2022-08-31 | Fail | Pass | 2022-10-12
81910 | 2022-07-27 | 2022-08-04 | Solar | 996 | 861D9 | VASSALBORO | 861T1 | 2022-08-11 | Fail | Fail | 2022-10-05 | Yes
81908 | 2022-07-26 | 2022-08-04 | Solar | 165 | 252D2 | WALDOBORO | 252T1 |  |  |  |  | Yes
81909 | 2022-07-26 | 2022-08-04 | Solar | 996 | 837D2 | NEWPORT | 837T2 | 2022-08-29 | Fail |  | 2022-10-03 | Yes
81849 | 2022-07-25 | 2022-08-01 | Solar | 996 | 438D1 | PAPOOSE POND | Tap off of Transmission Line | 2022-08-24 | Fail | Fail | 2022-10-10 | Yes
81850 | 2022-07-25 | 2022-08-12 | Solar | 996 | 850D2 | SEARSPORT | 850T1 | 2022-09-06 | Fail | Fail | 2022-10-17 | Yes
81851 | 2022-07-25 | 2022-08-25 | Solar | 2000 | 667D1 | SOUTH SANFORD | 667T2 | 2022-10-12 | Fail |  |  | Yes
81852 | 2022-07-25 |  | Solar | 1700 | 626D1 | HIGH STREET | 626T1 |  |  |  |  | Yes
81894 | 2022-07-25 | 2022-08-15 | Solar | 999 | 866D2 | WESTON | 866T2 | 2022-08-29 | Fail | Fail | 2022-09-21 | Yes
81895 | 2022-07-25 | 2022-08-15 | Solar | 400 | 454D2 | TURNER | 454T1 | 2022-08-25 | Pass
81896 | 2022-07-25 | 2022-08-01 | Solar | 730 | 412D3 | DEER RIPS | 412T4 | 2022-08-01 | Fail |  |  | Yes
81847 | 2022-07-21 |  |  | 210 | 638D2 | NORTH LIMINGTON | 638T1 |  |  |  |  | Yes
81848 | 2022-07-21 | 2022-07-21 | Solar | 850 | 412D3 | DEER RIPS | 412T4 | 2022-08-29 | Fail | Fail | 2022-10-17 | Yes
81817 | 2022-07-20 | 2022-07-27 | Solar | 1000 | 837D2 | NEWPORT | 837T2 | 2022-08-29 | Fail | Fail | 2022-10-10 | Yes
81819 | 2022-07-20 | 2022-07-27 | Solar | 999 | 821D3 | GUILFORD | 821T2 | 2022-09-13 | Fail | Pass | 2022-11-02
81816 | 2022-07-19 | 2022-07-25 | Solar | 996 | 860D2 | UNITY | 860T1 | 2022-08-02 | Fail |  | 2022-09-02 | Yes
81815 | 2022-07-18 | 2022-08-02 | Solar | 124 | 225D4 | FREEPORT | 225T1 | 2022-08-16 | Fail |  |  | Yes
81810 | 2022-07-15 | 2022-07-22 | Solar | 996 | 209D3 | BOOTHBAY HARBOR | 209T1 | 2022-08-18 | Fail | Pass | 2022-10-05
81811 | 2022-07-15 | 2022-07-22 | Solar | 996 | 250D1 | TOPSHAM | 250T2 | 2022-08-18 | Fail |  |  | Yes
81812 | 2022-07-15 | 2022-07-22 | Solar | 996 | 817D3 | FAIRFIELD | 817T1 | 2022-08-18 | Fail |  | 2022-09-07 | Yes
81754 | 2022-07-08 | 2022-07-12 | Solar | 190 | 457D2 | MONMOUTH | 457T2 | 2022-07-27 | Pass |  |  | Yes
81752 | 2022-07-01 | 2022-07-12 | Solar | 540 | 250D2 | TOPSHAM | 250T2 | 2022-07-25 | Fail | Pass | 2022-09-13
81680 | 2022-06-24 | 2022-07-08 | Solar | 466 | 255D2 | WEST STREET | 255T1 | 2022-08-01 | Pass
81653 | 2022-06-21 | 2022-06-27 | Solar | 115.2 | 470D1 | SAND ROAD TAP | 470T1 | 2022-07-08 | Pass
81675 | 2022-06-21 | 2022-06-27 | Solar | 990 | 431D1 | MECHANIC FALLS | 431T2 | 2022-07-08 | Fail |  |  | Yes
81676 | 2022-06-21 | 2022-06-29 | Solar | 875 | 412D3 | DEER RIPS | 412T4 | 2022-07-27 | Fail |  |  | Yes
81677 | 2022-06-21 | 2022-06-29 | Solar | 875 | 412D3 | DEER RIPS | 412T4 | 2022-07-27 | Fail |  |  | Yes
81678 | 2022-06-21 | 2022-06-29 | Solar | 1000 | 858D4 | STURTEVANT | 858T2 | 2022-08-01 | Fail |  |  | Yes
81679 | 2022-06-21 | 2022-06-29 | Solar | 1000 | 858D4 | STURTEVANT | 858T2 | 2022-08-01 | Fail |  |  | Yes
81628 | 2022-06-17 | 2022-06-24 | Solar | 244 | 839D2 | OAKLAND | 839T1 | 2022-07-09 | Pass |  |  | Yes
81512 | 2022-06-02 | 2022-06-08 | Solar | 975 | 852D1 | SHAWMUT | 852T3 | 2022-06-15 | Fail | Fail |  | Yes
81513 | 2022-06-02 | 2022-06-08 | Solar | 975 | 873D1 | COUNTY RD (RICE RIPS) | 873T1 | 2022-06-15 | Fail | Pass | 2022-09-01
81515 | 2022-06-02 | 2022-06-08 | Solar | 975 | 873D1 | COUNTY RD (RICE RIPS) | 873T1 | 2022-06-27 | Fail |  |  | Yes
81516 | 2022-06-02 | 2022-06-08 | Solar | 975 | 454D2 | TURNER | 454T1 | 2022-06-15 | Fail |  |  | Yes
81506 | 2022-05-31 | 2022-06-06 | Solar | 975 | 870D1 | WINSLOW | 870T4 | 2022-07-06 | Fail |  | 2022-10-11 | Yes
81508 | 2022-05-31 | 2022-06-06 | Solar | 975 | 853D1 | SKOWHEGAN NORTH SIDE | 853T1 | 2022-06-15 | Fail |  |  | Yes
81509 | 2022-05-31 | 2022-06-06 | Solar | 975 | 853D1 | SKOWHEGAN NORTH SIDE | 853T1 | 2022-06-15 | Fail |  |  | Yes
81511 | 2022-05-31 | 2022-06-06 | Solar | 350 | 866D2 | WESTON | 866T2 | 2022-07-19 | Pass
81489 | 2022-05-27 | 2022-05-31 | Solar | 475 | 412D3 | DEER RIPS | 412T4 | 2022-06-08 | Pass
81435 | 2022-05-26 | 2022-06-01 | Solar | 975 | 412D3 | DEER RIPS | 412T4 | 2022-06-08 | Fail |  |  | Yes
81465 | 2022-05-26 | 2022-06-01 | Solar | 900 | 255D2 | WEST STREET | 255T1 | 2022-06-15 | Fail |  |  | Yes
81413 | 2022-05-23 | 2022-05-24 | Solar | 975 | 870D1 | WINSLOW | 870T4 | 2022-06-08 | Fail |  |  | Yes
81409 | 2022-05-20 | 2022-05-27 | Solar | 200 | 237D1 | MCCOYS | 237T1 | 2022-06-17 | Pass |  |  | Yes
81396 | 2022-05-19 | 2022-05-23 | Solar | 337.5 | 603D2 | BERWICK | 603T1 | 2022-08-11 | Fail | Pass | 2022-10-31
81395 | 2022-05-17 | 2022-06-06 | Solar | 975 | 457D2 | MONMOUTH | 457T2 | 2022-06-08 | Fail |  |  | Yes
81393 | 2022-05-16 | 2022-05-31 | Solar | 125 | 647D1 | PRIDES CORNER | 647T2 | 2022-06-14 | Pass
81394 | 2022-05-16 | 2022-05-23 | Solar | 975 | 457D2 | MONMOUTH | 457T2 | 2022-06-10 | Fail | Pass | 2022-07-29
81270 | 2022-05-09 | 2022-05-13 | Solar | 104.1 | 430D1 | LOVELL | 430T1 |  |  |  |  | Yes
81265 | 2022-05-03 | 2022-05-09 | Solar | 975 | 839D2 | OAKLAND | 839T1 | 2022-05-26 | Fail |  |  | Yes
81267 | 2022-05-03 | 2022-07-14 | Solar | 975 | 839D2 | OAKLAND | 839T1 | 2022-05-26 | Fail |  |  | Yes
81262 | 2022-05-02 | 2022-05-09 | Solar | 975 | 663D2 | SOUTH BERWICK | 663T1 | 2022-06-22 | Fail |  |  | Yes
81264 | 2022-05-02 | 2022-05-09 | Solar | 150 | 821D1 | GUILFORD | 821T1 | 2022-08-30 | Pass
81490 | 2022-04-30 | 2022-05-05 | Solar | 800 | 263D1 | BOWMAN STREET | 34kV BUS 2 | 2022-06-15 | Pass | Pass | 2022-08-16
81259 | 2022-04-29 | 2022-04-29 | Solar | 975 | 638D2 | NORTH LIMINGTON | 638T1 | 2022-07-06 | Fail |  |  | Yes
81260 | 2022-04-29 | 2022-05-05 | Solar | 650 | 861D9 | VASSALBORO | 861T1 | 2022-06-02 | Pass |  |  | Yes
81257 | 2022-04-28 | 2022-05-05 | Solar | 999 | 638D1 | NORTH LIMINGTON | 638T1 |  |  |  |  | Yes
81258 | 2022-04-28 | 2022-05-16 | Solar | 975 | 638D2 | NORTH LIMINGTON | 638T1 | 2022-07-06 | Fail |  |  | Yes
81223 | 2022-04-25 | 2022-04-25 | Other | 350 | 435D1 | NORWAY | 435T2 | 2022-07-21 | Pass
81222 | 2022-04-21 | 2022-04-29 | Solar | 975 | 663D2 | SOUTH BERWICK | 663T1 | 2022-07-06 | Fail |  |  | Yes
81170 | 2022-04-20 | 2022-04-27 | Solar | 750 | 695D2 | LEBANON | 695T1 | 2022-05-05 | Fail |  |  | Yes
81171 | 2022-04-20 | 2022-04-25 | Solar | 850 | 631D1 | LAMBERT STREET | 631T1 | 2022-07-08 | Fail | Pass | 2022-08-18
81179 | 2022-04-20 | 2022-04-27 | Solar | 750 | 695D2 | LEBANON | 695T1 | 2022-05-26 | Fail |  |  | Yes
81200 | 2022-04-20 | 2022-04-27 | Solar | 975 | 841D1 | PHILLIPS/STRONG | 841T1 | 2022-05-19 | Fail | Pass | 2022-07-21
81201 | 2022-04-20 | 2022-04-27 | Solar | 975 | 457D1 | MONMOUTH | 457T1 | 2022-05-17 | Fail | Pass | 2022-08-02
81203 | 2022-04-20 | 2022-04-27 | Solar | 975 | 841D1 | PHILLIPS/STRONG | 841T1 | 2022-05-18 | Fail |  |  | Yes
81132 | 2022-04-13 | 2022-04-15 | Solar | 172 | 874D1 | BELFAST 115 | 874T2 | 2022-05-27 | Pass |  |  | Yes
81130 | 2022-04-03 | 2022-04-15 | Solar | 975 | 225D4 | FREEPORT | 225T1 | 2022-06-02 | Fail | Pass | 2022-08-03 | Yes
81019 | 2022-03-30 | 2022-04-07 | Solar | 975 | 225D4 | FREEPORT | 225T1 | 2022-04-08 | Fail |  |  | Yes
81015 | 2022-03-29 | 2022-04-04 | Solar | 650 | 861D9 | VASSALBORO | 861T1 | 2022-04-28 | Fail |  |  | Yes
81016 | 2022-03-29 | 2022-04-04 | Solar | 280 | 865D5 | WEST WATERVILLE | 865T2 | 2022-05-17 | Fail | Pass | 2022-06-27
81017 | 2022-03-29 | 2022-04-07 | Solar | 500 | 444D2 | RAYMOND 34 KV | 444T1 | 2022-04-25 | Fail | Pass | 2022-08-12 | Yes
81006 | 2022-03-25 | 2022-04-21 | Solar | 475 | 239D10 | PARK STREET | 239T5 | 2022-05-19 | Pass |  |  | Yes
80962 | 2022-03-22 | 2022-03-22 | Solar | 975 | 244D2 | SOUTH CHINA | 244T1 | 2022-04-19 | Fail |  |  | Yes
80971 | 2022-03-22 | 2022-03-29 | Solar | 975 | 244D2 | SOUTH CHINA | 244T1 | 2022-04-29 | Fail | Pass | 2022-07-29 | Yes
80892 | 2022-03-21 | 2022-03-25 | Solar | 975 | 239D10 | PARK STREET | 239T5 | 2022-05-17 | Pass
80977 | 2022-03-21 | 2022-03-31 | Solar | 2000 | 457D2 | MONMOUTH | 457T2 | 2022-04-21 | Fail |  |  | Yes
80842 | 2022-03-02 | 2022-03-17 | Solar | 975 | 450D1 | SABATTUS | 450T1 | 2022-04-15 | Fail |  |  | Yes
80841 | 2022-03-01 | 2022-03-08 | Solar | 1990 | 801D1 | ANSON | 801T1 | 2022-03-29 | Fail |  |  | Yes
80838 | 2022-02-28 | 2022-03-17 | Solar | 1992 | 806D2 | BUCKSPORT | 806T3 | 2022-03-30 | Fail | Pass | 2022-06-25 | Yes
80825 | 2022-02-24 | 2022-03-09 | Solar | 1999 | 233D2 | MANCHESTER | 233T1 | 2022-03-30 | Fail | Fail | 2022-05-17 | Yes
80807 | 2022-02-16 | 2022-02-23 | Solar | 975 | 817D3 | FAIRFIELD | 817T1 | 2022-03-03 | Fail |  |  | Yes
80808 | 2022-02-16 | 2022-02-23 | Solar | 975 | 861D8 | VASSALBORO | 861T1 | 2022-03-29 | Fail | Fail | 2022-05-19 | Yes
80726 | 2022-02-04 | 2022-02-09 | Solar | 975 | 853D1 | SKOWHEGAN NORTH SIDE | 853T1 | 2022-03-28 | Fail |  |  | Yes
80727 | 2022-02-04 | 2022-02-09 | Solar | 975 | 874D1 | BELFAST 115 | 874T2 | 2022-03-07 | Fail |  |  | Yes
80728 | 2022-02-04 | 2022-02-10 | Solar | 975 | 428D3 | LIVERMORE FALLS | 428T1 | 2022-03-04 | Fail | Fail | 2022-06-03 | Yes
80736 | 2022-02-04 | 2022-02-10 | Solar | 975 | 420D7 | HOTEL ROAD | 420T1 | 2022-03-28 | Pass
80737 | 2022-02-04 | 2022-02-09 | Solar | 975 | 420D4 | HOTEL ROAD | 420T1 | 2022-03-03 | Fail |  |  | Yes
80725 | 2022-02-03 | 2022-02-09 | Solar | 975 | 866D2 | WESTON | 866T2 | 2022-02-11 | Fail |  |  | Yes
80701 | 2022-01-31 | 2022-02-04 | Solar | 1750 | 850D1 | SEARSPORT | 850T1 | 2022-02-10 | Fail | Fail | 2022-04-18 | Yes
80677 | 2022-01-26 | 2022-02-02 | Solar | 200 | 693D2 | SCARBOROUGH | 693T1 | 2022-04-06 | Fail | Pass | 2022-05-23
80667 | 2022-01-25 | 2022-02-01 | Solar | 499 | 420D7 | HOTEL ROAD | 420T1 | 2022-02-10 | Pass
80656 | 2022-01-20 | 2022-01-27 | Solar | 200 | 650D1 | RIGBY | 650T1 | 2022-02-17 | Pass
80658 | 2022-01-20 | 2022-01-27 | Solar | 436 | 650D1 | RIGBY | 650T1 | 2022-02-10 | Fail | Pass | 2022-06-06 | Yes
80659 | 2022-01-20 | 2022-01-27 | Solar | 516 | 650D1 | RIGBY | 650T1 | 2022-02-17 | Pass
80609 | 2022-01-13 | 2022-01-20 | Solar | 1999 | 263D1 | BOWMAN STREET | 34kV BUS 2 | 2022-01-21 | Fail | Pass | 2022-05-16 | Yes
80605 | 2022-01-12 | 2022-01-31 | Solar | 1500 | 412D4 | DEER RIPS | 412T4 | 2022-02-10 | Fail | Fail | 2022-05-12 | Yes
80585 | 2022-01-04 | 2022-01-11 | Solar | 1000 | 861D9 | VASSALBORO | 861T1 | 2022-01-21 | Fail | Pass | 2022-06-20 | Yes

## Comments
Row 1 | Followed up on AOR(Incomplete) 5/16/2025 | Andrew Jackson | 05/16/25 10:58 AM
Row 22 | 4/17/2025 Withdrawn | Kaiya Hoogkamp | 04/17/25 10:31 AM
Row 23 | 4/17/2025 Withdrawn | Kaiya Hoogkamp | 04/17/25 10:32 AM
Row 24 | 105711 | Kaiya Hoogkamp | 04/17/25 10:32 AM
Row 24 | Additional invoice created for remaining application payment balance, $1996.00 | Kaiya Hoogkamp | 03/18/25 9:23 AM
Row 25 | Additional invoice created for remaining application payment balance, $1996.00 | Kaiya Hoogkamp | 03/18/25 9:23 AM
Row 28 | Draft 0000001119 refund issued via ACH on 5/2/2025 | Kaiya Hoogkamp | 05/02/25 8:37 AM
Row 28 | Adjusted Ombudsman fee invoice to $0.00 910265697 | Kaiya Hoogkamp | 05/01/25 9:28 AM
Row 28 | Adjusted app invoice to $0.00 910264462 | Kaiya Hoogkamp | 04/22/25 4:06 PM
Row 28 | 4/2/25 app withdrawn. | Kaiya Hoogkamp | 04/02/25 3:06 PM
Row 29 | 3/19/25 Application withdrawn. Failed technical screen and will fail and ESA. Advised to proceed with level 4. | Kaiya Hoogkamp | 03/19/25 1:12 PM
Row 30 | DO NOT EXECUTE IA OR COC UNTIL OMBUDSMAN FEE IS PAID | Kaiya Hoogkamp | 05/07/25 11:45 AM
Row 31 | DO NOT EXECUTE IA OR COC UNTIL OMBUDSMAN FEE IS PAID | Kaiya Hoogkamp | 05/07/25 11:46 AM
Row 32 | 3/19/25 Application withdrawn. Failed technical screen and will fail and ESA. Advised to proceed with level 4. | Kaiya Hoogkamp | 03/19/25 12:55 PM
Row 33 | 3/19/25 Application withdrawn. Failed technical screen and will fail and ESA. Advised to proceed with level 4. | Kaiya Hoogkamp | 03/19/25 1:03 PM
Row 37 | 2/26/25 emailed template to apply $1500 from previous ESA to this new PIA invoice | Kaiya Hoogkamp | 02/26/25 4:09 PM
Row 37 | If they go forward with the ESA we need to zero out previous ESA invoice and move funds to this new ESA | Kaiya Hoogkamp | 02/21/25 12:07 PM
Row 37 | Adjusted to $0.00 invoice 910253996 | Kaiya Hoogkamp | 02/18/25 1:12 PM
Row 37 | App fee is waived, previous project, 104609, could not be completed due to a level 4 study. We waived app fee and ESA fee (move fee from previous project to new project). | Kaiya Hoogkamp | 02/17/25 10:33 AM
Row 41 | 2/13/25 customer submitted payment and it was received. Opening the project up instead of reapplication. | Kaiya Hoogkamp | 02/13/25 8:20 AM
Row 41 | 2/11/25 project withdrawn, failure to pay application fee and unresponsive to outreach. | Kaiya Hoogkamp | 02/11/25 9:15 AM
Row 42 | Application late past AOR complete date due to developer delay sending application payment. | Kaiya Hoogkamp | 02/11/25 3:05 PM
Row 42 | Developer provided documentation of wire that was sent on 2/10/2025, reopened the application. | Kaiya Hoogkamp | 02/11/25 2:59 PM
Row 42 | 2/11/25 project withdrawn, failure to pay application fee and unresponsive to outreach. | Kaiya Hoogkamp | 02/11/25 9:14 AM
Row 47 | 1/29/25 offered one time extention to 2/5/2025 waiting for wire payment. | Kaiya Hoogkamp | 01/29/25 3:52 PM
Row 48 | 0000000189 is the draft refund | Kaiya Hoogkamp | 05/16/25 9:31 AM
Row 48 | 4/16/25 application withdrawn. Project unresponsive to outreach after technical screen failure. | Kaiya Hoogkamp | 04/16/25 8:16 AM
Row 50 | The developer advised this project was submitted in error and is withdrawn. | Kaiya Hoogkamp | 12/23/24 11:49 AM
Row 54 | $187.64 invoice 910266466/920289826 | Kaiya Hoogkamp | 05/07/25 9:24 AM
Row 54 | Additional $187.64 invoice received. Sent to workf flow 5/6/25. Per Dante "Project 104903 – the additional two hours were for a peer review. Its dated near the start of the month and on the other its dated at the end of the month so it must have been missed because it was split between the two invoices. " | Kaiya Hoogkamp | 05/06/25 10:21 AM
Row 54 | Original IA for incorrect $2500 910250371/ 920272691 Updated PIA to $1500 910250593/920272951 | Kaiya Hoogkamp | 01/21/25 3:17 PM
Row 57 | Developer is proposing a utility owned 750 kVA Pad mounted transformer. This will exceed the $30,000 Level 2 Threshold and will need to go to a level 4 study. | Nathan Lawrence | 12/17/24 1:56 PM
Row 57 | AOR complete delayed due to customer, waiting for payment to be received. | Kaiya Hoogkamp | 12/13/24 10:41 AM
Row 58 | TS Failed due to costs for proposed upgrades. | Nathan Lawrence | 01/08/25 10:10 AM
Row 58 | AOR complete delayed due to customer, waiting for payment to be received. | Kaiya Hoogkamp | 12/13/24 10:42 AM
Row 59 | AOR complete delayed due to customer, waiting for payment to be received. | Kaiya Hoogkamp | 12/13/24 10:42 AM
Row 60 | AOR complete delayed due to customer, waiting for payment to be received. | Kaiya Hoogkamp | 12/13/24 10:41 AM
Row 61 | AOR complete delayed due to customer, waiting for payment to be received. | Kaiya Hoogkamp | 12/13/24 10:41 AM
Row 62 | 12/4/2024 informed developer we needed to terminate ESA and withdraw project due to level 4 PRJ 308 being in study. | Kaiya Hoogkamp | 05/14/25 9:11 AM
Row 62 | terminated contract on 3/11/25 | Kaiya Hoogkamp | 03/11/25 1:21 PM
Row 63 | Withdrawn on 1/2/2025 | Kaiya Hoogkamp | 01/27/25 8:32 AM
Row 66 | 12/2/2024 customer requested to withdraw, as they have not finalized the SLD. | Kaiya Hoogkamp | 12/02/24 11:47 AM
Row 70 | 11/7/24 application failed technical screen and was advised it would fail addtional screening. Application withdrew and will reapply as a level 4. | Kaiya Hoogkamp | 11/07/24 11:13 AM
Row 71 | 12/4/2024 customer has withdrawn and will apply as a level 4 | Kaiya Hoogkamp | 12/04/24 12:19 PM
Row 73 | Application Fee waived, this is a resubmission for original application 101658 | Kaiya Hoogkamp | 09/25/24 12:11 PM
Row 76 | Holding COC due to problems with the phone line. CMP cannot connect to the meter. | Nathan Lawrence | 03/11/25 1:32 PM
Row 77 | 9/3/2024 app withdrawn, it incorrectly applied as a level 2, it needs to be a level 4. Customer advised of this. | Kaiya Hoogkamp | 09/03/24 9:54 AM
Row 79 | MANUAL PORTAL APPLICATION | Kaiya Hoogkamp | 09/23/24 12:15 PM
Row 80 | Original projects 103022 ($1060) and 103021 ($200). $1060+$200 = $1260. The NEW app total is $1180. $1180 - $1260 = -$80 is due to the customer as a refund. | Kaiya Hoogkamp | 08/07/24 3:02 PM
Row 81 | Original projects 103019 ($250 payment valid) and 103017 (project went to tech screen). App total is $350. Minus the $250 availible = $100 due | Kaiya Hoogkamp | 08/07/24 2:54 PM
Row 82 | Original projects 103016 & 103014, both projects went through tech screen, so full app total of $400 is due | Kaiya Hoogkamp | 08/07/24 2:39 PM
Row 84 | 9/30/2024 ESA failed, project withdrawn | Kaiya Hoogkamp | 10/31/24 10:37 AM
Row 84 | 8/23/24 resent ESA for new signatures, with a date line added next to customer signature | Kaiya Hoogkamp | 08/23/24 11:41 AM
Row 85 | 8/6/24 withdrawn, project being combined. | Kaiya Hoogkamp | 08/06/24 3:13 PM
Row 86 | 8/12/2024 failed ESA, project withdrawn | Kaiya Hoogkamp | 08/12/24 3:17 PM
Row 87 | 8/6/24 withdrawn, project being combined. | Kaiya Hoogkamp | 08/12/24 3:19 PM
Row 88 | 8/23/2024 project withdrawn after failing ESA | Kaiya Hoogkamp | 10/15/24 1:48 PM
Row 89 | 10/2/2024 ESA failed and project withdrawn. | Kaiya Hoogkamp | 10/15/24 1:54 PM
Row 89 | 7/30 invoice adjustment to make it $2050, funds are on debtor. Need to wait for adjustment invoice before entering IT ticket to clear. 910231855 | Kaiya Hoogkamp | 09/12/24 3:21 PM
Row 90 | 8/28/2024 ESA failed, project withdrawn. | Kaiya Hoogkamp | 10/15/24 1:56 PM
Row 92 | 9/3/2024 ESA failed, project withdrawn. | Kaiya Hoogkamp | 10/15/24 1:57 PM
Row 93 | Kaiya Hoogkamp 4/7/25 email for IA sent. 30 BD 5/20/2025 | Kaiya Hoogkamp | 04/07/25 8:43 AM
Row 95 | 8/12/2024 project withdrawn, failed ESA | Kaiya Hoogkamp | 08/13/24 3:18 PM
Row 102 | 6/14/2024 customer advsied they are withdrawing and reapplying as a level 4. They did not mean to apply as a level 2. | Kaiya Hoogkamp | 06/14/24 10:33 AM
Row 104 | Application delayed AOR complete due to customer waiting for PE stamp on their SLD | Kaiya Hoogkamp | 07/10/24 2:09 PM
Row 106 | 6/18/2024 customer confirmed they are withdrawing after failing technical screen and reapplying as a level 4. | Kaiya Hoogkamp | 06/18/24 10:22 AM
Row 107 | 6/10/24 customer failed technical screen and requested to withdraw | Kaiya Hoogkamp | 06/10/24 10:34 AM
Row 108 | kWh, No on-site load | Nathan Lawrence | 08/01/24 1:18 PM
Row 110 | 7/16/2024 project emailed to confirm withdrawn after failing technical screen | Kaiya Hoogkamp | 07/17/24 8:25 AM
Row 112 | 6/5/2024 project failed tech screen and requested to withdraw and reapply as level 4. | Kaiya Hoogkamp | 10/15/24 2:11 PM
Row 114 | 120006528 terminated contract, ESA was never performed. | Kaiya Hoogkamp | 03/10/25 1:51 PM
Row 114 | 7/16/2024 application withdrawn as we cannot perform the level 2 ESA at this time. Refund has been issued. 0000001479 | Kaiya Hoogkamp | 07/16/24 3:34 PM
Row 115 | Additional ESA Invoice 910265922/920289270 for $656.73, additional study charges that were initially missed from Dante due to being out at the time. | Kaiya Hoogkamp | 05/02/25 11:49 AM
Row 117 | 6/28/2024 ESA failed, project withdrawn. | Kaiya Hoogkamp | 10/15/24 2:14 PM
Row 118 | 5/23/2024 ESA failed, project withdrawn. | Kaiya Hoogkamp | 10/15/24 2:15 PM
Row 120 | Withdrawn 4/5/2024 Customer did not respond to multiple outreach attempts to provide required documents and payment to deem application complete. | Kaiya Hoogkamp | 04/05/24 10:13 AM
Row 121 | Withdrawn 4/5/2024 Customer did not respond to multiple outreach attempts to provide required documents and payment to deem application complete. | Kaiya Hoogkamp | 04/05/24 10:18 AM
Row 122 | No on-site load | Nathan Lawrence | 08/19/24 12:46 PM
Row 123 | Debit memo to offset Credit memo: 910265865/920289224 | Kaiya Hoogkamp | 05/02/25 9:46 AM
Row 123 | credit memo created to offset invoice 910263066/920286135. Credit Memo is 910264738/920288363 | Kaiya Hoogkamp | 04/24/25 10:48 AM
Row 123 | 5/21/2024 ESA failed, project withdrawn. | Kaiya Hoogkamp | 10/15/24 2:18 PM
Row 124 | Refunded thru credit of 811.24 given to Level4 PRJ 820 per Tyler | Thomas Blanchard | 03/06/25 8:32 AM
Row 125 | 5/1/2024 project failed ESA and withdrawn. | Kaiya Hoogkamp | 10/15/24 2:20 PM
Row 127 | 4/5/2024 Refund processed in SAP. | Kaiya Hoogkamp | 04/05/24 10:55 AM
Row 127 | INC3492935 entered to open up refund for $1500 ESA payment. The developer paid for an ESA even though they passed technical screen. | Kaiya Hoogkamp | 04/05/24 10:44 AM
Row 127 | 4/3/24 Customer has withdrawn due to construction issues. | Kaiya Hoogkamp | 04/03/24 11:07 AM
Row 128 | adjusted invoice 910253799 to $0.00 on 2/17/2025 | Kaiya Hoogkamp | 02/17/25 1:37 PM
Row 128 | 3/5/24 customer is withdrawing due to developer being no longer in business. Customer will apply again in the future with a new developer. | Kaiya Hoogkamp | 03/05/24 1:23 PM
Row 128 | 3/4/2024 emailed requesting update as today is day 10 | Kaiya Hoogkamp | 03/04/24 1:55 PM
Row 129 | 2/28/24 customer requested to withdraw and have refund issued, project did not go to technical screen and refund will be issued. | Kaiya Hoogkamp | 02/29/24 9:29 AM
Row 131 | 5/7/2024 project failed ESA and withdrawn. | Kaiya Hoogkamp | 10/15/24 2:26 PM
Row 133 | project withdrawn as it failed ESA on 4/12/2024 | Kaiya Hoogkamp | 04/29/24 9:10 AM
Row 135 | 5/16/2024 project withdrew and reapplied as level 4. | Kaiya Hoogkamp | 09/13/24 3:21 PM
Row 135 | 3/4 application complete delayed by customer - applied for 1000 kW AC then informed us it was 999 kW AC. Required updated SLD & Site plan with the change. Requested updated documents on 2/23/24 and received them 3/4/2024 | Kaiya Hoogkamp | 03/04/24 3:09 PM
Row 135 | currently missing required deration letter. CANNOT issue IA without this documentation 3/4/2024 | Kaiya Hoogkamp | 03/04/24 2:28 PM
Row 136 | Refund used as credit towards a Level4 invoice (PRJ820) per Tyler | Thomas Blanchard | 03/06/25 8:21 AM
Row 136 | 2/7/25 duplicate application fee of $2098 has been refunded. | Kaiya Hoogkamp | 02/07/25 8:22 AM
Row 136 | 5/7/2024 failed ESA, project withdrawn | Kaiya Hoogkamp | 08/26/24 2:39 PM
Row 138 | currently missing required deration letter. CANNOT issue IA without this documentation 3/4/2024 | Kaiya Hoogkamp | 03/04/24 1:27 PM
Row 139 | Refund request number: 0000001051 | Kaiya Hoogkamp | 05/14/25 8:51 AM
Row 139 | 4/19/2024 application withdrawn. | Kaiya Hoogkamp | 08/20/24 1:05 PM
Row 139 | 4/30/2024 refund reissued for $1152. Original amount to be refunded $1500 for ESA. However, there was an outstanding invoice for $348 on invoice 910212016/920232028. That has now been paid. | Kaiya Hoogkamp | 04/30/24 3:10 PM
Row 139 | 4/23 Refund updated to JUST the ESA fee of $1500. We will waive app fee if they reapply in the future. | Kaiya Hoogkamp | 04/23/24 12:31 PM
Row 139 | project withdrawn, cannot process ESA due to level 4 studies. | Kaiya Hoogkamp | 04/19/24 2:30 PM
Row 139 | 4/18/24 processed refuned for $2600 | Kaiya Hoogkamp | 04/18/24 3:28 PM
Row 139 | 910219227 invoice adjustment to adjust invoice to $0 in order to issue refund. We are refunding application and ESA fee due to project being unable to move forward due to level 4 applications. | Kaiya Hoogkamp | 04/16/24 3:26 PM
Row 139 | waiting to receive W-9 or email confirmation of financial responsiblity for the ESA before creating contract. Create the ESA in the portal | Kaiya Hoogkamp | 02/06/24 11:26 AM
Row 142 | 4/26/24 withdrawn after failing ESA | Kaiya Hoogkamp | 08/20/24 12:36 PM
Row 148 | portal contract 120006228 PIA 910212543 / 920232559. Created and cancelled 2/23/24. Portal contract and "old way" contract both made. | Kaiya Hoogkamp | 02/23/24 2:04 PM
Row 149 | 1/3/24 withdrawn after not responding within the 10 business day deadline | Kaiya Hoogkamp | 03/21/24 12:51 PM
Row 150 | 5/17/2024 project failed technical screen and withdrew. | Kaiya Hoogkamp | 10/15/24 2:39 PM
Row 151 | 2/9/2024 project failed ESA and withdrawn. | Kaiya Hoogkamp | 10/15/24 2:38 PM
Row 152 | Withdrawn 1/3/2024 after customer did not provide required documentation within the required 10 days and after an extention was granted. | Kaiya Hoogkamp | 03/21/24 11:39 AM
Row 154 | 4/9/2024 project withdrawn as it failed ESA. | Kaiya Hoogkamp | 04/29/24 9:07 AM
Row 157 | 6/7/2024 project withdrew | Kaiya Hoogkamp | 06/07/24 3:25 PM
Row 157 | 2/6 emailed customer asking for W-9 for New Sharon Community Solar or an email confirming Genie Solar Energy is financially responsible for ESA before we can create contract and PIA | Kaiya Hoogkamp | 02/06/24 10:41 AM
Row 160 | Rick tech screen, originally on time, but, contained wrong project size in TS, delay from Rick for updated TS with correct project size caused delay sent to customer | Kaiya Hoogkamp | 09/09/24 1:49 PM
Row 164 | 4/29/2024 failed ESA, project withdrawn | Kaiya Hoogkamp | 06/18/24 3:02 PM
Row 164 | Developer submitted 4 applications for same size all at once during transition to new portal, payments and additional documents were not all submitted at the same time. There was numerous back and forth with customer to ensure we received payments, export control and new account creation caused delays with the customer. Developer has worked in good faith to keep us informed as they worked to get all required documentation and payment. | Kaiya Hoogkamp | 01/24/24 2:50 PM
Row 165 | Refund draft: 0000000989 | Kaiya Hoogkamp | 05/14/25 8:47 AM
Row 165 | 4/24/2024 withdrawn | Kaiya Hoogkamp | 10/22/24 11:52 AM
Row 165 | 4/23 Refund updated to JUST the ESA fee of $2500. We will waive app fee if they reapply in the future. | Kaiya Hoogkamp | 04/23/24 12:21 PM
Row 165 | project withdrawn as it cannot go through ESA due to level 4 studies. | Kaiya Hoogkamp | 04/19/24 2:20 PM
Row 165 | $4640 refund issued for app fee and ESA. Project withdrawn | Kaiya Hoogkamp | 04/19/24 2:20 PM
Row 165 | 910219232 invoice adjustment to adjust invoice to $0 in order to issue refund. We are refunding application and ESA fee due to project being unable to move forward due to level 4 applications. | Kaiya Hoogkamp | 04/16/24 3:20 PM
Row 166 | Withdrawn 3/22 due to failing ESA | Kaiya Hoogkamp | 04/30/24 10:27 AM
Row 167 | 3/12/2024 project failed ESA and was withdrawn. | Kaiya Hoogkamp | 10/15/24 2:32 PM
Row 169 | 1/22/24 customer requested to withdraw project. | Kaiya Hoogkamp | 02/27/24 12:00 PM
Row 170 | 2/22/2024 failed ESA | Kaiya Hoogkamp | 07/23/24 3:18 PM
Row 172 | 1/11/2024 customer withdrew after technical screen. | Kaiya Hoogkamp | 07/23/24 2:52 PM
Row 174 | Customer requested to withdraw on 1/4/2024 | Kaiya Hoogkamp | 05/07/24 10:57 AM
Row 174 | Refund issued in SAP | Kaiya Hoogkamp | 01/22/24 1:48 PM
Row 174 | Original contract 120005879 cancelled on 1/18/2024, customer withdrawn without doing ESA and PIA $1500 refunded. | Kaiya Hoogkamp | 01/18/24 11:33 AM
Row 174 | Duplicate contract 12000085887 created by Nate Lawrence was cancelled. No payment attached. | Kaiya Hoogkamp | 01/18/24 11:32 AM
Row 175 | 1/7/2024 customer requested to withdraw | Kaiya Hoogkamp | 05/22/24 9:09 AM
Row 177 | 1/2/2024 ESA failed, project withdrawn. | Kaiya Hoogkamp | 10/15/24 2:54 PM
Row 178 | 1/26/2024 project withdrawn after failing ESA | Kaiya Hoogkamp | 07/23/24 3:32 PM
Row 179 | 1/24/2024 customer has decided to withdraw the project. | Kaiya Hoogkamp | 02/27/24 1:21 PM
Row 180 | 2/20/2024 project failed ESA and withdrawn. | Kaiya Hoogkamp | 10/15/24 2:55 PM
Row 183 | No task 24 in SAP | Kaiya Hoogkamp | 12/17/24 2:40 PM
Row 184 | 5/16/2024 project requested to be withdrawn, project no longer viable. | Kaiya Hoogkamp | 10/15/24 2:57 PM
Row 188 | 4/4/25 email for IA sent. 30 BD 5/19/2025 | Kaiya Hoogkamp | 04/04/25 3:43 PM
Row 188 | Customer has not paid ESA deposit. DO NOT issue COC until we receive payment | Kaiya Hoogkamp | 03/07/25 11:33 AM
Row 190 | original PIA 910202573/920222068 cancelled due to incorrect project name entered in description. Ticket INC3254016 entered to cancel. | Kaiya Hoogkamp | 12/05/23 1:45 PM
Row 192 | 1211/24 project requested to withdraw in favor of their level 4 project 599 | Kaiya Hoogkamp | 12/11/24 8:44 AM
Row 193 | 2/22/2024 project failed ESA and withdrew. | Kaiya Hoogkamp | 10/15/24 3:05 PM
Row 198 | 1/31/2024 project failed ESA and withdrew. | Kaiya Hoogkamp | 10/15/24 3:09 PM
Row 200 | "Install 500 kVA Pad Mount Transformer." listed under "Estimated Cost to Interconnect". | Nathan Lawrence | 09/03/24 2:31 PM
Row 202 | 11/13/2023 project failed ESA and withdrew. | Kaiya Hoogkamp | 10/15/24 3:10 PM
Row 204 | 11/6/2023 project failed tech screen and withdrew. | Kaiya Hoogkamp | 10/15/24 3:17 PM
Row 205 | 10/25/2023 project failed ESA and withdrew. | Kaiya Hoogkamp | 10/15/24 3:18 PM
Row 207 | additional ESA invioice: 910265923/920289271 | Kaiya Hoogkamp | 05/02/25 11:52 AM
Row 210 | 12/8/2023 application failed ESA. Project withdrawn. | Kaiya Hoogkamp | 06/24/24 11:53 AM
Row 212 | 9/8/2023 project unresponsive to outreach and withdrawn after 10 bd deadline. | Kaiya Hoogkamp | 10/15/24 3:48 PM
Row 213 | Has a related noti 10300727127 for customer building construction per Gary Ham | Nathan Lawrence | 07/30/24 8:36 AM
Row 215 | 9/14/2023 project failed ESA and project withdrawn. | Kaiya Hoogkamp | 10/16/24 7:40 AM
Row 218 | 1/24/2024 customer withdrew project. | Kaiya Hoogkamp | 10/16/24 7:43 AM
Row 219 | 11/3/2023 project withdrew. | Kaiya Hoogkamp | 10/16/24 7:42 AM
Row 220 | Original PIA 910191401/920210205 was never cleared w/ payment and sales admin cleared 3/26/2024. Created new PIA 910223778/920244513 on 5/23/2024 to apply payment to. | Thomas Blanchard | 05/28/24 2:44 PM
Row 221 | 10/12/2023 project failed ESA and withdrew. | Kaiya Hoogkamp | 10/16/24 8:21 AM
Row 222 | 10/3/2023 project failed ESA and withdrew. | Kaiya Hoogkamp | 10/16/24 8:19 AM
Row 223 | Contract cancelled. | Kaiya Hoogkamp | 03/10/25 1:27 PM
Row 223 | 10/26/2023 project requested to withdraw | Kaiya Hoogkamp | 10/22/24 12:01 PM
Row 224 | ESA Cancelled | Kaiya Hoogkamp | 03/10/25 1:28 PM
Row 224 | 10/26/2023 customer withdrew project. | Kaiya Hoogkamp | 10/16/24 8:28 AM
Row 225 | 4/4/25 email for IA sent. 30 BD 5/19/2025 | Kaiya Hoogkamp | 04/04/25 3:28 PM
Row 226 | 9/20/2023 project failed ESA and withdrew. | Kaiya Hoogkamp | 10/16/24 8:30 AM
Row 227 | 8/16/23 withdrawn after project failed ESA | Kaiya Hoogkamp | 10/07/24 10:53 AM
Row 228 | 5/6/25 Sent additional ESA for study work | Kaiya Hoogkamp | 05/06/25 1:15 PM
Row 228 | Additional PIA for restudy work done Spring 2024 910266050/920289412 $140.73 | Kaiya Hoogkamp | 05/05/25 9:56 AM
Row 228 | Original developer Perennial Renewables LLC, sold to Madison Energy Infrastructure | Kaiya Hoogkamp | 11/26/24 12:58 PM
Row 230 | 1/21/2025 customer withdrew | Kaiya Hoogkamp | 01/22/25 7:37 AM
Row 234 | 9/6/2023 project failed ESA and withdrew. | Kaiya Hoogkamp | 10/16/24 8:35 AM
Row 235 | 9/6/2023 project failed ESA and withdrew. | Kaiya Hoogkamp | 10/16/24 8:35 AM
Row 238 | 8/30/2023 project failed ESA and withdrew. | Kaiya Hoogkamp | 10/16/24 8:36 AM
Row 240 | 8/16/2023 project failed ESA and withdrew. | Kaiya Hoogkamp | 10/16/24 8:37 AM
Row 243 | 9/2/2023 application withdrawn | Kaiya Hoogkamp | 10/18/24 11:48 AM
Row 247 | 7/30/2023 app failed ESA and withdrew | Kaiya Hoogkamp | 10/18/24 11:54 AM
Row 247 | TIN has been used for Acadia Energy, can I use that # | Jessie Ladaga | 06/16/23 12:55 PM
Row 248 | 6/30/2023 application withdrawn | Kaiya Hoogkamp | 10/18/24 11:49 AM
Row 249 | Can I use the Green Lantern #; emailed Christy | Jessie Ladaga | 06/16/23 12:45 PM
Row 250 | Debtor # extended | Jessie Ladaga | 06/16/23 10:45 AM
Row 251 | DEBTOR # CREATED | Jessie Ladaga | 06/29/23 12:52 PM
Row 253 | 9/21/2023 application withdrawn | Kaiya Hoogkamp | 10/18/24 12:01 PM
Row 254 | Invoice for NOTI 10301049886 paid 10/31/24 | Nathan Lawrence | 12/10/24 12:25 PM
Row 255 | 7/14/2023 app failed ESA and project withdrawn | Kaiya Hoogkamp | 10/18/24 12:00 PM
Row 256 | 6/25/2023 application withdrawn | Kaiya Hoogkamp | 10/18/24 12:02 PM
Row 256 | NH Solar Garden payment - confirmed via email - see email? is there a debtor #? is there a w9? | Jessie Ladaga | 06/14/23 5:34 PM
Row 257 | this project failed tech screen in error and needs to be refunded the ESA charge- after rescreen on tech screen they passed. | William Dawe | 07/11/23 8:54 AM
Row 257 | this is on RE # - can i use 1289121? | Jessie Ladaga | 06/14/23 5:20 PM
Row 260 | additional charges found and billable per Portal | Staci Pellegrini | 03/13/24 1:05 PM
| Added charges of $246.68 to invoice on 3/20/24 | Thomas Blanchard | 03/21/24 7:38 AM
Row 260 | no debtor # created. Can i use 929103? W9 is lacking address. Sent email. | Jessie Ladaga | 06/14/23 4:31 PM
Row 260 | debtor # created | Jessie Ladaga | 06/14/23 4:23 PM
Row 260 | email sent requesting w9 | Jessie Ladaga | 05/19/23 11:33 AM
Row 261 | Original developer GREEN LANTERN DEVELOPMENT LLC, sold to Madison Energy Infrastructure | Kaiya Hoogkamp | 11/26/24 12:55 PM
Row 261 | Created new paid 910206445/920226265 ticket sent xfer 2500.00 to correct debtor | Staci Pellegrini | 01/08/24 12:32 PM
Row 261 | pia 910183424/920201756 was canceled by sales admin | Staci Pellegrini | 01/05/24 9:35 AM
Row 261 | Pia was cancel because the payment was on the original payee debtor 924257 / set itnow ticket move to 932591 and will xfer contract to me and then set up new pia to clear. | Staci Pellegrini | 01/05/24 9:33 AM
Row 261 | found debtor # = 932591 | Jessie Ladaga | 06/14/23 2:39 PM
Row 261 | requested w9 | Jessie Ladaga | 06/14/23 2:30 PM
Row 262 | 8/14/2023 application withdrawn | Kaiya Hoogkamp | 10/18/24 12:09 PM
Row 262 | w9 reques sent | Jessie Ladaga | 05/31/23 2:44 PM
Row 262 | Request for w9 was sent out by front end analysis on 5/12/2023 | Jessie Ladaga | 05/12/23 2:48 PM
Row 263 | 8/8/2023 app failed ESA and withdrew | Kaiya Hoogkamp | 10/18/24 12:05 PM
Row 263 | w9 request sent | Jessie Ladaga | 05/31/23 2:48 PM
Row 263 | w9 request sent on 5/12 with ESA | Jessie Ladaga | 05/12/23 2:49 PM
Row 264 | 7/26/23 project failed ESA and withdrawn. | Kaiya Hoogkamp | 09/05/24 10:25 AM
Row 265 | NO W9 REC;D THIS HAS A NOTI # 1508679 | Jessie Ladaga | 06/30/23 3:22 PM
Row 265 | sent a follow up email requesting w9 | Jessie Ladaga | 06/14/23 2:17 PM
Row 265 | w9 email request sent | Jessie Ladaga | 05/31/23 2:26 PM
Row 266 | 5/20/2024 project has withdrawn. | Kaiya Hoogkamp | 05/20/24 3:30 PM
Row 266 | has credit willo need to apply to balance on 83453 email sent to Kiaya | Staci Pellegrini | 01/04/24 2:52 PM
Row 266 | email sent requesting .pdf PIA (study about to kick off) | Jessie Ladaga | 05/12/23 1:49 PM
Row 267 | 6/22/2023 ESA failed, application withdrawn | Kaiya Hoogkamp | 10/18/24 12:15 PM
Row 267 | THIS WAS EXTENDED BY STACI | Jessie Ladaga | 06/14/23 3:49 PM
Row 267 | 1416460 = noti / can this be extended to use? | Jessie Ladaga | 06/14/23 2:07 PM
Row 268 | sent IT ticket | Jessie Ladaga | 05/11/23 9:34 AM
Row 269 | FBL5N review; ? | Jessie Ladaga | 05/17/23 3:00 PM
Row 269 | Sent IT | Jessie Ladaga | 05/15/23 9:20 AM
Row 270 | 10/19/2023 The project listed 83668 is in fact a cancelled project per conversation with developer just now- Ryan Darlow. | Kaiya Hoogkamp | 10/18/24 12:20 PM
Row 270 | to have contract 120005075 reassigned to me then closed out .incorrect debtor | Staci Pellegrini | 03/05/24 4:37 PM
Row 270 | Duplicate contract Pia created for Prj 83668 contract 120005075 debtor 928950 910179620/920197672 incorrect debtor payment 5/5 pa 8400015200 will need to be moved debtor 929226 and applied invoice 920198765 contract 120005124. sent email jess. | Staci Pellegrini | 06/14/23 2:46 PM
Row 270 | sent IT | Jessie Ladaga | 05/15/23 8:44 AM
Row 270 | cutomer has sent in confirmation of ESA payment | Jessie Ladaga | 05/10/23 4:23 PM
Row 270 | have w9 and debtor #, need signed ESA | Jessie Ladaga | 05/10/23 1:06 PM
Row 270 | W9 requested | Jessie Ladaga | 05/10/23 12:59 PM
Row 271 | Payment refund 896..58 was taken from prj 83670 and applied to level 4 prj balance prj 692 1/17/2024 | Staci Pellegrini | 04/26/24 11:30 AM
Row 273 | Credit memo: 910266673 for $19.92 refund that is due | Kaiya Hoogkamp | 05/08/25 9:16 AM
Row 273 | 5/7/25 Sent contract to work flow | Kaiya Hoogkamp | 05/07/25 8:21 AM
Row 273 | New PIA 910266262/920289612 | Kaiya Hoogkamp | 05/06/25 9:42 AM
Row 273 | New Contract: 120007536 released on 5/6/25 | Kaiya Hoogkamp | 05/06/25 9:35 AM
Row 273 | Per Michelle and Brian and sales admin, because we cannot get the PIA to show on the contract, we need to cancel the contract and PIA and start over. 120005031 has been terminated | Kaiya Hoogkamp | 05/06/25 9:10 AM
Row 273 | 910266160/920289513 - new PIA created per Michelle in Sales Admin | Kaiya Hoogkamp | 05/05/25 3:04 PM
Row 273 | Original developer MECHANIC FALLS GLC SOLAR LLC, sold to Madison Energy Infrastructure | Kaiya Hoogkamp | 11/26/24 12:57 PM
Row 273 | INC3162470 ticket requesting payment | Kaiya Hoogkamp | 10/24/23 10:24 AM
Row 273 | Original PIA 910179625/920197692 was never cleared w/ payment and sales admin cleared 9/28/2023. Created new PIA 910199075/920218318 on 10/24/2023 to apply payment to. | Kaiya Hoogkamp | 10/24/23 10:19 AM
Row 274 | katie to create debtor # | Jessie Ladaga | 04/28/23 10:10 AM
Row 275 | old PIA that closed out 910178292/920196202 | Kaiya Hoogkamp | 11/01/23 3:11 PM
Row 275 | sent IT ticket | Jessie Ladaga | 05/12/23 4:07 PM
Row 275 | rec'd W9; found debtor; sent to Christy to fix spelling in SAP and confirm TIN's match | Jessie Ladaga | 04/26/23 12:14 PM
Row 276 | 5/17/2023 app failed ESA and withdrawn | Kaiya Hoogkamp | 10/18/24 12:21 PM
Row 276 | pia was created by jess/ pia got cancelled due to no pmt being applied / found no confirmation of payment from the customerr via portal. I sent email to customer 11/11 to confirm if paid or not before we invoice | Staci Pellegrini | 01/11/24 11:36 AM
Row 276 | sent email to Sales Admin to have address updated Debtor # 923285 - office moved; sent W9 and IA for backup documentaiton | Jessie Ladaga | 06/14/23 12:22 PM
Row 276 | need to send email to update address-- speak with staci | Jessie Ladaga | 05/31/23 1:39 PM
Row 276 | debtor # reuqest sent | Jessie Ladaga | 05/10/23 12:52 PM
Row 277 | Original developer GREEN LANTERN DEVELOPMENT LLC, sold to Madison Energy Infrastructure | Kaiya Hoogkamp | 11/26/24 12:56 PM
Row 277 | Debtor creation requested | Jessie Ladaga | 05/09/23 2:38 PM
Row 278 | Kiaya created credit memo | Staci Pellegrini | 11/08/23 5:44 PM
Row 278 | sent email for OCR to place 2500 on 9003006 | Jessie Ladaga | 04/28/23 11:18 AM
Row 278 | sent KK a request to create debtor # | Jessie Ladaga | 04/26/23 1:13 PM
Row 279 | Charges waived, contract closed on 5/7/2024 | Thomas Blanchard | 05/07/24 11:48 AM
Row 279 | PIA Had been preivously cancelled. Contract completed on 10/20/2023. We will not be billing the contractor charges as it was a pass. | Kaiya Hoogkamp | 10/20/23 11:11 AM
Row 279 | This was a tech screen fail in error, it was in fact a PASS but ESA was billed out. | Kaiya Hoogkamp | 10/20/23 11:08 AM
Row 280 | debtor # created | Jessie Ladaga | 05/15/23 2:24 PM
Row 280 | email sent requesting w9 | Jessie Ladaga | 05/10/23 10:52 AM
Row 281 | 4/27/2023 project failed ESA and withdrew | Kaiya Hoogkamp | 09/23/24 2:19 PM
Row 281 | sent request to KK to have # created | Jessie Ladaga | 04/26/23 1:38 PM
Row 283 | 4/23/2023 app withdrawn | Kaiya Hoogkamp | 10/18/24 12:23 PM
Row 284 | April 3, 2024 developer requested withdraw | Kaiya Hoogkamp | 07/11/24 3:55 PM
Row 284 | completed refund 1/17/24 | Staci Pellegrini | 02/20/24 9:02 AM
Row 284 | sent invoices to customer 1/4/2024 this is credit back to the customer no other outstanding projects owed so i requested refund 0000000086 1/17/24 sap | Staci Pellegrini | 01/17/24 9:30 AM
Row 284 | Issue with customer name | Kristina Waterhouse | 04/03/23 2:39 PM
Row 285 | $ is still open on open cash draw as of 5/26 sent ITNOW ticket | Staci Pellegrini | 05/26/23 1:48 PM
Row 285 | 5/16/23 follow up email sent in RE of W9 | Jessie Ladaga | 05/17/23 4:39 PM
Row 285 | Put $2500 (paid on 5/15/2023) ESA fee on debtor 1568046, pending W-9 with Arundel Solar | Kaiya Hoogkamp | 05/16/23 2:44 PM
Row 285 | need w9 with ESA name, email request sent | Jessie Ladaga | 05/12/23 2:38 PM
Row 286 | debtor # request sent/ email attached | Jessie Ladaga | 05/10/23 6:23 PM
Row 286 | there is a fully exectued ESA | Jessie Ladaga | 05/10/23 10:22 AM
Row 286 | debtor # creation requested | Jessie Ladaga | 05/10/23 10:21 AM
Row 286 | No ESA - email sent requesting signed Agreement | Jessie Ladaga | 04/26/23 2:15 PM
Row 286 | Requested W9 4/4 | Kristina Waterhouse | 04/04/23 1:28 PM
Row 287 | 6/9/2023 application withdrew | Kaiya Hoogkamp | 10/22/24 12:10 PM
Row 287 | Chase Warren payment on 1289121; sent IT | Jessie Ladaga | 05/12/23 4:46 PM
Row 287 | After researching the project number was over written in error making info look incorrect. | Kristina Waterhouse | 05/04/23 1:52 PM
Row 287 | wrong project details on this ROW- updated cor | William Dawe | 05/04/23 9:54 AM
Row 287 | PIA sent to customer/developer (ReVision) | Jessie Ladaga | 04/26/23 2:51 PM
Row 287 | ESA uploaded; waiting on Christy to release from workfolow to release Contract | Jessie Ladaga | 04/24/23 1:26 PM
Row 287 | need CMP to sign ESA | Jessie Ladaga | 04/24/23 10:43 AM
Row 287 | reuqested katie to create debtor # | Jessie Ladaga | 04/17/23 12:27 PM
Row 288 | 120005064 completed on 2/27/2024 | Kaiya Hoogkamp | 02/27/24 12:33 PM
Row 288 | original contract 120005064 (created incorrectly on Revisions debtor) | Kaiya Hoogkamp | 10/24/23 9:39 AM
Row 288 | sent needed US mailing addy to Katie for # creation | Jessie Ladaga | 04/26/23 3:15 PM
Row 288 | katie to create debtor # | Jessie Ladaga | 04/17/23 12:31 PM
Row 289 | i can create the contract and not release | Jessie Ladaga | 05/10/23 4:25 PM
Row 289 | no signed ESA | Jessie Ladaga | 05/10/23 10:13 AM
Row 289 | Sent email requesting w9 | Jessie Ladaga | 05/09/23 12:16 PM
Row 290 | 4/4/25 email for IA sent. 30 BD 5/19/2025 | Kaiya Hoogkamp | 04/04/25 2:37 PM
Row 294 | 4/4/25 email for IA sent. 30 BD 5/19/2025 | Kaiya Hoogkamp | 04/04/25 2:46 PM
Row 296 | completed refund 1/17/24 sjp | Staci Pellegrini | 02/20/24 9:03 AM
Row 296 | sent invoices to customer 1/4/2024 this is credit back to the customer no other outstanding projects owed so i requested refund 0000000086 1/17/24 sap | Staci Pellegrini | 01/17/24 9:29 AM
Row 297 | Withdraw request from customer 3/21/23 after failed TS. | Nathan Lawrence | 10/15/24 3:28 PM
Row 298 | PIF | Thomas Blanchard | 05/29/24 11:06 AM
Row 298 | Moved 103.42 from Acadia refunded projects to this Acadia balance due. OK'd by Glenn Walker | Thomas Blanchard | 05/29/24 11:03 AM
Row 299 | 4/7/2025 app withdrawn | Kaiya Hoogkamp | 04/07/25 8:54 AM
Row 299 | 4/4/25 email for IA sent. 30 BD 5/19/2025 | Kaiya Hoogkamp | 04/04/25 2:44 PM
Row 300 | no documentation verifying withdrawal | Kaiya Hoogkamp | 10/22/24 12:13 PM
Row 303 | Noti 10300899161 CANC | Nathan Lawrence | 01/30/25 12:45 PM
Row 305 | cleared SAP | Jessie Ladaga | 05/11/23 1:08 PM
Row 305 | need to change/update name in contract, add ESA then release | Jessie Ladaga | 04/24/23 10:34 AM
Row 305 | Requested Katie created debtor | Jessie Ladaga | 04/17/23 12:17 PM
Row 305 | Requested debtor | Kristina Waterhouse | 04/04/23 1:20 PM
Row 306 | Moved 596.78 from Acadia refunded projects to this Acadia balance due. OK'd by Glenn Walker. PIF | Thomas Blanchard | 05/29/24 11:05 AM
Row 308 | contract reassigned to me | Staci Pellegrini | 09/26/23 2:15 PM
Row 308 | charges 1480.08/ 1500.00 will need to refund 19.92. | Staci Pellegrini | 09/26/23 2:03 PM
Row 308 | Created USM1 debtor | Kristina Waterhouse | 04/03/23 3:02 PM
Row 308 | Requested W9 4/3 | Kristina Waterhouse | 04/03/23 12:02 PM
Row 310 | Customer confirmed withdrawal 4/11/2023, resubmitted as a L4. | Nathan Lawrence | 10/15/24 6:07 PM
Row 315 | 12/5/2023 project withdrew due to wetlands and being unable to develop the land. | Kaiya Hoogkamp | 07/09/24 12:53 PM
Row 317 | 3/4/2024 the project failed ESA and is withdrawn. | Kaiya Hoogkamp | 07/09/24 1:00 PM
Row 317 | INC2871444 to move and clear PIA | Kristina Waterhouse | 05/31/23 2:19 PM
Row 317 | Requested debtor in SAP | Kristina Waterhouse | 04/26/23 11:30 AM
Row 317 | Emailed again for W9 request | Kristina Waterhouse | 04/25/23 1:51 PM
Row 317 | Requested W9 | Kristina Waterhouse | 04/04/23 2:22 PM
Row 318 | ESA Fees waived! | Kristina Waterhouse | 04/05/23 2:59 PM
Row 319 | 8/23/2023 application withdrew | Kaiya Hoogkamp | 10/22/24 12:46 PM
Row 320 | Requested debtor in SAP | Kristina Waterhouse | 04/06/23 10:36 AM
Row 320 | Requested W9 | Kristina Waterhouse | 04/05/23 8:26 AM
Row 322 | Customer requested withdrawal 1/4/2023, downsized and resubmitted. | Nathan Lawrence | 10/15/24 6:02 PM
Row 323 | 2/1/2023 customer confirmed they wanted to withdraw | Kaiya Hoogkamp | 06/12/24 10:47 AM
Row 326 | Wthdrawal requested by customer 2/27/2023. | Nathan Lawrence | 10/15/24 5:56 PM
Row 326 | Submitted INC2876458 to open CM for refund | Kristina Waterhouse | 06/02/23 10:15 AM
Row 326 | Sent email requesting they confirm refund information | Kristina Waterhouse | 05/23/23 11:31 AM
Row 326 | Created debtor in SAP | Kristina Waterhouse | 05/04/23 10:02 AM
Row 326 | Followed up on W9 request | Kristina Waterhouse | 04/25/23 1:55 PM
Row 326 | W9 requested 4/3 | Kristina Waterhouse | 04/03/23 1:48 PM
Row 327 | Also terminated contract 120004858 | Kristina Waterhouse | 06/13/23 8:44 AM
Row 327 | Submitted INC2895073 to cancell PIA | Kristina Waterhouse | 06/13/23 8:44 AM
Row 327 | Waived per Nate 4/12/2023 | Kristina Waterhouse | 04/13/23 6:25 AM
Row 328 | no documentation confirming withdrawal | Kaiya Hoogkamp | 10/22/24 11:45 AM
Row 329 | Customer confirmed withdrawal 2/15/2023 after failed TS, resubmitted as L4. | Nathan Lawrence | 10/15/24 5:52 PM
Row 331 | no documentation confirming withdrawal | Kaiya Hoogkamp | 10/22/24 11:44 AM
Row 332 | Project sold to Perennial September 2024. New IA sent 10/2/24. Awaiting letter of intent and updated assignement sheet - NAL 10/2/24. | Nathan Lawrence | 10/02/24 10:37 AM
Row 332 | sent IT ticket | Jessie Ladaga | 05/11/23 9:59 AM
Row 335 | paid 07-06-2023 | Helen Markham | 01/11/24 10:40 AM
Row 335 | reopend aplication due to the POI incorrect during screenings awaiting on DE for updated results | William Dawe | 05/08/23 10:41 AM
Row 335 | Might be waiving second set of ESA Charges?????? | Kristina Waterhouse | 05/08/23 10:27 AM
Row 335 | Requested USM1 debtor in SAP | Kristina Waterhouse | 05/08/23 10:19 AM
Row 335 | They replied that Goodwin Motors was not a valid DBA for "FRG, Inc"... responded that we need customer name to match on W9 | Kristina Waterhouse | 04/25/23 12:15 PM
Row 335 | Followed up on W9 request | Kristina Waterhouse | 04/12/23 7:20 AM
Row 335 | Requested W9 | Kristina Waterhouse | 04/07/23 1:13 PM
Row 337 | Customer withdraw request 6/13/2023. | Nathan Lawrence | 10/15/24 5:42 PM
Row 337 | contract completed | Staci Pellegrini | 02/27/24 8:12 AM
Row 337 | INC3066209 entered ticket to cancel PIA | Kaiya Hoogkamp | 09/05/23 11:14 AM
Row 337 | released contract 9/5/2023 & Informed Christy prj is withdrawn, she will cancel | Kaiya Hoogkamp | 09/05/23 10:59 AM
Row 337 | Found that this should not have been invoiced per Will dated 6/13/23 This project 82404 withdrew before ESA. Contract and PIA will need to be canceled. | Staci Pellegrini | 06/14/23 11:54 AM
Row 337 | invoice sent to customer | Jessie Ladaga | 05/15/23 9:31 AM
Row 337 | waiting on invoice; then need to sent to developer | Jessie Ladaga | 05/11/23 12:49 PM
Row 337 | esa agreement sent on 5/8/2023 waiting on dev and signature | William Dawe | 05/08/23 2:32 PM
Row 337 | need to send invoice. no signed ESA as of 4/24/2023 | Jessie Ladaga | 04/24/23 2:46 PM
Row 338 | INC2889448 to clear payment | Kristina Waterhouse | 06/09/23 9:06 AM
Row 338 | INC2770901 to clear PIA | Kristina Waterhouse | 04/12/23 12:47 PM
Row 338 | Requested debtor in SAP | Kristina Waterhouse | 04/11/23 1:56 PM
Row 338 | Requested W9 | Kristina Waterhouse | 04/07/23 1:35 PM
Row 339 | Customer confirmed PRJ withdrawn 2/23/23. Replaced w/ 82924. | Nathan Lawrence | 10/15/24 4:00 PM
Row 340 | 1233.40 | Staci Pellegrini | 08/16/23 11:32 AM
Row 340 | Extended debtor to 90/90 | Kristina Waterhouse | 04/06/23 10:21 AM
Row 340 | Requested W9 | Kristina Waterhouse | 04/05/23 8:36 AM
Row 341 | Submitted INC2807753 to open CM 910178007 for refund | Kristina Waterhouse | 05/01/23 9:40 AM
Row 342 | Project withdrawn 5/11/23, failed ESA. | Nathan Lawrence | 10/15/24 3:57 PM
Row 342 | Submitted INC2770359 to move/clear PIA | Kristina Waterhouse | 04/12/23 10:17 AM
Row 342 | Katherine used this PIA for project 82255 | Kristina Waterhouse | 04/12/23 8:42 AM
Row 342 | Found PIA confirmation but don't see payment? | Kristina Waterhouse | 04/11/23 2:34 PM
Row 342 | Created debtor | Kristina Waterhouse | 04/07/23 2:05 PM
Row 342 | Requested W9 4/3 | Kristina Waterhouse | 04/03/23 12:11 PM
Row 343 | 4/10/2024 project withdrawn per customer request. They cannot receive permits required to build. | Kaiya Hoogkamp | 04/10/24 3:15 PM
Row 343 | remaining credit will need to be refunded | Staci Pellegrini | 10/06/23 8:45 AM
Row 343 | invoice created 3/9/2023 sjp | Staci Pellegrini | 03/09/23 11:31 AM
Row 344 | 1/26/2023 failed esa and withdrew | Kaiya Hoogkamp | 10/22/24 11:42 AM
Row 344 | can't find deposit | Kristina Waterhouse | 04/13/23 10:07 AM
Row 344 | extended debtor in SAP | Kristina Waterhouse | 04/11/23 2:41 PM
Row 346 | Submitted INC2836191 to clear old milestone. Changed contract amount and released. | Kristina Waterhouse | 05/15/23 11:51 AM
Row 346 | Sumbitted CM 910179847 to clear incorrect invoice. Then need to redo milestone. New PIA #1 910179850/920197922 INC2832601 to move money from old PIA New PIA #2 910179851/ INC2832623 to move money | Kristina Waterhouse | 05/12/23 9:27 AM
Row 346 | Katherine used the wrong PIA payment and dollar amount.... This project only had a PIA of $500. Submitted INC270359 to cancel PIA 910173793/920191452 | Kristina Waterhouse | 04/12/23 9:56 AM
Row 348 | 10/21/2024 project requested withdrawal | Kaiya Hoogkamp | 10/22/24 11:41 AM
Row 349 | INC2873394 to clear payment | Kristina Waterhouse | 06/01/23 8:55 AM
Row 349 | INC2773312 to clear PIA | Kristina Waterhouse | 04/13/23 10:35 AM
Row 349 | Extended debtor in SAP | Kristina Waterhouse | 04/12/23 11:22 AM
Row 350 | Customer withdraw request 2/9/23 after failed TS. | Nathan Lawrence | 10/15/24 3:49 PM
Row 351 | 5/22/2023 customer confirmed withdrawing project | Kaiya Hoogkamp | 06/20/24 8:32 AM
Row 353 | Submitted INC2807736 to open credit memo for refund | Kristina Waterhouse | 05/01/23 9:32 AM
Row 353 | INC2773476 to clear PIA | Kristina Waterhouse | 04/13/23 11:31 AM
Row 353 | Emailed Christy.... debtors don't match W9 | Kristina Waterhouse | 04/12/23 11:39 AM
Row 354 | no documentation confirming withdrawal | Kaiya Hoogkamp | 10/22/24 11:40 AM
Row 355 | 2/22/2023 project failed ESA and withdrew. | Kaiya Hoogkamp | 10/16/24 8:42 AM
Row 355 | Can't find fully executed ESA | Kristina Waterhouse | 04/13/23 11:54 AM
Row 355 | Extended debtor in SAP | Kristina Waterhouse | 04/12/23 11:52 AM
Row 356 | IA for Tenant Change sent 10/3/24. Changed from "Moose River Lumber Co" to "Boundary Co". | Nathan Lawrence | 10/03/24 12:53 PM
Row 357 | Per Staci we have reassignment, new W9 and new IA so we are billing under Propspect Solar One LLC.... Extended USM1 in SAP | Kristina Waterhouse | 04/13/23 12:09 PM
Row 357 | The ESA is under VCP but customer is now Prospect Solar One LLC.... | Kristina Waterhouse | 04/12/23 12:09 PM
Row 358 | 2/9/2023 application withdrew | Kaiya Hoogkamp | 10/16/24 2:09 PM
Row 359 | 11/8/2022 project failed ESA and withdrew. | Kaiya Hoogkamp | 10/16/24 2:12 PM
Row 359 | Sent follow up email on refund info | Kristina Waterhouse | 06/02/23 10:58 AM
Row 359 | Sent follow up email for refund info. | Kristina Waterhouse | 05/22/23 7:40 AM
Row 359 | INC2836420 to open funds for refund and emailed customer for refund info | Kristina Waterhouse | 05/15/23 1:26 PM
Row 359 | Refund on straight invoice | Kristina Waterhouse | 04/13/23 1:41 PM
Row 360 | 11/16/2022 project requested to withdraw. | Kaiya Hoogkamp | 10/16/24 2:13 PM
Row 360 | Emailed again for status on where the payment was moved | Kristina Waterhouse | 05/22/23 1:28 PM
Row 360 | This projects deposit was cleared to PRJ 81513. PRJ 81513's deposit went to consumption. Emailed Sales admin. | Kristina Waterhouse | 04/14/23 11:53 AM
Row 360 | Created debtor in SAP | Kristina Waterhouse | 04/13/23 2:22 PM
Row 360 | Requested W9 4/3 | Kristina Waterhouse | 04/03/23 1:47 PM
Row 361 | 4/14/2023 project withdrawn | Kaiya Hoogkamp | 10/16/24 2:23 PM
Row 361 | Submitted INC2871126 to clear PIA | Kristina Waterhouse | 05/31/23 12:24 PM
Row 361 | PRJ 81958's deposit is missing. PRJ 81959's deposit was cleared to 81958. Sent email to sales admin to track down payment. There is an uncleared 500 on debtor 931931 but it's just a bank recon and I can't find anything else tied to the doc #. | Kristina Waterhouse | 05/18/23 2:03 PM
| Treasurey was able to find the payment and release it to sundry. | Kristina Waterhouse | 05/25/23 2:03 PM
Row 361 | Requested debtor in SAP | Kristina Waterhouse | 05/04/23 10:59 AM
Row 361 | Requested W9 | Kristina Waterhouse | 04/14/23 1:04 PM
Row 362 | 12/7/2022 project failed ESA and withdrew. | Kaiya Hoogkamp | 10/16/24 2:22 PM
Row 363 | 10/13/2022 project withdrawn. | Kaiya Hoogkamp | 10/16/24 2:21 PM
Row 365 | 2/21/2023 application withdrawn. | Kaiya Hoogkamp | 10/16/24 2:20 PM
Row 366 | Invoice for NOTI 10300952863 paid 11/11/2024 | Nathan Lawrence | 12/10/24 12:26 PM
Row 366 | Updated ESA name to Rewild per ESA agreement | Kristina Waterhouse | 03/20/23 12:48 PM
Row 368 | 1/26/2023 failed ESA and project withdrew. | Kaiya Hoogkamp | 10/16/24 2:17 PM
Row 368 | INC2803382 to cancel Katherines old PIA 910174793, it was never paid | Kristina Waterhouse | 04/27/23 1:24 PM
Row 369 | 9/6/2022 project failed ESA and withdrew. | Kaiya Hoogkamp | 10/16/24 2:15 PM
Row 371 | 11/21/2022 project failed ESA and withdrew. | Kaiya Hoogkamp | 10/16/24 2:29 PM
Row 371 | the PIA was refunded customer not charged because of mis communication and email accidentially sent stating it was Pass when it was not ... | Staci Pellegrini | 01/11/24 12:30 PM
Row 371 | PIA was refunded! | Kristina Waterhouse | 05/04/23 11:21 AM
Row 371 | Found my deposit but it's cleared to a DC?? | Kristina Waterhouse | 04/14/23 1:39 PM
Row 372 | Correct Debtor is 933090 | Kaiya Hoogkamp | 04/16/25 9:06 AM
Row 372 | ESA Contract 120007418 INVOICE: 910262401 | Kaiya Hoogkamp | 04/09/25 9:03 AM
Row 372 | Coordination Study Contract 12007402 INVOICE: 910262399 | Kaiya Hoogkamp | 04/09/25 8:55 AM
Row 372 | NEW $500 contract: 120007418 PIA 910258361/920281370 | Kaiya Hoogkamp | 03/18/25 10:20 AM
Row 372 | Credit memo created 3/11/25: 910256926/920280771 & released | Kaiya Hoogkamp | 03/11/25 1:46 PM
Row 372 | Second contract for coordination study ($3200): 120007402. PIA: 910256233/920279200 | Kaiya Hoogkamp | 03/05/25 3:56 PM
Row 372 | 4/11/2023 project withdrew. | Kaiya Hoogkamp | 10/16/24 2:25 PM
Row 372 | Helen followed up on outstanding bal 2/14/24 | Staci Pellegrini | 02/28/24 4:24 PM
Row 372 | invoice 910197050 created for $500.00 ESA this correct debtor. | Staci Pellegrini | 10/06/23 9:35 AM
Row 372 | Need to lower the contract amount... this is the one that's cleared to a straight invoice | Kristina Waterhouse | 05/25/23 2:16 PM
| because of this kristina's invoice will need to be cancel and rebilled correctly with a PIA | Staci Pellegrini | 09/20/23 10:39 AM
Row 372 | PRJ 81958's deposit is missing. PRJ 819589's deposit was cleared to 81958. Sent email to sales admin to track down payment. There is an uncleared 500 on debtor 931931 but it's just a bank recon and I can't find anything else tied to the doc #. | Kristina Waterhouse | 05/18/23 2:03 PM
| this 500.00 is actual on debtor 931931, had to cancel invoice on 931931 and have $500.00 pmt mvd 933090 | Staci Pellegrini | 09/20/23 10:39 AM
Row 372 | i canceled the straight invoice last week ( smartsheets down) uner 931931 910160414/920176842 (adj 0.00) and asked for money to be moved over 933090. | Staci Pellegrini | 09/20/23 10:37 AM
Row 372 | email sent to Kaiya and straight invoice will need to be canceled. and contract reset from no guarantee to a guarantee. | Staci Pellegrini | 08/22/23 4:38 PM
Row 372 | PIA payment is pa 8400040065 11/15/2022 500.00 sitting on 931931 and needs to be moved to 933090. | Staci Pellegrini | 08/22/23 4:37 PM
Row 372 | INC2871110 to cancel PIA... paid with straight invoice | Kristina Waterhouse | 05/31/23 12:25 PM
Row 372 | Requested debtor in SAP | Kristina Waterhouse | 05/04/23 11:00 AM
Row 373 | 10/19/2022 project failed ESA and withdrew. | Kaiya Hoogkamp | 10/16/24 2:31 PM
Row 373 | Sent follow up email on refund info. | Kristina Waterhouse | 05/22/23 7:36 AM
Row 373 | Sent email to confirm refund info | Kristina Waterhouse | 05/15/23 12:58 PM
Row 373 | Submitted INC2836298 to clear invoice and open 766.60 for refund | Kristina Waterhouse | 05/15/23 12:52 PM
Row 373 | Exteded debtor in SAP | Kristina Waterhouse | 05/04/23 11:45 AM
Row 374 | NEW invoice on debtor 924030. Invoice: 910267874/920291265 | Kaiya Hoogkamp | 05/15/25 9:28 AM
Row 374 | Invoice adjustment to $0, 910267871 | Kaiya Hoogkamp | 05/15/25 9:06 AM
Row 374 | The correct debtor is 924030 | Kaiya Hoogkamp | 05/15/25 8:23 AM
Row 374 | UPDATED Invoice for $1000: 910262692/920285786 | Kaiya Hoogkamp | 04/10/25 1:34 PM
Row 374 | 4/10/25 app invoice adjustment to $0.00 910262686 | Kaiya Hoogkamp | 04/10/25 1:27 PM
Row 375 | 10/10/2022 project failed ESA and withdrew. | Kaiya Hoogkamp | 10/16/24 2:32 PM
Row 376 | sent email Sachin 4/11 for W-9 | Staci Pellegrini | 04/11/23 9:57 AM
Row 378 | 9/28/2022 project failed ESA and withdrew | Kaiya Hoogkamp | 10/16/24 2:49 PM
Row 379 | 3/3/2023 application withdrawn. | Kaiya Hoogkamp | 10/16/24 2:59 PM
Row 380 | 10/10/2022 project failed ESA and withdrew | Kaiya Hoogkamp | 10/16/24 2:57 PM
Row 381 | 10/19/2023 failed ESA, application withdrew. | Kaiya Hoogkamp | 10/17/24 10:55 AM
Row 381 | Canceled Katherine's PIA - INC2802646 | Kristina Waterhouse | 04/27/23 9:33 AM
Row 381 | Cancelled Katherine's contract, cannot find PIA and this needs to be released. | Kristina Waterhouse | 04/25/23 9:38 AM
Row 382 | 10/19/2022 project failed ESA and withdrew. | Kaiya Hoogkamp | 10/17/24 10:51 AM
Row 383 | 2/9/2023 application withdrew. | Kaiya Hoogkamp | 10/17/24 10:50 AM
Row 384 | 2/9/2023 application withdrew. | Kaiya Hoogkamp | 10/17/24 10:36 AM
Row 385 | 9/23/2022 project failed ESA and withdrew. | Kaiya Hoogkamp | 10/17/24 10:29 AM
Row 385 | sent reminder email for payment 1/10/2024 | Helen Markham | 01/10/24 2:52 PM
Row 385 | No deposit required | Kristina Waterhouse | 05/04/23 11:29 AM
Row 387 | 9/26/2022 application withdrawn. | Kaiya Hoogkamp | 10/16/24 3:02 PM
Row 388 | 8/3/2022 application withdrew. | Kaiya Hoogkamp | 10/17/24 11:07 AM
Row 389 | 10/19/2022 failed ESA and withdrew. | Kaiya Hoogkamp | 10/17/24 10:59 AM
Row 389 | The Payment 500.00 Kristina used originated 922312 clearing doc 2200003472 | Staci Pellegrini | 01/10/24 1:29 PM
Row 389 | per Portal & SAP $500.00 was invoiced under 910160407 10/21/2022 and cleared. for 81848 | Staci Pellegrini | 10/17/23 8:01 AM
| debtor 922331 | Staci Pellegrini | 10/17/23 11:54 AM
Row 389 | INC2855649 to move payment and clear PIA | Kristina Waterhouse | 05/24/23 9:03 AM
Row 389 | Submitted INC2855572 to clear adjusted invoice | Kristina Waterhouse | 05/24/23 8:45 AM
Row 389 | Released CM.... will do milestone after so it doesn't get stuck in my WF | Kristina Waterhouse | 05/23/23 11:15 AM
Row 389 | CM 910180038 to clear incorrect invoice | Kristina Waterhouse | 05/15/23 11:59 AM
Row 389 | I found a deposit when I was about to send this out to the customer..... need to adjust invoice and redo with PIA. | Kristina Waterhouse | 05/15/23 10:18 AM
Row 390 | 1/17/2023 failed ESA, application withdrawn. | Kaiya Hoogkamp | 10/17/24 11:19 AM
Row 390 | INC2856078 to clear random HA/HT pair | Kristina Waterhouse | 05/24/23 10:42 AM
Row 390 | 910181237 to clear Katherine's incorrect invoice | Kristina Waterhouse | 05/24/23 10:18 AM
Row 390 | Submitted ticket # INC2807808 to clear PIA | Kristina Waterhouse | 05/01/23 10:36 AM
Row 390 | Submitted ticket INC2807806 to cancel hx invoice 910165985 which never had a payment cleared to it. | Kristina Waterhouse | 05/01/23 10:31 AM
Row 391 | Ticket to cancel old PIA was closed but never done.... submitted INC2932865 | Kristina Waterhouse | 06/30/23 10:11 AM
Row 391 | Emailed front end.... I don't think a deposit was paid on this one. | Kristina Waterhouse | 05/09/23 12:16 PM
Row 391 | Submitted ticket INC2807815 to cancel PIA INC2807815, it was never paid so we'll bill total charges on milestone | Kristina Waterhouse | 05/01/23 10:40 AM
Row 392 | 9/28/2022 failed ESA and withdrew | Kaiya Hoogkamp | 10/17/24 11:28 AM
Row 392 | Extended debtor in SAP | Kristina Waterhouse | 04/27/23 12:05 PM
Row 392 | Cancelled Katherine's old contract | Kristina Waterhouse | 04/25/23 9:41 AM
Row 393 | 8/8/2022 failed tech screen, no formal email requesting withdraw. | Kaiya Hoogkamp | 10/17/24 11:45 AM
Row 395 | 9/12/2022 project withdrew | Kaiya Hoogkamp | 10/17/24 11:55 AM
Row 395 | Confirmed project never went to ESA | Kristina Waterhouse | 04/27/23 8:49 AM
Row 395 | Doesn't look like the ESA on this one was ever actually executed, project was withdrawn the same day the agreement was issued to the customer. | Kristina Waterhouse | 04/27/23 8:11 AM
Row 395 | Application was withdrawn 9/12/22.... we need to verify the study was not aleady started. | Kristina Waterhouse | 04/05/23 7:27 AM
Row 396 | 9/28/2022 failed ESA and withdrew. | Kaiya Hoogkamp | 10/17/24 11:49 AM
Row 396 | Submitted INC2802599 to cancel Katherine's old PIA | Kristina Waterhouse | 04/27/23 9:25 AM
Row 397 | 9/1/2022 application withdrawn. | Kaiya Hoogkamp | 10/17/24 12:22 PM
Row 398 | 500.00 Pia created ... need to bill remaining | Staci Pellegrini | 06/20/23 4:26 PM
Row 398 | 120004855 - cancelled contract | Kristina Waterhouse | 05/26/23 12:06 PM
Row 398 | Brian is going to cancel the PIA that katherine created on Revision ... as this needs to go on Oceanview instead. | Staci Pellegrini | 05/24/23 3:56 PM
Row 401 | 7/25/2022 application withdrawn. | Kaiya Hoogkamp | 10/17/24 12:51 PM
Row 402 | 8/3/2022 application withdrawn | Kaiya Hoogkamp | 10/17/24 12:50 PM
Row 403 | no documentation verifying withdrawal. | Kaiya Hoogkamp | 10/17/24 12:39 PM
Row 404 | 2/10/2023 application withdrew | Kaiya Hoogkamp | 10/17/24 12:24 PM
Row 405 | 2/10/2023 application withdrawn. | Kaiya Hoogkamp | 10/17/24 12:23 PM
Row 406 | 12/6/2022 application withdrawn. | Kaiya Hoogkamp | 10/17/24 12:54 PM
Row 407 | 8/10/2022 application withdrawn. | Kaiya Hoogkamp | 10/17/24 12:57 PM
Row 407 | Created USS1 under NES | Kristina Waterhouse | 05/31/23 1:51 PM
Row 407 | Requested W9 | Kristina Waterhouse | 05/30/23 12:07 PM
Row 408 | Requested W9 | Kristina Waterhouse | 05/30/23 12:11 PM
Row 408 | This project used deposit meant for project 81972. Deposit meant for this project was sent to consumption.... emailed sales admin. | Kristina Waterhouse | 04/14/23 11:53 AM
Row 409 | 3/3/2023 application withdrawn | Kaiya Hoogkamp | 10/17/24 12:56 PM
Row 410 | 6/21/2022 application withdrawn | Kaiya Hoogkamp | 10/17/24 12:55 PM
Row 411 | 10/19/2022 application withdrawn | Kaiya Hoogkamp | 10/17/24 1:08 PM
Row 411 | Created USS1 under NES | Kristina Waterhouse | 05/31/23 1:51 PM
Row 411 | Requested W9 | Kristina Waterhouse | 05/30/23 12:04 PM
Row 412 | 6/17/2022 application withdrawn. | Kaiya Hoogkamp | 10/17/24 12:59 PM
Row 413 | 6/17/2022 application withdrawn | Kaiya Hoogkamp | 10/17/24 12:58 PM
Row 416 | 6/30/2022 application withdrawn | Kaiya Hoogkamp | 10/17/24 1:10 PM
Row 417 | 6/15/2022 application withdrawn | Kaiya Hoogkamp | 10/17/24 1:09 PM
Row 418 | 6/8/2022 application withdrawn | Kaiya Hoogkamp | 10/17/24 1:27 PM
Row 419 | 6/27/2022 application withdrawn | Kaiya Hoogkamp | 10/17/24 1:28 PM
Row 420 | Extended debtor in SAP | Kristina Waterhouse | 06/02/23 12:29 PM
Row 420 | Receiced W9 naming Outlook Farm LLC as a DBA for Great Works Properties. There is a blocked debtor in SAP that matches by TIN. Submitted INC2876682 to have it unblocked. | Kristina Waterhouse | 06/02/23 12:09 PM
Row 420 | Emailed for updated assigment information and W9.... name in portal and on CMP account has been updated to Great Works Property Inc | Kristina Waterhouse | 05/31/23 11:19 AM
Row 421 | 6/8/2022 application withdrawn | Kaiya Hoogkamp | 10/17/24 1:30 PM
Row 422 | Old Account# 30013836017 | Nathan Lawrence | 07/25/24 3:42 PM
Row 423 | Ticket INC2812351 to clear payment | Kristina Waterhouse | 05/03/23 7:07 AM
Row 424 | no documentation confirming the withdrawal date | Kaiya Hoogkamp | 10/17/24 1:57 PM
Row 425 | no documentation confirming the project is withdrawn | Kaiya Hoogkamp | 10/17/24 2:33 PM
Row 426 | 6/30/2022 application withdrawn | Kaiya Hoogkamp | 10/17/24 2:16 PM
Row 427 | 4/9/2022 failed ESA and withdrew | Kaiya Hoogkamp | 10/17/24 2:39 PM
Row 427 | Adj invoicefrom 2994.64 to 2007.92 910207125 | Staci Pellegrini | 01/12/24 10:38 AM
Row 427 | Kristina has over billed 81262 she billed part of Auburn Penley Corner to this one invoice needs to be adj | Staci Pellegrini | 01/12/24 9:50 AM
Row 427 | They replied that they will update the name on the account to Novel... still has not been done. Sent follow up email. | Kristina Waterhouse | 05/30/23 12:00 PM
Row 427 | Requested W9 | Kristina Waterhouse | 05/24/23 1:09 PM
Row 428 | 8/30/2022 4:17:31 PM Jessie Roderick (U341040) ESA not needed. TS passed. DE revised. | Kristina Waterhouse | 03/21/23 12:32 PM
Row 429 | Charges in 12/22 but study was completed 8/22 | Kristina Waterhouse | 05/24/23 1:45 PM
Row 430 | 7/19/2022 application withdrawn | Kaiya Hoogkamp | 10/17/24 2:47 PM
Row 431 | no documentation for withdrawal | Kaiya Hoogkamp | 10/17/24 2:45 PM
Row 432 | no documentation regarding withdrawal | Kaiya Hoogkamp | 10/17/24 2:58 PM
Row 432 | cleared by doubtful debt | Kaiya Hoogkamp | 04/17/23 8:57 AM
Row 433 | no documentation about withdrawal | Kaiya Hoogkamp | 10/17/24 2:55 PM
Row 435 | 2/9/2023 application withdrawn | Kaiya Hoogkamp | 10/17/24 3:03 PM
Row 436 | 8/9/2022 application withdrawn | Kaiya Hoogkamp | 10/17/24 3:16 PM
Row 437 | Per W9 refund needs to be issued on USM1 debtor 929912. Submitted INC2879510 to move payment to correct debtor. | Kristina Waterhouse | 06/05/23 7:51 AM
Row 437 | Sent follow up email | Kristina Waterhouse | 06/02/23 10:35 AM
Row 437 | Sent follow up email for refund info. | Kristina Waterhouse | 05/22/23 7:33 AM
Row 437 | Sent email requesting W9 and to confirm refund info | Kristina Waterhouse | 05/15/23 12:49 PM
Row 437 | Submitted INC2836270 to clear adjusted invoice and open funds for refund. | Kristina Waterhouse | 05/15/23 12:43 PM
Row 438 | 8/9/2022 application withdrawn. | Kaiya Hoogkamp | 10/17/24 3:12 PM
Row 439 | INC2812351 to clear payment | Kristina Waterhouse | 05/03/23 7:07 AM
Row 441 | no documentation confirming withdrawal | Kaiya Hoogkamp | 10/17/24 3:10 PM
Row 442 | 8/17/2022 customer withdrew project | Kaiya Hoogkamp | 05/22/24 9:53 AM
Row 443 | 8/8/2022 application withdrew | Kaiya Hoogkamp | 10/17/24 3:19 PM
Row 443 | sent reminder email for payment 1/10/2024 | Helen Markham | 01/10/24 2:52 PM
Row 444 | no documentation on withdrawal | Kaiya Hoogkamp | 10/17/24 3:23 PM
Row 445 | 8/2/2022 application withdrawn | Kaiya Hoogkamp | 10/17/24 3:30 PM
Row 446 | 2000.00 910154560 | Staci Pellegrini | 01/08/24 4:58 PM
Row 446 | revision 1289121 | Staci Pellegrini | 01/08/24 4:55 PM
Row 446 | $2000.00 esa deposit paid by revision 1489121.. remaining balance Kristina billed under 933140 | Staci Pellegrini | 01/08/24 4:54 PM
Row 446 | Requested debtor in SAP | Kristina Waterhouse | 05/12/23 1:26 PM
Row 447 | no documentation verifying withdrawal. | Kaiya Hoogkamp | 10/17/24 3:29 PM
Row 447 | Converted NOTI to USM1 and exteneded to 90/90 | Kristina Waterhouse | 05/30/23 1:14 PM
Row 447 | Followed up on W9 request | Kristina Waterhouse | 05/24/23 12:52 PM
Row 447 | Requested W9 | Kristina Waterhouse | 05/12/23 1:37 PM
Row 448 | 9/27/2022 application withdrawn | Kaiya Hoogkamp | 10/17/24 3:32 PM
Row 449 | 9/28/2022 application moved to level 4 and withdrawn as level 2. | Kaiya Hoogkamp | 10/17/24 3:42 PM
Row 450 | 10/10/2022 application withdrawn | Kaiya Hoogkamp | 10/17/24 3:41 PM
Row 450 | Submitted INC2833148 to clear adjusted invoice and open for refund | Kristina Waterhouse | 05/12/23 1:17 PM
Row 452 | 4/26/2022 application withdrew | Kaiya Hoogkamp | 10/17/24 3:39 PM
Row 453 | 5/26/2022 application moved to level 4 and withdrawn as level 2. | Kaiya Hoogkamp | 10/17/24 3:44 PM
Row 454 | no documentation verifying withdrawal. | Kaiya Hoogkamp | 10/17/24 3:45 PM
Row 455 | no documentation confirming withdrawal | Kaiya Hoogkamp | 10/17/24 3:52 PM
Row 455 | paid 06/26/2023 | Helen Markham | 01/11/24 10:27 AM
Row 455 | sent itnow ticket to clear dd with credit memo | Staci Pellegrini | 01/08/24 4:43 PM
Row 455 | Original invoice is with doubtful debt, need to identify the process | Kristina Waterhouse | 07/03/23 9:36 AM
Row 455 | Requested extension to 90/90 in SAP | Kristina Waterhouse | 06/05/23 12:31 PM
Row 455 | Customer replied that they are in the process of this project changing from Penobscot Narrow Solar to Penobscot Narrow Solar I. Asked estimated time frame | Kristina Waterhouse | 05/23/23 1:37 PM
Row 455 | Requested W9 | Kristina Waterhouse | 05/12/23 12:23 PM
Row 456 | 5/26/2022 project failed ESA and withdrew | Kaiya Hoogkamp | 10/17/24 3:56 PM
Row 457 | 12/6/2022 application withdrawn | Kaiya Hoogkamp | 10/18/24 11:18 AM
Row 458 | 6/8/2022 application withdrawn | Kaiya Hoogkamp | 10/18/24 11:15 AM
Row 458 | sent reminder email for payment 1/10/2024 | Helen Markham | 01/10/24 2:53 PM
Row 458 | Sent email for charge clarification. Katherine had labeled some June charges for this project but the study had already been completed in May. Novel had multiple projects during this time period. | Kristina Waterhouse | 05/30/23 11:53 AM
Row 459 | 6/20/2022 application withdrawn | Kaiya Hoogkamp | 10/18/24 11:23 AM
Row 460 | 5/26/2022 application withdrawn | Kaiya Hoogkamp | 10/18/24 11:22 AM
Row 461 | 6/30/2022 application withdrawn. | Kaiya Hoogkamp | 10/18/24 11:21 AM
Row 463 | 4/5/2022 application withdrawn | Kaiya Hoogkamp | 10/18/24 11:20 AM
Row 464 | 9/14/2022 application withdrawn | Kaiya Hoogkamp | 10/18/24 11:25 AM
Row 465 | 4/25/2022 app failed ESA and withdrawn | Kaiya Hoogkamp | 10/18/24 11:28 AM
Row 465 | sent email to dante to ask why charges are 6475.35 when est being 500.00 | Staci Pellegrini | 01/08/24 3:05 PM
Row 465 | We charged 500.00 flat fee 7/7/2022 910150282/920166049 | Staci Pellegrini | 01/08/24 1:12 PM
Row 465 | W-9 Received | Kaiya Hoogkamp | 10/10/23 7:41 AM
Row 465 | Emailed requesting W-9 in order to create final invoice | Kaiya Hoogkamp | 10/02/23 1:41 PM
Row 465 | Followed up on W9 request | Kristina Waterhouse | 06/21/23 8:24 AM
Row 465 | Requested W9 | Kristina Waterhouse | 06/05/23 11:42 AM
Row 465 | Requested W9 | Kristina Waterhouse | 05/26/23 9:18 AM
Row 466 | Sent email confirming refund information | Kristina Waterhouse | 05/23/23 8:46 AM
Row 466 | 910152320 920169118 7/28/2022 CREATED / ADJ 3/17/2023 920191690 2000.00 | Staci Pellegrini | 04/18/23 3:50 PM
Row 466 | REFUND NEEDED | Staci Pellegrini | 04/18/23 3:26 PM
Row 469 | orig inovice 2000.00 910155488 920171646 4/28/2022 debtor 910795 has been adj 0.00 910232840 due to inv kristina created listed here | Staci Pellegrini | 08/07/24 11:23 AM
Row 469 | Paid 07/28/2023 | Helen Markham | 01/11/24 10:29 AM
Row 469 | The hx invoice is with doubtful debt. Submitted INC2936503 to determine the correct process for adjusting this invoice | Kristina Waterhouse | 07/03/23 9:21 AM
Row 469 | Extended debtor in SAP | Kristina Waterhouse | 06/05/23 9:12 AM
Row 469 | Followed up again on W9 request | Kristina Waterhouse | 05/31/23 11:26 AM
Row 469 | Followed up on W9 request | Kristina Waterhouse | 05/23/23 1:13 PM
Row 469 | Requested W9 | Kristina Waterhouse | 05/11/23 1:59 PM
Row 471 | 6/3/2022 application withdrawn | Kaiya Hoogkamp | 10/18/24 11:31 AM
Row 471 | Prior invoice 0.00 due to pia found 2000.00 from 10/11/2022 6000.00 group pmt, Tom created new PIA NEW CONTRACT 120006275/ | Staci Pellegrini | 03/15/24 9:53 AM
Row 471 | 910185191 to clear Katherines old invoice | Kristina Waterhouse | 06/30/23 12:15 PM
Row 472 | 5/18/2022 application failed ESA and withdrew | Kaiya Hoogkamp | 10/18/24 11:31 AM
Row 472 | New contract 120006269, PIA 910213705 | Thomas Blanchard | 03/06/24 9:46 AM
Row 472 | 120005192 prior contract from Kristina did not have 500.00 pai this has been canceled and 0.00 TOm to create an new contract and pia and invoice 3/5/24 | Staci Pellegrini | 03/05/24 11:33 AM
Row 472 | prior invoice 2096..78 has been 0.00 Helen located 500.00 pia that belongs to this contract this needs to be reinvoiced under a new contract. Details in project backup file | Staci Pellegrini | 03/05/24 11:25 AM
Row 472 | sent reminder email for payment 1/10/2024 | Helen Markham | 01/10/24 2:53 PM
Row 472 | I had already tried to adjust this.... verified all old invoices are correctly cleared and only invoice that is outstanding is the one for 2096.78 | Kristina Waterhouse | 06/30/23 12:10 PM
Row 472 | ORIGINAL INVOICE WAS AMENDED SO CREDIT CREDIT INVOICE WAS CREATED 910184660 | Staci Pellegrini | 06/26/23 12:46 PM
Row 472 | 6/26/2023 0.00 invoice created 9/15/2022 910156432/920172671 930085 was replaced w 120005192 invoice920200848 910182481 | Staci Pellegrini | 06/26/23 11:59 AM
Row 472 | 910183703 to clear Katherines unpaid straight invoice | Kristina Waterhouse | 06/16/23 12:11 PM
Row 473 | 9/30/2024 project withdrawn. | Kaiya Hoogkamp | 09/30/24 11:51 AM
Row 473 | sent reminder email for payment 1/10/2024 | Helen Markham | 01/10/24 2:54 PM