## 2021-2021 IA Value (hidden)
PRJ # | WBS | IA value 12/31/2020 | IA value 12/31/2021
1 | UI-C6157 | N/A | 150688
2&3 | UI-C6005 | N/A | 437870
4 | UI-C6009 | 56522 | N/A
5 | UI-C6011 | 46000 | 46000
6 | UI-C6139 | 399152 | 333793
7 | UI-C6013 | 216810 | 234310
8 | UI-C6031 | 42118 | 43118
9 | UI-C6033 | 33310 | 34310
11 | UI-C6295 | 73810 | 175118
13 | UI-C6305 | 55118 | 253164
14 | UI-C6015 | 24310 | 41810
15 | UI-C6307 | 78618 | 102118
17 | UI-C6035 | 46310 | 301088
18 | UI-C6165 | 360310 | 361310
19 | UI-C6123 | 474485 | 603968
20 | UI-C6167 | 85810 | 161365
21 | UI-C6017 | 71810 | 89310
22 | UI-C6163 | 646810 | 421589
23 | UI-C6019 | N/A | 43118
24 | UI-C6037 | 114310 | 114310
25 | UI-C6021 | 97022 | 97022
28 | UI-C6183 | 42118 | N/A
29 | UI-C6265 | 119306 | N/A
30 | UI-C6169 | 222610 | N/A
31 | UI-C6107 | 54522 | 55522
32 | UI-C6109 | 39522 | 40522
33 | UI-C6111 | 893723 | 1096642
34 | UI-C6399 | 230207 | 310668
37 | UI-C6125 | 44022 | 208742
40 | UI-C6039 | 496022 | 658132
43 | UI-C6185 | 40522 | 41522
44 | UI-C6041 | 183522 | 204210
45 | UI-C6023 | 24522 | 25522
48 | UI-C6043 | 511513 | 512513
49 | UI-C6045 | 145522 | 146522
50 | UI-C6047 | 42118 | 43118
51 | UI-C6025 | 90310 | 91310
53 | UI-C6153 | 100910 | 226797
54 | UI-C6533 | N/A | 973721
57 | UI-C6027 | 79500 | 380522
59 | UI-C6187 | 229022 | 230022
61 | UI-C6171 | 864522 | 864522
62 | UI-C6029 | 42118 | 43118
63 | UI-C6103 | 1376522 | N/A
64 | UI-C6049 | 80522 | 349295
65 | UI-C6245 | 360105 | 361105
66 | UI-C6173 | N/A | 388712
67 | UI-C6401 | 199943 | 217443
68 | UI-C6297 | 1186448 | N/A
69 | UI-C6313 | 167238 | 240263
70 | UI-C6101 | 69899 | 124658
74 | UI-C6317 | 245841 | 246841
76 | UI-C6319 | 256982 | 501790
77 | UI-C6213 | 42118 | 43118
79 | UI-C6127 | 614022 | 614022
80 | UI-C6085 | 46522 | 161631
81 | UI-C6051 | 24522 | 25522
82 | UI-C6241 | N/A | 173641
84 | UI-C6235 | 390522 | 327022
86 | UI-C6179 | 74899 | 75899
88 | UI-C6321 | 77456 | 78456
89 | UI-C6189 | 587618 | 588618
90 | UI-C6053 | 35865 | 36865
92 | UI-C6403 | 191185 | 122571
94 | UI-C6095 | 32022 | 33022
95 | UI-C6323 | 415905 | 599717
96 | UI-C6325 | 122016 | 285516
102 | UI-C6131 | 78810 | 493335
110 | UI-C6133 | 271067 | 272067
114 | UI-C6181 | N/A | 36835
116 | UI-C6267 | 409425 | 593796
117 | UI-C6269 | 945339 | 1160607
118 | UI-C6271 | 79522 | 80522
119 | UI-C6197 | 64118 | 65118
122 | UI-C6055 | 708690 | N/A
123 | UI-C6057 | 235097 | 247747
124 | UI-C6059 | 349031 | N/A
125 | UI-C6237 | 69899 | 70899
129 | UI-C6135 | 362333 | 487912
130 | UI-C6405 | N/A | 494055
131 | UI-C6247 | 720550 | 862677
133 | UI-C6175 | 155960 | N/A
135 | UI-C6583 | N/A | 460974
138 | UI-C6407 | 367420 | 384920
140 | UI-C6557 | 272231 | 316122
141 | UI-C6327 | 68772 | 69772
142 | UI-C6117 | 96522 | 97522
144 | UI-C6329 | 51685 | 168335
146 | UI-C6191 | 46522 | 153956
148 | UI-C6061 | 24522 | 48022
149 | UI-C6409 | 107522 | 75834
150 | UI-C6063 | 77456 | 78456
151 | UI-C6331 | 151466 | 103673
152 | UI-C6679 | 2900995 | 1707817
153 | UI-C6065 | 79522 | 80522
158 | UI-C6535 | 84974 | 241129
160 | UI-C6411 | N/A | 1636213.42
161 | UI-C6137 | 35835 | N/A
163 | UI-C6067 | 24522 | 25522
168 | UI-C6219 | 84022 | 85022
169 | UI-C6413 | N/A | 699492
170 | UI-C6333 | 958522 | N/A
172 | UI-C6097 | 363427 | 526927
174 | UI-C6069 | 214899 | 540899
175 | UI-C6221 | 749454 | 750454
176 | UI-C6121 | 869022 | 911140
180 | UI-C6071 | 64522 | 138693
181 | UI-C6115 | 805091 | 1336361
184 | UI-C6701 | N/A | 439353
186 | UI-C6335 | 160997 | 149353
189 | UI-C6273 | 625358 | 866470
190 | UI-C6337 | 92219 | 93219
191 | UI-C6339 | 394331 | 1125806
198 | UI-C6141 | 35835 | 161988
201 | UI-C6417 | 290617 | 540591
202 | UI-C6341 | 194673 | 157698
203 | UI-C6193 | 225022 | 309417
205 | UI-C6537 | N/A | 315782
206 | UI-C6275 | 541863 | 642392
207 | UI-C6143 | 35835 | 163208
209 | UI-C6145 | 525277 | 762978
213 | UI-C6343 | 42118 | 43118
214 | UI-C6073 | 26522 | 95461
217 | UI-C6345 | 200834 | 224334
218 | UI-C6105 | 89522 | 90522
221 | UI-C6075 | 286819 | 543879
222 | UI-C6419 | N/A | 608103
225 | UI-C6077 | 73810 | N/A
226 | UI-C6249 | 129110 | 762610
227 | UI-C6147 | 587199 | 684105
233 | UI-C6423 | 160185 | 160185
234 | UI-C6559 | N/A | 7330637
235 | UI-C6149 | 148793 | 221818
236 | UI-C6425 | N/A | 235112
237 | UI-C6091 | 46685 | 47685
240 | UI-C6349 | 546676 | 665965
245 | UI-C6195 | 489212 | 490212
246 | UI-C6277 | 243962 | 244962
247 | UI-C6351 | 173349 | 174349
249 | UI-C6607 | N/A | 315477
251 | UI-C6079 | 74522 | 162479
252 | UI-C6081 | 65522 | 66522
253 | UI-C6353 | 1149474 | 1150474
254 | UI-C6151 | 186475 | 303759
255 | UI-C6539 | N/A | 165941
256 | UI-C6087 | 107522 | 131022
258 | UI-C6155 | 625784 | 665784
260 | UI-C6355 | 323138 | 495169
262 | UI-C6427 | N/A | 1220233
264 | UI-C6177 | 448455 | 449455
265 | UI-C6429 | N/A | 720392
268 | UI-C6357 | 590378 | 804275
270 | UI-C6223 | 548851 | 641275
271 | UI-C6099 | 35835 | N/A
272 | UI-C6093 | 90476 | 91476
275 | UI-C6159 | 174996 | 175996
282 | UI-C6239 | 1249776 | 1484384
285 | UI-C6253 | 482391 | 482391
287 | UI-C6541 | N/A | 459745
290 | UI-C6217 | 73620 | 416120
295 | UI-C6359 | 80749 | N/A
297 | UI-C6215 | 433374 | N/A
298 | UI-C6361 | 362074 | 315370
301 | UI-C6083 | 179094 | 180094
306 | UI-C6593 | N/A | 402909
308 | UI-C6621 | N/A | 763297
310 | UI-C6585 | N/A | 483621
311 | UI-C6279 | 130541 | N/A
312 | UI-C6365 | N/A | 525085
316 | UI-C6367 | 43353 | N/A
318 | UI-C6431 | 51682 | 162682
319 | UI-C6433 | 238770 | 178692
321 | UI-C6225 | N/A | 471100
325 | UI-C6435 | N/A | 437480
326 | UI-C6437 | 501843 | 594144
328 | UI-C6369 | 62535 | 152976
329 | UI-C6609 | N/A | 65492
330 | UI-C6255 | 423772 | 504210
333 | UI-C6161 | 619788 | 705563
334 | UI-C6655 | N/A | 691296
338 | UI-C6227 | 162281 | 185899
339 | UI-C6281 | 199943 | 208693
341 | UI-C6439 | N/A | 548430
343 | UI-C6257 | 287157 | 304657
344 | UI-C6199 | 83810 | 101310
345 | UI-C6283 | 456995 | 405995
349 | UI-C6371 | 403767 | 695347
351 | UI-C6603 | N/A | 537666
352 | UI-C6605 | N/A | 681828
355 | UI-C6259 | 377581 | 384231
358 | UI-C6443 | 115041 | 123791
359 | UI-C6445 | 485907 | 841501
360 | UI-C6447 | 226332 | 398266
361 | UI-C6449 | N/A | 978840
365 | UI-C6201 | 360560 | 361560
366 | UI-C6229 | 218278 | 281615
368 | UI-C6565 | N/A | 170281
370 | UI-C6633 | N/A | 554137
372 | UI-C6231 | 304101 | 305101
374 | UI-C6451 | 200175 | 435088
376 | UI-C6203 | 181321 | 362408
377 | UI-C6299 | 1030910 | N/A
380 | UI-C6453 | 461563 | 486813
382 | UI-C6373 | 35835 | 162061
385 | UI-C6455 | N/A | 376015
386 | UI-C6243 | 61685 | 162685
388 | UI-C6375 | N/A | 214735
389 | UI-C6635 | N/A | 200322
390 | UI-C6457 | 140025 | 140025
399 | UI-C6251 | 218465 | 223613
400 | UI-C6287 | 111747 | 62602
401 | UI-C6261 | 79899 | 83899
403 | UI-C6381 | 111747 | 474560
407 | UI-C6555 | N/A | 131143
409 | UI-C6461 | 605422 | 677939
411 | UI-C6385 | 84974 | 231228
412 | UI-C6569 | N/A | 370419
413 | UI-C6205 | 112522 | 142031
414 | UI-C6463 | 62341 | 138634
415 | UI-C6263 | 281068 | 787331
416 | UI-C6207 | 79899 | 248496.76
418 | UI-C6519 | N/A | 1190968
429 | UI-C6301 | 40835 | 41835
436 | UI-C6289 | 176847 | 145522
437 | UI-C6291 | 493997 | 907882
440 | UI-C6521 |  | 754353
444 | UI-C6389 | 541001 | 524563
445 | UI-C6465 | N/A | 421059
448 | UI-C6467 | 648009 | 658784
449 | UI-C6469 | 474641 | 716257
450 | UI-C6391 | 655415 | N/A
453 | UI-C6303 | 128987 | 166674
457 | UI-C6471 | 544207 | 543269
459 | UI-C6293 | 212023 | 195546
461 | UI-C6595 | N/A | 1433623
464 | UI-C6473 | 328631 | 537030
469 | UI-C6393 | 110507 | 123157
470 | UI-C6657 | N/A | 265040
473 | UI-C6233 | 205100 | 271425
474 | UI-C6475 | 1476619 | 1624162
477 | UI-C6479 | 80360 | N/A
478 | UI-C6397 | 43353 | N/A
479 | UI-C6481 | 369154 | 377726
483 | UI-C6483 | N/A | 1434786
484 | UI-C6485 | N/A | 456974
485 | UI-C6487 | 302455 | 534145
491 | UI-C6489 | 199478 | 231610
492 | UI-C6545 | N/A | 110326
493 | UI-C6591 | 419423 | 617066
497 | UI-C6491 | 405631 | 573618
499 | UI-C6493 | 935301 | 1359989
504 | UI-C6495 | N/A | 123791
505 | UI-C6497 | 598757 | 761212
506 | UI-C6499 | 360992 | 384492
509 | UI-C6501 | 618579 | 531423
513 | UI-C6597 | N/A | 441068
515 | UI-C6503 | N/A | 688379
519 | UI-C6505 | 314187 | 552070
523 | UI-C6507 | 366722 | 282849
526 | UI-C6571 | N/A | 362360
528 | UI-C6509 | 120058 | 496176
531 | UI-C6511 | N/A | 655034
540 | UI-C6677 | N/A | 80974
541 | UI-C6601 | N/A | 680560
546 | UI-C6531 | N/A | 85622
547 | UI-C6573 | N/A | 1202778
548 | UI-C6623 | N/A | 978161
552 | UI-C6523 | N/A | 1499624
554 | UI-C6513 | N/A | 345444
555 | UI-C6661 | N/A | 242248
557 | UI-C6561 | N/A | 1002103
558 | UI-C6517 | N/A | 524314
560 | UI-C6525 | N/A | 691313
561 | UI-C6625 | N/A | 444395
562 | UI-C6663 | N/A | 276098
565 | UI-C6689 | N/A | N/A
566 | UI-C6515 | N/A | 85974
567 | UI-C6665 | N/A | 352098
568 | UI-C6641 | N/A | 240252
574 | UI-C6617 | N/A | 48992
575 | UI-C6619 | N/A | 388203
579 | UI-C6575 | N/A | 739841
583 | UI-C6667 | N/A | 230923
586 | UI-C6669 | N/A | 133359
588 | UI-C6599 | N/A | 232677
591 | UI-C6691 | N/A | 364353
592 | UI-C6643 | N/A | 119925
594 | UI-C6547 | N/A | 336216
596 | UI-C6611 | N/A | N/A
599 | UI-C6577 | N/A | 446675
600 | UI-C6527 | N/A | 122279
601 | UI-C6645 | N/A | 499335
602 | UI-C6631 | N/A | 896393
603 | UI-C6627 | N/A | 654335
605 | UI-C6613 | N/A | 151343
608 | UI-C6579 | N/A | 461705
613 | UI-C6637 | N/A | 604842
621 | UI-C6673 | N/A | 149353
626 | UI-C6549 | N/A | 685539
627 | UI-C6649 | N/A | 159147
629 | UI-C6639 | N/A | 394340
632 | UI-C6581 | N/A | 1787228
633 | UI-C6529 | N/A | 725823
637 | UI-C6553 | N/A | 54853
639 | UI-C6647 | N/A | 39353
651 | UI-C6563 | N/A | 39353
656 | UI-C6681 | N/A | 1085144
660 | UI-C6615 | N/A | 253064
665 | UI-C6629 | N/A | 90599
675 | UI-C6651 | N/A | 114141
101/106 | UI-C6211 | 109644 | 188367
107/108 | UI-C6089 | N/A | N/A
241/242 | UI-C6653 | N/A | 7277007
97/98 | UI-C6129 | 56685 | N/A
99/100 | UI-C6209 | 75248 | 76248
395 |  | 40835 | 40835
394 |  | N/A | 44587
488 |  |  | 416323
229 |  | 142360 | 267008

## Non-contingent PRJ Tracker. (hidden)
STATUS | EXECUTED
Non-Energized QP | (Multiple Items)
Row Labels
ANDOVER
AUGUSTA K5
BASSETT
BATH 34
BATH NORTH END
BELFAST 115
BELFAST WEST SIDE
BIDDEFORD PUMP
BIGELOW
BONNY EAGLE
BOWMAN STREET
BRIDGTON
BRISTOL
BUCKSPORT
BURNHAM
BUTLER'S CORNER
CAPE ELIZABETH
CLINTON
CORINNA
COUNTY RD (RICE RIPS)
DAMARISCOTTA MILLS
DUNSTAN
ELM STREET
EMBDEN
FAIRFIELD
FREEPORT
FRYEBURG TAP
GREAT FALLS
GUILFORD
HOTEL ROAD
KIMBALL ROAD
LEBANON
LEEDS
LIMERICK
LISBON
LISBON FALLS
LOCKES MILLS
LUDDEN LANE
MANCHESTER
MCCOYS
MESSINA
MIDDLE STREET
MONMOUTH
MONSON
NORTH AUGUSTA
NORTH LIMINGTON
NORWAY
PARK STREET
PNSY
PRATT & WHITNEY
PRIDES CORNER
PUDDLEDOCK ROAD
RAYMOND 115 KV
RAYMOND 34 KV
RICHMOND
RIGBY
RUMFORD
RUMFORD INDUSTRIAL PARK
SANFORD INDUSTRIAL PARK
SEARSPORT
SHAWMUT
SHAWS MILL ROAD
SIDNEY
SKOWHEGAN NORTH SIDE
SKOWHEGAN SOUTH SIDE
SKOWHEGAN TAP
SOUTH BERWICK
SOUTH CHINA
SWETT ROAD
TURNER
WESTON HYDRO
WINTHROP
Grand Total

## Level 4 Applications
PRJ | ISO_QP | Distribution Planning Engineer | Dist Engineer | AREC | ReQued ReStudy Triggered One Date | Trigger One | ReQued ReStudy Triggered One | ReQued ReStudy Triggered Two Date | Trigger Two | ReQued ReStudy Triggered Two2 | ReQued ReStudy Triggered Three Date | Trigger Three | ReQued ReStudy Triggered Three2 | ReQued ReStudy Triggered Four Date | Trigger Four | ReQued ReStudy Triggered Four | ReQued ReStudy Triggered Five Date | Trigger Five | ReQued ReStudy Triggered Five | ReQued ReStudy Triggered Six Date | Trigger Six | ReQued ReStudy Triggered Six | ReQued ReStudy Triggered Seven | Trigger Seven | ReQued ReStudy Triggered Seven2 | ReQued ReStudy Triggered Eight Date | Trigger Eight | ReQued ReStudy Triggered Eight | ReQued ReStudy Triggered Nine | Trigger Nine | ReQued ReStudy Triggered Nine2 | Current ReQued Position | QP | QPOLD | DEP | SubStation_QP | Non-Energized QP | Circuit | SubStation_Dep | ReQueued | STATUS | PHASE | Received | Contact | Developer | Project Name | SAP_ContractAccount | BP | CMP_Acct | Type of Gen | kW AC | MW AC | KW DC | BESS AC | BESS DC | Latitude | Longitude | Address | House Number | Road | Town | Pole Number | Substation | Circuit2 | Transformer | PRIME VOLTAGE | FLOC | FERCSTATUS | IMPACTED_OV | GFOV Determination | OV_TX_COST | Proof of Site Control Rec'd | Developer Executed NEB Affidavit | BESS_Appendix_B | Distribution | Transmission | ISONOTId | ISO_Notif | AORd | NOCd | AOR | NOC | Scoping Availability | Scoping Request | Scoping Due by Date | Scoping Scheduled | Scoping Actual | SCOPING Notes Actual | Dev_Dec_Due_Date | 00Dev Decision FS Actual | 00Dev Decision IS Actual | 00Dev Decision CS Actual | 00Dev Decision RS Actual | 00Dev Decision FC Actual | Decision_I | Decision_dt_I | Decision_II | Decision_dt_II | Decision_III | Decision_dt_III | Decision_IV_ | Decision_dt_IV_ | Intial Study Path | 01FS_Issue_UnEx Actual | 01IS_Issue_UnEx Actual | 01CS_Issue_UnEx Actual | 01RS_Issue_UnEx Actual | 01FC_Issue_UnEx Actual | rQd_RS_Issue_UnEx One Actual | rQd_RS_Issue_UnEx Two Actual2 | rQd_RS_Issue_UnEx Three Actual | rQd_RS_Issue_UnEx Four | FS Documents Complete2 | IS or CS Documents Complete3 | RS Documents Complete4 | FC Documents Complete | FS Deposit Receipt | IS or CS Deposit Receipt | RS Fee Receipt Date | FC Deposit Receipt Date | rQd_RS_Issue_Fee Received One Actual | rQd_RS_Issue_Fee Received Two Actual | rQd_RS_Issue_Fee Received Three Actual | rQd_RS_Issue_Fee Received Four Actual2 | FS_Dev_Req_Comp | IS_Dev_Req_Comp | CS_Dev_Req_Comp | RS_Dev_Req_Comp | FC_Dev_Req_Comp | rQd_RS_Devel_Req_One_Complete | rQd_RS_Devel_Req_Two_Complete | rQd_RS_Devel_Req_Three_Complete | rQd_RS_Devel_Req_Four_Complete2 | 4FS Executed Actual | 4IS Executed Actual | 4CS Executed Actual | 4ReStudy Executed Actual | 4Facility Executed Actual | rQd_RS_ One_Executed Actual | rQd_RS_ Two_Executed Actual | rQd_RS_ Three_Executed Actual | rQd_RS_ Four_Executed Actual2 | Charge Numbers Ordered | 30 PERCENT REPORT | 100 PERCENT REPORT | 51 FS Report Issue Due | 51 IS Report Issue Due | 51 CS Report Issue Due | 51 RS Report Issue Due | 51 FC Report Issue Due | Addendum Issued Date | Addendum or Rev Final Report | 51 FS Report Issue Actual | 51 IS Report Issue Actual | 51 CS Report Issue Actual | 51 RS Report Issue Actual | 51 FC Report Issue Actual | ReQued_RS_ One_Report Complete Actual22 | ReQued_RS_ Two_Report Complete Actual2 | ReQued_RS_ Three_Report Complete Actual222 | ReQued_RS_ Four_Report Complete Actual3 | 5FS Report Issue | 5IS Report Issue | 5CS Report Issue | 5RS Report Issue | 5FC Report Issue | ReQued_RS_ One_Report Issue | ReQued_RS_ Two_Report Issue | ReQued_RS_ Three_Report Issue | ReQued_RS_ Four_Report Issue2 | 9FS Results Meeting Scheduled | 9IS Results Meeting Scheduled | 9CS Results Meeting Scheduled | 9RS Results Meeting Scheduled | 9FC Results Meeting Scheduled | ReQued_RS_ One_Results Meeting Scheduled | ReQued_RS_ Two_Results Meeting Scheduled | ReQued_RS_ Three_Results Meeting Scheduled | ReQued_RS_ Four_Results Meeting Scheduled2 | 9FS Results Meeting Actual | 9IS Results Meeting Actual | 9CS Results Meeting Actual | 9RS Results Meeting Actual | 9FC Results Meeting Actual | ReQued_RS_ One_Results Meeting Actual | ReQued_RS_ Two_Results Meeting Actual2 | ReQued_RS_ Three_Results Meeting Actual3 | FS_15BD_Sent - Results Notes | IS_15BD_Sent - Results Notes | CS_15BD_Sent - Results Notes | RS_15BD_Sent - Results Notes | FC_15BD_Sent - Results Notes | rQd_RS_One_15BD_Sent - Results Notes | rQd_RS_Two_15BD_Sent - Results Notes2 | rQd_RS_Three_ 15BD_Sent - Results Notes | Addendum Results Meeting | Addendum 15 BD Sent | Request IA | Rev Written Notice to Proceed | Executable IA_Date | Updated Executable IA_Date 1-REV | Executable IA_Returned Partial | Executable IA_Returned Partial_REV | i_3_9_Cluster Updated Executable IA_Date | i_3_9_Cluster Updated Executable IA_Issued Date | Est. Cost FAC Study Date Requested | Est. Cost FAC Study Date Due | Est. FAC Study Cost | SIS COST | SIS COST DATE | REVISED SIS COST | REVISED SIS COST DATE2 | Withdrawn Date | Fully Executed IA_Agreement | Fully Executed IA -- Issued Date | REV-1 Fully Executed IA_Agreement | REV-1 Fully Executed IA -- Issued Date | REV- 2 Fully Executed IA_Agreement | REV - 2 Fully Executed IA -- Issued Date | REV - 3 Fully Executed IA_Agreement | REV - 3 Fully Executed IA -- Issued Date | REV - 4 Fully Executed IA_Agreement2 | REV - 4 Fully Executed IA -- Issued Date3 | i_3_9_Cluster Updated Fully Executed IA_Agreement | i_3_9_Cluster Updated Fully Executed IA -- Issued Date | Post ReQued Fully Executed IA4 | Post ReQued Fully Executed IA Date | ReQued ReStudy One Start | ReQued ReStudy One Stop | ReQued ReStudy Two Start | ReQued ReStudy Two Stop | ReQued ReStudy Two Stop2 | ReQued ReStudy Three Start | ReQued ReStudy Three Stop | Estimated ISD | Amendment No.1 Date | Assignment No.1 Date | FP Apt Date | SAP Billing Notification | RevSAP Notification # Due to Addendum | Trans Plan completed review | Yes PP 5-1 SubD | No PP 5-1 SubD | Refunded Developer the Per kW portion of app fee | Developer billed for TOTAL Cost of the Study | Developer been billed for ISO work | Transmission | Distribution | Notes | Project Title | QP Test | PRJ Test | TEST4 | TEST43 | TEST44 | TEST42 | TEST422 | TEST5 | Addendum Results Meeting2 | Addendum 15 BD Sent3 | Rev Written Notice to Proceed2 | Addendum Issued Date | Addendum or Rev Final Report
1 |  | Lanie Patterson | Brent Brooks | 2018-08-06 | [31 empty] | 1 - FAIR |  | 817D3 |  |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2019-08-26 | Paige Kutschbach | Madison Energy Holdings | HEP Barefoot SPV, LLC | Eskelund Drive, Fairfield | 2000100473 | 30014974619 | Solar | 4320 | 4.32 | 5348 |  |  | 44.599 | -68.6013 | Eskelund Drive |  |  | Fairfield | 12.1 | FAIRFIELD | 817D3 | 817T1 |  | FLOC-MISSING-01142021 | Non-FERC | TRIGGERING | TRIGGERING (325,000) | 136762.09 | Yes |  |  | Ray Boucher | Terry Vogel |  | 2019-05-03 | 2018-08-13 | 2018-08-20 |  |  | 2018-08-20 |  | 2018-09-04 |  | 2018-08-20 | 2018-08-20 | 2018-09-03 |  |  | 2018-08-20 |  |  | CS | 2018-08-20 | [6 empty] | CS |  |  | 2018-08-20 | [29 empty] | 2018-08-20 | [14 empty] | 2021-06-08 | Addendum |  |  | 2018-10-04 | [8 empty] | 2018-10-04 | [17 empty] | 2018-10-10 | [13 empty] | 2021-06-16 |  | 2018-10-15 | [10 empty] | 150688 |  |  |  |  | 2019-06-07 | 2019-06-07 | 2021-07-08 | 2021-07-08 | [17 empty] | Q1 2021 |  |  | 2018-10-30 | 10300518257 |  | 2018-10-12 | 2018-10-12 |  | Yes - 7/12/2019 | 2019-01-18 | Helen |  |  |  |  | TRUE | TRUE | 1 | 2019-06-07 | 2019-06-07 | 2019 | 2019 | 2019 | 44363 |  |  | 2021-06-08 | Addendum
2 |  | Eben Snow | Brent Brooks | 2018-08-29 | [31 empty] | 1 - OXFO |  | 437D1 |  |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2019-08-26 | Adam Carte | CRSEF Acadia Aggregator, LLC | BD SOLAR OXFORD LLC (D1) | Main St, Lot 3 &3, Oxford | 2000057180 | 30010803721 | Solar | 4600 | 4.6 | 9710 |  |  | 44.1467 | -70.4802 | Oxford Business Park |  |  | Oxford | 514 | OXFORD | 437D1 | 437T1 |  | 9310-L0178-4420-0064-ED00072 | Non-FERC | TRIGGERING | TRIGGERING (375,000) | 100795 | Yes |  |  | Brent Brooks | Terry Vogel |  | 2019-05-09 | 2018-09-06 | 2018-09-13 |  |  | 2018-09-10 |  | 2018-09-24 |  | 2018-09-10 | 2018-09-10 | 2018-09-24 |  |  | 2018-09-10 |  |  | CS | 2018-09-10 | [6 empty] | CS |  |  | 2018-09-10 | [20 empty] | 2018-10-09 | [8 empty] | 2018-10-11 | [6 empty] | Yes | [7 empty] | 2021-04-23 | Addendum |  |  | 2018-12-17 | [8 empty] | 2018-12-17 | [17 empty] | 2018-12-20 | [13 empty] | 2021-04-30 |  | 2018-12-21 | [10 empty] | 292310 |  |  |  |  | 2019-05-30 | 2019-05-30 | 2021-08-17 | 2021-08-17 |  | 2022-01-22 | [15 empty] | Q4 2020 |  |  | 2018-01-09 | 10300538670 |  | Yes | Yes |  | Yes - 6/26/2019 | 2020-01-28 | Helen |  |  |  |  | TRUE | TRUE | 2 | 2019-05-30 | 2019-05-30 | 2019 | 2019 | 2019 | 44316 |  |  | 2021-04-23 | Addendum
3 |  | Eben Snow | Brent Brooks | 2018-08-29 | [31 empty] | 2 - OXFO |  | 437D2 | 2 |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2019-08-26 | Adam Carte | CRSEF Acadia Aggregator, LLC | BD SOLAR OXFORD LLC (D2) | Main St, Lot 3 &3, Oxford | 2000057180 | 30012970429 | Solar | 4600 | 4.6 | 3738 |  |  | 44.1467 | -70.4802 | Oxford Business Park |  |  | Oxford | 515 | OXFORD | 437D2 | 437T1 |  | 9310-L0178-4420-0064-ED00072 | Non-FERC | COST SHARE | COST SHARE (375,000) | 100795 | Yes |  |  | Brent Brooks | Terry Vogel |  | 2019-05-09 | 2018-09-06 | 2018-09-13 |  |  | 2018-09-10 |  | 2018-09-24 |  | 2018-09-10 | 2018-09-10 | 2018-09-24 |  |  | 2018-09-10 |  |  | CS | 2018-09-10 | [6 empty] | CS |  |  | 2018-09-10 | [29 empty] | 2018-10-11 | [6 empty] | Yes | [7 empty] | 2021-04-23 | Addendum |  |  | 2018-12-17 | [8 empty] | 2018-12-17 | [17 empty] | 2018-12-20 | [13 empty] | 2021-04-30 |  | 2018-12-21 | [10 empty] | 292310 |  |  |  |  | 2019-05-30 | 2019-05-30 | 2021-08-17 | 2021-08-17 |  | 2022-01-23 | [15 empty] | Q4 2020 |  |  | 2018-01-09 | 10300538670 |  | Yes | Yes |  | Yes - 6/26/2019 | 2020-01-28 | Helen |  |  |  |  | TRUE | TRUE | 3 | 2019-05-30 | 2019-05-30 | 2019 | 2019 | 2019 | 44316 |  |  | 2021-04-23 | Addendum
4 |  | Lanie Patterson | Brent Brooks | 2018-10-15 | [31 empty] | 1 - BLRD |  | 207D2 |  |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2019-08-26 | Adam Carte | CRSEF Acadia Aggregator, LLC | BD SOLAR AUGUSTA LLC | 153 Church Hill Rd | 2000065996 | 30010930854 | Solar | 7200 | 7.2 | 9710 |  |  | 44.3278 | -69.7285 | Church Hill Road |  |  | Augusta | 2 | BLAIR ROAD | 207D2 | 207T1 |  | 9310-L0020-0240-0062-ED00239 | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Yes |  |  | Ray Boucher | Terry Vogel |  | 2019-05-09 | 2018-10-22 | 2018-10-29 |  |  | 2018-10-23 |  | 2018-11-06 |  | 2018-10-23 | 2018-10-23 | 2018-11-06 |  |  | 2018-10-23 |  |  | CS | 2018-10-23 | [6 empty] | CS |  |  | 2018-10-23 | [29 empty] | 2018-10-24 | [6 empty] | Yes | [7 empty] | 2021-04-23 | Addendum |  |  | 2019-01-04 | [8 empty] | 2019-01-04 | [17 empty] | 2019-01-11 | [13 empty] | 2021-04-30 |  | 2019-01-11 | [10 empty] | 43000 |  |  |  |  | 2019-05-30 | 2019-05-30 | [19 empty] | Q4 2020 |  |  | 2019-01-29 | 10300670352 |  | Yes | 2019-01-31 |  | Yes - 6/26/2019 | 2020-01-28 | Helen |  |  |  |  | TRUE | TRUE | 4 | 2019-05-30 | 2019-05-30 | 2019 | 2019 | 2019 | 44316 |  |  | 2021-04-23 | Addendum
5 |  | Lanie Patterson | Brent Brooks | 2018-10-29 | [31 empty] | 1 - SHAW |  | 852D1 |  |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2019-05-01 | Adam Carte | CRSEF Acadia Aggregator, LLC | BD SOLAR FAIRFIELD LLC | 2 Dirigo Dr, Fairfield | 2000066261 | 30010934682 | Solar | 4990 | 4.99 | 6713 |  |  | 44.6315 | -69.5942 | Dirigo Drive |  |  | Fairfield | 41 | SHAWMUT | 852D1 | 852T3 |  | FLOC-MISSING-01142021 | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Yes |  |  | Marshall Ripley | Terry Vogel |  | 2019-05-09 | 2018-11-05 | 2018-11-13 |  |  | 2018-11-14 |  | 2018-11-30 |  | 2018-11-14 | 2018-11-14 | 2018-11-28 |  |  | 2018-11-14 |  |  | CS | 2018-11-14 | [6 empty] | CS |  |  | 2018-11-14 | [11 empty] | 2018-12-04 | [17 empty] | 2018-12-11 | [6 empty] | Yes | [7 empty] | 2021-04-23 | Addendum |  |  | 2019-02-13 | [8 empty] | 2019-02-13 | [17 empty] | 2019-02-20 | [13 empty] | 2021-04-30 |  | 2019-02-20 | [10 empty] | 46000 |  |  |  |  | 2019-05-30 | 2019-05-30 | [19 empty] | Q4 2020 |  |  | 2019-03-07 | 10300551861 |  | 2019-03-08 | 2019-03-08 |  | Yes - 6/26/2019 | 2020-01-28 | Helen |  |  |  |  | TRUE | TRUE | 5 | 2019-05-30 | 2019-05-30 | 2019 | 2019 | 2019 | 44316 |  |  | 2021-04-23 | Addendum
6 |  | Lanie Patterson | Brent Brooks | 2018-11-19 | [31 empty] | 1 - WINS |  | 870D2 |  |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2020-07-27 | Adam Carte | CRSEF Acadia Aggregator, LLC | BD SOLAR 2 LLC | Clinton Ave Winslow | 2000072254 | 30011024251 | Solar | 6999 | 6.999 | 9830 |  |  | 44.5608 | -69.5921 | Roderick Road |  |  | Winslow | 18.3 | WINSLOW | 870D2 | 870T4 |  | FLOC-MISSING-01142021 | FERC | NOT IMPACTED | NOT IMPACTED | NONE | Yes |  |  | K&L Engineering | Terry Vogel |  | 2019-05-09 | 2018-11-28 | 2018-12-05 |  |  | 2019-01-08 |  | 2019-01-23 |  | 2019-01-08 | 2019-01-08 | 2019-01-22 |  |  | 2019-01-08 |  |  | CS | 2019-01-08 | [6 empty] | CS |  |  | 2019-01-08 | [29 empty] | 2019-02-08 | [6 empty] | Yes | 2019-03-11 | 2019-04-08 | [9 empty] | 2019-04-11 | [8 empty] | 2019-04-11 | [17 empty] | 2019-04-11 | [15 empty] | 2019-05-02 | [15 empty] | 2019-06-07 | 2019-06-07 | 2021-08-17 | 2021-08-17 | [17 empty] | Q4 2020 |  |  | 2019-06-05 | 10300569616 |  | TBD | TBD |  | Yes - 6/26/2019 |  | Helen |  |  |  |  | TRUE | TRUE | 6 | 2019-06-07 | 2019-06-07 | 2019 | 2019 | 2019
7 |  | Lanie Patterson | Brent Brooks | 2019-01-24 | [31 empty] | 1 - SOWA |  | 855D2 |  |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2019-12-13 | Paige Kutschbach | Madison Energy Holdings | HEP BROADHEAD SPV LLC | 41 Webb Rd, Waterville | 2000100437 | 30014974627 | Solar | 4920 | 4.92 | 6105 |  |  | 44.5203 | -69.6688 | Webb Road |  |  | Waterville | 1H | SOUTH WATERVILLE | 855D2 | 855T1 |  | FLOC-MISSING-01142021 | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Under Review 1/31/2020 |  |  | K&L Engineering | Terry/Bruce |  | 2019-05-03 | 2019-01-31 | 2019-02-07 | 2019-01-30 | 2019-02-12 | 2019-02-22 |  | 2019-03-08 |  | 2019-02-22 | 2019-02-22 | 2019-03-08 |  |  | 2019-02-22 |  |  | CS | 2019-02-22 | [6 empty] | CS |  |  | 2019-02-22 | [29 empty] | 2019-03-15 | [6 empty] | Yes | 2019-04-10 | 2019-05-08 | [5 empty] | 2021-06-30 |  |  |  | 2019-05-16 | [8 empty] | 2019-05-16 | [17 empty] | 2019-05-21 | [15 empty] | 2019-05-21 | [15 empty] | 2019-06-07 | 2019-06-07 | 2021-07-21 | 2021-07-21 | [17 empty] | Q1 2021 |  |  | 2019-06-24 | 10300679514 |  | Yes | Yes |  | Yes - 7/12/2019 |  | Helen |  |  |  |  | TRUE | TRUE | 7 | 2019-06-07 | 2019-06-07 | 2019 | 2019 | 2019 |  |  |  | 2021-06-30
8 |  | Govinda Neupane |  | 2019-02-04 | [31 empty] | 1 - RUIP |  | 466D1 |  |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2020-04-10 | Jeff Perry | Agilitas Energy, Inc. | RUMFORD ESS LLC | 21 Industrial Park Rd Rumford | 2000104996 | 30011502850 | Battery | 4999 | 4.999 | 4999 | 4999 |  | 44.5322 | -70.5195 | 21 Industrial Park |  |  | Rumford | 4.5 | RUMFORD INDUSTRIAL PARK | 466D1 | 466T1 |  | 9310-L0188-5020-0073-ED00007 | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Yes |  |  | K&L Engineering | Terry/Bruce |  | 2019-05-03 | 2019-02-11 | 2019-02-19 | 2019-02-11 | 2019-02-25 | 2019-03-04 |  | 2019-03-18 |  | 2019-03-04 | 2019-03-04 | 2019-03-18 |  |  | 2019-03-04 |  |  | CS | 2019-03-04 | [6 empty] | CS |  |  | 2019-03-04 | [29 empty] | 2019-04-29 | [6 empty] | Yes | [7 empty] | 2021-06-04 | Addendum |  |  | 2019-07-02 | [8 empty] | 2019-07-02 | [17 empty] | 2019-07-09 | [7 empty] | 2019-07-09 | [5 empty] | 2021-06-08 |  | 2019-07-09 |  | 2019-07-19 | [8 empty] | 65618 |  |  |  |  | 2019-08-05 | 2019-08-05 | [19 empty] | Q1 2021 |  |  | 2019-08-19 | 10300593502 |  | TBD | TBD |  | Helen |  | Helen |  |  |  |  | TRUE | TRUE | 8 | 2019-08-05 | 2019-08-05 | 2019 | 2019 | 2019 | 44355 |  |  | 2021-06-04 | Addendum
9 |  | Rigel Paradise | Rick Duperre | 2019-03-05 | [31 empty] | 1 - HIST |  | 626D1 |  |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2019-12-30 | Abby Broedlin | Nautilus Solar | Sanford Solar LLC | Rushton St Sanford | 2000087468 | 30011240709 | Solar | 4950 | 4.95 | 6542 |  |  | 45.3156 | -69.2036 | 81 Rushton Street |  |  | Sanford | 5 4 | HIGH STREET | 626D1 | 626T1 |  | 9310-L0252-5170-0305-ED00012 | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Yes |  |  | K&L Engineering | Terry/Bruce |  | 2019-05-03 | 2019-03-12 | 2019-03-19 | 2019-03-11 | 2019-03-26 | 2019-06-04 |  | 2019-06-18 |  | 2019-06-04 | 2019-06-04 | 2019-06-18 |  |  | 2019-06-18 |  |  | CS | 2019-07-11 | [6 empty] | CS |  |  | 2019-07-11 | [11 empty] | 2019-07-11 | [17 empty] | 2019-07-11 | [6 empty] | Yes | 2019-08-06 | [6 empty] | 2021-06-08 | Addendum |  |  | 2019-09-09 | [8 empty] | 2019-09-09 | [17 empty] | 2019-09-16 | [15 empty] | 2019-09-21 |  | 2019-09-26 | [8 empty] | 50810 |  |  |  |  | 2020-02-19 | 2020-02-19 | 2021-09-28 | 2021-09-30 | [17 empty] | Q4 2020 |  |  | 2019-11-27 | 10300614911 |  | Yes | Yes |  | Helen |  | Helen |  |  |  |  | TRUE | TRUE | 9 | 2020-02-19 | 2020-02-19 | 2020 | 2020 | 2020 |  |  |  | 2021-06-08 | Addendum
10 |  | Lanie Patterson | Brent Brooks | 2019-03-11 | [31 empty] | 2 - SHAW |  | 852D1 | 5 |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED |  | Zach Good | Aligned Solar Partners | Freeport Solar LLC | 630 Skowhegan Rd Fairfield | 2000135859 | 30011969950 | Solar | 650 | 0.65 | 879 |  |  | 44.7775 | -69.6325 | 122 Skowhegan Road |  |  | Fairfield | 121 | SHAWMUT | 852D1 | 852T3 |  | FLOC-MISSING-01142021 | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Under Review 1/31/2020 |  |  | K&L Engineering | Bruce |  |  | 2019-03-18 | 2019-03-25 |  |  | 2019-03-25 |  | 2019-04-08 |  | 2019-03-25 | 2019-03-25 | 2019-04-08 |  |  | 2019-04-02 |  |  | CS | 2019-04-02 | [6 empty] | CS |  |  | 2019-04-02 | [11 empty] | 2019-04-16 | [17 empty] | 2019-05-02 | [6 empty] | Yes | [11 empty] | 2019-07-01 | [8 empty] | 2019-07-01 | [17 empty] | 2019-07-09 | [7 empty] | 2019-07-09 | [7 empty] | 2019-07-15 |  | 2019-07-19 | [13 empty] | 2019-12-05 | 2019-12-05 | 2021-05-26 | 2021-05-26 | [17 empty] | Q4 2019 |  |  | 2019-09-05 | 10300593675 |  | Yes | Yes |  | Helen | 2020-01-28 | Helen |  |  |  |  | TRUE | TRUE | 10 | 2019-12-05 | 2019-12-05 | 2019 | 2019 | 2019
11 |  | Rigel Paradise | Rick Duperre | 2019-04-02 | [31 empty] | 1 - SAIP | 1 - SAIP | 656D3 |  |  | EXECUTED | EXECUTED | 2020-07-14 | Jeff Perry | NEW ENGLAND BATTERY STORAGE | SANFORD ESS LLC | 60 Cyro Rd Sanford | 2000104977 | 30011502801 | Battery | 4999 | 4.999 | 4999 | 4999 |  | 44.1511 | -70.6329 | 60 Cyro Dr |  |  | Sanford | 2 | SANFORD INDUSTRIAL PARK | 656D3 | 656T1 |  | 9310-L0318-5170-0076-ED00035 | Non-FERC | TRIGGERING | TRIGGERING ( $250,000) | 113748 | Yes |  |  | K&L Engineering | Terry/Bruce |  | 2019-05-03 | 2019-04-09 | 2019-04-17 | 2019-04-03 | 2019-04-15 | 2019-04-24 |  | 2019-05-08 |  | 2019-04-24 | 2019-04-24 | 2019-05-08 |  |  | 2019-05-08 |  |  | CS | 2019-06-14 | [6 empty] | CS |  |  | 2019-06-14 | [11 empty] | 2019-06-14 | [17 empty] | 2019-06-20 | [6 empty] | Yes | [7 empty] | 2021-05-24 | Addendum |  |  | 2019-08-23 | [8 empty] | 2020-04-27 | [17 empty] | 2020-05-01 | [13 empty] | 2021-06-17 |  | 2020-05-01 |  | 2020-05-05 | [8 empty] | 337618 |  |  |  |  | 2020-05-11 | 2020-05-11 | 2021-07-07 | 2021-07-07 | [17 empty] | Q4 2020 | 2021-07-07 |  | TBD | 10300668347 | [11 empty] | TRUE | TRUE | 11 | 2020-05-11 | 2020-05-11 | 2020 | 2020 | 2020 | 44364 |  |  | 2021-05-24 | Addendum
12 |  | Govinda Neupane |  | 2019-04-25 | [31 empty] | 1 - DOVE |  | 815D1 |  |  | WITHDRAWN | WITHDRAWN |  | Jeff Perry | NEW ENGLAND BATTERY STORAGE | DOVER FOXCROFT ESS LLC | Pinecrest Park Lot 8 Dover Foxcroft | 2000101658 | 30011454102 | Battery | [7 empty] | Pine Crest Park Lot 8 |  |  | Dover |  | DOVER | 815D1 |  |  | 86-Withdrawn-86d | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2019-05-02 | 2019-05-09 |  |  |  |  | 1900-01-12 | [57 empty] | Yes | [69 empty] | 2019-12-12 | [37 empty] | TRUE | TRUE | 12 | 0 | 0 | 1900 | #VALUE! | #VALUE!
13 |  | Lanie Patterson | Brent Brooks | 2019-05-02 | [31 empty] | 1 - PDRD |  | 262D1 |  |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Cary Drake | Agilitas Energy, Inc. | AE‑ESS Puddledock, LLC | 10 sylvester dr manchester | 2000248964 | 30013554420 | Battery | [5 empty] | 43.9618 | -69.7071 | 38 Puddle Dock Road |  |  | Manchester | P-2 | PUDDLEDOCK ROAD | 262D1 | 34.5 kV Bus |  | 9310-L0101-3540-0075-ED00012 | Non-FERC | WITHDRAWN | WITHDRAWN | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-05-09 | 2019-05-09 | 2019-05-16 | 2019-05-09 | 2019-05-23 | 2019-06-03 |  | 2019-06-17 |  | 2019-06-03 | 2019-06-03 | 2019-06-17 |  |  | 2019-06-17 |  |  | CS | 2019-07-08 | [6 empty] | CS |  |  | 2019-07-08 | [11 empty] | 2019-07-08 | [17 empty] | 2019-07-09 | [6 empty] | Yes | 2019-08-01 | [6 empty] | 2021-06-21 | Addendum |  |  | 2019-09-11 | [8 empty] | 2020-09-11 | [17 empty] | 2019-09-19 | [15 empty] | 2019-10-02 | 2021-07-29 | 2019-10-02 | [12 empty] | 2023-07-07 | 2020-05-15 | 2020-05-15 | [21 empty] | 2021-11-11 | TBD | 10300671150 | [11 empty] | TRUE | TRUE | 13 | 2020-05-15 | 2020-05-15 | 2020 | 2020 | 2020 |  |  | 44406 | 2021-06-21 | Addendum
14 |  | Govinda Neupane |  | 2019-05-03 | [31 empty] | 1 - HART |  | 824D2 |  |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2019-12-13 | Paige Kutschbach | Madison Energy Holdings | HEP USA SPV 6 HARTLAND LLC | Hartland | 2000096395 | 30012637648 | Solar | 4000 | 4 | 5246 |  |  | 44.8494 | -69.4561 | 280 Fuller Corner Rd |  |  | Hartland | 34 | HARTLAND | 824D2 | 824T1 |  | FLOC-MISSING-01142021 | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Under Review 1/31/2020 |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-05-10 | 2019-05-10 | 2019-05-17 | 2019-05-10 | 2019-05-24 | 2019-05-29 |  | 2019-06-12 |  | 2019-05-29 | 2019-05-29 | 2019-06-12 |  |  | 2019-06-12 |  |  | CS | 2019-06-14 | [6 empty] | CS |  |  | 2019-06-14 | [11 empty] | 2019-06-14 | [17 empty] | 2019-06-17 | [6 empty] | Yes | 2019-07-18 | 2019-08-01 | [9 empty] | 2019-08-20 | [8 empty] | 2019-08-20 | [17 empty] | 2019-08-27 | [15 empty] | 2019-08-27 |  | 2019-08-28 | [13 empty] | 2019-08-29 | 2019-08-29 | 2021-08-25 | 2021-09-14 | [17 empty] | Q1 2021 |  |  | 2019-10-11 | 10300605894 |  | Yes | Yes |  | Helen |  | Helen |  |  |  |  | TRUE | TRUE | 14 | 2019-08-29 | 2019-08-29 | 2019 | 2019 | 2019
15 |  | Marshall Ripley | Rick Duperre | 2019-05-15 | 2023-02-15 | L2_Bump |  | 2023-03-07 | L2_Bump | [26 empty] | 1 - MURD |  | 636D2 |  |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Jeff Perry | NEW ENGLAND BATTERY STORAGE | SOUTH PORTLAND ESS LLC | 2290 West Broadway South Portland | 2000104997 | 30011502868 | Battery | [5 empty] | 43.6217 | -70.3289 | 2273 West Broadway |  |  | South Portland | 2 | MUSSEY ROAD | 636D2 | 636T1 | 34.5 | 9310-L0273-5430-0467-ED00005 | Non-FERC | WITHDRAWN | WITHDRAWN | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-05-22 | 2019-05-22 | 2019-05-30 | 2019-05-22 | 2019-06-05 | 2019-06-17 |  | 2019-07-01 |  | 2019-06-17 | 2019-06-17 | 2019-07-01 |  |  | 2019-06-26 |  |  | CS | 2019-06-26 | [6 empty] | CS |  |  | 2019-06-26 |  |  | 2023-02-16 | [8 empty] | 2019-06-26 |  |  | 2023-02-17 | [8 empty] | 2023-03-06 | [5 empty] | 2019-07-08 |  |  | 2023-03-07 |  |  |  | Yes | [11 empty] | 2019-09-09 |  |  | 2023-04-19 | [5 empty] | 2019-09-09 |  |  | 2023-04-19 | [14 empty] | 2019-09-30 | [15 empty] | 2019-10-17 | 2021-08-04 | 2019-10-24 | 2023-01-31 |  | 2023-02-03 | [5 empty] | 243836 | 2023-01-24 | 543004 | 2023-04-19 | 2024-04-25 | 2019-11-06 | 2019-11-06 | 2021-08-04 | 2021-08-04 | 2023-02-03 | 2023-02-07 | 2023-05-16 | 2023-05-16 | [16 empty] | 2020-01-14 | 10300622340 |  | Yes | Yes |  | Helen |  | Helen |  |  |  |  | TRUE | TRUE | 15 | 2019-11-06 | 2019-11-06 | 2019 | 2019 | 2019 |  |  | 44412
16 |  | Govinda Neupane |  | 2019-05-15 | [31 empty] | 2 - HART |  | 824D1 | 14 |  | WITHDRAWN | WITHDRAWN |  | Jack Kenworthy | Walden Renewables | WALDEN SOLAR MAINE I LLC | Lower Main St Hartland | 2000096992 | 30011382410 | Solar | [7 empty] | 154 Pleasant Street |  |  | Hartland |  | HARTLAND | 824D1 |  |  | 86-Withdrawn-86d | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2019-05-22 | 2019-05-30 |  |  |  |  | 1900-01-12 | [57 empty] | Yes | [69 empty] | 2019-11-19 | [37 empty] | TRUE | TRUE | 16 | 0 | 0 | 1900 | #VALUE! | #VALUE!
17 |  | Rigel Paradise | Rick Duperre | 2019-05-16 | [31 empty] | 1 - PRAT |  | 661D2 |  |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2020-04-28 | Abby Broedlin | Nautilus Solar | WALDEN SOLAR MAINE II LLC | Crediford Rd Wells | 2000096993 | 30011382428 | Solar | 4800 | 4.8 | 6240 |  |  | 45.3153 | -69.2051 | (Gravel Pitt) Crediford Road |  |  | Wells | 21 | PRATT & WHITNEY | 661D2 | 661T1 |  | 9310-L0330-6273-0038-ED00056 | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-05-23 | 2019-05-23 | 2019-05-31 | 2019-05-23 | 2019-06-05 | 2019-06-13 |  | 2019-06-27 |  | 2019-06-13 | 2019-06-13 | 2019-06-27 |  |  | 2019-06-27 |  |  | CS | 2019-07-12 | [6 empty] | CS |  |  | 2019-07-12 | [11 empty] | 2019-07-12 | [17 empty] | 2019-07-12 | [6 empty] | Yes | 2019-08-28 | 2019-09-13 | [5 empty] | 2021-06-30 | Addendum |  |  | 2019-09-16 | [8 empty] | 2019-09-16 | [17 empty] | 2019-09-20 | [15 empty] | 2019-12-17 | 2021-08-09 | 2019-12-17 | [13 empty] | 2020-02-13 | 2020-02-13 | 2021-09-27 | 2021-09-30 | [17 empty] | Q4 2020 |  |  | 2020-01-22 | 10300638557 |  | TBD |  |  | Helen |  | Helen |  |  |  |  | TRUE | TRUE | 17 | 2020-02-13 | 2020-02-13 | 2020 | 2020 | 2020 |  |  | 44417 | 2021-06-30 | Addendum
18 |  | Rigel Paradise | Rick Duperre | 2019-05-21 | [31 empty] | 1 - SOSA |  | 667D1 |  |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2020-04-28 | Abby Broedlin | Nautilus Solar | CGA SOLAR LLC | 229 New Dam Rd (Solar) Sanford | 2000153803 | 30012242373 | Solar | 4950 | 4.95 | 6542 |  |  | 45.3148 | -69.2053 | 229 New Dam Road |  |  | Sanford | 11 | SOUTH SANFORD | 667D1 | 667T2 |  | 9310-L0333-5170-0471-ED00022 | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-05-29 | 2019-05-29 | 2019-06-05 | 2019-05-29 | 2019-06-13 | 2019-06-19 |  | 2019-07-03 |  | 2019-06-19 | 2019-06-19 | 2019-07-03 |  |  | 2019-07-03 |  |  | CS | 2019-07-12 | [6 empty] | CS |  |  | 2019-07-12 | [11 empty] | 2019-07-12 | [17 empty] | 2019-07-12 | [6 empty] | Yes | 2019-08-28 | 2019-09-13 | [5 empty] | 2021-05-18 | Addendum |  |  | 2019-09-16 | [8 empty] | 2019-09-16 | [17 empty] | 2019-09-23 | [13 empty] | 2021-05-26 |  | 2020-01-15 |  | 2020-01-15 | [8 empty] | 385310 |  |  |  |  | 2020-02-18 | 2020-02-18 | 2021-04-30 | 2021-04-30 | [17 empty] | Q4 2020 |  |  | 2020-03-05 | 10300646142 | [11 empty] | TRUE | TRUE | 18 | 2020-02-18 | 2020-02-18 | 2020 | 2020 | 2020 | 44342 |  |  | 2021-05-18 | Addendum
19 |  | Rigel Paradise | Rick Duperre | 2019-05-23 | [31 empty] | 2 - PRAT |  | 661D2 | 17 |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2020-07-30 | Jack Kenworthy | Walden Renewables | LITTLEFIELD SOLAR LLC | Littlefield Rd Wells | 2000153804 | 30012242381 | Solar | 4950 | 4.95 | 6542 |  |  | 43.4136 | -70.7054 | 9B Landfill |  |  | Wells | 33H | PRATT & WHITNEY | 661D2 | 661T1 |  | 9310-L0330-6273-0028-ED00083 | Non-FERC | TRIGGERING | TRIGGERING (340,000) | 153726.75 | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-05-30 | 2019-05-31 | 2019-06-07 | 2019-05-30 | 2019-06-13 | 2019-12-20 |  | 2020-01-07 |  | 2019-12-20 | 2019-12-20 | 2020-01-06 |  |  | 2020-01-06 |  |  | CS | 2020-01-13 | [6 empty] | CS |  |  | 2020-01-13 | [11 empty] | 2020-01-27 | [17 empty] | 2020-01-27 | [6 empty] | Yes | [7 empty] | 2021-06-03 | Addendum |  |  | 2020-03-30 | [8 empty] | 2020-04-01 | [17 empty] | 2020-04-07 | [15 empty] | 2020-04-22 |  | 2020-04-21 | [8 empty] | 620468 |  |  |  |  | 2020-05-01 | 2020-05-01 | 2021-08-19 | 2021-08-19 | [17 empty] | Q4 2020 |  |  | TBD | 10300670287 | [11 empty] | TRUE | TRUE | 19 | 2020-05-01 | 2020-05-01 | 2020 | 2020 | 2020 |  |  |  | 2021-06-03 | Addendum
20 |  | Lanie Patterson | Brent Brooks | 2019-06-07 | [31 empty] | 1 - DETR |  | 812D1 |  |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2020-02-26 | Chad Allen | LongRoad Development Company LLC | Maine DG Solar Pittsfield, LLC | Curtis St Pittsfield | 2000239315 | 30013970949 | Solar | 4875 | 4.875 | 6408 |  |  | 44.7886 | -69.3689 | Curtis Street |  |  | Pittsfield | 4 | DETROIT | 812D1 | 812T2 |  | 9310-SS0812-014 | Non-FERC | TRIGGERING | TRIGGERING (250,000) | 123668 | Under Review 1/31/2020 |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-06-14 | 2019-06-14 | 2019-06-21 | 2019-06-14 | 2019-06-21 | 2019-07-10 |  | 2019-07-24 |  | 2019-07-10 | 2019-07-10 | 2019-07-24 |  |  | 2019-07-12 |  |  | CS | 2019-07-12 | [6 empty] | CS |  |  | 2019-07-12 | [11 empty] | 2019-07-12 | [17 empty] | 2019-07-16 | [6 empty] | Yes | 2019-09-05 | [6 empty] | 2021-06-11 | Addendum |  |  | 2019-09-17 | [8 empty] | 2019-09-17 | 2021-10-21 | [16 empty] | 2019-09-23 | [13 empty] | 2021-06-22 |  | 2019-09-26 | 2021-08-05 | 2019-10-01 | [8 empty] | 221865 |  |  |  |  | 2019-10-02 | 2019-10-02 | 2021-08-05 | 2021-08-05 | [17 empty] | Q4 2020 |  |  | 2019-11-05 | 10300614987 |  | Yes | Yes |  | Helen |  | Helen |  |  |  |  | TRUE | TRUE | 20 | 2019-10-02 | 2019-10-02 | 2019 | 2019 | 2019 | 44369 |  | 44413 | 2021-06-11 | Addendum
21 |  | Lanie Patterson | Brent Brooks | 2019-06-13 | [31 empty] | 1 - UNIT |  | 860D1 |  |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2019-12-13 | Paige Kutschbach | Madison Energy Holdings | HEP USA SPV 5 UNITY LLC | Albion Rd Unity | 2000096395 | 30012637655 | Solar | 4980 | 4.98 | 6450 |  |  | 44.5986 | -69.3542 | Albion Road |  |  | Unity | 46 | UNITY | 860D1 | 860T1 |  | 9310-SS0860-003-CIRCT | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Under Review 1/31/2020 |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-06-20 | 2019-06-20 | 2019-06-27 | 2019-06-20 | 2019-06-27 | 2019-07-10 |  | 2019-07-24 |  | 2019-07-10 | 2019-07-10 | 2019-07-24 |  |  | 2019-07-24 |  |  | CS | 2019-07-30 | [6 empty] | CS |  |  | 2019-07-30 | [11 empty] | 2019-07-30 | [17 empty] | 2019-08-05 | [6 empty] | Yes | 2019-09-17 | [10 empty] | 2019-10-07 | [8 empty] | 2019-10-08 | [17 empty] | 2019-10-15 | [7 empty] | 2019-10-15 | [7 empty] | 2019-11-04 |  | 2019-11-04 | [13 empty] | 2019-11-14 | 2019-11-14 | 2021-07-12 | 2021-07-12 | [17 empty] | Q4 2020 |  |  | 2019-12-05 | 10300627648 |  | Yes | Yes |  | Helen |  | Helen |  |  |  |  | TRUE | TRUE | 21 | 2019-11-14 | 2019-11-14 | 2019 | 2019 | 2019
22 |  | Govinda Neupane |  | 2019-06-14 | [31 empty] | 1 - NEWP |  | 837D1 |  |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2020-02-26 | Adam Carte | CRSEF Acadia Aggregator, LLC | BD SOLAR PALMYRA LLC | Us Rt 2 Palmyra | 2000104382 | 30011493993 | Solar | 4990 | 4.99 | 7073 |  |  | 44.8392 | -69.3061 | Main Street |  |  | Palmyra | 24 | NEWPORT | 837D1 | 837T1 |  | 9310-L0418-4497-0015-ED00025 | Non-FERC | TRIGGERING | TRIGGERING | 325000 | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-06-21 | 2019-06-21 | 2019-06-28 | 2019-06-21 | 2019-06-27 | 2019-07-12 |  | 2019-07-26 |  | 2019-07-12 | 2019-07-12 | 2019-07-26 |  |  | 2019-07-24 |  |  | CS | 2019-07-24 | [6 empty] | CS |  |  | 2019-07-24 | [11 empty] | 2019-07-24 | [17 empty] | 2019-07-24 | [6 empty] | Yes | 2019-09-11 | [6 empty] | 2021-05-18 | Addendum |  |  | 2019-09-25 | [8 empty] | 2019-09-25 | [17 empty] | 2019-10-01 | [13 empty] | 2021-06-03 |  | 2020-01-13 |  | 2020-01-13 | [8 empty] | 798897.85 |  |  |  |  | 2020-02-13 | 2020-02-13 | 2021-08-17 | 2021-08-17 | [17 empty] | Q2 2021 |  |  | 2019-11-20 | 10300619668 |  | Yes | Yes |  | Helen |  | Helen |  |  |  |  | TRUE | TRUE | 22 | 2020-02-13 | 2020-02-13 | 2020 | 2020 | 2020 | 44350 |  |  | 2021-05-18 | Addendum
23 |  | Eben Snow | Brent Brooks | 2019-06-17 | 2022-06-02 | L2_Bump | [29 empty] | 1 - HORD |  | 420D4 |  |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2020-02-26 | Andrew Martin | Renewable Properties | NextGrid Peppertree LLC | 0 Lewiston Junction Poland Solar | 2000104939 | 30012780661 | Solar | 4875 | 4.875 | 5992 |  |  | 44.496 | -70.3046 | Lewiston Junction Road |  |  | Poland | 2 | HOTEL ROAD | 420D4 | 420T1 |  | 9310-SS0420-015-CIRCT | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-06-25 | 2019-06-24 | 2019-07-01 | 2019-06-25 | 2019-07-01 | 2019-07-15 |  | 2019-07-29 |  | 2019-07-15 | 2019-07-15 | 2019-07-29 |  |  | 2019-07-29 |  |  | CS | 2019-08-13 | [6 empty] | CS |  |  | 2019-08-13 | [11 empty] | 2019-08-13 | [17 empty] | 2019-08-14 | [6 empty] | Yes | 2019-10-02 | [6 empty] | 2021-05-20 | Addendum |  |  | 2019-10-16 | [8 empty] | 2019-10-17 | [17 empty] | 2019-10-25 | [13 empty] | 2021-06-08 |  | 2019-11-15 | 2021-08-20 | 2019-11-18 | [8 empty] | 159618 |  |  |  |  | 2019-12-05 | 2019-12-05 | 2021-08-23 | 2021-08-23 | [17 empty] | Q3 2020 | 2021-07-15 |  | 2019-12-09 | 10300633585 | 10300809571 | Yes | Yes |  | Helen |  | Helen |  |  |  |  | TRUE | TRUE | 23 | 2019-12-05 | 2019-12-05 | 2019 | 2019 | 2019 | 44355 |  | 44428 | 2021-05-20 | Addendum
24 |  | Eben Snow | Brent Brooks | 2019-07-12 | [31 empty] | 1 - DEER |  | 412D4 |  |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2020-02-28 | Andrew Martin | Renewable Properties | NEXTGRID MANGROVE LLC | 265 Merill St (Lewiston) | 2000167672 | 30011566350 | Solar | 4900 | 4.9 | 5568 |  |  | 44.1564 | -70.1903 | 265 Merrill Road |  |  | Lewiston | 9 | DEER RIPS | 412D4 | 412T4 |  | 9310-SS0412 | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-07-19 | 2019-07-19 | 2019-07-26 | 2019-07-19 | 2019-07-25 | 2019-07-26 |  | 2019-08-09 |  | 2019-07-26 | 2019-07-26 | 2019-08-09 |  |  | 2019-08-09 |  |  | CS | 2019-08-13 | [6 empty] | CS |  |  | 2019-08-13 | [11 empty] | 2019-08-13 | [17 empty] | 2019-08-14 | [6 empty] | Yes | [11 empty] | 2019-10-16 | [8 empty] | 2019-10-16 | [17 empty] | 2019-10-25 | [15 empty] | 2019-11-18 |  | 2019-11-18 | [13 empty] | 2019-12-05 | 2019-12-05 | [19 empty] | Q3 2020 |  |  | 2019-12-12 | 10300633566 |  | Yes | Yes |  | Helen |  | Helen |  |  |  |  | TRUE | TRUE | 24 | 2019-12-05 | 2019-12-05 | 2019 | 2019 | 2019
25 |  | Govinda Neupane |  | 2019-07-18 | [31 empty] | 1 - SKNS |  | 853D1 |  |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2020-04-28 | Tim Richardson | MN8 Energy LLC | MADISON SOLAR ONE LLC | 214 E Madison R | 2000162075 | 30012374614 | Solar | 4999 | 4.999 | 7000 |  |  | 44.3321 | -69.856 | East Madison Road |  |  | Madison | 3 | SKOWHEGAN NORTH SIDE | 853D1 | 853T1 |  | FLOC-MISSING-01142021 | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-07-24 | 2019-07-25 | 2019-08-01 | 2019-07-24 | 2019-08-01 | 2019-08-05 |  | 2019-08-19 |  | 2019-08-05 | 2019-08-05 | 2019-08-19 |  |  | 2019-08-19 |  |  | CS | 2019-09-03 | [6 empty] | CS |  |  | 2019-09-03 | [11 empty] | 2019-10-01 | [17 empty] | 2019-10-01 | [6 empty] | Yes | [7 empty] | 2021-06-04 | Addendum |  |  | 2019-12-03 | [8 empty] | 2019-12-03 | [17 empty] | 2019-12-10 | [15 empty] | 2019-12-23 |  | 2019-12-23 | [8 empty] | 114522 |  |  |  |  | 2020-02-06 | 2020-02-06 | [19 empty] | Q4 2020 |  |  | TBD | 10300668584 |  |  |  |  | Helen |  | Helen |  |  |  |  | TRUE | TRUE | 25 | 2020-02-06 | 2020-02-06 | 2020 | 2020 | 2020 |  |  |  | 2021-06-04 | Addendum
26 |  | Govinda Neupane |  | 2019-07-31 | [31 empty] | 2 - SKNS |  | 853D1 | 25 |  | WITHDRAWN | WITHDRAWN |  | Greg Boyer | Dynamic Energy | DYNAMIC ENERGY SOLUTIONS LLC | E Madison Rd Madison | 2000110140 | 30011608616 | Solar/Battery | [7 empty] | East Madison Road |  |  | Madison |  | SKOWHEGAN NORTH SIDE | 853D1 |  |  | 86-Withdrawn-86d | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2019-08-07 | 2019-08-14 |  |  |  |  | 1900-01-12 | [127 empty] | 2020-08-14 | [37 empty] | TRUE | TRUE | 26 | 0 | 0 | 1900 | #VALUE! | #VALUE!
27 |  | Marshall Ripley | Rick Duperre | 2019-07-31 | [31 empty] | 1 - DUNS |  | 617D2 |  |  | WITHDRAWN | WITHDRAWN |  | Christian Bain | BORREGO SOLAR SYSTEMS INC | 510 PV PROJECT DEVELOPMENT LLC | 1016 Portland Rd, Saco | 2000113260 | 30011627699 | Solar | [7 empty] | 1016 Portland Road |  |  | Saco |  | DUNSTAN | 617D2 |  |  | 86-Withdrawn-86d | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2019-08-07 | 2019-08-14 |  |  |  |  | 1900-01-12 | [57 empty] | Yes | [69 empty] | 2019-09-29 | [37 empty] | TRUE | TRUE | 27 | 0 | 0 | 1900 | #VALUE! | #VALUE!
28 |  | Eben Snow | Brent Brooks | 2019-08-06 | 2022-06-02 | L2_Bump |  | 2022-12-15 | L2_Bump |  | 2023-02-03 | L2_Bump |  | 2023-03-20 | L2_Bump |  | 2025-09-18 | L2_With | [17 empty] | 2 - HORD |  | 420D4 | 23 | Yes | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Adam Carte | CRSEF Acadia Aggregator, LLC | BD SOLAR AUBURN LLC | 445 Lewiston Jct Rd Auburn | 2000113130 | 30011625644 | Solar | [5 empty] | 44.5167 | -70.2907 | 445 Lewiston Junction Road |  |  | Auburn | 501 | HOTEL ROAD | 420D4 | 420T1 | 34.5 | 9310-L0140-0230-0206-ED00050 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-08-13 | 2019-08-13 | 2019-08-20 | 2019-08-13 | 2019-08-19 | 2019-12-04 |  | 2019-12-18 |  | 2019-12-04 | 2019-12-04 | 2019-12-18 |  |  | 2019-12-05 |  |  | CS | 2019-12-05 | [6 empty] | CS |  |  | 2019-12-05 | 2022-06-13 |  | 2022-06-13 | 2022-12-20 | 2023-02-06 | [6 empty] | 2020-01-02 |  |  | 2022-07-05 | 2023-01-04 | 2023-02-10 | [8 empty] | 2023-02-22 |  |  |  | 2020-01-02 |  |  | 2022-06-28 | 2023-01-10 | 2023-02-23 |  | Yes | [7 empty] | 2021-05-20 | Addendum |  |  | 2020-03-05 |  |  | 2022-08-09 |  | 2023-04-03 |  |  |  | 2020-03-06 |  |  |  |  | 2024-05-04 |  |  |  | 2020-03-11 | [8 empty] | 2020-03-13 | [13 empty] | 2021-06-08 |  | 2020-03-13 |  | 2020-03-18 | 2023-06-14 |  | 2023-06-16 | 2023-07-12 | 2023-07-12 |  |  |  | 59618 |  | 178204 | 2023-04-03 | 2025-11-04 | 2020-04-08 | 2020-04-08 | 2023-06-16 | 2023-06-16 | [6 empty] | 2023-08-09 | 2023-08-10 | [9 empty] | Q2 2021 |  |  | 2020-04-06 | 10300657943 | [11 empty] | TRUE | TRUE | 28 | 2020-04-08 | 2020-04-08 | 2020 | 2020 | 2020 | 44355 |  |  | 2021-05-20 | Addendum
29 |  | Eben Snow | Brent Brooks | 2019-08-06 | 2022-06-02 | L2_Bump |  | 2022-12-15 | L2_Bump |  | 2023-02-03 | L2_Bump |  | 2023-03-20 | L2_Bump |  | 2025-09-18 | L2_With | [16 empty] | 28 | 3 - HORD |  | 420D4 | 28 | Yes | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Adam Carte | CRSEF Acadia Aggregator, LLC | BD SOLAR LEWISTON JUNCTION LLC | 445 Lewiston Junction Rd/ Auburn Me | 2000113401 | 30011630172 | Solar | [5 empty] | 44.5023 | -70.2907 | 445 Lewiston Junction Road |  |  | Auburn | 503 | HOTEL ROAD | 420D4 | 420T1 | 34.5 | 9310-L0140-0230-0206-ED00050 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-08-13 | 2019-08-13 | 2019-08-20 | 2019-08-13 | 2019-08-19 | 2020-04-21 |  | 2020-05-05 |  | 2020-04-21 | 2020-04-21 | 2020-05-05 |  |  | 2020-04-23 |  |  | CS | 2020-04-23 | [6 empty] | CS |  |  | 2020-04-23 |  |  | 2022-09-26 | 2023-06-19 | [7 empty] | 2020-04-24 |  |  | 2022-09-09 | 2023-06-29 | [7 empty] | 2022-09-09 | 2023-07-13 |  |  |  |  | 2020-04-29 |  |  | 2022-09-26 | 2023-07-13 |  |  | Yes | [11 empty] | 2020-06-29 |  |  | 2022-11-09 | 2023-08-24 |  |  |  |  | 2020-06-29 |  |  |  | 2023-08-24 | [8 empty] | 2023-08-31 |  |  |  |  | 2020-07-07 | [15 empty] | 2020-07-28 |  | 2020-07-28 | 2022-12-01 |  | 2022-12-19 | 2023-07-12 | 2023-07-12 |  |  |  | 119306 | 2020-06-22 | 422851 | 2023-08-24 | 2025-11-04 | 2020-08-26 | 2020-08-26 | 2023-11-07 | 2023-11-07 | [6 empty] | 2023-08-11 | 2023-08-11 | [9 empty] | Q2 2021 |  |  |  | 10300705903 | [11 empty] | TRUE | TRUE | 29 | 2020-08-26 | 2020-08-26 | 2020 | 2020 | 2020
30 |  | Eben Snow | Brent Brooks | 2019-08-06 | 2022-06-08 | L2_Bump |  | 2022-07-27 | L2_Bump |  | 2023-01-18 | L2_With |  | 2023-10-05 | L2_Bump | [18 empty] | 1 - DEER |  | 2 - DEER |  | 412D4 | 24 | Yes | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Daniel Serber | NEXTGRID INC | NEXTGRID MAHOGANY LLC | 1043 Main St (Lewiston) | 2000167670 | 30012456569 | Solar | [5 empty] | 44.1334 | -70.1924 | 1043 Main Street |  |  | Lewiston | 151 | DEER RIPS | 412D4 | 412T4 | 12.47 | FLOC-MISSING-01142021 | Non-FERC | WITHDRAWN | WITHDRAWN | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-08-13 | 2019-08-13 | 2019-08-20 | 2019-08-13 | 2019-08-19 | 2019-12-04 |  | 2019-12-18 |  | 2019-12-04 | 2019-12-04 | 2019-12-18 |  |  | 2019-12-05 | 2020-04-07 |  | CS | 2019-12-05 | RS | 2020-04-07 |  |  |  |  | CS |  |  | 2019-12-05 | 2020-04-07 |  | 2022-07-19 | 2022-10-07 | 2023-10-05 | [6 empty] | 2019-12-27 |  |  | 2022-07-19 | 2022-10-07 | 2023-10-20 | [8 empty] | 2023-11-04 |  |  |  | 2019-12-27 | 2020-04-27 |  | 2022-07-25 | 2022-11-08 |  | 2023-11-03 | Yes |  |  |  |  | 2020-03-23 | [6 empty] | 2020-03-23 | 2020-06-09 |  | 2022-09-06 |  | 2023-01-12 |  |  |  | 2020-03-23 | 2020-06-01 |  |  | 2022-12-01 | 2023-01-12 |  |  |  | 2020-03-23 | [8 empty] | 2020-03-27 | 2020-06-17 |  |  |  | 2024-01-29 | [7 empty] | 2024-01-30 |  |  | 2020-06-17 |  | 2020-06-17 | 2023-02-01 | 2020-06-17 | 2023-02-02 | 2023-07-12 | 2023-07-12 |  |  |  | 222610 |  | 205486 | 2024-01-30 | 2025-07-15 | 2020-06-17 | 2020-06-17 | 2023-02-03 | 2023-02-02 | [6 empty] | 2024-03-25 | 2024-03-25 | [9 empty] | Q3 2020 |  |  |  | 10300681917 | [11 empty] | FALSE | TRUE | 30 | 2020-06-17 | 2020-06-17 | 2020 | 2020 | 2020
31 |  | Govinda Neupane |  | 2019-08-07 | [31 empty] | 1 - RUMF |  | 447D2 |  |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2020-06-25 | Tyler William Perkins | Nexamp, Inc | Rumford Solar LLC | 101 Wyman Hill Rd/ Rumford | 2000114877 | 30012995418 | Solar | 4990 | 4.99 | 6254 |  |  | 45.3154 | -69.2034 | 101 Wyman Hill Road |  |  | Rumford | 31 | RUMFORD | 447D2 | 447T4 |  | 9310-L0187-5020-0151-ED00038 | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-08-14 | 2019-08-14 | 2019-08-21 | 2019-08-14 | 2019-08-19 | 2019-08-22 |  | 2019-09-06 |  | 2019-08-22 | 2019-08-22 | 2019-09-05 |  |  | 2019-09-05 |  |  | CS | 2019-11-12 | [6 empty] | CS |  |  | 2019-11-12 | [11 empty] | 2019-11-20 | [17 empty] | 2019-11-20 | [6 empty] | Yes | [7 empty] | 2021-06-04 | Addendum |  |  | 2020-01-29 | [8 empty] | 2020-01-30 | [17 empty] | 2020-02-03 | [15 empty] | 2020-03-30 |  | 2020-03-31 | 2022-08-18 | 2022-10-05 | [6 empty] | 55522 |  |  |  |  | 2020-04-13 | 2020-04-13 | 2021-07-06 | 2021-07-06 | 2022-10-06 | 2022-10-06 | [15 empty] | Q4 2020 |  |  | TBD | 10300676242 | [11 empty] | TRUE | TRUE | 31 | 2020-04-13 | 2020-04-13 | 2020 | 2020 | 2020 |  |  |  | 2021-06-04 | Addendum
32 |  | Marshall Ripley | Rick Duperre | 2019-08-07 | [31 empty] | 1 - FOHI |  | 624D1 |  |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2020-07-14 | Tyler William Perkins | Nexamp, Inc | Gorham Solar LLC | 314 Fort Hill Rd/ Gorham | 2000114877 | 30012995434 | Solar/Battery | 4990 | 4.99 | 6104 | 3000 |  | 44.791 | -69.7402 | 314 Fort Hill Road |  |  | Gorham | 15 | FORT HILL | 624D1 | 624T1 |  | 9310-L0250-2240-0039-ED00007 | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-08-14 | 2019-08-14 | 2019-08-21 | 2019-08-14 | 2019-08-19 | 2019-08-22 |  | 2019-09-06 |  | 2019-08-22 | 2019-08-22 | 2019-09-05 |  |  | 2019-09-05 |  |  | CS | 2019-11-12 | [6 empty] | CS |  |  | 2019-11-12 | [11 empty] | 2019-11-20 | [17 empty] | 2019-11-20 | [6 empty] | Yes | [7 empty] | 2021-06-30 | Addendum |  |  | 2020-01-29 | [8 empty] | 2020-02-03 | [17 empty] | 2020-02-05 | [15 empty] | 2020-03-30 | 2021-08-11 | 2020-03-31 | [13 empty] | 2020-04-15 | 2020-04-15 | 2021-08-17 | 2021-08-17 | [17 empty] | Q4 2020 |  |  | TBD | 10300676381 | [11 empty] | TRUE | TRUE | 32 | 2020-04-15 | 2020-04-15 | 2020 | 2020 | 2020 |  |  | 44419 | 2021-06-30 | Addendum
33 |  | Eben Snow | Brent Brooks | 2019-08-07 | [31 empty] | 1 - GRFA |  | 436D6 |  |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2020-07-14 | Tyler William Perkins | Nexamp, Inc | Auburn Renewables LLC | 276 Penley Corner Rd Auburn | 2000207930 | 30012995467 | Solar | 4990 | 4.99 | 6613 |  |  | 44.5124 | -70.5204 | 276 Penley Corner Road |  |  | Auburn | 617 | GREAT FALLS | 436D6 | 436T1 |  | 9310-L0176-0230-0154-ED00073 | FERC | TRIGGERING | TRIGGERING (505,000) | 361076 | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-08-14 | 2019-08-14 | 2019-08-21 | 2019-08-14 | 2019-08-19 | 2019-08-23 |  | 2019-09-09 |  | 2019-08-23 | 2019-08-23 | 2019-09-06 |  |  | 2019-09-06 |  |  | CS | 2019-11-12 | [6 empty] | CS |  |  | 2019-11-12 | [11 empty] | 2019-12-05 | [17 empty] | 2019-12-05 | [6 empty] | Yes | [7 empty] | 2021-06-24 | Addendum |  |  | 2020-02-04 | [8 empty] | 2020-03-03 | [17 empty] | 2020-03-06 | [15 empty] | 2020-03-30 |  | 2020-04-13 | [13 empty] | 2020-04-20 | 2020-04-20 | 2021-07-06 | 2021-07-06 | [17 empty] | Q4 2020 |  |  | TBD | 10300678598 | [11 empty] | TRUE | TRUE | 33 | 2020-04-20 | 2020-04-20 | 2020 | 2020 | 2020 |  |  |  | 2021-06-24 | Addendum
34 |  | Eben Snow | Brent Brooks | 2019-08-07 | 2023-05-04 | L2_Bump |  | 2024-10-23 | L2_With | [26 empty] | 2 - GRFA | 1 - GRFA | 436D6 | 33 | Yes | EXECUTED | EXECUTED |  | Noah Gonzalez | Nexamp, Inc | Auburn Renewables 2, LLC | 100 Penley Corner Rd/ Auburn | 2000114877 | 30013456675 | Solar | 999 | 0.999 | 1306 |  |  | 44.4734 | -70.2027 | 100 Penley Corner Road |  |  | Auburn | 609 | GREAT FALLS | 436D6 | 436T1 |  | 9310-L0176-0230-0154-ED00065 | FERC | COST SHARE | COST SHARE (505,000) | 72288 | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-08-14 | 2019-08-14 | 2019-08-21 | 2019-08-14 | 2019-08-19 | 2020-06-15 |  | 2020-06-29 |  | 2020-06-15 | 2020-06-15 | 2020-06-29 |  |  | 2020-06-29 |  |  | CS | 2020-06-29 | [6 empty] | CS |  |  | 2020-06-29 |  |  | 2023-07-21 | 2024-11-15 | [7 empty] | 2020-07-14 |  |  |  | 2024-11-27 | [8 empty] | 2024-12-06 |  |  |  |  | 2020-07-13 |  |  | 2023-06-19 | 2024-12-06 |  |  | Yes | [7 empty] | 2021-06-24 | Addendum |  |  | 2020-09-15 |  |  | 2023-08-09 | 2025-02-13 |  |  |  |  | 2020-09-28 |  |  | 2023-08-09 | 2025-02-15 | [7 empty] | 2023-08-10 | 2025-02-21 |  |  |  |  | 2020-09-30 | [14 empty] | 2022-06-16 | 2020-10-19 | 2021-08-03 | 2020-10-19 | [10 empty] | 861094 | 2025-02-12 |  | 2020-11-08 | 2020-11-08 | 2021-08-03 | 2021-09-15 | 2023-12-08 | 2023-12-08 | 2025-04-07 | 2025-04-07 | [13 empty] | Q3 2028 |  |  |  | 10300733787 | [11 empty] | FALSE | TRUE | 34 | 2020-11-08 | 2020-11-08 | 2020 | 2020 | 2020 |  |  | 44411 | 2021-06-24 | Addendum
35 |  | Govinda Neupane |  | 2019-08-07 | [31 empty] | 1 - TPCO |  | 453D1 |  |  | WITHDRAWN | WITHDRAWN |  | Noah Gonzalez | Nexamp, Inc | NEXAMP SOLAR LLC | 180 Felt Rd/ Woodstock | 2000114877 |  | Solar/Battery | [7 empty] | 180 Felt Road |  |  | Woodstock |  | TRAP CORNER | 453D1 |  |  | 9310-SS0453 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2019-08-14 | 2019-08-21 |  |  |  |  | 1900-01-12 | [57 empty] | Yes | [69 empty] | 2020-04-03 | [37 empty] | TRUE | TRUE | 35 | 0 | 0 | 1900 | #VALUE! | #VALUE!
36 |  |  | Anthony Boucher | 2019-08-07 | [31 empty] | 1 - THCR |  | 246D1 |  |  | WITHDRAWN | WITHDRAWN |  | Noah Gonzalez | Nexamp, Inc | NEXAMP SOLAR LLC | Route 131 / South Thomaston | 2000114877 |  | Solar/Battery | [7 empty] | Route 131 |  |  | South Thomaston |  | THOMASTON CREEK | 246D1 |  |  | 9310-L0081-5440-0048-ED00122 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2019-08-14 | 2019-08-21 |  |  |  |  | 1900-01-12 | [57 empty] | Yes | [69 empty] | 2020-01-20 | [37 empty] | TRUE | TRUE | 36 | 0 | 0 | 1900 | #VALUE! | #VALUE!
37 |  | Rigel Paradise | Rick Duperre | 2019-08-09 | [31 empty] | 1 - BDPP |  | 605D2 |  |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2020-04-28 | Santiago Quijano | Bluewave MA, LLC | BWC SWAN POND CREEK LLC | 1018 South St Dayton #1 | 2000153670 | 30012240237 | Solar | 4990 | 4.99 | 6991 |  |  | 43.5057 |  | 1018 South Street |  |  | Dayton | 245 | BIDDEFORD PUMP | 605D2 | 605T1 |  | 9310-L0215-1530-0003-ED00007 | Non-FERC | TRIGGERING | TRIGGERING (355,000) | 303851 | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-08-16 | 2019-08-16 | 2019-08-23 | 2019-08-16 | 2019-08-19 | 2019-08-28 |  | 2019-09-12 |  | 2019-08-28 | 2019-08-28 | 2019-09-11 | 2019-10-03 | 2019-12-10 |  |  |  | FS | 2019-10-03 | IS | 2019-12-10 |  |  |  |  | Split | [13 empty] | 2020-10-21 | 2021-01-10 | [15 empty] | 2019-10-21 | 2020-01-10 | [7 empty] | Yes | [7 empty] | 2021-06-11 | Addendum | 2019-11-20 | 2020-02-11 | [7 empty] | 2019-11-20 | 2020-02-11 | [16 empty] | 2019-12-09 | 2020-03-03 | [6 empty] | 2019-12-09 | 2020-03-03 | [8 empty] | 2020-03-24 |  | 2020-03-24 | [8 empty] | 208742 |  |  |  |  | 2020-11-08: 2020-04-02; 2020-11-08: 2020-04-02; 2021-08-03: 2021-06-11; 2021-09-15: 2021-06-11 | [13 empty] | Q4 2020 |  |  | 2020-04-29 | 10300659342 | [11 empty] | TRUE | TRUE | 37 | 2020-04-02 | 2020-04-02 | 2020 | 2020 | 2020 |  |  |  | 2021-06-11 | Addendum
38 |  | Rigel Paradise | Rick Duperre | 2019-08-09 | [31 empty] | 2 - BDPP |  | 605D1 | 37 |  | WITHDRAWN | WITHDRAWN |  | Tyson Buerkle | Bluewave MA, LLC | BWC BLUE WAVE MA LLC | 1018 South St Dayton #2 | 2000114857 | 30011652267 | Solar/Battery | [7 empty] | 1018 South Street |  |  | Dayton |  | BIDDEFORD PUMP | 605D1 |  |  | 9310-L0215-1530-0003-ED00046 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2019-08-16 | 2019-08-23 |  |  |  |  | 1900-01-12 | [127 empty] | 2020-04-09 | [37 empty] | TRUE | TRUE | 38 | 0 | 0 | 1900 | #VALUE! | #VALUE!
39 |  | Rigel Paradise | Rick Duperre | 2019-08-09 | [31 empty] | 3 - BDPP |  | 605D1 | 38 |  | WITHDRAWN | WITHDRAWN |  | Tyson Buerkle | Bluewave MA, LLC | BWC BLUE WAVE MA LLC | 1018 South St Dayton #3 | 2000114857 | 30011652283 | Solar/Battery | [7 empty] | 1018 South Street |  |  | Dayton |  | BIDDEFORD PUMP | 605D1 |  |  | 9310-L0215-1530-0003-ED00046 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2019-08-16 | 2019-08-23 |  |  |  |  | 1900-01-12 | [127 empty] | 2020-04-09 | [37 empty] | TRUE | TRUE | 39 | 0 | 0 | 1900 | #VALUE! | #VALUE!
40 |  | Marshall Ripley | Rick Duperre | 2019-08-09 | [31 empty] | 1 - SCAR |  | 693D1 |  |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2020-07-14 | Stephen Campbell | Navisun LLC | BWC BEECH RIDGE BROOK LLC | Johnson Rd Scarborogh | 2000153672 | 30012240252 | Solar | 4980 | 4.98 | 6998 |  |  | 43.6141 | -70.4158 | 12 Johnson Road |  |  | Scarborough | 4 | SCARBOROUGH | 693D1 | 693T1 |  | 9310-L0339-5200-0267-ED00004 | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-08-16 | 2019-08-16 | 2019-08-23 | 2019-08-16 | 2019-08-19 | 2019-08-29 |  | 2019-09-13 |  | 2019-08-29 | 2019-08-29 | 2019-09-12 |  |  | 2019-09-12 |  |  | CS | 2019-11-20 | [6 empty] | CS |  |  | 2019-11-20 | [11 empty] | 2019-12-05 | [17 empty] | 2019-12-05 | [6 empty] | Yes |  |  |  |  | 2020-02-10 |  |  | 2021-06-04 | Addendum |  |  | 2020-02-04 | [8 empty] | 2020-02-06 | [17 empty] | 2020-02-10 | [15 empty] | 2020-03-27 |  | 2020-03-30 | [8 empty] | 658132 |  |  |  |  | 2020-11-08: 2020-04-10; 2020-11-08: 2020-04-10; 2021-08-03: 2021-07-01; 2021-09-15: 2021-07-01 | [13 empty] | Q4 2020 |  |  | 2020-04-09 | 10300659715 | [11 empty] | TRUE | TRUE | 40 | 2020-04-10 | 2020-04-10 | 2020 | 2020 | 2020 |  |  |  | 2021-06-04 | Addendum
41 |  | Marshall Ripley | Rick Duperre | 2019-08-09 | [31 empty] | 1 - BONE |  | 610D2 |  |  | WITHDRAWN | WITHDRAWN |  | Tyson Buerkle | Bluewave MA, LLC | BWC LITTLE RIVER LLC | 211 Groveville Rd Buxton | 2000114970 |  | Solar/Battery | [7 empty] | 211 Groveville Road |  |  | Buxton |  | BONNY EAGLE | 610D2 |  |  | 86-Withdrawn-86d | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2019-08-16 | 2019-08-23 |  |  |  |  | 1900-01-12 | [57 empty] | Pending | [69 empty] | 2019-09-16 | [35 empty] | Re-Submitted Application now deemed PRJ:60 |  | TRUE | TRUE | 41 | 0 | 0 | 1900 | #VALUE! | #VALUE!
42 |  | Marshall Ripley | Rick Duperre | 2019-08-09 | [31 empty] | 2 - BONE |  | 610D2 | 41 |  | WITHDRAWN | WITHDRAWN |  | Tyson Buerkle | Bluewave MA, LLC | BWC LITTLE RIVER LLC | 211 Groveville Rd Buxton #2 | 2000114970 |  | Solar/Battery | [7 empty] | 211 Groveville Road |  |  | Buxton |  | BONNY EAGLE | 610D2 |  |  | 86-Withdrawn-86d | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2019-08-16 | 2019-08-23 |  |  |  |  | 1900-01-12 | [57 empty] | Pending | [69 empty] | 2019-09-16 | [35 empty] | Re-Submitted Application now deemed PRJ:59 |  | TRUE | TRUE | 42 | 0 | 0 | 1900 | #VALUE! | #VALUE!
43 |  | Eben Snow | Brent Brooks | 2019-08-12 | [31 empty] | 1 - KIRD |  | 423D1 |  |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2020-02-28 | Tyler William Perkins | Nexamp, Inc | Norway Road Solar 1 LLC | 0 Norway Rd, Harrison | 2000235902 | 30013375719 | Solar/Battery | 4990 | 4.99 | 6908 | 4990 |  | 44.1364 | -70.6536 | Norway Road |  |  | Harrison | 75 | KIMBALL ROAD | 423D1 | 423T2 |  | 9310-L0147-2520-0056-ED00178 | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-08-19 | 2019-08-19 | 2019-08-26 | 2019-08-19 | 2019-08-22 | 2019-09-03 |  | 2019-09-17 |  | 2019-09-03 | 2019-09-04 | 2019-09-18 |  |  | 2019-09-18 |  |  | CS | 2019-09-19 | [6 empty] | CS |  |  | 2019-09-19 | [11 empty] | 2019-10-31 | [17 empty] | 2019-10-31 | [6 empty] | Yes |  |  |  |  | 2020-01-03 |  |  | 2021-05-24 | Addendum |  |  | 2020-01-10 | [8 empty] | 2020-01-10 | [17 empty] | 2020-01-15 | [13 empty] | 2021-06-27 |  | 2020-01-16 |  | 2020-01-16 | [8 empty] | 203022 |  |  |  |  | 2020-11-08: 2020-01-28; 2020-11-08: 2020-01-28; 2021-08-03: 2021-07-06; 2021-09-15: 2021-07-06 | [13 empty] | Q4 2020 |  |  | 2020-01-30 | 10300644050 | [11 empty] | TRUE | TRUE | 43 | 2020-01-28 | 2020-01-28 | 2020 | 2020 | 2020 | 44374 |  |  | 2021-05-24 | Addendum
44 |  | Rigel Paradise | Rick Duperre | 2019-08-12 | [31 empty] | 1 - LOUD |  | 633D1 |  |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2020-04-28 | Santiago Quijano | Bluewave MA, LLC | BWC DEEP BROOK LLC | 97 New County Rd Saco | 2000153671 | 30012240245 | Solar | 4800 | 4.8 | 6719 |  |  | 43.5177 | -70.48 | 97 New County Road |  |  | Saco | 75 | LOUDEN | 633D1 | 633T3 | 12.47 | 9310-L0265-5090-0186-ED00108 | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-08-19 | 2019-08-19 | 2019-08-26 | 2019-08-19 | 2019-08-22 | 2019-09-04 |  | 2019-09-18 |  | 2019-09-04 | 2019-09-04 | 2019-09-18 | [5 empty] | FS | 2019-10-03 | IS | 2019-12-12 | RS |  |  |  | Split |  |  |  | 2020-03-16 | [9 empty] | 2020-10-23 | 2020-01-10 | [15 empty] | 2019-10-23 | 2020-01-13 |  | 2020-03-18 | [5 empty] | Yes |  |  | 2019-11-27 | 2020-02-26 |  | 2020-04-30 |  | 2021-06-17 | Addendum | 2019-11-27 | 2020-02-11 | [7 empty] | 2019-11-27 | 2020-02-14 | [16 empty] | 2019-12-12 | 2020-02-25 | [6 empty] | 2019-12-12 | 2020-02-25 | [8 empty] | 2020-03-24 |  | 2020-03-24 | [13 empty] | 2020-11-08: 2020-04-03; 2020-11-08: 2020-04-03; 2021-08-03: 2021-06-21; 2021-09-15: 2021-06-21 | [13 empty] | Q4 2020 |  |  | 2020-04-27 | 10300659361 | [11 empty] | TRUE | TRUE | 44 | 2020-04-03 | 2020-04-03 | 2020 | 2020 | 2020 |  |  |  | 2021-06-17 17:18 | Addendum
45 |  | Eben Snow | Brent Brooks | 2019-08-13 | [31 empty] | 1 - CROW |  | 411D1 |  |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2020-02-28 | Alejandro Fernandez | Renewable Properties | NEXTGRID CLIFFROSE LLC | 1875 Lisbon St (Lewiston) | 2000104939 | 30011648984 | Solar | 2000 | 2 | 2629 |  |  | 45.3159 | -69.2034 | 1875 Lisbon Street |  |  | Lewiston | 1 | CROWLEYS | 411D1 | 411T2 |  | FLOC-MISSING-01142021 | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-08-20 | 2019-08-20 | 2019-08-27 | 2019-08-20 | 2019-08-27 | 2019-09-05 |  | 2019-09-19 |  | 2019-09-05 | 2019-09-05 | 2019-09-19 | [5 empty] | CS | 2019-09-17 | [6 empty] | CS |  |  | 2019-09-17 | [11 empty] | 2019-10-08 | [17 empty] | 2019-10-08 | [6 empty] | Yes |  |  |  |  | 2019-12-10 |  |  | 2021-06-17 | Addendum |  |  | 2019-12-11 | [8 empty] | 2019-12-12 | [17 empty] | 2019-12-20 | [15 empty] | 2019-12-23 |  | 2019-12-24 | [13 empty] | 2020-11-08: 2020-01-06; 2020-11-08: 2020-01-06 | [13 empty] | Q3 2020 |  |  | 2020-02-13 | 10300651183 |  | Yes | Yes |  | Helen |  | Helen |  |  |  |  | TRUE | TRUE | 45 | 2020-01-06 | 2020-01-06 | 2020 | 2020 | 2020 |  |  |  | 2021-06-17 17:06 | Addendum
46 |  | Lanie Patterson | Brent Brooks | 2019-08-15 | [31 empty] | 2 - WINS |  | 870D2 | 6 |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2020-08-31 | Daniel Serber | NEXTGRID INC | NEXTGRID SWEETLEAF LLC | 85 Roderick Road Winslow | 2000192553 | 30012796865 | Solar | 4600 | 4.6 | 6301 |  |  | 44.559 | -69.6091 | 85 Roderick Road |  |  | Winslow | 1 | WINSLOW | 870D2 | 870T4 |  | FLOC-MISSING-01142021 | FERC | NOT IMPACTED | NOT IMPACTED | NONE | Under Review 1/31/2020 |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-08-22 | 2019-08-22 | 2019-08-29 | 2019-08-22 | 2019-08-28 | 2019-09-06 |  | 2019-09-20 |  | 2019-09-06 | 2019-09-06 | 2019-09-20 |  |  |  | 2020-04-07 |  | CS | 2019-09-17 | RS | 2020-04-07 |  |  |  |  | CS |  |  | 2019-09-17 | 2020-04-07 | [10 empty] | 2019-10-08 | [17 empty] | 2019-10-08 | [6 empty] | Yes |  |  |  |  | 2019-12-10 | [6 empty] | 2019-12-11 | [8 empty] | 2019-12-12 | 2021-06-17 | [16 empty] | 2019-12-19 | 2020-06-23 | [14 empty] | 2020-06-24 | 2021-08-05 | 2020-06-25 | [13 empty] | 2020-11-08: 2020-07-01; 2020-11-08: 2020-07-01; 2021-08-03: 2021-08-05; 2021-09-15: 2021-09-15 | [13 empty] | Q4 2020 |  |  |  | 10300686659 | [11 empty] | TRUE | TRUE | 46 | 2020-07-01 | 2020-07-01 | 2020 | 2020 | 2020 |  |  | 44413
47 |  | Rigel Paradise | Rick Duperre | 2019-08-15 | [31 empty] | 4 - BDPP |  | 605D1 | 39 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN | 2021-03-30 | Daniel Serber | NEXTGRID INC | NEXTGRID INC | 413 South Street Biddeford | 2000104939 | 30011674659 | Solar | [5 empty] | 43.4958 | -70.4964 | 413 South Street |  |  | Biddeford | 86 | BIDDEFORD PUMP | 605D1 | 605T1 |  | 9310-L0215-0409-0272-ED00174 | Non-FERC | WITHDRAWN | WITHDRAWN | 355000 |  |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-08-22 | 2019-08-22 | 2019-08-29 | 2019-08-22 | 2019-08-28 | 2020-05-04 |  | 2020-05-18 |  | 2020-05-04 | 2020-05-04 | 2020-05-18 | [5 empty] | CS | 2020-05-15 | [6 empty] | CS |  |  | 2020-05-15 | [11 empty] | 2020-05-20 | [17 empty] | 2020-05-18 | [6 empty] | Yes |  |  |  |  | 2020-07-22 |  |  | 2021-06-08 | Addendum |  |  | 2020-07-22 | [8 empty] | 2020-07-22 | [17 empty] | 2020-07-27 | [15 empty] | 2020-07-31 |  | 2020-07-31 | [8 empty] | 214335 |  |  |  | 2022-11-07 | 2020-11-08: 2020-08-05; 2020-11-08: 2020-08-05; 2021-08-03: 2021-08-24; 2021-09-15: 2021-08-24 | [17 empty] | 10300698857 | [11 empty] | TRUE | TRUE | 47 | 2020-08-05 | 2020-08-05 | 2020 | 2020 | 2020 |  |  |  | 2021-06-08 | Addendum
48 |  | Lanie Patterson | Brent Brooks | 2019-08-15 | [31 empty] | 1 - OAKL |  | 839D1 |  |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2020-07-14 | Andrew Martin | Renewable Properties | NEXTGRID MASTIC LLC | 0 Webb Road Waterville | 2000192390 | 30012794324 | Solar | 4600 | 4.6 | 6548 |  |  | 44.5256 | -69.6984 | 0 Webb Road |  |  | Waterville | 24 | OAKLAND | 839D1 | 839T1 |  | 9310-SS0839 | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-08-22 | 2019-08-22 | 2019-08-29 | 2019-08-22 | 2019-08-28 | 2019-09-09 |  | 2019-09-23 |  | 2019-09-09 | 2019-09-09 | 2019-09-23 |  |  |  | 2020-04-07 |  | CS | 2019-09-17 | RS | 2020-04-07 |  |  |  |  | CS |  |  | 2019-09-17 | 2020-04-07 | [10 empty] | 2019-10-08 | [17 empty] | 2019-10-08 | [6 empty] | Yes |  |  |  |  | 2019-12-10 |  |  | 2021-06-30 | Addendum |  |  | 2019-12-11 | [8 empty] | 2019-12-12 | 2020-05-28 | [16 empty] | 2019-12-19 | 2020-06-01 | [6 empty] | 2019-12-19 | 2020-06-01 | [6 empty] | 2019-12-27 |  | 2020-01-03 | [13 empty] | 2020-11-08: 2020-06-11; 2020-11-08: 2020-06-11; 2021-08-03: 2021-08-23; 2021-09-15: 2021-08-23 | [13 empty] | Q4 2020 |  |  | 2020-01-22 | 10300640661 |  | Yes | Yes |  | Helen |  | Helen |  |  |  |  | TRUE | TRUE | 48 | 2020-06-11 | 2020-06-11 | 2020 | 2020 | 2020 |  |  |  | 2021-06-30 | Addendum
49 |  | Eben Snow | Brent Brooks | 2019-08-19 | [31 empty] | 1 - FRYT |  | 405D2 |  |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2020-04-28 | Abby Broedlin | Nautilus Solar | Fryeburg Solar LLC | Route 302, Fryeburg | 2000116643 | 30011678833 | Solar | 4900 | 4.9 | 6542 |  |  | 44.1253 | -70.5745 | Littlefield Road |  |  | Fryeburg | 38 | FRYEBURG TAP | 405D2 | 405T1 |  | 9310-L0117-2130-0008-ED00034 | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-08-22 | 2019-08-26 | 2019-09-03 | 2019-08-22 | 2019-08-28 | 2019-09-10 |  | 2019-09-24 |  | 2019-09-10 | 2019-09-10 | 2019-09-24 | [5 empty] | CS | 2019-10-31 | [6 empty] | CS |  |  | 2019-10-31 | [11 empty] | 2019-11-04 | [17 empty] | 2019-11-04 | [6 empty] | Yes |  |  |  |  | 2020-01-07 | [6 empty] | 2020-01-14 | [8 empty] | 2020-01-15 | [17 empty] | 2020-01-21 | [15 empty] | 2020-01-27 |  | 2020-01-29 | [13 empty] | 2020-11-08: 2020-03-02; 2020-11-08: 2020-03-02; 2021-08-03: 2021-08-27; 2021-09-15: 2021-09-17 | [13 empty] | Q4 2020 |  |  | 2020-03-12 | 10300652899 | [11 empty] | TRUE | TRUE | 49 | 2020-03-02 | 2020-03-02 | 2020 | 2020 | 2020
50 |  | Eben Snow | Brent Brooks | 2019-08-21 | [31 empty] | 1 - R115 |  | 445D2 |  |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2020-07-14 | Cameron Clark | Harrison Street | NAPLES CASCO SOLAR 1 LLC | 86 Casco Rd (Solar) | 2000174911 | 30012556830 | Solar | 2000 | 2 | 2375 |  |  | 43.9698 | -70.5734 | 86 Casco Road |  |  | Naples | 22 | RAYMOND 115 KV | 445D2 | 445T2 |  | 9310-L0185-4040-0070-ED00036 | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-08-28 | 2019-08-28 | 2019-09-05 | 2019-08-28 | 2019-09-04 | 2019-09-11 |  | 2019-09-25 |  | 2019-09-11 | 2019-09-11 | 2019-09-25 | [5 empty] | CS | 2019-09-24 | [6 empty] | CS |  |  | 2019-09-24 | [11 empty] | 2019-11-05 | [17 empty] | 2019-11-05 | [6 empty] | Yes |  |  |  |  | 2020-01-08 | [6 empty] | 2020-01-15 | [8 empty] | 2020-01-15 | [17 empty] | 2020-01-22 | [15 empty] | 2020-04-14 |  | 2020-04-14 | [13 empty] | 2020-11-08: 2020-04-20; 2020-11-08: 2020-04-20 | [13 empty] | Q1 2020 |  |  | 2020-05-18 | 10300662608 | [11 empty] | TRUE | TRUE | 50 | 2020-04-20 | 2020-04-20 | 2020 | 2020 | 2020
51 |  | Govinda Neupane |  | 2019-08-29 | [31 empty] | 1 - WSTN |  | 866D1 |  |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2020-04-28 | Zach Good | Aligned Solar Partners | DIRT SOLAR LLC | 35 East Ridge Rd Skowhegan | 2000144594 | 30012105406 | Solar | 2625 | 2.625 | 3675 |  |  | 44.4639 | -69.3757 | 35 East Ridge Road |  |  | Skowhegan | 6 | WESTON HYDRO | 866D1 | 866T2 |  | FLOC-MISSING-01142021 | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-09-04 | 2019-09-06 | 2019-09-13 | 2019-09-04 | 2019-09-10 | 2019-09-12 |  | 2019-09-26 |  | 2019-09-12 | 2019-09-12 | 2019-09-26 | [5 empty] | CS | 2019-09-24 | [6 empty] | CS |  |  | 2019-09-24 | [11 empty] | 2019-10-07 | [17 empty] | 2019-10-07 | [6 empty] | Yes |  |  |  |  | 2019-12-09 |  |  | 2021-07-15 | Addendum |  |  | 2019-12-10 | [8 empty] | 2019-12-10 | [17 empty] | 2019-12-17 | [13 empty] | 2021-07-20 |  | 2019-12-18 |  | 2019-12-18 | [13 empty] | 2020-11-08: 2020-01-15; 2020-11-08: 2020-01-15 | [13 empty] | Q4 2021 |  |  | 2020-01-10 | 10300599802 |  |  |  |  | Helen |  | Helen |  |  |  |  | TRUE | TRUE | 51 | 2020-01-15 | 2020-01-15 | 2020 | 2020 | 2020 | 44397 |  |  | 2021-07-15 | Addendum
52 |  | Rigel Paradise | Rick Duperre | 2019-08-29 | [31 empty] | 1 - LEBA |  | 695D2 |  |  | WITHDRAWN | WITHDRAWN |  | Daniel Serber | NEXTGRID INC | NEXTGRID INC | 390 Lebanon Road Lebanon | 2000104939 | 30011674667 | Solar/Battery | [7 empty] | 390 West Lebanon Road |  |  | Lebanon |  | LEBANON | 695D2 |  |  | 9310-L0473-3190-0007-ED00044 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2019-09-06 | 2019-09-13 |  |  |  |  | 1900-01-12 | [57 empty] | Yes | [69 empty] | 2019-11-17 | [37 empty] | TRUE | TRUE | 52 | 0 | 0 | 1900 | #VALUE! | #VALUE!
53 |  | Marshall Ripley | Rick Duperre | 2019-08-29 | [31 empty] | 1 - SMRD |  | 660D1 |  |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2020-04-28 | Abby Broedlin | Nautilus US Power Holdco, LLC | Casco Standish Solar LLC | Moody Rd Standish | 2000118435 | 30011704340 | Solar | 4990 | 4.99 | 7073 |  |  | 43.4542 | -70.3227 | Moody Road |  |  | Standish | 8 | SHAWS MILL ROAD | 660D1 | 660T1 |  | 9310-L0328-5500-0026-ED00049 | Non-FERC | TRIGGERING | TRIGGERING (250,000) | 208612 | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-09-04 | 2019-09-06 | 2019-09-13 | 2019-09-04 | 2019-09-10 | 2019-09-16 |  | 2019-09-30 |  | 2019-09-16 | 2019-09-16 | 2019-09-30 | [5 empty] | CS | 2019-09-23 | [6 empty] | CS |  |  | 2019-09-23 | [11 empty] | 2019-10-01 | [17 empty] | 2019-10-01 | [6 empty] | Yes | 2019-10-15 |  |  |  | 2019-12-03 |  |  | 2021-06-11 | Addendum |  |  | 2019-12-03 | [8 empty] | 2019-12-03 | [17 empty] | 2019-12-12 | [7 empty] | 2019-12-12 | [7 empty] | 2020-01-06 |  | 2020-01-09 | [8 empty] | 226797 |  |  |  |  | 2020-11-08: 2020-02-06; 2020-11-08: 2020-02-06; 2021-08-03: 2021-06-29; 2021-09-15: 2021-06-29 | [13 empty] | Q4 2021 |  |  | 2020-03-03 | 10300641952 | [11 empty] | TRUE | TRUE | 53 | 2020-02-06 | 2020-02-06 | 2020 | 2020 | 2020 |  |  |  | 2021-06-11 | Addendum
54 |  | Eben Snow | Brent Brooks | 2019-08-29 | 2022-06-02 | L2_Bump |  | 2022-12-15 | L2_Bump |  | 2023-02-03 | L2_Bump |  | 2023-03-20 | L2_Bump | [20 empty] | 4 - HORD |  | 420D2 | 29 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Kelsey Haley | New Leaf Energy, Inc | 510 PV PROJECT DEVELOPMENT | 1040 Perkins Ridge Rd (Auburn) | 2000116264 | 30011673636 | Solar/Battery | [5 empty] | 44.1337 | -70.2887 | 1040 Perkins Ridge Rd |  |  | Auburn | 60 | HOTEL ROAD | 420D2 | 420T2 |  | 9310-L0138-0230-0551-ED00100 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Under Review 1/31/2020 |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-09-04 | 2019-09-06 | 2019-09-13 | 2019-09-04 | 2019-09-11 | 2020-08-27 |  | 2020-09-11 |  | 2020-08-27 | 2020-08-27 | 2020-09-11 | [5 empty] | CS | 2020-09-04 | [6 empty] | CS |  |  | 2020-09-04 | [29 empty] | 2020-09-17 | [6 empty] | Pending |  |  |  |  | 2020-11-20 |  |  | 2021-05-18 | Addendum |  |  | 2020-11-23 | [8 empty] | 2020-11-25 | [17 empty] | 2020-12-02 | [7 empty] | 2020-12-02 | [5 empty] | 2021-05-20 |  | 2021-06-09 |  | 2021-06-09 |  |  |  | 2023-07-17 | 2023-07-17 |  |  |  | 1073721 |  |  |  | 2023-10-24 | 2020-11-08: 2021-02-19; 2020-11-08: 2021-02-19; 2021-08-03: 2021-06-09; 2021-09-15: 2021-06-09 |  |  | 2023-08-16 | 2023-08-16 | [13 empty] | Requested | [11 empty] | TRUE | TRUE | 54 | 2021-02-19 | 2021-02-19 | 2021 | 2021 | 2021 | 44336 |  |  | 2021-05-18 | Addendum
55 |  | Eben Snow | Brent Brooks | 2019-08-29 | 2022-06-02 | L2_Bump |  | 2022-12-15 | L2_Bump |  | 2023-02-03 | L2_Bump |  | 2023-03-20 | L2_Bump | [20 empty] | 5 - HORD |  | 420D2 | 54 |  | WITHDRAWN | WITHDRAWN |  | Kelsey Haley | New Leaf Energy, Inc | 510 PV PROJECT DEVELOPMENT | Pinecrest Park Lot 8 Dover Foxcroft | 2000116264 | 30011673669 | Solar/Battery | [5 empty] | 44.1337 | -70.2887 | 295-006 Perkins Ridge Rd |  |  | Auburn | 64 | HOTEL ROAD | 420D2 | 420T2 |  | 9310-L0138-0230-0551-ED00100 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Under Review 1/31/2020 |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-09-04 | 2019-09-06 | 2019-09-13 | 2019-09-04 | 2019-09-11 | 2021-06-22 | 2021-03-04 | 2021-07-07 | 2021-03-05 | 2021-03-08 | 2021-03-18 | 2021-03-24 |  |  | 2021-03-24 | 2021-11-19 |  | CS | 2021-03-24 | RS | 2021-11-19 |  |  |  |  | CS |  |  | 2021-03-24 | 2021-11-19 |  | 2023-11-08 |  |  |  |  | 2021-06-15 |  |  |  | 2021-07-28 | [7 empty] | 2021-07-09 | 2021-07-09 | 2021-12-06 | [7 empty] | 2021-07-13 | 2021-12-11 | [10 empty] | 2021-09-14 | 2022-01-04 | [5 empty] | 2021-09-13 | 2022-01-18 | [7 empty] | 2021-09-13 | 2022-01-18 | [7 empty] | 2022-01-18 | [8 empty] | 2021-09-20 | 2022-01-18 | [6 empty] | 2021-09-20 | 2022-01-18 | [17 empty] | 404602 | 2021-09-16 | 421102 | 2022-03-10 | 2023-11-29 | [37 empty] | TRUE | TRUE | 55 | 0 | 0 | 1900 | 1900 | 1900 |  |  |  |  | 2021-09-20
56 |  | Eben Snow | Brent Brooks | 2019-08-29 | 2022-06-02 | L2_Bump |  | 2022-12-15 | L2_Bump |  | 2023-02-03 | L2_Bump |  | 2023-03-20 | L2_Bump |  | 2023-11-29 | wthdw | [17 empty] | 6 - HORD |  | 420D2 | 55 |  | WITHDRAWN | WITHDRAWN |  | Kelsey Haley | New Leaf Energy, Inc | 510 PV PROJECT DEVELOPMENT | 1470 Perkins Ridge Rd (Auburn) | 2000116264 | 30011673644 | Solar/Battery | [5 empty] | 44.1337 | -70.2887 | 1470 Perkins Ridge Rd | 1470 | Perkins Ridge Rd | Auburn |  | HOTEL ROAD | 420D2 | 420T2 | 12.47 | FLOC-MISSING-01142021 | Non-FERC | WITHDRAWN | WITHDRAWN |  |  |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-09-04 | 2019-09-06 | 2019-09-13 | 2019-09-04 | 2019-09-11 | 2023-11-29 | 2023-12-06 | 2023-12-13 | 2023-12-07 | 2023-12-15 | 2023-12-15 | 2023-12-29 | [123 empty] | 2024-01-02 | [18 empty] | FALSE | TRUE | 1900-02-24 |  |  | #VALUE! | #VALUE! | #VALUE!
57 |  | Govinda Neupane |  | 2019-08-29 | [31 empty] | 1 - BETH |  | 403D1 |  |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2020-04-28 | Todd Fryatt | ECA Solar | ECA MAINE BET LLC | 001 West Bethel Rd, Bethel | 2000119658 | 30011722003 | Solar | 4800 | 4.8 | 3280 |  |  | 44.4161 | -70.8381 | 0 West Bethel Rd |  |  | Bethel | 69 | BETHEL | 403D1 | 403T1 |  | FLOC-MISSING-01142021 | Non-FERC | TRIGGERING | TRIGGERING | 375000 | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-09-05 | 2019-09-06 | 2019-09-13 | 2019-09-05 | 2019-09-11 | 2019-09-17 |  | 2019-10-01 |  | 2019-09-17 | 2019-09-17 | 2019-10-01 | [5 empty] | CS | 2019-10-15 | [6 empty] | CS |  |  | 2019-10-15 | [11 empty] | 2019-10-31 | [17 empty] | 2019-10-31 | [6 empty] | Yes |  |  |  |  | 2020-01-03 |  |  | 2021-06-08 | Addendum |  |  | 2020-01-10 | [8 empty] | 2020-01-16 | [17 empty] | 2020-01-23 | [13 empty] | 2021-06-10 |  | 2020-01-27 |  | 2020-01-27 | [8 empty] | 380522 |  |  |  |  | 2020-11-08: 2020-02-18; 2020-11-08: 2020-02-18; 2021-08-03: 2021-09-02; 2021-09-15: 2021-09-02 | [13 empty] | Q4 2020 |  |  | 2020-03-03 | 10300646357 | [11 empty] | TRUE | TRUE | 57 | 2020-02-18 | 2020-02-18 | 2020 | 2020 | 2020 | 44357 |  |  | 2021-06-08 | Addendum
58 |  | Eben Snow | Brent Brooks | 2019-08-30 | 2022-06-02 | L2_Bump |  | 2022-12-15 | L2_Bump |  | 2023-02-03 | L2_Bump |  | 2023-03-20 | L2_Bump |  | 2023-11-29 | wthdw |  | 2023-01-02 | wthdw | [14 empty] | 7 - HORD |  | 420D2 | 56 |  | WITHDRAWN | WITHDRAWN |  | Kelsey Haley | New Leaf Energy, Inc | 510 PV Project Development, LLC | 319-025 Perkins Ridge Rd (Auburn) | 2000116264 | 30011673651 | Solar/Battery | [5 empty] | 44.1337 | -70.2887 | 319-025 Perkins Ridge Rd |  |  | Auburn | 90 | HOTEL ROAD | 420D2 | 420T2 | 12.47 | FLOC-MISSING-01142021 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Under Review 1/31/2020 |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-09-04 | 2019-09-09 | 2019-09-16 | 2019-09-04 | 2019-09-11 | 2023-01-02 | 2024-01-04 | 2024-01-17 | [127 empty] | 2024-01-09 | [37 empty] | TRUE | TRUE | 58 | 0 | 0 | 1900 | #VALUE! | #VALUE!
59 |  | Marshall Ripley | Rick Duperre | 2019-08-30 | [31 empty] | 3 - BONE |  | 610D2 | 42 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Tyson Buerkle | Bluewave ME, LLC | BWC LITTLE RIVER LLC | 211 Groveville Rd Buxton #2 | 2000114970 | 30011653455 | Solar | [5 empty] | 43.6572 | -70.5271 | 211 Groveville Road |  |  | Buxton | 35 | BONNY EAGLE | 610D2 | 610T4 |  | 9310-L0221-0820-0033-ED00041 | Non-FERC | WITHDRAWN | WITHDRAWN | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-09-09 | 2019-09-09 | 2019-09-16 | 2019-09-09 | 2019-09-11 | 2019-09-18 |  | 2019-10-02 |  | 2019-09-18 | 2019-09-18 | 2019-10-02 | [5 empty] | FS | 2019-10-03 | IS | 2019-12-13 | RS |  |  |  | Split |  |  |  | 2020-03-16 | [9 empty] | 2019-10-23 | [16 empty] | 2019-10-23 | 2020-01-10 |  | 2020-03-23 | [5 empty] | Yes |  |  | 2019-11-27 | 2020-02-25 |  | 2020-05-05 |  | 2021-06-04 | Addendum | 2019-11-27 | 2020-02-11 | [7 empty] | 2019-11-27 | 2020-02-13 | [16 empty] | 2019-12-13 | 2020-02-21 | [6 empty] | 2019-12-13 | 2020-02-21 | [8 empty] | 2020-03-24 |  | 2020-03-24 |  |  |  | 2023-07-03 |  |  |  |  | 230022 |  | 457255 | 2022-09-27 | 2023-07-14 | 2020-11-08: 2020-04-03; 2020-11-08: 2020-04-03 | [16 empty] | 2020-04-28 | 10300659353 | [11 empty] | TRUE | TRUE | 59 | 2020-04-03 | 2020-04-03 | 2020 | 2020 | 2020 |  |  |  | 2021-06-04 | Addendum
60 |  | Marshall Ripley | Rick Duperre | 2019-08-30 | [31 empty] | 4 - BONE |  | 610D2 | 59 |  | WITHDRAWN | WITHDRAWN |  | Tyson Buerkle | Bluewave MA, LLC | BWC LITTLE RIVER LLC | 211 Groveville Rd Buxton | 2000114970 |  | Solar/Battery | [7 empty] | 211 Groveville Road |  |  | Buxton |  | BONNY EAGLE | 610D2 |  |  | 86-Withdrawn-86d | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2019-09-09 | 2019-09-16 |  |  |  |  | 1900-01-12 | [57 empty] | Pending | [69 empty] | 2020-04-09 | [37 empty] | TRUE | TRUE | 60 | 0 | 0 | 1900 | #VALUE! | #VALUE!
61 |  | Lanie Patterson | Brent Brooks | 2019-09-03 | [31 empty] | 1 - WINT |  | 256D1 |  |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2020-04-28 | Tyler William Perkins | Nexamp, Inc | WINTHROP CENTER SOLAR 1 LLC | 201 Winthrop Center Rd Winthrop | 2000113260 | 30013465031 | Solar/Battery | 4990 | 4.99 | 6986 | 5000 |  | 44.3077 | -69.9236 | 201 Winthrop Center Road |  |  | Winthrop | 17 | WINTHROP | 256D1 | 256T2 |  | 9310-L0095-6450-0177-ED00065 | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Under Review 1/31/2020 |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-09-09 | 2019-09-10 | 2019-09-17 | 2019-09-09 | 2019-09-11 | 2019-09-19 |  | 2019-10-03 |  | 2019-09-19 | 2019-09-19 | 2019-10-03 | [5 empty] | CS | 2019-09-19 | [6 empty] | CS |  |  | 2019-09-19 | [11 empty] | 2019-10-31 | [17 empty] | 2019-10-31 | [6 empty] | Yes |  |  |  |  | 2020-01-03 | [6 empty] | 2020-01-10 | [8 empty] | 2020-01-10 | [17 empty] | 2020-01-17 | [15 empty] | 2020-03-09 | 2021-08-05 | 2020-04-02 | [13 empty] | 2020-11-08: 2020-04-02; 2020-11-08: 2020-04-02; 2021-08-03: 2021-09-01; 2021-09-15: 2021-09-01 | [13 empty] | Q2 2021 |  |  | 2020-03-23 | 10300655211 | [11 empty] | TRUE | TRUE | 61 | 2020-04-02 | 2020-04-02 | 2020 | 2020 | 2020 |  |  | 44413
62 |  | Govinda Neupane |  | 2019-09-03 | [31 empty] | 2 - RUIP |  | 466D1 | 8 |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2020-07-14 | Jim Gordon | Energy Management, Inc. | RUMFORD PARK SOLAR LLC | Industrial Park Dr Rumford | 2000119690 | 30011722284 | Solar | 4988 | 4.988 | 6681 |  |  | 44.5322 | -70.5195 | Industrial Park Drive |  |  | Rumford | 6 | RUMFORD INDUSTRIAL PARK | 466D1 | 466T1 |  | 9310-L0188-5020-0073-ED00012 | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-09-09 | 2019-09-10 | 2019-09-17 | 2019-09-09 | 2019-09-11 | 2019-09-23 |  | 2019-10-07 |  | 2019-09-23 | 2019-09-23 | 2019-10-07 | [5 empty] | CS | 2019-10-01 | [6 empty] | CS |  |  | 2019-10-01 | [11 empty] | 2019-10-03 | [17 empty] | 2019-10-03 | [6 empty] | Yes |  |  |  |  | 2019-12-05 | [6 empty] | 2019-12-09 | [8 empty] | 2019-12-11 | [17 empty] | 2019-12-18 | [15 empty] | 2019-12-18 |  | 2019-12-18 | [13 empty] | 2020-11-08: 2020-01-16; 2020-11-08: 2020-01-16 | [13 empty] | Q4 2020 |  |  | 2020-01-13 | 10300643118 |  |  |  |  | Helen |  | Helen |  |  |  |  | TRUE | TRUE | 62 | 2020-01-16 | 2020-01-16 | 2020 | 2020 | 2020
63 |  | Eben Snow | Brent Brooks | 2019-09-04 | [31 empty] | 1 - CATP |  | 463D1 |  |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2020-07-14 | Scott Moore | REA Investments | NUTTING RIDGE SOLAR LLC | 804 State Route 121, Otisfield | 2000124342 | 30011791917 | Solar/Battery | 3880 | 3.88 | 5648 |  | 4000 | 44.7082 | -70.5429 | 723 Oxford Rd |  |  | Otisfield | 9 | CASCO TAP | 463D1 | 463T1 |  | 9310-L0204-4390-0044-ED00115 | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-09-09 | 2019-09-11 | 2019-09-18 | 2019-09-09 | 2019-09-11 | 2019-09-20 |  | 2019-10-04 |  | 2019-09-20 | 2019-09-20 | 2019-10-04 |  |  |  | 2020-03-11 |  | CS | 2019-10-01 | RS | 2020-03-11 |  |  |  |  | CS |  |  | 2019-10-01 | 2020-03-11 | [10 empty] | 2019-10-07 | [17 empty] | 2019-10-07 | [6 empty] | Yes |  |  |  |  | 2019-12-09 |  |  | 2021-07-15 | Addendum |  |  | 2019-12-10 | [8 empty] | 2019-12-10 | [17 empty] | 2019-12-18 | 2020-05-18 | [12 empty] | 2021-07-21 |  | 2020-06-03 |  | 2020-06-11 | [13 empty] | 2020-11-08: 2020-06-19; 2020-11-08: 2020-06-19; 2021-08-03: 2021-01-18; 2021-09-15: 2021-01-18 | [13 empty] | Q4 2020 |  |  |  | 10300681907 | [11 empty] | TRUE | TRUE | 63 | 2020-06-19 | 2020-06-19 | 2020 | 2020 | 2020 | 44398 |  |  | 2021-07-15 | Addendum
64 |  | Eben Snow | Brent Brooks | 2019-09-04 | [31 empty] | 1 - GRAY |  | 416D2 |  |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2020-04-28 | Abby Broedlin | Nautilus US Power Holdco, LLC | Sturgeon Solar Grey, LLC | 97 Shaker Road Gray | 2000119678 | 30013403966 | Solar | 4990 | 4.99 | 6528 |  |  | 43.7141 | -70.4703 | 97 Shaker Road |  |  | Gray | 276 | GRAY | 416D2 | 416T1 |  | FLOC-MISSING-01142021 | Non-FERC | TRIGGERING | TRIGGERING (380,000) | 380000 | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-09-09 | 2019-09-11 | 2019-09-18 | 2019-09-09 | 2019-09-11 | 2019-09-24 |  | 2019-10-08 |  | 2019-09-24 | 2019-09-24 | 2019-10-08 | [5 empty] | CS | 2019-10-01 | [6 empty] | CS |  |  | 2019-10-01 | [11 empty] | 2019-10-03 | [17 empty] | 2019-10-03 | [6 empty] | Yes |  |  |  |  | 2019-12-05 |  |  | 2021-06-11 | Addendum |  |  | 2019-12-09 | [8 empty] | 2019-12-10 | [17 empty] | 2019-12-16 | [15 empty] | 2020-02-25 |  | 2020-02-28 | [8 empty] | 349295 |  |  |  |  | 2020-11-08: 2020-03-26; 2020-11-08: 2020-03-26; 2021-08-03: 2021-07-15; 2021-09-15: 2021-07-15 | [13 empty] | Q4 2020 |  |  | TBD | 10300668602 | [11 empty] | TRUE | TRUE | 64 | 2020-03-26 | 2020-03-26 | 2020 | 2020 | 2020 |  |  |  | 2021-06-11 | Addendum
65 |  | Eben Snow | Brent Brooks | 2019-09-05 | [31 empty] | 1 - TURN |  | 454D1 |  |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Kelsey Haley | New Leaf Energy, Inc | 510 PV PROJECT DEVELOPMENT LLC | 0 Ricker Hill Rd (Turner) | 2000116264 | 30011673628 | Solar/Battery | [5 empty] | 44.5267 | -70.2071 | 0 Ricker Hill Rd |  |  | Turner | 22 | TURNER | 454D1 | 454T1 | 12.47 | 9310-L0196-5880-0084-ED00017 | Non-FERC | WITHDRAWN | WITHDRAWN | NONE | Under Review 1/31/2020 |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-09-11 | 2019-09-12 | 2019-09-19 | 2019-09-11 | 2019-09-13 | 2019-09-25 |  | 2019-10-09 |  | 2019-09-25 | 2019-09-25 | 2019-10-09 | [5 empty] | CS | 2019-10-31 | [6 empty] | CS |  |  | 2019-10-31 |  |  | 2022-08-31 | [8 empty] | 2020-01-09 | [17 empty] | 2020-02-28 | [6 empty] | Yes |  |  |  |  | 2020-05-04 |  |  | 2021-05-21 | Addendum |  |  | 2020-05-04 | [8 empty] | 2020-04-01 | [17 empty] | 2021-06-16 | [7 empty] | 2021-06-16 | [5 empty] | 2021-06-06 |  | 2020-04-02 |  | 2020-04-03 | 2023-02-13 | 2020-04-03 | [6 empty] | 450255 |  |  |  | 2023-03-10 | 2020-11-08: 2020-04-03; 2020-11-08: 2020-04-03; 2021-08-03: 2021-07-22; 2021-09-15: 2021-07-22 | [16 empty] | TBD | 10300660625 | [11 empty] | TRUE | TRUE | 65 | 2020-04-03 | 2020-04-03 | 2020 | 2020 | 2020 | 44353 |  |  | 2021-05-21 | Addendum
66 |  | Govinda Neupane |  | 2019-09-05 | [31 empty] | 1 - STUR |  | 858D3 |  |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2019-12-30 | Paige Kutschbach | Madison Energy Holdings | HEP FARMINGTON SPV LLC | (SOLAR) WILTON RD FARMINGTON | 2000407821 | 30015674556 | Solar | 4875 | 4.875 | 6408 |  |  | 44.3922 | -70.9755 | Wilton Road |  |  | Farmington | 21 | STURTEVANT | 858D3 | 858T2 |  | 9310-L0440-2030-0158-ED00015 | Non-FERC | TRIGGERING | TRIGGERING | 338902 | Under Review 1/31/2020 |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-09-11 | 2019-09-12 | 2019-09-19 | 2019-09-11 | 2019-09-13 | 2019-09-26 |  | 2019-10-10 |  | 2019-09-26 | 2019-09-26 | 2019-10-10 | [5 empty] | CS | 2019-09-26 | [6 empty] | CS |  |  | 2019-09-26 | [11 empty] | 2019-10-02 | [17 empty] | 2019-10-02 | [6 empty] | Yes | 2019-10-15 |  |  |  | 2019-12-04 |  |  | 2021-05-19 | Addendum |  |  | 2019-11-12 | [8 empty] | 2019-11-12 | [17 empty] | 2019-11-15 | [13 empty] | 2021-05-27 |  | 2019-11-15 |  | 2019-11-18 | [8 empty] | 388712 |  |  |  |  | 2020-11-08: 2019-11-20; 2020-11-08: 2019-11-20; 2021-08-03: 2021-07-12; 2021-09-15: 2021-07-12 | [13 empty] | Q4 2020 |  |  | 2019-12-05 | 10300633586 |  | Yes | Yes |  | Helen |  | Helen |  |  |  |  | TRUE | TRUE | 66 | 2019-11-20 | 2019-11-20 | 2019 | 2019 | 2019 | 44343 |  |  | 2021-05-19 | Addendum
67 |  | Marshall Ripley | Rick Duperre | 2019-09-05 | 2023-07-14 | wthdw | [29 empty] | 5 - BONE |  | 610D2 | 60 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Joseph Feole | Soltage LLC | STANDISH BONNY EAGLE SOLAR 1 LLC | Bonnie Eagle Standish | 2000176161 | 30012576010 | Solar | [5 empty] | 43.7072 | -70.5759 | Bonney Eagle Road |  |  | Standish | 86 | BONNY EAGLE | 610D2 | 610T4 | 12.47 | 9310-L0221-5500-0006-ED00201 | Non-FERC | WITHDRAWN | WITHDRAWN | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-09-11 | 2019-09-12 | 2019-09-19 | 2019-09-11 | 2019-09-19 | 2020-04-24 |  | 2020-05-08 |  | 2020-04-24 | 2020-04-24 | 2020-05-08 |  |  | 2020-05-04 |  |  | CS | 2020-05-04 | [6 empty] | CS |  |  | 2020-05-04 |  |  | 2023-10-30 | [8 empty] | 2020-04-29 |  |  | 2023-11-02 | [8 empty] | 2023-11-16 | [5 empty] | 2020-05-05 |  |  | 2023-11-22 |  |  |  | Yes |  |  |  |  | 2020-07-09 |  |  | 2021-06-04 | Addendum |  |  | 2020-07-09 |  |  | 2024-01-09 | [5 empty] | 2020-07-23 | 2020-10-30 |  | N/A | [14 empty] | 2020-07-29 | 2020-11-02 | [14 empty] | 2020-11-02 |  | 2020-11-03 |  |  |  | 2023-07-10 | 2023-07-10 |  |  |  | 1209948 |  | 318338 | 2023-06-06 | 2024-09-18 | 2020-11-08: 2020-11-14; 2020-11-08: 2020-11-14; 2021-08-03: 2021-06-16; 2021-09-15: 2021-06-16 |  |  | 2023-10-10 | 2023-10-11 | [13 empty] | 10300735556 | [11 empty] | TRUE | TRUE | 67 | 2020-11-14 | 2020-11-14 | 2020 | 2020 | 2020 |  |  |  | 2021-06-04 | Addendum
68 |  | Eben Snow | Brent Brooks | 2019-09-05 | [31 empty] | 1 - LEED |  | 471D2 |  |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2021-12-17 | Jack Kenworthy | Walden Renewables | Kearsarge Leeds Tenant LLC | Route 106/ Leeds | 2000120551 | 30011735872 | Solar | 20000 | 20 | 26400 |  |  | 44.336 | -70.1672 | Rte 106 |  |  | Leeds | 1 | LEEDS | 471D2 | 471T1 |  | 9310-L0210-3210-0034-ED00256 | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-09-11 | 2019-09-12 | 2019-09-19 | 2019-09-11 | 2019-09-13 | 2019-09-30 |  | 2019-10-15 |  | 2019-09-30 | 2019-09-30 | 2019-10-14 | [5 empty] | FS | 2019-10-14 | IS | 2020-01-15 | RS |  |  |  | Split |  |  |  | 2020-01-15 | [9 empty] | 2019-10-21 | 2020-01-28 | [15 empty] | 2019-12-04 | 2020-01-28 | [7 empty] | Yes |  |  | 2020-01-09 | 2020-03-11 |  |  |  | 2021-06-04 | Addendum | 2020-01-03 | 2020-02-27 | [7 empty] | 2020-01-06 | 2020-03-06 | [16 empty] | 2020-01-13 | 2020-03-11 | [6 empty] | 2020-01-13 | 2020-03-11 | [6 empty] | 2021-06-17 |  | 2020-04-01 |  | 2020-06-05 | [8 empty] | 325305 |  |  |  |  | 2020-11-08: 2020-06-11; 2020-11-08: 2020-06-11 | [13 empty] | Q2 2021 |  |  |  | 10300678670 | [11 empty] | TRUE | TRUE | 68 | 2020-06-11 | 2020-06-11 | 2020 | 2020 | 2020 | 44364 |  |  | 2021-06-04 | Addendum
69 |  | Eben Snow | Brent Brooks | 2019-09-06 | [31 empty] | 2 - TURN |  | 454D1 | 65 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Eric Weinstein | BORREGO SOLAR SYSTEMS INC | BORREGO SOLAR SYSTEMS INC | 11 Ricker Hill Rd (Turner) | 2000116264 | 30013399479 | Solar/Battery | [5 empty] | 44.267 | -70.2821 | 11 Ricker Hill Rd |  |  | Turner |  | TURNER | 454D1 |  |  | 9310-L0196-5880-0084-ED00035 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2019-09-13 | 2019-09-20 | 2019-09-11 | 2019-09-13 |  | 2020-04-22 | 1900-01-12 | 2020-04-30 | 2020-05-06 | 2020-05-06 | [6 empty] | CS | 2020-05-13 | [6 empty] | CS |  |  | 2020-05-13 | [11 empty] | 2020-05-27 | [7 empty] | 2021-05-28 | 2021-05-28 | [8 empty] | 2021-06-04 | [6 empty] | Yes |  |  |  |  | 2020-08-07 | [33 empty] | 2020-08-20 | [7 empty] | 2020-08-20 | [7 empty] | 2020-09-08 |  | 2020-09-11 |  | 2020-09-11 | [6 empty] | 334197 |  |  |  | 2022-03-07 | 2020-11-08: 2020-09-11; 2020-11-08: 2020-09-11; 2021-08-03: 2021-07-14; 2021-09-15: 2021-07-14 | [17 empty] | 10300710383 | [11 empty] | TRUE | TRUE | 69 | 2020-09-11 | 2020-09-11 | 2020 | 2020 | 2020
70 |  | Lanie Patterson | Brent Brooks | 2019-09-09 | 2023-07-07 | wthdw | [29 empty] | 2 - PDRD |  | 262D1 | 13 | Yes | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2021-01-04 | Zach Schrowang | Syncarpha Solar LLC | READFIELD SOLAR 1 LLC | Main St / Readfield Me 04355 | 2000134234 | 30015302737 | Solar | 4950 | 4.95 | 6359 |  |  | 44.21 | -69.9156 | 368 Main St |  |  | Readfield | 142 | PUDDLEDOCK ROAD | 262D1 | 34.5 kV Bus |  | 9310-L0101-4910-0057-ED00046 | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Yes | Yes |  | K&L Engineering | Bruce Jagolinzer |  | 2019-09-13 | 2019-09-16 | 2019-09-23 | 2019-09-13 | 2019-09-20 | 2019-10-02 |  | 2019-10-17 |  | 2019-10-02 | 2019-10-02 | 2019-10-16 | [5 empty] | CS | 2019-11-14 | [6 empty] | CS |  |  | 2019-11-14 | [11 empty] | 2020-03-06 | [17 empty] | 2020-04-02 |  |  | 2023-07-14 |  |  |  | Yes |  |  |  |  | 2020-06-08 |  |  | 2021-06-21 | Addendum |  |  | 2020-06-08 |  |  |  | 2023-07-25 |  |  |  |  | 2020-05-28 |  |  |  | 2023-07-25 | [13 empty] | 2020-06-02 | [15 empty] | 2020-06-02 |  | 2020-06-03 | 2023-08-02 |  | 2023-08-04 | [7 empty] | 146351 | 2023-07-25 |  | 2020-06-17 | 2020-06-17 | 2021-07-01 | 2021-07-01 | 2023-08-04 | 2023-08-04 | [15 empty] | Q4 2020 |  |  |  | 10300681819 | [11 empty] | TRUE | TRUE | 70 | 2020-06-17 | 2020-06-17 | 2020 | 2020 | 2020 |  |  |  | 2021-06-21 | Addendum
71 |  | Lanie Patterson | Brent Brooks | 2019-09-09 | [31 empty] | 3 - PDRD |  | 262D1 | 70 |  | WITHDRAWN | WITHDRAWN |  | Xander Neve | Syncarpha Solar LLC | READFIELD SOLAR 2 LLC |  | 2000134235 | 30011945562 | Solar | [7 empty] | 368 Main St |  |  | Readfield |  | PUDDLEDOCK ROAD | 262D1 |  |  | 9310-L0101-4910-0057-ED00046 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2019-09-16 | 2019-09-23 |  |  |  |  | 1900-01-12 | [57 empty] | Yes | [69 empty] | 2020-07-01 | [37 empty] | TRUE | TRUE | 71 | 0 | 0 | 1900 | #VALUE! | #VALUE!
72 |  | Eben Snow | Brent Brooks | 2019-09-09 | [31 empty] | 2 - LEED |  | 471D2 | 68 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | David Kane | LongRoad Development Company LLC | MAINE DG HOLDINGS LLC | 394 Howes Corner Rd Leeds | 2000149310 | 30012250624 | Solar | [5 empty] | 44.3455 | -70.1468 | 394 Howes Rd |  |  | Leeds |  | LEEDS | 471D2 |  |  | 9310-L0210-3210-0034-ED00254 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2019-09-16 | 2019-09-23 |  |  |  |  | 1900-01-12 | [57 empty] | Yes | [69 empty] | 2021-08-03 | 2020-11-08: 2020-08-07; 2020-11-08: 2020-08-07 | [17 empty] | 10300701985 | [11 empty] | TRUE | TRUE | 72 | 2020-08-07 | 2020-08-07 | 2020 | 2020 | 2020
73 |  | Eben Snow | Brent Brooks | 2019-09-09 | [31 empty] | 3 - LEED |  | 471D2 | 72 |  | WITHDRAWN | WITHDRAWN |  | David Kane | LongRoad Development Company LLC | LONGROAD DEVELOPMENT COMPANY LLC | 394 Howes Rd-Prj Dead River 2 | 2000118100 | 30011699862 | Solar | [7 empty] | 394 Howes Rd |  |  | Leeds |  | LEEDS | 471D2 |  |  | 86-Withdrawn-86d | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2019-09-16 | 2019-09-23 |  |  |  |  | 1900-01-12 | [57 empty] | Yes | [69 empty] | 2020-08-19 | [37 empty] | TRUE | TRUE | 73 | 0 | 0 | 1900 | #VALUE! | #VALUE!
74 |  | Eben Snow | Brent Brooks | 2019-09-09 | [31 empty] | 1 - FRYE |  | 415D2 |  |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Nick Sampson | Dirigo/BNRG | BD SOLAR FRYEBURG LLC | Lyman Dr | 2000118434 | 30011704324 | Solar | [5 empty] | 43.8982 | -70.3424 | Lyman Dr |  |  | Fryeburg | 31 | FRYEBURG | 415D2 | 415T1 |  | 9310-L0132-2130-0073-ED00038 | Non-FERC | WITHDRAWN | WITHDRAWN | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-09-16 | 2019-09-16 | 2019-09-23 | 2019-09-16 | 2019-09-20 | 2019-10-04 |  | 2019-10-21 |  | 2019-10-04 | 2019-10-18 | 2019-10-04 | [5 empty] | CS | 2019-10-04 | [6 empty] | CS |  |  | 2019-10-04 | [29 empty] | 2020-03-31 | [6 empty] | Yes |  |  |  |  | 2020-06-04 |  |  | 2021-06-08 | Addendum |  |  | 2020-06-05 | [8 empty] | 2020-05-08 | [17 empty] | 2020-05-13 | [15 empty] | 2020-05-13 |  | 2020-05-14 | 2022-12-19 |  | 2022-12-19 | 2023-07-03 | 2023-07-10 |  |  |  | 246841 |  | 413701 | 2022-11-28 | 2025-05-14 | 2020-05-18 | 2020-05-18 | 2021-06-22 | 2021-06-22 | 2022-12-20 | 2022-12-20 |  |  |  |  | 2023-10-09 | 2023-10-10 | [9 empty] | Q4 2021 |  |  | TBD | 10300671523 | [11 empty] | TRUE | TRUE | 74 | 2020-05-18 | 2020-05-18 | 2020 | 2020 | 2020 |  |  |  | 2021-06-08 | Addendum
75 |  | Lanie Patterson | Brent Brooks | 2019-09-09 | [31 empty] | 2 - OAKL |  | 839D1 | 48 |  | WITHDRAWN | WITHDRAWN |  | Bob Patton | HEP | HEP ENERGY USA PROJECT DEVELOPMENT LLC | Webb Rd Waterville | 2000096395 | 30011743694 | Solar | [7 empty] | Webb Road (Transfer Station) |  |  | Waterville |  | OAKLAND | 839D1 |  |  | 86-Withdrawn-86d | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2019-09-16 | 2019-09-23 |  |  |  |  | 1900-01-12 | [57 empty] | Yes | [69 empty] | 2020-05-21 | [37 empty] | TRUE | TRUE | 75 | 0 | 0 | 1900 | #VALUE! | #VALUE!
76 |  | Marshall Ripley | Rick Duperre | 2019-09-09 | 2023-02-15 | L2_Bump | [29 empty] | 2 - FOHI |  | 624D2 | 32 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Bob Patton | HEP | HEP ENERGY USA PROJECT DEVELOPMENT LLC | Wescott Rd Gorham | 2000096395 | 30012660228 | Solar | [5 empty] | 43.4497 | -70.2958 | Wescott Road |  |  | Gorham | 16 | FORT HILL | 624D2 | 624T1 | 12.47 | 9310-L0251-2240-0125-ED00008 | Non-FERC | WITHDRAWN | WITHDRAWN | 325000 | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-09-16 | 2019-09-16 | 2019-09-23 | 2019-09-16 | 2019-09-20 | 2020-05-01 |  | 2020-05-15 |  | 2020-05-01 | 2020-05-01 | 2020-05-15 | [5 empty] | CS | 2020-05-20 | [6 empty] | CS |  |  | 2020-05-20 |  |  | 2023-02-22 | [8 empty] | 2020-06-15 |  |  | 2023-03-20 | [8 empty] | 2023-03-17 | [5 empty] | 2020-06-24 |  |  | 2023-03-23 |  |  |  | Yes |  |  |  |  | 2020-08-27 |  |  | 2021-05-25 | Addendum |  |  | 2020-08-27 |  |  | 2023-05-05 | [5 empty] | 2020-09-02 |  |  | 2023-05-05 | [8 empty] | 2023-05-15 | [5 empty] | 2020-09-08 |  |  | 2023-05-17 | [10 empty] | 2021-06-15 |  | 2020-09-17 |  | 2020-09-18 | 2022-11-30 | 2022-12-20 | [6 empty] | 518290 |  | 794155 | 2023-05-04 | 2024-08-09 | 2020-09-23 | 2020-09-23 | 2021-06-30 | 2021-06-30 | 2022-12-20 | 2022-12-21 | 2023-09-01 | 2023-09-01 | [17 empty] | 10300716697 | [11 empty] | TRUE | TRUE | 76 | 2020-09-23 | 2020-09-23 | 2020 | 2020 | 2020 | 44362 |  |  | 2021-05-25 | Addendum
77 |  | Eben Snow | Brent Brooks | 2019-09-09 | [31 empty] | 1 - BALD |  | 691D1 |  |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2020-07-14 | Chad Allen | LongRoad Development Company LLC | Maine DG Solar Baldwin, LLC | 418 Main Rt 113 West Baldwin | 2000149310 | 30013299745 | Solar | 4950 | 4.95 | 6316 |  |  | 44.2667 | -70.2815 | 418-420 ME-113 |  |  | Baldwin | 259 | BALDWIN | 691D1 | 691T1 |  | 9310-L0371-0360-0016-ED00208 | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-09-16 | 2019-09-16 | 2019-09-23 | 2019-09-16 | 2019-09-20 | 2019-09-27 |  | 2019-10-11 |  | 2019-09-27 | 2019-09-27 | 2019-10-11 | [5 empty] | CS | 2019-10-01 | [6 empty] | CS |  |  | 2019-10-01 | [11 empty] | 2019-10-18 | [17 empty] | 2019-10-18 | [6 empty] | Yes |  |  |  |  | 2019-12-20 |  |  | 2021-06-17 | Addendum |  |  | 2019-12-19 | [8 empty] | 2019-12-19 | [17 empty] | 2020-01-03 | [15 empty] | 2020-04-22 |  | 2020-04-23 | [13 empty] | 2020-11-08: 2020-04-29; 2020-11-08: 2020-04-29; 2021-08-03: 2021-06-18; 2021-09-15: 2021-06-18 | [13 empty] | Q4 2021 |  |  | TBD | 10300666873 | 10300797582 | [10 empty] | TRUE | TRUE | 77 | 2020-04-29 | 2020-04-29 | 2020 | 2020 | 2020 |  |  |  | 2021-06-17 13:43 | Addendum
78 |  | Marshall Ripley | Rick Duperre | 2019-09-10 | [31 empty] | 2 - DUNS |  | 617D2 | 27 |  | WITHDRAWN | WITHDRAWN |  | Christian Bain | BORREGO SOLAR SYSTEMS INC | 510 PV PROJECT DEVELOPMENT LLC | 1016 Portland Rd, Saco | 2000113260 |  | Solar/Battery | [7 empty] | 1016 Portland Road |  |  | Saco |  | DUNSTAN | 617D2 |  |  | 86-Withdrawn-86d | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2019-09-17 | 2019-09-24 |  |  |  |  | 1900-01-12 |  | 2019-09-30 | 2019-09-30 | [54 empty] | Yes | [69 empty] | 2020-02-13 | [37 empty] | TRUE | TRUE | 78 | 0 | 0 | 1900 | #VALUE! | #VALUE!
79 |  | Govinda Neupane |  | 2019-09-10 | 2022-09-09 | L2_Bump |  |  |  |  | 2023-10-06 | L2_Bump | [23 empty] | 1 - GUIL |  | 821D1 |  | Yes | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2020-04-10 | Nathan Curtis | C2 ENERGY DEVELOPMENT LLC | Parkman Solar DG LLC | 1 Checkline Rd 5mw | 2000206431 | 30013400368 | Solar | 4875 | 4.875 | 6713 |  |  | 43.9935 | -70.9446 | Checkline Rd |  |  | Parkman | 11 | GUILFORD | 821D1 | 821T1 | 12.47 | FLOC-MISSING-01142021 | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-09-17 | 2019-09-17 | 2019-09-24 | 2019-09-17 | 2019-09-23 | 2019-10-01 |  | 2019-10-16 |  | 2019-10-01 | 2019-10-01 | 2019-10-15 |  |  | 2019-10-08 |  |  | CS | 2019-10-08 | [6 empty] | CS |  |  | 2019-10-08 |  |  | 2022-09-13 | 2022-12-01 | 2023-10-06 | [6 empty] | 2019-10-11 |  |  |  |  | 2022-10-07 | [8 empty] | 2023-10-12 |  |  |  | 2019-10-11 |  |  | 2022-10-12 | 2022-12-20 | 2023-10-12 |  | Yes |  |  |  |  | 2019-12-13 |  |  | 2021-06-04 | Addendum |  |  | 2019-12-16 |  |  | 2022-11-23 |  | 2023-11-28 |  |  |  | 2019-12-16 |  |  |  |  | 2023-11-28 | [12 empty] | 2020-01-02 |  |  |  |  | 2023-12-08 | [7 empty] | 2023-12-08 |  |  | 2020-01-06 |  | 2020-01-09 | [8 empty] | 615022 |  | 1208600 | 2023-11-28 |  | 2020-01-15 | 2020-01-15 | 2020-09-17 | 2020-09-17 | 2021-07-15 | 2021-07-15 | 2024-02-28 | 2024-02-28 | [13 empty] | Q1 2022 |  |  | TBD | 10300642489 | [11 empty] | TRUE | TRUE | 79 | 2020-01-15 | 2020-01-15 | 2020 | 2020 | 2020 |  |  |  | 2021-06-04 | Addendum
80 |  | Lanie Patterson | Brent Brooks | 2019-09-10 | [31 empty] | 2 - DETR |  | 812D1 | 20 |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2020-06-25 | Liam McCormack | Summit Ridge Energy | SOMERSET SOLAR LLC | 510 Somerset Ave Pittsfield | 2000238960 | 30013417370 | Solar | 4980 | 4.98 | 6713 |  |  | 43.8075 | -70.7451 | 510 Somerset Ave | 510 | Somerset Ave | Pittsfield | 34 | DETROIT | 812D1 | 812T2 |  | 9310-L0392-4650 | Non-FERC | COST SHARE | COST SHARE ($250,000) | 126332 | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-09-17 | 2019-09-17 | 2019-09-24 | 2019-09-17 | 2019-09-23 | 2019-10-02 |  | 2019-10-17 |  | 2019-10-02 | 2019-10-02 | 2019-10-16 |  |  | 2019-10-02 |  |  | CS | 2019-10-02 | [6 empty] | CS |  |  | 2019-10-02 | [11 empty] | 2019-10-09 | [17 empty] | 2019-10-09 | [6 empty] | Yes |  |  |  |  | 2019-12-11 |  |  | 2021-06-11 | Addendum |  |  | 2019-12-12 | [8 empty] | 2019-12-17 | [17 empty] | 2020-01-03 | [15 empty] | 2020-04-13 |  | 2020-04-14 | [8 empty] | 178131 |  |  |  |  | 2020-01-15: 2020-05-11; 2020-01-15: 2020-05-11; 2020-09-17: 2021-09-10; 2020-09-17: 2021-09-17 | [13 empty] | Q4 2021 |  |  | TBD | 10300670658 | [11 empty] | TRUE | TRUE | 80 | 2020-05-11 | 2020-05-11 | 2020 | 2020 | 2020 |  |  |  | 2021-06-11 | Addendum
81 |  |  | Anthony Boucher | 2019-09-10 | [31 empty] | 1 - STCO |  | 245D2 |  |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2020-04-28 | Liam McCormack | Summit Ridge Energy | Waldoboro Solar LLC | 712 Waldoboro Rd / Washington Me 04 | 2000120852 | 30013492506 | Solar | 2000 | 2 | 2984 |  |  | 44.229 | -69.3881 | Ave, |  |  | Washington | 15 | STICKNEYS CORNER | 245D2 | 245T1 |  | 9310-L0080-6187-0007-ED00012 | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-09-17 | 2019-09-17 | 2019-09-24 | 2019-09-17 | 2019-09-23 | 2019-10-03 |  | 2019-10-18 |  | 2019-10-03 | 2019-10-03 | 2019-10-17 |  |  | 2019-10-17 |  |  | CS | 2019-10-21 | [6 empty] | CS |  |  | 2019-10-21 | [11 empty] | 2019-10-29 | [17 empty] | 2019-10-29 | [6 empty] | Yes |  |  |  |  | 2019-12-31 |  |  | 2021-06-04 | Addendum |  |  | 2019-12-24 | [8 empty] | 2019-12-24 | [17 empty] | 2020-01-07 | [14 empty] | 2021-06-14 | 2020-02-10 | 2021-08-16 | 2020-02-10 | [8 empty] | 25522 |  |  |  |  | 2020-01-15: 2020-02-25; 2020-01-15: 2020-02-25; 2020-09-17: 2021-08-17; 2020-09-17: 2021-08-17 | [13 empty] | Q1 2021 |  | 2021-08-19 | 2020-03-11 | 10300649511 | [9 empty] | Assignment |  | TRUE | TRUE | 81 | 2020-02-25 | 2020-02-25 | 2020 | 2020 | 2020 |  | 44361 | 44424 | 2021-06-04 | Addendum
82 |  | Lanie Patterson | Brent Brooks | 2019-09-10 | [31 empty] | 1 - RRPS |  | 873D1 |  |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2020-06-25 | Abby Broedlin | Nautilus US Power Holdco, LLC | Mavis Oakland LLC | 414 Fairfield St Oakland | 2000119525 | 30013492811 | Solar | 4990 | 4.99 | 6713 |  |  | 45.1574 | -69.3891 | 414 Fairfield St. |  |  | Oakland | 473 | COUNTY RD (RICE RIPS) | 873D1 | 873T1 | 34.5 | FLOC-MISSING-01142021 | Non-FERC | TRIGGERING | 260000 | 260000 | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-09-17 | 2019-09-17 | 2019-09-24 | 2019-09-17 | 2019-09-23 | 2019-10-04 |  | 2019-10-21 |  | 2019-10-04 | 2019-10-04 | 2019-10-18 |  |  | 2019-10-18 |  |  | CS | 2019-11-14 | [6 empty] | CS |  |  | 2019-11-14 | [11 empty] | 2019-12-05 | [17 empty] | 2019-12-05 | [6 empty] | Yes |  |  |  |  | 2020-02-10 |  |  | 2021-05-18 | Addendum |  |  | 2020-02-04 | [8 empty] | 2020-03-06 | [17 empty] | 2020-03-12 | [13 empty] | 2021-05-24 |  | 2020-03-13 | 2021-08-16 | 2020-03-18 | [8 empty] | 173641 |  |  |  |  | 2020-01-15: 2020-05-05; 2020-01-15: 2020-05-05; 2020-09-17: 2021-08-16; 2020-09-17: 2021-08-16 | [13 empty] | Q4 2021 |  |  | TBD | 10300657069 | [11 empty] | TRUE | TRUE | 82 | 2020-05-05 | 2020-05-05 | 2020 | 2020 | 2020 | 44340 |  | 44424 | 2021-05-18 | Addendum
83 |  | Govinda Neupane |  | 2019-09-10 | [31 empty] | 1 - WILT |  | 885D1 |  |  | WITHDRAWN | WITHDRAWN |  | Nick Mazuroski | Dirigo/BNRG | BD SOLAR WILTON LLC | 128 Weld Rd Wilton Solar 1999kw | 2000120694 | 30011739403 | Solar | [7 empty] | 158 Weld Rd |  |  | Wilton |  | WILTON | 885D1 |  |  | 86-Withdrawn-86d | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2019-09-17 | 2019-09-24 |  |  |  |  | 1900-01-12 | [57 empty] | Pending | [69 empty] | 2020-06-09 | [37 empty] | TRUE | TRUE | 83 | 0 | 0 | 1900 | #VALUE! | #VALUE!
84 |  | Eben Snow | Brent Brooks | 2019-09-10 | [31 empty] | 1 - BRID |  | 406D1 |  |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2020-07-14 | Abby Broedlin | Nautilus US Power Holdco, LLC | Mavis Solar North Bridgton LLC | 10 Chadbourne Hill Rd Bridgton | 2000120096 | 30014735317 | Solar | 4990 | 4.99 | 6725.16 |  |  | 44.0991 | -70.7052 | 38 Chadbourn Hill Rd |  |  | North Bridgton | 11 | BRIDGTON | 406D1 | 406T1 |  | 9310-L0118-0690-0017-ED00004 | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-09-17 | 2019-09-17 | 2019-09-24 | 2019-09-17 | 2019-09-23 | 2019-10-04 |  | 2019-10-21 |  | 2019-10-04 | 2019-10-04 | 2019-10-18 | [5 empty] | CS | 2019-11-14 | [6 empty] | CS |  |  | 2019-11-14 | [11 empty] | 2019-12-05 | [17 empty] | 2019-12-05 | [6 empty] | Yes |  |  |  |  | 2020-02-10 |  |  | 2021-07-20 | Addendum |  |  | 2020-02-04 | [8 empty] | 2020-02-06 | [17 empty] | 2020-02-11 | [13 empty] | 2021-07-20 |  | 2020-03-25 | 2021-08-16 | 2020-03-25 | [13 empty] | 2020-01-15: 2020-03-26; 2020-01-15: 2020-03-26; 2020-09-17: 2021-08-24; 2020-09-17: 2021-08-24 | [13 empty] | Q4 2021 |  |  | 2020-04-29 | 10300658837 | [11 empty] | TRUE | TRUE | 84 | 2020-03-26 | 2020-03-26 | 2020 | 2020 | 2020 | 44397 |  | 44424 | 2021-07-20 | Addendum
85 |  | Eben Snow | Brent Brooks | 2019-09-10 | [31 empty] | 2 - BALD |  | 691D1 | 77 |  | WITHDRAWN | WITHDRAWN |  | David Kane | LongRoad Development Company LLC | LONGROAD DEVELOPMENT COMPANY LLC | 418 Maine Rt113-Prj Baldwin 2 | 2000118100 | 30011700108 | Solar | [7 empty] | 418-420 ME-113 |  |  | Baldwin |  | BALDWIN | 691D1 |  |  | 9310-L0371-0360-0016-ED00208 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2019-09-17 | 2019-09-24 |  |  |  |  | 1900-01-12 | [57 empty] | No Study | [69 empty] | 2020-07-29 | [37 empty] | TRUE | TRUE | 85 | 0 | 0 | 1900 | #VALUE! | #VALUE!
86 |  | Eben Snow | Brent Brooks | 2019-09-10 | [31 empty] | 1 - BR34 |  | 406D4 |  |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Brent Buchberger | Summit Ridge Energy | Naples PV LLC | 1412 Roosevelt Tr Naples | 2000149310 | 30012361892 | Solar | [5 empty] | 43.9792 | -70.6256 | 11 Dees Way |  |  | Naples | 2 1 | BRIDGTON 34 KV | 406D4 | 34kV Bus at substation |  | 9310-L0476-4040-0078-ED00046 | Non-FERC | WITHDRAWN | WITHDRAWN | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-09-17 | 2019-09-17 | 2019-09-24 | 2019-09-17 | 2019-09-23 | 2020-04-08 |  | 2020-04-23 |  | 2020-04-08 | 2020-04-08 | 2020-04-23 | [5 empty] | FS | 2020-04-15 | IS | 2020-06-05 |  |  |  |  | Split | [13 empty] | 2020-04-15 | 2020-06-05 | [15 empty] | 2020-04-17 | 2020-06-10 | [7 empty] | Yes |  |  | 2020-05-26 | 2020-07-23 |  |  |  | 2021-05-21 | Addendum | 2020-05-26 | 2020-07-23 | [7 empty] | 2020-05-26 | 2020-07-01 | [16 empty] | 2020-05-28 | 2020-07-20 | [6 empty] | 2020-05-28 | 2020-07-20 | [6 empty] | 2021-06-14 |  | 2020-07-22 |  | 2020-07-22 |  |  |  | 2023-07-03 | 2023-07-10 |  |  |  | 260899 |  | 145715 | 2023-09-12 | 2023-10-09 | 2020-01-15: 2020-07-24; 2020-01-15: 2020-07-24; 2020-09-17: 2021-06-24; 2020-09-17: 2021-06-24 | [17 empty] | 10300696470 | [11 empty] | TRUE | TRUE | 86 | 2020-07-24 | 2020-07-24 | 2020 | 2020 | 2020 | 44361 |  |  | 2021-05-21 | Addendum
87 |  | Govinda Neupane |  | 2019-09-11 | [31 empty] | 1 - BNHE |  | 120D1 |  |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED |  | Denise Murillo | Atlus Power LLC | BD SOLAR DAVES WAY LLC | Daves Wy, Hermon | 2000121583 | 30011751085 | Solar | 4990 | 4.99 | 6713 |  |  | 44.7748 | -68.8772 | Daves Way |  |  | Hermon | 13 | BANGOR HYDRO (Versant) | 120D1 | Not Applicable |  | FLOC-MISSING-01142021 | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-09-23 | 2019-09-18 | 2019-09-25 | 2019-09-23 | 2019-09-24 | 2020-03-12 |  | 2020-03-26 |  | 2020-03-12 | 2020-03-12 | 2020-03-26 |  |  |  | 2021-08-18 |  | CS | 2020-03-04 | RS | 2021-08-18 |  |  |  |  | CS |  |  | 2020-03-04 | 2021-08-18 | [10 empty] | 2020-03-05 | [17 empty] | 2020-03-10 | 2021-08-23 | [5 empty] | Yes |  |  |  |  | 2020-05-13 | 2021-10-05 | [5 empty] | 2020-05-13 | 2021-09-16 | [7 empty] | 2020-05-15 | 2021-09-03 | [16 empty] | 2020-05-26 | 2021-09-24 |  |  |  |  | 2020-05-28 | 2020-07-20 | 2021-09-24 | [5 empty] | 2021-05-24 | 2021-05-24 | 2021-11-17 |  | 2021-11-17 | 2022-11-01 | [7 empty] | 355755 |  | 995364 | 2022-11-01 |  | 2020-01-15: 2021-11-30; 2020-01-15: 2021-12-01 | [13 empty] | Q4 2021 |  |  |  | Requested | [11 empty] | TRUE | TRUE | 87 | 2021-11-30 | 2021-11-30 | 2021 | 2021 | 2021 | 44340 | 44340
88 |  | Eben Snow | Brent Brooks | 2019-09-13 | [31 empty] | 1 - TUTP |  | 467D1 |  |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Christian Bain | Greenbacker Capital | Beals Pond Solar 1, LLC |  | 2000113260 | 30011687982 | Solar/Battery | [5 empty] | 44.2726 | -70.2688 | 0 Beals Pond Rd |  |  | Turner | 12 | TURNER TAP | 467D1 | Tap off of Transmission Line |  | 9310-L0206-5880-0067-ED00071 | Non-FERC | WITHDRAWN | WITHDRAWN | NONE | Under Review 1/31/2020 |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-09-23 | 2019-09-20 | 2019-09-27 | 2019-09-23 | 2019-09-24 | 2019-10-08 |  | 2019-10-23 |  | 2019-10-08 | 2019-10-08 | 2019-10-22 | [5 empty] | CS | 2019-10-08 | [6 empty] | CS |  |  | 2019-10-08 | [11 empty] | 2020-01-30 | [17 empty] | 2020-01-30 | [6 empty] | Yes |  |  |  |  | 2020-04-03 | [6 empty] | 2020-04-06 | [8 empty] | 2020-03-18 | [17 empty] | 2020-03-25 | [15 empty] | 2020-03-18 |  | 2020-03-19 |  |  |  | 2023-07-17 | 2023-07-17 | [7 empty] | 2025-04-15 | 2020-01-15: 2020-03-26; 2020-01-15: 2020-03-26; 2020-09-17: 2021-07-20; 2020-09-17: 2021-07-20 |  |  | 2023-08-16 | 2023-08-16 | [9 empty] | Q2 2021 |  |  | 43920 | 10300657524 | [11 empty] | TRUE | TRUE | 88 | 2020-03-26 | 2020-03-26 | 2020 | 2020 | 2020
89 |  | Lanie Patterson | Brent Brooks | 2019-09-13 | [31 empty] | 1 - MONM |  | 457D1 |  |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2020-06-25 | Chad Allen | LongRoad Development Company LLC | MAINE DG SOLAR MONMOUTH LLC | 547 Ridge Rd Corner 1, Monmouth | 2000149310 | 30013299786 | Solar | 4950 | 4.95 | 6316 |  |  | 44.1858 | -70.0222 | Ridge Rd |  |  | Monmouth | 4 | MONMOUTH | 457D1 | 457T1 |  | 9310-L0198-3747-0009-ED00002 | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-09-23 | 2019-09-20 | 2019-09-27 | 2019-09-23 | 2019-09-24 | 2019-10-08 |  | 2019-10-23 |  | 2019-10-08 | 2019-10-08 | 2019-10-22 | [5 empty] | CS | 2019-10-09 | [6 empty] | CS |  |  | 2019-10-09 | [11 empty] | 2019-10-29 | [17 empty] | 2019-10-29 | [6 empty] | Yes |  |  |  |  | 2019-12-31 |  |  | 2021-05-24 | Addendum |  |  | 2020-01-02 | [8 empty] | 2020-01-02 | [17 empty] | 2020-01-08 | [13 empty] | 2021-06-10 |  | 2020-02-20 |  | 2020-02-20 | [8 empty] | 688618 |  |  |  |  | 2020-01-15: 2020-03-23; 2020-01-15: 2020-03-23; 2020-09-17: 2021-06-09; 2020-09-17: 2021-06-09 | [16 empty] | 43916 | 10300655761 | [11 empty] | TRUE | TRUE | 89 | 2020-03-23 | 2020-03-23 | 2020 | 2020 | 2020 | 44357 |  |  | 2021-05-24 | Addendum
90 |  | Eben Snow | Brent Brooks | 2019-09-16 | [31 empty] | 2 - KIRD |  | 423D1 | 43 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Lara Bushwood | Pine Gate Renewables LLC | Moose Solar, LLC. | Kimball Rd, Harrison | 2000213784 | 30013069288 | Solar | [5 empty] | 45.3158 | -69.2056 | Kimball Road |  |  | Harrison | 5 2 | KIMBALL ROAD | 423D1 | 423T2 |  | 9310-L0147-2520-0039-ED00034 | Non-FERC | WITHDRAWN | WITHDRAWN | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-09-23 | 2019-09-23 | 2019-09-30 | 2019-09-23 | 2019-09-24 | 2020-02-06 |  | 2020-02-21 |  | 2020-02-06 | 2020-02-06 | 2020-02-21 | [5 empty] | CS | 2020-02-06 | [6 empty] | CS |  |  | 2020-02-06 | [11 empty] | 2020-01-30 | [17 empty] | 2020-02-19 | [6 empty] | Yes |  |  |  |  | 2020-04-23 |  |  | 2021-05-20 | Addendum |  |  | 2020-04-23 | [8 empty] | 2020-04-03 | [17 empty] | 2020-04-09 | [13 empty] | 2021-06-09 |  | 2020-04-03 |  | 2020-04-06 | 2022-06-03 |  |  | 2023-07-03 | 2023-07-10 |  |  |  | 36835 |  | 95327 | 2023-09-12 | 2023-07-25 | 2020-01-15: 2020-04-14; 2020-01-15: 2020-04-14; 2020-09-17: 2022-06-08; 2020-09-17: 2022-06-09 | [16 empty] | TBD | 10300660990 | [11 empty] | TRUE | TRUE | 90 | 2020-04-14 | 2020-04-14 | 2020 | 2020 | 2020 | 44356 |  |  | 2021-05-20 | Addendum
91 |  | Marshall Ripley | Rick Duperre | 2019-09-16 | [31 empty] | 6 - BONE |  | 610D2 | 67 |  | WITHDRAWN | WITHDRAWN |  | Lara Bushwood | Pine Gate Renewables LLC | Sea Dog Solar Facility | Cape Rd, Standish | 2000123038 | 30013022923 | Solar | [5 empty] | 43.7086 | -70.5993 | Cape Road |  |  | Standish |  | BONNY EAGLE | 610D2 |  |  | FLOC-MISSING-01142021 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2019-09-23 | 2019-09-30 |  |  |  |  | 1900-01-12 | [127 empty] | 2021-07-20 | [25 empty] | PENDING | [11 empty] | TRUE | TRUE | 91 | 0 | 0 | 1900 | #VALUE! | #VALUE!
92 |  | Lanie Patterson | Brent Brooks | 2019-09-16 | 2023-07-07 | wthdw |  |  |  |  | 2025-09-19 | L2_With | [23 empty] | 4 - PDRD | 1 - PDRD | 262D1 | 71 | Yes | EXECUTED | EXECUTED |  | Kelsey Haley | New Leaf Energy, Inc | 510 PV PROJECT DEVELOPMENT LLC | 0 Readfield Rd Manchester | 2000113260 | 30011688915 | Solar | 998 | 0.999 | 1755 |  |  | 44.3459 | -69.8705 | Readfield Rd |  |  | Manchester | 52.H | PUDDLEDOCK ROAD | 262D1 | 34.5 kV Bus |  | 9310-L0101-3540-0076-ED00082 | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Under Review 1/31/2020 |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-09-23 | 2019-09-23 | 2019-09-30 | 2019-09-23 | 2019-09-24 | 2020-08-28 |  | 2020-09-14 |  | 2020-08-28 | 2020-08-28 | 2020-09-14 |  |  |  | 2023-11-07 |  | CS | 2020-09-15 | [6 empty] | CS |  |  | 2020-09-15 | 2023-11-08 |  | 2023-08-07 | 2025-10-23 |  |  |  |  | 2023-11-10 |  |  |  | 2023-11-27 |  | 2023-08-22 | 2025-10-30 | [5 empty] | 2023-11-28 |  | 2023-09-11 | 2025-10-30 |  |  |  |  | 2020-09-17 | 2023-11-30 |  | 2023-09-11 | 2025-10-30 |  |  | Pending |  |  |  |  | 2020-11-20 | 2024-01-16 |  | 2021-06-21 | Addendum |  |  | 2020-11-23 | 2024-01-15 |  | 2023-10-24 | 2026-01-07 |  |  |  |  | 2020-11-24 | 2024-01-16 |  | 2023-10-24 | 2026-01-07 | [5 empty] | 2023-01-17 |  |  | 2026-01-22 |  |  |  |  | 2020-11-30 | 2024-01-23 |  |  | 2026-01-23 |  |  |  | 2020-11-30 | 2024-01-23 |  |  | 2026-01-23 |  |  |  | 2021-01-12 |  |  | 2024-02-13 |  | 2024-02-28 | [5 empty] | 191185 |  | 248890 | 2026-01-07 |  | 2021-01-12 | 2021-01-12 | 2021-07-06 | 2021-07-06 | 2024-02-29 | 2024-02-29 |  |  |  |  | 2026-03-18 | 2026-03-18 | [9 empty] | Q3 2026 |  |  |  | 10300602459 | [11 empty] | FALSE | TRUE | 92 | 2021-01-12 | 2021-01-12 | 2021 | 2021 | 2021 |  |  |  | 2021-06-21 | Addendum
93 |  |  | KRISTOFER COLEMAN | 2019-09-17 | [31 empty] | 1 - MAYA |  | 274D1 |  |  | WITHDRAWN | WITHDRAWN |  | Mike Imoto | MEVS LLC AKA CENERGY | MEVS WISCASSET LLC | 96 Chewonki Neck Rd P1 Wiscasset | 2000151041 | 30012199912 | Solar | [7 empty] | 96 Chewonki Neck Road #1 |  |  | Wiscasset |  | MAINE YANKEE | 274D1 |  |  | 9310-L0111-6463-0034-ED00083 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2019-09-24 | 2019-10-01 |  |  |  |  | 1900-01-12 | [57 empty] | Yes | [69 empty] | 2021-04-29 | [25 empty] | 10300673566 | [11 empty] | TRUE | TRUE | 93 | 0 | 0 | 1900 | 1900 | 1900
94 |  |  |  | 2019-09-17 | [31 empty] | 1 - AGK5 |  | 200D2 |  |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2020-04-28 | Jason Masilla | Syncarpha Capital, LLC | RIVERSIDE SOLAR LLC | RIVERSIDE SOLAR LLC / NEW YORK NY 10107-0799 | 2000122868 | 30011769681 | Solar | 4988 | 4.988 | 6680 |  |  | 44.334 | -69.7605 | Route 3 |  |  | Augusta | 6 | AUGUSTA K5 | 200D2 | 200T1 |  | 9310-L0014-0240-0013-ED00209 | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-09-24 | 2019-09-24 | 2019-10-01 | 2019-09-24 | 2019-10-01 | 2019-10-09 |  | 2019-10-24 |  | 2019-10-09 | 2019-10-09 | 2019-10-23 |  |  | 2019-10-09 |  |  | CS | 2019-10-09 | [6 empty] | CS |  |  | 2019-10-09 | [11 empty] | 2019-10-11 | [17 empty] | 2019-10-11 | [6 empty] | Yes |  |  |  |  | 2019-12-13 |  |  | 2021-06-08 | Addendum |  |  | 2019-12-16 | [8 empty] | 2019-12-17 | [17 empty] | 2020-01-02 | [15 empty] | 2020-01-06 |  | 2020-01-06 | [8 empty] | 33022 |  |  |  |  | 2020-01-15: 2020-01-28; 2020-01-15: 2020-01-28 | [13 empty] | Q4 2020 |  |  | 43872 | 10300805260 | [11 empty] | TRUE | TRUE | 94 | 2020-01-28 | 2020-01-28 | 2020 | 2020 | 2020 |  |  |  | 2021-06-08 | Addendum
95 |  | Lanie Patterson | Brent Brooks | 2019-09-17 | [31 empty] | 1 - MANC |  | 233D1 |  |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2021-01-04 | David Gomez | AES Clean Energy | Treasure Lane Solar 1, LLC | 0 Treasure Ln Manchester | 2000113260 | 30014011727 | Solar | 4500 | 4.5 | 6122 |  |  | 44.3351 | -69.8398 | Treasure Ln |  |  | Manchester | 32 | MANCHESTER | 233D1 | 233T1 |  | 9310-L0064-3540-0068-ED00050 | Non-FERC | TRIGGERING | TRIGGERING (325,000) | 195888 | Under Review 1/31/2020 |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-09-24 | 2019-09-24 | 2019-10-01 | 2019-09-24 | 2019-10-01 | 2019-10-31 |  | 2019-11-15 |  | 2019-10-31 | 2019-10-11 | 2019-10-25 |  |  | 2019-10-25 |  |  | CS | 2019-10-31 | [6 empty] | CS |  |  | 2019-10-31 | [11 empty] | 2020-01-30 | [17 empty] | 2020-01-30 | [6 empty] | Yes |  |  |  |  | 2020-04-03 |  |  | 2021-06-03 | Addendum |  |  | 2020-04-06 | [8 empty] | 2020-04-03 | [17 empty] | 2020-04-08 | [15 empty] | 2021-06-04 |  | 2020-04-13 | [8 empty] | 599717 |  |  |  |  | 2020-01-15: 2020-04-14; 2020-01-15: 2020-04-14; 2020-09-17: 2021-06-16; 2020-09-17: 2021-06-16 | [13 empty] | Q4 2021 |  | 2021-11-18 | 43955 | 10300662289 | [11 empty] | TRUE | TRUE | 95 | 2020-04-14 | 2020-04-14 | 2020 | 2020 | 2020 |  |  |  | 2021-06-03 | Addendum
96 |  | Eben Snow | Brent Brooks | 2019-09-18 | [31 empty] | 2 - FRYT |  | 405D1 | 49 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Todd Fryatt | ECA Solar | ECA Maine Fry LLC | W. Fryeburg Rd Map 017 Lot024 Fryeb | 2000119658 | 30011727606 | Solar | [5 empty] | 44.701 | -70.9752 | 0 West Fryeburg Rd |  |  | Fryeburg | 123 | FRYEBURG TAP | 405D1 | 405T1 |  | 9310-L0116-2130-0097-ED00030 | Non-FERC | WITHDRAWN | WITHDRAWN | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-09-24 | 2019-09-25 | 2019-10-02 | 2019-09-24 | 2019-10-01 | 2020-03-23 |  | 2020-04-06 |  | 2020-03-23 | 2020-03-23 | 2020-04-06 |  |  | 2020-04-03 | 2020-07-10 |  | CS | 2020-04-03 | RS | 2020-07-10 |  |  |  |  | CS |  |  | 2020-04-03 | 2020-07-10 | [10 empty] | 2020-04-03 | [17 empty] | 2020-04-03 | 2020-08-13 | [5 empty] | Yes |  |  |  |  | 2020-06-09 | [6 empty] | 2020-06-09 | [8 empty] | 2020-06-09 | 2020-09-25 | [16 empty] | 2020-06-16 | 2020-09-28 | [14 empty] | 2020-09-28 |  | 2020-09-30 |  |  |  | 2023-07-03 | 2023-07-10 |  |  |  | 285516 | 2021-07-16 |  |  | 2024-09-30 | 2020-01-15: 2020-10-19; 2020-01-15: 2020-10-19; 2020-09-17: 2021-08-30; 2020-09-17: 2021-10-15 |  |  | 2023-10-10 | 2023-10-11 | [13 empty] | 10300718417 | [11 empty] | TRUE | TRUE | 96 | 2020-10-19 | 2020-10-19 | 2020 | 2020 | 2020
97 |  | Rigel Paradise | Rick Duperre | 2019-09-18 | [31 empty] | 2 - LEBA |  | 695D2 | 52 |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2022-06-27 | Jacob Fraatz | Dimension Renewable Energy | LEBANON CSG LLC | 429 W Lebanon Rd #1 / Lebanon | 2000155076 | 30012262694 | Solar | 2000 | 2 | 2771 |  |  | 43.3746 | -70.9417 | 429 W Lebanon Rd |  |  | Lebanon | 4 | LEBANON | 695D2 | 695T1 |  | 9310-L0473-3190-0007-ED00083 | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-09-24 | 2019-09-25 | 2019-10-02 | 2019-09-24 | 2019-10-02 | 2019-11-18 |  | 2019-12-04 |  | 2019-11-18 | 2019-11-18 | 2019-12-02 |  |  | 2019-12-02 |  |  | CS | 2020-03-06 | [6 empty] | CS |  |  | 2020-03-06 | [11 empty] | 2020-03-09 | [17 empty] | 2020-04-08 | [6 empty] | Yes |  |  |  |  | 2020-06-12 |  |  | 2021-06-30 | Addendum |  |  | 2020-06-11 | [8 empty] | 2020-06-12 | [17 empty] | 2020-06-18 | [14 empty] | 2022-06-15 | 2020-06-18 |  | 2020-06-19 | [13 empty] | 2020-01-15: 2020-07-01; 2020-01-15: 2020-07-01 | [13 empty] | Q2 2022 |  |  |  | 10300686682 | [9 empty] | 7/1/2020 combo 97&98 |  | TRUE | TRUE | 97 | 2020-07-01 | 2020-07-01 | 2020 | 2020 | 2020 |  |  |  | 2021-06-30 | Addendum
98 |  | Rigel Paradise | Rick Duperre | 2019-09-18 | [31 empty] | 3 - LEBA |  | 695D2 | 97 |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2022-06-27 | Jacob Fraatz | Dimension Renewable Energy | LEBANON CSG LLC | 429 W Lebanon Rd #2 / Lebanon | 2000155076 | 30012262694 | Solar | 1750 | 1.75 | 2241.28 |  |  | 43.3746 | -70.9417 | 429 W Lebanon Rd |  |  | Lebanon | 4 | LEBANON | 695D2 | 695T1 |  | 9310-L0473-3190-0007-ED00083 | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | [7 empty] | 2019-09-25 | 2019-10-02 |  |  | 2019-11-18 |  | 2019-12-04 |  | 2019-11-18 | 2019-11-18 | 2019-12-02 |  |  | 2019-12-02 |  |  | CS | 2020-03-06 | [6 empty] | CS |  |  | 2020-03-06 | [11 empty] | 2020-03-09 | [17 empty] | 2020-04-08 | [6 empty] | Yes |  |  |  |  | 2020-06-12 |  |  | 2021-06-30 | Addendum |  |  | 2020-06-11 | [8 empty] | 2020-06-12 | [17 empty] | 2020-06-18 | [14 empty] | 2022-06-15 | 2020-06-18 |  | 2020-06-19 | [13 empty] | 2020-01-15: 2020-07-01; 2020-01-15: 2020-07-01 | [13 empty] | Q2 2022 |  |  |  | 10300686682 | [9 empty] | 7/1/2020 combo 97&98 |  | TRUE | TRUE | 98 | 2020-07-01 | 2020-07-01 | 2020 | 2020 | 2020 |  |  |  | 2021-06-30 | Addendum
99 |  | Eben Snow | Brent Brooks | 2019-09-19 | [31 empty] | 2 - TUTP |  | 467D1 | 88 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Jamal Batar | Dimension Renewable Energy | TURNER CSG LLC | 1393 Auburn Rd # 1 / Turner Me | 2000155079 | 30012262835 | Solar | [5 empty] | 44.2723 | -70.2691 | 1393 Auburn Rd |  |  | Turner | 6 | TURNER TAP | 467D1 | Tap off of Transmission Line |  | 9310-L0206-5880-0067-ED00264 | Non-FERC | WITHDRAWN | WITHDRAWN | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-09-24 | 2019-09-26 | 2019-10-03 | 2019-09-24 | 2019-10-02 | 2020-04-14 |  | 2020-04-29 |  | 2020-04-14 | 2020-04-14 | 2020-04-29 |  |  | 2020-04-24 | 2020-05-14 |  | CS | 2020-04-24 | RS | 2020-05-14 |  |  |  |  | CS |  |  | 2020-04-24 | 2020-05-14 | [10 empty] | 2020-05-28 | [17 empty] | 2020-05-28 | [6 empty] | Yes |  |  |  |  | 2020-07-31 | [6 empty] | 2020-07-30 | [8 empty] | 2020-08-04 | [17 empty] | 2020-08-05 | [15 empty] | 2020-08-05 | 2021-07-27 | 2020-08-05 | [12 empty] | 2024-10-18 | 2020-01-15: 2020-08-07; 2020-01-15: 2020-08-07; 2020-09-17: 2021-07-27; 2020-09-17: 2021-09-23 | [17 empty] | 10300701154 | [9 empty] | 8/7/2020 combo 99&100 |  | TRUE | TRUE | 99 | 2020-08-07 | 2020-08-07 | 2020 | 2020 | 2020 |  |  | 44404
100 |  | Eben Snow | Brent Brooks | 2019-09-19 | [31 empty] | 3 - TUTP |  | 467D1 | 99 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Jamal Batar | Dimension Renewable Energy | TURNER CSG LLC | 1393 Auburn Rd # 2 / Turner Me | 2000155079 | 30012262835 | Solar | [5 empty] | 44.2723 | -70.2691 | 1393 Auburn Rd |  |  | Turner | 6 | TURNER TAP | 467D1 | Tap off of Transmission Line |  | 9310-L0206-5880-0067-ED00264 | Non-FERC | WITHDRAWN | WITHDRAWN | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-09-24 | 2019-09-26 | 2019-10-03 | 2019-09-24 | 2019-10-02 | 2020-04-21 |  | 2020-05-05 |  | 2020-04-21 | 2020-04-21 | 2020-05-05 |  |  | 2020-05-05 |  |  | CS | 2020-05-14 | [6 empty] | CS |  |  | 2020-05-14 | [11 empty] | 2020-05-28 | [17 empty] | 2020-05-28 | [6 empty] | Yes |  |  |  |  | 2020-07-31 | [6 empty] | 2020-07-30 | [8 empty] | 2020-08-04 | [17 empty] | 2020-08-05 | [15 empty] | 2020-08-05 | 2021-07-27 | 2020-08-05 | [12 empty] | 2024-10-18 | 2020-01-15: 2020-08-07; 2020-01-15: 2020-08-07; 2020-09-17: 2021-07-27; 2020-09-17: 2021-09-23 | [17 empty] | 10300701154 | [9 empty] | 8/7/2020 combo 99&100 |  | TRUE | TRUE | 100 | 2020-08-07 | 2020-08-07 | 2020 | 2020 | 2020 |  |  | 44404
101 |  | Rigel Paradise | Rick Duperre | 2019-09-19 | [31 empty] | 1 - LIME | 1 - LIME | 632D1 |  |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED |  | Jacob Fraatz | Dimension Renewable Energy | LIMERICK CSG LLC | 170 Burnham Rd # 1 / Limerick | 2000155082 | 30012262892 | Solar | 2000 | 2 | 3270.44 |  |  | 43.6839 | -70.7755 | 170 Burnham Rd |  |  | Limerick | 513 | LIMERICK | 632D1 | 632T1 |  | 9310-L0263-3260-0155-ED00076 | FERC | TRIGGERING | TRIGGERING (325,000) combined w/106 | 72707 | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-09-24 | 2019-09-26 | 2019-10-03 | 2019-09-24 | 2019-10-02 | 2019-10-11 |  | 2019-10-28 |  | 2019-10-11 | 2019-10-11 | 2019-10-25 |  |  | 2019-10-25 |  |  | CS | 2020-01-30 | [6 empty] | CS |  |  | 2020-01-30 | [11 empty] | 2020-02-03 | [17 empty] | 2020-02-10 | [6 empty] | Yes |  |  |  |  | 2020-04-14 |  |  | 2021-06-03 | Addendum |  |  | 2020-04-15 | [8 empty] | 2020-04-08 | [17 empty] | 2020-04-13 | [13 empty] | 2021-06-09 |  | 2020-04-08 |  | 2020-04-09 |  |  |  | 2023-07-03 | 2023-07-10 |  |  |  | 134808.5 |  | 252618 | 2023-03-07 |  | 2020-01-15: 2020-05-06; 2020-01-15: 2020-05-06; 2020-09-17: 2021-06-24; 2020-09-17: 2021-06-24 |  |  | 2023-10-05 | 2023-10-05 | [9 empty] | Q1 2028 |  |  | TBD | 10300678732 | [9 empty] | 5/6/20 combo w PRJ 106 |  | TRUE | TRUE | 101 | 2020-05-06 | 2020-05-06 | 2020 | 2020 | 2020 | 44356 |  |  | 2021-06-03 | Addendum
102 |  |  | Anthony Boucher | 2019-09-19 | [31 empty] | 2 - STCO |  | 245D1 | 81 |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2020-10-05 | Abby Broedlin | Nautilus US Power Holdco, LLC | Washington WS03 LLC | Ws03 Waldoboro Rd Washington | 2000186833 | 30013327991 | Solar | 4000 | 4 | 7000 |  |  | 44.2392 | -69.3816 | Waldoboro Rd |  |  | Washington | 2 | STICKNEYS CORNER | 245D1 | 245T1 |  | 9310-L0079-6180-0042-ED00046 | Non-FERC | TRIGGERING | TRIGGERING | 325000 | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-09-24 | 2019-09-26 | 2019-10-03 | 2019-09-24 | 2019-10-02 | 2020-03-16 |  | 2020-03-30 |  | 2020-03-16 | 2020-03-17 | 2020-03-31 |  |  | 2020-03-31 |  |  | CS | 2020-04-10 | [6 empty] | CS |  |  | 2020-04-10 | [11 empty] | 2020-04-07 | [17 empty] | 2020-04-16 | [6 empty] | Yes |  |  |  |  | 2020-06-22 |  |  | 2021-06-08 | Addendum |  |  | 2020-06-18 | [8 empty] | 2020-06-18 | [17 empty] | 2020-06-24 | [15 empty] | 2020-06-29 |  | 2020-06-29 | [8 empty] | 493335 |  |  |  |  | 2020-01-15: 2020-07-02; 2020-01-15: 2020-07-02; 2020-09-17: 2021-07-13; 2020-09-17: 2021-07-13 | [17 empty] | 10300686701 | 10300808784 | [10 empty] | TRUE | TRUE | 102 | 2020-07-02 | 2020-07-02 | 2020 | 2020 | 2020 |  |  |  | 2021-06-08 | Addendum
103 |  | Rigel Paradise | Rick Duperre | 2019-09-19 | [31 empty] | 2 - LOUD |  | 633D1 | 44 |  | WITHDRAWN | WITHDRAWN |  | James Marshall | Turning Point Energy | TPE DEVELOPMENT LLC | Sc03 571 Boom Rd Saco | 2000123236 | 30011775209 | Solar | [7 empty] | Boom Rd |  |  | Saco |  | LOUDEN | 633D1 |  |  | 9310-L0265-5090-0022-ED00141 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2019-09-26 | 2019-10-03 |  |  |  |  | 1900-01-12 | [57 empty] | Yes | [69 empty] | 2020-01-10 | [37 empty] | TRUE | TRUE | 103 | 0 | 0 | 1900 | #VALUE! | #VALUE!
104 |  | Eben Snow | Brent Brooks | 2019-09-19 | [31 empty] | 2 - CROW |  | 411D1 | 45 |  | WITHDRAWN | WITHDRAWN |  | James Marshall | Turning Point Energy | TPE DEVELOPMENT LLC | Oo01 Ross Rd Old Orchard Beach | 2000123236 |  | Solar | [7 empty] | Ross Road |  |  | Old Orchard Beach |  | CROWLEYS | 411D1 |  |  | 86-Withdrawn-86d | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2019-09-26 | 2019-10-03 |  |  |  |  | 1900-01-12 | [57 empty] | Pending | [69 empty] | 2020-01-13 | [37 empty] | TRUE | TRUE | 104 | 0 | 0 | 1900 | #VALUE! | #VALUE!
105 |  | Govinda Neupane |  | 2019-09-19 | [31 empty] | 2 - NEWP |  | 837D2 | 22 |  | WITHDRAWN | WITHDRAWN |  | James Marshall | Turning Point Energy | TPE DEVELOPMENT LLC | Ne02 445 Elm St Newport | 2000123236 | 30011775233 | Solar | [7 empty] | Elm Street |  |  | Newport |  | NEWPORT | 837D2 |  |  | 86-Withdrawn-86d | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2019-09-26 | 2019-10-03 |  |  |  |  | 1900-01-12 | [57 empty] | Pending | [69 empty] | 2019-10-19 | [37 empty] | TRUE | TRUE | 105 | 0 | 0 | 1900 | #VALUE! | #VALUE!
106 |  | Rigel Paradise | Rick Duperre | 2019-09-19 | [31 empty] | 2 - LIME | 2 - LIME | 632D1 | 101 |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED |  | Jacob Fraatz | Dimension Renewable Energy | LIMERICK CSG LLC | 170 Burnham Rd # 1 / Limerick | 2000155082 | 30012262892 | Solar | 2000 | 2 | 2770.56 |  |  | 43.6839 | -70.7755 | 170 Burnham Rd |  |  | Limerick | 513 | LIMERICK | 632D1 | 632T1 |  | 9310-L0263-3260-0155-ED00076 | FERC | COST SHARE | COST SHARE (325,000) combined w/101 | 72707 |  |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-09-24 | 2019-09-26 | 2019-10-03 | 2019-09-24 | 2019-10-02 | 2020-01-15 |  | 2020-01-30 |  | 2020-01-15 | 2020-01-15 | 2020-01-30 | [5 empty] | CS | 2020-01-30 | [6 empty] | CS |  |  | 2020-01-30 | [11 empty] | 2020-02-03 | [17 empty] | 2020-02-10 | [6 empty] | Yes |  |  |  |  | 2020-04-14 |  |  | 2021-06-03 | Addendum |  |  | 2020-04-15 | [8 empty] | 2020-04-08 | [17 empty] | 2020-04-13 | [15 empty] | 2020-04-08 |  | 2020-04-09 |  |  |  | 2023-07-03 | 2023-07-10 |  |  |  | 134808.5 |  |  |  |  | 2020-01-15: 2020-05-06; 2020-01-15: 2020-05-06; 2020-09-17: 2021-06-24; 2020-09-17: 2021-06-24 | [13 empty] | Q1 2028 |  |  | TBD | 10300678732 | [9 empty] | 5/6/20 combo w PRJ 101 |  | TRUE | TRUE | 106 | 2020-05-06 | 2020-05-06 | 2020 | 2020 | 2020 |  |  |  | 2021-06-03 | Addendum
107 |  | Govinda Neupane |  | 2019-09-19 | [31 empty] | 1 - LVFA |  | 428D3 |  |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2020-06-25 | Tyler William Perkins | Nexamp, Inc | LIVERMORE FALLS CSG LLC | 166 Moose Hill Rd / Livermore | 2000155089 | 30012263049 | Solar | 2000 | 2.5 | 2771 |  |  | 44.4797 | -70.1701 | 71 Turmel Rd |  |  | Jay | 5 | LIVERMORE FALLS | 428D3 | 428T1 |  | 9310-L0263-3260-0155-ED00076 | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-09-24 | 2019-09-26 | 2019-10-03 | 2019-09-24 | 2019-10-02 | 2019-10-11 |  | 2019-10-28 |  | 2019-10-11 | 2019-10-11 | 2019-10-25 | [5 empty] | CS | 2020-02-03 | [6 empty] | CS |  |  | 2020-02-03 | [11 empty] | 2020-02-03 | [17 empty] | 2020-02-07 | [6 empty] | Yes |  |  |  |  | 2020-04-13 | [6 empty] | 2020-04-14 | [8 empty] | 2020-04-08 | [8 empty] | 2020-04-08 | [8 empty] | 2020-04-16 | [7 empty] | 2020-04-16 | [7 empty] | 2020-04-08 |  | 2020-04-10 | [10 empty] | 36835 | 2021-04-29 |  | 2020-01-15: 2020-04-28; 2020-01-15: 2020-04-28; 2020-09-17: 2021-11-16; 2020-09-17: 2022-01-17 | [13 empty] | Q4 2021 |  |  | TBD | 10300678745 | [9 empty] | 4/28/20 combo w PRJ 108 |  | TRUE | TRUE | 107 | 2020-04-28 | 2020-04-28 | 2020 | 2020 | 2020
108 |  | Govinda Neupane |  | 2019-09-19 | [31 empty] | 2 - LVFA |  | 428D3 | 107 |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2020-06-25 | Tyler William Perkins | Nexamp, Inc | LIVERMORE FALLS CSG LLC | 166 Moose Hill Rd / Livermore | 2000155089 | 30012263049 | Solar | 1250 | 1.25 | 1620 |  |  | 44.4797 | -70.1701 | 71 Turmel Rd |  |  | Jay | 5 | LIVERMORE FALLS | 428D3 | 428T1 |  | 9310-L0263-3260-0155-ED00076 | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-09-24 | 2019-09-26 | 2019-10-03 | 2019-09-24 | 2019-10-02 | 2019-10-11 |  | 2019-10-28 |  | 2019-10-11 | 2019-10-11 | 2019-10-25 | [5 empty] | CS | 2020-02-03 | [6 empty] | CS |  |  | 2020-02-03 | [11 empty] | 2020-02-03 | [17 empty] | 2020-02-07 | [6 empty] | Yes |  |  |  |  | 2020-04-13 | [6 empty] | 2020-04-14 | [8 empty] | 2020-04-08 | [17 empty] | 2020-04-16 | [15 empty] | 2020-04-08 |  | 2020-04-10 | [13 empty] | 2020-01-15: 2020-04-28; 2020-01-15: 2020-04-28; 2020-09-17: 2021-11-16; 2020-09-17: 2022-01-17 | [13 empty] | Q4 2021 |  |  | TBD | 10300678745 | [9 empty] | 4/28/20 combo w PRJ 107 |  | TRUE | TRUE | 108 | 2020-04-28 | 2020-04-28 | 2020 | 2020 | 2020
109 |  | Eben Snow | Brent Brooks | 2019-09-20 | [31 empty] | 8 - HORD |  | 420D6 | 58 |  | WITHDRAWN | WITHDRAWN |  | James Marshall | Turning Point Energy | TPE DEVELOPMENT LLC | Au07 16 Danville Corner Auburn | 2000123236 | 30011774897 | Solar | [7 empty] | Danville Corner |  |  | Auburn |  | HOTEL ROAD | 420D6 |  |  | 9310-SS40420-017 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2019-09-27 | 2019-10-04 |  |  |  |  | 1900-01-12 | [57 empty] | Pending | [69 empty] | 2020-01-09 | [37 empty] | TRUE | TRUE | 109 | 0 | 0 | 1900 | #VALUE! | #VALUE!
110 |  | Rigel Paradise | Rick Duperre | 2019-10-31 | [31 empty] | 1 - BASS |  | 602D3 |  |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2020-07-14 | Tyler William Perkins | Nexamp, Inc | TPE ME NB11 LLC | 35 Coffin Ln (Nb 11) No Berwick | 2000123236 | 30012600612 | Solar | 4950 | 4.95 | 7000 |  |  | 43.2773 | -70.7645 | 35 Coffin Rd |  |  | North Berwick | 51 | BASSETT | 602D3 | 602T1 |  | 9310-L0212-4160-0025-ED00073 | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-11-05 | 2019-11-07 | 2019-11-15 | 2019-11-05 | 2019-11-06 | 2019-11-22 |  | 2019-12-10 |  | 2019-11-22 | 2019-11-22 | 2019-12-06 | [5 empty] | CS | 2020-01-27 | [6 empty] | CS |  |  | 2020-01-27 | [11 empty] | 2020-01-30 | [17 empty] | 2020-01-30 | [6 empty] | Yes |  |  |  |  | 2020-04-03 | [6 empty] | 2020-04-06 | [8 empty] | 2020-04-06 | [17 empty] | 2020-04-10 | [15 empty] | 2020-04-06 | 2021-07-26 | 2020-04-06 | [13 empty] | 2020-01-15: 2020-04-13; 2020-01-15: 2020-04-13; 2020-09-17: 2021-07-21; 2020-09-17: 2021-07-21 | [16 empty] | TBD | 10300660953 | [11 empty] | TRUE | TRUE | 110 | 2020-04-13 | 2020-04-13 | 2020 | 2020 | 2020 |  |  | 44403
111 |  |  | KRISTOFER COLEMAN | 2019-09-20 | [31 empty] | 1 - BRWE |  | 213D3 |  |  | WITHDRAWN | WITHDRAWN |  | James Marshall | Turning Point Energy | TPE DEVELOPMENT LLC | Br03 339 River Rd Brunswick | 2000123236 | 30011775043 | Solar | [7 empty] | River Rd |  |  | Brunswick |  | BRUNSWICK WEST SIDE | 213D3 |  |  | 9310-L0032-0770-0288-ED00207 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2019-09-27 | 2019-10-04 |  |  |  |  | 1900-01-12 | [127 empty] | 2020-04-13 | [37 empty] | TRUE | TRUE | 111 | 0 | 0 | 1900 | #VALUE! | #VALUE!
112 |  | Rigel Paradise | Rick Duperre | 2019-09-20 | [31 empty] | 3 - PRAT |  | 661D1 | 19 |  | WITHDRAWN | WITHDRAWN |  | James Marshall | Turning Point Energy | TPE DEVELOPMENT LLC | Nb06 134 Elm St N Berwick | 2000123236 | 30011775050 | Solar | [7 empty] | 134 Elm Street |  |  | Berwick |  | PRATT & WHITNEY | 661D1 |  |  | 9310-L0329-4160-0060-ED00051 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2019-09-27 | 2019-10-04 |  |  |  |  | 1900-01-12 | [57 empty] | Pending | [69 empty] | 2020-05-05 | [37 empty] | TRUE | TRUE | 112 | 0 | 0 | 1900 | #VALUE! | #VALUE!
113 |  | Govinda Neupane |  | 2019-09-20 | [31 empty] | 3 - NEWP |  | 837D2 | 105 |  | WITHDRAWN | WITHDRAWN |  | James Marshall | Turning Point Energy | TPE DEVELOPMENT LLC | Ne01 Ridge Rd Newport | 2000123236 | 30011775068 | Solar | [7 empty] | Ridge Road |  |  | Newport |  | NEWPORT | 837D2 |  |  | 86-Withdrawn-86d | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2019-09-27 | 2019-10-04 |  |  |  |  | 1900-01-12 | [127 empty] | 2020-04-06 | [37 empty] | TRUE | TRUE | 113 | 0 | 0 | 1900 | #VALUE! | #VALUE!
114 |  | Eben Snow | Brent Brooks | 2019-09-20 | [31 empty] | 3 - CROW |  | 411D1 | 104 |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED |  | Liam McCormack | Summit Ridge Energy | Crowley Solar LLC | 303 Crowley St Sabattus | 2000120852 | 30013492548 | Solar | 2000 | 2 | 2866 |  |  | 44.744 | -70.1137 | 308 Crowley Road |  |  | Sabattus | 1 | CROWLEYS | 411D1 | 411T2 |  | FLOC-MISSING-01142021 | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-09-26 | 2019-09-27 | 2019-10-04 | 2019-09-26 | 2019-10-02 | 2020-01-14 |  | 2020-01-29 |  | 2020-01-14 | 2020-01-14 | 2020-01-29 |  |  | 2020-01-29 |  |  | CS | 2020-02-11 | [6 empty] | CS |  |  | 2020-02-11 | [11 empty] | 2020-02-13 | [17 empty] | 2020-02-18 | [6 empty] | Yes |  |  |  |  | 2020-04-22 |  |  | 2021-06-17 | Addendum |  |  | 2020-04-22 | [8 empty] | 2020-04-01 | [17 empty] | 2020-04-08 | [15 empty] | 2020-04-10 | 2021-08-16 | 2020-04-11 |  |  |  | 2023-03-29 | 2023-03-29 |  |  |  | 36835 | 2021-06-14 |  |  |  | 2020-01-15: 2020-04-14; 2020-01-15: 2020-04-14; 2020-09-17: 2021-08-17; 2020-09-17: 2021-08-17 | [13 empty] | Q2 2021 |  | 2021-08-19 | 43942 | 10300662630 | [9 empty] | Assignment |  | TRUE | TRUE | 114 | 2020-04-14 | 2020-04-14 | 2020 | 2020 | 2020 |  |  | 44424 | 2021-06-17 17:16 | Addendum
115 |  | Rigel Paradise | Rick Duperre | 2019-09-20 | [31 empty] | 1 - FAIS |  | 621D1 |  |  | WITHDRAWN | WITHDRAWN |  | James Marshall | Turning Point Energy | TPE DEVELOPMENT LLC | Sb01 Webster Corner Sabattus | 2000123236 | 30011775217 | Solar | [7 empty] | Webster Corner |  |  | Sabattus |  | FACTORY ISLAND | 621D1 |  |  | 86-Withdrawn-86d | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2019-09-27 | 2019-10-04 |  |  |  |  | 1900-01-12 | [57 empty] | Pending | [69 empty] | 2019-10-24 | [37 empty] | TRUE | TRUE | 115 | 0 | 0 | 1900 | #VALUE! | #VALUE!
116 |  | Lanie Patterson | Brent Brooks | 2019-09-23 | [31 empty] | 2 - WINT |  | 256D3 | 61 |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2021-01-04 | Tyler William Perkins | Nexamp, Inc | MARINER SOLAR LLC | Maranacook Rd, Winthrop | 2000200481 | 30012898729 | Solar | 2500 | 2.5 | 3557 |  |  | 44.3429 | -69.9736 | Maranacook Road |  |  | Winthrop | 11 | WINTHROP | 256D3 | 256T1 |  | 9310-L0097-6450-0101-ED00008 | Non-FERC | TRIGGERING | TRIGGERING ($330,000) | 237410 | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-09-26 | 2019-09-30 | 2019-10-07 | 2019-09-26 | 2019-10-02 | 2020-04-09 |  | 2020-04-24 |  | 2020-04-09 | 2020-04-09 | 2020-04-24 | [5 empty] | CS | 2020-04-22 | [6 empty] | CS |  |  | 2020-04-22 | [11 empty] | 2020-04-27 | [17 empty] | 2020-04-29 | [6 empty] | Yes |  |  |  |  | 2020-07-02 |  |  | 2021-06-09 | Addendum |  |  | 2020-07-02 | [8 empty] | 2020-07-06 | [17 empty] | 2020-07-14 | [13 empty] | 2021-06-23 |  | 2020-09-01 |  | 2020-09-02 | [8 empty] | 610296 |  |  |  |  | 2020-01-15: 2020-09-29; 2020-01-15: 2020-09-29; 2020-09-17: 2021-06-30; 2020-09-17: 2021-06-30 | [13 empty] | Q3 2021 |  |  |  | 10300708466 | [11 empty] | TRUE | TRUE | 116 | 2020-09-29 | 2020-09-29 | 2020 | 2020 | 2020 | 44370 |  |  | 2021-06-09 | Addendum
117 |  | Govinda Neupane |  | 2019-09-23 | 2022-09-09 | L2_Bump |  | 2022-12-01 | L2_Bump |  | 2023-10-06 | L2_Bump |  | 2023-12-06 | L2_Bump | [20 empty] | 2 - GUIL |  | 821D3 | 79 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Nathan Curtis | C2 ENERGY DEVELOPMENT LLC | C2 PARKMAN SOLAR LLC | 1 Checkline Rd 14 Mw | 2000237740 | 30013400624 | Solar | [5 empty] | 45.1574 | -69.3891 | 369 ME 150 |  |  | Parkman | 6 | GUILFORD | 821D3 | 821T2 |  | FLOC-MISSING-01142021 | Non-FERC | WITHDRAWN | WITHDRAWN | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-09-26 | 2019-09-30 | 2019-10-07 | 2019-09-26 | 2019-10-02 | 2020-01-23 |  | 2020-02-06 |  | 2020-01-23 | 2020-01-23 | 2020-02-06 | [5 empty] | CS | 2020-01-27 | [6 empty] | CS |  |  | 2020-01-27 |  |  | 2023-01-17 | [8 empty] | 2020-01-30 | [11 empty] | 2023-03-31 | [5 empty] | 2020-02-04 |  |  | 2023-03-31 |  |  |  | Pending |  |  |  |  | 2020-04-08 |  |  | 2021-05-25 | Addendum |  |  | 2020-04-08 |  |  | 2023-05-15 | [5 empty] | 2020-04-08 |  |  | 2023-05-15 | [8 empty] | 2023-05-24 | [5 empty] | 2020-04-17 |  |  | 2023-05-30 | [10 empty] | 2021-06-10 |  | 2020-04-28 |  | 2020-06-01 | [8 empty] | 1160607 |  | 834326 | 2023-05-25 | 2024-12-16 | 2020-07-13 | 2020-07-13 | 2021-07-15 | 2021-07-15 | 2023-07-19 | 2023-02-21 | [19 empty] | 10300690159 | 10300605837 | [10 empty] | TRUE | TRUE | 117 | 2020-07-13 | 2020-07-13 | 2020 | 2020 | 2020 | 44357 |  |  | 2021-05-25 | Addendum
118 |  | Govinda Neupane |  | 2019-09-23 | [31 empty] | 1 - WYHY |  | 872D1 |  |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2020-06-25 | Mike Imoto | MEVS LLC AKA CENERGY | MEVS CLARK LLC | Sw Nichols Corner Rd Hwy Bingham | 2000151042 | 30012199920 | Solar | 4950 | 4.95 | 7007 |  |  | 45.065 | -69.8839 | Corner of Nichols Hills Rd and Hwy 201 |  |  | Bingham | 5 | WYMAN HYDRO | 872D1 | 872T11 |  | FLOC-MISSING-01142021 | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-10-01 | 2019-09-30 | 2019-10-07 | 2019-10-01 | 2019-10-02 | 2019-10-17 |  | 2019-10-31 |  | 2019-10-17 | 2019-10-17 | 2019-10-31 | [5 empty] | CS | 2019-11-12 | [6 empty] | CS |  |  | 2019-11-12 | [11 empty] | 2019-11-18 | [17 empty] | 2019-11-18 | [6 empty] | Yes |  |  |  |  | 2020-01-22 | [6 empty] | 2020-01-27 | [8 empty] | 2020-01-29 | [17 empty] | 2020-02-04 | [15 empty] | 2020-02-24 | 2021-07-28 | 2020-02-25 | [13 empty] | 2020-01-15: 2020-03-26; 2020-01-15: 2020-03-26; 2020-09-17: 2021-07-28; 2020-09-17: 2021-09-15 | [13 empty] | Q3 2021 |  |  | TBD | 10300676406 | [11 empty] | TRUE | TRUE | 118 | 2020-03-26 | 2020-03-26 | 2020 | 2020 | 2020 |  |  | 44405
119 |  |  | Anthony Boucher | 2019-09-23 | [31 empty] | 1 - BUCK |  | 806D2 |  |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2020-04-28 | Tyler William Perkins | Nexamp, Inc | FRONT RIDGE ROAD SOLAR 1 LLC | 267 Front Ridge Rd Orland | 2000113260 | 30012421340 | Solar/Battery | 4990 | 4.99 | 6954 |  | 4990 | 44.5536 | -68.6944 | 267 Front Ridge Rd |  |  | Orland | 2 | BUCKSPORT | 806D2 | 806T3 |  | 9310-L0386-4330-0004-ED00006 | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-10-09 | 2019-09-30 | 2019-10-07 | 2019-10-09 | 2019-10-07 | 2019-10-17 |  | 2019-10-31 |  | 2019-10-17 | 2019-10-17 | 2019-10-31 | [5 empty] | CS | 2019-10-31 | [6 empty] | CS |  |  | 2019-10-31 | [11 empty] | 2019-11-18 | [17 empty] | 2019-11-18 | [6 empty] | Yes |  |  |  |  | 2020-01-22 |  |  | 2021-05-18 | Addendum |  |  | 2020-01-27 | [8 empty] | 2020-01-28 | [31 empty] | 2021-05-19 |  | 2020-01-28 |  | 2020-01-29 | [8 empty] | 165118 |  | 168215 | 2023-01-18 |  | 2020-01-15: 2020-03-02; 2020-01-15: 2020-03-02; 2020-09-17: 2021-06-17; 2020-09-17: 2021-06-17 | [13 empty] | Q2 2021 |  |  | 43906 | 10300653653 | [11 empty] | TRUE | TRUE | 119 | 2020-03-02 | 2020-03-02 | 2020 | 2020 | 2020 | 44335 |  |  | 2021-05-18 | Addendum
120 |  | Lanie Patterson | Brent Brooks | 2019-09-23 | [31 empty] | 1 - BURN |  | 807D1 |  |  | WITHDRAWN | WITHDRAWN |  | Bruce Metrick | CIANBRO CORP | CIANBRO CORP | 411 Webb Rd Pittsfield Me | 2800436517 | 30011765630 | Solar | [7 empty] | 411 Webb Rd |  |  | Pittsfield |  | BURNHAM | 807D1 |  |  | 9310-L0112-0120-0002-ED00187 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2019-09-30 | 2019-10-07 |  |  |  |  | 1900-01-12 | [57 empty] | Pending | [69 empty] | 2021-04-27 | [37 empty] | TRUE | TRUE | 120 | 0 | 0 | 1900 | #VALUE! | #VALUE!
121 |  | Eben Snow | Brent Brooks | 2019-09-24 | [31 empty] | 3 - KIRD |  | 423D1 | 90 |  | WITHDRAWN | WITHDRAWN |  | Eric Weinstein | BORREGO SOLAR SYSTEMS INC | 510 PV PROJECT DEVELOPMENT LLC | 518 Norway Rd Harrison | 2000113260 |  | Solar/Battery | [7 empty] | 518 Norway Rd |  |  | Harrison |  | KIMBALL ROAD | 423D1 |  |  | 9310-L0112-0120-0023-ED00056 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2019-10-01 | 2019-10-08 |  |  |  |  | 1900-01-12 | [57 empty] | Pending | [69 empty] | 2020-05-20 | [37 empty] | TRUE | TRUE | 121 | 0 | 0 | 1900 | #VALUE! | #VALUE!
122 |  |  | Anthony Boucher | 2019-09-24 | [31 empty] | 1 - WALD |  | 252D2 |  |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2020-06-25 | Scott Moore | SunRaise Investments LLC | NORTH NOBLEBORO ROAD WALDOBORO SOLAR LLC | 475 N Nobleboro Rd Waldoboro | 2000155370 | 30012267289 | Solar | 2500 | 2.5 | 6000 |  |  | 44.1307 | -69.4225 | 475 North Nobleboro Rd |  |  | Waldoboro | 46 | WALDOBORO | 252D2 | 252T1 |  | 9310-L0114-0485-0116-ED00086 | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-10-01 | 2019-10-01 | 2019-10-08 | 2019-10-01 | 2019-10-02 | 2019-10-22 |  | 2019-11-05 |  | 2019-10-22 | 2019-10-23 | 2019-11-06 | 2019-11-05 |  |  | 2020-03-05 |  | CS | 2019-11-05 |  |  | RS | 2020-03-05 |  |  | CS | 2019-11-05 | 2020-02-14 |  | 2020-03-05 | [9 empty] | 2019-11-12 | 2020-02-14 | 2020-02-14 | [14 empty] | 2019-11-12 | 2020-02-27 |  | 2020-03-12 | [5 empty] | Yes |  |  | 2019-12-17 | 2020-04-10 |  | 2020-04-24 |  |  |  | 2019-12-16 |  |  | 2020-04-27 | [7 empty] | 2020-12-16 | 2020-04-17 | [16 empty] | 2019-12-16 | 2020-04-23 | [6 empty] | 2019-12-16 | 2020-04-23 | [6 empty] | 2020-04-23 |  | 2020-04-28 | [13 empty] | 2020-01-15: 2020-04-29; 2020-01-15: 2020-04-29 | [13 empty] | Q4 2020 |  |  | TBD | 10300666136 | [11 empty] | TRUE | TRUE | 122 | 2020-04-29 | 2020-04-29 | 2020 | 2020 | 2020
123 |  | Lanie Patterson | Brent Brooks | 2019-09-24 | [31 empty] | 2 - BLRD |  | 207D2 | 4 |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2021-01-04 | Scott Moore | SunRaise Investments LLC | CHURCH HILL ROAD AUGUSTA SOLAR LLC | 823 Church Hill Rd Augusta | 2000155364 | 30012267214 | Solar/Battery | 3750 | 3.75 | 6000 | 2000 |  | 44.3704 | -69.7083 | 823 Church Hill Road |  |  | Augusta | 12 | BLAIR ROAD | 207D2 | 207T1 |  | 9310-L0123-3230-0086-ED00003 | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-10-01 | 2019-10-01 | 2019-10-08 | 2019-10-01 | 2019-10-03 | 2019-10-22 |  | 2019-11-05 |  | 2019-10-22 | 2019-10-23 | 2019-11-06 | [5 empty] | FS | 2019-11-05 | IS | 2020-12-16 | RS |  |  |  | Split | 2019-11-05 | 2019-12-16 |  | 2020-03-11 | [9 empty] | 2019-11-12 | 2019-12-27 | 2020-03-27 | [14 empty] | 2019-11-12 | 2019-12-27 |  | 2020-03-30 | [5 empty] | Yes |  |  | 2019-12-17 | 2020-02-11 |  | 2020-05-12 |  |  |  | 2019-12-16 | 2020-01-28 |  | 2020-05-12 | [5 empty] | 2019-12-16 | 2020-01-28 |  | 2020-04-17 | [14 empty] | 2019-12-16 | 2020-02-17 |  | 2020-04-23 |  |  |  |  | 2019-12-16 | 2020-02-17 | [8 empty] | 2020-04-23 |  | 2020-04-27 | [13 empty] | 2020-01-15: 2020-04-28; 2020-01-15: 2020-04-28; 2020-09-17: 2021-09-15; 2020-09-17: 2021-09-15 | [13 empty] | Q4 2020 |  |  | TBD | 10300666190 | [11 empty] | TRUE | TRUE | 123 | 2020-04-28 | 2020-04-28 | 2020 | 2020 | 2020
124 |  | Lanie Patterson | Brent Brooks | 2019-09-24 | [31 empty] | 1 - SOCH |  | 244D1 |  |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2020-06-25 | Scott Moore | SunRaise Investments LLC | ROUTE 32 CHINA SOLAR LLC | 233 Windsor Rd, China | 2000149090 | 30012170582 | Solar | 4875 | 4.875 | 6000 |  |  | 44.3798 | -69.5773 | 233 Windsor Road |  |  | China | 21 | SOUTH CHINA | 244D1 | 244T1 |  | 9310-L0123-3230-0225-ED00095 | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-10-01 | 2019-10-01 | 2019-10-08 | 2019-10-01 | 2019-10-03 | 2019-10-22 |  | 2019-11-05 |  | 2019-10-22 | 2019-10-23 | 2019-11-06 |  |  |  | 2020-03-11 |  | CS | 2019-11-04 | RS | 2020-03-11 |  |  |  |  | CS |  |  | 2019-11-04 | 2020-03-11 | [10 empty] | 2019-11-12 | 2020-03-27 | [16 empty] | 2019-11-12 | 2020-03-30 | [5 empty] | Yes |  |  |  |  | 2020-01-15 | 2020-05-12 |  | 2021-05-21 | Addendum |  |  | 2019-01-21 | 2020-04-16 | [7 empty] | 2020-01-22 | 2020-04-16 | [16 empty] | 2020-02-13 | 2020-04-22 | [12 empty] | 2021-06-15 |  | 2020-04-22 |  | 2020-04-23 | [8 empty] | 466531 |  |  |  |  | 2020-01-15: 2020-04-23; 2020-01-15: 2020-04-23 | [13 empty] | Q4 2020 |  |  | 43963 | 10300664752 | [11 empty] | TRUE | TRUE | 124 | 2020-04-23 | 2020-04-23 | 2020 | 2020 | 2020 | 44362 |  |  | 2021-05-21 | Addendum
125 |  | Lanie Patterson | Brent Brooks | 2019-09-25 | [31 empty] | 1 - NOAU |  | 272D6 |  |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2020-07-30 | Chad Allen | LongRoad Development Company LLC | MAINE DG SOLAR AUGUSTA LLC | 859 Civic Center Dr Augusta | 2000149310 | 30013299497 | Solar | 2475 | 2.475 | 3158 |  |  | 44.23 | -69.8025 | Civic Center Drive |  |  | Augusta | 622 | NORTH AUGUSTA | 272D6 | 272T2 |  | 9310-L0123-3230-0297-ED00024 | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-10-01 | 2019-10-02 | 2019-10-09 | 2019-10-01 | 2019-10-03 | 2019-10-24 |  | 2019-11-07 |  | 2019-10-24 | 2019-10-24 | 2019-11-07 |  |  |  | 2020-03-11 |  | CS | 2019-10-24 | RS | 2020-03-11 |  |  |  |  | CS |  |  | 2019-10-24 | 2020-03-11 | [10 empty] | 2019-10-31 | [17 empty] | 2019-10-31 | 2020-04-09 | [5 empty] | Yes |  |  |  |  | 2020-01-03 | 2020-05-22 |  | 2021-05-20 | Addendum |  |  | 2019-01-10 | 2020-05-19 | [7 empty] | 2019-01-10 | 2020-05-10 | [16 empty] | 2020-01-16 | 2020-05-12 | [12 empty] | 2021-05-24 |  | 2020-05-14 |  | 2020-05-15 |  | 2020-06-03 | [6 empty] | 215054 |  |  |  |  | 2020-01-15: 2020-06-04; 2020-01-15: 2020-06-04; 2020-09-17: 2021-06-08; 2020-09-17: 2021-06-08 | [13 empty] | Q2 2021 |  |  | TBD | 10300681937 | [11 empty] | TRUE | TRUE | 125 | 2020-06-04 | 2020-06-04 | 2020 | 2020 | 2020 | 44340 |  |  | 2021-05-20 | Addendum
126 |  |  | Anthony Boucher | 2019-09-26 | [31 empty] | 2 - THCR |  | 246D3 | 36 |  | WITHDRAWN | WITHDRAWN |  | James Marshall | Turning Point Energy | TPE DEVELOPMENT LLC | Wr01 Beechwood Rd, Warren | 2000123236 | 30011801385 | Solar | [7 empty] | Beechwood Road |  |  | Warren |  | THOMASTON CREEK | 246D3 |  |  | 9310-L0123-3230-0297-ED00042 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2019-10-03 | 2019-10-10 |  |  |  |  | 1900-01-12 | [127 empty] | 2020-04-29 | [37 empty] | TRUE | TRUE | 126 | 0 | 0 | 1900 | #VALUE! | #VALUE!
127 |  |  |  | 2019-09-26 | [31 empty] | 1 - SWRD |  | 682D1/D2 |  |  | WITHDRAWN | WITHDRAWN |  | James Marshall | Turning Point Energy | TPE DEVELOPMENT LLC | Wh03 Swett Rd, Windham | 2000123236 | 30011801377 | Solar | [7 empty] | Swett Road |  |  | Windham |  | SWETT ROAD | 682D1/D2 |  |  | 9310-L0123-6230-0042-ED00024 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2019-10-03 | 2019-10-10 |  |  |  |  | 1900-01-12 | [127 empty] | 2020-04-14 | [37 empty] | TRUE | TRUE | 127 | 0 | 0 | 1900 | #VALUE! | #VALUE!
128 |  | Lanie Patterson | Brent Brooks | 2019-09-26 | [31 empty] | 1 - RICH |  | 240D1 |  |  | WITHDRAWN | WITHDRAWN |  | James Marshall | Turning Point Energy | TPE DEVELOPMENT LLC | Ri01 Alexander Reed Rd, Richmond | 2000123236 | 30011801369 | Solar | [7 empty] | Alexander Reed Road |  |  | Richmond |  | RICHMOND | 240D1 |  |  | 9310-L0125-0230-0257-ED00053 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2019-10-03 | 2019-10-10 |  |  |  |  | 1900-01-12 | [127 empty] | 2020-01-09 | [37 empty] | TRUE | TRUE | 128 | 0 | 0 | 1900 | #VALUE! | #VALUE!
129 |  | Govinda Neupane |  | 2019-09-26 | 2023-04-07 | L2_Bump |  |  |  |  | 2023-08-14 | L2_bump |  | 2023-09-14 | L2_Bump | [20 empty] | 4 - NEWP |  | 837D2 | 113 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | James Marshall | Turning Point Energy | TPE ME NE05 LLC | Ne05 Ridge Rd / Newport Me 04953 | 2000123236 | 30011801351 | Solar | [5 empty] | 44.8172 | -69.2604 | Ridge Road |  |  | Newport | 14 | NEWPORT | 837D2 | 837T2 | 12.47 | 9310-L0127-0230-0382-ED00032 | Non-FERC | WITHDRAWN | WITHDRAWN | 325000 | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-10-03 | 2019-10-03 | 2019-10-10 | 2019-10-03 | 2019-10-03 | 2020-04-16 |  | 2020-05-01 |  | 2020-04-16 | 2020-04-16 | 2020-05-01 |  |  | 2020-04-23 |  |  | CS | 2020-04-23 | RS | [5 empty] | CS |  |  | 2020-04-23 |  |  | 2023-04-10 | 2023-09-14 | [7 empty] | 2020-04-07 |  |  | 2023-04-17 | 2023-09-06 | [7 empty] | 2023-04-29 | 2023-10-03 |  |  |  |  | 2020-04-24 | 2020-04-24 |  | 2023-05-03 | 2023-10-05 |  |  | Yes |  |  |  |  | 2020-06-29 | 2020-06-08 |  | 2021-06-03 | Addendum |  |  | 2020-06-29 | 2020-06-29 |  | 2023-06-15 | 2023-11-20 |  |  |  |  | 2020-07-08 |  |  | 2023-06-16 | 2023-11-20 | [7 empty] | 2023-07-06 | 2023-11-22 |  |  |  |  | 2020-07-15 |  |  |  | 2023-12-07 | [7 empty] | 2023-12-07 |  |  |  | 2020-07-15 |  | 2020-07-15 | 2023-07-31 |  | 2023-07-31 | [5 empty] | 487912 |  | 164709 | 2023-11-16 | 2024-02-26 | 2020-07-16 | 2020-07-16 | 2021-06-04 | 2021-06-04 | 2023-08-01 | 2023-08-03 | [19 empty] | 10300691536 | [11 empty] | TRUE | TRUE | 129 | 2020-07-16 | 2020-07-16 | 2020 | 2020 | 2020 |  |  |  | 2021-06-03 | Addendum
130 |  | Eben Snow | Brent Brooks | 2019-09-26 | [31 empty] | 3 - BALD |  | 691D1 | 85 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Jack Kenworthy | Walden Renewables | WALDEN SOLAR MAINE VI LLC | Rte 113 Solar Farm (Baldwin) | 2000124175 | 30011789358 | Solar | [5 empty] | 43.8078 | -70.7273 | State Route 113 |  |  | Baldwin | 230 | BALDWIN | 691D1 | 691T1 |  | 9310-L0127-5880-0001-ED00075 | Non-FERC | WITHDRAWN | WITHDRAWN | 330000 | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-10-02 | 2019-10-03 | 2019-10-10 | 2019-10-02 | 2019-10-02 | 2020-08-04 |  | 2020-08-18 |  | 2020-08-04 | 2020-08-04 | 2020-08-18 |  |  | 2020-08-17 |  |  | CS | 2020-08-17 | [6 empty] | CS |  |  | 2020-08-17 | [11 empty] | 2020-08-17 | [17 empty] | 2020-08-18 | [6 empty] | Pending |  |  |  |  | 2020-10-22 |  |  | 2021-05-18 | Addendum |  |  | 2020-10-22 | [8 empty] | 2020-10-23 | [17 empty] | 2020-10-27 | [7 empty] | 2020-10-28 | [5 empty] | 2021-05-27 |  | 2020-11-05 | 2021-05-20 | 2020-11-05 | [8 empty] | 494055 |  |  |  | 2023-06-16 | 2020-01-15: 2021-05-24; 2020-01-15: 2021-05-24 | [17 empty] | 10300745084 | 10300787973 | [10 empty] | TRUE | TRUE | 130 | 2021-05-24 | 2021-05-24 | 2021 | 2021 | 2021 | 44343 |  | 44336 | 2021-05-18 | Addendum
131 |  | Lanie Patterson | Brent Brooks | 2019-09-26 | 2022-09-08 | L2_Bump | [29 empty] | 2 - RRPS |  | 873D1 | 82 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN | 2021-12-17 | David Kane | Summit Ridge Energy | Belgrade PV, LLC | 200 Maine Route 8 Belgrade | 2000149310 | 30012250632 | Solar | [5 empty] | 44.4735 | -69.8183 | Oakland Road |  |  | Belgrade | 27 | COUNTY RD (RICE RIPS) | 873D1 | 873T1 | 34.5 | 9310-L0127-5880-0026-ED00075 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-10-03 | 2019-10-03 | 2019-10-10 | 2019-10-03 | 2019-10-03 | 2020-01-31 |  | 2020-02-14 |  | 2020-01-31 | 2020-02-05 | 2020-02-20 |  |  | 2020-02-07 |  |  | CS | 2020-02-07 | [6 empty] | CS |  |  | 2020-02-07 |  |  | 2022-09-09 | [8 empty] | 2020-02-20 |  |  | 2022-09-28 | [14 empty] | 2020-03-03 |  |  | 2022-10-03 |  |  |  | Yes |  |  |  |  | 2020-05-06 |  |  | 2021-05-18 | Addendum |  |  | 2020-05-06 |  |  | 2022-11-16 | [5 empty] | 2020-05-11 |  |  | 2022-11-17 | [14 empty] | 2020-05-18 | [13 empty] | 2021-05-27 |  | 2020-06-09 |  | 2020-06-11 | 2022-12-05 | [7 empty] | 862677 |  | 1653807 | 2022-11-16 | 2024-06-14 | 2020-07-01 | 2020-07-01 | 2021-06-16 | 2021-06-16 | 2022-12-12 | 2022-12-13 | [18 empty] | TBD | 10300686828 | [11 empty] | TRUE | TRUE | 131 | 2020-07-01 | 2020-07-01 | 2020 | 2020 | 2020 | 44343 |  |  | 2021-05-18 | Addendum
132 |  | Lanie Patterson | Brent Brooks | 2019-09-26 | 2022-09-08 | [30 empty] | 3 - RRPS |  | 873D1 | 131 |  | WITHDRAWN | WITHDRAWN |  | David Kane | LongRoad Development Company LLC | LONGROAD DEVELOPMENT COMPANY LLC | 306 Maine/11 Belgrade | 2000118100 | 30011781595 | Solar | [7 empty] | Oakland Road |  |  | Belgrade |  | COUNTY RD (RICE RIPS) | 873D1 |  |  | 9310-L0127-5880-0179-ED00039 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2019-10-03 | 2019-10-10 |  |  |  |  | 1900-01-12 | [57 empty] | Pending | [69 empty] | 2020-12-15 | [37 empty] | TRUE | TRUE | 132 | 0 | 0 | 1900 | #VALUE! | #VALUE!
133 |  | Govinda Neupane |  | 2019-09-26 | [31 empty] | 3 - LVFA |  | 428D3 | 108 |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2020-11-20 | Zach Good | REVISION ENERGY INC | CAMDEN SOLAR LLC | 58 Souther Rd Lot 5 / Livermore Fal | 2000173655 | 30012539968 | Solar | 3892 | 3.892 | 4984 |  |  | 44.4834 | -70.158 | 58 Souther Road |  |  | Livermore Falls | 14 | LIVERMORE FALLS | 428D3 | 428T1 |  | FLOC-MISSING-01142021 | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-10-02 | 2019-10-03 | 2019-10-10 | 2019-10-02 | 2019-10-04 | 2020-05-13 |  | 2020-05-28 |  | 2020-05-13 | 2020-05-13 | 2020-05-28 |  |  | 2020-05-28 |  |  | CS | 2020-05-28 | [6 empty] | CS |  |  | 2020-05-28 | [11 empty] | 2020-05-28 | [17 empty] | 2020-06-02 | [6 empty] | Yes |  |  |  |  | 2020-08-05 | [6 empty] | 2020-08-04 | [8 empty] | 2020-08-04 | [17 empty] | 2020-08-06 | [15 empty] | 2020-08-14 |  | 2020-08-17 | [13 empty] | 2020-01-15: 2020-08-24; 2020-01-15: 2020-08-24 | [13 empty] | Q4 2020 |  |  |  | 10300704887 | [11 empty] | TRUE | TRUE | 133 | 2020-08-24 | 2020-08-24 | 2020 | 2020 | 2020
134 |  | Lanie Patterson | Brent Brooks | 2019-09-26 | [31 empty] | 2 - MONM |  | 457D1 | 89 |  | WITHDRAWN | WITHDRAWN |  | John Motta | Dynamic Energy | DYNAMIC ENERGY SOLUTIONS LLC | Woods Rd Wales | 2000110140 | 30011800825 | Solar | [7 empty] | Woods Rd |  |  | Wales |  | MONMOUTH | 457D1 |  |  | 9310-L0128-3230-0153-ED00028 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2019-10-03 | 2019-10-10 |  |  |  |  | 1900-01-12 | [57 empty] | Yes | [69 empty] | 2020-07-27 | [37 empty] | TRUE | TRUE | 134 | 0 | 0 | 1900 | 1900 | 1900
135 |  | Lanie Patterson | Brent Brooks | 2019-09-26 | [31 empty] | 3 - MONM |  | 457D1 | 134 |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2021-02-25 | Denise Murillo | Atlus Power LLC | WALES LEEDS JUNCTION SOLAR LLC | Leeds Junction Rd Wales | 2000193119 | 30012803786 | Solar | 4500 | 4.5 | 6300 |  |  | 44.1994 | -70.0735 | Leeds Junction Rd |  |  | Wales | 54 | MONMOUTH | 457D1 | 457T1 |  | 9310-L0128-3230-0255-ED00012 | Non-FERC | TRIGGERING | TRIGGERING (375,000) | 259695 | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-10-03 | 2019-10-03 | 2019-10-10 | 2019-10-03 | 2019-10-04 | 2020-08-06 |  | 2020-08-20 |  | 2020-08-06 | 2020-08-27 | 2020-09-11 |  |  | 2020-09-03 |  |  | CS | 2020-09-03 | [6 empty] | CS |  |  | 2020-09-03 | [29 empty] | 2020-09-09 | [6 empty] | Pending |  |  |  |  | 2020-11-12 |  |  | 2021-06-03 | Addendum |  |  | 2020-11-12 | [8 empty] | 2020-11-13 | [17 empty] | 2020-11-17 | [7 empty] | 2020-11-17 | [7 empty] | 2021-06-02 | [10 empty] | 460974 |  |  |  |  | 2020-01-15: 2021-06-04; 2020-01-15: 2021-06-04; 2020-09-17: 2021-06-04; 2020-09-17: 2021-06-04 | [17 empty] | 10300760225 | [11 empty] | TRUE | TRUE | 135 | 2021-06-04 | 2021-06-04 | 2021 | 2021 | 2021 |  |  |  | 2021-06-03 | Addendum
136 |  | Lanie Patterson | Brent Brooks | 2019-09-26 | 2022-07-28 | L2_Bump |  | 2022-09-15 | L2_With | [26 empty] | 4 - MONM |  | 457D1 | 135 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN | 2021-11-23 | Tim Richardson | MN8 Energy LLC | WALES POND ROAD SOLAR LLC | 642 Pond Rd Lot1 Wales | 2000214636 | 30013081739 | Solar | [5 empty] | 44.1775 | -70.0691 | 642 Pond Rd |  |  | Wales | 2 | MONMOUTH | 457D1 | 457T1 |  | 9310-L0128-3230-0392-ED00008 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-10-03 | 2019-10-03 | 2019-10-10 | 2019-10-03 | 2019-10-04 | 2021-06-16 |  | 2021-07-01 |  | 2021-06-23 | 2021-06-23 | 2021-07-06 |  |  | 2021-07-06 |  |  | CS | 2021-07-06 | [6 empty] | CS |  |  | 2021-07-06 | 2022-07-29 |  | 2022-07-28 | 2022-09-20 | [7 empty] | 2021-06-18 | [11 empty] | 2022-10-03 | [5 empty] | 2021-07-12 | 2022-08-08 |  | 2022-08-08 | 2022-10-04 | [7 empty] | 2021-09-14 | 2022-09-19 | [5 empty] | 2021-09-14 |  |  | 2022-09-28 | 2022-11-02 |  |  |  |  | 2021-09-14 |  |  | 2022-11-02 | [8 empty] | 2022-11-09 | [5 empty] | 2021-09-28 |  |  | 2022-11-23 |  |  |  |  | 2021-09-28 | [7 empty] | 2021-11-03 |  | 2021-11-03 | 2022-12-12 |  | 2022-12-13 | [5 empty] | 126762 |  | 376345 | 2022-10-25 | 2024-08-12 | 2020-01-15: 2021-11-05; 2020-01-15: 2021-11-18; 2020-09-17: 2022-12-14; 2020-09-17: 2022-12-15 | [17 empty] | Requested | [11 empty] | TRUE | TRUE | 136 | 2021-11-05 | 2021-11-05 | 2021 | 2021 | 2021
137 |  | Lanie Patterson | Brent Brooks | 2019-09-26 | 2022-07-28 | L2_Bump |  | 2022-09-15 | L2_With | [26 empty] | 5 - MONM |  | 457D1 | 136 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN | 2021-11-23 | Tim Richardson | MN8 Energy LLC | WALES POND ROAD SOLAR LLC | 642 Pond Rd Lot 2 Wales | 2000110140 | 30011800809 | Solar | [5 empty] | 44.1766 | -70.0694 | 642 Pond Rd |  |  | Wales | 2 | MONMOUTH | 457D1 | 457T1 |  | 9310-L0133-2300-0094-ED00039 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-10-03 | 2019-10-03 | 2019-10-10 | 2019-10-03 | 2019-10-04 | 2021-06-16 |  | 2021-07-01 |  | 2021-06-23 | 2021-06-23 | 2021-07-06 |  |  | 2021-07-06 |  |  | CS | 2021-07-06 | [6 empty] | CS |  |  | 2021-07-06 | 2022-07-29 | [10 empty] | 2021-06-18 | [17 empty] | 2021-07-12 | 2022-08-08 |  | 2022-08-08 | 2022-10-04 | [7 empty] | 2021-09-14 | 2022-09-19 | [5 empty] | 2021-09-14 |  |  | 2022-09-28 | 2022-11-02 |  |  |  |  | 2021-09-14 |  |  | 2022-11-02 | [8 empty] | 2022-11-09 | [5 empty] | 2021-09-28 |  |  | 2022-11-23 |  |  |  |  | 2021-09-28 | [7 empty] | 2021-11-03 |  | 2021-11-03 | [8 empty] | 126762 |  |  |  | 2024-08-12 | 2020-01-15: 2021-11-05; 2020-01-15: 2021-11-18 | [17 empty] | Requested | [11 empty] | TRUE | TRUE | 137 | 2021-11-05 | 2021-11-05 | 2021 | 2021 | 2021
138 |  | Eben Snow | Brent Brooks | 2019-09-26 | 2023-10-09 | wthdw | [29 empty] | 2 - BR34 |  | 406D4 | 86 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Joseph Feole | Soltage LLC | NAPLES OLD COUNTY SOLAR 1 LLC | 4 Old County Rd Naples | 2000176159 | 30012576002 | Solar | [5 empty] | 43.933 | -70.592 | 4 Old County Rd |  |  | Naples | 561 | BRIDGTON 34 KV | 406D4 |  | 34kV Bus at substation | 9310-L0133-4743-0005-ED00010 | Non-FERC | WITHDRAWN | WITHDRAWN | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-10-03 | 2019-10-03 | 2019-10-10 | 2019-10-03 | 2019-10-04 | 2020-07-31 |  | 2020-08-14 |  | 2020-07-31 | 2020-07-31 | 2020-08-14 |  |  | 2020-08-14 |  |  | CS | 2020-08-18 | [6 empty] | CS |  |  | 2020-08-18 | [29 empty] | 2020-08-19 |  |  | 2023-11-08 |  |  |  | Pending |  |  |  |  | 2020-10-23 |  |  | 2021-05-21 | Addendum |  |  | 2020-10-23 |  |  | 2023-01-18 | [5 empty] | 2020-10-27 |  |  | 2023-01-18 | [14 empty] | 2020-11-04 | [13 empty] | 2021-06-14 |  | 2020-11-04 |  | 2020-11-04 | 2022-11-30 |  |  | 2023-07-03 | 2023-07-10 |  |  |  | 384920 |  | 560068 | 2023-11-28 | 2024-10-09 | 2020-11-10 | 2020-11-10 | 2021-06-11 | 2021-06-11 | 2024-02-29 | 2024-02-29 | [19 empty] | 10300735554 | [11 empty] | TRUE | TRUE | 138 | 2020-11-10 | 2020-11-10 | 2020 | 2020 | 2020 | 44361 |  |  | 2021-05-21 | Addendum
139 |  | Rigel Paradise | Rick Duperre | 2019-09-27 | [31 empty] | 3 - LIME |  | 632D1 | 106 |  | WITHDRAWN | WITHDRAWN |  | John Motta | Dynamic Energy | DYNAMIC ENERGY SOLUTIONS LLC | Burnham Rd Limerick | 2000110140 | 30011800833 | Solar | [7 empty] | 2 Burnham Rd |  |  | Limerick |  | LIMERICK | 632D1 |  |  | 9310-L0134-2300-0069-ED00115 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2019-10-04 | 2019-10-11 |  |  |  |  | 1900-01-12 | [57 empty] | Pending | [69 empty] | 2020-01-12 | [37 empty] | TRUE | TRUE | 139 | 0 | 0 | 1900 | #VALUE! | #VALUE!
140 |  | Govinda Neupane |  | 2019-09-27 | 2022-09-09 | L2_Bump |  | 2022-12-01 | L2_Bump |  | 2023-10-06 | L2_Bump |  | 2023-12-06 | L2_Bump | [7 empty] | 2024-12-16 | wthdw | [11 empty] | 3 - GUIL | 1 - GUIL | 821D1 | 117 | Yes | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED |  | Toya Ogollo | REC Solar Commercial Corporation | GUILFORD HIGH STREET SOLAR LLC | 107 HIGH ST SOLAR PROJ / GUILFORD | 2000525731 | 30017399301 | Solar | 999 | 0.999 | 1501 |  |  | 45.1719 | -69.3977 | 107 High St |  |  | Guilford | 36 | GUILFORD | 821D1 | 821T1 |  | 9310-L0135-2305-0016-ED00117 | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-10-03 | 2019-10-04 | 2019-10-11 | 2019-10-03 | 2019-10-04 | 2020-07-22 |  | 2020-08-05 |  | 2020-07-22 | 2020-07-22 | 2020-08-05 |  |  | 2020-07-27 | 2020-12-29 |  | CS | 2020-07-27 | RS | 2020-12-29 |  |  |  |  | CS |  |  | 2020-07-27 | 2020-12-29 |  | 2023-07-21 | 2024-03-15 | 2024-05-07 | [6 empty] | 2020-08-14 |  |  | 2023-08-03 | N/A | 2024-05-22 | [7 empty] | 2024-03-21 | 2024-05-22 |  |  |  | 2020-08-05 | 2021-01-04 |  | 2023-08-23 | 2024-03-21 | 2024-05-22 |  | Pending |  |  |  |  | 2020-10-08 | 2021-02-17 |  | 2021-05-20 | Addendum |  |  | 2020-10-08 | 2021-02-03 |  | 2024-07-29 | [5 empty] | 2020-10-12 | 2021-01-04 |  | 2024-07-29 | [14 empty] | 2020-10-19 | 2021-02-03 | [6 empty] | 2020-10-19 | 2021-02-03 |  |  |  |  | 2021-06-10 |  | 2021-07-09 | 2021-07-09 | 2021-07-09 | 2024-07-31 | [7 empty] | 409556 |  |  |  |  | 2021-07-09 | 2021-07-09 | 2021-07-09 | 2021-07-09 | 2024-08-29 | 2024-08-29 | [15 empty] | Q3 2025 |  |  |  | Requested | [11 empty] | FALSE | TRUE | 140 | 2021-07-09 | 2021-07-09 | 2021 | 2021 | 2021 | 44357 |  | 44386 | 2021-05-20 | Addendum
141 |  | Lanie Patterson | Brent Brooks | 2019-09-27 | [31 empty] | 2 - SOCH |  | 244D2 | 124 |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2021-01-04 | Scott Moore | SunRaise Investments LLC | ROUTE 3 CHINA SOLAR LLC | Route 3, China, Me | 2000163643 | 30012397862 | Solar/Battery | 4478 | 4.478 | 6140 | 2250 |  | 44.4102 | -69.5257 | Rte 3 |  |  | China | 755 | SOUTH CHINA | 244D2 | 244T1 |  | 9310-L0137-0230-0232-ED00067 | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-10-03 | 2019-10-04 | 2019-10-11 | 2019-10-03 | 2019-10-07 | 2020-04-28 |  | 2020-05-12 |  | 2020-04-28 | 2020-04-28 | 2020-05-12 |  |  | 2020-04-29 |  |  | CS | 2020-04-29 | [6 empty] | CS |  |  | 2020-04-29 | [11 empty] | 2020-04-29 | [17 empty] | 2020-05-01 | [6 empty] | Yes |  |  |  |  | 2020-07-07 |  |  | 2021-05-21 | Addendum |  |  | 2020-07-06 | [8 empty] | 2020-07-08 | 2020-02-03 | [16 empty] | 2020-07-16 | 2020-02-03 | [13 empty] | 2021-05-24 | 2020-07-16 |  | 2020-07-16 | [8 empty] | 69772 |  |  |  |  | 2020-01-15: 2020-07-24; 2020-01-15: 2020-07-24 | [13 empty] | Q4 2020 |  |  |  | 10300692532 | [11 empty] | TRUE | TRUE | 141 | 2020-07-24 | 2020-07-24 | 2020 | 2020 | 2020 |  | 44340 |  | 2021-05-21 | Addendum
142 |  |  | Anthony Boucher | 2019-09-27 | [31 empty] | 1 - UNIO |  | 251D1 |  |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2020-07-14 | Chris Denton | Standard Solar | Union ME 2, LLC | Appleton Rd Union Parc.#008046001 | 2000156859 | 30012292485 | Solar | 4875 | 4.875 | 6662 |  |  | 44.2217 | -69.2844 | Appleton Road |  |  | Union | 4 | UNION | 251D1 | 251T1 |  | 9310-L0138-0230-0551-ED00100 | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-10-03 | 2019-10-04 | 2019-10-11 | 2019-10-03 | 2019-10-07 | 2019-10-23 |  | 2019-11-06 |  | 2019-10-23 | 2019-10-23 | 2019-11-06 |  |  | 2019-10-24 |  |  | CS | 2019-10-24 | [6 empty] | CS |  |  | 2019-10-24 | [11 empty] | 2019-11-05 | [17 empty] | 2019-11-05 | [6 empty] | Yes |  |  |  |  | 2020-01-08 |  |  | 2021-06-17 | Addendum |  |  | 2020-01-15 | [8 empty] | 2020-01-16 | [17 empty] | 2020-01-22 | [15 empty] | 2020-04-14 |  | 2020-04-14 | [13 empty] | 2020-01-15: 2020-05-11; 2020-01-15: 2020-05-11 | [13 empty] | Q4 2020 |  |  | TBD | 10300678873 | [11 empty] | TRUE | TRUE | 142 | 2020-05-11 | 2020-05-11 | 2020 | 2020 | 2020 |  |  |  | 2021-06-17 17:14 | Addendum
143 |  | Eben Snow | Brent Brooks | 2019-09-27 | [31 empty] | 9 - HORD |  | 420D4 | 109 |  | WITHDRAWN | WITHDRAWN |  | Eric Weinstein | BORREGO SOLAR SYSTEMS INC | 510 PV PROJECT DEVELOPMENT LLC | 518 Norway Rd Harrison | 2000113260 |  | Solar | [7 empty] | Lewiston Junction Rd |  |  | Poland |  | HOTEL ROAD | 420D4 |  |  | 86-Withdrawn-86d | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2019-10-04 | 2019-10-11 |  |  |  |  | 1900-01-12 | [127 empty] | 2020-02-18 | [37 empty] | TRUE | TRUE | 143 | 0 | 0 | 1900 | #VALUE! | #VALUE!
144 |  |  | Anthony Boucher | 2019-10-01 | 2022-10-20 | L2_Bump | [29 empty] | 2 - UNIO |  | 251D1 | 142 |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2021-03-30 | Zach Good | Aligned Solar Partners 6, LP | UNION ME 1 LLC | Appleton Rd Union Parc.#009002 | 2000156847 | 30012292030 | Solar | 2000 | 2 | 2917 |  |  | 44.2216 | -69.2827 | Appleton Road |  |  | Union | 01 | UNION | 251D1 | 251T1 |  | 9310-L0138-0230-0551-ED00100 | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-10-03 | 2019-10-08 | 2019-10-16 | 2019-10-03 | 2019-10-07 | 2020-06-04 |  | 2020-06-18 |  | 2020-06-04 | 2020-06-04 | 2020-06-18 |  |  | 2020-06-09 |  |  | CS | 2020-06-09 | [6 empty] | CS |  |  | 2020-06-09 |  |  | 2022-10-24 | [8 empty] | 2020-06-11 |  |  |  | 2022-11-03 | [7 empty] | 2022-11-08 | [5 empty] | 2020-06-10 |  |  | 2022-11-10 |  |  |  | Pending |  |  |  |  | 2020-08-13 |  |  | 2021-06-17 | Addendum |  |  | 2020-08-13 | [8 empty] | 2020-08-13 | [17 empty] | 2020-08-19 | [15 empty] | 2020-09-09 |  | 2020-09-09 | 2022-12-15 | [9 empty] | 221827 | 2022-12-14 |  | 2020-09-23 | 2020-09-23 | 2021-07-13 | 2021-07-13 |  |  | 2024-06-03 | 2024-06-03 | [13 empty] | Q4 2020 | 7/13/221 |  |  | 10300716786 | [11 empty] | TRUE | TRUE | 144 | 2020-09-23 | 2020-09-23 | 2020 | 2020 | 2020 |  |  |  | 2021-06-17 17:12 | Addendum
145 |  | Eben Snow | Brent Brooks | 2019-10-01 | [31 empty] | 1 - BRPO |  | 407D1 |  |  | WITHDRAWN | WITHDRAWN |  | Eric Weinstein | BORREGO SOLAR SYSTEMS INC | 510 PV PROJECT DEVELOPMENT LLC | S Main St Bryant Pond | 2000113260 | 30011764666 | Solar/Battery | [7 empty] | South Main St |  |  | Woodstock |  | BRYANT POND | 407D1 |  |  | 9310-L0140-0230-0206-ED00028 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2019-10-08 | 2019-10-16 |  |  |  |  | 1900-01-12 | [57 empty] | Pending | [69 empty] | 2020-05-06 | [37 empty] | TRUE | TRUE | 145 | 0 | 0 | 1900 | #VALUE! | #VALUE!
146 |  | Eben Snow | Brent Brooks | 2019-10-01 | [31 empty] | 3 - OXFO |  | 437D1 | 3 |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2020-07-14 | Tyler William Perkins | Nexamp, Inc | Oxford Solar 1, LLC | 278 Main St | 2000330989 | 30014667254 | Solar/Battery | 4290 | 4.29 | 6218 |  |  | 44.1244 | -70.4506 | Main Street |  |  | Oxford | 39 | OXFORD | 437D1 | 437T1 |  | 9310-L0140-4710-0053-ED00001 | Non-FERC | COST SHARE | COST SHARE (375,000) | 94002 | Under Review 1/31/2020 |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-10-07 | 2019-10-08 | 2019-10-16 | 2019-10-07 | 2019-10-08 | 2019-10-24 |  | 2019-11-07 |  | 2019-10-24 | 2019-10-24 | 2019-11-07 |  |  | 2019-10-31 |  |  | CS | 2019-10-31 | [6 empty] | CS |  |  | 2019-10-31 | [11 empty] | 2019-11-14 | [17 empty] | 2019-11-14 | [6 empty] | Yes |  |  |  |  | 2020-01-17 |  |  | 2021-05-24 | Addendum |  |  | 2020-01-23 | [8 empty] | 2020-01-23 | [17 empty] | 2021-06-16 | [7 empty] | 2021-06-16 | [5 empty] | 2021-06-16 |  | 2020-01-27 |  | 2020-01-28 | [8 empty] | 153956 |  |  |  |  | 2020-01-15: 2020-02-13; 2020-01-15: 2020-02-13; 2020-09-17: 2021-07-06; 2020-09-17: 2021-07-06 | [13 empty] | Q4 2020 |  |  | 43900 | 10300649510 | 10300714122 | [10 empty] | TRUE | TRUE | 146 | 2020-02-13 | 2020-02-13 | 2020 | 2020 | 2020 | 44363 |  |  | 2021-05-24 | Addendum
147 |  | Rigel Paradise | Rick Duperre | 2019-10-01 | [31 empty] | 1 - NOLI |  | 638D1 |  |  | WITHDRAWN | WITHDRAWN |  | Michael Whigham | CEC Development LLC | CEC DEVELOPMENT LLC | 93 Sedona On The Saco Limington | 2000123496 | 30011780001 | Solar/Battery | [10 empty] | Limington |  | NORTH LIMINGTON | 638D1 |  |  | 9310-L0161-3340-0010-ED00046 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2019-10-08 | 2019-10-16 |  |  |  |  | 1900-01-12 | [57 empty] | Pending | [69 empty] | 2020-01-04 | [37 empty] | TRUE | TRUE | 147 | 0 | 0 | 1900 | #VALUE! | #VALUE!
148 |  |  | Anthony Boucher | 2019-10-01 | [31 empty] | 1 - MERO |  | 270D1 |  |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2020-04-28 | Tyler William Perkins | Nexamp, Inc | SAMOSET SOLAR LLC | Rockland St, Rockport | 2000200843 | 30012903537 | Solar | 2125 | 2.125 | 3091 |  |  | 44.1694 | -69.1197 | Rockland St |  |  | Rockport | 9 | MEADOW ROAD | 270D1 | 270T2 |  | 9310-L0161-3350-0096-ED00028 | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-10-07 | 2019-10-08 | 2019-10-16 | 2019-10-07 | 2019-10-08 | 2019-10-28 |  | 2019-11-12 |  | 2019-10-28 | 2019-10-28 | 2019-11-11 |  |  | 2019-11-11 |  |  | CS | 2019-11-12 | [6 empty] | CS |  |  | 2019-11-12 | [11 empty] | 2019-12-05 | [17 empty] | 2019-12-05 | [6 empty] | Yes |  |  |  |  | 2020-02-10 |  |  | 2021-05-19 | Addendum |  |  | 2020-02-04 | [8 empty] | 2020-02-04 | [17 empty] | 2020-02-10 | [13 empty] | 2021-05-27 |  | 2020-02-10 |  | 2020-02-12 | [8 empty] | 203177 |  |  |  |  | 2020-01-15: 2020-02-18; 2020-01-15: 2020-02-18 | [13 empty] | Q3 2020 |  |  | 43901 | 10300649355 | 10300796353 | [10 empty] | TRUE | TRUE | 148 | 2020-02-18 | 2020-02-18 | 2020 | 2020 | 2020 | 44343 |  |  | 2021-05-19 | Addendum
149 |  | Rigel Paradise | Rick Duperre | 2019-10-01 | [31 empty] | 2 - NOLI |  | 638D1 | 147 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Joseph Feole | Soltage LLC | LIMINGTON SOKOKIS SOLAR 1 LLC | Sokokis Limington Solar | 2000174912 | 30012556848 | Solar | [5 empty] | 43.7458 | -70.6819 | 460 Sokokis Ave |  |  | Limington | 515 | NORTH LIMINGTON | 638D1 | 638T1 |  | 9310-L0162-3350-0063-ED00028 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-10-07 | 2019-10-08 | 2019-10-16 | 2019-10-07 | 2019-10-08 | 2020-01-06 |  | 2020-01-21 |  | 2020-01-06 | 2020-01-06 | 2020-01-21 |  |  | 2020-01-07 |  |  | CS | 2020-01-07 | [6 empty] | CS |  |  | 2020-01-07 | [11 empty] | 2020-01-14 | [17 empty] | 2020-01-14 | [6 empty] | Yes |  |  |  |  | 2020-03-19 |  |  | 2021-05-21 | Addendum |  |  | 2020-03-20 | [8 empty] | 2020-03-20 | [17 empty] | 2020-03-27 | [14 empty] | 2021-05-27 | 2021-05-28 | 2021-05-27 | 2020-06-29 |  |  |  | 2023-07-03 | 2023-07-10 |  |  |  | 75834 |  |  |  | 2023-10-09 | 2020-01-15: 2020-08-21; 2020-01-15: 2020-08-21; 2020-09-17: 2021-05-28; 2020-09-17: 2021-05-28 | [17 empty] | 10300704071 | [11 empty] | TRUE | TRUE | 149 | 2020-08-21 | 2020-08-21 | 2020 | 2020 | 2020 |  | 44343 | 44343 | 2021-05-21 | Addendum
150 |  | Rigel Paradise | Rick Duperre | 2019-10-01 | [31 empty] | 1 - HITP |  | 692D1 |  |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2020-07-14 | Scott Moore | SunRaise Investments LLC | PEQUAWKET TRAIL BALDWIN SOLAR LLC | 1093 Pequawket Trl Baldwiin | 2000150008 | 30012183791 | Solar | 4875 | 4.875 | 6000 |  |  | 43.8392 | -70.7827 | 1093 Pequawket Trail |  |  | Baldwin | 42 | HIRAM TAP | 692D1 | 692T1 |  | 9310-L0162-3350-0063-ED00028 | FERC | NOT IMPACTED | NOT IMPACTED | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-10-07 | 2019-10-08 | 2019-10-16 | 2019-10-07 | 2019-10-08 | 2019-10-29 |  | 2019-11-13 |  | 2019-10-29 | 2019-10-29 | 2019-11-12 | [5 empty] | FS | 2019-11-12 | IS | 2020-12-16 | RS |  |  |  | Split | 2019-11-12 | 2020-12-16 |  | 2020-03-11 | [9 empty] | 2019-11-14 | 2019-12-27 | 2020-03-27 | [14 empty] | 2019-11-14 | 2019-12-27 |  | 2020-03-31 | [5 empty] | Yes |  |  | 2019-12-19 | 2020-02-11 |  | 2020-05-13 |  |  |  | 2019-12-16 | 2020-01-28 |  | 2020-05-14 | [5 empty] | 2020-01-29 | 2020-04-27 |  | 2020-05-14 | [14 empty] | 2019-12-16 | 2020-02-04 |  | 2020-04-30 |  |  |  |  | 2019-12-16 | 2020-02-04 | [8 empty] | 2020-04-30 |  | 2020-05-01 | [13 empty] | 2020-01-15: 2020-05-05; 2020-01-15: 2020-05-05 | [13 empty] | Q4 2020 |  |  | TBD | 10300667133 | [11 empty] | TRUE | TRUE | 150 | 2020-05-05 | 2020-05-05 | 2020 | 2020 | 2020
151 |  | Eben Snow | Brent Brooks | 2019-10-01 | 2023-07-25 | wthdw |  | 2023-11-17 | L2_Bump | [26 empty] | 4 - KIRD | 1 - KIRD | 423D2 | 121 | Yes | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED |  | Jacob Fraatz | DIMENSION ENERGY LLC | ISM Solar Bolster Mills, LLC | 40 Bolsters Mill Rd, Harrison | 2000119678 | 30012490303 | Solar | 999 | 0.999 | 1498.095 |  |  | 44.1461 | -70.6278 | Bolsters Mills Rd |  |  | Harrison | 4 | KIMBALL ROAD | 423D2 | 423T2 |  | 9310-L0162-3350-0079-ED00007 | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Under Review 1/31/2020 |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-10-07 | 2019-10-08 | 2019-10-16 | 2019-10-07 | 2019-10-08 | 2020-06-12 |  | 2020-06-26 |  | 2020-06-12 | 2020-06-12 | 2020-06-26 |  |  | 2020-06-19 |  |  | CS | 2020-06-19 | RS | 2024-04-12 |  |  |  |  | CS |  |  | 2020-06-19 | 2024-04-12 |  | 2023-07-27 | 2023-11-22 |  |  |  |  | 2024-04-12 |  |  | 2020-06-22 | 2024-04-17 |  | 2023-08-11 | 2023-12-12 | [5 empty] | 2024-04-17 |  | 2023-08-22 | 2023-12-12 |  |  |  |  | 2020-06-24 | 2024-04-17 |  | 2023-08-28 | 2024-01-12 |  |  | Pending |  |  |  |  | 2020-08-27 | 2024-05-30 |  | 2021-06-04 | Addendum |  |  | 2020-08-27 | 2024-05-30 |  | 2023-10-10 | 2024-03-18 |  |  |  |  | 2020-09-01 | 2024-05-30 |  | 2023-10-10 | 2024-03-18 | [5 empty] | N/A | [7 empty] | 2020-09-03 | N/A | [7 empty] | N/A | [6 empty] | 2020-09-03 |  | 2020-09-03 | 2024-06-28 |  | 2024-06-28 | 2023-07-03 |  |  |  |  | 120173 |  | 265837 | 2024-05-29 |  | 2020-01-15: 2020-09-09; 2020-01-15: 2020-09-09; 2020-09-17: 2021-07-08; 2020-09-17: 2021-07-08 | [13 empty] | Q4 2025 |  |  |  | 10300710349 | [11 empty] | FALSE | TRUE | 151 | 2020-09-09 | 2020-09-09 | 2020 | 2020 | 2020 |  |  |  | 2021-06-04 | Addendum
152 |  | Eben Snow | Brent Brooks | 2019-10-02 | 2021-08-10 | wthdw | [29 empty] | 4 - LEED |  | 471D2 | 73 |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED |  | John Motta | Dynamic Energy | LEEDS ROUTE 106 SOLAR LLC | 1053 Route 106 Norridgewock | 2000214611 | 30013081317 | Solar | 4999 | 4.999 | 7000 |  |  | 44.2902 | -70.1189 | 1053 Road 106 |  |  | Leeds | 82 | LEEDS | 471D2 | 471T1 |  | 9310-L0210-3210-0068-ED00056 | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-10-07 | 2019-10-09 | 2019-10-17 | 2019-10-07 | 2019-10-08 | 2020-09-14 |  | 2020-09-28 |  | 2020-09-14 | 2020-09-14 | 2020-09-28 |  |  | 2020-09-28 | 2021-07-13 |  | CS | 2020-09-28 | RS | 2021-07-13 |  |  |  |  | CS |  |  | 2020-09-28 | 2021-07-13 | [10 empty] | 2020-08-30 | [17 empty] | 2020-09-29 | 2021-10-01 | 2021-08-10 |  |  |  |  | Pending |  |  |  |  | 2020-12-04 | 2021-11-16 |  | 2021-05-18 | Addendum |  |  | 2020-12-04 | 2021-11-12 | [7 empty] | 2020-12-11 | 2021-11-11 | 2021-10-01 | [15 empty] | 2020-12-11 | [7 empty] | 2020-12-11 | [7 empty] | 2021-11-19 |  | 2021-11-22 | [8 empty] | 1707817 |  | 265837 | 2021-10-28 |  | 2020-01-15: 2021-11-20; 2020-01-15: 2021-11-23 | [17 empty] | Requested | [11 empty] | TRUE | TRUE | 152 | 2021-11-20 | 2021-11-20 | 2021 | 2021 | 2021 |  |  |  | 2021-05-18 | Addendum
153 |  | Govinda Neupane |  | 2019-10-02 | [31 empty] | 1 - SKTP |  | 864D1 |  |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2020-06-25 | Cameron Clark | Harrison Street | NORRIDGEWOCK RIVER ROAD SOLAR LLC | 552 River Rd Norridgewock | 2000161664 | 30012368079 | Solar | 4999 | 4.999 | 7000 |  |  | 44.7437 | -69.7636 | 552 River Rd |  |  | Norridgewock | 73 | SKOWHEGAN TAP | 864D1 | 864T1 |  | 9310-L0162-3350-0097-ED00010 | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-10-07 | 2019-10-09 | 2019-10-17 | 2019-10-07 | 2019-10-11 | 2019-10-29 |  | 2019-11-13 |  | 2019-10-29 | 2019-10-29 | 2019-11-12 |  |  | 2019-11-06 |  |  | CS | 2019-11-06 | [6 empty] | CS |  |  | 2019-11-06 | [11 empty] | 2019-12-10 | [17 empty] | 2019-12-10 | [6 empty] | Yes |  |  |  |  | 2020-02-13 | [6 empty] | 2020-02-14 | [8 empty] | 2020-02-17 | [17 empty] | 2020-02-20 | [15 empty] | 2020-03-04 |  | 2020-03-05 | [13 empty] | 2020-01-15: 2020-03-26; 2020-01-15: 2020-03-26 | [13 empty] | Q1 2021 |  |  | TBD | 10300673406 | [11 empty] | TRUE | TRUE | 153 | 2020-03-26 | 2020-03-26 | 2020 | 2020 | 2020
154 |  | Govinda Neupane |  | 2019-10-02 | [31 empty] | 1 - SKSS |  | 854D1 |  |  | WITHDRAWN | WITHDRAWN |  | John Motta | Dynamic Energy | DYNAMIC ENERGY SOLUTIONS LLC | 205 Smithfield Rd Norridgewock | 2000110140 | 30011800569 | Solar | [7 empty] | 205 Smithfield Rd |  |  | Norridgewock |  | SKOWHEGAN SOUTH SIDE | 854D1 |  |  | 9310-L0163-0485-0077-ED00022 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2019-10-09 | 2019-10-17 |  |  |  |  | 1900-01-12 | [57 empty] | Pending | [69 empty] | 2021-02-26 | [37 empty] | TRUE | TRUE | 154 | 0 | 0 | 1900 | #VALUE! | #VALUE!
155 |  | Eben Snow | Brent Brooks | 2019-10-03 | [31 empty] | 2 - GRAY |  | 416D3 | 64 |  | WITHDRAWN | WITHDRAWN |  | Eric Weinstein | BORREGO SOLAR SYSTEMS INC | 510 PV PROJECT DEVELOPMENT LLC | Lakeside Dr Windham | 2000113260 | 30011792576 | Solar/Battery | [7 empty] | Rear Lakeside Drive |  |  | Windham |  | GRAY | 416D3 |  |  | 86-Withdrawn-86d | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2019-10-10 | 2019-10-18 |  |  |  |  | 1900-01-12 | [57 empty] | Pending | [69 empty] | 2020-01-13 | [37 empty] | TRUE | TRUE | 155 | 0 | 0 | 1900 | #VALUE! | #VALUE!
156 |  | Marshall Ripley | Rick Duperre | 2019-10-04 | [31 empty] | 2 - SMRD |  | 660D1 | 53 |  | WITHDRAWN | WITHDRAWN |  | Michael Whigham | CEC Development LLC | CEC DEVELOPMENT LLC | 152 Shaw Mills Rd Standish | 2000123496 | 30011779797 | Solar | [7 empty] | 164 Shaws Mill Rd |  |  | Standish |  | SHAWS MILL ROAD | 660D1 |  |  | 86-Withdrawn-86d | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2019-10-11 | 2019-10-21 |  |  |  |  | 1900-01-12 | [57 empty] | Pending | [69 empty] | 2020-12-10 | [37 empty] | TRUE | TRUE | 156 | 0 | 0 | 1900 | #VALUE! | #VALUE!
157 |  | Govinda Neupane |  | 2019-10-04 | [31 empty] | 2 - STUR |  | 858D1A | 66 |  | WITHDRAWN | WITHDRAWN |  | TJ Murphy | Environomics | ENVIRONOMICS | 414 Farmington Falls Rd Lot 12 Farm | 2000125792 | 30011813281 | Solar | [7 empty] | 414 Farmington Falls Rd |  |  | Farmington |  | STURTEVANT | 858D1A |  |  | 86-Withdrawn-86d | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2019-10-11 | 2019-10-21 |  |  |  |  | 1900-01-12 | [50 empty] | 2020-01-20 | [6 empty] | Pending | [69 empty] | 2020-07-07 | [37 empty] | TRUE | TRUE | 157 | 0 | 0 | 1900 | #VALUE! | #VALUE!
158 |  | Govinda Neupane |  | 2019-10-04 | 2022-11-08 | L2_bump |  | 2023-01-09 | L2_bump | [19 empty] | 2025-01-22 | L2_with | [5 empty] | 3 - STUR |  | 858D1A | 157 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | TJ Murphy | EDF Renewables | Clearwater Solar Partners, LLC | 414 Farmington Falls Rd Farmington | 2000125792 | 30014879057 | Solar | [5 empty] | 44.6566 | -70.1125 | 414 Farmington Falls Rd |  |  | Farmington | 20 | STURTEVANT | 858D1A | 858T1 | 34.5 | 9310-L0437-2030-0043-ED00012 | Non-FERC | WITHDRAWN | WITHDRAWN | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-10-08 | 2019-10-11 | 2019-10-21 | 2019-10-08 | 2019-10-11 | 2020-07-28 |  | 2020-08-11 |  | 2020-07-28 | 2020-07-28 | 2020-08-11 |  |  | 2020-08-11 |  |  | CS | 2020-08-17 | [6 empty] | CS |  |  | 2020-08-17 |  |  | 2022-11-10 | [11 empty] | 2022-11-10 | [8 empty] | 2023-01-20 | [5 empty] | 2020-08-27 |  |  | 2023-01-23 |  |  |  | Pending |  |  |  |  | 2020-11-02 |  |  | 2021-05-10 | Addendum |  |  | 2020-11-02 | [8 empty] | 2020-11-10 | [17 empty] | 2020-11-12 | [7 empty] | 2020-11-12 | [6 empty] | 2021-05-11 | 2020-12-02 | 2021-05-11 | 2020-12-02 | 2023-03-09 |  | 2023-03-09 | [5 empty] | 241129 |  | 212607 | 2023-03-06 | 2025-02-04 | 2021-05-17 | 2021-05-17 | 2021-06-09 | 2021-06-09 | 2023-03-10 | 2023-03-10 | [19 empty] | 10300784560 | [11 empty] | TRUE | TRUE | 158 | 2021-05-17 | 2021-05-17 | 2021 | 2021 | 2021 |  | 44327 | 44327 | 2021-05-10 | Addendum
159 |  | Govinda Neupane |  | 2019-10-04 | [31 empty] | 5 - NEWP |  | 837D2 | 129 |  | WITHDRAWN | WITHDRAWN |  | Matthew Doubleday | SunRaise Investments LLC | SUNRAISE DEVELOPMENT LLC | 125 Valley Rd Plymouth | 2000124937 |  | Solar/Battery | [7 empty] | 125 Valley Rd |  |  | Plymouth |  | NEWPORT | 837D2 |  |  | 86-Withdrawn-86d | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2019-10-11 | 2019-10-21 |  |  |  |  | 1900-01-12 | [57 empty] | No Study | [69 empty] | 2020-07-28 | [37 empty] | TRUE | TRUE | 159 | 0 | 0 | 1900 | #VALUE! | #VALUE!
160 |  | Govinda Neupane |  | 2019-10-04 | 2023-04-07 | L2_Bump | [29 empty] | 6 - NEWP |  | 837D2 | 159 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Matthew Doubleday | SunRaise Investments LLC | Moosehead Trail Plymouth Solar, LLC | 125 Valley Rd Plymouth | 2000210178 | 30013022048 | Solar/Battery | [5 empty] | 44.7812 | -69.1995 | Moosehead Trail |  |  | Plymouth | 17 | NEWPORT | 837D2 | 837T2 | 12.47 | 9310-L0419-4695-0023-ED00029 | Non-FERC | WITHDRAWN | WITHDRAWN | 325000 | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-10-08 | 2019-10-11 | 2019-10-21 | 2019-10-08 | 2019-10-14 | 2020-07-29 |  | 2020-08-12 |  | 2020-07-29 | 2020-07-30 | 2020-08-13 |  |  | 2020-08-13 |  |  | CS | 2020-08-17 | RS | [5 empty] | CS |  |  | 2020-08-17 | [11 empty] | 2020-08-18 | [17 empty] | 2020-08-18 | 2020-12-04 | [5 empty] | Pending |  |  |  |  | 2020-10-22 | 2021-01-20 |  | 2021-05-19 | Addendum |  |  | 2020-10-22 | 2021-02-03 | [7 empty] | 2020-10-27 | 2021-02-03 | [16 empty] | 2020-11-03 | 2021-02-03 | [6 empty] | 2020-11-03 | [6 empty] | 2021-05-20 | 2021-02-11 | 2021-05-20 | 2021-02-11 | [8 empty] | 81840 |  |  |  | 2023-07-17 | 2020-01-15: 2021-05-28; 2020-01-15: 2021-05-28; 2020-09-17: 2021-06-07; 2020-09-17: 2021-06-07 | [17 empty] | 10300792496 | [11 empty] | TRUE | TRUE | 160 | 2021-05-28 | 2021-05-28 | 2021 | 2021 | 2021 |  | 44336 | 44336 | 2021-05-19 | Addendum
161 |  | Rigel Paradise | Rick Duperre | 2019-10-07 | [31 empty] | 1 - BDIP |  | 673D1 |  |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED |  | Jack Von Feldt | Madison Energy Holdings | Biddeford Morin Street Solar LLC | 11 Morin St Biddeford | 2000341372 | 30014799933 | Solar | 700 | 0.7 | 1300 |  |  | 43.4677 | -70.4923 | 11 Morin St |  |  | Biddeford | 12 | BIDDEFORD INDUSTRIAL PARK | 673D1 | 673T2 |  | 9310-L0343-0490-0079-ED00004 | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-10-09 | 2019-10-15 | 2019-10-22 | 2019-10-09 | 2019-10-14 | 2019-10-30 |  | 2019-11-14 |  | 2019-10-30 | 2019-10-30 | 2019-11-13 |  |  | 2019-11-13 |  |  | CS | 2020-02-12 | [6 empty] | CS |  |  | 2020-02-12 | [11 empty] | 2020-02-05 | [17 empty] | 2020-04-02 | [6 empty] | Pending |  |  |  |  | 2020-06-08 | [6 empty] | 2020-06-08 | [8 empty] | 2020-05-26 | [17 empty] | 2020-05-28 | [15 empty] | 2020-05-28 |  | 2020-05-29 |  |  |  | 2025-06-10 | 2025-06-10 | [8 empty] | 2020-01-15: 2020-06-16; 2020-01-15: 2020-06-16 | [13 empty] | Q4 2020 |  |  |  | 10300682711 | [11 empty] | TRUE | TRUE | 161 | 2020-06-16 | 2020-06-16 | 2020 | 2020 | 2020
162 |  |  | Anthony Boucher | 2019-10-07 | [31 empty] | 3 - STCO |  | 245D2 | 102 |  | WITHDRAWN | WITHDRAWN |  | Matthew Doubleday | SunRaise Investments LLC | SUNRAISE DEVELOPMENT LLC | 149 Jefferdson Rd Washington Me | 2000124937 | 30011833800 | Solar/Battery | [7 empty] | 149 Jefferson Road |  |  | Washington |  | STICKNEYS CORNER | 245D2 |  |  | 9310-L0080-6187-0001-ED00081 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2019-10-15 | 2019-10-22 |  |  |  |  | 1900-01-12 | [127 empty] | 2020-07-29 | [37 empty] | TRUE | TRUE | 162 | 0 | 0 | 1900 | #VALUE! | #VALUE!
163 |  | Lanie Patterson | Brent Brooks | 2019-10-07 | [31 empty] | 1 - COMR |  | 230D1 |  |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2020-07-14 | Liam McCormack | Summit Ridge Energy | Maxcys Mill Solar | 163 Maxcys Mill Rd Windsor | 2000120852 | 30013492563 | Solar | 2000 | 2 | 2828 |  |  | 44.2927 | -69.5722 | 163 Maxcys Mill Road |  |  | Windsor | 15 | COOPERS MILLS ROAD | 230D1 | 230T2 |  | 9310-L0474-6400-0027-ED00010 | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-10-14 | 2019-10-15 | 2019-10-22 | 2019-10-14 | 2019-10-15 | 2019-10-31 |  | 2019-11-15 |  | 2019-10-31 | 2019-10-31 | 2019-11-14 |  |  | 2019-11-14 |  |  | CS | 2019-12-12 | [6 empty] | CS |  |  | 2019-12-12 | [11 empty] | 2019-12-23 | [17 empty] | 2019-12-23 | [6 empty] | Yes |  |  |  |  | 2020-02-27 | [6 empty] | 2020-02-27 | [8 empty] | 2020-02-27 | [17 empty] | 2020-03-03 | [15 empty] | 2020-03-11 | 2021-08-16 | 2020-03-12 | [13 empty] | 2020-01-15: 2020-04-06; 2020-01-15: 2020-04-06; 2020-09-17: 2021-08-17; 2020-09-17: 2021-08-17 | [13 empty] | Q2 2021 |  | 2021-08-19 | 43928 | 10300656766 | [9 empty] | Assignment |  | TRUE | TRUE | 163 | 2020-04-06 | 2020-04-06 | 2020 | 2020 | 2020 |  |  | 44424
164 |  | Govinda Neupane |  | 2019-10-08 | [31 empty] | 1 - DEXT |  | 813D3 |  |  | WITHDRAWN | WITHDRAWN |  | James Marshall | Turning Point Energy | TPE DEVELOPMENT LLC | Ri01 Dexter Rd Ripley | 2000123236 | 30011834089 | Solar | [7 empty] | Dexter Rd |  |  | Ripley |  | DEXTER | 813D3 |  |  | 86-Withdrawn-86d | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2019-10-16 | 2019-10-23 |  |  |  |  | 1900-01-12 | [57 empty] | Pending | [69 empty] | 2020-04-14 | [37 empty] | TRUE | TRUE | 164 | 0 | 0 | 1900 | #VALUE! | #VALUE!
165 |  | Lanie Patterson | Brent Brooks | 2019-10-08 | [31 empty] | 6 - MONM |  | 457D1 | 137 |  | WITHDRAWN | WITHDRAWN |  | David Kane | LongRoad Development Company LLC | LONGROAD DEVELOPMENT COMPANY LLC | 547 Ridge Rd Days Cor 2 Monmouth | 2000118100 | 30011754527 | Solar | [7 empty] | Ridge Rd |  |  | Monmouth |  | MONMOUTH | 457D1 |  |  | 9310-L0200-3740-0106-ED00014 (NEEDS TO BE CONFIRMED WITH DEVELOPER) | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2019-10-16 | 2019-10-23 |  |  |  |  | 1900-01-12 | [127 empty] | 2021-12-08 | [37 empty] | TRUE | TRUE | 165 | 0 | 0 | 1900 | #VALUE! | #VALUE!
166 |  | Marshall Ripley | Rick Duperre | 2019-10-08 | [31 empty] | 3 - SMRD |  | 660D1 | 156 |  | WITHDRAWN | WITHDRAWN |  | Michael Whigham | CEC Development LLC | CEC DEVELOPMENT LLC | 164 Shaws Mill Rd Standish | 2000123496 | 30011792717 | Solar | [7 empty] | 164 Shaws Mill Rd |  |  | Standish |  | SHAWS MILL ROAD | 660D1 |  |  | 86-Withdrawn-86d | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2019-10-16 | 2019-10-23 |  |  |  |  | 1900-01-12 | [57 empty] | Pending | [69 empty] | 2020-12-10 | [37 empty] | TRUE | TRUE | 166 | 0 | 0 | 1900 | #VALUE! | #VALUE!
167 |  | Govinda Neupane |  | 2019-10-08 | [31 empty] | 1 - CARM |  | 808D1 |  |  | WITHDRAWN | WITHDRAWN |  | Michael Whigham | CEC Development LLC | CEC DEVELOPMENT LLC | 79 Stage Rd Etna | 2000123496 | 30011779771 | Solar | [7 empty] | 799 Stage Road |  |  | Etna |  | CARMEL | 808D1 |  |  | 86-Withdrawn-86d |  | WITHDRAWN | WITHDRAWN | [8 empty] | 2019-10-16 | 2019-10-23 |  |  |  |  | 1900-01-12 | [127 empty] | 2020-09-21 | [37 empty] | TRUE | TRUE | 167 | 0 | 0 | 1900 | #VALUE! | #VALUE!
168 |  |  | KRISTOFER COLEMAN | 2019-10-08 | [31 empty] | 1 - TP34 |  | 250D2 |  |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2020-04-28 | Tyler William Perkins | Nexamp, Inc | Middlesex Turnpike Solar 1 LLC | 59 Murder Rd Topsham | 2000246161 | 30013515496 | Solar/Battery | 4990 | 4.99 | 4944 | 4990 |  | 43.9434 | -69.9294 | 59 Murder Road |  |  | Topsham | 95H | TOPSHAM 34 KV | 250D2 | 250T2 |  | 9310-L0087-5840-0102-ED00268 | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-10-14 | 2019-10-16 | 2019-10-23 | 2019-10-14 | 2019-10-18 | 2019-10-31 |  | 2019-11-15 |  | 2019-10-31 | 2019-11-14 | 2019-10-31 |  |  | 2019-10-31 |  |  | CS | 2019-10-31 | [6 empty] | CS |  |  | 2019-10-31 | [11 empty] | 2019-12-05 | [17 empty] | 2019-12-05 | [6 empty] | Yes |  |  |  |  | 2020-02-10 |  |  | 2021-06-04 | Addendum |  |  | 2020-02-04 | [8 empty] | 2020-02-04 | [33 empty] | 2020-02-11 |  | 2020-02-13 | [8 empty] | 85022 |  |  |  |  | 2020-01-15: 2020-03-02; 2020-01-15: 2020-03-02; 2020-09-17: 2021-08-24; 2020-09-17: 2021-08-24 | [13 empty] | Q2 2021 |  |  | 43920 | 10300652459 | [11 empty] | TRUE | TRUE | 168 | 2020-03-02 | 2020-03-02 | 2020 | 2020 | 2020 |  |  |  | 2021-06-04 | Addendum
169 |  | Govinda Neupane |  | 2019-10-09 | [31 empty] | 2 - CARM |  | 808D1 | 167 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Michael Whigham | CEC Development LLC | ETNA ME 1 LLC | 846 Stage Rd, Etna | 2000156873 | 30012292634 | Solar | [5 empty] | 44.8166 | -69.1395 | 846 Stage Road |  |  | Etna | 44 | CARMEL | 808D1 | 808T1 |  | 9310-SS0808 | Non-FERC | WITHDRAWN | WITHDRAWN | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-10-14 | 2019-10-17 | 2019-10-24 | 2019-10-14 | 2019-10-18 | 2020-06-05 |  | 2020-06-19 |  | 2020-06-05 | 2020-06-05 | 2020-06-19 |  |  | 2020-06-09 | 2020-11-05 |  | CS | 2020-06-09 | RS | 2020-11-05 |  |  |  |  | CS |  |  | 2020-06-09 | 2020-11-05 | [10 empty] | 2020-06-11 | [17 empty] | 2020-06-10 | 2020-11-17 | [5 empty] | Pending |  |  |  |  | 2020-08-13 | 2021-01-04 |  | 2021-05-05 | Addendum |  |  | 2020-08-13 | 2021-01-08 | [7 empty] | 2020-08-26 | 2021-01-25 | [16 empty] | 2020-08-26 | 2021-01-28 | [6 empty] | 2020-08-31 | 2021-01-28 |  |  |  |  | 2021-05-20 |  | 2021-05-06 | 2021-05-05 |  | 2022-11-30 | [7 empty] | 788983 |  |  |  | 2023-03-09 | 2020-01-15: 2021-05-07; 2020-01-15: 2021-05-07; 2020-09-17: 2021-05-07; 2020-09-17: 2021-05-07 | [17 empty] | 10300781986 | [11 empty] | TRUE | TRUE | 169 | 2021-05-07 | 2021-05-07 | 2021 | 2021 | 2021 | 44336 |  | 44321 | 2021-05-05 | Addendum
170 |  | Eben Snow | Brent Brooks | 2019-10-09 | 2022-07-21 | L2_Bump | [27 empty] | 1 - NORW |  | 1 - NORW |  | 435D3 |  | Yes | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED |  | Liam McCormack | Summit Ridge Energy | South Paris PV LLC | 566 HIGH ST PARIS (NEB SOLAR) | 2000405196 | 30015641621 | Solar | 4950 | 4.95 | 6751 |  |  | 44.2609 | -70.5333 | High Street |  |  | South Paris | 17 | NORWAY | 435D3 | 435T2 |  | 9310-L0170-4500-0037-ED00037 | Non-FERC | TRIGGERING | TRIGGERING (250,000) | 138283.61 | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-10-14 | 2019-10-17 | 2019-10-24 | 2019-10-14 | 2019-10-18 | 2019-11-04 |  | 2019-11-19 |  | 2019-11-04 | 2019-11-04 | 2019-11-18 |  |  | 2019-11-06 |  |  | CS | 2019-11-06 | [6 empty] | CS |  |  | 2019-11-06 | 2022-11-10 |  | 2022-08-01 | [8 empty] | 2019-11-14 | 2022-11-14 |  | 2022-08-08 | [14 empty] | 2019-11-14 |  |  | 2022-08-09 |  |  |  | Yes |  |  |  |  | 2020-01-17 |  |  | 2021-06-04 | Addendum |  |  | 2020-01-23 |  |  | 2022-09-20 | [5 empty] | 2020-01-23 | [8 empty] | 2020-01-23 | [8 empty] | 2020-01-31 | [7 empty] | 2020-01-31 | [7 empty] | 2020-03-30 |  | 2020-04-02 | 2022-12-23 |  | 2022-12-23 | 2023-03-29 | 2023-03-29 |  |  |  | 959522 | 2020-01-16 | 1680908 | 2022-06-27 |  | 2020-04-07 | 2020-04-07 | 2021-06-24 | 2021-06-24 | 2022-12-23 | 2022-12-28 |  |  |  |  | 2023-05-16 | 2023-05-16 | [9 empty] | Q4 2021 |  |  | TBD | 10300660898 | [11 empty] | FALSE | TRUE | 170 | 2020-04-07 | 2020-04-07 | 2020 | 2020 | 2020 |  |  |  | 2021-06-04 | Addendum
171 |  | Eben Snow | Brent Brooks | 2019-10-09 | [31 empty] | 2 - BRID |  | 406D2 | 84 |  | WITHDRAWN | WITHDRAWN |  | David Kane | LongRoad Development Company LLC | LONGROAD DEVELOPMENT COMPANY LLC | 1412 Roosevelt Trl Naples 2 Naples | 2000118100 | 30011754576 | Solar | [7 empty] | 11 Dees Way |  |  | Naples |  | BRIDGTON | 406D2 |  |  | 9310-L0476-4040-0078-ED00046 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2019-10-17 | 2019-10-24 |  |  |  |  | 1900-01-12 | [57 empty] | Pending | [69 empty] | 2020-02-10 | [37 empty] | TRUE | TRUE | 171 | 0 | 0 | 1900 | #VALUE! | #VALUE!
172 |  | Rigel Paradise | Rick Duperre | 2019-10-15 | [31 empty] | 1 - BUCO |  | 612D2 |  |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2020-07-14 | Cameron Clark | Harrison Street | ACTON H RD SOLAR 1 LLC | Acton Rd Solar | 2000120957 | 30011815245 | Solar | 3450 | 3.45 | 6021 |  |  | 43.5471 | -70.9121 | H Road |  |  | Acton | 17 | BUTLER'S CORNER | 612D2 | 612T1 |  | 9310-L0226-0020-0017-ED00010 | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-10-17 | 2019-10-22 | 2019-10-29 | 2019-10-17 | 2019-10-21 | 2019-11-05 |  | 2019-11-20 |  | 2019-11-05 | 2019-11-05 | 2019-11-19 |  |  | 2019-11-19 | 2020-04-03 |  | CS | 2019-12-03 | RS | 2020-04-03 |  |  |  |  | CS | 2019-12-03 | 2020-03-18 | 2019-12-03 | 2020-04-03 | [10 empty] | 2019-12-18 | [17 empty] | 2019-12-18 | 2020-04-09 | [5 empty] | Yes |  |  |  |  | 2020-02-24 | 2020-05-22 |  | 2021-07-20 | Addendum |  |  | 2020-05-18 | [8 empty] | 2020-05-18 | [17 empty] | 2020-03-02 | 2020-05-21 | [12 empty] | 2021-07-21 |  | 2020-05-21 |  | 2020-05-22 | [10 empty] | 526927 |  |  | 2020-01-15: 2020-06-02; 2020-01-15: 2020-06-02; 2020-09-17: 2021-10-27; 2020-09-17: 2021-10-27 | [13 empty] | Q1 2021 |  |  | TBD | 10300666302 | [11 empty] | TRUE | TRUE | 172 | 2020-06-02 | 2020-06-02 | 2020 | 2020 | 2020 | 44398 |  |  | 2021-07-20 | Addendum
173 |  | Lanie Patterson | Brent Brooks | 2019-10-15 | [31 empty] | 3 - WINS |  | 870D1 | 46 |  | WITHDRAWN | WITHDRAWN |  | Matthew Doubleday | SunRaise Investments LLC | SUNRAISE DEVELOPMENT LLC | 165 Albion Rd Benton | 2000124937 | 30011847180 | Solar/Battery | [7 empty] | Albion Road |  |  | Benton |  | WINSLOW | 870D1 | ` |  | 86-Withdrawn-86d | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2019-10-22 | 2019-10-29 |  |  |  |  | 1900-01-12 | [57 empty] | Pending | [69 empty] | 2020-07-09 | [37 empty] | TRUE | TRUE | 173 | 0 | 0 | 1900 | #VALUE! | #VALUE!
174 |  |  | Anthony Boucher | 2019-10-15 | [31 empty] | 1 - BEWE |  | 803D5 |  |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2020-06-25 | Scott Moore | SunRaise Investments LLC | PERKINS ROAD BELFAST SOLAR LLC | 42 Perkins Rd Belfast | 2000150353 | 30012189475 | Solar | 4750 | 4.75 | 6607 | 3000 |  | 44.4013 | -68.996 | Perkins Rd |  |  | Belfast | 11 | BELFAST WEST SIDE | 803D5 | 803T1 |  | 9310-L0382-0430-0112-ED00002 | FERC | TRIGGERING | TRIGGERING (375,000) | 268524.96 | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-10-17 | 2019-10-22 | 2019-10-29 | 2019-10-17 | 2019-10-21 | 2019-11-05 |  | 2019-11-20 |  | 2019-11-05 | 2019-11-05 | 2019-11-19 | [5 empty] | FS | 2019-11-14 | IS | 2019-12-31 | RS |  |  |  | Split | 2019-11-14 | 2019-12-31 |  | 2020-03-11 | [9 empty] | 2019-11-25 | 2020-01-09 | 2020-03-27 | [14 empty] | 2019-11-25 | 2020-01-09 |  | 2020-03-31 | [5 empty] | Yes |  |  | 2019-12-30 | 2020-02-24 |  | 2020-05-13 |  | 2021-06-03 | Addendum | 2019-12-24 | 2020-02-07 |  | 2020-05-14 | [5 empty] | 2019-12-24 | 2020-02-11 |  | 2020-05-14 | [14 empty] | 2020-01-07 | 2020-02-19 |  | 2020-04-28 |  |  |  |  | 2020-01-07 | 2020-02-19 | [8 empty] | 2020-04-28 |  | 2020-04-30 |  | 2020-04-30 | [6 empty] | 540899 |  |  |  |  | 2020-01-15: 2020-04-30; 2020-01-15: 2020-04-30; 2020-09-17: 2021-06-23; 2020-09-17: 2021-06-23 | [13 empty] | Q4 2020 |  |  | TBD | 10300667790 | [11 empty] | TRUE | TRUE | 174 | 2020-04-30 | 2020-04-30 | 2020 | 2020 | 2020 |  |  |  | 2021-06-03 | Addendum
175 |  |  | KRISTOFER COLEMAN | 2019-10-15 | [31 empty] | 2 - TP34 |  | 250D1 | 168 |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2020-07-30 | Scott Moore | SunRaise Investments LLC | AUGUSTA ROAD BOWDOIN SOLAR LLC | 1052 Augusta Rd, Bowdoin, Me | 2000163637 | 30014001397 | Solar/Battery | 3638 | 3.638 | 5593 |  | 2000 | 44.1279 | -69.9459 | Augusta Rd |  |  | Bowdoin | 167 | TOPSHAM 34 KV | 250D1 | 250T2 |  | 9310-L0086-0570-0011-ED00057 | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-10-17 | 2019-10-22 | 2019-10-29 | 2019-10-17 | 2019-10-21 | 2020-03-12 |  | 2020-03-26 |  | 2020-03-12 | 2020-03-12 | 2020-03-26 |  |  | 2020-03-19 |  |  | CS | 2020-03-19 | [6 empty] | CS |  |  | 2020-03-19 | [11 empty] | 2020-03-19 | [17 empty] | 2020-03-24 | [6 empty] | Yes |  |  |  |  | 2020-05-28 |  |  | 2021-06-04 | Addendum |  |  | 2020-05-28 | [8 empty] | 2020-05-29 | [17 empty] | 2020-06-03 | [15 empty] | 2020-06-18 |  | 2020-06-18 |  | 2020-06-18 | [6 empty] | 750454 |  |  |  |  | 2020-06-19 | 2020-06-19 | 2020-06-22 | 2020-06-22 | 1/ | [16 empty] | Q4 2020 |  |  |  | 10300685860 | [11 empty] | TRUE | TRUE | 175 | 2020-06-19 | 2020-06-19 | 2020 | 2020 | 2020 |  |  |  | 2021-06-04 | Addendum
176 |  | Marshall Ripley | Rick Duperre | 2019-10-15 | [31 empty] | 1 - SPST |  | 668D5 |  |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2020-07-30 | Liam McCormack | Summit Ridge Energy | Gorham ME 1, LLC | 17 Nonesuch Rd Gorham | 2000123496 | 30012292600 | Solar | 4875 | 4.875 | 4831 |  |  | 43.6261 | -70.4341 | Nonesuch Rd |  |  | Gorham | 21 | SPRING STREET | 668D5 | 668T2 |  | 9310-L0339-2240-0010-ED00028 | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-10-18 | 2019-10-22 | 2019-10-29 | 2019-10-18 | 2019-10-21 | 2019-11-06 |  | 2019-11-21 |  | 2019-11-06 | 2019-11-06 | 2019-11-20 |  |  | 2019-11-15 |  |  | CS | 2019-11-15 | [6 empty] | CS |  |  | 2019-11-15 | [11 empty] | 2019-12-11 | [17 empty] | 2019-12-11 | [6 empty] | Yes |  |  |  |  | 2020-02-14 | [6 empty] | 2020-02-17 | [8 empty] | 2020-02-24 | [17 empty] | 2020-03-02 | [15 empty] | 2020-04-15 |  | 2020-04-16 | [13 empty] | 2020-01-15: 2020-05-12; 2020-01-15: 2020-05-12 | [13 empty] | Q3 2020 | 2021-09-28 |  | TBD | 10300678856 | [9 empty] | 9/28/21 2nd Amendment Issued |  | TRUE | TRUE | 176 | 2020-05-12 | 2020-05-12 | 2020 | 2020 | 2020
177 |  | Govinda Neupane |  | 2019-10-15 | 2023-03-09 | wthdw |  | 2023-09-08 | L2_Bump |  | 2023-10-03 | L2_bump | [23 empty] | 3 - CARM |  | 808D3 | 169 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Xander Neve | Syncarpha Solar LLC | CARMEL SOLAR I LLC | FIVE RD CARMEL | 2000125428 | 30013730418 | Solar | [5 empty] | 44.4993 | -69.2575 | Fuller Road |  |  | Carmel | 10 | CARMEL | 808D3 | 808T1 | 12.47 | 9310-L0388-1020-0018-ED00075 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes | Yes |  | K&L Engineering | Bruce Jagolinzer |  | 2019-10-18 | 2019-10-22 | 2019-10-29 | 2019-10-18 | 2019-10-21 | 2021-05-05 | 2021-05-10 | 2021-05-19 | 2021-05-11 | 2021-05-13 | 2021-05-13 | 2021-05-27 |  |  | 2021-05-25 | 2022-02-04 | 2021-11-01 | CS | 2021-06-03 | RS | 2022-02-04 | FC | 2021-10-21 |  |  | CS |  |  | 2021-06-03 | 2022-02-04 | 2021-11-01 |  |  | 2023-10-12 |  |  |  |  | 2021-11-18 |  | 2021-06-07 |  |  |  | 2023-08-10 |  |  |  | 2021-06-18 | 2021-06-18 | 2022-02-10 | 2021-11-18 | [6 empty] | 2021-06-23 | 2022-02-15 | 2021-11-23 | [9 empty] | 2021-09-02 | 2022-03-23 | 2022-01-06 |  |  |  |  | 2021-08-30 | 2022-03-24 | 2022-01-18 | [6 empty] | 2021-08-30 |  | 2022-01-18 | 2023-05-15 | [5 empty] | 2021-08-30 | 2022-03-23 | 2022-01-18 | 2023-06-19 | [5 empty] | 2021-09-08 | 2022-03-24 | 2022-01-18 | 2023-06-22 |  |  |  |  | 2021-09-08 | 2022-04-28 | 2022-01-18 | [5 empty] | 2022-05-06 |  | 2022-05-10 |  | 2022-05-19 |  | 2022-02-07 | 2022-02-14 | [7 empty] | 2023-10-27 | 2020-01-15: 2022-05-23; 2020-01-15: 2022-05-23 | [17 empty] | Requested | [11 empty] | TRUE | TRUE | 177 | 2022-05-23 | 2022-05-23 | 2022 | 2022 | 2022 |  |  |  |  | 2021-09-08
178 |  | Eben Snow | Brent Brooks | 2019-10-15 | [31 empty] | 2 - NORW |  | 435D3 | 170 |  | WITHDRAWN | WITHDRAWN |  | David Kane | LongRoad Development Company LLC | LONGROAD DEVELOPMENT COMPANY LLC | Gravel Pitt Rd Paris | 2000118100 | 30011843437 | Solar | [7 empty] | Gravel Pitt Road |  |  | Paris |  | NORWAY | 435D3 |  |  | 9310-L0170-4500-0147-ED00004 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2019-10-22 | 2019-10-29 |  |  |  |  | 1900-01-12 | [57 empty] | Pending | [69 empty] | 2020-09-15 | [37 empty] | TRUE | TRUE | 178 | 0 | 0 | 1900 | #VALUE! | #VALUE!
179 |  | Lanie Patterson | Brent Brooks | 2019-10-15 | [31 empty] | 7 - MONM |  | 457D1 | 165 |  | WITHDRAWN | WITHDRAWN |  | David Kane | LongRoad Development Company LLC | LONGROAD DEVELOPMENT COMPANY LLC | 2 Blue Rock Rd Leeds | 2000118100 | 30011855449 | Solar | [7 empty] | Blue Rock Road |  |  | Leeds |  | MONMOUTH | 457D1 |  |  | 9310-L0198-3210-0025-ED00066 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2019-10-22 | 2019-10-29 |  |  |  |  | 1900-01-12 | [57 empty] | Pending | [69 empty] | 2020-01-12 | [37 empty] | TRUE | TRUE | 179 | 0 | 0 | 1900 | #VALUE! | #VALUE!
180 |  | Marshall Ripley | Rick Duperre | 2019-10-15 | [31 empty] | 1 - BRML |  | 678D2 |  |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2020-04-28 | Brian | REVISION ENERGY INC | SHAW BROTHERS CONST INC | Array Old Orchard Rd Buxton | 2800393808 | 30011845002 | Solar | 2400 | 2.4 | 5984 |  |  | 43.3612 | -70.3146 | Old Orchard Road |  |  | Buxton | 14 | BAR MILLS | 678D2 | 678T4 |  | 9310-L0356-0820-0057-ED00008 | Non-FERC | TRIGGERING | TRIGGERING ( $375,000 ) | 122449 | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-10-18 | 2019-10-22 | 2019-10-29 | 2019-10-18 | 2019-10-21 | 2019-11-06 |  | 2019-11-21 |  | 2019-11-06 | 2019-11-06 | 2019-11-20 |  |  | 2019-11-20 |  |  | CS | 2019-12-12 | [6 empty] | CS |  |  | 2019-12-12 | [11 empty] | 2019-12-23 | [17 empty] | 2019-12-23 | [6 empty] | Yes |  |  |  |  | 2020-02-27 |  |  | 2021-06-04 | Addendum |  |  | 2020-02-27 | [8 empty] | 2020-02-27 | [17 empty] | 2020-03-05 | [15 empty] | 2020-03-11 |  | 2020-03-11 | [8 empty] | 138693 |  |  |  |  | 2020-01-15: 2020-03-19; 2020-01-15: 2020-03-19 | [13 empty] | Q3 2020 |  |  | 43927 | 10300653256 | [11 empty] | TRUE | TRUE | 180 | 2020-03-19 | 2020-03-19 | 2020 | 2020 | 2020 |  |  |  | 2021-06-04 | Addendum
181 |  | Lanie Patterson | Brent Brooks | 2019-10-15 | [31 empty] | 2 - UNIT |  | 860D2 | 21 |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2020-07-30 | Nate Niles | REVISION ENERGY INC | Community Solar New England, LLC | Route 137 And Curra Rd, Knox | 2000038393 | 30013530073 | Solar | 1500 | 1.5 | 1950 |  |  | 44.5356 | -69.2751 | Curra Rd |  |  | Knox | 3 | UNITY | 860D2 | 860T1 |  | 9310-L0443-3110-0005-ED00004 | Non-FERC | TRIGGERING | TRIGGERING ($330,000) | 66478.65 | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-10-18 | 2019-10-22 | 2019-10-29 | 2019-10-18 | 2019-10-21 | 2019-12-05 |  | 2019-12-19 |  | 2019-12-05 | 2019-12-05 | 2019-12-19 |  |  | 2019-12-19 |  |  | CS | 2020-01-29 | [6 empty] | CS |  |  | 2020-01-29 | [11 empty] | 2020-02-12 | [17 empty] | 2020-02-20 | [6 empty] | Pending |  |  |  |  | 2020-04-24 |  |  | 2021-06-11 | Addendum |  |  | 2020-04-24 | [8 empty] | 2020-04-16 | [17 empty] | 2020-04-20 | [15 empty] | 2020-05-12 |  | 2020-06-04 | [8 empty] | 1336361 |  |  |  |  | 2020-01-15: 2020-06-17; 2020-01-15: 2020-06-17; 2020-09-17: 2021-09-29; 2020-09-17: 2021-10-05 | [13 empty] | Q4 2020 |  |  | TBD | 10300684324 | [11 empty] | TRUE | TRUE | 181 | 2020-06-17 | 2020-06-17 | 2020 | 2020 | 2020 |  |  |  | 2021-06-11 | Addendum
182 |  | Govinda Neupane |  | 2019-10-15 | [31 empty] | 2 - WSTN |  | 866D2 | 51 |  | WITHDRAWN | WITHDRAWN |  | Mike Imoto | MEVS LLC AKA CENERGY | BAP POWER CORP | Back Rd, Skowhegan | 2000122114 | 30011759294 | Solar | [7 empty] | Back Rd |  |  | Skowhegan |  | WESTON HYDRO | 866D2 |  |  | 86-Withdrawn-86d | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2019-10-22 | 2019-10-29 |  |  |  |  | 1900-01-12 | [57 empty] | Pending | [69 empty] | 2020-02-03 | [37 empty] | TRUE | TRUE | 182 | 0 | 0 | 1900 | #VALUE! | #VALUE!
183 |  | Lanie Patterson | Brent Brooks | 2019-10-15 | [31 empty] | 2 - FAIR |  | 817D1 | 1 |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2021-12-17 | Tyler William Perkins | Nexamp, Inc | MSD GUIMOND LLC | 3 Franklin Dr #1, Fairfield | 2000151040 | 30012199904 | Solar | 4980 | 4.98 | 6676 |  |  | 44.5829 | -69.6235 | 3 Franklin Drive |  |  | Fairfield | 3 | FAIRFIELD | 817D1 | 817T1 |  | FLOC-MISSING-01142021 | Non-FERC | COST SHARE | COST SHARE (325,000) | 156706.55 | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-10-21 | 2019-10-22 | 2019-10-29 | 2019-10-21 | 2019-10-29 | 2019-11-07 |  | 2019-11-22 |  | 2019-11-07 | 2019-11-07 | 2019-11-21 |  |  | 2019-11-12 |  |  | CS | 2019-11-12 | [6 empty] | CS |  |  | 2019-11-12 | [11 empty] | 2019-12-11 | [17 empty] | 2019-12-11 | [6 empty] | Yes |  |  |  |  | 2020-02-14 |  |  | 2021-06-11 | Addendum |  |  | 2020-02-17 | [8 empty] | 2020-02-21 | [17 empty] | 2020-02-25 | [13 empty] | 2021-06-21 |  | 2020-03-17 |  | 2020-03-18 | 2022-07-01 | 2022-07-11 | [6 empty] | 198752 |  |  |  |  | 2020-04-16 | 2020-04-16 | 2021-07-20 | 2021-07-20 |  | 2022-07-12 | [15 empty] | Q3 2021 |  |  | TBD | 10300678595 | [11 empty] | TRUE | TRUE | 183 | 2020-04-16 | 2020-04-16 | 2020 | 2020 | 2020 | 44368 |  |  | 2021-06-11 | Addendum
184 |  | Govinda Neupane |  | 2019-10-15 | [31 empty] | 2 - SKTP |  | 864D1 | 153 |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2021-12-17 | Mike Imoto | MEVS LLC AKA CENERGY | MSD Galbraith LLC | 83 Norridgewock Ave P1 Skowhegan | 2000151043 | 30012199938 | Solar | 1453 | 1.453 | 2381 |  |  | 44.7662 | -69.7357 | 83 Norridgewock Ave |  |  | Skowhegan | 20.5 | SKOWHEGAN TAP | 864D1 | 864T1 |  | FLOC-MISSING-01142021 | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-10-23 | 2019-10-22 | 2019-10-29 | 2019-10-23 | 2019-10-29 | 2020-04-13 |  | 2020-04-28 |  | 2020-04-13 | 2020-04-13 | 2020-04-28 |  |  | 2020-04-28 | 2020-10-20 | 2020-07-24 | CS | 2020-04-28 | RS | 2020-10-20 | FAC |  |  |  | CS |  |  | 2020-04-28 | 2020-10-20 | 2020-07-24 | [9 empty] | 2020-04-29 | [17 empty] | 2020-05-01 | 2020-10-21 | 2020-08-28 |  |  |  |  | Yes |  |  |  |  | 2020-07-07 | 2020-12-07 | 2020-10-13 | 2021-09-27 | Report |  |  | 2020-07-07 | 2020-12-18 | 2020-09-02 | [6 empty] | 2020-07-10 | 2020-12-22 | 2020-10-05 | [15 empty] | 2020-07-16 | 2020-12-24 | 2020-10-05 | [5 empty] | 2020-07-16 | 2020-12-24 | 2020-10-05 |  |  |  |  | 2021-09-27 | 2021-11-08 |  | 2022-02-14 |  | 2021-11-30 | [6 empty] | 439353 | 2021-09-22 |  |  |  | 2020-01-15: 2021-12-02; 2020-01-15: 2021-12-02 |  |  | 2023-05-02 | 2023-05-02 | [9 empty] | Q4 2021 |  |  |  | Requested | [11 empty] | TRUE | TRUE | 184 | 2021-12-02 | 2021-12-02 | 2021 | 2021 | 2021 |  | 44466 |  | 2021-09-27 | Report
185 |  | Govinda Neupane |  | 2019-10-15 | [29 empty] | 1 - SKTP |  | 3 - SKTP |  | 864D1 | 184 |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED |  | Mike Imoto | MEVS LLC AKA CENERGY | MSD Galbraith LLC | 83 Norridgewock Ave P2 Skowhegan | 2000141274 | 30012053838 | Solar | 996 | 0.996 | 1377 |  |  | 44.7712 | -69.7422 | 83 Norridgewock Ave |  |  | Skowhegan | 20 | SKOWHEGAN TAP | 864D1 | 864T1 | 12.47 | FLOC-MISSING-01142021 | Non-FERC | TRIGGERING | TRIGGERING (290,000) | 144782 | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-10-23 | 2019-10-22 | 2019-10-29 | 2019-10-23 | 2019-10-29 | 2021-12-02 | 2021-12-20 | 2021-12-16 | 2021-12-30 | 2021-12-30 | 2021-12-30 | 2022-01-14 |  |  | 2022-01-13 |  |  | CS | 2022-01-13 | [6 empty] | CS |  |  | 2022-01-13 | [11 empty] | 2022-01-19 | 2022-01-13 | [6 empty] | 2022-01-19 | 2022-01-19 | 2022-01-13 | [7 empty] | 2022-01-24 | [11 empty] | 2022-03-29 | [6 empty] | 2022-03-28 | [8 empty] | 2022-03-28 | [8 empty] | 2022-03-29 | [8 empty] | 2022-03-29 | [7 empty] | 2022-03-29 | [7 empty] | 2022-05-25 |  | 2022-05-31 | 2022-07-22 | 2022-07-29 | 2022-07-28 | [5 empty] | 869982 | 2022-05-09 | 835428 | 2022-09-12 |  | 2020-01-15: 2022-07-29; 2020-01-15: 2022-07-29; 2020-09-17: 2023-05-12; 2020-09-17: 2023-05-15 | [13 empty] | Q3 2025 |  |  |  | Requested | [11 empty] | FALSE | TRUE | 185 | 2022-07-29 | 2022-07-29 | 2022 | 2022 | 2022
186 |  |  | KRISTOFER COLEMAN | 2019-10-15 | [31 empty] | 2 - MAYA |  | 274D1 | 93 |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2020-10-05 | Jonovan (Jonny) Lizama | Luminace | MSD Wiscasset LLC | 96 Chewonki Neck Rd P2 Wiscass | 2000152902 | 30012228265 | Solar | 4950 | 4.95 | 6765 |  |  | 43.9602 | -69.705 | Old Ferry Road |  |  | Wiscasset | 520 | MAINE YANKEE | 274D1 | 274T2 |  | 9310-L0111-6463-0034-ED00083 | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-10-21 | 2019-10-22 | 2019-10-29 | 2019-10-21 | 2019-10-29 | 2020-04-13 |  | 2020-04-28 |  | 2020-04-13 | 2020-04-13 | 2020-04-28 |  |  | 2020-04-28 | 2021-06-15 |  | CS | 2020-04-28 | RS | 2021-06-15 |  |  |  |  | CS |  |  | 2020-04-28 | 2021-06-15 | [10 empty] | 2020-04-29 | [17 empty] | 2020-05-01 | 2021-06-24 | [5 empty] | Pending |  |  |  |  | 2020-07-07 | 2021-07-06 | [5 empty] | 2020-07-06 | 2021-07-12 | [7 empty] | 2020-07-07 | [17 empty] | 2020-07-15 | [15 empty] | 2020-07-17 |  | 2020-08-13 | [13 empty] | 2020-01-15: 2020-08-18; 2020-01-15: 2020-08-18; 2020-09-17: 2021-07-13; 2020-09-17: 2021-07-13 | [13 empty] | Q3 2020 |  |  |  | 10300701628 | [11 empty] | TRUE | TRUE | 186 | 2020-08-18 | 2020-08-18 | 2020 | 2020 | 2020
187 |  | Govinda Neupane |  | 2019-10-15 | [31 empty] | 4 - STUR |  | 858D1A | 158 |  | WITHDRAWN | WITHDRAWN |  | John Motta | Dynamic Energy | DYNAMIC ENERGY SOLUTIONS LLC | Us Route 2 Farmington | 2000110140 | 30011860811 | Solar | [7 empty] | US-2 |  |  | Farmington |  | STURTEVANT | 858D1A |  |  | 86-Withdrawn-86d | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2019-10-22 | 2019-10-29 |  |  |  |  | 1900-01-12 | [57 empty] | Pending | [69 empty] | 2020-01-21 | [37 empty] | TRUE | TRUE | 187 | 0 | 0 | 1900 | #VALUE! | #VALUE!
188 |  | Eben Snow | Brent Brooks | 2019-10-17 | [31 empty] | 3 - BR34 |  | 406D4 | 138 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Xander Neve | Syncarpha Solar LLC | NAPLES SOLAR 1 LLC | Lands Mill Rd (Naples) | 2000125427 | 30011808547 | Solar | [5 empty] | 43.97 | -70.635 | Lambs Mills Rd |  |  | Naples | 5 | BRIDGTON 34 KV | 406D4 | 34kV Bus at substation | 12.47 | 9310-L0501-4040-0030-ED00001 | Non-FERC | WITHDRAWN | WITHDRAWN | NONE | Yes | Yes |  | K&L Engineering | Bruce Jagolinzer |  | 2019-10-21 | 2019-10-24 | 2019-10-31 | 2019-10-21 | 2019-10-29 | 2020-11-17 |  | 2020-12-03 |  | 2020-11-17 | 2020-11-18 | 2020-12-04 |  |  | 2020-12-02 | 2021-08-16 |  | CS | 2020-12-02 | RS | 2021-08-16 |  |  |  |  | CS |  |  | 2020-12-02 | 2021-08-16 | [10 empty] | 2020-12-02 | [17 empty] | 2020-12-14 | 2021-08-31 | [10 empty] | 2021-02-19 | 2021-10-14 |  | 2021-05-25 | Report |  |  | 2021-05-25 | 2021-11-12 | [7 empty] | 2021-05-25 | 2021-11-11 | [16 empty] | 2021-06-08 | 2021-11-16 | [6 empty] | 2021-06-08 | 2021-11-16 |  |  |  |  | 2021-06-08 | 2021-06-08 |  |  | 2021-12-09 | 2022-12-05 |  | 2022-12-05 | 2023-07-03 | 2023-07-10 |  |  |  | 750871 |  | 1049151 | 2022-11-30 | 2023-08-24 | 2020-01-15: 2021-12-30; 2020-01-15: 2021-12-30; 2020-09-17: 2022-12-06; 2020-09-17: 2022-12-07 | [17 empty] | Requested | [11 empty] | TRUE | TRUE | 188 | 2021-12-30 | 2021-12-30 | 2021 | 2021 | 2021 | 44355 | 44355 |  | 2021-05-25 | Report
189 |  |  | KRISTOFER COLEMAN | 2019-10-17 | [31 empty] | 1 - MESS |  | 238D1 |  |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2020-08-31 | Zach Schrowang | Syncarpha Solar LLC | WISCASSET SOLAR 1 LLC | Jones Rd Wiscasset | 2000128081 | 30011849996 | Solar | 4950 | 4.95 | 4795 |  |  | 44.0181 | -69.7405 | Lowelltown Rd |  |  | Wiscasset | 45 | MESSINA | 238D1 | 238T1 | 12.47 | 9310-L0068-6463-0061-ED00078 | Non-FERC | TRIGGERING | TRIGGERING (325,000) | 271519 | Yes | Yes |  | K&L Engineering | Bruce Jagolinzer |  | 2019-10-21 | 2019-10-24 | 2019-10-31 | 2019-10-21 | 2019-10-29 | 2019-11-07 |  | 2019-11-22 |  | 2019-11-07 | 2019-11-07 | 2019-11-21 |  |  | 2019-11-12 |  |  | CS | 2019-11-12 | [6 empty] | CS |  |  | 2019-11-12 | [11 empty] | 2020-01-27 | 2020-03-06 | [16 empty] | 2020-04-02 | [6 empty] | Pending |  |  |  |  | 2020-06-08 |  |  | 2021-06-11 | Addendum |  |  | 2020-06-08 | [8 empty] | 2020-06-08 | [17 empty] | 2020-06-15 | [13 empty] | 2021-06-16 |  | 2020-06-16 |  | 2020-06-17 | [8 empty] | 866470 |  |  |  |  | 2020-01-15: 2020-07-23; 2020-01-15: 2020-07-23; 2020-09-17: 2021-07-01; 2020-09-17: 2021-07-01 | [13 empty] | Q4 2020 |  |  |  | 10300692497 | [11 empty] | TRUE | TRUE | 189 | 2020-07-23 | 2020-07-23 | 2020 | 2020 | 2020 | 44363 |  |  | 2021-06-11 | Addendum
190 |  | Lanie Patterson | Brent Brooks | 2019-10-17 | [31 empty] | 1 - PITT |  | 842D1 |  |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Xander Neve | Syncarpha Solar LLC | PITTSFIELD SOLAR 1 LLC | Mccarty Rd / Pittsfield Me 04967 | 2000125460 | 30011808562 | Solar | [5 empty] | 44.7742 | -69.3978 | Main Street |  | Main Street | Pittsfield | 816 | PITTSFIELD | 842D1 | 842T1 |  | 9310-L0425-4650-0064-ED00078 | Non-FERC | WITHDRAWN | WITHDRAWN | NONE | Yes | Yes |  | K&L Engineering | Bruce Jagolinzer |  | 2019-10-21 | 2019-10-24 | 2019-10-31 | 2019-10-21 | 2019-10-31 | 2019-11-12 |  | 2019-11-26 |  | 2019-11-12 | 2019-11-12 | 2019-11-26 |  |  | 2019-11-12 |  |  | CS | 2019-11-12 | [6 empty] | CS |  |  | 2019-11-12 | [11 empty] | 2020-03-06 | [17 empty] | 2020-04-03 | [6 empty] | Pending |  |  |  |  | 2020-06-09 |  |  | 2021-05-20 | Addendum |  |  | 2020-06-08 | [8 empty] | 2020-06-15 | [17 empty] | 2020-06-22 | [13 empty] | 2021-06-14 |  | 2020-07-10 |  | 2020-07-13 | 2022-12-06 |  | 2022-12-07 | [5 empty] | 249719 |  | 153519 | 2022-12-05 | 2024-09-18 | 2020-07-23 | 2020-07-23 | 2021-07-01 | 2021-07-01 | 2023-09-06 | 2023-09-06 | [19 empty] | 10300692560 | [11 empty] | TRUE | TRUE | 190 | 2020-07-23 | 2020-07-23 | 2020 | 2020 | 2020 | 44361 |  |  | 2021-05-20 | Addendum
191 |  |  | Anthony Boucher | 2019-10-17 | [31 empty] | 2 - WALD |  | 252D2 | 122 |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2021-03-30 | Zach Schrowang | Syncarpha Solar LLC | WALDOBORO SOLAR 1 LLC | Controversy Ln (Waldoboro) | 2000125463 | 30011808703 | Solar | 4950 | 4.95 | 7001 |  |  | 44.1186 | -69.4372 | Controversy Lane |  |  | Waldoboro | 8 | WALDOBORO | 252D2 | 252T1 |  | 9310-L0091-6135-0009-ED00013 | Non-FERC | TRIGGERING | TRIGGERING | 325000 | Yes | Yes |  | K&L Engineering | Bruce Jagolinzer |  | 2019-10-21 | 2019-10-24 | 2019-10-31 | 2019-10-21 | 2019-10-31 | 2020-05-05 |  | 2020-05-19 |  | 2020-05-05 | 2020-05-05 | 2020-05-19 |  |  | 2020-05-13 |  |  | CS | 2020-05-13 | [6 empty] | CS |  |  | 2020-05-13 | [11 empty] | 2020-05-26 | [17 empty] | 2020-06-04 | [6 empty] | Pending |  |  |  |  | 2020-08-07 |  |  | 2021-06-11 | Addendum |  |  | 2020-08-07 | [8 empty] | 2020-08-07 | [17 empty] | 2020-08-12 | [13 empty] | 2021-06-16 |  | 2020-09-01 |  | 2020-09-02 | [8 empty] | 661976 |  |  |  |  | 2020-01-15: 2020-10-27; 2020-01-15: 2020-10-27; 2020-09-17: 2021-07-01; 2020-09-17: 2021-07-01 | [13 empty] | Q4 2020 |  |  |  | 10300708433 | 10300808785 | [10 empty] | TRUE | TRUE | 191 | 2020-10-27 | 2020-10-27 | 2020 | 2020 | 2020 | 44363 |  |  | 2021-06-11 | Addendum
192 |  | Govinda Neupane |  | 2019-10-17 | [31 empty] | 2 - DOVE |  | 815D2 | 12 |  | WITHDRAWN | WITHDRAWN |  | Nate Niles | REVISION ENERGY INC | REVISION ENERGY INC | Reservoir Rd Dover Foxcroft | 2800693910 | 30011814073 | Solar | [7 empty] | Airport Rd |  |  | Dover-Foxcroft |  | DOVER | 815D2 |  |  | 86-Withdrawn-86d | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2019-10-24 | 2019-10-31 |  |  |  |  | 1900-01-12 | [57 empty] | Pending | [69 empty] | 2020-03-05 | [37 empty] | TRUE | TRUE | 192 | 0 | 0 | 1900 | #VALUE! | #VALUE!
193 |  | Lanie Patterson | Brent Brooks | 2019-10-17 | [31 empty] | 8 - MONM |  | 457D2 | 179 |  | WITHDRAWN | WITHDRAWN |  | Eric Weinstein | BORREGO SOLAR SYSTEMS INC | 510 PV PROJECT DEVELOPMENT LLC | 57 Prescott Hill Rd Monmouth | 2000113260 | 30011831572 | Solar/Battery | [7 empty] | 57 Prescott Hill Road |  |  | Monmouth |  | MONMOUTH | 457D2 |  |  | 9310-L0199-3740-0080-ED00001 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2019-10-24 | 2019-10-31 |  |  |  |  | 1900-01-12 | [57 empty] | Pending | [69 empty] | 2020-02-17 | [37 empty] | TRUE | TRUE | 193 | 0 | 0 | 1900 | #VALUE! | #VALUE!
194 |  | Govinda Neupane |  | 2019-10-18 | [31 empty] | 1 - ANSO |  | 801D1 |  |  | WITHDRAWN | WITHDRAWN |  | Nate Niles | REVISION ENERGY INC | REVISION ENERGY INC | 272 Anson Rd Starks Maine | 2800693910 | 30011863906 | Solar | [7 empty] | 272 Anson Road |  |  | Starks |  | ANSON | 801D1 |  |  | 86-Withdrawn-86d | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2019-10-25 | 2019-11-01 |  |  |  |  | 1900-01-12 | [57 empty] | Pending | [69 empty] | 2019-11-19 | [37 empty] | TRUE | TRUE | 194 | 0 | 0 | 1900 | #VALUE! | #VALUE!
195 |  | Lanie Patterson | Brent Brooks | 2019-10-18 | [31 empty] | 3 - BLRD |  | 207D2 | 123 |  | WITHDRAWN | WITHDRAWN |  | Nate Niles | REVISION ENERGY INC | REVISION ENERGY INC | 2495 N Belfast Ave / Augusta | 2800693910 |  | Solar | [7 empty] | 2495 North Belfast Ave |  |  | Augusta |  | BLAIR ROAD | 207D2 |  |  | 9310-L0020-0240-0252-ED00567 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2019-10-25 | 2019-11-01 |  |  |  |  | 1900-01-12 | [57 empty] | Pending | [69 empty] | 2020-05-28 | [37 empty] | TRUE | TRUE | 195 | 0 | 0 | 1900 | #VALUE! | #VALUE!
196 |  | Govinda Neupane |  | 2019-10-18 | [31 empty] | 3 - WSTN |  | 866D1 | 182 |  | WITHDRAWN | WITHDRAWN |  | Nate Niles | REVISION ENERGY INC | REVISION ENERGY INC | 119 Eaton Mtn Rd Skowhegan | 2000038393 |  | Solar | [7 empty] | Swain Hill Road/Eaton Mtn Rd |  |  | Skowhegan |  | WESTON HYDRO | 866D1 |  |  | 86-Withdrawn-86d | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2019-10-25 | 2019-11-01 |  |  |  |  | 1900-01-12 | [57 empty] | Pending | [69 empty] | 2020-02-03 | [37 empty] | TRUE | TRUE | 196 | 0 | 0 | 1900 | #VALUE! | #VALUE!
197 |  | Govinda Neupane |  | 2019-10-18 | [31 empty] | 4 - WSTN |  | 866D1 | 196 |  | WITHDRAWN | WITHDRAWN |  | Nate Niles | REVISION ENERGY INC | REVISION ENERGY INC | 328 Eaton Mountain Rd / Skowhegan | 2800693910 | 30011857817 | Solar | [7 empty] | 328 Eaton Mtn Rd |  |  | Skowhegan |  | WESTON HYDRO | 866D1 |  |  | 86-Withdrawn-86d | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2019-10-25 | 2019-11-01 |  |  |  |  | 1900-01-12 | [57 empty] | Pending | [69 empty] | 2020-02-03 | [37 empty] | TRUE | TRUE | 197 | 0 | 0 | 1900 | #VALUE! | #VALUE!
198 |  |  | KRISTOFER COLEMAN | 2019-10-21 | [31 empty] | 1 - LISB |  | 231D2 |  |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Jamal Batar | Dimension Renewable Energy | LISBON CSG LLC | 57 Upland Rd, Lisbon | 2000155111 | 30012263072 | Solar | [5 empty] | 44.3082 | -70.0921 | 57 Upland Rd |  |  | Lisbon | 24 | LISBON | 231D2 | 231T1 |  | 9310-L0060-3310-0126-ED00025 | Non-FERC | WITHDRAWN | WITHDRAWN | 325000 | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-10-23 | 2019-10-28 | 2019-11-04 | 2019-10-23 | 2019-10-31 | 2019-11-12 |  | 2019-11-26 |  | 2019-11-12 | 2019-11-12 | 2019-11-26 |  |  | 2019-11-26 |  |  | CS | 2020-01-30 | [6 empty] | CS |  |  | 2020-01-30 | [11 empty] | 2020-02-03 | [17 empty] | 2020-02-12 | [6 empty] | Pending |  |  |  |  | 2020-04-16 |  |  | 2021-06-03 | Addendum |  |  | 2020-04-17 | [8 empty] | 2020-04-14 | [17 empty] | 2020-04-17 | [13 empty] | 2021-06-09 |  | 2020-04-27 |  | 2020-04-28 | [8 empty] | 161988 |  |  |  | 2024-10-18 | 2020-01-15: 2020-05-18; 2020-01-15: 2020-05-18; 2020-09-17: 2021-07-20; 2020-09-17: 2021-07-20 | [16 empty] | TBD | 10300678806 | [11 empty] | TRUE | TRUE | 198 | 2020-05-18 | 2020-05-18 | 2020 | 2020 | 2020 | 44356 |  |  | 2021-06-03 | Addendum
199 |  | Eben Snow | Brent Brooks | 2019-10-21 | [31 empty] | 4 - OXFO |  | 437D1 | 146 |  | WITHDRAWN | WITHDRAWN |  | Nate Niles | REVISION ENERGY INC | REVISION ENERGY INC | Main Street, Oxford | 2000038393 | 30011796586 | Solar | [7 empty] | 103 Main St |  |  | Oxford |  | OXFORD | 437D1 |  |  | 9310-L0178-4420-0075-ED00102 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2019-10-28 | 2019-11-04 |  |  |  |  | 1900-01-12 | [57 empty] | Pending | [69 empty] | 2020-01-12 | [37 empty] | TRUE | TRUE | 199 | 0 | 0 | 1900 | #VALUE! | #VALUE!
200 |  | Eben Snow | Brent Brooks | 2019-10-21 |  |  |  | 2023-01-05 | L2_Bump | [26 empty] | 5 - LEED | 1 - LEED | 471D1 | 152 | Yes | EXECUTED | EXECUTED |  | Xander Neve | Syncarpha Solar LLC | LIVERMORE SOLAR 1 LLC | Federal Rd Livermore | 2000128082 | 30011850119 | Solar | 999 | 0.999 | 1248.48 |  |  | 44.3678 | -70.2478 | North Turner Road |  |  | Livermore | 172 | LEEDS | 471D1 | 471T1 | 34.5 | 9310-L0209-3345-0023-ED00028 | Non-FERC | TRIGGERING | TRIGGERING (375,000) | 62468 | Yes | Yes |  | K&L Engineering | Bruce Jagolinzer |  | 2019-10-23 | 2019-10-28 | 2019-11-04 | 2019-10-23 | 2019-10-31 | 2021-11-24 | 2021-11-30 | 2021-12-10 | 2021-11-30 | 2021-12-02 | 2021-12-02 | 2021-12-16 |  |  | 2021-12-15 |  |  | CS | 2021-12-16 | [6 empty] | CS |  |  | 2021-12-16 |  |  | 2024-01-31 | 2024-02-24 | [7 empty] | 2021-12-16 |  |  |  | 2024-03-07 |  |  |  | 2021-12-30 | 2021-12-30 |  |  |  | 2024-03-12 |  |  |  |  | 2022-01-04 |  |  |  | 2024-03-12 | [7 empty] | 2022-03-10 | [6 empty] | 2022-03-02 |  |  |  | 2024-05-16 |  |  |  |  | 2022-03-03 |  |  | 2024-05-16 | [5 empty] | 2022-03-04 |  |  | 2024-05-21 | [5 empty] | 2022-03-07 |  |  | 2024-05-24 |  |  |  |  | 2022-03-07 |  |  | 2024-05-24 |  |  |  |  | 2022-03-08 |  | 2022-03-11 | 2023-03-20 | 2022-03-20 | [6 empty] | 364593 |  | 679914 | 2024-05-15 |  | 2022-03-21 | 2022-03-22 |  | 2022-05-18 | 2024-07-01 | 2024-07-01 | [15 empty] | Q4 2023 |  |  |  | Requested | [11 empty] | TRUE | TRUE | 200 | 2022-03-21 | 2022-03-21 | 2022 | 2022 | 2022
201 |  | Lanie Patterson | Brent Brooks | 2019-10-21 | 2022-06-09 | L2_Bump |  | 2023-07-27 | L2_bump | [24 empty] | 1 - UNIT |  | 3 - UNIT |  | 860D1 | 181 | Yes | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED |  | Zach Schrowang | Syncarpha Solar LLC | TROY SOLAR 1 LLC | Bangor Rd Troy | 2000129088 | 30011865596 | Solar | 995 | 0.995 | 1472.25 |  |  | 44.6564 | -69.2881 | Bangor Rd |  |  | Troy | 142 | UNITY | 860D1 | 860T1 |  | 9310-L0442-5870-0003-ED00043 | Non-FERC | COST SHARE | COST SHARE ($330,000) | 219319.55 | Yes | Yes |  | K&L Engineering | Bruce Jagolinzer |  | 2019-10-23 | 2019-10-28 | 2019-11-04 | 2019-10-23 | 2019-10-31 | 2020-07-08 |  | 2020-07-22 |  | 2020-07-08 | 2020-07-10 | 2020-07-24 |  |  | 2020-07-21 | 2023-03-21 |  | CS | 2020-07-21 | [6 empty] | CS |  |  | 2020-07-21 | 2023-03-21 | 2022-10-19 | 2022-06-23 | 2023-03-21 | [5 empty] | 2022-10-19 |  | 2020-07-28 | 2023-04-04 | 2022-10-19 | 2022-07-15 | 2023-04-05 | [5 empty] | 2021-04-18 | 2022-10-19 |  | 2023-04-19 |  |  |  |  | 2020-08-07 | 2023-04-18 | 2022-11-11 | 2022-07-19 | 2023-04-19 |  |  | Pending |  |  |  |  | 2020-10-13 | 2023-06-01 | 2023-01-20 | 2021-06-08 | Addendum |  |  | 2020-10-13 | 2023-06-01 | 2023-02-09 | 2022-08-30 | 2023-06-01 |  |  |  | 2022-08-31 | 2020-10-20 | 2023-06-01 | 2023-02-09 | 2022-08-31 | 2023-06-01 |  |  |  |  | 2020-10-26 | 2023-06-07 | 2023-02-14 | 2022-09-16 | 2023-06-06 |  |  |  |  | 2020-10-26 | 2023-06-07 | 2023-02-15 | 2022-09-19 | [5 empty] | 2023-06-07 | 2023-02-15 |  |  |  | 2021-06-15 |  | 2020-10-26 |  | 2020-10-26 | 2023-06-08 |  | 2023-06-08 | [5 empty] | 603124 | 2023-02-07 | 226090 | 2023-06-01 |  | 2020-11-08 | 2020-11-08 | 2021-06-30 | 2021-06-30 | 2023-06-09 | 2023-06-09 | [15 empty] | Q2 2025 |  |  |  | 10300733828 | [11 empty] | FALSE | TRUE | 201 | 2020-11-08 | 2020-11-08 | 2020 | 2020 | 2020 | 44362 |  |  | 2021-06-08 | Addendum
202 |  | Marshall Ripley | Rick Duperre | 2019-10-21 | [31 empty] | 2 - SWRD |  | 682D2 | 127 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Kelsey Haley | New Leaf Energy, Inc | 510 PV PROJECT DEVELOPMENT LLC | 464 Roosevelt Trl Windham | 2000113260 | 30011840094 | Solar/Battery | [5 empty] | 43.809 | -70.4156 | 464 Roosevelt Trail |  |  | Windham | 174 | SWETT ROAD | 682D2 | 682T1 |  | 9310-L0361-6390-0101-ED00146 | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-10-23 | 2019-10-28 | 2019-11-04 | 2019-10-23 | 2019-10-31 | 2020-04-17 |  | 2020-05-04 |  | 2020-04-17 | 2020-04-17 | 2020-05-04 |  |  | 2020-04-23 |  |  | CS | 2020-04-23 | [6 empty] | CS |  |  | 2020-04-23 | [11 empty] | 2020-04-27 | [17 empty] | 2020-04-28 | [6 empty] | Pending |  |  |  |  | 2020-07-01 |  |  | 2021-05-19 | Addendum |  |  | 2020-06-29 | [8 empty] | 2020-07-06 | [17 empty] | 2020-07-09 | [13 empty] | 2021-06-03 |  | 2020-07-13 |  | 2020-07-14 | 2023-03-22 |  | 2023-04-14 | 2024-11-21 |  |  |  |  | 174198 |  | 181334 | 2023-03-08 | 2025-12-18 | 2020-07-24 | 2020-07-24 | 2021-06-18 | 2021-06-18 | 2023-04-18 | 2023-04-18 | [15 empty] | Q3 2021 |  |  |  | 10300692572 | [11 empty] | TRUE | TRUE | 202 | 2020-07-24 | 2020-07-24 | 2020 | 2020 | 2020 | 44350 |  |  | 2021-05-19 | Addendum
203 |  |  | Anthony Boucher | 2019-10-21 | [31 empty] | 1 - SEAR |  | 850D1 |  |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2020-04-28 | Tyler William Perkins | Nexamp, Inc | SEARSPORT SOLAR 1 LLC | 100 Turnpike Rd Searsport | 2000173010 | 30012531163 | Solar/Battery | 4990 | 4.99 | 5414 | 4990 |  | 44.4795 | -68.8901 | 100 Turnpike Road |  |  | Searsport | 7H | SEARSPORT | 850D1 | 850T1 |  | 9310-L0427-5220-0075-ED00022 | Non-FERC | TRIGGERING | TRIGGERING (325,000) | 270788 | Under Review 1/31/2020 |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-10-29 | 2019-10-28 | 2019-11-04 | 2019-10-29 | 2019-10-31 | 2019-10-31 |  | 2019-11-15 |  | 2019-10-31 | 2019-11-14 | 2019-10-31 |  |  | 2019-10-31 |  |  | CS | 2019-10-31 | [6 empty] | CS |  |  | 2019-10-31 | [11 empty] | 2019-11-20 | [17 empty] | 2019-11-20 | [6 empty] | Yes |  |  |  |  | 2020-01-24 |  |  | 2021-05-18 | Addendum |  |  | 2020-01-29 | [8 empty] | 2020-01-31 | [31 empty] | 2021-05-27 |  | 2020-02-07 |  | 2020-02-07 | [8 empty] | 408471 |  |  |  |  | 2020-01-15: 2020-03-02; 2020-01-15: 2020-03-02; 2020-09-17: 2021-06-22; 2020-09-17: 2021-06-22 | [13 empty] | Q2 2021 |  |  | 43914 | 10300649815 | [11 empty] | TRUE | TRUE | 203 | 2020-03-02 | 2020-03-02 | 2020 | 2020 | 2020 | 44343 |  |  | 2021-05-18 | Addendum
204 |  | Govinda Neupane |  | 2019-10-22 | [31 empty] | 5 - STUR |  | 858D1A | 187 |  | WITHDRAWN | WITHDRAWN |  | TJ Murphy | Environomics | 414 FFR SOLAR FARM 3 LLC | 414 Farmington Fall Rd Farmington | 2000129977 | 30011878482 | Solar | [5 empty] | 44.6566 | -70.1125 | 414 Farmington Falls Rd |  |  | Farmington |  | STURTEVANT | 858D1A |  |  | 9310-L0437-2030-0043-ED00012 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2019-10-29 | 2019-11-05 |  |  |  |  | 1900-01-12 | [57 empty] | No Study | [69 empty] | 2021-07-09 | [37 empty] | TRUE | TRUE | 204 | 0 | 0 | 1900 | #VALUE! | #VALUE!
205 |  | Lanie Patterson | Brent Brooks | 2019-10-22 | 2022-06-09 | L2_Bump | RQP-1 | 2023-07-27 | L2_bump | [24 empty] | 2 - UNIT | 201 | 4 - UNIT |  | 860D2 | 201 | Yes | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED |  | Zach Good | Aligned Solar Partners | LEONARD ROAD THORNDIKE SOLAR LLC | 130 Leonard Rd, Thorndike | 2000211887 | 30013044588 | Solar | 996 | 0.996 | 2475 |  |  | 44.5694 | -69.2731 | 130 Leonard Road |  |  | Thorndike | 8 | UNITY | 860D2 | 860T1 | 12.47 | FLOC-MISSING-01142021 | Non-FERC | COST SHARE | COST SHARE ($330,000) | 44141.81 | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-10-29 | 2019-10-29 | 2019-11-05 | 2019-10-29 | 2019-10-31 | 2020-11-16 |  | 2020-12-02 |  | 2020-11-16 | 2020-11-17 | 2020-12-03 |  |  | 2020-11-30 |  |  | CS | 2020-11-30 | [6 empty] | CS |  |  | 2020-11-30 |  |  | 2023-06-09 | 2023-07-28 | [7 empty] | 2020-12-02 |  |  | 2023-06-15 | 2023-06-15 | [8 empty] | 2023-06-20 |  |  |  |  | 2020-12-02 |  |  | 2023-06-21 | 2023-08-22 | [7 empty] | 2021-02-08 |  |  | 2021-06-09 | Addendum |  |  | 2021-02-08 | [8 empty] | 2021-02-10 | [17 empty] | 2021-02-17 | [7 empty] | 2021-02-17 | 2021-02-17 |  |  |  |  | 2021-06-16 | [12 empty] | 315782 |  |  |  |  | 2021-06-21 | 2021-06-21 | 2021-06-21 | 2021-06-21 | 2023-10-16 | 2023-10-16 | [15 empty] | Q4 2021 |  |  |  | 10300801699 | [11 empty] | FALSE | TRUE | 205 | 2021-06-21 | 2021-06-21 | 2021 | 2021 | 2021 | 44363 |  |  | 2021-06-09 | Addendum
206 |  | Rigel Paradise | Rick Duperre | 2019-10-22 | [31 empty] | 4 - PRAT |  | 661D1 | 112 |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2020-10-05 | Abby Broedlin | Nautilus US Power Holdco, LLC | Sturgeon Quarry Solar LLC | 486 High St North Berwick | 2000170137 | 30012490352 | Solar | 4999 | 4.999 | 6104 |  |  | 43.3382 | -70.7334 | 486 High St |  |  | North Berwick | 54 | PRATT & WHITNEY | 661D1 | 661T1 |  | 9310-L0329-4160-0059-ED00122 | Non-FERC | COST SHARE | COST SHARE (340,000) | 155248.49 | Under Review 1/31/2020 |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-10-29 | 2019-10-29 | 2019-11-05 | 2019-10-29 | 2019-10-31 | 2020-05-13 |  | 2020-05-28 |  | 2020-05-13 | 2020-05-13 | 2020-05-28 |  |  | 2020-05-15 |  |  | CS | 2020-05-15 | [6 empty] | CS |  |  | 2020-05-15 | [11 empty] | 2020-05-18 | [17 empty] | 2020-05-18 | [6 empty] | Yes |  |  |  |  | 2020-07-22 |  |  | 2021-06-08 | Addendum |  |  | 2020-07-22 | [8 empty] | 2020-07-23 | [17 empty] | 2020-07-28 | [15 empty] | 2020-07-28 |  | 2020-07-28 |  | 2020-07-28 | [6 empty] | 658892 |  |  |  |  | 2020-01-15: 2020-08-04; 2020-01-15: 2020-08-04; 2020-09-17: 2021-06-22; 2020-09-17: 2021-06-22 | [13 empty] | Q3 2021 |  |  |  | 10300695733 | [11 empty] | TRUE | TRUE | 206 | 2020-08-04 | 2020-08-04 | 2020 | 2020 | 2020 |  |  |  | 2021-06-08 | Addendum
207 |  | Govinda Neupane |  | 2019-10-23 | [31 empty] | 1 - ATHN |  | 827D2 |  |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2020-06-25 | Abby Broedlin | Nautilus Solar | NSE AT01 LLC | Harmony Rd Athens | 2000175088 | 30013327967 | Solar | 4400 | 4.4 | 5176 |  |  | 44.9484 | -69.655 | Harmony Road |  |  | Athens | 193 | ATHENS | 827D2 | 827T1 |  | 9310-L0412-0200-0014-ED00171 | Non-FERC | TRIGGERING | TRIGGERING ( $305,000) | 109873 | Yes | Yes |  | K&L Engineering | Bruce Jagolinzer |  | 2019-10-31 | 2019-10-30 | 2019-11-06 | 2019-10-31 | 2019-11-04 | 2019-11-13 |  | 2019-11-27 |  | 2019-11-13 | 2019-11-13 | 2019-11-27 |  |  | 2019-11-27 |  |  | CS | 2020-01-27 | [6 empty] | CS |  |  | 2020-01-27 | [11 empty] | 2020-01-30 | [17 empty] | 2020-02-03 | [6 empty] | Yes |  |  |  |  | 2020-04-07 |  |  | 2021-06-11 | Addendum |  |  | 2020-04-08 | [8 empty] | 2020-04-06 | [17 empty] | 2020-04-09 | [15 empty] | 2020-04-06 |  | 2020-04-06 | [13 empty] | 2020-01-15: 2020-04-13; 2020-01-15: 2020-04-13; 2020-09-17: 2021-08-18; 2020-09-17: 2021-08-18 | [13 empty] | Q4 2021 |  |  | 43965 | 10300661453 | [11 empty] | TRUE | TRUE | 207 | 2020-04-13 | 2020-04-13 | 2020 | 2020 | 2020 |  |  |  | 2021-06-11 | Addendum
208 |  | Lanie Patterson | Brent Brooks | 2019-10-23 | [31 empty] | 1 - CONY |  | 216D1 |  |  | WITHDRAWN | WITHDRAWN |  | James Marshall | Turning Point Energy | TPE DEVELOPMENT LLC | Hallowell Rd Chelsea | 2000123236 | 30011882500 | Solar | [7 empty] | Hallowell Rd |  |  | Augusta |  | CONY ROAD | 216D1 | 216T1 |  | 9310-L0043-1110-0029-ED00128 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2019-10-30 | 2019-11-06 |  |  |  |  | 1900-01-12 | [57 empty] | Pending | [69 empty] | 2020-01-10 | [37 empty] | TRUE | TRUE | 208 | 0 | 0 | 1900 | #VALUE! | #VALUE!
209 |  | Lanie Patterson | Brent Brooks | 2019-10-23 | [31 empty] | 1 - BRCR |  | 211D2 |  |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2020-07-14 | Abby Broedlin | Nautilus Solar | NSE FA01 LLC | Bowman St Farmingdale | 2000169555 | 30013327975 | Solar | 4850 | 4.85 | 4408 |  |  | 44.2483 | -69.8014 | Bowman Street |  |  | Farmingdale | 47 | BROWNS CROSSING | 211D2 | 211T1 |  | 9310-L0029-2020-0009-ED00057 | Non-FERC | TRIGGERING | TRIGGERING (395,000) | 219570.22 | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-10-31 | 2019-10-30 | 2019-11-06 | 2019-10-31 | 2019-11-04 | 2019-11-18 |  | 2019-12-04 |  | 2019-11-18 | 2019-11-18 | 2019-12-02 |  |  | 2019-12-02 |  |  | CS | 2020-02-17 | [6 empty] | CS |  |  | 2020-02-17 | [11 empty] | 2020-02-14 | [17 empty] | 2020-03-05 | [6 empty] | Yes |  |  |  |  | 2020-05-08 |  |  | 2021-05-18 | Addendum |  |  | 2020-05-08 | [8 empty] | 2020-05-07 | [17 empty] | 2020-05-14 | [13 empty] | 2021-05-21 |  | 2020-05-14 |  | 2020-05-14 | [8 empty] | 862978 |  |  |  |  | 2020-01-15: 2020-05-15; 2020-01-15: 2020-05-15; 2020-09-17: 2021-08-18; 2020-09-17: 2021-08-18 | [13 empty] | Q3 2020 |  |  | TBD | 10300678754 | [11 empty] | TRUE | TRUE | 209 | 2020-05-15 | 2020-05-15 | 2020 | 2020 | 2020 | 44337 |  |  | 2021-05-18 | Addendum
210 |  | Lanie Patterson | Brent Brooks | 2019-10-23 | [31 empty] | 3 - DETR |  | 812D2 | 80 |  | WITHDRAWN | WITHDRAWN |  | James Marshall | Turning Point Energy | TPE DEVELOPMENT LLC | Smith Rd Palmyra | 2000123236 | 30011882526 | Solar | [7 empty] | Smith Rd |  |  | Palmyra |  | DETROIT | 812D2 |  |  | 86-Withdrawn-86d | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2019-10-30 | 2019-11-06 |  |  |  |  | 1900-01-12 | [127 empty] | 2020-01-10 | [37 empty] | TRUE | TRUE | 210 | 0 | 0 | 1900 | #VALUE! | #VALUE!
211 |  | Govinda Neupane |  | 2019-10-23 | [31 empty] | 7 - NEWP |  | 837D1 | 160 |  | WITHDRAWN | WITHDRAWN |  | James Marshall | Turning Point Energy | TPE DEVELOPMENT LLC | Sunset Hill Rd Palmyra | 2000123236 | 30011882534 | Solar | [7 empty] | 53 Sunset Hill Rd |  |  | Palmyra |  | NEWPORT | 837D1 |  |  | 86-Withdrawn-86d | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2019-10-30 | 2019-11-06 |  |  |  |  | 1900-01-12 | [127 empty] | 2020-01-10 | [37 empty] | TRUE | TRUE | 211 | 0 | 0 | 1900 | #VALUE! | #VALUE!
212 |  | Lanie Patterson | Brent Brooks | 2019-10-23 | [31 empty] | 1 - BOND |  | 208D3 |  |  | WITHDRAWN | WITHDRAWN |  | Mike Imoto | MEVS LLC AKA CENERGY | BAP POWER CORP | Augusta Airport #1 | 2000122114 | 30011883169 | Solar | [7 empty] | 75 Airport Rd |  |  | Augusta |  | BOND BROOK | 208D3 |  |  | 9310-L0023-0240-0394-ED00006 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2019-10-30 | 2019-11-06 |  |  |  |  | 1900-01-12 | [127 empty] | 2020-02-26 | [37 empty] | TRUE | TRUE | 212 | 0 | 0 | 1900 | #VALUE! | #VALUE!
213 |  | Lanie Patterson | Brent Brooks | 2019-10-23 | [31 empty] | 1 - BOST |  | 263D1 |  |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2021-01-04 | Matt Allegretto | AES Clean Energy | Randolph Solar 1 LLC | Water St Randolf | 2000282961 | 30014011594 | Solar | 4990 | 4.99 | 6258 |  |  | 44.243 | -69.7653 | Water Street |  |  | Randolph | 34 | BOWMAN STREET | 263D1 | 34kV Bus at substation |  | 9310-L0102-4870-0035-ED00037 | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Under Review 1/31/2020 |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-10-31 | 2019-10-30 | 2019-11-06 | 2019-10-31 | 2019-11-04 | 2019-11-04 |  | 2019-11-19 |  | 2019-11-04 | 2019-11-18 | 2019-11-04 |  |  | 2019-11-04 |  |  | CS | 2019-11-04 | [6 empty] | CS |  |  | 2019-11-04 | [11 empty] | 2019-12-05 | [17 empty] | 2019-12-05 | [6 empty] | Yes |  |  |  |  | 2020-02-10 |  |  | 2021-05-18 | Addendum |  |  | 2020-02-04 | [8 empty] | 2020-02-07 | [31 empty] | 2021-05-26 |  | 2020-02-07 |  | 2020-02-07 | [8 empty] | 143118 |  |  |  |  | 2020-01-15: 2020-02-13; 2020-01-15: 2020-02-13; 2020-09-17: 2021-06-16; 2020-09-17: 2021-06-16 | [16 empty] | 43902 | 10300653640 | [11 empty] | TRUE | TRUE | 213 | 2020-02-13 | 2020-02-13 | 2020 | 2020 | 2020 | 44342 |  |  | 2021-05-18 | Addendum
214 |  | Lanie Patterson | Brent Brooks | 2019-10-23 | [31 empty] | 1 - GARD |  | 226D2 |  |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED |  | Scott Moore | SunRaise Investments LLC | ENTERPRISE AVE GARDINER SOLAR LLC | 100 Enterprise Ave Gardiner | 2000147251 | 30012142383 | Solar | 875 | 0.875 | 7488 |  |  | 44.1744 | -69.8276 | 100 Enterprise Road |  |  | Gardiner | 12 | GARDINER | 226D2 | 226T1 |  | 9310-L0057-2190-0036-ED00006 | FERC | TRIGGERING | TRIGGERING (325,000) | 68969 | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-10-31 | 2019-10-30 | 2019-11-06 | 2019-10-31 | 2019-11-04 | 2019-11-15 |  | 2019-12-03 |  | 2019-11-15 | 2019-11-15 | 2019-11-29 |  |  | 2019-11-15 |  |  | CS | 2019-11-15 | [6 empty] | CS |  |  | 2019-11-15 | [11 empty] | 2019-11-25 | [17 empty] | 2019-11-25 | [6 empty] | Yes |  |  |  |  | 2020-01-29 |  |  | 2021-06-10 | Addendum |  |  | 2020-01-31 | [8 empty] | 2020-02-03 | [17 empty] | 2020-02-07 | [15 empty] | 2020-02-03 |  | 2020-02-04 | [8 empty] | 11961 |  |  |  |  | 2020-01-15: 2020-03-02; 2020-01-15: 2020-03-02; 2020-09-17: 2021-06-30; 2020-09-17: 2021-06-30 | [13 empty] | Q4 2020 |  |  | 43892 | 10300648027 | [11 empty] | TRUE | TRUE | 214 | 2020-03-02 | 2020-03-02 | 2020 | 2020 | 2020 |  |  |  | 2021-06-10 | Addendum
215 |  |  | KRISTOFER COLEMAN | 2019-10-25 | [31 empty] | 1 - LSFA |  | 232D2 |  |  | WITHDRAWN | WITHDRAWN |  | James Marshall | Turning Point Energy | TPE DEVELOPMENT LLC | Pinkham Brook Rd Durham | 2000123236 | 30011882542 | Solar | [7 empty] | 318 Pinkham Brook Rd |  |  | Durham |  | LISBON FALLS | 232D2 |  |  | 9310-L0062-1680-0082-ED00271 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2019-11-01 | 2019-11-08 |  |  |  |  | 1900-01-12 | [57 empty] | Pending | [69 empty] | 2020-01-10 | [37 empty] | TRUE | TRUE | 215 | 0 | 0 | 1900 | #VALUE! | #VALUE!
216 |  | Lanie Patterson | Brent Brooks | 2019-10-25 | [31 empty] | 1 - MCCO |  | 237D1 |  |  | WITHDRAWN | WITHDRAWN |  | James Marshall | Turning Point Energy | TPE DEVELOPMENT LLC | Webber Pond Rd Vassalboro | 2000123236 | 30011882559 | Solar | [7 empty] | 1074 Webber Pond Rd |  |  | Vassalboro |  | MCCOYS | 237D1 |  |  | 86-Withdrawn-86d | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2019-11-01 | 2019-11-08 |  |  |  |  | 1900-01-12 | [57 empty] | Pending | [69 empty] | 2020-04-14 | [37 empty] | TRUE | TRUE | 216 | 0 | 0 | 1900 | #VALUE! | #VALUE!
217 |  | Marshall Ripley | Rick Duperre | 2019-10-25 | [31 empty] | 2 - SPST |  | 668D5 | 176 |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2020-12-14 | Abby Broedlin | Nautilus Solar | BD SOLAR LARSON LLC | Country Rd Westbrook | 2000129970 | 30011878268 | Solar | 4990 | 4.99 | 4260 |  |  | 43.6481 | -70.3738 | 740 Country Rd |  |  | Westbrook | 60 | SPRING STREET | 668D5 | 668T2 |  | 9310-L0339-6320-0038-ED00076 | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-10-31 | 2019-11-01 | 2019-11-08 | 2019-10-31 | 2019-11-04 | 2020-05-28 |  | 2020-06-11 |  | 2020-05-28 | 2020-05-28 | 2020-06-11 |  |  | 2020-05-28 |  |  | CS | 2020-05-28 | [6 empty] | CS |  |  | 2020-05-28 | [11 empty] | 2020-07-01 | [17 empty] | 2020-06-02 | [6 empty] | Pending |  |  |  |  | 2020-08-05 | [6 empty] | 2020-08-04 | [8 empty] | 2020-08-06 | [17 empty] | 2020-08-10 | [15 empty] | 2020-08-13 |  | 2020-08-13 | [13 empty] | 2020-01-15: 2020-08-18; 2020-01-15: 2020-08-18; 2020-09-17: 2021-08-23; 2020-09-17: 2021-08-23 | [13 empty] | Q4 2021 |  |  |  | 10300702805 | [11 empty] | TRUE | TRUE | 217 | 2020-08-18 | 2020-08-18 | 2020 | 2020 | 2020
218 |  | Govinda Neupane |  | 2019-10-25 | [31 empty] | 1 - RILE |  | 449D2 |  |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2020-07-14 | Tyler William Perkins | Nexamp, Inc | Jay Solar LLC | Main St Jay | 2000114877 | 30013425985 | Solar | 4950 | 4.95 | 7000 |  |  | 44.513 | -70.222 | Main Street |  |  | Jay | 125 | RILEY | 449D2 | 449T1 |  | 9310-L0191-2920-0085-ED00082 | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-10-31 | 2019-11-01 | 2019-11-08 | 2019-10-31 | 2019-11-04 | 2019-11-19 |  | 2019-12-05 |  | 2019-11-19 | 2019-11-19 | 2019-12-03 |  |  | 2019-11-20 |  |  | CS | 2019-11-20 | [6 empty] | CS |  |  | 2019-11-20 | [11 empty] | 2019-12-05 | [17 empty] | 2019-12-05 | [6 empty] | Yes |  |  |  |  | 2020-02-10 |  |  | 2021-04-30 | Addendum |  |  | 2020-02-04 | [8 empty] | 2020-02-17 | [17 empty] | 2020-02-20 | [13 empty] | 2021-05-04 |  | 2020-02-25 | 2021-07-26 | 2020-06-15 | [8 empty] | 720392 |  |  |  |  | 2020-01-15: 2020-06-16; 2020-01-15: 2020-06-16; 2020-09-17: 2021-08-16; 2020-09-17: 2021-08-16 | [13 empty] | Q4 2020 |  |  | TBD | 10300652058 | [11 empty] | TRUE | TRUE | 218 | 2020-06-16 | 2020-06-16 | 2020 | 2020 | 2020 | 44320 |  | 44403 | 2021-04-30 | Addendum
219 |  | Lanie Patterson | Brent Brooks | 2019-10-25 | [31 empty] | 1 - CLIN |  | 810D1 |  |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2021-12-17 | Stephen Campbell | Navisun LLC | BWC Unity Pond, LLC | 16 Bangor Rd Benton | 2000130164 | 30011881254 | Solar | 4450 | 4.45 | 5445 |  |  | 44.6181 | -69.5269 | 16 Bangor Rd |  |  | Benton | 6 | CLINTON | 810D1 | 810T1 |  | FLOC-MISSING-01142021 | Non-FERC | TRIGGERING | TRIGGERING (380,000) | 311705 | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-10-31 | 2019-11-01 | 2019-11-08 | 2019-10-31 | 2019-11-04 | 2019-11-19 |  | 2019-12-05 |  | 2019-11-19 | 2019-11-19 | 2019-12-03 |  |  | 2019-11-20 |  |  | CS | 2019-11-20 | [6 empty] | CS |  |  | 2019-11-20 | [11 empty] | 2019-12-16 | [17 empty] | 2019-12-16 | [6 empty] | Yes |  |  |  |  | 2020-02-20 |  |  | 2021-05-18 | Addendum |  |  | 2020-02-20 | [8 empty] | 2020-02-26 | [8 empty] | 2022-02-26 | [8 empty] | 2020-03-03 | [13 empty] | 2021-05-26 |  | 2020-02-24 |  | 2020-02-25 |  |  |  | 2022-02-07 | 2022-02-14 |  |  |  | 1128677 |  |  |  |  | 2020-01-15: 2020-04-03; 2020-01-15: 2020-04-03; 2020-09-17: 2021-06-14; 2020-09-17: 2021-06-14 |  |  | 2022-02-14 | 2022-02-15 | [9 empty] | Q2 2021 |  |  | TBD | 10300665084 | [11 empty] | TRUE | TRUE | 219 | 2020-04-03 | 2020-04-03 | 2020 | 2020 | 2020 | 44342 |  |  | 2021-05-18 | Addendum
220 |  |  | Anthony Boucher | 2019-10-25 | [31 empty] | 1 - WARR |  | 253D1 |  |  | WITHDRAWN | WITHDRAWN |  | Tyson Buerkle | Bluewave MA, LLC | BWC BLUE WAVE MA LLC | Atlantinc Hwy Warren | 2000114857 | 30011881338 | Solar | [7 empty] | Atlantic Highway |  |  | Warren |  | WARREN | 253D1 |  |  | 9310-L0092-6160-0102-ED00038 (NEEDS TO BE CONFIRMED WITH DEVELOPER) | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2019-11-01 | 2019-11-08 |  |  |  |  | 1900-01-12 | [57 empty] | Pending | [69 empty] | 2020-02-03 | [37 empty] | TRUE | TRUE | 220 | 0 | 0 | 1900 | #VALUE! | #VALUE!
221 |  | Lanie Patterson | Brent Brooks | 2019-10-28 | [31 empty] | 2 - GARD |  | 226D2 | 214 |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2021-01-04 | Scott Moore | SunRaise Investments LLC | MARKET STREET GARDINER SOLAR LLC | 47 Market St Gardiner | 2000155365 | 30012267230 | Solar | 3250 | 3.25 | 4378 |  |  | 44.1842 | -69.8226 | 47 Market St |  |  | Gardiner | 3 | GARDINER | 226D2 | 226T1 |  | 9310-L0057-2190-0007-ED00006 | FERC | COST SHARE | COST SHARE (325,000) | 256060 | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-11-04 | 2019-11-04 | 2019-11-12 | 2019-11-04 | 2019-11-05 | 2020-02-07 |  | 2020-02-24 |  | 2020-02-07 | 2020-02-07 |  |  |  | 2020-02-07 |  |  | CS | 2020-02-07 | [6 empty] | CS |  |  | 2020-02-07 | [11 empty] | 2020-02-07 | [17 empty] | 2020-02-12 | [6 empty] | Yes |  |  |  |  | 2020-04-16 |  |  | 2021-06-10 | Addendum |  |  | 2020-04-14 | [8 empty] | 2020-04-14 | [17 empty] | 2020-04-17 | [15 empty] | 2020-04-17 |  | 2020-04-21 | [8 empty] | 543879 |  |  |  |  | 2020-01-15: 2020-04-27; 2020-01-15: 2020-04-27; 2020-09-17: 2021-06-30; 2020-09-17: 2021-06-30 | [13 empty] | Q4 2020 |  |  | TBD | 10300672773 | [11 empty] | TRUE | TRUE | 221 | 2020-04-27 | 2020-04-27 | 2020 | 2020 | 2020 |  |  |  | 2021-06-10 | Addendum
222 |  |  | KRISTOFER COLEMAN | 2019-10-28 | [31 empty] | 3 - TP34 |  | 250D1 | 175 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN | 2021-03-30 | Matthew Doubleday | SunRaise Investments LLC | AUGUSTA ROAD TOPSHAM SOLAR LLC | 449 Augusta Rd (Topsham) | 2000200720 | 30012901788 | Solar/Battery | [7 empty] | 449 Augusta Rd |  |  | Topsham |  | TOPSHAM 34 KV | 250D1 |  |  | 9310-L0086-5840-0003-ED00143 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2019-11-04 | 2019-11-12 |  |  |  |  | 1900-01-12 | [9 empty] | CS |  | RS | [38 empty] | 2020-07-06 | 2020-10-26 | [5 empty] | Pending |  |  |  |  | 2020-09-08 | 2020-12-09 |  | 2021-05-21 | Addendum |  |  | 2020-09-08 | 2020-12-14 | [7 empty] | 2020-09-09 | 2020-12-14 | [16 empty] | 2020-09-16 | 2020-12-17 | [6 empty] | 2020-09-16 | 2020-12-17 |  |  |  |  | 2021-05-24 |  | 2020-12-17 |  | 2020-12-17 | [8 empty] | 642103 |  |  |  | 2022-04-19 | 2020-01-15: 2021-01-12; 2020-01-15: 2021-01-12; 2020-09-17: 2021-06-24; 2020-09-17: 2021-06-24 | [17 empty] | 10300748316 | [11 empty] | TRUE | TRUE | 222 | 2021-01-12 | 2021-01-12 | 2021 | 2021 | 2021 | 44340 |  |  | 2021-05-21 | Addendum
223 |  | Eben Snow | Brent Brooks | 2019-10-28 | [31 empty] | 1 - PATP |  | 409D1 |  |  | WITHDRAWN | WITHDRAWN |  | Matthew Doubleday | SunRaise Investments LLC | SUNRAISE DEVELOPMENT LLC | 571 Park St (So Paris) | 2000124937 | 30011892442 | Solar/Battery | [7 empty] | 571 Park Street |  |  | South Paris |  | PARIS TAP | 409D1 |  |  | 9310-L0122-4500-0007-ED00102 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2019-11-04 | 2019-11-12 |  |  |  |  | 1900-01-12 | [57 empty] | Pending | [69 empty] | 2020-11-20 | [37 empty] | TRUE | TRUE | 223 | 0 | 0 | 1900 | #VALUE! | #VALUE!
224 |  | Eben Snow | Brent Brooks | 2019-10-28 | [31 empty] | 2 - PATP |  | 409D1 | 223 |  | WITHDRAWN | WITHDRAWN |  | Matthew Doubleday | SunRaise Investments LLC | SUNRAISE DEVELOPMENT LLC | 1 Everett Rd (W Paris) | 2000124937 | 30011892459 | Solar/Battery | [7 empty] | 1 Everett Road |  |  | West Paris |  | PARIS TAP | 409D1 |  |  | 9310-L0122-6310-0017-ED00042 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2019-11-04 | 2019-11-12 |  |  |  |  | 1900-01-12 | [57 empty] | Pending | [69 empty] | 2020-04-23 | [37 empty] | TRUE | TRUE | 224 | 0 | 0 | 1900 | #VALUE! | #VALUE!
225 |  | Eben Snow | Brent Brooks | 2019-10-28 | 2023-06-06 | L2_Bump | [29 empty] | 1 - MEFA |  | 431D3 |  |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Daniel Serber | NEXTGRID INC | NEXTGRID AVOCADO LLC | 6 Timber Ln (Mechanic Falls) | 2000167674 | 30012456742 | Solar | [5 empty] | 44.9257 | -70.3986 | 0 South Main St |  |  | Mechanic Falls | 26 | MECHANIC FALLS | 431D3 | 431T2 | 12.47 | 9310-L0167-3610-0052-ED00023 | Non-FERC | WITHDRAWN | WITHDRAWN | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-11-04 | 2019-11-04 | 2019-11-12 | 2019-11-04 | 2019-11-06 | 2019-11-21 |  | 2019-12-09 |  | 2019-11-21 | 2019-11-21 | 2019-12-05 |  |  | 2019-12-05 |  |  | CS | 2019-12-10 | [6 empty] | CS |  |  | 2019-12-10 |  |  | 2023-07-20 | [8 empty] | 2020-01-09 |  |  | 2023-07-21 | [8 empty] | 2023-07-25 | [5 empty] | 2020-01-09 |  |  | 2023-07-26 |  |  |  | Yes |  |  |  |  | 2020-03-16 |  |  | 2021-06-03 | Addendum |  |  | 2020-03-12 |  |  | 2023-09-08 | [5 empty] | 2020-03-18 |  |  | 2023-09-08 | [8 empty] | 2023-09-08 | [5 empty] | 2020-03-26 |  |  | 2023-09-12 | [7 empty] | 2023-09-12 |  |  | 2021-06-09 |  | 2020-03-27 |  | 2020-03-30 | 2022-06-28 | [7 empty] | 73810 |  | 285493 | 2023-09-07 | 2024-10-21 | 2020-04-08 | 2020-04-08 | 2022-07-11 |  |  |  | 2023-11-16 | 2023-11-17 | [16 empty] | 43951 | 10300659339 | [11 empty] | TRUE | TRUE | 225 | 2020-04-08 | 2020-04-08 | 2020 | 2020 | 2020 | 44356 |  |  | 2021-06-03 | Addendum
226 |  | Eben Snow | Brent Brooks | 2019-10-28 | 2023-06-06 | L2_Bump | [7 empty] | 2024-10-21 | wthdw | [20 empty] | 2 - MEFA |  | 431D2 | 225 | Yes | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Daniel Serber | NEXTGRID INC | NEXTGRID BAYBERRY LLC | 498 W Minot Rd (Minot) | 2000167676 | 30012456767 | Solar | [5 empty] | 44.1536 | -70.3805 | 498 W Minot Rd |  |  | Minot | 66 | MECHANIC FALLS | 431D2 | 431T1 |  | 9310-L0166-3710-0056-ED00078 | Non-FERC | Triggering | 385558 | 257124 | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-11-04 | 2019-11-04 | 2019-11-12 | 2019-11-04 | 2019-11-05 | 2020-04-20 |  | 2020-05-04 |  | 2020-04-20 | 2020-04-20 | 2020-05-04 |  |  | 2020-04-21 |  |  | CS | 2020-04-21 | [6 empty] | CS |  |  | 2020-04-21 |  |  | 2023-11-20 | [11 empty] | 2023-12-06 | [8 empty] | 2023-12-14 | [5 empty] | 2020-05-01 |  |  | 2023-12-22 |  |  |  | Pending |  |  |  |  | 2020-07-07 |  |  | 2021-05-19 | Addendum |  |  | 2020-07-22 |  |  | 2024-02-28 | [5 empty] | 2020-07-22 |  |  | 2024-02-28 | [5 empty] | 2020-07-27 |  |  | 2024-03-05 | [5 empty] | 2020-07-27 |  |  | 2024-03-07 | [7 empty] | 2024-03-07 |  |  | 2021-06-03 |  | 2020-07-31 |  | 2020-07-31 | 2023-03-09 | 2020-08-01 | [6 empty] | 762610 |  | 628350 | 2023-03-09 | 2025-07-15 | 2020-01-15: 2020-08-05; 2020-01-15: 2020-08-05; 2020-09-17: 2021-07-01; 2020-09-17: 2021-07-01 |  |  | 2023-10-27 | 2023-10-27 | [9 empty] | Q4 2020 |  |  |  | 10300698903 | [11 empty] | TRUE | TRUE | 226 | 2020-08-05 | 2020-08-05 | 2020 | 2020 | 2020 | 44350 |  |  | 2021-05-19 | Addendum
227 |  | Govinda Neupane |  | 2019-10-29 | [31 empty] | 5 - WSTN |  | 866D1 | 197 |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2021-12-17 |  | REC Energy Solar Holdings, LLC | Westbound Solar 3 LLC | 328 Eaton Mountain Rd Skowhegan | 2000167280 | 30015539783 | Solar | 4950 | 4.95 | 7079 |  |  | 44.77 | -69.638 | 328 Eaton Mtn Rd |  |  | Skowhegan | 28 | WESTON HYDRO | 866D1 | 866T2 |  | 9310-SS0866 | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-11-04 | 2019-11-05 | 2019-11-13 | 2019-11-04 | 2019-11-05 | 2020-02-03 |  | 2020-02-18 |  | 2020-02-03 | 2020-01-27 | 2020-02-10 |  |  | 2020-02-10 |  |  | CS | 2020-02-24 | [6 empty] | CS |  |  | 2020-02-24 | [11 empty] | 2020-03-11 | [17 empty] | 2020-03-20 | [6 empty] | Pending |  |  |  |  | 2020-05-26 | [6 empty] | 2020-05-27 | [8 empty] | 2020-05-14 | [17 empty] | 2020-05-22 | [15 empty] | 2020-06-15 | 2021-08-03 | 2020-06-15 | [13 empty] | 2020-01-15: 2020-06-19; 2020-01-15: 2020-06-19; 2020-09-17: 2021-08-03; 2020-09-17: 2021-08-03 | [13 empty] | Q4 2021 |  |  |  | 10300685799 | [11 empty] | TRUE | TRUE | 227 | 2020-06-19 | 2020-06-19 | 2020 | 2020 | 2020 |  |  | 44411
228 |  | Eben Snow | Brent Brooks | 2019-10-29 | [31 empty] | 3 - PATP |  | 409D1 | 224 |  | WITHDRAWN | WITHDRAWN |  | Rayo Bhumgara | Sustainable Strategies 2050 Inc | PARIS SOLAR 1 LLC | Hill Street Terrace Paris | 2000130611 | 30011887616 | Solar | [7 empty] | Hill Street Terrace |  |  | Paris |  | PARIS TAP | 409D1 |  |  | 9310-L0122-4500-0044-ED00003 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2019-11-05 | 2019-11-13 |  |  |  |  | 1900-01-12 | [57 empty] | Pending | [69 empty] | 2020-01-20 | [37 empty] | TRUE | TRUE | 228 | 0 | 0 | 1900 | #VALUE! | #VALUE!
229 |  | Govinda Neupane |  | 2019-10-29 | [31 empty] | 3 - SKNS |  | 853D1 | 26 |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2021-12-17 | Tyler William Perkins | Nexamp, Inc | MADISON CSG LLC | 34 Lakewood Rd Madison | 2000155119 | 30012263403 | Solar | 4000 | 4 | 5342 |  |  | 44.7888 | -69.7369 | 34 Lakewood Rd |  |  | Madison | 23H | SKOWHEGAN NORTH SIDE | 853D1 | 853T1 |  | 9310-SS0853 | Non-FERC | TRIGGERING | TRIGGERING (325,000) | 217610 | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-11-04 | 2019-11-05 | 2019-11-13 | 2019-11-04 | 2019-11-06 | 2020-08-11 |  | 2020-08-25 |  | 2020-08-11 | 2020-08-11 | 2020-08-25 |  |  | 2020-08-14 |  |  | CS | 2020-08-14 | [6 empty] | CS |  |  | 2020-08-14 | [11 empty] | 2020-08-14 | [17 empty] | 2020-08-14 | [6 empty] | Pending |  |  |  |  | 2020-10-20 |  |  | 2021-06-03 | Addendum |  |  | 2020-10-20 | [8 empty] | 2020-10-21 | [17 empty] | 2020-10-26 | [15 empty] | 2020-10-26 |  | 2020-10-27 | 2022-12-19 |  | 2023-05-09 | [5 empty] | 267008 |  | 295481 | 2022-12-16 |  | 2020-10-29 | 2020-10-29 | 2021-08-20 | 2021-08-20 | 2023-05-09 | 2023-05-09 | [19 empty] | 10300733816 | [11 empty] | TRUE | TRUE | 229 | 2020-10-29 | 2020-10-29 | 2020 | 2020 | 2020 |  |  |  | 2021-06-03 | Addendum
230 |  | Govinda Neupane |  | 2019-10-29 | 2022-09-09 | L2_Bump | [29 empty] | 4 - GUIL |  | 821D1 | 140 |  | WITHDRAWN | WITHDRAWN |  | Jamal Batar | Dimension Renewable Energy | PARKMAN CSG LLC | 375 Me-150 Parkman | 2000155118 | 30012263189 | Solar | [5 empty] | 45.1475 | -69.4168 | 375 ME-150 |  |  | Parkman |  | GUILFORD | 821D1 |  |  | FLOC-MISSING-01142021 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2019-11-05 | 2019-11-13 |  |  |  |  | 1900-01-12 | [57 empty] | No Study | [69 empty] | 2021-09-15 | [37 empty] | TRUE | TRUE | 230 | 0 | 0 | 1900 | #VALUE! | #VALUE!
231 |  | Rigel Paradise | Rick Duperre | 2019-10-31 | [31 empty] | 5 - PRAT |  | 661D1 | 206 |  | WITHDRAWN | WITHDRAWN |  | James Marshall | Turning Point Energy | TPE DEVELOPMENT LLC | Lebanon Rd (Nb 13) No Berwick | 2000123236 | 30011907984 | Solar | [7 empty] | 321 Lebanon Rd |  |  | North Berwick |  | PRATT & WHITNEY | 661D1 |  |  | 9310-L0329-4160-0028-ED00173 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2019-11-07 | 2019-11-15 |  |  |  |  | 1900-01-12 | [57 empty] | Pending | [69 empty] | 2021-01-19 | [37 empty] | TRUE | TRUE | 231 | 0 | 0 | 1900 | #VALUE! | #VALUE!
232 |  | Rigel Paradise | Rick Duperre | 2019-09-20 | [31 empty] | 2 - BASS |  | 602D3 | 110 |  | WITHDRAWN | WITHDRAWN |  | James Marshall | Turning Point Energy | TPE DEVELOPMENT LLC | Be05 39 Old Route 4 Berwick | 2000123236 | 30011775092 | Solar | [7 empty] | Old Route 4 |  |  | Berwick |  | BASSETT | 602D3 |  |  | 9310-L0212-4160-0025-ED00073 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2019-09-27 | 2019-10-04 |  |  |  |  | 1900-01-12 | [57 empty] | Pending | [69 empty] | 2019-11-21 | [37 empty] | TRUE | TRUE | 232 | 0 | 0 | 1900 | #VALUE! | #VALUE!
233 |  | Eben Snow | Brent Brooks | 2019-11-01 | [31 empty] | 1 - LOVE |  | 430D1 |  |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Noah Gonzalez | Nexamp, Inc | Sweden Solar 2, LLC | 748 Lovell Rd, Sweden | 2000114877 | 30011899652 | Solar/Battery | [5 empty] | 44.1222 | -70.8762 | 748 Lovell Rd |  |  | Sweden | 126 | LOVELL | 430D1 | 430T1 |  | 9310-L0164-5640-0004-ED00032 | Non-FERC | WITHDRAWN | WITHDRAWN | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-11-04 | 2019-11-08 | 2019-11-18 | 2019-11-04 | 2019-11-06 | 2019-11-21 |  | 2019-12-09 |  | 2019-11-21 | 2019-11-21 | 2019-12-05 |  |  | 2019-12-05 | 2020-08-11 |  | CS | 2020-04-10 | RS | 2020-08-11 |  |  |  |  | CS | 2020-01-02 | 2020-04-10 | 2020-04-10 | 2020-08-11 | [10 empty] | 2020-04-24 | [17 empty] | 2020-08-14 | 2020-08-14 | [5 empty] | Pending |  |  |  |  | 2020-10-20 | 2020-09-28 | [5 empty] | 2020-07-02 | 2020-09-28 | [7 empty] | 2020-07-02 | 2020-09-28 | [16 empty] | 2020-07-08 | 2020-10-01 | [14 empty] | 2020-10-05 | 2021-08-11 | 2020-10-06 | [12 empty] | 2022-10-20 | 2020-01-15: 2020-11-03; 2020-01-15: 2020-11-03; 2020-09-17: 2021-08-17; 2020-09-17: 2021-08-17 | [17 empty] | 10300731124 | [11 empty] | TRUE | TRUE | 233 | 2020-11-03 | 2020-11-03 | 2020 | 2020 | 2020 |  |  | 44419
234 |  | Eben Snow | Brent Brooks | 2019-11-01 | [31 empty] | 2 - LOVE |  | 430D1 | 233 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Noah Gonzalez | Nexamp, Inc | NEXAMP SOLAR LLC | 1011 Knights Hill Rd, Sweden | 2000114877 | 30011899678 | Solar/Battery | [5 empty] | 44.1196 | -70.8688 | 1011 Knights Hill Rd |  |  | Sweden | 114 | LOVELL | 430D1 | 430T1 | 12.47 | 9310-L0164-5640-0004-ED00019 | Non-FERC | WITHDRAWN | WITHDRAWN | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-11-04 | 2019-11-08 | 2019-11-18 | 2019-11-04 | 2019-11-06 | 2020-11-10 |  | 2020-11-25 |  | 2020-11-10 | 2020-11-10 | 2020-11-24 |  |  | 2020-11-24 |  |  | CS | 2020-12-07 | [6 empty] | CS |  |  | 2020-12-07 | [29 empty] | 2020-12-18 | [11 empty] | 2021-02-25 |  |  | 2021-05-26 | Report |  |  | 2021-05-26 | [8 empty] | 2021-05-26 | [17 empty] | 2021-06-17 | [13 empty] | 2021-06-17 |  | 2021-07-08 | 2021-07-08 | 2021-07-08 | [8 empty] | 7330637 |  |  |  | 2022-10-20 | 2020-01-15: 2021-07-08; 2020-01-15: 2021-07-08; 2020-09-17: 2021-07-08; 2020-09-17: 2021-07-08 | [17 empty] | Requested | [11 empty] | TRUE | TRUE | 234 | 2021-07-08 | 2021-07-08 | 2021 | 2021 | 2021 | 44364 |  | 44385 | 2021-05-26 | Report
235 |  | Govinda Neupane |  | 2019-11-04 | [31 empty] | 2 - TPCO |  | 453D1 | 35 |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2020-10-05 | Tyler William Perkins | Nexamp, Inc | WEST PARIS CSG LLC | 38 Briggs St/ W Paris | 2000155122 | 30012263411 | Solar | 2500 | 2.5 | 3174 |  |  | 44.3284 | -70.5615 | 38 Briggs St |  |  | West Paris | 5H | TRAP CORNER | 453D1 | 453T1 |  | 9310-L0195-6315-0023-ED00065 | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-11-06 | 2019-11-12 | 2019-11-19 | 2019-11-06 | 2019-11-15 | 2020-04-17 |  | 2020-05-04 |  | 2020-04-17 | 2020-04-17 | 2020-05-04 |  |  | 2020-04-22 |  |  | CS | 2020-04-22 | [6 empty] | CS |  |  | 2020-04-22 | [11 empty] | 2020-04-28 | 2020-04-28 | [16 empty] | 2020-05-01 | [6 empty] | Pending |  |  |  |  | 2020-07-07 | [6 empty] | 2020-07-06 | [8 empty] | 2020-07-07 | [17 empty] | 2020-07-07 | [15 empty] | 2020-07-08 |  | 2020-07-09 | [13 empty] | 2020-01-15: 2020-07-13; 2020-01-15: 2020-07-13; 2020-09-17: 2021-09-21 | [13 empty] | Q4 2021 |  |  |  | 10300690151 | [11 empty] | TRUE | TRUE | 235 | 2020-07-13 | 2020-07-13 | 2020 | 2020 | 2020
236 |  | Lanie Patterson | Brent Brooks | 2019-11-06 | [31 empty] | 4 - WINS |  | 870D1 | 173 |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2021-12-17 | Scott Moore | SunRaise Investments LLC | ALBION ROAD BENTON SOLAR, LLC | 165 Albion Rd Benton | 2000204888 | 30012954852 | Solar/Battery | 873 | 0.873 | 1749 |  |  | 45.5802 | -69.5319 | Albion Road |  |  | Benton | 719.3 | WINSLOW | 870D1 | 870T4 |  | 9310-L0453-0460-0018-ED00150 | FERC | NOT IMPACTED | NOT IMPACTED | NONE | Yes | Yes |  | K&L Engineering | Bruce Jagolinzer |  | 2019-11-06 | 2019-11-14 | 2019-11-21 | 2019-11-06 | 2019-11-15 | 2020-07-09 |  | 2020-07-23 |  | 2020-07-09 | 2020-07-13 | 2020-07-27 |  |  | 2020-07-27 | 2020-11-15 |  | CS | 2020-07-28 | RS | 2020-11-15 |  |  |  |  | CS |  |  | 2020-07-28 | 2020-11-15 | [10 empty] | 2020-07-24 | [17 empty] | 2020-07-28 | 2020-11-17 | [5 empty] | Pending |  |  |  |  | 2020-09-30 | 2021-01-04 | [5 empty] | 2020-09-30 | 2020-01-06 | [7 empty] | 2020-10-13 | 2021-01-12 | [16 empty] | 2020-10-23 | [7 empty] | 2020-10-23 | 2021-01-12 | [6 empty] | 2021-01-13 | 2021-08-02 | 2021-01-13 | [8 empty] | 541281 |  |  |  |  | 2020-01-15: 2021-01-19; 2020-01-15: 2021-01-19; 2020-09-17: 2021-08-02; 2020-09-17: 2021-09-16 | [13 empty] | Q4 2020 |  |  |  | 10300793051 | [11 empty] | TRUE | TRUE | 236 | 2021-01-19 | 2021-01-19 | 2021 | 2021 | 2021 |  |  | 44410
237 |  | Eben Snow | Brent Brooks | 2019-11-07 | [31 empty] | 1 - DENM |  | 413D1 |  |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Jeffrey Lord | Con Edison Clean Energy | CED Denmark Solar, LLC | West Main St Denmark | 2800000074 | 30011921696 | Solar/Battery | [5 empty] | 43.9703 | -70.8185 | West Main St |  |  | Denmark | 47 | DENMARK | 413D1 | 413T1 |  | 9310-L0129-1580-0007-ED00096 | Non-FERC | WITHDRAWN | WITHDRAWN | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-11-12 | 2019-11-15 | 2019-11-22 | 2019-11-12 | 2019-11-15 | 2019-11-22 |  | 2019-12-10 |  | 2019-11-22 | 2019-11-22 | 2019-12-06 |  |  | 2019-12-03 | 2020-04-07 |  | CS | 2019-12-03 | RS | 2020-04-07 |  |  |  |  | CS |  |  | 2019-12-03 | 2020-04-07 | [10 empty] | 2019-12-16 | [17 empty] | 2019-12-16 | 2020-04-09 | [5 empty] | Yes |  |  |  |  | 2020-02-21 | 2020-05-22 |  | 2021-05-18 | Addendum |  |  | 2020-02-20 | 2020-05-14 | [7 empty] | 2020-02-21 | 2020-05-14 | [16 empty] | 2020-02-26 | 2020-05-21 | [12 empty] | 2021-05-25 |  | 2020-05-21 |  | 2020-05-22 | [8 empty] | 59335 |  |  |  | 2023-03-09 | 2020-01-15: 2020-05-27; 2020-01-15: 2020-05-27 | [17 empty] | 10300653136 | [11 empty] | TRUE | TRUE | 237 | 2020-05-27 | 2020-05-27 | 2020 | 2020 | 2020 | 44341 |  |  | 2021-05-18 | Addendum
238 |  | Lanie Patterson | Brent Brooks | 2019-11-07 | [31 empty] | 2 - MANC |  | 233D1 | 95 |  | WITHDRAWN | WITHDRAWN |  | Mark Chrisos | Con Edison Clean Energy | CONSOLIDATED EDISON SOLUTIONS | Bowdion St Manchester | 2800000074 | 30011921688 | Solar/Battery | [7 empty] | Bowdoin St |  |  | Manchester |  | MANCHESTER | 233D1 |  |  | 9310-L0063-3540-0001-ED00041 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2019-11-15 | 2019-11-22 |  |  |  |  | 1900-01-12 | [57 empty] | Pending | [69 empty] | 2020-01-16 | [37 empty] | TRUE | TRUE | 238 | 0 | 0 | 1900 | #VALUE! | #VALUE!
239 |  | Rigel Paradise | Rick Duperre | 2019-11-07 | [31 empty] | 2 - HITP |  | 692D1 | 150 |  | WITHDRAWN | WITHDRAWN |  | Michael Whigham | CEC Development LLC | CEC DEVELOPMENT LLC | 152 Towles Hill Rd / Cornish Me | 2000123496 | 30011898373 | Solar | [7 empty] | 152 Towles Hill Rd |  |  | Cornish |  | HIRAM TAP | 692D1 |  |  | 9310-L0372-1240-0030-ED00015 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2019-11-15 | 2019-11-22 |  |  |  |  | 1900-01-12 | [57 empty] | Pending | [69 empty] | 2020-04-23 | [37 empty] | TRUE | TRUE | 239 | 0 | 0 | 1900 | #VALUE! | #VALUE!
240 |  |  | Anthony Boucher | 2019-11-07 | 2023-01-09 | L2_Bump | [29 empty] | 2 - SEAR |  | 850D2 | 203 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Matthew Doubleday | SunRaise Investments LLC | W MAIN STREET SEARSPORT SOLAR LLC | 324 W Main (Searsport) | 2000163638 | 30012397847 | Solar/Battery | [5 empty] | 44.4384 | -68.9507 | 324 West Main Street |  |  | Searsport | 42 | SEARSPORT | 850D2 | 850T1 |  | 2 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-11-12 | 2019-11-15 | 2019-11-22 | 2019-11-12 | 2019-11-15 | 2020-03-12 |  | 2020-03-26 |  | 2020-03-12 | 2020-03-12 | 2020-03-26 |  |  | 2020-03-19 |  |  | CS | 2020-03-19 | [6 empty] | CS |  |  | 2020-03-19 | [11 empty] | 2020-03-19 | [17 empty] | 2020-03-24 | [6 empty] | Yes |  |  |  |  | 2020-05-28 |  |  | 2021-05-18 | Addendum |  |  | 2020-05-28 | [8 empty] | 2020-05-28 | [17 empty] | 2020-06-03 | [14 empty] | 2021-05-21 | 2020-06-15 | 2021-05-24 | 2020-06-15 | [8 empty] | 665965 |  |  |  | 2023-02-22 | 2020-01-15: 2020-06-16; 2020-01-15: 2020-06-16; 2020-09-17: 2021-05-24; 2020-09-17: 2021-05-24 | [17 empty] | 10300681079 | 10300797585 | [10 empty] | TRUE | TRUE | 240 | 2020-06-16 | 2020-06-16 | 2020 | 2020 | 2020 |  | 44337 | 44340 | 2021-05-18 | Addendum
241 |  | Lanie Patterson | Brent Brooks | 2019-11-07 | [31 empty] | 5 - WINS |  | 870D1 | 236 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Tyson Buerkle | Bluewave MA, LLC | BWC MESSALONSKEE STREAM LLC | Benton Ave Benton | 2000130138 | 30011881221 | Solar | [5 empty] | 44.5795 | -69.5903 | Benton Ave |  |  | Benton | 22 | WINSLOW | 870D1 | 870T4 |  | 9310-L0453-0460-0005-ED00016 | FERC | WITHDRAWN | WITHDRAWN | NONE | Yes | Yes |  | K&L Engineering | Bruce Jagolinzer |  | 2019-11-12 | 2019-11-15 | 2019-11-22 | 2019-11-12 | 2019-11-15 | 2021-01-28 |  | 2021-02-11 |  | 2021-01-28 | 2021-01-28 | 2021-02-11 |  |  | 2021-02-11 |  |  | CS | 2021-02-15 | [6 empty] | CS |  |  | 2021-02-15 | [11 empty] | 2021-02-15 | [17 empty] | 2021-02-19 | [11 empty] | 2021-04-26 |  |  | 2021-06-22 | Report |  |  | 2021-06-22 | [8 empty] | 2021-06-22 | [17 empty] | 2021-06-30 | [7 empty] | 2021-06-30 | [22 empty] | 2023-12-04 | 2020-01-15: 2021-07-13; 2020-01-15: 2021-07-13; 2020-09-17: 2021-07-13; 2020-09-17: 2021-07-13 | [17 empty] | Requested | [11 empty] | TRUE | TRUE | 241 | 2021-07-13 | 2021-07-13 | 2021 | 2021 | 2021 |  |  |  | 2021-06-22 | Report
242 |  | Lanie Patterson | Brent Brooks | 2019-11-07 | [31 empty] | 6 - WINS |  | 870D1 | 241 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Tyson Buerkle | Bluewave MA, LLC | BWC MESSALONSKEE STREAM LLC | Benton Ave B Benton | 2000130138 | 30011881221 | Solar | [5 empty] | 44.5791 | -69.5899 | Benton Ave |  |  | Benton | 22 | WINSLOW | 870D1 | 870T4 |  | FLOC-MISSING-01142021 | FERC | WITHDRAWN | WITHDRAWN |  | Yes | Yes |  | K&L Engineering | Bruce Jagolinzer |  | 2019-11-12 | 2019-11-15 | 2019-11-22 | 2019-11-12 | 2019-11-15 | 2021-01-28 |  | 2021-02-11 |  | 2021-01-28 | 2021-01-28 | 2021-02-11 |  |  | 2021-02-11 |  |  | CS | 2021-02-15 | [6 empty] | CS |  |  | 2021-02-15 | [11 empty] | 2021-02-15 | [17 empty] | 2021-02-19 | [11 empty] | 2021-04-26 |  |  | 2021-06-22 | Report |  |  | 2021-06-22 | [8 empty] | 2021-06-22 | [17 empty] | 2021-06-30 | [7 empty] | 2021-06-30 | [22 empty] | 2023-12-04 | 2020-01-15: 2021-07-13; 2020-01-15: 2021-07-13; 2020-09-17: 2021-07-13; 2020-09-17: 2021-07-13 | [17 empty] | Requested | [11 empty] | TRUE | TRUE | 242 | 2021-07-13 | 2021-07-13 | 2021 | 2021 | 2021 |  |  |  | 2021-06-22 | Report
243 |  | Lanie Patterson | Brent Brooks | 2019-11-07 | [31 empty] | 7 - WINS |  | 870D1 | 242 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Tyson Buerkle | Bluewave MA, LLC | BWC TWELEVEMILE BROOK LLC | 0 Bangor Rd Benton | 2000130160 | 30011881239 | Solar/Battery | [5 empty] | 44.5906 | -69.5481 | 0 Bangor Rd |  |  | Benton | 19 | WINSLOW | 870D1 | 870T4 |  | FLOC-MISSING-01142021 | FERC | WITHDRAWN | WITHDRAWN |  | Yes | Yes |  | K&L Engineering | Bruce Jagolinzer |  | 2019-11-12 | 2019-11-15 | 2019-11-22 | 2019-11-12 | 2019-11-15 | 2021-07-13 |  | 2021-07-27 |  | 2021-08-05 | 2021-08-05 | 2021-08-19 |  |  | 2021-08-18 |  |  | CS | 2021-08-19 | [6 empty] | CS |  |  | 2021-08-19 | [11 empty] | 2021-08-25 | [17 empty] | 2021-08-31 | [11 empty] | 2021-11-04 | [6 empty] | 2021-11-17 | [8 empty] | 2021-11-17 | [8 empty] | 2021-11-18 | [16 empty] | 2021-11-22 | [9 empty] | 2021-12-07 | [12 empty] | 2023-12-04 | 2020-01-15: 2021-12-08; 2020-01-15: 2021-12-08 | [17 empty] | Requested | [11 empty] | TRUE | TRUE | 243 | 2021-12-08 | 2021-12-08 | 2021 | 2021 | 2021
244 |  |  | Anthony Boucher | 2019-11-07 | [31 empty] | 3 - SEAR |  | 850D2 | 240 |  | WITHDRAWN | WITHDRAWN |  | Matthew Doubleday | SunRaise Investments LLC | SUNRAISE DEVELOPMENT LLC | 247 W Main (Searsport) | 2000124937 | 30011924369 | Solar/Battery | [7 empty] | 247 West Main Street |  |  | Searsport |  | SEARSPORT | 850D2 |  |  | 9310-L0428-5220-0005-ED00035 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2019-11-15 | 2019-11-22 |  |  |  |  | 1900-01-12 | [57 empty] | Pending | [69 empty] | 2020-01-12 | [37 empty] | TRUE | TRUE | 244 | 0 | 0 | 1900 | #VALUE! | #VALUE!
245 |  | Govinda Neupane |  | 2019-11-07 | [31 empty] | 2 - ANSO |  | 801D1 | 194 |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2021-12-17 | Nate Niles | REVISION ENERGY INC | Community Solar New England, LLC | 486 Anson Rd Starks | 2000322628 | 30014554130 | Solar | 1800 | 1.8 | 2311.36 |  |  | 44.7374 | -69.9203 | 7 Redtail road | 7 | Redtail Road | Starks | 19 | ANSON | 801D1 | 801T1 |  | FLOC-MISSING-01142021 | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-11-12 | 2019-11-15 | 2019-11-22 | 2019-11-12 | 2019-11-15 | 2019-11-22 |  | 2019-12-10 |  | 2019-11-22 | 2019-11-22 | 2019-12-06 |  |  | 2019-12-06 | 2020-04-21 |  | CS | 2019-12-17 | RS | 2020-04-21 |  |  |  |  | CS |  |  | 2019-12-17 | 2020-04-21 | [10 empty] | 2020-01-27 | 2020-04-21 | [16 empty] | 2020-01-30 | 2020-04-24 | [5 empty] | Yes |  |  |  |  | 2020-04-03 | 2020-06-08 | [5 empty] | 2020-04-01 | 2020-06-04 | [6 empty] | 2020-04-02 | 2020-06-04 | [17 empty] | 2020-04-06 | 2020-06-09 | [14 empty] | 2020-06-29 |  | 2020-06-29 | 2022-11-08 |  | 2022-11-08 | [10 empty] | 2020-01-15: 2020-07-06; 2020-01-15: 2020-07-06 | [13 empty] | Q4 2021 |  |  |  | 10300687589 | [11 empty] | TRUE | TRUE | 245 | 2020-07-06 | 2020-07-06 | 2020 | 2020 | 2020
246 |  | Govinda Neupane |  | 2019-11-07 | 2022-12-13 | L2_Bump |  | 2023-07-18 | L2_Bump |  | 2024-01-04 | L2_bump |  | 2024-10-21 | L2 With | [20 empty] | 2 - DEXT |  | 813D1 | 164 | Yes | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Nick Mazuroski | Dirigo/BNRG | BD SOLAR DEXTER LLC | Corinna Rd/ Dexter | 2000130309 | 30011883474 | Solar | [5 empty] | 45.0017 | -69.2819 | 383 Corinna Rd |  |  | Dexter | 26 | DEXTER | 813D1 | 813T1 | 12.47 | 9310-SS0813 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-11-12 | 2019-11-15 | 2019-11-22 | 2019-11-12 | 2019-11-15 | 2020-04-23 |  | 2020-05-07 |  | 2020-04-23 | 2020-04-23 | 2020-05-07 |  |  | 2020-04-23 | 2023-12-12 |  | CS | 2020-04-23 | [6 empty] | CS |  |  | 2020-04-23 | 2024-06-10 |  | 2022-12-15 | 2023-07-19 | 2024-01-05 |  |  |  | 2024-06-24 |  |  | 2020-05-07 | 2024-06-25 |  | 2022-12-22 | 2023-08-14 | 2024-01-29 |  |  |  |  | 2024-06-25 |  |  | 2023-08-15 | 2024-02-15 |  |  |  | 2020-05-01 | 2024-06-25 |  | 2023-12-27 | 2023-08-21 | 2024-02-16 |  | Pending |  |  |  |  | 2020-07-07 | 2024-08-07 |  | 2021-05-24 | Addendum |  |  | 2020-07-06 | 2024-08-07 |  | 2023-02-08 | 2023-10-03 | 2024-04-24 |  |  |  | 2020-07-10 | 2024-08-07 |  | 2023-02-08 | 2023-10-04 | 2024-04-24 |  |  |  |  | 2024-08-15 |  | 2023-02-14 | 2023-10-09 | 2024-05-08 |  |  |  | 2020-07-16 | 2024-08-21 |  | 2023-02-16 |  | 2024-05-15 |  |  |  | 2024-08-21 |  |  |  | 2024-05-15 | 2021-06-03 |  | 2020-08-10 |  | 2020-08-13 | 2023-03-10 |  | 2023-04-06 | [5 empty] | 261462 |  | 514737 | 2024-08-07 | 2025-08-07 | 2020-08-18 | 2020-08-18 | 2021-06-16 | 2021-06-16 | 2023-04-07 | 2023-04-07 | 2024-09-25 | 2024-09-25 | [13 empty] | Q4 2021 |  |  |  | 10300702850 | [11 empty] | TRUE | TRUE | 246 | 2020-08-18 | 2020-08-18 | 2020 | 2020 | 2020 | 44350 |  |  | 2021-05-24 | Addendum
247 |  | Govinda Neupane |  | 2019-11-07 | [31 empty] | 1 - NOAN |  | 838D1 |  |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2021-12-17 | Abby Broedlin | Nautilus US Power Holdco, LLC | BD SOLAR NORTH ANSON LLC | Valley Rd Rt 234 N Anson | 2000130585 | 30011887202 | Solar | 2000 | 2 | 2764.8 |  |  | 44.851 | -69.9162 | 110 ME-234 |  |  | North Anson | 4 | NORTH ANSON | 838D1 | 838T1 |  | FLOC-MISSING-01142021 | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-11-15 | 2019-11-15 | 2019-11-22 | 2019-11-15 | 2019-11-18 | 2019-11-20 |  | 2019-12-06 |  | 2019-11-20 | 2019-11-20 | 2019-12-04 |  |  | 2019-11-20 |  |  | CS | 2019-11-20 | [6 empty] | CS |  |  | 2019-11-20 | [11 empty] | 2020-01-30 | [17 empty] | 2020-02-03 | [6 empty] | Yes |  |  |  |  | 2020-04-07 |  |  | 2021-05-20 | Addendum |  |  | 2020-04-08 | [8 empty] | 2020-03-23 | 2020-05-14 | [16 empty] | 2020-03-29 | 2020-05-22 | [12 empty] | 2021-06-07 |  | 2020-05-22 |  | 2020-05-26 |  |  |  | 2023-04-18 | 2023-04-18 |  |  |  | 174349 | 2023-05-21 |  |  |  | 2020-01-15: 2020-06-04; 2020-01-15: 2020-06-04; 2020-09-17: 2021-06-24; 2020-09-17: 2021-06-24 |  |  | 2023-04-18 | 2023-04-18 | [9 empty] | Q4 2021 |  |  |  | 10300684315 | [11 empty] | TRUE | TRUE | 247 | 2020-06-04 | 2020-06-04 | 2020 | 2020 | 2020 | 44354 |  |  | 2021-05-20 | Addendum
248 |  | Marshall Ripley | Rick Duperre | 2019-11-07 | [31 empty] | 3 - SPST |  | 668D5 | 217 |  | WITHDRAWN | WITHDRAWN |  | Nick Mazuroski | Dirigo/BNRG | BD SOLAR WESTLAND LLC | Eleanor Ave Westbrook | 2000130971 | 30011893259 | Solar | [7 empty] | 740 County Rd |  |  | Westbrook |  | SPRING STREET | 668D5 |  |  | 86-Withdrawn-86d | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2019-11-15 | 2019-11-22 |  |  |  |  | 1900-01-12 | [57 empty] | Pending | [69 empty] | 2020-01-29 | [37 empty] | TRUE | TRUE | 248 | 0 | 0 | 1900 | #VALUE! | #VALUE!
249 |  | Govinda Neupane |  | 2019-11-07 | [31 empty] | 4 - SKNS |  | 853D2 | 229 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Nick Mazuroski | Dirigo/BNRG | BD SOLAR SKOWHEGAN LLC | Transfer Station Drive Skowhegan | 2000132131 | 30011910566 | Solar | [5 empty] | 44.7936 | -69.7165 | Transfer Station Dr |  |  | Skowhegan | 9.2 | SKOWHEGAN NORTH SIDE | 853D2 | 853T1 |  | FLOC-MISSING-01142021 | Non-FERC | WITHDRAWN | WITHDRAWN | 325000 | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-11-15 | 2019-11-15 | 2019-11-22 | 2019-11-15 | 2019-11-18 | 2020-11-06 |  | 2020-11-23 |  | 2020-11-06 | 2020-11-08 | 2020-11-20 |  |  | 2020-11-09 | 2021-07-26 |  | CS | 2020-11-09 | RS | 2021-07-26 |  |  |  |  | CS |  |  | 2020-11-09 | 2021-07-26 | [28 empty] | 2020-11-12 | 2021-08-03 | [10 empty] | 2021-01-21 | 2021-09-15 |  | 2021-05-24 | Addendum |  |  | 2021-01-21 | 2021-08-26 | [7 empty] | 2021-01-27 | 2021-08-26 | [16 empty] | 2021-02-04 | 2021-08-31 | [6 empty] | 2021-02-04 | 2021-08-31 |  |  |  |  | 2021-06-15 |  |  |  |  | 2022-11-15 |  | 2022-12-05 | [5 empty] | 315477 |  | 479067 | 2022-11-30 | 2023-12-20 | 2020-01-15: 2021-09-16; 2020-01-15: 2021-09-16; 2020-09-17: 2022-12-07; 2020-09-17: 2022-12-08 | [17 empty] | Requested | [11 empty] | TRUE | TRUE | 249 | 2021-09-16 | 2021-09-16 | 2021 | 2021 | 2021 | 44362 |  |  | 2021-05-24 | Addendum
250 |  | Lanie Patterson | Brent Brooks | 2019-11-12 | [31 empty] | 2 - BOND |  | 208D3 | 212 |  | WITHDRAWN | WITHDRAWN |  | Mike Imoto | MEVS LLC AKA CENERGY | BAP POWER CORP | Augusta Airport #2 | 2000122114 | 30011883185 | Solar | [7 empty] | 75 Airport Rd |  |  | Augusta |  | BOND BROOK | 208D3 |  |  | 9310-L0021-0240-0265-ED00068 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2019-11-19 | 2019-11-26 |  |  |  |  | 1900-01-12 | [57 empty] | Pending | [69 empty] | 2020-01-24 | [37 empty] | TRUE | TRUE | 250 | 0 | 0 | 1900 | #VALUE! | #VALUE!
251 |  | Govinda Neupane |  | 2019-11-12 | [31 empty] | 1 - FAFA |  | 818D2 |  |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN | 2020-06-25 | Stephanie Sienkowski | Summit Ridge Energy | SRE SOLAR ORIGINATION 1 LLC | 538 Whittier Rd, Farmington | 2000120852 | 30011908453 | Solar | [5 empty] | 44.6345 | -70.1151 | 538 Whittier Rd |  |  | Farmington | 54 | FARMINGTON FALLS | 818D2 | 818T1 |  | 9310-L0403-2030-0006-ED00063 | Non-FERC | WITHDRAWN | WITHDRAWN | 250000 | [7 empty] | 2019-11-19 | 2019-11-26 | 2019-11-15 | 2019-11-18 |  | 2019-11-20 | 1900-01-12 | 2019-11-20 | 2019-11-21 | 2019-11-21 | [6 empty] | CS | 2019-12-03 | [9 empty] | 2019-12-03 | [19 empty] | 2019-12-04 | 2019-12-04 | [8 empty] | 2019-12-13 | [6 empty] | Yes | [11 empty] | 2020-02-21 | [26 empty] | 2020-03-05 | [7 empty] | 2020-03-12 | [7 empty] | 2020-03-18 |  | 2020-03-18 |  | 2020-03-18 | [6 empty] | 262479 |  |  |  | 2022-02-11 | 2020-01-15: 2020-03-20; 2020-01-15: 2020-03-20; 2020-09-17: 2021-08-16; 2020-09-17: 2021-08-16 | [16 empty] | TBD | 10300657461 | [11 empty] | TRUE | TRUE | 251 | 2020-03-20 | 2020-03-20 | 2020 | 2020 | 2020
252 |  | Rigel Paradise | Rick Duperre | 2019-11-13 | [31 empty] | 1 - BERW |  | 603D2 |  |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2020-06-25 | Jim Gordon | Energy Management, Inc. | BERWICK SOLAR LLC | 193 Route 236 Berwick | 2000134326 | 30011946628 | Solar | 3562 | 3.562 | 4147 |  |  | 43.2499 | -70.8315 | 193 Route 236 |  |  | Berwick | 56 | BERWICK | 603D2 | 603T1 |  | 9310-L0214-0470-0147-ED00158 | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-11-15 | 2019-11-20 | 2019-11-27 | 2019-11-15 | 2019-11-18 | 2019-11-18 |  | 2019-12-04 |  | 2019-11-18 | 2019-11-18 | 2019-12-02 |  |  | 2019-11-18 |  |  | CS | 2019-11-18 | [6 empty] | CS |  |  | 2019-11-18 | [11 empty] | 2019-12-05 | [17 empty] | 2019-12-05 | [6 empty] | Yes |  |  |  |  | 2020-02-10 |  |  | 2021-06-17 | Addendum |  |  | 2020-02-04 | [8 empty] | 2020-02-05 | [17 empty] | 2020-02-12 | [15 empty] | 2020-03-05 |  | 2020-03-06 | [13 empty] | 2020-01-15: 2020-03-24; 2020-01-15: 2020-03-24 | [13 empty] | Q4 2020 |  |  | TBD | 10300672734 | [11 empty] | TRUE | TRUE | 252 | 2020-03-24 | 2020-03-24 | 2020 | 2020 | 2020 |  |  |  | 2021-06-17 17:07 | Addendum
253 |  | Eben Snow | Brent Brooks | 2019-11-13 | [31 empty] | 2 - R115 |  | 445D2 | 50 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Mike Lucini | ISM Solar Development LLC | ISM SOLAR CROOKED RIVER LLC | 0 River Rd Naples | 2000170138 | 30012490386 | Solar | [5 empty] | 44.1 | -70.574 | 0 River Rd |  |  | Naples | 3 | RAYMOND 115 KV | 445D2 | 445T2 |  | 9310-L0185-4040-0070-ED00036 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Under Review 1/31/2020 | Yes |  | K&L Engineering | Bruce Jagolinzer |  | 2019-11-15 | 2019-11-20 | 2019-11-27 | 2019-11-15 | 2019-11-18 | 2020-05-05 |  | 2020-05-19 |  | 2020-05-05 | 2020-05-05 | 2020-05-19 |  |  | 2020-05-08 |  |  | CS | 2020-05-08 | [6 empty] | CS |  |  | 2020-05-08 | [11 empty] | 2020-05-08 | [17 empty] | 2020-05-15 | [6 empty] | Yes |  |  |  |  | 2020-07-21 | [6 empty] | 2020-07-16 | [8 empty] | 2020-07-17 | [17 empty] | 2020-07-20 | [15 empty] | 2020-07-28 |  | 2020-07-28 | [12 empty] | 2024-05-14 | 2020-01-15: 2020-08-04; 2020-01-15: 2020-08-04 | [17 empty] | 10300695744 | [11 empty] | TRUE | TRUE | 253 | 2020-08-04 | 2020-08-04 | 2020 | 2020 | 2020
254 |  | Lanie Patterson | Brent Brooks | 2019-11-13 | [31 empty] | 2 - SOWA |  | 855D2 | 7 |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2021-12-17 | Laurie Birmingham | REVISION ENERGY INC | Sidney Solar II LLC | 377 West River Rd Sidney Me | 2000349909 | 30014910142 | Solar | 1950 | 1.95 | 2789 |  |  | 44.5011 | -69.6839 | 377 W River Rd |  |  | Sidney | 121 | SOUTH WATERVILLE | 855D2 | 855T1 |  | FLOC-MISSING-01142021 | Non-FERC | TRIGGERING | TRIGGERING ($325,000) | 116284.4 | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-11-15 | 2019-11-20 | 2019-11-27 | 2019-11-15 | 2019-11-18 | 2019-12-02 |  | 2019-12-16 |  | 2019-12-02 | 2019-12-02 | 2019-12-16 |  |  | 2019-12-16 |  |  | CS | 2020-01-21 | [6 empty] | CS |  |  | 2020-01-21 | [11 empty] | 2020-01-20 | [17 empty] | 2020-01-27 | [6 empty] | Yes |  |  |  |  | 2020-03-31 |  |  | 2021-06-10 | Addendum |  |  | 2020-04-01 | [8 empty] | 2020-03-20 | [17 empty] | 2020-04-02 | [15 empty] | 2020-04-22 |  | 2020-04-23 | [8 empty] | 303759 |  |  |  |  | 2020-01-15: 2020-05-20; 2020-01-15: 2020-05-20; 2020-09-17: 2021-06-11; 2020-09-17: 2021-06-11 | [13 empty] | Q4 2021 |  |  | TBD | 10300666056 | [11 empty] | TRUE | TRUE | 254 | 2020-05-20 | 2020-05-20 | 2020 | 2020 | 2020 |  |  |  | 2021-06-10 | Addendum
255 |  | Marshall Ripley | Rick Duperre | 2019-11-13 | 2023-02-15 | L2_Bump | [29 empty] | 3 - FOHI |  | 624D2 | 76 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Nate Niles | REVISION ENERGY INC | REVISION ENERGY INC | 81 Huston Rd Gorham Me 04038 | 2000038393 | 30011935639 | Solar | [5 empty] | 43.7225 | -70.4489 | 81 Huston Rd |  |  | Gorham | 137 | FORT HILL | 624D2 | 624T1 |  | 9310-L0251-2240-0118-ED00035 | Non-FERC | WITHDRAWN | WITHDRAWN | 325000 | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-11-15 | 2019-11-20 | 2019-11-27 | 2019-11-15 | 2019-11-18 | 2020-10-05 |  | 2020-10-20 |  | 2020-10-05 | 2020-10-09 | 2020-10-26 |  |  | 2020-10-21 | 2021-02-18 |  | CS | 2020-10-21 | RS | 2021-02-18 |  |  |  |  | CS |  |  | 2020-10-21 | 2021-02-18 | [11 empty] | 2021-02-01 |  | 2023-09-01 | [14 empty] | 2020-10-22 | 2021-02-19 | [5 empty] | Yes |  |  |  |  | 2020-12-29 | 2021-04-02 |  | 2021-06-11 | Report |  |  | 2021-01-08 | 2021-06-11 | [7 empty] | 2021-01-08 | 2021-06-11 | [16 empty] | 2021-01-14 | [7 empty] | 2021-01-14 | [22 empty] | 2023-10-03 | 2020-01-15: 2021-06-24; 2020-01-15: 2021-06-24; 2020-09-17: 2021-06-24; 2020-09-17: 2021-06-24 | [17 empty] | 10300802371 | [11 empty] | TRUE | TRUE | 255 | 2021-06-24 | 2021-06-24 | 2021 | 2021 | 2021 |  |  |  | 2021-06-11 | Report
256 |  |  | Anthony Boucher | 2019-11-13 | [31 empty] | 2 - MERO |  | 270D2 | 148 |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2020-08-31 | Stephen Campbell | Navisun LLC | BWC MACES POND LLC | 468 Rockland, Rockport | 2000133960 | 30011940084 | Solar | 3550 | 3.55 | 5680 |  |  | 44.1741 | -69.1242 | 468 Rockland St |  |  | Rockport | 7 6 | MEADOW ROAD | 270D2 | 270T2 |  | 9310-L0477-4980-0092-ED00011 | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-11-15 | 2019-11-20 | 2019-11-27 | 2019-11-15 | 2019-11-18 | 2020-03-09 |  | 2020-03-23 |  | 2020-03-09 | 2020-03-09 | 2020-03-23 |  |  | 2020-03-20 |  |  | CS | 2020-03-20 | [6 empty] | CS |  |  | 2020-03-20 | [11 empty] | 2020-03-26 | [17 empty] | 2020-04-08 | [6 empty] | Yes |  |  |  |  | 2020-06-12 |  |  | 2021-05-19 | Addendum |  |  | 2020-06-11 | [8 empty] | 2020-06-05 | [17 empty] | 2020-06-10 | [13 empty] | 2021-06-01 |  | 2020-06-10 |  | 2020-06-11 | [8 empty] | 147522 |  |  |  |  | 2020-01-15: 2020-06-12; 2020-01-15: 2020-06-12; 2020-09-17: 2021-06-14; 2020-09-17: 2021-06-14 | [13 empty] | Q4 2020 |  |  | TBD | 10300681806 | [11 empty] | TRUE | TRUE | 256 | 2020-06-12 | 2020-06-12 | 2020 | 2020 | 2020 | 44348 |  |  | 2021-05-19 | Addendum
257 |  | Lanie Patterson | Brent Brooks | 2019-11-13 | [31 empty] | 3 - MANC |  | 233D2 | 238 |  | WITHDRAWN | WITHDRAWN |  | Mark Chrisos | Con Edison Clean Energy | HALLOWELL A LLC | Pinicle Drive Hallowell | 2000192659 | 30012798010 | Solar/Battery | [7 empty] | Pinnacle Dr |  |  | Hallowell |  | MANCHESTER | 233D2 |  |  | 9310-L0064-2450-0008-ED00046 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2019-11-20 | 2019-11-27 |  |  |  |  | 1900-01-12 | [57 empty] | Yes | [69 empty] | 2021-01-05 | [25 empty] | 10300735552 | [11 empty] | TRUE | TRUE | 257 | 0 | 0 | 1900 | 1900 | 1900
258 |  | Eben Snow | Brent Brooks | 2019-11-13 | [31 empty] | 4 - CROW |  | 411D1 | 114 |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED |  | Abby Broedlin | Nautilus US Power Holdco, LLC | Sabattus Solar SB01 LLC | Sb01 Webster Corner Sabattus | 2000123236 | 30013328007 | Solar | 4900 | 4.9 | 5577 |  |  | 44.6478 | -70.1059 | Webster Corner Rd |  |  | Sabattus | 21 | CROWLEYS | 411D1 | 411T2 |  | 9310-L0123-6230-0035-ED00016 | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Yes | Yes |  | K&L Engineering | Bruce Jagolinzer |  | 2019-11-18 | 2019-11-20 | 2019-11-27 | 2019-11-18 | 2019-12-03 | 2019-12-03 |  | 2019-12-17 |  | 2019-12-03 | 2019-12-03 | 2019-12-17 |  |  | 2019-12-17 |  |  | CS | 2020-03-03 | [6 empty] | CS |  |  | 2020-03-03 | [11 empty] | 2020-02-14 | [17 empty] | 2020-03-26 | [6 empty] | Yes |  |  |  |  | 2020-06-01 | [6 empty] | 2020-06-02 | [8 empty] | 2020-06-08 | [17 empty] | 2020-06-11 | [15 empty] | 2020-06-15 |  | 2020-06-15 |  |  |  | 2023-03-29 | 2023-03-29 | [5 empty] | 665784 | 2021-07-27 |  | 2020-01-15: 2020-06-19; 2020-01-15: 2020-06-19; 2020-09-17: 2021-08-23; 2020-09-17: 2021-09-30 |  |  | 2023-07-17 | 2023-07-20 | [13 empty] | 10300685840 | [11 empty] | TRUE | TRUE | 258 | 2020-06-19 | 2020-06-19 | 2020 | 2020 | 2020
259 |  | Govinda Neupane |  | 2019-11-13 | [31 empty] | 3 - HART |  | 824D2 | 16 |  | WITHDRAWN | WITHDRAWN |  | Jay Smith | Standard Solar | STANDARD SOLAR INC | Webb Reach Rd, St Albans | 2000133526 | 30011933923 | Solar | [7 empty] | Webb Ridge |  |  | St Albans |  | HARTLAND | 824D2 |  |  | 86-Withdrawn-86d | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2019-11-20 | 2019-11-27 |  |  |  |  | 1900-01-12 | 2019-11-20 | 2019-12-03 | 2019-12-03 | [54 empty] | Yes | [69 empty] | 2020-04-14 | [37 empty] | TRUE | TRUE | 259 | 0 | 0 | 1900 | #VALUE! | #VALUE!
260 |  | Rigel Paradise | Rick Duperre | 2019-11-14 | [31 empty] | 3 - HITP |  | 692D1 | 239 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Joseph Feole | Soltage LLC | PARSONFIELD SOKOKIS SOLAR 1 LLC | 30 Sokokis Rd Parsonsfield | 2000176156 | 30012575764 | Solar | [5 empty] | 43.8012 | -70.8995 | 42 Sokokis Rd |  |  | Parsonfield | 4 | HIRAM TAP | 692D1 | 692T1 |  | 9310-L0372-4550-0050-ED00027 | FERC | WITHDRAWN | WITHDRAWN | 325000 | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-11-18 | 2019-11-21 | 2019-12-02 | 2019-11-18 | 2019-12-03 | 2020-05-21 |  | 2020-06-05 |  | 2020-05-21 | 2020-05-21 | 2020-06-05 |  |  | 2020-06-05 |  |  | CS | 2020-06-15 | [6 empty] | CS |  |  | 2020-06-15 | [11 empty] | 2020-06-18 | [17 empty] | 2020-06-17 | [6 empty] | Yes |  |  |  |  | 2020-08-20 |  |  | 2021-06-14 | Addendum |  |  | 2020-08-20 | [8 empty] | 2020-08-19 | [17 empty] | 2020-08-24 | [15 empty] | 2020-08-24 |  | 2020-08-26 |  |  |  | 2023-07-03 | 2023-07-10 | [7 empty] | 2024-07-01 | 2020-01-15: 2020-09-11; 2020-01-15: 2020-09-11; 2020-09-17: 2021-06-22; 2020-09-17: 2021-06-22 |  |  | 2023-10-10 | 2023-10-11 | [13 empty] | 10300714409 | [11 empty] | TRUE | TRUE | 260 | 2020-09-11 | 2020-09-11 | 2020 | 2020 | 2020 |  |  |  | 2021-06-14 | Addendum
261 |  | Govinda Neupane |  | 2019-11-14 | [31 empty] | 1 - STRA |  | 877D1 |  |  | WITHDRAWN | WITHDRAWN |  | Tyler Bailey | EDF Renewables | EDF RENEWABLES | Vaughn Rd Eustis | 2000134214 | 30011945075 | Solar | [7 empty] | Vaughn Road |  |  | Eustis |  | STRATTON | 877D1 |  |  | 86-Withdrawn-86d | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2019-11-21 | 2019-12-02 |  |  |  |  | 1900-01-12 | [57 empty] | Yes | [69 empty] | 2020-07-01 | [37 empty] | TRUE | TRUE | 261 | 0 | 0 | 1900 | #VALUE! | #VALUE!
262 |  | Govinda Neupane |  | 2019-11-18 | [31 empty] | 4 - LVFA |  | 428D1 | 133 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN | 2021-07-15 | Daniel Serber | NEXTGRID INC | NEXTGRID POTOMAC LLC | 111 Franklin Rd Jay | 2000201112 | 30012906639 | Solar | [5 empty] | 44.4886 | -70.1834 | 111 Franklin Rd |  |  | Jay | 126S | LIVERMORE FALLS | 428D1 | 428T1 |  | 9310-L0160-2920-0010-ED00151 | Non-FERC | NOT IMPACTED | NOT IMPACTED |  | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-11-25 | 2019-11-25 | 2019-12-04 | 2019-11-25 | 2019-12-03 | 2020-09-02 |  | 2020-09-17 |  | 2020-09-02 | 2020-09-02 | 2020-09-17 |  |  | 2020-09-17 |  |  | CS | 2020-09-25 | [6 empty] | CS |  |  | 2020-09-25 | [29 empty] | 2020-09-29 | [6 empty] | Yes |  |  |  |  | 2020-12-04 | [6 empty] | 2020-12-04 | [8 empty] | 2020-12-10 | [17 empty] | 2020-12-14 | [7 empty] | 2020-12-14 | [7 empty] | 2021-03-10 | 2021-08-05 | 2021-03-10 | [8 empty] | 1216645 |  |  |  | 2025-07-15 | 2020-01-15: 2021-03-10; 2020-01-15: 2021-03-10; 2020-09-17: 2021-08-13; 2020-09-17: 2021-08-13 | [13 empty] | Q3 2020 |  |  |  | 10300761644 | 10300827682 | [10 empty] | TRUE | TRUE | 262 | 2021-03-10 | 2021-03-10 | 2021 | 2021 | 2021 |  |  | 44413
263 |  | Lanie Patterson | Brent Brooks | 2019-11-18 | [31 empty] | 9 - MONM |  | 457D3 | 193 |  | WITHDRAWN | WITHDRAWN |  | Jamal Batar | Dimension Renewable Energy | MONMOUTH CSG LLC | 85 Oak Hill Rd Monmouth Me | 2000155124 | 30012263460 | Solar | [5 empty] | 44.1825 | -69.9909 | 85 Oak Hill Rd |  |  | Monmouth |  | MONMOUTH | 457D3 | 457T2 |  | 9310-L0200-3740-0031-ED00028 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  |  | 2019-11-25 | 2019-12-04 | 2019-11-25 | 2019-12-03 |  | 2022-01-18 | 1900-01-12 | 2022-01-18 | 2022-01-19 | 2022-01-19 | [6 empty] | N/A | [47 empty] | No Study | [69 empty] | 2022-01-31 | [37 empty] | TRUE | TRUE | 263 | 0 | 0 | 1900 | 1900 | 1900
264 |  | Govinda Neupane |  | 2019-11-18 | [31 empty] | 1 - PHST |  | 841D1 |  |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2020-08-31 | Tyler William Perkins | Nexamp, Inc | Norton Road Solar 1 LLC | 276 Norton Hill Rd Strong | 2000276130 | 30013924615 | Solar | 4990 | 4.99 |  |  |  | 44.7959 | -70.2055 | 276 Norton Hill Rd |  |  | Strong | 6 | PHILLIPS/STRONG | 841D1 | 841T1 |  | 9310-L0424-5580-0026-ED00033 | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-11-25 | 2019-11-25 | 2019-12-04 | 2019-11-25 | 2019-12-04 | 2019-12-04 |  | 2019-12-18 |  | 2019-12-04 | 2019-12-04 | 2019-12-18 |  |  | 2019-12-05 |  |  | CS | 2019-12-05 | [6 empty] | CS |  |  | 2019-12-05 | [11 empty] | 2020-02-20 | [17 empty] | 2020-02-25 | [6 empty] | Yes |  |  |  |  | 2020-04-29 |  |  | 2021-05-20 | Addendum |  |  | 2020-04-29 | [8 empty] | 2020-04-28 | [17 empty] | 2020-05-04 | [13 empty] | 2021-06-10 |  | 2020-05-04 |  | 2020-05-05 | [8 empty] | 611955 |  |  |  |  | 2020-01-15: 2020-05-06; 2020-01-15: 2020-05-06; 2020-09-17: 2021-06-22; 2020-09-17: 2021-06-22 | [13 empty] | Q3 2021 |  |  | TBD | 10300675406 | 10300797584 | [10 empty] | TRUE | TRUE | 264 | 2020-05-06 | 2020-05-06 | 2020 | 2020 | 2020 | 44357 |  |  | 2021-05-20 | Addendum
265 |  | Lanie Patterson | Brent Brooks | 2019-11-19 | 2022-07-09 | L2_Bump | [29 empty] | 3 - OAKL |  | 839D1 | 75 |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2021-12-17 | Jess Roden | Greenbacker Capital | ER ALPINE STREET SOLAR LLC | 86 So Alpine St Oakland | 2000134579 | 30012773724 | Solar | 2375 | 2.375 | 1500 |  |  | 44.5401 | -69.7149 | 86 South Alpine St |  |  | Oakland | 17 | OAKLAND | 839D1 | 839T1 |  | 9310-L0422-4300-0001-ED00011 | Non-FERC | TRIGGERING | TRIGGERING (330,000) | 232291 | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-11-26 | 2019-11-26 | 2019-12-05 | 2019-11-26 | 2019-12-05 | 2020-08-11 |  | 2020-08-25 |  | 2020-08-11 | 2020-08-11 | 2020-08-25 |  |  | 2020-08-25 |  |  | CS | 2020-08-26 | [6 empty] | CS |  |  | 2020-08-26 |  |  | 2022-07-19 | [8 empty] | 2020-08-25 |  |  | 2022-08-02 | [14 empty] | 2020-09-08 |  |  | 2022-10-13 |  |  |  | Pending |  |  |  |  | 2020-11-11 |  |  | 2021-05-18 | Addendum |  |  | 2020-11-11 |  |  | 2022-10-10 | [5 empty] | 2020-11-16 |  |  | 2022-10-12 | [8 empty] | 2022-10-21 | [5 empty] | 2020-11-18 |  |  | 2022-10-24 |  |  |  |  | 2020-11-18 | [5 empty] | 2021-05-24 |  | 2021-05-26 |  | 2021-01-04 | 2022-11-17 |  | 2022-12-01 | [5 empty] | 290075 | 2020-11-05 | 716225 | 2022-10-10 |  | 2021-05-28 | 2021-05-28 | 2021-05-26 | 2021-05-26 | 2022-12-02 | 2022-12-05 | [5 empty] | 2022-06-14 | [9 empty] | Q4 2020 |  |  |  | 10300793051 | [11 empty] | TRUE | TRUE | 265 | 2021-05-28 | 2021-05-28 | 2021 | 2021 | 2021 | 44340 |  |  | 2021-05-18 | Addendum
266 |  |  | KRISTOFER COLEMAN | 2019-11-19 | [31 empty] | 1 - DAMS |  | 219D2 |  |  | WITHDRAWN | WITHDRAWN |  | Noah Gonzalez | Nexamp, Inc | NEXAMP SOLAR LLC | 748 Us Route 1 Newcastle | 2000114877 | 30011951297 | Solar/Battery | [10 empty] | Newcastle |  | DAMARISCOTTA MILLS | 219D2 |  |  | 9310-L0051-4100-0074-ED00051 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2019-11-26 | 2019-12-05 |  |  |  |  | 1900-01-12 | [57 empty] | Pending | [69 empty] | 2021-07-07 | [24 empty] | TBD | [12 empty] | TRUE | TRUE | 266 | 0 | 0 | 1900 | #VALUE! | #VALUE!
267 |  | Lanie Patterson | Brent Brooks | 2019-11-19 | [31 empty] | 10 - MONM |  | 457D1 | 263 |  | WITHDRAWN | WITHDRAWN |  | Payne Morgan | Encore Redevelopment, LLC | ENCORE REDEVELOPMENT LLC | 195 Andrews Way Wales Me | 2000134579 | 30011954929 | Solar | [5 empty] | 44.1714 | -70.038 | 195 Andrews Road |  |  | Wales |  | MONMOUTH | 457D1 | 457T1 |  | 9310-L0198-6140-0001-ED00002 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  |  | 2019-11-26 | 2019-12-05 | 2019-11-26 | 2019-12-05 |  | 2022-03-07 | 1900-01-12 | 2022-03-08 | 2022-03-09 | 2022-03-09 | [6 empty] | N/A | [47 empty] | No Study | [69 empty] | 2022-03-10 | [37 empty] | TRUE | TRUE | 267 | 0 | 0 | 1900 | 1900 | 1900
268 |  | Govinda Neupane |  | 2019-11-19 | 2022-08-29 | L2_Bump |  | 2024-12-20 | L2_With | [26 empty] | 1 - CORI | 1 - CORI | 811D1 |  | Yes | EXECUTED | EXECUTED |  | Tyler Perkins | Nexamp, Inc | CORINNA SOLAR 1 LLC | White Rd / Corinna Me 04928 | 2000134710 | 30011952782 | Solar | 4950 | 4.95 | 7492 |  |  | 45.3156 | -69.2057 | 99 White Rd | 99 | White RD | Corinna | 6 | CORINNA | 811D1 | 811T1 | 12.47 | FLOC-MISSING-01142021 | Non-FERC | TRIGGERING | TRIGGERING | 325000 | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-11-26 | 2019-11-26 | 2019-12-05 | 2019-11-26 | 2019-12-05 | 2019-12-12 |  | 2019-12-27 |  | 2019-12-12 | 2019-12-12 | 2019-12-26 |  |  | 2019-12-12 |  |  | CS | 2019-12-12 | FS | 2022-11-10 |  |  |  |  | CS |  |  | 2019-12-12 |  | 2022-12-05 | 2022-08-31 | [8 empty] | 2020-03-06 | [17 empty] | 2020-04-02 |  | 2022-12-08 | 2022-09-06 |  |  |  | Pending |  |  |  |  | 2020-06-08 |  | 2023-02-14 | 2021-06-08 | Addendum |  |  | 2020-06-08 |  | 2023-04-26 | 2022-10-18 | [5 empty] | 2020-06-17 |  | 2023-04-14 | 2022-10-18 | [7 empty] | 2023-04-26 | 2022-10-20 | [5 empty] | 2020-06-24 |  | 2023-05-02 | 2022-10-24 | [10 empty] | 2021-06-14 |  | 2020-07-10 |  | 2020-07-20 | 2023-09-07 | [7 empty] | 820775 |  | 969578 | 2023-09-06 |  | 2020-07-23 | 2020-07-23 | 2021-07-01 | 2021-07-01 | 2023-10-10 | 2023-10-11 | [15 empty] | Q4 2020 |  |  |  | 10300692562 | [11 empty] | FALSE | TRUE | 268 | 2020-07-23 | 2020-07-23 | 2020 | 2020 | 2020 | 44361 |  |  | 2021-06-08 | Addendum
269 |  | Eben Snow | Brent Brooks | 2019-11-20 | [31 empty] | 3 - NORW |  | 435D3 | 178 |  | WITHDRAWN | WITHDRAWN |  | Eric Weinstein | BORREGO SOLAR SYSTEMS INC | 510 PV PROJECT DEVELOPMENT LLC | Hathaway Rd Paris | 2000113260 | 30011907588 | Solar/Battery | [7 empty] | Hathaway Rd |  |  | Paris |  | NORWAY | 435D3 |  |  | 9310-L0170-4500-0128-ED00004 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2019-11-27 | 2019-12-06 |  |  |  |  | 1900-01-12 | [57 empty] | Pending | [69 empty] | 2023-02-18 | [37 empty] | TRUE | TRUE | 269 | 0 | 0 | 1900 | #VALUE! | #VALUE!
270 |  | Lanie Patterson | Brent Brooks | 2019-11-20 |  | L2_Bump |  |  |  |  | 2023-03-27 | wthdw | [21 empty] | 1 - VASS |  | 1 - VASS |  | 861D8 |  | Yes | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2021-12-17 | Liam McCormack | Summit Ridge Energy | VASSALBORO PV LLC | 2579 Riverside Dr Vassalboro | 2000408735 | 30015687665 | Solar | 3300 | 3.3 | 6855 |  |  | 44.4772 | -69.678 | 2579 Riverside Dr |  |  | Vassalboro | 190 | VASSALBORO | 861D8 | 861T1 |  | FLOC-MISSING-01142021 | Non-FERC | TRIGGERING | TRIGGERING ($250,000) | 98215 | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-11-27 | 2019-11-27 | 2019-12-06 | 2019-11-27 | 2019-12-05 | 2019-12-13 |  | 2019-12-30 |  | 2019-12-13 | 2019-12-13 | 2019-12-27 |  |  | 2019-12-16 |  |  | CS | 2019-12-16 | [6 empty] | CS |  |  | 2019-12-16 | 2022-07-05 |  | 2022-07-05 | 2022-10-17 | 2023-03-27 | [6 empty] | 2020-01-20 |  |  |  | 2022-10-17 | 2023-04-27 | [7 empty] | 2022-10-17 | 2023-02-27 |  |  |  | 2020-01-27 |  |  | 2022-07-11 | 2022-10-18 | 2023-05-01 |  | Yes |  |  |  |  | 2020-03-31 | 2022-08-10 |  | 2021-05-20 | Addendum |  |  | 2020-03-30 | 2022-07-19 |  | 2022-07-20 | 2022-11-04 | 2023-06-13 |  |  |  | 2020-03-13 | 2022-07-20 |  | 2022-07-20 | 2022-11-04 | 2023-06-14 |  |  |  |  | N/A | [7 empty] | 2020-03-17 | N/A | [12 empty] | 2021-06-07 |  | 2020-04-08 |  | 2020-04-13 | 2022-07-26 | [7 empty] | 803775 |  | 1246998 | 2023-06-13 |  | 2020-04-17 | 2020-04-17 | 2021-07-07 | 2021-07-07 | 2022-08-01 | 2022-08-01 | 2022-11-11 | 2022-11-12 | 2023-07-03 | 2023-07-05 |  |  |  |  | 2022-07-11 | [6 empty] | Q1 2022 |  |  | TBD | 10300678588 | [11 empty] | FALSE | TRUE | 270 | 2020-04-17 | 2020-04-17 | 2020 | 2020 | 2020 | 44354 |  |  | 2021-05-20 | Addendum
271 |  | Eben Snow | Brent Brooks | 2019-11-21 | [31 empty] | 1 - SABA |  | 450D1 |  |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED |  | John Motta | Dynamic Energy | SABATTUS SOLAR LLC | Sabattus Rd Sabattus | 2000163167 | 30012390768 | Solar | 900 | 0.9 | 1244.16 |  |  | 44.1276 | -70.071 | Sabattus Rd |  |  | Sabattus | 6 | SABATTUS | 450D1 | 450T1 |  | 9310-L0192-6230-0023-ED00080 | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-12-02 | 2019-12-02 | 2019-12-09 | 2019-12-02 | 2019-12-05 | 2019-12-13 |  | 2019-12-30 |  | 2019-12-13 | 2019-12-13 | 2019-12-27 |  |  | 2019-12-16 | 2020-04-21 |  | CS | 2019-12-16 | RS | 2020-04-21 |  |  |  |  | CS |  |  | 2019-12-16 | 2020-04-21 | [10 empty] | 2020-01-07 | [17 empty] | 2020-01-07 | 2020-05-01 | [5 empty] | Yes |  |  |  |  | 2020-03-12 | 2020-06-15 |  | 2021-06-03 | Addendum |  |  | 2020-03-10 | 2020-06-01 | [7 empty] | 2020-03-13 | 2020-06-01 | [16 empty] | 2020-03-18 | 2020-06-08 | [14 empty] | 2020-06-15 |  | 2020-06-15 | [8 empty] | 36835 |  |  |  |  | 2020-04-17: 2020-06-16; 2020-04-17: 2020-06-16; 2021-07-07: 2021-07-13; 2021-07-07: 2021-07-13 | [12 empty] | 2021-07-19 |  |  | 10300681151 | 10300681151 | [10 empty] | TRUE | TRUE | 271 | 2020-06-16 | 2020-06-16 | 2020 | 2020 | 2020 |  |  |  | 2021-06-03 | Addendum
272 |  | Govinda Neupane |  | 2019-11-22 | [31 empty] | 1 - MONS |  | 834D2 |  |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  |  | Nexamp, Inc | GREENVILLE CSG LLC | 166 Moosehead Lake Rd Greenvil | 2000155127 | 30012263494 | Solar | [5 empty] | 45.4465 | -69.5899 | 166 Moosehead Lake Rd |  |  | Greenville | 67 | MONSON | 834D2 | 34.5 kV Bus |  | FLOC-MISSING-01142021 | FERC | WITHDRAWN | WITHDRAWN | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-12-03 | 2019-12-03 | 2019-12-10 | 2019-12-03 | 2019-12-10 | 2019-12-06 |  | 2019-12-20 |  | 2019-12-06 | 2019-12-06 | 2019-12-20 |  |  | 2019-12-20 |  |  | CS | 2020-01-30 | [6 empty] | CS |  |  | 2020-01-30 | [11 empty] | 2020-02-03 | [17 empty] | 2020-02-14 | [6 empty] | Yes |  |  |  |  | 2020-04-21 |  |  | 2021-06-03 | Addendum |  |  | 2020-04-20 | [8 empty] | 2020-04-20 | [17 empty] | 2020-04-27 | [13 empty] | 2021-06-22 |  | 2020-05-11 |  | 2020-05-12 | [8 empty] | 91476 |  |  |  | 2026-05-04 | 2020-04-17: 2020-05-18; 2020-04-17: 2020-05-18; 2021-07-07: 2021-07-13; 2021-07-07: 2021-07-13 | [11 empty] | Q4 2021 |  |  | TBD | 10300678865 | [11 empty] | TRUE | TRUE | 272 | 2020-05-18 | 2020-05-18 | 2020 | 2020 | 2020 | 44369 |  |  | 2021-06-03 | Addendum
273 |  | Govinda Neupane |  | 2019-11-22 | [31 empty] | 2 - BETH |  | 403D1 | 57 |  | WITHDRAWN | WITHDRAWN |  | Jamal Batar | Dimension Renewable Energy | DIMENSION ME 1 LLC | Brook Rd Bethel Me 04217 | 2000123007 | 30011966816 | Solar | [7 empty] | Brook Rd |  |  | Bethel |  | BETHEL | 403D1 |  |  | 86-Withdrawn-86d | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2019-12-03 | 2019-12-10 |  |  |  |  | 1900-01-12 | [57 empty] | Pending | [69 empty] | 2020-04-14 | [37 empty] | TRUE | TRUE | 273 | 0 | 0 | 1900 | #VALUE! | #VALUE!
274 |  | Govinda Neupane |  | 2019-11-22 | [31 empty] | 4 - CARM |  | 808D2 | 177 |  | WITHDRAWN | WITHDRAWN |  | Jamal Batar | Dimension Renewable Energy | CARMEL CSG LLC | 31 Perry Ln Carmel Me | 2000155126 | 30012263486 | Solar | [7 empty] | 31 Perry Ln |  |  | Carmel |  | CARMEL | 808D2 |  |  | 86-Withdrawn-86d | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2019-12-03 | 2019-12-10 |  |  |  |  | 1900-01-12 | [57 empty] | Pending | [69 empty] | 2022-06-01 | [37 empty] | TRUE | TRUE | 274 | 0 | 0 | 1900 | #VALUE! | #VALUE!
275 |  | Lanie Patterson | Brent Brooks | 2019-11-25 | [31 empty] | 1 - SIDN |  | 242D1 |  |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2021-01-04 | Liam McCormack | Summit Ridge Energy | RE SIDNEY SOLAR LLC | 45 Shephard Rd., Sidney 04330 | 2000232282 | 30013526113 | Solar | 2000 | 2 | 2603.52 |  |  | 44.4246 | -69.7566 | 45 Shepherd Rd |  |  | Sidney | 47 | SIDNEY | 242D1 | 242T1 |  | 9310-L0076-5320-0076-ED00040 | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-12-03 | 2019-12-04 | 2019-12-11 | 2019-12-03 | 2019-12-10 | 2019-12-09 |  | 2019-12-23 |  | 2019-12-09 | 2019-12-09 | 2019-12-23 |  |  | 2019-12-19 |  |  | CS | 2019-12-19 | [6 empty] | CS |  |  | 2019-12-19 | [11 empty] | 2020-02-18 | [17 empty] | 2020-02-21 | [6 empty] | Yes |  |  |  |  | 2020-04-27 |  |  | 2021-06-08 | Addendum |  |  | 2020-04-27 | [8 empty] | 2020-04-17 | [17 empty] | 2020-04-24 | [15 empty] | 2020-05-14 | 2021-08-04 | 2020-05-15 | [8 empty] | 175996 |  |  |  |  | 2020-04-17: 2020-06-18; 2020-04-17: 2020-06-18; 2021-07-07: 2021-08-04; 2021-07-07: 2021-08-04 | [11 empty] | Q4 2021 |  |  | TBD | 1030671311 | [11 empty] | TRUE | TRUE | 275 | 2020-06-18 | 2020-06-18 | 2020 | 2020 | 2020 |  |  | 44412 | 2021-06-08 | Addendum
276 |  | Marshall Ripley | Rick Duperre | 2019-11-25 | [31 empty] | 1 - MOSH |  | 635D1 |  |  | WITHDRAWN | WITHDRAWN |  | Nate Niles | REVISION ENERGY INC | REVISION ENERGY INC | 10 Wentworth Dr Gorham | 2000038393 | 30011965628 | Solar | [7 empty] | 10 Wentworth Dr |  |  | Gorham |  | MOSHERS | 635D1 |  |  | 86-Withdrawn-86d | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2019-12-04 | 2019-12-11 |  |  |  |  | 1900-01-12 | [57 empty] | Pending | [69 empty] | 2020-01-28 | [37 empty] | TRUE | TRUE | 276 | 0 | 0 | 1900 | #VALUE! | #VALUE!
277 |  | Lanie Patterson | Brent Brooks | 2019-11-26 | [31 empty] | 3 - SOCH |  | 244D2 | 141 |  | WITHDRAWN | WITHDRAWN |  | David Kane | LongRoad Development Company LLC | LONGROAD DEVELOPMENT COMPANY LLC | Horseback Rd / Rte 3 China | 2000118100 | 30011899959 | Solar | [10 empty] | China |  | SOUTH CHINA | 244D2 |  |  | 9310-L0480-1150-0010-ED00028 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2019-12-05 | 2019-12-12 |  |  |  |  | 1900-01-12 | [57 empty] | Pending | [69 empty] | 2020-07-29 | [37 empty] | TRUE | TRUE | 277 | 0 | 0 | 1900 | #VALUE! | #VALUE!
278 |  | Eben Snow | Brent Brooks | 2019-11-26 | [31 empty] | 10 - HORD |  | 420D7 | 143 |  | WITHDRAWN | WITHDRAWN |  | David Kane | LongRoad Development Company LLC | LONGROAD DEVELOPMENT COMPANY LLC | 241 Peacock Hill Rd New Gloucester | 2000118100 | 30011899942 | Solar | [7 empty] | 190 Peacock Hill Rd |  |  | New Gloucester |  | HOTEL ROAD | 420D7 |  |  | 86-Withdrawn-86d | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2019-12-05 | 2019-12-12 |  |  |  |  | 1900-01-12 | [57 empty] | Pending | [69 empty] | 2020-01-12 | [37 empty] | TRUE | TRUE | 278 | 0 | 0 | 1900 | #VALUE! | #VALUE!
279 |  | Lanie Patterson | Brent Brooks | 2019-11-26 | [31 empty] | 5 - UNIT |  | 860D2 | 205 |  | WITHDRAWN | WITHDRAWN |  | David Kane | LongRoad Development Company LLC | LONGROAD DEVELOPMENT COMPANY LLC | Berry/Mussey Rd Union | 2000118100 | 30011899983 | Solar | [5 empty] | 44.5869 | -69.3052 |  |  |  | Unity |  | UNITY | 860D2 |  |  | FLOC-MISSING-01142021 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2019-12-05 | 2019-12-12 |  |  |  |  | 1900-01-12 | [57 empty] | Pending | [69 empty] | 2021-06-29 | [37 empty] | TRUE | TRUE | 279 | 0 | 0 | 1900 | #VALUE! | #VALUE!
280 |  | Lanie Patterson | Brent Brooks | 2019-11-26 | [31 empty] | 6 - UNIT |  | 860D1 | 279 |  | WITHDRAWN | WITHDRAWN |  | David Kane | LongRoad Development Company LLC | LONGROAD DEVELOPMENT COMPANY LLC | 450 Main St Unity | 2000118100 | 30011962054 | Solar | [10 empty] | Unity |  | UNITY | 860D1 |  |  | 86-Withdrawn-86d | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2019-12-05 | 2019-12-12 |  |  |  |  | 1900-01-12 | [57 empty] | Pending | [69 empty] | 2020-01-12 | [37 empty] | TRUE | TRUE | 280 | 0 | 0 | 1900 | #VALUE! | #VALUE!
281 |  | Lanie Patterson | Brent Brooks | 2019-11-26 |  | L2_Bump |  |  |  |  | 2023-03-27 | wthdw | [22 empty] | 270 | 2 - VASS |  | 861D9 | 270 | Yes | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2021-12-17 | Liam McCormack | Summit Ridge Energy | WINSLOW PV LLC | 355 Cushman Rd Winslow | 2000298959 | 30014725482 | Solar | 4125 | 4.125 | 7000 |  |  | 44.5078 | -69.6313 | Cushman Road |  |  | Winslow | 84 | VASSALBORO | 861D9 | 861T1 | 12.47 | FLOC-MISSING-01142021 | Non-FERC | COST SHARE | COST SHARE($250,000) | 122769 | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-12-05 | 2019-12-05 | 2019-12-12 | 2019-12-05 | 2019-12-10 | 2020-05-01 |  | 2020-05-15 |  | 2020-05-01 | 2020-05-01 | 2020-05-15 |  |  | 2020-05-15 | 2020-09-15 |  | CS | 2020-05-20 | RS | 2020-09-15 |  |  |  |  | CS |  |  | 2020-05-20 | 2020-09-15 |  | 2022-08-01 |  | 2023-08-04 | [6 empty] | 2020-05-22 |  |  | 2022-08-09 | 2022-11-11 | [8 empty] | 2022-11-14 |  |  |  |  | 2020-06-04 | 2020-09-24 |  | 2022-08-10 | 2022-11-15 | 2023-08-04 |  | Pending |  |  |  |  | 2020-08-07 | 2020-11-06 |  | 2021-05-20 | Addendum |  |  | 2020-08-07 | 2020-11-10 |  | 2022-09-12 | 2022-12-22 | 2023-09-19 |  |  |  | 2020-08-07 | 2020-11-10 |  |  | 2022-12-22 | 2023-09-19 | [12 empty] | 2020-08-10 | [7 empty] | 2020-11-17 | 2020-11-17 |  |  |  |  | 2021-06-07 |  | 2020-12-08 |  | 2020-12-08 | 2022-09-13 | 2022-06-13 | 2022-09-15 | [5 empty] | 650655 |  | 555913 | 2022-12-22 |  | 2021-06-16 | 2021-06-16 |  | 2022-06-21 | 2022-09-16 | 2022-09-19 | 2023-11-14 | 2023-11-14 | [17 empty] | 10300827672 | [11 empty] | TRUE | TRUE | 281 | 2021-06-16 | 2021-06-16 | 2021 | 2021 | 2021 | 44354 |  |  | 2021-05-20 | Addendum
282 |  | Govinda Neupane |  | 2019-11-26 | [31 empty] | 2 - ATHN |  | 827D2 | 207 |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2020-10-05 | Chad Allen | LongRoad Development Company LLC | Maine DG Solar Harmony | 26 Route 150 Harmony | 2000149310 | 30012297377 | Solar | 4910 | 4.91 | 4695 |  |  | 44.9322 | -69.5429 | 26 Route 150 |  |  | Harmony | 16 | ATHENS | 827D2 | 827T1 |  | FLOC-MISSING-01142021 | Non-FERC | COST SHARE | COST SHARE ( $305,000) | 123608 | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-12-05 | 2019-12-05 | 2019-12-12 | 2019-12-05 | 2019-12-10 | 2020-04-29 |  | 2020-05-13 |  | 2020-04-29 | 2020-04-29 | 2020-05-13 |  |  | 2020-05-04 | 2020-05-06 |  | CS | 2020-05-04 | RS | 2020-05-06 |  |  |  |  | CS |  |  | 2020-05-04 | 2020-05-06 | [10 empty] | 2020-05-15 | [17 empty] | 2020-05-15 | [6 empty] | Pending |  |  |  |  | 2020-07-21 |  |  | 2021-06-10 | Addendum |  |  | 2020-07-15 | [8 empty] | 2020-07-20 | [17 empty] | 2020-07-21 | [13 empty] | 2021-06-14 |  | 2020-08-07 |  | 2020-08-14 | [8 empty] | 1500884 |  |  |  |  | 2020-04-17: 2020-09-04; 2020-04-17: 2020-09-04; 2021-07-07: 2021-06-15; 2021-07-07: 2021-06-15 | [15 empty] | 10300709042 | 10300797583 | [10 empty] | TRUE | TRUE | 282 | 2020-09-04 | 2020-09-04 | 2020 | 2020 | 2020 | 44361 |  |  | 2021-06-10 | Addendum
283 |  | Eben Snow | Brent Brooks | 2019-11-26 | [31 empty] | 2 - DENM |  | 413D2 | 237 |  | WITHDRAWN | WITHDRAWN |  | David Kane | LongRoad Development Company LLC | LONGROAD DEVELOPMENT COMPANY LLC | 739 Route 117 Denmark | 2000118100 | 30011962021 | Solar | [10 empty] | Denmark |  | DENMARK | 413D2 |  |  | 86-Withdrawn-86d | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2019-12-05 | 2019-12-12 |  |  |  |  | 1900-01-12 | [57 empty] | Pending | [69 empty] | 2020-08-24 | [37 empty] | TRUE | TRUE | 283 | 0 | 0 | 1900 | #VALUE! | #VALUE!
284 |  | Eben Snow | Brent Brooks | 2019-11-26 | 2022-06-02 | L2_Bump | [29 empty] | 11 - HORD |  | 420D4 | 278 |  | WITHDRAWN | WITHDRAWN |  | Mark Chrisos | Con Edison Clean Energy | CONSOLIDATED EDISON SOLUTIONS | Lewis Junction Rd Auburn | 2800000074 | 30011964928 | Solar/Battery | [5 empty] | 44.4769 | -70.3007 | Lewiston Junction Rd |  |  | Auburn |  | HOTEL ROAD | 420D4 | 420T1 |  | FLOC-MISSING-01142021 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2019-12-05 | 2019-12-05 | 2019-12-12 | 2019-12-05 | 2019-12-10 |  |  | 1900-01-12 | [57 empty] | Pending | [69 empty] | 2022-06-06 | [37 empty] | TRUE | TRUE | 284 | 0 | 0 | 1900 | #VALUE! | #VALUE!
285 |  | Rigel Paradise | Rick Duperre | 2019-11-26 | [31 empty] | 2 - SOSA |  | 667D2 | 18 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Jeffrey Lord | Con Edison Clean Energy | Sanford A, LLC | State Rd 4 Sanford | 2800000074 | 30011964944 | Solar/Battery | [5 empty] | 43.3783 | -70.7338 | State Rd 4 |  |  | Sanford |  | SOUTH SANFORD | 667D2 | 667T2 |  | 9310-L0334-5170-0070-ED00060 | Non-FERC | WITHDRAWN | WITHDRAWN | 250000 | Yes |  |  | K&L Engineering |  |  |  | 2019-12-05 | 2019-12-12 | 2019-12-05 | 2019-12-10 | 2020-02-19 | 2025-02-19 | 2020-03-27 |  | 2020-03-13 | 2020-03-13 | 2020-03-27 |  |  | 2020-03-17 | 2020-06-05 |  | CS | 2020-03-17 | RS | 2020-06-05 |  |  |  |  | CS |  |  | 2020-03-17 | 2020-06-05 | [10 empty] | 2020-03-19 | [17 empty] | 2020-03-25 | 2020-06-09 | [5 empty] | Pending |  |  |  |  | 2020-05-29 | 2020-07-22 |  | 2021-05-19 | Addendum |  |  | 2020-05-29 | 2020-07-22 | [7 empty] | 2020-05-27 | 2020-07-23 | [16 empty] | 2020-06-01 | 2020-07-28 | [6 empty] | 2021-06-17 | [5 empty] | 2021-06-01 |  | 2020-07-28 |  | 2020-07-28 | 2023-02-10 | [7 empty] | 723490 |  |  |  | 2023-03-09 | 2020-04-17: 2020-08-04; 2020-04-17: 2020-08-04; 2021-07-07: 2021-06-30; 2021-07-07: 2021-06-30 | [12 empty] | 2021-07-19 |  |  | 10300698914 | [11 empty] | TRUE | TRUE | 285 | 2020-08-04 | 2020-08-04 | 2020 | 2020 | 2020 | 44348
286 |  | Lanie Patterson | Brent Brooks | 2019-12-02 | [31 empty] | 8 - WINS |  | 870D1 | 243 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Santiago Quijano | Bluewave MA, LLC | BWC PATTEE POND LLC | 239 Eames Rd Winslow | 2000130166 | 30011881304 | Solar/Battery | [5 empty] | 44.5669 | -69.5483 | 239 Eames Rd |  |  | Winslow | 17 | WINSLOW | 870D1 | 870T4 |  | FLOC-MISSING-01142021 | FERC | WITHDRAWN | WITHDRAWN |  | Yes | Yes |  | K&L Engineering | Meg Sullivan |  | 2019-12-05 | 2019-12-09 | 2019-12-16 | 2019-12-05 | 2019-12-10 | 2021-12-08 | 2021-12-17 | 2021-12-22 | 2021-12-17 | 2021-12-20 | 2021-12-20 | 2021-01-05 |  |  | 2021-12-27 |  |  | CS | 2021-12-28 | [6 empty] | CS |  |  | 2021-12-28 | [19 empty] | 2022-01-06 | 2022-01-06 | [8 empty] | 2022-01-07 | [6 empty] | Pending |  |  |  |  | 2022-03-15 | [6 empty] | 2022-03-18 | [8 empty] | 2022-03-18 | [8 empty] | 2022-03-03 | [8 empty] | 2022-03-23 | [7 empty] | 2022-03-23 | [7 empty] | 2022-03-24 |  | 2022-03-25 |  | 2022-03-25 | [10 empty] | 2023-12-04 | 2020-04-17: 2022-03-25; 2020-04-17: 2022-03-25 | [15 empty] | Requested | [11 empty] | TRUE | TRUE | 286 | 2022-03-25 | 2022-03-25 | 2022 | 2022 | 2022
287 |  | Eben Snow | Brent Brooks | 2019-12-02 | 2022-07-21 | L2_Bump | [27 empty] | 2 - NORW |  | 4 - NORW |  | 435D1 | 269 | Yes | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED |  | Abby Broedlin | Nautilus Solar Energy, LLC | Sturgeon Ryan Ranch Solar LLC | 0 Fore St., Paris | 2000170134 | 30012490329 | Solar | 3000 | 3 | 4494.285 |  |  | 44.181 | -70.514 | Fore St at Knightly Rd |  |  | Oxford | 2H | NORWAY | 435D1 | 435T2 |  | 9310-L0168-4420-0098-ED00035 | FERC | COST SHARING | COST SHARING (250,000) | 838808.25 | Under Review 1/31/2020 | Yes |  | K&L Engineering | Meg Sullivan |  | 2019-12-05 | 2019-12-09 | 2019-12-16 | 2019-12-05 | 2019-12-12 | 2020-09-30 |  | 2020-10-15 |  | 2020-09-30 | 2020-09-30 | 2020-10-15 |  |  | 2020-09-30 |  |  | CS | 2020-09-30 | [6 empty] | CS |  |  | 2020-09-30 |  |  | 2022-12-28 | [8 empty] | 2020-09-30 |  |  | 2022-12-30 | [14 empty] | 2020-10-05 |  |  | 2023-01-10 |  |  |  | Pending |  |  |  |  | 2020-12-10 |  |  | 2021-06-03 | Addendum |  |  | 2020-12-10 |  |  | 2023-02-20 | [5 empty] | 2020-12-15 |  |  | 2023-02-24 | [14 empty] | 2020-12-16 | [7 empty] | 2020-12-16 | [7 empty] | 2020-12-22 |  | 2020-12-22 | 2023-02-28 |  | 2023-02-28 | 2023-03-29 |  |  |  |  | 459748 |  | 387988 | 2023-02-20 |  | 2020-04-17: 2021-06-17; 2020-04-17: 2021-06-17; 2021-07-07: 2023-03-01; 2021-07-07: 2023-03-02 | 2023-03-31 | 2023-03-31 | [9 empty] | Q4 2021 |  |  |  | 10300803164 | [11 empty] | FALSE | TRUE | 287 | 2021-06-17 | 2021-06-17 | 2021 | 2021 | 2021 |  |  |  | 2021-06-03 | Addendum
288 |  | Govinda Neupane |  | 2019-12-03 | [31 empty] | 5 - SKNS |  | 853D1 | 249 |  | WITHDRAWN | WITHDRAWN |  | Peter Bay | EDF Renewables | EDF RENEWABLES | Russell Rd Skowhegan | 2000134214 | 30011945059 | Solar | [5 empty] | 44.7856 | -69.7312 | Russel Rd |  |  | Skowhegan |  | SKOWHEGAN NORTH SIDE | 853D1 |  |  | FLOC-MISSING-01142021 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2019-12-10 | 2019-12-17 |  |  |  |  | 1900-01-12 | [57 empty] | NO STUDY | [69 empty] | 2021-11-10 | [37 empty] | TRUE | TRUE | 288 | 0 | 0 | 1900 | #VALUE! | #VALUE!
289 |  | Govinda Neupane |  | 2019-12-03 | [31 empty] | 6 - SKNS |  | 853D1 | 288 |  | WITHDRAWN | WITHDRAWN |  | Peter Bay | EDF Renewables | EDF RENEWABLES | 17 E Madison Rd Skowhegan | 2000134214 | 30011945067 | Solar | [5 empty] | 44.7839 | -69.728 | 17 East Madison Rd |  |  | Skowhegan |  | SKOWHEGAN NORTH SIDE | 853D1 |  |  | FLOC-MISSING-01142021 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2019-12-10 | 2019-12-17 | 2019-12-10 | 2019-12-11 |  | 2021-11-15 |  | 2021-12-01 | 2021-12-01 | 2021-12-01 |  |  |  | 2022-02-09 |  |  | CS | 2022-02-09 | [6 empty] | CS |  |  | 2022-02-09 | [11 empty] | 2022-02-24 | [24 empty] | Pending | [60 empty] | 2022-02-07 | 2022-02-14 | [7 empty] | 2022-03-07 | [37 empty] | TRUE | TRUE | 289 | 0 | 0 | 1900 | 1900 | 1900
290 |  |  | KRISTOFER COLEMAN | 2019-12-03 | [31 empty] | 1 - WOOL |  | 258D1 |  |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2020-07-14 | Jonovan (Jonny) Lizama | Luminace | Green Mile Solar, LLC | Nequasset Rd Woolwich | 2000347346 | 30014873829 | Solar | 4999 | 4.999 | 7311 |  |  | 43.9387 | -69.7809 | 84 Nequasset Rd |  |  | Woolwich | 3 | WOOLWICH | 258D1 | 258T1 |  | 9310-L0098-6490-0053-ED00044 | Non-FERC | TRIGGERING | TRIGGERING | 325000 | Yes |  |  | K&L Engineering | Meg Sullivan |  | 2019-12-10 | 2019-12-10 | 2019-12-17 | 2019-12-10 | 2019-12-17 | 2019-12-17 |  | 2020-01-02 |  | 2019-12-17 | 2019-12-17 | 2019-12-31 |  |  | 2019-12-23 |  |  | CS | 2019-12-23 | [6 empty] | CS |  |  | 2019-12-23 | [11 empty] | 2020-01-13 | [17 empty] | 2020-01-13 | [6 empty] | Yes |  |  |  |  | 2020-03-18 |  |  | 2021-05-19 | Addendum |  |  | 2020-03-16 | [8 empty] | 2020-03-16 | [17 empty] | 2020-03-19 | [13 empty] | 2021-05-27 |  | 2020-04-07 |  | 2020-04-07 | [8 empty] | 578620 |  |  |  |  | 2020-04-17: 2020-05-27; 2020-04-17: 2020-05-27; 2021-07-07: 2021-06-24; 2021-07-07: 2021-06-24 | [11 empty] | Q4 2020 |  |  | 43942 | 10300661355 | [11 empty] | TRUE | TRUE | 290 | 2020-05-27 | 2020-05-27 | 2020 | 2020 | 2020 | 44343 |  |  | 2021-05-19 | Addendum
291 |  | Eben Snow | Brent Brooks | 2019-12-04 | [31 empty] | 4 - BR34 |  | 406D4 | 188 |  | WITHDRAWN | WITHDRAWN |  | David Kane | LongRoad Development Company LLC | LONGROAD DEVELOPMENT COMPANY LLC | 630 Kansas Rd Bridgton | 2000118100 | 30011962062 | Solar | [10 empty] | Bridgton |  | BRIDGTON 34 KV | 406D4 |  |  | 9310-L0119-0690-0070-ED00171 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2019-12-11 | 2019-12-18 |  |  |  |  | 1900-01-12 | [57 empty] | NO STUDY | [69 empty] | 2022-06-01 | [37 empty] | TRUE | TRUE | 291 | 0 | 0 | 1900 | 1900 | 1900
292 |  | Rigel Paradise | Rick Duperre | 2019-12-04 | [31 empty] | 6 - PRAT |  | 661D2 | 231 |  | WITHDRAWN | WITHDRAWN |  | David Kane | LongRoad Development Company LLC | LONGROAD DEVELOPMENT COMPANY LLC | 247 Perry Oliver Rd Wells | 2000118100 | 30011962047 | Solar | [10 empty] | Wells |  | PRATT & WHITNEY | 661D2 |  |  | 9310-L0330-6273-0165-ED00003 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2019-12-11 | 2019-12-18 |  |  |  |  | 1900-01-12 | [127 empty] | 2020-10-27 | [37 empty] | TRUE | TRUE | 292 | 0 | 0 | 1900 | #VALUE! | #VALUE!
293 |  | Rigel Paradise | Rick Duperre | 2019-12-12 | [31 empty] | 3 - BASS |  | 602D2 | 232 |  | WITHDRAWN | WITHDRAWN |  | Peter Bay | EDF Renewables | EDF RENEWABLES | 488 School St Berwick | 2000134214 | 30011961163 | Solar | [7 empty] | 488 School Street |  |  | Berwick |  | BASSETT | 602D2 |  |  | 9310-L0211-0470-0008-ED00068 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2019-12-19 | 2019-12-27 |  |  |  |  | 1900-01-12 | [57 empty] | Pending | [69 empty] | 2020-04-27 | [37 empty] | TRUE | TRUE | 293 | 0 | 0 | 1900 | #VALUE! | #VALUE!
294 |  | Eben Snow | Brent Brooks | 2019-12-12 | [31 empty] | 6 - LEED |  | 471D2 | 200 |  | WITHDRAWN | WITHDRAWN |  | Santiago Quijano | Bluewave MA, LLC | BWC ALLEN STREAM LLC | 1053 Ne 106 Leeds | 2000137469 | 30011994990 | Solar/Battery | [7 empty] | ME-106 |  |  | Leeds |  | LEEDS | 471D2 |  |  | 86-Withdrawn-86d | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2019-12-19 | 2019-12-27 |  |  |  |  | 1900-01-12 | [127 empty] | 2020-02-03 | [37 empty] | TRUE | TRUE | 294 | 0 | 0 | 1900 | #VALUE! | #VALUE!
295 |  | Eben Snow | Brent Brooks | 2019-12-20 | [31 empty] | 1 - PAPO |  | 438D1 |  |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Matthew Doubleday | SunRaise Investments LLC | BISBEE TOWN ROAD WATERFORD SOLAR LLC | 90 Bisbee Town Rd Waterford | 2000155360 | 30012266992 | Solar/Battery | [5 empty] | 44.2329 | -70.7639 | 90 Bisbee Town Rd |  |  | Waterford | 2 | PAPOOSE POND | 438D1 | Tap off of Transmission Line |  | 9310-L0180-6205-0063-ED00004 | Non-FERC | WITHDRAWN | WITHDRAWN | NONE | Yes |  |  | K&A Engineering | Meg Sullivan |  | 2019-12-31 | 2019-12-30 | 2020-01-07 | 2019-12-31 | 2020-01-07 | 2019-01-08 |  | 2019-01-23 |  | 2019-01-08 | 2019-01-08 | 2019-01-22 |  |  | 2019-01-22 | 2020-04-09 |  | CS | 2020-04-06 | RS | 2020-04-09 |  |  |  |  | CS |  |  | 2020-01-06 | 2020-04-09 |  | 2023-01-09 | [8 empty] | 2020-01-14 | [17 empty] | 2020-04-10 | 2020-04-10 | [5 empty] | Yes |  |  |  |  | 2020-06-16 | 2020-05-26 |  | 2021-05-20 | Addendum |  |  | 2020-03-20 | 2020-05-07 | [7 empty] | 2020-03-12 | 2020-05-07 | [16 empty] | 2020-03-16 | 2020-05-13 | [13 empty] | 2021-05-21 | 2021-05-21 | [10 empty] | 81749 |  |  |  | 2023-02-02 | 2020-04-17: 2020-05-14; 2020-04-17: 2020-05-14 | [14 empty] | TBD | 10300671287 | [11 empty] | TRUE | TRUE | 295 | 2020-05-14 | 2020-05-14 | 2020 | 2020 | 2020 |  | 44337 |  | 2021-05-20 | Addendum
296 |  | Eben Snow | Brent Brooks | 2019-12-20 | [31 empty] | 3 - MEFA |  | 431D2 | 226 |  | WITHDRAWN | WITHDRAWN |  | Hillel Halberstam | Synergen Solar | SYNERGEN SOLAR LLC | 30-32 Lewiston St Mechanic Falls | 2000139723 | 30012029622 | Solar | [7 empty] | 30 Lewiston St |  |  | Mechanic Falls |  | MECHANIC FALLS | 431D2 | 431T1 |  | 86-Withdrawn-86d | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2019-12-30 | 2020-01-07 |  |  |  |  | 1900-01-12 | [57 empty] | Pending | [69 empty] | 2020-09-04 | [37 empty] | TRUE | TRUE | 296 | 0 | 0 | 1900 | #VALUE! | #VALUE!
297 |  | Rigel Paradise | Rick Duperre | 2019-12-20 | [31 empty] | 1 - WATE |  | 671D1 |  |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2020-06-25 | Paige Kutschbach | Madison Energy Holdings | HEP WATERBORO SPV LLC | 89 Mclucas Ln | 2000180645 | 30012637663 | Solar | 4875 | 4.875 | 3912 |  |  | 43.5943 | -70.7236 | 89 McLucas Rd |  |  | Waterboro | 12 | WATERBORO | 671D1 | 671T1 |  | 9310-L0341-6190-0056-ED00006 | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Yes |  |  | K&A Engineering | Meg Sullivan |  | 2019-12-30 | 2019-12-30 | 2020-01-07 | 2019-12-30 | 2020-01-07 | 2019-01-08 |  | 2019-01-23 |  | 2019-01-08 | 2020-01-08 | 2020-01-23 |  |  | 2020-01-09 |  |  | CS | 2020-01-09 | [6 empty] | CS |  |  | 2020-01-09 | [11 empty] | 2020-01-10 | [17 empty] | 2020-01-10 | [6 empty] | Yes |  |  |  |  | 2020-03-17 |  |  | 2021-06-21 | Addendum |  |  | 2020-03-17 | [8 empty] | 2020-03-17 | [17 empty] | 2020-03-24 | [15 empty] | 2020-03-31 |  | 2020-04-01 | [13 empty] | 2020-04-17: 2020-04-22; 2020-04-17: 2020-04-22 | [11 empty] | Q4 2021 |  |  | TBD | 10300678650 | [11 empty] | TRUE | TRUE | 297 | 2020-04-22 | 2020-04-22 | 2020 | 2020 | 2020 |  |  |  | 2021-06-21 14:33 | Addendum
298 |  | Govinda Neupane |  | 2019-12-20 | [31 empty] | 2 - SKSS |  | 854D1 | 154 |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2021-12-17 | Greg Boyer | Dynamic Energy | NORRIDGEWOCK MARTIN STREAM SOLAR LLC | Martin Stream Rd Norridgewock | 2000165630 | 30012426539 | Solar | 4999 | 4.999 | 7001 |  |  | 44.6958 | -69.7976 | 205 Smithfield Rd |  |  | Norridgewock | 64 | SKOWHEGAN SOUTH SIDE | 854D1 | 854T1 |  | FLOC-MISSING-01142021 | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Yes |  |  | K&A Engineering | Meg Sullivan |  | 2019-12-31 | 2019-12-30 | 2020-01-07 | 2019-12-31 | 2020-01-07 | 2020-02-28 |  | 2020-03-13 |  | 2020-02-28 | 2020-02-28 | [6 empty] | CS | 2020-02-28 | [6 empty] | CS |  |  | 2020-02-28 | [29 empty] | 2020-03-02 | [6 empty] | Yes |  |  |  |  | 2020-04-13 |  |  | 2021-05-19 | Addendum |  |  | 2020-04-02 | [8 empty] | 2020-04-02 | [17 empty] | 2020-04-07 | [7 empty] | 2020-04-07 | [7 empty] | 2020-04-23 |  | 2020-04-23 | [8 empty] | 415370 |  |  |  |  | 2020-04-17: 2020-05-14; 2020-04-17: 2020-05-14; 2021-07-07: 2021-07-12; 2021-07-07: 2021-07-12 | [11 empty] | Q4 2021 |  |  | TBD | 10300678769 | [11 empty] | TRUE | TRUE | 298 | 2020-05-14 | 2020-05-14 | 2020 | 2020 | 2020 |  |  |  | 2021-05-19 | Addendum
299 |  | Eben Snow | Brent Brooks | 2020-01-07 | 2022-06-02 | L2_Bump |  | 2022-12-15 | L2_Bump |  | 2023-02-03 | L2_Bump |  | 2023-03-20 | L2_Bump |  | 2023-11-29 | wthdw |  |  |  |  | 2023-01-09 | wthdw | [11 empty] | 12 - HORD |  | 420D4 | 284 |  | WITHDRAWN | WITHDRAWN |  | Jay Smith | Standard Solar | NORTHERN LIGHTS SOLAR LLC | 586 Lewiston Junction Rd Auburn | 2000139226 | 30012029143 | Solar | [5 empty] | 44.4378 | -70.3043 | 586 Lewiston Junction RD |  |  | Auburn |  | HOTEL ROAD | 420D4 | 420T1 | 34.5 | 9310-L0140-0230-0530-ED00003 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&A Engineering | Meg Sullivan |  | 2020-01-14 | 2020-01-14 | 2020-01-22 | 2020-01-14 | 2020-01-21 | 2024-01-09 | 2024-01-15 | 2024-01-24 | 2024-01-16 | 2024-01-22 | 2024-01-22 | 2024-02-05 |  |  | 2024-02-05 |  |  | CS | [7 empty] | CS |  |  | 2023-02-07 | [106 empty] | 2024-02-28 | [37 empty] | TRUE | TRUE | 299 | 0 | 0 | 1900 | #VALUE! | #VALUE!
300 |  | Lanie Patterson | Brent Brooks | 2020-01-07 | [31 empty] | 4 - DETR |  | 812D1 | 210 |  | WITHDRAWN | WITHDRAWN |  | Jay Smith | Standard Solar | NORTHERN LIGHTS SOLAR LLC | 323 Ill Hill Rd Palmyra | 2000139226 |  | Solar | [7 empty] | 323 Ell Hill Rd |  |  | Palmyra |  | DETROIT | 812D1 |  |  | 86-Withdrawn-86d | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2020-01-14 | 2020-01-22 |  |  |  |  | 1900-01-12 | [57 empty] | Pending | [69 empty] | 2020-06-11 | [37 empty] | TRUE | TRUE | 300 | 0 | 0 | 1900 | #VALUE! | #VALUE!
301 |  | Lanie Patterson | Brent Brooks | 2020-01-07 | [31 empty] | 2 - CONY |  | 216D2 | 208 |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2021-01-04 | Abby Broedlin | Nautilus Solar Energy | STURGEON TOWN HOUSE SOLAR LLC | 351 Hallowell Rd, Chelsea | 2000119678 | 30014758095 | Solar | 4999 | 4.999 | 5529.6 |  |  | 44.2782 | -69.7542 | 351 Hallowell Road |  |  | Chelsea | 4 | CONY ROAD | 216D2 | 216T1 |  | 9310-L0044-1110-0057-ED00011 | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Under Review 1/31/2020 |  |  | K&A Engineering | Meg Sullivan |  | 2020-01-14 | 2020-01-14 | 2020-01-22 | 2020-01-14 | 2020-01-21 | 2020-01-31 |  | 2020-02-14 |  | 2020-01-31 | 2020-01-31 | 2020-02-14 |  |  | 2020-01-31 |  |  | CS | 2020-01-31 | [6 empty] | CS |  |  | 2020-01-31 | [11 empty] | 2020-01-31 | [17 empty] | 2020-03-02 | [6 empty] | Yes |  |  |  |  | 2020-05-05 |  |  | 2021-06-08 | Addendum |  |  | 2020-05-05 | [8 empty] | 2020-05-05 | [17 empty] | 2020-05-07 | [15 empty] | 2020-05-07 |  | 2020-05-11 | [8 empty] | 180094 |  |  |  |  | 2020-04-17: 2020-05-12; 2020-04-17: 2020-05-12; 2021-07-07: 2021-05-17; 2021-07-07: 2021-05-17 | [11 empty] | Q3 2021 |  |  | TBD | 10300676409 | [11 empty] | TRUE | TRUE | 301 | 2020-05-12 | 2020-05-12 | 2020 | 2020 | 2020 |  |  |  | 2021-06-08 | Addendum
302 |  | Eben Snow | Brent Brooks | 2020-01-07 | [31 empty] | 4 - MEFA |  | 431D3 | 296 |  | WITHDRAWN | WITHDRAWN |  | Mike Lucini | ISM Solar Development LLC | ISM SOLAR DEVELOPMENT LLC | 324 Bakerstown Rd Poland | 2000119678 | 30012037336 | Solar | [7 empty] | 324 Bakerstown Road |  |  | Poland |  | MECHANIC FALLS | 431D3 | 431T2 |  | 86-Withdrawn-86d | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2020-01-14 | 2020-01-22 |  |  |  |  | 1900-01-12 | [57 empty] | Pending | [69 empty] | 2020-05-27 | [37 empty] | TRUE | TRUE | 302 | 0 | 0 | 1900 | #VALUE! | #VALUE!
303 |  | Govinda Neupane |  | 2020-01-09 | 2022-11-08 | L2_bump |  | 2023-01-09 | L2_bump |  | 2023-05-08 | L2_Bump |  | 2023-07-18 | L2_Bump | [20 empty] | 6 - STUR |  | 858D2 | 204 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Xander Neve | Syncarpha Solar LLC | KINGFIELD SOLAR ONE LLC | Tufts Pond Rd, Kingfield | 2000137833 | 30012000334 | Solar | [5 empty] | 44.5813 | -70.0956 | Tufts Pond RD |  |  | Kingfield | 109 | STURTEVANT | 858D2 | 858T1 | 34.5 | 9310-L0439-3070-0042-ED00055 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&A Engineering | Meg Sullivan |  | 2020-01-16 | 2020-01-16 | 2020-01-24 | 2020-01-16 | 2020-01-23 | 2021-07-08 | 2021-07-26 | 2021-07-22 | 2021-07-26 | 2021-07-27 | 2021-07-29 | 2021-08-11 |  |  | 2021-08-10 |  |  | CS | 2021-08-10 | [6 empty] | CS |  |  | 2021-08-10 |  |  | 2023-03-15 | 2023-05-09 | 2023-07-21 | [9 empty] | 2023-04-03 |  |  |  |  | 2021-08-25 | 2021-08-25 |  |  | 2023-04-13 | [5 empty] | 2021-08-31 |  |  | 2023-04-13 | [8 empty] | 2021-11-04 | [6 empty] | 2021-11-18 |  |  | 2023-05-30 | [5 empty] | 2021-11-19 |  |  | 2023-05-31 |  |  |  | 2021-11-19 |  | 2021-11-19 |  |  | 2023-06-08 | [5 empty] | 2021-11-23 |  |  | 2023-06-12 |  |  |  |  | 2021-11-23 | [7 empty] | 2021-12-14 |  | 2021-12-16 |  | 2021-12-28 | [6 empty] | 488068 |  |  |  | 2023-08-14 | 2020-04-17: 2021-12-23; 2020-04-17: 2022-01-11 | [15 empty] | Requested | [11 empty] | TRUE | TRUE | 303 | 2021-12-23 | 2021-12-23 | 2021 | 2022 | 2022
304 |  | Govinda Neupane |  | 2020-01-09 | 2022-11-08 | L2_bump |  | 2023-01-09 | L2_bump |  | 2023-05-08 | L2_Bump |  | 2023-07-18 | L2_Bump |  | 2023-10-05 | L2_Bump | [17 empty] | 7 - STUR |  | 858D2 | 303 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Xander Neve | Syncarpha Solar LLC | New Portland Solar I LLC | 972 Carrabassett Rd, New Portland | 2000137818 | 30013963597 | Solar | [5 empty] | 44.9429 | -70.1462 | 972 Carrabassett Road |  |  | New Portland | 326 | STURTEVANT | 858D2 | 858T1 | 34.5 | 9310-L0439-3070-0045-ED00046 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&A Engineering | Meg Sullivan |  | 2020-01-16 | 2020-01-16 | 2020-01-24 | 2020-01-16 | 2020-01-23 |  | 2022-01-20 | 1900-01-12 | 2022-01-27 | 2022-01-28 | 2022-01-28 | 2022-02-11 |  |  | 2022-01-31 |  |  | CS | 2022-02-11 | [6 empty] | CS |  |  | 2022-02-11 |  |  | 2023-08-16 | 2023-10-24 | [11 empty] | 2024-11-17 |  |  |  | 2022-02-28 | 2022-02-28 |  |  |  | 2023-11-22 |  |  |  |  | 2022-03-07 |  |  |  | 2023-11-22 | [7 empty] | 2022-05-10 | [6 empty] | 2022-05-26 |  |  |  | 2024-01-09 |  |  |  |  | 2022-05-26 |  |  |  | 2024-01-09 |  |  |  |  | 2022-05-27 |  |  |  | 2024-01-18 |  |  |  |  | 2022-06-08 |  |  |  | 2024-01-22 |  |  |  | 2022-06-09 |  |  |  | 2024-01-22 |  |  |  | 2022-06-21 |  | 2022-06-22 | 2024-04-01 | 2022-06-24 | 2024-05-02 | 2022-02-07 | 2022-02-14 | [5 empty] | 595253 | 2024-01-04 | 2024-12-13 | 2020-04-17: 2022-06-28; 2020-04-17: 2022-06-28; 2021-07-07: 2024-05-16; 2021-07-07: 2024-05-20 | [15 empty] | Requested | [11 empty] | TRUE | TRUE | 304 | 2022-06-28 | 2022-06-28 | 2022 | 2022 | 2022
305 |  | Govinda Neupane |  | 2020-01-09 | [31 empty] | 1 - RANG |  | 875D2 |  |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2020-08-31 | Abby Broedlin | Nautilus US Power Holdco, LLC | BD SOLAR RANGELEY LLC | Pleasant St, Rangeley | 2000134638 | 30011951644 | Solar | 3000 | 3 | 5616 |  |  | 44.9809 | -70.6579 | Pleasant Street |  |  | Rangeley | 5 | RANGELEY | 875D2 | 875T1 |  | 9310-L0460-4880-0063-ED00031 | Non-FERC | TRIGGERING | TRIGGERING | 250000 | Yes |  |  | K&A Engineering | Meg Sullivan |  | 2020-01-17 | 2020-01-16 | 2020-01-24 | 2020-01-16 | 2020-01-23 | 2020-01-21 |  | 2020-02-04 |  | 2020-01-21 | 2020-01-21 | 2020-02-04 |  |  | 2020-01-23 | 2020-04-06 |  | CS | 2020-01-23 | RS | 2020-04-06 |  |  |  |  | CS |  |  | 2020-01-23 | 2020-04-06 | [10 empty] | 2020-01-30 | [17 empty] | 2020-04-09 | 2021-03-05 | [5 empty] | Yes |  |  |  |  | 2020-06-15 |  |  | 2021-06-08 | Addendum |  |  | 2020-06-10 | [8 empty] | 2020-06-08 | [17 empty] | 2020-06-11 | [15 empty] | 2020-07-20 |  | 2020-07-20 | [8 empty] | 615154 | 2020-05-30 | 615154 | 2021-06-07 |  | 2020-04-17: 2020-08-04; 2020-04-17: 2020-08-04; 2021-07-07: 2021-07-07; 2021-07-07: 2021-07-07 | [11 empty] | Q4 2021 |  | 2021-12-02 |  | 10300698865 | [11 empty] | TRUE | TRUE | 305 | 2020-08-04 | 2020-08-04 | 2020 | 2020 | 2020 |  |  |  | 2021-06-08 | Addendum
306 |  | Govinda Neupane |  | 2020-01-09 | 2022-08-29 | L2_Bump | [29 empty] | 2 - CORI |  | 811D1 | 268 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Nick Mazuroski | Dirigo/BNRG | BD SOLAR CORINNA LLC | Mill St Corinna | 2000138859 | 30012017007 | Solar | [5 empty] | 44.9158 | -69.2561 | 52 Mill Street |  |  | Corinna | 10.2 | CORINNA | 811D1 | 811T1 | 12.47 | 9310-SS0811 | Non-FERC | WITHDRAWN | WITHDRAWN | 325000 | Yes |  |  | K&A Engineering | Meg Sullivan |  | 2020-01-17 | 2020-01-16 | 2020-01-24 | 2020-01-17 | 2020-01-23 | 2020-07-31 |  | 2020-08-14 |  | 2020-07-31 | 2020-07-31 | 2020-08-14 |  |  | 2020-08-06 |  |  | CS | 2020-08-06 | RS | [5 empty] | CS |  |  | 2020-08-06 |  |  | 2023-10-17 | [8 empty] | 2020-08-13 |  |  | 2023-11-01 | [8 empty] | 2023-11-06 | [5 empty] | 2020-08-17 | 2020-12-08 |  | 2023-11-07 |  |  |  | Pending |  |  |  |  | 2020-10-21 | 2021-01-22 |  | 2021-06-22 | Addendum |  |  | 2020-10-21 | 2021-01-22 |  | 2023-12-29 | [5 empty] | 2020-10-26 | 2021-01-26 |  | 2023-01-02 | [8 empty] | 2024-01-19 | [5 empty] | 2020-10-29 | 2021-02-03 |  | 2024-01-22 |  |  |  |  | 2020-10-29 | 2021-02-03 |  | 2024-01-22 |  |  | 2021-06-23 |  | 2021-07-14 | 2021-07-14 | 2021-07-14 | 2022-07-19 | 2022-07-27 | [6 empty] | 402909 | 2020-10-17 | 691685 | 2023-12-28 | 2024-12-19 | 2020-04-17: 2021-07-14; 2020-04-17: 2021-08-12; 2021-07-07: 2022-07-28 | [15 empty] | Requested | [11 empty] | TRUE | TRUE | 306 | 2021-07-14 | 2021-07-14 | 2021 | 2021 | 2021 | 44370 |  | 44391 | 2021-06-22 | Addendum
307 |  | Govinda Neupane |  | 2020-01-10 | [31 empty] | 5 - LVFA |  | 428D2 | 262 |  | WITHDRAWN | WITHDRAWN |  | Glenn McKay | OYA Diamond | OYA SOLAR LP | 61 Diamond Rd / Livermore Falls | 2000136723 | 30011983357 | Solar | [5 empty] | 44.4404 | -70.162 | 61 Diamond Road |  |  | Livermore Falls |  | LIVERMORE FALLS | 428D2 |  |  | FLOC-MISSING-01142021 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2020-01-17 | 2020-01-27 |  |  |  |  | 1900-01-12 | [57 empty] | Pending | [69 empty] | 2021-07-30 | [37 empty] | TRUE | TRUE | 307 | 0 | 0 | 1900 | #VALUE! | #VALUE!
308 |  | Govinda Neupane |  | 2020-01-15 | 2022-12-13 | L2_Bump |  | 2023-07-18 | L2_Bump |  | 2024-01-04 | L2_bump |  | 2024-10-21 | L2 With |  | 2025-08-07 | wthdw | [17 empty] | 3 - DEXT | 1 - DEXT | 813D1 | 246 | Yes | EXECUTED | EXECUTED |  | Allen Tate | US Solar Development, LLC | USS BLAINE SOLAR LLC | 555 Garland Rd | 2000140882 | 30012047830 | Solar | 995 | 0.995 | 1390.35 |  |  | 45.0129 | -69.2718 | County Road 94 |  |  | Dexter | 4 | DEXTER | 813D1 | 813T1 | 12.47 | FLOC-MISSING-01142021 | Non-FERC | TRIGGERING | TRIGGERING | 255000 | Yes |  |  | K&A Engineering | Meg Sullivan |  | 2020-01-22 | 2020-01-23 | 2020-01-30 | 2020-01-22 | 2020-01-23 | 2020-08-25 |  | 2020-09-09 |  | 2020-08-25 | 2020-08-25 | 2020-09-09 | [5 empty] | FS | 2020-08-27 | IS | 2020-12-02 |  |  |  |  | Split | 2020-08-27 | 2020-12-02 |  |  |  | 2023-04-10 | 2024-11-07 | 2025-08-08 | [5 empty] | 2020-09-03 |  |  |  |  | 2024-11-22 | 2025-08-20 | [6 empty] | 2023-07-07 | 2024-11-22 | 2025-08-20 |  | 2020-09-09 | 2020-12-08 |  |  |  |  | 2024-11-22 | 2025-08-20 |  |  |  |  | 2020-10-15 | 2021-01-22 |  |  |  | 2021-05-25 | Addendum | 2020-11-11 | 2021-01-22 |  |  |  |  | 2025-01-29 | 2025-10-24 |  | 2021-11-12 | 2021-02-04 |  |  |  |  | 2025-01-29 | 2025-10-27 | [7 empty] | 2025-01-30 | 2025-11-10 |  | 2020-11-16 | 2021-02-08 |  |  |  |  | 2025-01-31 | 2025-11-12 | 2020-11-16 | 2021-02-08 |  |  |  |  | 2025-01-31 | 2025-11-12 | 2021-06-17 |  |  |  |  | 2024-10-02 |  | 2024-10-18 | [5 empty] | 763297 |  | 585182 | 2025-01-27 |  | 2021-08-30 | 2021-08-30 | 2021-08-30 | 2021-08-30 | 2025-02-10 | 2025-02-11 | 2026-01-06 | 2026-01-06 | [13 empty] | Q1 2025 |  |  |  | Requested | [11 empty] | TRUE | TRUE | 308 | 2021-08-30 | 2021-08-30 | 2021 | 2021 | 2021 | 44364 |  |  | 2021-05-25 | Addendum
309 |  | Govinda Neupane |  | 2020-01-15 | [31 empty] | 4 - DEXT |  | 813D1 | 308 |  | WITHDRAWN | WITHDRAWN |  | Michelle Simms | US Solar Development, LLC | USS FERN SOLAR LLC | 113 Fern Rd | 2000140883 | 30012047863 | Solar | [5 empty] | 45.0123 | -69.2556 | Fern Road |  |  | Dexter |  | DEXTER | 813D1 |  |  | FLOC-MISSING-01142021 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2020-01-23 | 2020-01-30 |  |  |  |  | 1900-01-12 | [57 empty] | No Study | [69 empty] | 2021-09-29 | [37 empty] | TRUE | TRUE | 309 | 0 | 0 | 1900 | #VALUE! | #VALUE!
310 |  | Lanie Patterson | Brent Brooks | 2020-01-17 | 2023-03-29 | L2_Bump |  | 2023-12-08 | L2_Bump | [26 empty] | 3 - WINT |  | 256D3 | 116 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Cate Parker | Summit Ridge Energy | SRE SOLAR ORIGINATION 2 LLC | 164 Route 41 Winthrop | 2000138691 | 30012014012 | Solar | [5 empty] | 44.2002 | -69.5842 | 164 Route 41 |  |  | Winthrop | 69 | WINTHROP | 256D3 | 256T1 |  | 9310-L0097-6450-0143-ED00101 | Non-FERC | WITHDRAWN | WITHDRAWN | 330000 | Yes |  |  | K&A Engineering | Meg Sullivan |  | 2020-01-27 | 2020-01-27 | 2020-02-03 | 2020-01-27 | 2020-01-31 | 2020-10-02 |  | 2020-10-19 |  | 2020-10-02 | 2020-10-02 | 2020-10-19 |  |  | 2020-10-07 |  |  | CS | 2020-10-07 | [6 empty] | CS |  |  | 2020-10-07 | [11 empty] | 2020-10-08 |  |  | 2023-04-13 | [8 empty] | 2023-04-17 | [5 empty] | 2020-10-09 |  |  | 2023-04-27 |  |  |  | Pending |  |  |  |  | 2020-12-16 |  |  | 2021-06-03 | Addendum |  |  | 2020-12-16 |  |  | 2023-06-09 | [5 empty] | 2020-12-19 |  |  | 2023-06-09 | [8 empty] | 2023-07-05 | [5 empty] | 2020-12-22 |  |  | 2023-07-06 |  |  |  |  | 2020-12-22 | [5 empty] | 2021-06-15 |  | 2020-12-28 |  | 2020-12-29 | 2023-02-13 |  | 2023-02-17 | [5 empty] | 1364639 |  | 802515 | 2023-02-09 | 2024-01-22 | 2021-06-15 | 2021-06-15 | 2021-06-15 | 2021-06-15 | 2023-02-17 | 2023-02-17 | [19 empty] | 10300745088 | [11 empty] | TRUE | TRUE | 310 | 2021-06-15 | 2021-06-15 | 2021 | 2021 | 2021 | 44362 |  |  | 2021-06-03 | Addendum
311 |  | Lanie Patterson | Brent Brooks | 2020-01-17 | [31 empty] | 2 - COMR |  | 230D2 | 163 |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED |  | Nate Niles | REVISION ENERGY INC | Community Solar New England, LLC | 190 Howe Rd Whitefield | 2000202157 | 30014106923 | Solar | 990 | 0.99 | 1380 |  |  | 44.2462 | -69.5727 | 190 Howe Road |  |  | Whitefield | 34 | COOPERS MILLS ROAD | 230D2 | 230T2 |  | 9310-L0474-6340-0023-ED00063 | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Yes |  |  | K&A Engineering | Meg Sullivan |  | 2020-01-27 | 2020-01-27 | 2020-02-03 | 2020-01-27 | 2020-01-31 | 2020-04-16 |  | 2020-05-01 |  | 2020-04-16 | 2020-04-16 | 2020-05-01 |  |  | 2020-04-28 |  |  | CS | 2020-04-28 | RS | [5 empty] | CS |  |  | 2020-04-28 | [11 empty] | 2020-05-12 | [17 empty] | 2020-05-15 | 2020-08-28 | [5 empty] | Pending |  |  |  |  | 2020-07-21 | 2020-10-13 | [5 empty] | 2020-07-20 | 2020-10-09 | [7 empty] | 2020-07-20 | 2020-10-09 | [16 empty] | 2020-07-23 | 2020-10-22 |  |  |  |  | 2020-10-22 | [9 empty] | 2020-11-12 |  | 2020-11-12 | [8 empty] | 130541 |  |  |  |  | 2020-04-17: 2020-12-01; 2020-04-17: 2020-12-01 | [15 empty] | 10300734671 | [11 empty] | TRUE | TRUE | 311 | 2020-12-01 | 2020-12-01 | 2020 | 2020 | 2020
312 |  | Eben Snow | Brent Brooks | 2020-01-17 | [31 empty] | 1 - NATP |  | 469D1 |  |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Colin Sexton | Bluewave MA, LLC | BWC BRANDY POND LLC | Harrison Rd Naples | 2000142502 | 30012072531 | Solar | [5 empty] | 43.9882 | -70.6028 | Harrison Road |  |  | Naples | 46 | NAPLES TAP | 469D1 | 469T1 |  | 9310-L0207-4040-0031-ED00098 | Non-FERC | WITHDRAWN | WITHDRAWN | NONE | Yes |  |  | K&A Engineering | Meg Sullivan |  | 2020-01-27 | 2020-01-27 | 2020-02-03 | 2020-01-27 | 2020-01-27 | 2020-02-07 |  | 2020-02-24 |  | 2020-02-07 | 2020-02-07 | 2020-02-24 |  |  | 2020-02-18 | 2020-06-05 |  | CS | 2020-02-18 | RS | 2020-06-05 |  |  |  |  | CS |  |  | 2020-02-18 | 2020-06-05 | [10 empty] | 2020-02-20 | [17 empty] | 2020-03-09 | 2020-06-12 | [5 empty] | Yes |  |  |  |  | 2020-05-12 | 2020-07-27 |  | 2021-06-21 | Addendum |  |  | 2020-05-11 | 2020-07-23 | [7 empty] | 2020-05-05 | 2020-07-24 | [16 empty] | 2020-05-11 | 2020-07-29 | [14 empty] | 2020-08-21 |  | 2020-08-24 | 2022-11-03 |  |  | 2024-11-21 | [6 empty] | 919150 | 2022-11-01 | 2025-01-15 | 2020-08-26 | 2020-08-26 | 2021-06-22 | 2021-06-22 | 2024-08-19 | 2024-08-20 | [19 empty] | 10300706418 | [11 empty] | TRUE | TRUE | 312 | 2020-08-26 | 2020-08-26 | 2020 | 2020 | 2020 |  |  |  | 2021-06-21 14:34 | Addendum
313 |  | Govinda Neupane |  | 2020-01-17 | [31 empty] | 3 - ANSO |  | 801D1 | 245 |  | WITHDRAWN | WITHDRAWN |  | Payne Morgan | Encore Redevelopment, LLC | ENCORE REDEVELOPMENT LLC | 894 Anson Rd, Starks | 2000134579 | 30012025778 | Solar | [7 empty] | 894 Anson Road |  |  | Starks |  | ANSON | 801D1 |  |  | 86-Withdrawn-86d | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2020-01-27 | 2020-02-03 |  |  |  |  | 1900-01-12 | [57 empty] | No Study | [65 empty] | n/a | n/a | n/a | n/a | 2021-02-17 | [37 empty] | TRUE | TRUE | 313 | 0 | 0 | 1900 | #VALUE! | #VALUE!
314 |  | Lanie Patterson | Brent Brooks | 2020-01-21 | [31 empty] | 4 - BLRD |  | 207D2 | 195 |  | WITHDRAWN | WITHDRAWN |  | Josh Mayer | AES DISTRIBUTED ENERGY, INC. | AES DE DEVCO NC LLC | 196 Church Hill Rd Augusta | 2000139917 | 30012032998 | Solar | [7 empty] | 196 Church Hill Road |  |  | Augusta |  | BLAIR ROAD | 207D2 |  |  | 9310-L0020-0240-0062-ED00363 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2020-01-28 | l |  |  |  |  | 1900-01-12 | [127 empty] | 2020-09-18 | [25 empty] | YES | [11 empty] | TRUE | TRUE | 314 | 0 | 0 | 1900 | #VALUE! | #VALUE!
315 |  | Eben Snow | Brent Brooks | 2020-01-21 | [31 empty] | 5 - MEFA |  | 431D3 | 302 |  | WITHDRAWN | WITHDRAWN |  | Colin Sexton | Bluewave MA, LLC | BWC EDWARDS COVE LLC | Johnson Hill Rd | 2000139942 | 30012033228 | Solar/Battery | [7 empty] | Johnson Hill Road |  |  | Poland |  | MECHANIC FALLS | 431D3 | 431T2 |  | 9310-L0167-4710-0044-ED00213 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2020-01-28 | 2020-02-04 |  |  |  |  | 1900-01-12 | [57 empty] | Pending | [69 empty] | 2021-03-12 | [37 empty] | TRUE | TRUE | 315 | 0 | 0 | 1900 | #VALUE! | #VALUE!
316 |  | Lanie Patterson | Brent Brooks | 2020-01-21 | [31 empty] | 2 - NOAU |  | 272D4 | 125 |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED |  | Matt Effler | SOL ALLIANCE DEVELOPMENT LLC | SOL ME Augusta 13 York Farm, LLC | 13 York Farm Rd Augusta | 2000142784 | 30014108697 | Solar | 999 | 0.999 | 1499.42 |  |  | 44.3274 | -69.8179 | 13 York Farm Rd |  |  | Augusta | 17 | NORTH AUGUSTA | 272D4 | 272T1 |  | 9310-L0107-0240-0211-ED00090 | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Yes |  |  | K&A Engineering | Meg Sullivan |  | 2020-01-28 | 2020-01-28 | 2020-02-04 | 2020-01-28 | 2020-02-03 | 2020-06-24 |  | 2020-07-09 |  | 2020-06-24 | 2020-06-24 | 2020-07-09 |  |  | 2020-07-06 |  |  | CS | 2020-07-06 | [6 empty] | CS |  |  | 2020-07-06 | [11 empty] | 2020-07-20 | [17 empty] | 2020-07-27 | [6 empty] | Pending |  |  |  |  | 2020-09-29 |  |  | 2021-05-19 | Addendum |  |  | 2020-09-29 | [8 empty] | 2020-09-29 | [17 empty] | 2020-10-06 | [13 empty] | 2021-06-02 |  | 2020-10-16 |  | 2020-10-16 | 2022-06-14 | [7 empty] | 60853 |  |  |  |  | 2020-04-17: 2020-11-03; 2020-04-17: 2020-11-03; 2021-07-07: 2022-06-14; 2021-07-07: 2022-06-14 | [15 empty] | 10300731239 | [11 empty] | TRUE | TRUE | 316 | 2020-11-03 | 2020-11-03 | 2020 | 2020 | 2020 | 44349 |  |  | 2021-05-19 | Addendum
317 |  | Eben Snow | Brent Brooks | 2020-01-24 | [31 empty] | 5 - NORW |  | 435D3 | 287 |  | WITHDRAWN | WITHDRAWN |  | Tyler Adkins | UGE USA Inc | UGE USA INC | Brown St Norway | 2000142913 | 30012078603 | Solar | [5 empty] | 44.2079 | -70.526 |  |  |  | Norway |  | NORWAY | 435D3 |  |  | 9310-L0170-4420-0008-ED00013 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2020-01-31 | 2020-02-07 |  |  |  |  | 1900-01-12 | [127 empty] | 2021-08-26 | [37 empty] | TRUE | TRUE | 317 | 0 | 0 | 1900 | #VALUE! | #VALUE!
318 |  | Govinda Neupane |  | 2020-01-24 | 2023-05-22 | L2_Bump | [29 empty] | 2 - MONS |  | 834D1 | 272 | Yes | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Tyler Adkins | UGE USA Inc | ME CDG 002 LLC | N Guilford Rd | 2000183204 | 30012671829 | Solar | [5 empty] | 45.2782 | -69.4919 | 153 N. Guilford Rd |  |  | Monson | 24 | MONSON | 834D1 | 834T1 |  | 9310-SS0834 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&A Engineering | Meg Sullivan |  | 2020-01-29 | 2020-01-31 | 2020-02-07 | 2020-01-29 | 2020-02-05 | 2020-06-02 |  | 2020-06-16 |  | 2020-06-02 | 2020-06-02 | 2020-06-16 |  |  | 2020-06-05 |  |  | CS | 2020-06-05 | [6 empty] | CS |  |  | 2020-06-05 |  |  | 2023-05-23 | [8 empty] | 2020-06-10 |  |  | 2023-06-22 | [8 empty] | 2023-07-22 | [5 empty] | 2020-06-10 |  |  | 2023-08-02 |  |  |  | Pending |  |  |  |  | 2020-08-13 | [6 empty] | 2020-08-13 |  |  | 2023-09-18 | [5 empty] | 2020-08-26 |  |  | 2023-09-19 | [8 empty] | 2023-09-19 | [5 empty] | 2020-08-31 |  |  | 2023-09-21 | [7 empty] | 2023-09-21 |  |  |  |  | 2020-09-10 |  | 2020-09-14 | 2022-07-14 |  | 2022-08-30 | [7 empty] | 365986 | 2023-09-18 | 2025-11-11 | 2020-10-05 | 2020-10-05 | 2021-08-23 | 2021-08-23 |  | 2022-08-31 | 2023-10-16 | 2023-10-16 | [13 empty] | Q3 2025 |  |  |  | 10300718439 | [11 empty] | TRUE | TRUE | 318 | 2020-10-05 | 2020-10-05 | 2020 | 2020 | 2020
319 |  | Eben Snow | Brent Brooks | 2020-01-24 | 2022-08-22 | L2_Bump | [29 empty] | 1 - RA34 |  | 444D3 |  |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Sachin Patel | LastMile Energy | SEBAGO SOLAR LLC | Pipline Rd And Bittersweet Way Wind | 2000143907 | 30012094816 | Solar | [5 empty] | 43.8792 | -70.4591 | Pipeline Rd and Bittersweet Way |  |  | Windham | 702 | RAYMOND 34 KV | 444D3 | 444T1 | 12.47 | 9310-L0183-6397-0005-ED00027 | Non-FERC | WITHDRAWN | WITHDRAWN | NONE | Yes |  |  | K&A Engineering | Meg Sullivan |  | 2020-01-28 | 2020-01-31 | 2020-02-07 | 2020-01-28 | 2020-02-05 | 2020-06-18 |  | 2020-07-02 |  | 2020-06-18 | 2020-06-18 | 2020-07-02 |  |  | 2020-06-23 |  |  | CS | 2020-06-23 | [6 empty] | CS |  |  | 2020-06-23 |  |  | 2022-09-07 | 2023-01-27 | [7 empty] | 2020-06-25 |  |  | 2022-09-26 | 2023-02-06 | [7 empty] | 2022-09-27 | 2023-01-27 |  |  |  |  | 2020-07-02 |  |  | 2022-09-27 | 2023-02-07 |  |  | Pending |  |  |  |  | 2020-09-04 | [6 empty] | 2020-09-03 | 2023-03-20 |  | 2022-11-08 | 2023-03-21 |  |  |  |  | 2020-09-18 | 2023-03-22 |  | 2022-11-08 | 2023-03-22 | [7 empty] | 2022-11-16 | 2023-03-27 |  |  |  |  | 2020-09-22 | 2023-03-29 |  | 2022-11-17 | 2023-03-29 |  |  |  |  | 2023-03-29 | [6 empty] | 2020-10-02 | 2021-08-03 | 2020-10-05 | 2023-05-25 |  | 2023-05-31 | [5 empty] | 213139 | 2021-11-11 | 497321 | 2023-03-21 | 2024-02-22 | 2020-10-27 | 2020-10-27 | 2021-08-03 | 2021-08-03 | 2023-05-31 | 2023-05-31 | [19 empty] | 10300728969 | [11 empty] | TRUE | TRUE | 319 | 2020-10-27 | 2020-10-27 | 2020 | 2020 | 2020 |  |  | 44411
320 |  | Rigel Paradise | Rick Duperre | 2020-01-24 | [31 empty] | 1 - BRCM |  | 689D1 |  |  | WITHDRAWN | WITHDRAWN |  | James Marshall | Turning Point Energy | TPE DEVELOPMENT LLC | Betty Welch Rd Kittery | 2000123236 | 30012026404 | Solar | [7 empty] | Betty Welch Rd |  |  | Kittery | 12 | BRAGDON COMMONS | 689D1 |  |  | 9310-L0367-6660-0031-ED00006 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2020-01-31 | 2020-02-07 |  |  |  |  | 1900-01-12 | [123 empty] | n/a | n/a | n/a | n/a | 2020-04-14 | [37 empty] | TRUE | TRUE | 320 | 0 | 0 | 1900 | #VALUE! | #VALUE!
321 |  | Rigel Paradise | Rick Duperre | 2020-01-24 | [31 empty] | 2 - WATE |  | 671D2 | 297 |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2020-10-05 | Daniel Poyenis | Solar Managment International | SOLAR MANAGEMENT INT LLC | 723 Main St Waterboro | 2000273065 | 30013884041 | Solar | 4998 | 4.998 | 7504 |  |  | 43.5497 | -70.7113 | 723 Main St |  |  | Waterboro | 21 | WATERBORO | 671D2 | 671T1 |  | 9310-L0342-6190-0001-ED00033 | Non-FERC | TRIGGERING | TRIGGERING ($340,000) | 170000 | Yes |  |  | K&A Engineering | Meg Sullivan |  | 2020-01-29 | 2020-01-31 | 2020-02-07 | 2020-01-29 | 2020-02-05 | 2020-05-07 |  | 2020-05-21 |  | 2020-05-07 | 2020-05-07 | 2020-05-21 |  |  | 2020-05-20 |  |  | CS | 2020-05-20 | [6 empty] | CS |  |  | 2020-05-20 | [11 empty] | 2020-05-20 | [17 empty] | 2020-05-22 | [6 empty] | Pending |  |  |  |  | 2020-07-28 |  |  | 2021-06-10 | Addendum |  |  | 2020-07-28 | [8 empty] | 2020-07-28 | [33 empty] | 2020-08-21 |  | 2020-08-26 | [8 empty] | 471100 |  |  |  |  | 2020-04-17: 2020-09-04; 2020-04-17: 2020-09-04; 2021-07-07: 2021-06-22; 2021-07-07: 2021-06-22 | [15 empty] | 10300709134 | 10300803675 | [10 empty] | TRUE | TRUE | 321 | 2020-09-04 | 2020-09-04 | 2020 | 2020 | 2020 |  |  |  | 2021-06-10 | Addendum
322 |  | Govinda Neupane |  | 2020-01-24 | [31 empty] | 4 - SKTP |  | 864D1 | 185 |  | WITHDRAWN | WITHDRAWN |  | Noah Gonzalez | Nexamp, Inc | NEXAMP SOLAR LLC | Mercer 2 | 2000114877 | 30012093784 | Solar | [5 empty] | 44.6781 | -69.8851 | 1053 Mercer Road |  |  | Mercer |  | SKOWHEGAN TAP | 864D1 | 864T1 |  | FLOC-MISSING-01142021 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&A Engineering | Meg Sullivan |  | 2020-01-29 | 2020-01-31 | 2020-02-07 | 2020-01-29 | 2020-02-11 | 2022-07-28 | 2022-08-02 | 2022-08-16 | 2022-08-10 | 2022-08-10 | 2022-08-10 | 2022-08-24 | [123 empty] | 2022-08-25 | [37 empty] | TRUE | TRUE | 322 | 0 | 0 | 1900 | #VALUE! | #VALUE!
323 |  | Govinda Neupane |  | 2020-01-24 | [31 empty] | 4 - HART |  | 824D1 | 259 |  | WITHDRAWN | WITHDRAWN |  | Noah Gonzalez | Nexamp, Inc | NEXAMP SOLAR LLC | Hartland Solar | 2000114877 | 30012093768 | Solar | [7 empty] | 876 Beans Corner Road |  |  | Hartland |  | HARTLAND | 824D1 |  |  | 9310-SS0824 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2020-01-31 | 2020-02-07 |  |  |  |  | 1900-01-12 | [57 empty] | Pending | [69 empty] | 2020-12-02 | [37 empty] | TRUE | TRUE | 323 | 0 | 0 | 1900 | #VALUE! | #VALUE!
324 |  |  | Anthony Boucher | 2020-01-24 | [31 empty] | 3 - UNIO |  | 251D1 | 144 |  | WITHDRAWN | WITHDRAWN |  | Nate Niles | REVISION ENERGY INC | REVISION ENERGY INC | 1980 Heald Highway Union | 2000038393 | 30012087653 | Solar | [7 empty] | 1980 Heald Highway |  |  | Union |  | UNION | 251D1 |  |  | 9310-L0089-5950-0001-ED00051 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2020-01-31 | 2020-02-07 |  |  |  |  | 1900-01-12 | [127 empty] | 2020-09-23 | [37 empty] | TRUE | TRUE | 324 | 0 | 0 | 1900 | #VALUE! | #VALUE!
325 |  | Eben Snow | Brent Brooks | 2020-01-27 | 2022-06-08 | L2_Bump |  | 2022-07-27 | L2_Bump |  | 2023-01-18 | L2_With |  | 2023-07-10 | L2_Bump |  | 2023-09-26 | wthdw |  | 2023-10-05 | L2_Bump |  | 2024-01-17 | L2_Bump | [11 empty] | 3 - DEER |  | 412D4 | 30 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Shanthini Sivaharan/Malina Ibelle | Ameresco, Inc | TAYLOR HILL ROAD SOLAR LLC | 106 Taylor Hill Rd Lewiston Solar | 2000139658 | 30012028640 | Solar | [5 empty] | 44.155 | -70.1959 | 106 Taylor Hill Rd |  |  | Lewiston | 185 | DEER RIPS | 412D4 | 412T4 |  | 9310-SS0412-006 | Non-FERC | WITHDRAWN | WITHDRAWN | NONE | Yes |  |  | K&A Engineering | Meg Sullivan |  | 2020-01-31 | 2020-02-03 | 2020-02-10 | 2020-01-31 | 2020-02-06 | 2020-07-09 |  | 2020-07-23 |  | 2020-07-09 | 2020-07-13 | 2020-07-27 |  |  | 2020-07-27 |  |  | CS | 2020-07-29 | RS | [5 empty] | CS |  |  | 2020-07-29 |  |  | 2023-02-09 | [8 empty] | 2020-08-05 |  |  | 2023-03-21 | [8 empty] | 2023-04-17 | [5 empty] | 2020-08-04 | 2020-11-24 |  | 2023-04-17 |  |  |  | Pending |  |  |  |  | 2020-10-07 | 2021-01-11 | [5 empty] | 2020-10-07 | 2021-01-11 |  | 2023-05-26 | [5 empty] | 2020-10-14 | 2021-01-15 |  | 2023-05-30 | [8 empty] | 2023-06-08 | [5 empty] | 2020-10-21 | 2021-01-20 | [6 empty] | 2020-10-21 | 2021-01-20 | [12 empty] | 2023-07-13 | 2023-07-13 |  |  |  | 525441 |  |  |  | 2024-05-13 | 2020-04-17: 2021-02-16; 2020-04-17: 2021-02-16; 2021-07-07: 2021-08-24; 2021-07-07: 2021-08-24 | 2023-08-09 | 2023-08-09 | [13 empty] | 10300756903 | [11 empty] | TRUE | TRUE | 325 | 2021-02-16 | 2021-02-16 | 2021 | 2021 | 2021
326 |  | Rigel Paradise | Rick Duperre | 2020-01-27 | 2023-10-09 | wthdw | [29 empty] | 3 - NOLI |  | 638D1 | 149 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Zeeshan Yasin | Novel Energy Solutions LLC | 697 Sokokis Ave Solar LLC | 697 Sokokis Ave Limington | 2000174917 | 30014074097 | Solar | [5 empty] | 43.7713 | -70.659 | 697 Sokokis Ave |  |  | Limington | 61 | NORTH LIMINGTON | 638D1 | 638T1 | 12.47 | 9310-L0274-3270-0039-ED00218 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&A Engineering | Meg Sullivan |  | 2020-01-31 | 2020-02-03 | 2020-02-10 | 2020-01-31 | 2020-02-11 | 2020-07-13 |  | 2020-07-27 |  | 2020-07-13 | 2020-07-14 | 2020-07-28 |  |  | 2020-07-27 |  |  | CS | 2020-07-27 | [6 empty] | CS |  |  | 2020-07-27 |  |  | 2023-10-30 | [8 empty] | 2020-07-16 |  |  | 2023-10-31 | [8 empty] | 2023-11-01 | [5 empty] | 2020-08-04 |  |  | 2023-11-02 |  |  |  | Pending |  |  |  |  | 2020-10-07 |  |  | 2021-05-24 | Addendum |  |  | 2020-10-07 |  |  | 2023-12-29 | [5 empty] | 2020-10-07 |  |  | 2024-01-02 | [8 empty] | 2023-01-23 | [5 empty] | 2020-10-21 |  |  | 2024-01-26 | [7 empty] | 2024-01-26 |  |  |  | 2021-05-24 | 2021-05-24 |  | 2020-10-30 | 2023-05-17 |  | 2023-05-17 | 2023-07-03 | 2023-07-10 |  |  |  | 156155 |  | 905261 | 2023-12-29 | 2024-09-30 | 2020-11-05 | 2020-11-05 | 2021-10-28 | 2021-11-04 | 2023-05-17 | 2023-05-17 | 2024-02-12 | 2024-02-13 |  |  | 2023-09-26 | 2023-09-26 | [13 empty] | 10300735563 | [11 empty] | TRUE | TRUE | 326 | 2020-11-05 | 2020-11-05 | 2020 | 2020 | 2020 |  | 44340 |  | 2021-05-24 | Addendum
327 |  | Marshall Ripley | Rick Duperre | 2020-01-27 | [31 empty] | 4 - SPST |  | 668D5 | 248 |  | WITHDRAWN | WITHDRAWN |  | Christian L'Oranger | NBD SOLAR MAINE LLC | NEO Virtus - NBDSolar - L ORANGE LLC - Gorham | 239 County Rd Gorham | 2000144160 | 30012097967 | Solar | [7 empty] | 239 County Rd |  |  | Gorham |  | SPRING STREET | 668D5 |  |  | 86-Withdrawn-86d | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2020-02-03 | 2020-02-10 |  |  |  |  | 1900-01-12 | [127 empty] | 2020-03-03 | [37 empty] | TRUE | TRUE | 327 | 0 | 0 | 1900 | #VALUE! | #VALUE!
328 |  | Rigel Paradise | Rick Duperre | 2020-01-27 | [31 empty] | 2 - SAIP |  | 656D3 | 11 |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2022-06-27 | Noah Craft | Novel Energy Solutions LLC | 83 AIRPORT ROAD SOLAR LLC | 83 Airport Rd. Sanford | 2000174917 | 30014073933 | Solar | 4998 | 4.998 | 5070 |  |  | 43.4011 | -70.7205 | 83 Airport Rd |  |  | Sanford | 12 | SANFORD INDUSTRIAL PARK | 656D3 | 656T1 |  | 9310-L0318-5170-0466-ED00027 | Non-FERC | COST SHARE | COST SHARE (250,000) | 113748 | Yes |  |  | K&A Engineering | Meg Sullivan |  | 2020-02-03 | 2020-02-03 | 2020-02-10 | 2020-02-03 | 2020-02-10 | 2020-05-25 |  | 2020-06-08 |  | 2020-05-25 | 2020-05-25 | 2020-06-08 |  |  | 2020-06-08 |  |  | CS | 2020-06-10 | [6 empty] | CS |  |  | 2020-06-10 | [11 empty] | 2020-06-10 | [17 empty] | 2020-06-23 | [6 empty] | Pending |  |  |  |  | 2020-08-26 |  |  | 2021-05-20 | Addendum |  |  | 2020-08-25 | [8 empty] | 2020-08-26 | [17 empty] | 2020-08-31 | [14 empty] | 2021-05-20 | 2021-05-21 |  | 2020-09-16 |  |  |  | 2023-08-02 | 2023-08-02 |  |  |  | 152976 |  |  |  |  | 2020-04-17: 2020-09-29; 2020-04-17: 2020-09-29; 2021-07-07: 2021-09-28; 2021-07-07: 2021-09-30 | 2023-08-04 | 2023-08-21 | [13 empty] | 10300720302 | [11 empty] | TRUE | TRUE | 328 | 2020-09-29 | 2020-09-29 | 2020 | 2020 | 2020 |  | 44336 |  | 2021-05-20 | Addendum
329 |  | Eben Snow | Brent Brooks | 2020-01-27 | 2022-06-08 | L2_Bump |  | 2022-07-27 | L2_Bump |  | 2023-01-18 | L2_With |  | 2023-07-10 | L2_Bump | [20 empty] | 4 - DEER |  | 412D1 | 325 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Nick Ford | Hexagon Energy LLC | AUBURN SOLAR LLC | 1054 North River Rd Auburn | 2000143906 | 30012094493 | Solar | [5 empty] | 44.1403 | -70.2107 | 1054 River Road |  |  | Auburn | 24 | DEER RIPS | 412D1 | 412T2 |  | FLOC-MISSING-01142021 | Non-FERC | WITHDRAWN | WITHDRAWN | NONE | Yes |  |  | K&A Engineering | Meg Sullivan |  | 2020-02-03 | 2020-02-03 | 2020-02-10 | 2020-02-03 | 2020-02-10 | 2021-02-24 |  | 2021-03-10 |  | 2021-02-24 | 2021-02-24 | 2021-03-10 |  |  | 2021-03-03 | 2021-10-14 | 2021-03-15 | CS | 2021-03-05 | RS | 2021-10-14 |  |  |  |  | CS |  |  | 2021-03-05 | 2021-10-14 | 2021-03-15 | [27 empty] | 2021-03-16 | 2021-10-18 | [10 empty] | 2021-05-19 | 2021-12-01 |  | 2021-06-29 | Report |  |  | 2021-06-29 | 2021-11-12 | [7 empty] | 2021-06-29 | 2021-11-11 | [16 empty] | 2021-07-19 | [7 empty] | 2021-07-19 | [7 empty] | 2021-08-17 | 2021-08-17 | 2021-08-17 | [10 empty] | 65492 | 2021-11-02 | 2023-09-26 | 2020-04-17: 2021-08-17; 2020-04-17: 2021-09-16; 2021-07-07: 2021-11-24; 2021-07-07: 2021-12-07 | [15 empty] | Requested | [11 empty] | TRUE | TRUE | 329 | 2021-08-17 | 2021-08-17 | 2021 | 2021 | 2021 |  |  | 44425 | 2021-06-29 | Report
330 |  | Rigel Paradise | Rick Duperre | 2020-01-27 | [31 empty] | 4 - BASS |  | 602D3 | 293 |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2021-03-30 | Liam McCormack | Summit Ridge Energy | KNIGHTS POND SOLAR LLC | 49 Junction Rd South Berwick | 2000143905 | 30012094485 | Solar | 4000 | 4 | 4987.84 |  |  | 43.2478 | -70.7783 | 49 Junction RD |  |  | South Berwick | 9 | BASSETT | 602D3 | 602T1 |  | 9310-L0212-5410-0018-ED00018 | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Yes |  |  | K&A Engineering | Meg Sullivan |  | 2020-02-03 | 2020-02-03 | 2020-02-10 | 2020-02-03 | 2020-02-10 | 2020-05-11 |  | 2020-05-26 |  | 2020-05-11 | 2020-05-11 | 2020-05-26 |  |  | 2020-05-15 |  |  | CS | 2020-05-15 | [6 empty] | CS |  |  | 2020-05-15 | [11 empty] | 2020-06-04 | [17 empty] | 2020-06-09 | [6 empty] | Pending |  |  |  |  | 2020-08-12 | [6 empty] | 2020-08-12 | [8 empty] | 2020-08-13 | [17 empty] | 2020-08-17 | [15 empty] | 2020-08-18 |  | 2020-08-19 | [13 empty] | 2020-04-17: 2020-09-11; 2020-04-17: 2020-09-11; 2021-07-07: 2021-09-14; 2021-07-07: 2021-09-22 | [15 empty] | 10300714135 | [11 empty] | TRUE | TRUE | 330 | 2020-09-11 | 2020-09-11 | 2020 | 2020 | 2020
331 |  | Govinda Neupane |  | 2020-01-28 | [31 empty] | 6 - WSTN |  | 866D1 | 227 |  | WITHDRAWN | WITHDRAWN |  | Nate Niles | REVISION ENERGY INC | REVISION ENERGY INC | 119 Eaton Mtn Rd Skowhegan | 2000038393 |  | Solar | [7 empty] | 119 EATON MTN RD |  |  | Skowhegan |  | WESTON HYDRO | 866D1 |  |  | 9310-L0450-5330-0059-ED00083 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2020-02-04 | 2020-02-11 |  |  |  |  | 1900-01-12 | [127 empty] | 2020-09-29 | [25 empty] | YES | [11 empty] | TRUE | TRUE | 331 | 0 | 0 | 1900 | #VALUE! | #VALUE!
332 |  | Govinda Neupane |  | 2020-01-28 | [31 empty] | 2 - NOAN |  | 838D1 | 247 |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2021-12-17 | Jess Roden | Greenbacker Capital | ER Dairy Farm Solar, LLC | ER DAIRY FARM SOLAR LLC | 2000186907 | 30012722507 | Solar | 4000 | 4 | 7000 |  |  | 44.8382 | -69.8812 | 644 River Road |  |  | Anson | 53 | NORTH ANSON | 838D1 | 838T1 |  | 9310-L0421-0150-0023-ED00060 | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2020-02-04 | 2020-02-04 | 2020-02-11 | 2020-02-04 | 2020-02-10 | 2020-06-22 |  | 2020-07-07 |  | 2020-06-22 | 2020-06-22 | 2020-07-07 |  |  | 2020-07-02 |  |  | CS | 2020-07-02 | [6 empty] | CS |  |  | 2020-07-02 | [11 empty] | 2020-07-02 | [17 empty] | 2020-07-06 | [6 empty] | Pending |  |  |  |  | 2020-09-08 |  |  | 2021-05-19 | Addendum |  |  | 2020-09-08 | [8 empty] | 2020-09-25 | [17 empty] | 2020-09-28 | [14 empty] | 2021-05-24 | 2021-05-19 |  | 2020-10-08 | 2023-03-13 | 2023-03-20 | 2023-03-20 | [5 empty] | 587555 |  | 683934 | 2023-03-09 |  | 2020-10-19 | 2020-10-19 | 2021-05-21 | 2021-05-21 | 2023-03-21 | 2023-03-21 | [15 empty] | Q2 2021 |  |  |  | 10300724982 | [11 empty] | TRUE | TRUE | 332 | 2020-10-19 | 2020-10-19 | 2020 | 2020 | 2020 |  | 44340 |  | 2021-05-19 | Addendum
333 |  | Rigel Paradise | Rick Duperre | 2020-01-28 | [31 empty] | 1 - GOOS |  | 630D4 | 115 |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2021-03-30 | Tyler William Perkins | Nexamp, Inc | TPE ME OO01 LLC | Oo01 Ross Rd Old Orchard Beach | 2000123236 | 30011775084 | Solar | 4700 | 4.7 | 7372.3 |  |  | 43.5277 | -70.4128 | OO01 Ross Rd |  |  | Old Orchard Beach | 39 | GOOSEFARE | 630D4 | 630T1 |  | 9310-L0239-4310-0180-ED00065 | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2020-02-03 | 2020-02-04 | 2020-02-11 | 2020-02-03 | 2020-02-03 | 2020-02-13 |  | 2020-02-28 |  | 2020-02-13 | 2020-02-13 | 2020-02-28 |  |  | 2020-02-14 | 2020-04-30 |  | CS | 2020-02-14 | RS | 2020-04-30 |  |  |  |  | CS |  |  | 2020-02-14 | 2020-04-30 | [10 empty] | 2020-04-29 | [17 empty] | 2020-05-05 | [6 empty] | Pending |  |  |  |  | 2020-07-09 | [6 empty] | 2020-07-09 | [8 empty] | 2020-07-10 | [17 empty] | 2020-07-14 | [15 empty] | 2020-07-14 | 2021-08-18 | 2020-07-15 | 2022-08-30 | [7 empty] | 619788 | 2020-07-05 | 1012755 | 2022-08-05 |  | 2020-04-17: 2020-07-16; 2020-04-17: 2020-07-16; 2021-07-07: 2021-08-18; 2021-07-07: 2021-08-18; 2022-08-01: 2022-09-29 | [11 empty] | Q3 2021 |  |  |  | 10300691582 | [11 empty] | TRUE | TRUE | 333 | 2020-07-16 | 2020-07-16 | 2020 | 2020 | 2020 |  |  | 44426
334 |  | Lanie Patterson | Brent Brooks | 2020-01-28 | [31 empty] | 3 - VASS |  | 861D9 | 281 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | James Marshall | Turning Point Energy | TPE DEVELOPMENT LLC | Bassett Rd Winslow (Wi01) | 2000123236 | 30012095458 | Solar | [5 empty] | 44.5234 | -69.6191 | Bassett Rd |  |  | Winslow | 21 | VASSALBORO | 861D9 | 861T1 |  | FLOC-MISSING-01142021 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2020-02-03 | 2020-02-04 | 2020-02-11 | 2020-02-03 | 2020-02-10 |  |  | 1900-01-12 |  | 2021-08-09 | 2021-08-09 | 2021-08-23 |  |  | 2021-08-09 |  |  | CS | 2021-08-11 | [6 empty] | CS |  |  | 2021-08-11 |  |  | 2022-09-26 | 2022-12-28 | [7 empty] | 2021-08-16 |  |  | 2022-09-29 | [14 empty] | 2021-08-16 | [11 empty] | 2021-10-20 | [6 empty] | 2021-10-21 | [8 empty] | 2021-10-21 | [17 empty] | 2021-10-25 | [7 empty] | 2021-10-25 | [18 empty] | 691296 | 2021-10-20 | n/a | n/a | 2023-01-06 | 2020-04-17: 2021-10-26; 2020-04-17: 2021-10-27; 2021-07-07: 2021-11-05 | [15 empty] | Requested | [11 empty] | TRUE | TRUE | 334 | 2021-10-26 | 2021-10-26 | 2021 | 2021 | 2021
335 |  | Govinda Neupane |  | 2020-01-30 | [31 empty] | 5 - SKTP |  | 864D1 | 322 |  | WITHDRAWN | WITHDRAWN |  | Noah Gonzalez | Nexamp, Inc | NEXAMP SOLAR LLC | Mercer 1 | 2000114877 | 30012093776 | Solar/Battery | [5 empty] | 44.6848 | -69.8791 | 1053 Mercer Road |  |  | Mercer |  | SKOWHEGAN TAP | 864D1 | 864T1 |  | FLOC-MISSING-01142021 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2020-02-05 | 2020-02-06 | 2020-02-13 | 2020-02-05 | 2020-02-10 |  |  | 1900-01-12 | [127 empty] | 2022-08-25 | [37 empty] | TRUE | TRUE | 335 | 0 | 0 | 1900 | #VALUE! | #VALUE!
336 |  | Lanie Patterson | Brent Brooks | 2020-01-30 | [31 empty] | 2 - MCCO |  | 237D1 | 216 |  | WITHDRAWN | WITHDRAWN |  | Kevin Hu | NextEra Energy Resources | DG Maine CS LLC | Hannaford Hill Rd Southoray - Vassa | 2000139230 | 30012022577 | Solar | [7 empty] | Hannaford Hill Rd. |  |  | Vassalboro |  | MCCOYS | 237D1 |  |  | 86-Withdrawn-86d | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2020-02-06 | 2020-02-13 |  |  |  |  | 1900-01-12 |  | 2020-10-24 | 2020-10-24 | [54 empty] | Pending | [65 empty] | n/a | n/a | n/a | n/a | 2020-04-14 | [37 empty] | TRUE | TRUE | 336 | 0 | 0 | 1900 | #VALUE! | #VALUE!
337 |  | Lanie Patterson | Brent Brooks | 2020-01-30 | [31 empty] | 3 - MCCO |  | 237D1 | 336 |  | WITHDRAWN | WITHDRAWN |  | Kevin Hu | NextEra Energy Resources | DG Maine CS LLC | Hannaford Hill Rd Northoray - Vassa | 2000139230 | 30012022569 | Solar | [7 empty] | Hannaford Hill Rd. |  |  | Vassalboro |  | MCCOYS | 237D1 |  |  | 86-Withdrawn-86d | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2020-02-06 | 2020-02-13 |  |  |  |  | 1900-01-12 | [57 empty] | Pending | [65 empty] | n/a | n/a | n/a | n/a | 2020-06-23 | [37 empty] | TRUE | TRUE | 337 | 0 | 0 | 1900 | #VALUE! | #VALUE!
338 |  | Govinda Neupane |  | 2020-01-31 | [31 empty] | 1 - SADD |  | 876D1 |  |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2020-08-31 | Tyler William Perkins | Nexamp, Inc | Arctaris Saddleback Solar LLC | 976 Saddleback Mountain Rd | 2000145053 | 30015337451 | Solar | 4890 | 4.89 | 7359 |  |  | 44.9718 | -70.5479 | 976 Saddleback Mountain Rd |  |  | Sandy River Plantation | 8 | SADDLEBACK | 876D1 | Tap off of Transmission Line |  | FLOC-MISSING-01142021 | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2020-02-05 | 2020-02-07 | 2020-02-14 | 2020-02-05 | 2020-02-10 | 2020-04-10 |  | 2020-04-27 |  | 2020-04-10 | 2020-04-10 | 2020-04-27 |  |  | 2020-04-17 |  |  | CS | 2020-04-17 | [6 empty] | CS |  |  | 2020-04-17 | [11 empty] | 2020-04-21 | [17 empty] | 2020-04-23 | [6 empty] | Pending |  |  |  |  | 2020-06-26 | [6 empty] | 2020-06-25 | [8 empty] | 2020-06-26 | [17 empty] | 2020-07-01 | [15 empty] | 2020-07-31 | 2021-07-29 | 2020-08-03 | [13 empty] | 2020-04-17: 2020-09-16; 2020-04-17: 2020-09-16; 2021-07-07: 2021-07-29; 2021-07-07: 2021-07-29 | [11 empty] | Q4 2020 |  |  |  | 10300714048 | [11 empty] | TRUE | TRUE | 338 | 2020-09-16 | 2020-09-16 | 2020 | 2020 | 2020 |  |  | 44406
339 |  | Govinda Neupane |  | 2020-02-03 | 2022-05-31 | L2_Bump | [29 empty] | 3 - DOVE |  | 815D2 | 192 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Tyler Adkins | UGE USA INC | UGE USA INC | 772 Essex St | 2000142913 | 30012102445 | Solar | [5 empty] | 45.1876 | -69.1924 | 772 Essex |  |  | Dover-Foxcroft | 44 | DOVER | 815D2 | 815T2 |  | FLOC-MISSING-01142021 | FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2020-02-06 | 2020-02-10 | 2020-02-18 | 2020-02-06 | 2020-02-06 | 2020-03-05 |  | 2020-03-19 |  | 2020-03-05 | 2020-03-05 | 2020-03-19 |  |  | 2020-03-19 |  |  | CS | 2020-03-23 | [6 empty] | CS |  |  | 2020-03-23 | 2022-07-07 | [10 empty] | 2020-04-06 | [17 empty] | 2020-04-09 | [6 empty] | Pending |  |  |  |  | 2020-06-15 | [6 empty] | 2020-06-10 | [8 empty] | 2020-06-18 | [17 empty] | 2020-06-23 | [15 empty] | 2020-08-03 |  | 2020-08-04 | 2023-03-13 | 2023-03-22 | 2023-03-17 | [5 empty] | 199943 |  | 301838 | 2023-03-09 | 2024-12-09 | 2020-09-02 | 2020-09-02 | 2021-08-19 | 2021-08-19 | 2023-03-20 | 2023-03-23 | [19 empty] | 10300708608 | [11 empty] | TRUE | TRUE | 339 | 2020-09-02 | 2020-09-02 | 2020 | 2020 | 2020
340 |  | Govinda Neupane |  | 2020-02-03 | [31 empty] | 8 - STUR |  | 858D4 | 304 |  | WITHDRAWN | WITHDRAWN |  | Allen Tate | US Solar Development, LLC | USS DAVIS SOLAR LLC | 278 Mosher Hill Rd Farmington | 2000141837 | 30012062821 | Solar | [5 empty] | 44.7133 | -70.1093 | 278 MOSHER HILL RD |  |  | Farmington |  | STURTEVANT | 858D4 | 858T2 |  | 9310-L0441-2030-0150-ED00158 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2020-02-06 | 2020-02-10 | 2020-02-18 | 2020-02-06 | 2020-02-14 | 2022-06-22 | 2022-06-28 | 2022-07-07 | 2022-07-13 | 2022-07-13 | 2022-07-13 | 2022-07-27 | [123 empty] | 2020-07-28 | [37 empty] | TRUE | TRUE | 340 | 0 | 0 | 1900 | #VALUE! | #VALUE!
341 |  | Rigel Paradise | Rick Duperre | 2020-02-03 | 2023-10-09 | wthdw |  | 2024-09-30 | wthdw | [26 empty] | 4 - NOLI | 1 - NOLI | 638D2 | 326 | Yes | EXECUTED | EXECUTED |  | Noah Craft | Novel Energy Solutions LLC | Hanscom School Rd Solar LLC | 196 Hanscomb School Rd Limington | 2000174917 | 30015848341 | Solar | 996 | 0.996 | 1937.52 |  | 1128 | 4378707 | -70.6637 | 196 Hanscomb School Rd. |  |  | Limington | 8 | NORTH LIMINGTON | 638D2 | 638T1 | 12.47 | 9310-L0274-3270-0039-ED00005 | Non-FERC | TRIGGERING | 125000 |  | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2020-02-06 | 2020-02-10 | 2020-02-18 | 2020-02-06 | 2020-02-11 | 2020-11-18 |  | 2020-12-04 |  | 2020-11-18 | 2020-11-19 | 2020-12-07 |  |  | 2020-12-07 |  |  | CS | 2020-12-07 | [6 empty] | CS |  |  | 2020-12-07 |  |  | 2024-02-23 | [11 empty] | 2024-03-13 | 2024-11-20 | [7 empty] | 2024-05-21 | 2024-11-20 |  |  |  |  | 2020-12-14 |  |  | 2024-05-21 | 2024-11-01 | [7 empty] | 2021-02-19 |  |  | 2021-05-24 | Addendum |  |  | 2021-02-19 |  |  | 2024-07-26 | 2025-01-29 |  |  |  |  | 2021-02-22 |  |  | 2024-07-26 | 2025-01-29 | [7 empty] | 2024-08-12 | 2025-01-31 |  |  |  |  | 2021-03-01 |  |  |  | 2025-02-06 |  |  |  | 2021-03-01 |  |  |  | 2025-02-06 |  | 2021-05-25 |  | 2021-05-24 | 2021-05-25 | 2021-05-24 |  | 2021-05-24 |  | 2023-07-03 | 2023-07-10 |  |  |  | 548430 |  | 999686 | 2024-07-26 |  | 2021-05-26 | 2021-05-26 | 2021-09-28 | 2021-09-30 | 2023-05-19 | 2023-05-19 | 2023-09-26 | 2023-09-26 | 2025-02-26 | 2025-02-26 | 2023-09-26 | 2023-09-27 | [9 empty] | Q2 2025 |  |  |  | 10300788010 | [11 empty] | TRUE | TRUE | 341 | 2021-05-26 | 2021-05-26 | 2021 | 2021 | 2021 | 44341 |  | 44341 | 2021-05-24 | Addendum
342 |  | Rigel Paradise | Rick Duperre | 2020-02-03 | [31 empty] | 3 - WATE |  | 671D2 | 321 |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2022-06-27 | Zeeshan Yasin | Novel Energy Solutions LLC | 41 SOKOKIS TRL SOLAR LLC | 43 Sokokis Trl Waterboro | 2000285112 | 30014040882 | Solar | 4998 | 4.998 | 7358.52 |  |  | 43.5739 | -70.6842 | 43 Sokokis Trl |  |  | Waterboro | 69 | WATERBORO | 671D2 | 671T1 |  | 9310-L0342-6190-0093-ED00126 | Non-FERC | COST SHARING | COST SHARE ($340,000) | 170000 | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2020-02-06 | 2020-02-10 | 2020-02-18 | 2020-02-06 | 2020-02-14 | 2020-09-18 |  | 2020-10-02 |  | 2020-09-18 | 2020-09-18 | 2020-10-02 |  |  | 2020-09-30 |  |  | CS | 2020-09-30 | [6 empty] | CS |  |  | 2020-09-30 | [29 empty] | 2020-10-23 | [6 empty] | Pending |  |  |  |  | 2020-12-30 |  |  | 2021-06-10 | Addendum |  |  | 2020-12-30 | [8 empty] | 2021-01-04 | [17 empty] | 2021-01-07 | [7 empty] | 2021-01-07 | [7 empty] | 2021-01-25 |  | 2021-01-25 | [8 empty] | 439829 |  |  |  |  | 2020-04-17: 2021-06-14; 2020-04-17: 2021-06-14; 2021-07-07: 2021-09-28; 2021-07-07: 2021-09-30 | [15 empty] | 10300798513 | [11 empty] | TRUE | TRUE | 342 | 2021-06-14 | 2021-06-14 | 2021 | 2021 | 2021 |  |  |  | 2021-06-10 | Addendum
343 |  |  | KRISTOFER COLEMAN | 2020-02-05 | [31 empty] | 1 - BRIS |  | 210D2 |  |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2020-07-30 | Jonovan (Jonny) Lizama | Luminace | Overlook Solar Partners, LLC | Christian Hill Rd, 010-034 Bristol | 2000347342 | 30014873670 | Solar | 4899 | 4.899 | 7618 |  |  | 43.9643 | -69.52 | Christian Hill Rd, 010-034 |  |  | Bristol | 6.7 | BRISTOL | 210D2 | 210T1 |  | 9310-L0478-0710-0020-ED00176 | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2020-02-07 | 2020-02-12 | 2020-02-20 | 2020-02-07 | 2020-02-07 | 2020-02-21 |  | 2020-03-06 |  | 2020-02-21 | 2020-02-21 | 2020-03-06 |  |  | 2020-02-21 |  |  | CS | 2020-02-21 | [6 empty] | CS |  |  | 2020-02-21 | [11 empty] | 2020-02-28 | [17 empty] | 2020-03-06 | [6 empty] | Pending |  |  |  |  | 2020-05-11 | [6 empty] | 2020-05-11 | [8 empty] | 2020-05-11 | [17 empty] | 2020-05-15 | [15 empty] | 2020-05-20 |  | 2020-05-20 | [13 empty] | 2020-04-17: 2020-05-21; 2020-04-17: 2020-05-21; 2021-07-07: 2021-07-20; 2021-07-07: 2021-07-20 | [11 empty] | Q4 2021 |  |  | TBD | 10300678938 | [11 empty] | TRUE | TRUE | 343 | 2020-05-21 | 2020-05-21 | 2020 | 2020 | 2020
344 |  | Govinda Neupane |  | 2020-02-05 | [31 empty] | 1 - EMDE |  | 868D1 |  |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2020-07-30 | Jonovan (Jonny) Lizama | Luminace | Tower Solar Partners, LLC | Kennebec River Rd, 009-018, Embden | 2000347345 | 30014873811 | Solar | 4999 | 4.999 | 2828 |  |  | 44.949 | -69.8801 | Kennebec River Rd, 009-018 |  |  | Embden | 28 | EMBDEN | 868D1 | 868T1 |  | FLOC-MISSING-01142021 | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2020-02-10 | 2020-02-12 | 2020-02-20 | 2020-02-10 | 2020-02-10 | 2020-02-28 |  | 2020-03-13 |  | 2020-02-28 | 2020-02-28 | 2020-03-13 |  |  | 2020-02-28 |  |  | CS | 2020-02-28 | [6 empty] | CS |  |  | 2020-02-28 | [11 empty] | 2020-01-31 | [17 empty] | 2020-03-25 | [6 empty] | Pending |  |  |  |  | 2020-05-29 | [6 empty] | 2020-05-29 | [8 empty] | 2020-05-21 | [17 empty] | 2020-05-27 | [15 empty] | 2020-05-27 | 2021-07-29 | 2020-05-28 | [13 empty] | 2020-04-17: 2020-06-01; 2020-04-17: 2020-06-01; 2021-07-07: 2021-07-29; 2021-07-07: 2021-07-29 | [11 empty] | Q4 2021 |  |  |  | 10300685854 | [11 empty] | TRUE | TRUE | 344 | 2020-06-01 | 2020-06-01 | 2020 | 2020 | 2020 |  |  | 44406
345 |  |  | Anthony Boucher | 2020-02-05 | [31 empty] | 2 - BUCK |  | 806D2 | 119 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN | 2020-10-05 | Greg Rosshirt | BORREGO SOLAR SYSTEMS INC | 510 PV PROJECT DEVELOPMENT LLC | Acadia Hwy / Orland Me | 2000113260 | 30012060320 | Solar/Battery | [5 empty] | 44.5636 | -68.6922 | Acadia Hwy |  |  | Orland | 248 | BUCKSPORT | 806D2 | 806T3 |  | 9310-L0386-4330-0027-ED00220 | Non-FERC | WITHDRAWN | WITHDRAWN | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2020-02-11 | 2020-02-12 | 2020-02-20 | 2020-02-11 | 2020-02-14 | 2020-04-22 |  | 2020-05-06 |  | 2020-04-22 | 2020-04-22 | 2020-05-06 |  |  | 2020-04-28 |  |  | CS | 2020-04-28 | [6 empty] | CS |  |  | 2020-04-28 | [11 empty] | 2020-04-24 | [17 empty] | 2020-05-05 | [6 empty] | Pending |  |  |  |  | 2020-07-09 |  |  | 2021-05-19 | Addendum |  |  | 2020-07-09 | [8 empty] | 2020-07-10 | [17 empty] | 2020-07-13 | [13 empty] | 2021-06-01 |  | 2020-07-14 |  | 2020-07-14 | [8 empty] | 428495 |  |  |  | 2022-08-11 | 2020-04-17: 2020-07-24; 2020-04-17: 2020-07-24; 2021-07-07: 2021-06-16; 2021-07-07: 2021-06-16 | [15 empty] | 10300690808 | [11 empty] | TRUE | TRUE | 345 | 2020-07-24 | 2020-07-24 | 2020 | 2020 | 2020 | 44348 |  |  | 2021-05-19 | Addendum
346 |  | Lanie Patterson | Brent Brooks | 2020-02-06 | [31 empty] | 4 - VASS |  | 861D9 | 334 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Matthew Doubleday | SunRaise Investments LLC | SUNRAISE DEVELOPMENT LLC | 0 China Rd/Winslow | 2000124937 | 30012117070 | Solar/Battery | [5 empty] | 44.5228 | -69.5825 | 0 China Road |  |  | Winslow | 58 | VASSALBORO | 861D9 | 861T1 | 12.47 | FLOC-MISSING-01142021 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2020-02-12 | 2020-02-13 | 2020-02-21 | 2020-02-12 | 2020-02-14 | 2021-10-27 | 2021-11-01 | 2021-11-10 | 2021-11-01 | 2021-11-02 | 2021-11-02 | 2021-11-17 |  |  | 2021-11-15 |  |  | CS | 2021-11-15 | [6 empty] | CS |  |  | 2021-11-15 |  |  | 2023-01-10 | [16 empty] | 2021-11-19 | 2021-11-19 | [8 empty] | 2021-11-23 | [11 empty] | 2022-01-28 | [6 empty] | 2022-01-21 | [8 empty] | 2022-01-21 | [17 empty] | 2022-01-25 | [7 empty] | 2022-01-25 | [7 empty] | 2022-01-31 | 2022-01-28 | 2022-01-31 |  | 2022-01-31 | [6 empty] | 182002 | 2022-01-10 | n/a | n/a | 2023-01-18 | 2020-04-17: 2021-12-21; 2020-04-17: 2022-02-01; 2021-07-07: 2022-05-26 | [15 empty] | Requested | [11 empty] | TRUE | TRUE | 346 | 2021-12-21 | 2021-12-21 | 2021 | 2022 | 2022 |  |  | 44589
347 |  | Eben Snow | Brent Brooks | 2020-02-07 | [31 empty] | 5 - OXFO |  | 437D1 | 199 |  | WITHDRAWN | WITHDRAWN |  | Mike Lucini | ISM Solar Development LLC | ISM SOLAR | Main St Oxford Me | 2000141835 | 30012062680 | Solar | [7 empty] | Main Street |  |  | Oxford |  | OXFORD | 437D1 |  |  | 9310-L0178-4420-0075-ED00102 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2020-02-14 | 2020-02-24 |  |  |  |  | 1900-01-12 | [57 empty] | Pending | [69 empty] | 2020-05-27 | [37 empty] | TRUE | TRUE | 347 | 0 | 0 | 1900 | #VALUE! | #VALUE!
348 |  | Lanie Patterson | Brent Brooks | 2020-02-07 | [31 empty] | 4 - WINT |  | 256D1 | 310 |  | WITHDRAWN | WITHDRAWN |  | Mike Lucini | ISM Solar Development LLC | ISM SOLAR DEVELOPMENT LLC | 87 Winthrop Center Road, Winslow 04 | 2000119678 | 30012108780 | Solar | [7 empty] | 87 Winthrop Center Rd |  |  | Winthrop |  | WINTHROP | 256D1 |  |  | 9310-L0095-6450-0177-ED00128 (NEEDS TO BE CONFIRMED WITH DEVELOPER) | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2020-02-14 | 2020-02-24 |  |  |  |  | 1900-01-12 | [57 empty] | No Study | [69 empty] | 2020-07-29 | [37 empty] | TRUE | TRUE | 348 | 0 | 0 | 1900 | #VALUE! | #VALUE!
349 |  | Rigel Paradise | Rick Duperre | 2020-02-07 | [31 empty] | 4 - LIME | 3 - LIME | 632D1 | 139 |  | EXECUTED | EXECUTED |  | David Shaffer | Novel Energy Solutions LLC | 549 Doles Ridge Rd Solar LLC | 549 Doles Ridge Rd Limerick | 2000285111 | 30014040858 | Solar | 4998 | 4.998 | 7492.5 |  |  | 45.5002 | -69.2513 | 549 Doles Ridge Rd |  |  | Limerick | 4 | LIMERICK | 632D1 | 632T1 |  | 9310-L0263-3260-0028-ED00014 | FERC | COST SHARE | COST SHARE (325,000) | 179586 | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2020-02-12 | 2020-02-14 | 2020-02-24 | 2020-02-12 | 2020-02-19 | 2020-05-15 |  | 2020-06-01 |  | 2020-05-15 | 2020-05-15 | 2020-06-01 |  |  | 2020-05-28 |  |  | CS | 2020-05-28 | [6 empty] | CS |  |  | 2020-05-28 | [11 empty] | 2020-05-20 | [17 empty] | 2020-06-09 | [6 empty] | Pending |  |  |  |  | 2020-08-12 |  |  | 2021-05-25 | Addendum |  |  | 2020-08-11 | [8 empty] | 2020-08-11 | [17 empty] | 2020-08-13 | [13 empty] | 2021-06-02 |  | 2021-06-04 |  | 2020-08-31 | 2023-02-13 |  |  | 2023-07-03 | 2023-07-11 |  |  |  | 403767 | 2020-08-02 | 1278004 | 2023-02-09 |  | 2020-04-17: 2020-09-04; 2020-04-17: 2020-09-04; 2021-07-07: 2021-10-20; 2021-07-07: 2021-10-27 | 2023-09-26 | 2023-09-26 | [9 empty] | Q2 2021 |  |  |  | 10300709075 | [11 empty] | TRUE | TRUE | 349 | 2020-09-04 | 2020-09-04 | 2020 | 2020 | 2020 | 44349 |  |  | 2021-05-25 | Addendum
350 |  | Lanie Patterson | Brent Brooks | 2020-02-12 | 2022-12-01 | L2_bump |  | 2023-05-21 | L2_bump |  | 2023-10-06 | L2_bump |  | 2023-01-05 | L2_bump | [20 empty] | 4 - MANC | 1 - MANC | 233D2 | 257 | Yes | EXECUTED | EXECUTED |  | Payne Morgan | Encore Redevelopment, LLC | ER Carlton Road Solar, LLC | 35 Carlton Rd Winthrop | 2000134579 | 30015965939 | Solar | 995 | 0.995 | 1380 |  |  | 44.324 | -69.9084 | 35 Carlton Road |  |  | Winthrop | 7 | MANCHESTER | 233D2 | 233T1 | 12.47 | 9310-L0064-6450-0001-ED00025 | Non-FERC | COST SHARING | COST SHARING (325,000) | 43313 | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2020-02-18 | 2020-02-20 | 2020-02-27 | 2020-02-18 | 2020-02-24 | 2020-11-20 |  | 2020-12-08 |  | 2020-11-20 | 2020-11-20 | 2020-12-08 |  |  | 2020-12-07 | 2021-07-27 |  | CS | 2020-12-07 | RS | 2021-07-27 | RS | 2024-05-03 |  |  | CS |  |  | 2020-12-07 | 2024-05-07 |  | 2022-12-22 | 2023-05-22 | 2023-10-10 | 2024-02-14 |  |  | 2024-05-03 | [5 empty] | 2023-01-26 | 2023-06-05 | 2023-10-27 | 2024-01-29 |  |  |  | 2024-06-06 |  | 2023-01-26 |  | 2023-10-23 | 2024-02-14 |  |  | 2020-12-18 | 2024-06-06 |  | 2023-01-26 | 2023-06-14 | 2023-10-27 | 2024-02-14 | [5 empty] | 2021-02-25 | 2024-07-22 |  | 2021-06-11 | Report |  |  | 2021-06-11 | 2024-07-24 | 2024-07-19 |  | 2023-07-20 | 2023-12-13 | 2024-04-19 |  |  | 2021-06-11 | 2024-07-24 |  |  | 2023-07-20 | 2023-12-13 | 2024-04-19 |  |  |  | 2024-07-30 |  | 2023-03-28 | [5 empty] | 2021-06-22 | 2024-07-31 |  | 2023-03-30 |  |  |  |  | 2021-06-22 | 2024-07-31 | [6 empty] | 2021-11-15 |  | 2021-11-24 | 2023-04-24 |  | 2023-04-25 | [5 empty] | 243943 | 2021-08-21 | 298703 | 2024-07-19 |  | 2021-11-24 | 2021-12-28 | 2023-04-25 | 2023-04-25 | 2023-09-19 | 2023-09-19 | 2024-09-20 | 2024-09-20 | [13 empty] | Q4 2025 |  |  |  | Requested | [11 empty] | TRUE | TRUE | 350 | 2021-11-24 | 2021-11-24 | 2021 | 2021 | 2021 |  |  |  | 2021-06-11 | Report
351 |  | Lanie Patterson | Brent Brooks | 2020-02-14 | [31 empty] | 3 - NOAU |  | 272D4 | 316 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Xander Neve | Syncarpha Solar LLC | SYNCARPHA SOLAR LLC | Leighton Rd (Augusta) | 2000146361 | 30012129992 | Solar | [5 empty] | 44.3278 | -69.8208 | Leighton Rd |  |  | Augusta | 17 | NORTH AUGUSTA | 272D4 | 272T1 |  |  | Non-FERC | WITHDRAWN | WITHDRAWN | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2020-02-20 | 2020-02-24 | 2020-03-02 | 2020-02-20 | 2020-02-28 | 2020-11-12 |  | 2020-11-30 |  | 2020-11-12 | 2020-11-13 | 2020-12-01 |  |  | 2020-11-24 |  |  | CS | 2020-11-24 | [6 empty] | CS |  |  | 2020-11-24 | [29 empty] | 2020-12-08 | [11 empty] | 2021-02-12 |  |  | 2021-05-10 | Addendum |  |  | 2021-02-12 | [8 empty] | 2021-02-22 | [17 empty] | 2021-03-01 | [13 empty] | 2021-06-02 |  | 2021-07-26 | 2021-07-26 | 2021-06-02 | 2022-12-05 |  | 2022-12-05 | [5 empty] | 692821 | 2022-05-09 | 824039 | 2022-12-05 | 2024-11-06 | 2021-11-24: 2021-07-01; 2021-12-28: 2021-07-01 | [17 empty] | 10300810935 | [11 empty] | TRUE | TRUE | 351 | 2021-07-01 | 2021-07-01 | 2021 | 2021 | 2021 | 44349 |  | 44403 | 2021-05-10 | Addendum
352 |  | Lanie Patterson | Brent Brooks | 2020-02-14 | 2024-01-26 | L2_bump | [29 empty] | 3 - COMR |  | 230D1 | 311 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Xander Neve | Syncarpha Solar LLC | SYNCARPHA SOLAR LLC | Ridge Rd (Windsor) | 2000146361 | 30012130206 | Solar | [5 empty] | 44.2794 | -69.5958 | Ridge Rd |  |  | Windsor | 72 | COOPERS MILLS ROAD | 230D1 | 230T2 |  | 9310-L0474-6400-0045-ED00042 (NEEDS TO BE CONFIRMED WITH DEVELOPER) | Non-FERC | WITHDRAWN | WITHDRAWN | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2020-02-20 | 2020-02-24 | 2020-03-02 | 2020-02-20 | 2020-02-28 | 2020-12-07 |  | 2020-12-21 |  | 2020-12-07 | 2020-12-07 | 2020-12-21 |  |  | 2020-12-21 |  |  | CS | 2020-12-15 | [6 empty] | CS |  |  | 2020-12-15 |  |  | 2024-02-06 | [11 empty] | 2024-03-04 | [8 empty] | 2024-03-26 | [5 empty] | 2021-01-04 |  |  | 2024-03-27 | [8 empty] | 2021-03-10 |  |  | 2021-05-26 | Report |  |  | 2021-05-26 |  |  | 2024-05-28 | [5 empty] | 2021-05-26 |  |  | 2024-05-28 | [8 empty] | 2024-05-31 | [5 empty] | 2021-06-07 |  |  | 2024-06-05 |  |  |  |  | 2021-06-07 |  |  | 2024-06-05 |  |  | 2021-06-07 |  | 2021-07-27 |  | 2021-07-27 | 2022-09-29 |  | 2022-10-31 | [5 empty] | 681828 |  | 1006067 | 2024-05-28 | 2024-08-20 | 2021-11-24: 2021-07-01; 2021-12-28: 2021-07-01 | [17 empty] | 10300810935 | [11 empty] | TRUE | TRUE | 352 | 2021-07-01 | 2021-07-01 | 2021 | 2021 | 2021 | 44354 |  |  | 2021-05-26 | Report
353 |  | Lanie Patterson | Brent Brooks | 2020-02-14 | [31 empty] | 2 - SIDN |  | 242D1 | 275 |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2021-01-04 | Abby Broedlin | Nautilus US Power Holdco, LLC | Casco Sidney Solar LLC | Lyons Rd, Sidney Me | 2000146048 | 30012125990 | Solar | 1500 | 1.5 | 2308 |  |  | 44.4519 | -69.7258 | Lyons Rd |  |  | Sidney | 13 | SIDNEY | 242D1 | 242T1 |  | 9310-L0076-5320-0028-ED00006 | Non-FERC | TRIGGERING | TRIGGERING (325,000) | 325000 | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2020-02-21 | 2020-02-24 | 2020-03-02 | 2020-02-21 | 2020-02-28 | 2020-07-01 |  | 2020-07-16 |  | 2020-07-01 | 2020-07-02 | 2020-07-17 |  |  | 2020-07-02 |  |  | CS | 2020-07-02 | [6 empty] | CS |  |  | 2020-07-02 | [11 empty] | 2020-07-13 | [17 empty] | 2020-07-06 | [6 empty] | Pending |  |  |  |  | 2020-09-08 |  |  | 2021-06-14 | Addendum |  |  | 2020-09-08 | [8 empty] | 2020-09-09 | [17 empty] | 2020-09-14 | [15 empty] | 2020-11-19 |  | 2020-11-19 | [13 empty] | 2021-11-24: 2020-12-08; 2021-12-28: 2020-12-08; 2023-04-25: 2021-07-12; 2023-04-25: 2021-07-12 | [13 empty] | Q1 2021 |  |  |  | 10300740965 | [11 empty] | TRUE | TRUE | 353 | 2020-12-08 | 2020-12-08 | 2020 | 2020 | 2020 |  |  |  | 2021-06-14 | Addendum
354 |  | Eben Snow | Brent Brooks | 2020-02-19 | [31 empty] | 3 - R115 |  | 445D2 | 253 |  | WITHDRAWN | WITHDRAWN |  | David Kane | LongRoad Development Company LLC | LONGROAD DEVELOPMENT COMPANY LLC | Poland Spring Rd Casco | 2000118100 | 30012066566 | Solar | [7 empty] | Poland Springs Rd |  |  | Casco |  | RAYMOND 115 KV | 445D2 |  |  | 9310-L0185-1060-0065-ED00162 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2020-02-26 | 2020-03-04 |  |  |  |  | 1900-01-12 | [57 empty] | No Study | [69 empty] | 2020-07-10 | [37 empty] | TRUE | TRUE | 354 | 0 | 0 | 1900 | #VALUE! | #VALUE!
355 |  | Ben Brooks | Anthony Boucher | 2020-02-19 | 2022-05-27 | L2_Bump | [29 empty] | 1 - B115 |  | 874D1 |  | Yes | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED |  | Jonovan (Jonny) Lizama | Luminace | Shining Solar Partners, LLC | 51 Back Searsport Rd / Belfast Me 0 | 2000348732 | 30014894239 | Solar | 4999 | 4.999 | 8757 |  |  | 44.4537 | -68.993 | 51 Back Searsport Rd |  |  | Belfast | 17 | BELFAST 115 | 874D1 | 874T2 |  | 9310-L0458-0430-0007-ED00015 | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2020-02-24 | 2020-02-26 | 2020-03-04 | 2020-02-24 | 2020-02-24 | 2020-03-20 |  | 2020-04-03 |  | 2020-03-20 | 2020-03-23 | 2020-04-06 |  |  | 2020-04-06 |  |  | CS | 2020-04-06 | [6 empty] | CS |  |  | 2020-04-06 |  |  | 2022-08-23 | [8 empty] | 2020-04-24 |  |  | 2022-08-22 | [14 empty] | 2020-04-17 |  |  | 2022-08-23 |  |  |  | Pending |  |  |  |  | 2020-06-23 |  |  | 2021-05-17 | Addendum |  |  | 2020-06-19 |  |  | 2022-10-05 | [5 empty] | 2020-06-22 |  |  | 2022-10-05 | [14 empty] | 2020-06-29 | [13 empty] | 2021-05-20 |  | 2020-07-14 |  | 2020-07-14 | 2022-10-24 | 2022-11-01 |  | 2023-07-13 | 2023-07-13 |  |  |  | 636222 |  | 809771 | 2022-10-05 |  | 2020-07-15 | 2020-07-15 | 2021-06-24 | 2021-06-24 | 2022-11-02 | 2022-11-03 | 2023-05-30 | 2023-05-30 |  |  | 2023-08-11 | [10 empty] | Q4 2021 |  |  |  | 10300690792 | [11 empty] | TRUE | TRUE | 355 | 2020-07-15 | 2020-07-15 | 2020 | 2020 | 2020 | 44336 |  |  | 2021-05-17 | Addendum
356 |  | Govinda Neupane |  | 2020-02-19 | [31 empty] | 9 - STUR |  | 858D4 | 340 |  | WITHDRAWN | WITHDRAWN |  | Nate Niles | REVISION ENERGY INC | REVISION ENERGY INC | 416 Bailey Hill Rd Farmington | 2000038393 | 30012128986 | Solar | [5 empty] | 44.6723 | -70.1206 | 416 Bailey Hill Rd |  |  | Farmington |  | STURTEVANT | 858D4 |  |  | 9310-L0441-2030-0164-ED00089 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2020-02-26 | 2020-03-04 | 2020-02-24 | 2020-02-28 |  |  | 1900-01-12 | [57 empty] | No Study | [69 empty] | 2022-01-06 | [25 empty] | NO STUDY | [11 empty] | TRUE | TRUE | 356 | 0 | 0 | 1900 | 1900 | 1900
357 |  | Marshall Ripley | Rick Duperre | 2020-02-20 | [31 empty] | 1 - ELM |  | 620D1 |  |  | WITHDRAWN | WITHDRAWN |  | Jeff Potter | Renewable Energy International LLC | RENEWABLE ENERGY INTERNATIONAL LLC | 0 Gray Rd Cumberland | 2000142998 | 30012080518 | Solar/Battery | [7 empty] | 0 Gray Rd |  |  | Cumberland |  | ELM STREET | 620D1 |  |  | 9310-L0235-1280-0026-ED00034 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2020-02-27 | 2020-03-05 |  |  |  |  | 1900-01-12 | [57 empty] | Pending | [69 empty] | 2020-04-28 | [37 empty] | TRUE | TRUE | 357 | 0 | 0 | 1900 | #VALUE! | #VALUE!
358 |  |  | Anthony Boucher | 2020-02-21 | [31 empty] | 2 - BEWE |  | 803D3 | 174 |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED |  | Zach Schrowang | Syncarpha Solar LLC | BELFAST SOLAR 1 LLC | 205 Northport Rd Belfast | 2000146327 | 30012129638 | Solar | 3500 | 3.5 | 4557.6 |  |  | 44.4047 | -69.0039 | 205 North Port Rd |  |  | Belfast | 510 | BELFAST WEST SIDE | 803D3 | 803T2 |  | 9310-L0380-0430-0035-ED00065 | FERC | NOT IMPACTED | NOT IMPACTED | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2020-02-26 | 2020-02-28 | 2020-03-06 | 2020-02-26 | 2020-03-06 | 2020-05-11 |  | 2020-05-26 |  | 2020-05-11 | 2020-05-11 | 2020-05-26 |  |  | 2020-05-26 | 2020-09-15 |  | CS | 2020-05-27 | RS | 2020-09-15 |  |  |  |  | CS |  |  | 2020-05-27 | 2020-09-15 | [10 empty] | 2020-06-01 | [17 empty] | 2020-06-09 | 2020-09-24 | [5 empty] | Pending |  |  |  |  | 2020-08-12 | 2020-11-06 | [5 empty] | 2020-08-12 | 2020-11-09 | [7 empty] | 2020-08-12 | 2020-11-05 | [16 empty] | 2020-08-17 | 2020-11-10 | [14 empty] | 2020-11-10 | 2021-08-06 | 2020-11-11 | 2022-11-03 |  | 2022-12-02 | 2023-07-14 | 2023-07-14 |  |  |  | 115041 | 2022-10-29 | 202754 | 2022-10-29 |  | 2020-11-14 | 2020-11-14 | 2021-08-09 | 2021-08-09 | 2022-12-05 | 2022-12-05 |  |  |  |  | 2023-07-20 | 2023-07-26 | [9 empty] | Q4 2020 |  |  |  | 10300735458 | [11 empty] | TRUE | TRUE | 358 | 2020-11-14 | 2020-11-14 | 2020 | 2020 | 2020 |  |  | 44414
359 |  |  | KRISTOFER COLEMAN | 2020-02-21 | 2023-10-13 | L2_Bump | [29 empty] | 2 - DAMS |  | 219D1 | 266 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Xander Neve | Syncarpha Solar LLC | DAMARISCOTTA SOLAR 1 LLC | Us Rte 1 Damariscotta | 2000146350 | 30012129661 | Solar | [5 empty] | 44.0425 | -69.5214 | US Route 1 |  |  | Damariscotta | 84 | DAMARISCOTTA MILLS | 219D1 | 219T1 | 12.47 | 9310-L0050-1520-0003-ED00001 | FERC | WITHDRAWN | WITHDRAWN | 325000 | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2020-02-26 | 2020-02-28 | 2020-03-06 | 2020-02-26 | 2020-03-06 | 2020-07-16 |  | 2020-07-30 |  | 2020-07-16 | 2020-07-16 | 2020-07-30 |  |  | 2020-07-27 |  |  | CS | 2020-07-27 | [6 empty] | CS |  |  | 2020-07-27 |  |  | 2023-10-16 | 2024-03-01 | [7 empty] | 2020-08-03 |  |  | 2023-11-22 | 2023-11-22 | [13 empty] | 2020-08-05 |  |  | 2024-03-14 |  |  |  | Pending |  |  |  |  | 2020-10-08 |  |  | 2021-06-14 | Addendum |  |  | 2020-10-06 |  |  | 2024-05-16 | [5 empty] | 2020-10-08 |  |  | 2024-05-16 | [8 empty] | 2024-05-16 | [5 empty] | 2020-10-19 |  |  | 2024-05-20 | [7 empty] | 2024-05-20 |  |  | 2021-06-17 |  | 2020-11-04 |  | 2020-11-04 | 2022-11-15 | 2022-12-02 |  | 2024-08-23 | 2024-08-23 |  |  |  | 485907 | 2021-06-10 | 688787 | 2024-05-13 | 2024-12-03 | 2020-11-12 | 2020-11-12 | 2021-07-27 | 2021-07-27 | 2022-12-05 | 2022-12-05 | 2024-06-12 | 2024-06-12 | [17 empty] | 10300735569 | [11 empty] | TRUE | TRUE | 359 | 2020-11-12 | 2020-11-12 | 2020 | 2020 | 2020 | 44364 |  |  | 2021-06-14 | Addendum
360 |  | Lanie Patterson | Brent Brooks | 2020-02-24 | [31 empty] | 3 - SOWA |  | 855D2 | 254 |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2021-12-17 | William Boyle <wboyle@cleantapenergy.com> | CleanTap Energy,LLC | Waterville Solar, LLC | Eight Rod Rd | 2000146666 | 30012742190 | Solar | 3500 | 3.5 | 5419 |  |  | 44.5146 | -69.6742 | EIGHT ROD RD |  |  | Waterville | 12 | SOUTH WATERVILLE | 855D2 | 855T1 |  | 9310-SS0855 | Non-FERC | COST SHARE | COST SHARE ($325,000) | 208715.6 | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2020-03-02 | 2020-03-02 | 2020-03-09 | 2020-03-02 | 2020-03-09 | 2020-06-11 |  | 2020-06-25 |  | 2020-06-11 | 2020-06-11 | 2020-06-25 |  |  | 2020-06-25 |  |  | CS | 2020-07-10 | [6 empty] | CS |  |  | 2020-07-10 | [11 empty] | 2020-07-21 | [17 empty] | 2020-07-24 | [6 empty] | Pending |  |  |  |  | 2020-09-28 |  |  | 2021-06-08 | Addendum |  |  | 2020-09-28 | [8 empty] | 2020-10-07 | [17 empty] | 2020-10-15 | [15 empty] | 2020-10-15 |  | 2020-10-16 | [8 empty] | 414766 |  |  |  |  | 2021-11-24: 2020-10-20; 2021-12-28: 2020-10-20; 2023-04-25: 2021-08-23; 2023-04-25: 2021-08-23 | [17 empty] | 10300727149 | [11 empty] | TRUE | TRUE | 360 | 2020-10-20 | 2020-10-20 | 2020 | 2020 | 2020 |  |  |  | 2021-06-08 | Addendum
361 |  | Rigel Paradise | Rick Duperre | 2020-02-24 | [31 empty] | 5 - BASS |  | 602D3 | 330 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN | 2022-06-27 | William Boyle <wboyle@cleantapenergy.com> | CleanTap Energy,LLC | SOUTH BERWICK SOLAR LLC | Agamenticus Road Solar Aray | 2000205594 | 30012964125 | Solar/Battery | [5 empty] | 43.2362 | -70.1311 | Agamenticus Rd |  |  | South Berwick | 5 | BASSETT | 602D3 | 602T1 |  | 9310-L0212-5410-0095-ED00010 | Non-FERC | WITHDRAWN | WITHDRAWN | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2020-03-02 | 2020-03-02 | 2020-03-09 | 2020-03-02 | 2020-03-06 | 2020-09-16 |  | 2020-09-30 |  | 2020-09-16 | 2020-09-25 | 2020-10-09 |  |  | 2020-10-09 |  |  | CS | 2020-10-12 | [6 empty] | CS |  |  | 2020-10-12 | [29 empty] | 2020-10-21 | [6 empty] | Pending |  |  |  |  | 2020-12-28 |  |  | 2021-07-08 | Addendum |  |  | 2020-12-29 | [8 empty] | 2020-12-29 | [17 empty] | 2021-01-04 | [5 empty] | 2021-01-04 | [7 empty] | 2021-07-20 | 2022-06-15 | 2021-01-22 | 2021-08-09 | [13 empty] | 2022-08-16 | 2021-11-24: 2021-02-18; 2021-12-28: 2021-02-18; 2023-04-25: 2021-08-09; 2023-04-25: 2021-08-09 | [17 empty] | 10300758895 | [11 empty] | TRUE | TRUE | 361 | 2021-02-18 | 2021-02-18 | 2021 | 2021 | 2021 | 44397 |  | 44417 | 2021-07-08 | Addendum
362 |  | Rigel Paradise | Rick Duperre | 2020-02-25 | [31 empty] | 4 - WATE |  | 671D2 | 342 |  | WITHDRAWN | WITHDRAWN |  | Nate Niles | REVISION ENERGY INC | REVISION ENERGY INC | 31 Pole Line Ln (Waterboro) | 2000038393 | 30012143548 | Solar | [5 empty] | 43.5389 | -70.7205 | 31 Pole Line Lane |  |  | Waterboro |  | WATERBORO | 671D2 |  |  | 9310-L0342-6190-0372-ED00004 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2020-03-03 | 2020-03-10 |  |  |  |  | 1900-01-12 | [57 empty] | No Study | [69 empty] | 2021-07-12 | [37 empty] | TRUE | TRUE | 362 | 0 | 0 | 1900 | #VALUE! | #VALUE!
363 |  | Lanie Patterson | Brent Brooks | 2020-02-25 | [31 empty] | 4 - COMR |  | 230D1 | 352 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Nate Niles | REVISION ENERGY INC | REVISION ENERGY INC | Pitt Rd Windsor Me | 2000038393 | 30012145923 | Solar | [5 empty] | 44.3163 | -69.5909 | Pitt Rd |  |  | Windsor | 7 | COOPERS MILLS ROAD | 230D1 | 230T2 |  | 9310-L0474-6400-0003-ED00007 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2020-03-03 | 2020-03-03 | 2020-03-10 | 2020-03-03 | 2020-03-06 | 2021-07-28 |  | 2021-08-11 |  | 2021-08-26 | 2021-08-26 | 2021-09-10 |  |  | 2021-09-09 |  |  | CS | 2021-09-09 | [6 empty] | CS |  |  | 2021-09-09 | [29 empty] | 2021-09-22 | [11 empty] | 2021-11-29 | [6 empty] | 2021-11-12 | [8 empty] | 2021-11-17 | [7 empty] | 2021-11-17 | [9 empty] | 2021-11-22 | [7 empty] | 2021-11-22 | [22 empty] | 2023-11-28 | 2021-11-24: 2021-12-13; 2021-12-28: 2021-12-21 | [17 empty] | Requested | [11 empty] | TRUE | TRUE | 363 | 2021-12-13 | 2021-12-13 | 2021 | 2021 | 2021
364 |  | Marshall Ripley | Rick Duperre | 2020-02-25 | [31 empty] | 7 - BONE |  | 610D2 | 91 |  | WITHDRAWN | WITHDRAWN |  | Jason Parise | SWEB Development | SWEB DEVELOPMENT USA LLC | Long Plains Rd Buxton | 2000145274 | 30012114309 | Solar | [5 empty] | 43.6488 | -70.5417 | Long Plains Rd |  |  | Buxton |  | BONNY EAGLE | 610D2 |  |  | 9310-L0221-0820-0045-ED00277 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2020-03-03 | 2020-03-10 |  |  |  |  | 1900-01-12 | [57 empty] | No Study | [69 empty] | 2021-09-22 | [37 empty] | TRUE | TRUE | 364 | 0 | 0 | 1900 | #VALUE! | #VALUE!
365 |  | Govinda Neupane |  | 2020-02-25 | [31 empty] | 1 - LOMS |  | 429D1 |  |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2020-08-31 | Liam McCormack | National Renewable Solutions LLC (Summit Ridge Energy) | NRS BETHEL SOLAR LLC (an SRE project) | Walkers Mills Rd Lot 31 Bethel | 2000163962 | 30012402621 | Solar | 2997 | 2.997 | 3744 |  |  | 44.4079 | -70.72 | Walkers Mill Rd |  |  | Bethel | 24 | LOCKES MILLS | 429D1 | 429T1 |  |  | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2020-03-03 | 2020-03-03 | 2020-03-10 | 2020-03-03 | 2020-03-03 | 2020-03-27 |  | 2020-04-10 |  | 2020-03-27 | 2020-03-27 | 2020-04-10 |  |  | 2020-03-31 |  |  | CS | 2020-03-31 | [6 empty] | CS |  |  | 2020-03-31 | [11 empty] | 2020-04-02 | [17 empty] | 2020-04-15 | [6 empty] | Pending |  |  |  |  | 2020-06-19 |  |  | 2021-05-20 | Addendum |  |  | 2020-06-19 | [8 empty] | 2020-06-11 | [17 empty] | 2020-06-17 | [13 empty] | 2021-06-14 |  | 2020-06-17 |  | 2020-06-18 | [8 empty] | 378060 |  |  |  |  | 2021-11-24: 2020-07-01; 2021-12-28: 2020-07-01; 2023-04-25: 2021-09-14; 2023-04-25: 2021-09-22 | [13 empty] | Q4 2021 |  |  |  | 10300682228 | [11 empty] | TRUE | TRUE | 365 | 2020-07-01 | 2020-07-01 | 2020 | 2020 | 2020 | 44361 |  |  | 2021-05-20 | Addendum
366 |  |  | KRISTOFER COLEMAN | 2020-02-28 | [31 empty] | 1 - EDGE |  | 223D1 |  |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2020-08-31 | Zach Schrowang | Syncarpha Solar LLC | EDGECOMB SOLAR 1 LLC | 17 A Dodge Rd / Edgecomb Me 04556 | 2000146328 | 30012129653 | Solar | 4950 | 4.95 | 6790 |  |  | 44.0017 | -69.6153 | 17A Dodge Rd |  |  | Edgecomb | 12 | EDGECOMB | 223D1 | 223T1 |  | 9310-L0052-1810-0001-ED00023 | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2020-03-04 | 2020-03-06 | 2020-03-13 | 2020-03-04 | 2020-03-04 | 2020-03-26 |  | 2020-04-09 |  | 2020-03-26 | 2020-03-26 | 2020-04-09 |  |  | 2020-04-09 |  |  | CS | 2020-04-09 | [6 empty] | CS |  |  | 2020-04-09 | [11 empty] | 2020-04-10 | [17 empty] | 2020-04-14 | [6 empty] | Pending |  |  |  |  | 2020-06-18 |  |  | 2021-06-03 | Addendum |  |  | 2020-06-18 | [8 empty] | 2020-06-19 | [17 empty] | 2020-06-25 | [13 empty] | 2021-06-14 |  | 2020-07-10 |  | 2020-07-13 | [8 empty] | 218278 | 2020-06-18 | 281615 | 2021-06-03 |  | 2021-11-24: 2020-07-21; 2021-12-28: 2020-07-21; 2023-04-25: 2021-07-12; 2023-04-25: 2021-07-12 | [17 empty] | 10300690799 | [11 empty] | TRUE | TRUE | 366 | 2020-07-21 | 2020-07-21 | 2020 | 2020 | 2020 | 44361 |  |  | 2021-06-03 | Addendum
367 |  | Ben Brooks | Anthony Boucher | 2020-02-28 | [31 empty] | 2 - B115 |  | 874D1 | 355 |  | WITHDRAWN | WITHDRAWN |  | David Kane | LongRoad Development Company LLC | LONGROAD DEVELOPMENT COMPANY LLC | 104 Waterville Rd Belfast | 2000118100 | 30012138761 | Solar | [7 empty] | 104 Waterville Rd |  |  | Belfast |  | BELFAST 115 | 874D1 |  |  | 9310-L0458-0430-0173-ED00037 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2020-03-06 | 2020-03-13 |  |  |  |  | 1900-01-12 | [57 empty] | No Study | [69 empty] | 2020-07-16 | [37 empty] | TRUE | TRUE | 367 | 0 | 0 | 1900 | #VALUE! | #VALUE!
368 |  |  | Anthony Boucher | 2020-02-28 | [31 empty] | 3 - BEWE |  | 803D6 | 358 |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED |  | Kacy Tucker | Summit Ridge Energy | Belfast PV LLC | 234 Belmont Ave Belfast | 2000312823 | 30014424722 | Solar | 2475 | 2.475 | 3202.56 |  |  | 44.4122 | -69.0662 | 234 Belmont Ave |  |  | Belfast | 120 | BELFAST WEST SIDE | 803D6 | 34.5 kV Bus |  | 9310-L0383-0430-0013-ED00028 | FERC | NOT IMPACTED | NOT IMPACTED | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2020-03-06 | 2020-03-06 | 2020-03-13 | 2020-03-06 | 2020-03-12 | 2020-11-24 |  | 2020-12-10 |  | 2020-11-24 | 2020-11-24 | 2020-12-10 |  |  | 2020-12-02 |  |  | CS | 2020-12-02 | [6 empty] | CS |  |  | 2020-12-02 | [29 empty] | 2021-01-15 | [11 empty] | 2021-03-23 |  |  | 2021-06-28 | Report |  |  | 2021-06-28 | [8 empty] | 2021-06-28 | [17 empty] | 2021-07-01 | [5 empty] | 2021-07-01 | [9 empty] | 2021-07-07 | 2021-07-07 | 2021-07-07 |  |  |  | 2023-07-31 | 2023-07-31 | [8 empty] | 2021-11-24: 2021-07-07; 2021-12-28: 2021-07-07; 2023-04-25: 2022-07-11 |  |  | 2023-10-10 | 2023-10-10 | [9 empty] | Q3 2022 |  |  |  | Requested | [11 empty] | TRUE | TRUE | 368 | 2021-07-07 | 2021-07-07 | 2021 | 2021 | 2021 |  |  | 44384 | 2021-06-28 | Report
369 |  |  | Anthony Boucher | 2020-02-28 | [31 empty] | 4 - BEWE |  | 803D6 | 368 |  | WITHDRAWN | WITHDRAWN |  | Mike Lucini | ISM Solar Development LLC | ISM SOLAR | 185 Belmont Ave Solar Belfast | 2000141835 | 30012142730 | Solar | [5 empty] | 44.4164 | -69.0559 | 185 Belmont Ave |  |  | Belfast |  | BELFAST WEST SIDE | 803D6 |  |  | 9310-L0383-0430-0088-ED00005 | FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2020-03-06 | 2020-03-13 |  |  |  |  | 1900-01-12 | [127 empty] | 2021-08-26 | [37 empty] | TRUE | TRUE | 369 | 0 | 0 | 1900 | #VALUE! | #VALUE!
370 |  | Eben Snow | Brent Brooks | 2020-02-28 | 2023-06-06 | L2_Bump | [29 empty] | 6 - MEFA |  | 431D2 | 315 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Tiffiny Chase | ASPEN POWER PARTNERS | ME I MECHANIC FALLS NORTH LLC | 90 North St Mechanics Falls | 2000148487 | 30013260465 | Solar | [5 empty] | 44.1202 | -70.4022 | 90 North Street |  |  | Mechanic Falls | 16 | MECHANIC FALLS | 431D2 | 431T1 | 12.47 | 9310-L0166-3610-0041-ED00018 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2020-03-06 | 2020-03-06 | 2020-03-13 | 2020-03-06 | 2020-03-12 | 2021-03-31 |  | 2021-04-14 |  | 2021-03-31 | 2021-03-31 | 2021-04-14 |  |  | 2021-04-13 | 2021-08-16 |  | CS | 2021-04-13 | RS | 2021-08-16 |  |  |  |  | CS |  |  | 2021-04-13 | 2021-08-16 |  | 2024-04-26 | [26 empty] | 2021-04-27 | 2021-08-25 | [10 empty] | 2021-06-30 | 2021-10-07 |  | 2021-07-09 | Report |  |  | 2021-07-09 | 2021-10-05 | [7 empty] | 2021-07-09 | 2021-10-05 | [16 empty] | 2021-07-13 | [7 empty] | 2021-07-13 | [10 empty] | 2023-02-13 |  | 2023-02-14 | [5 empty] | 554137 |  | 852571 | 2023-02-13 | 2024-05-10 | 2021-10-12 | 2021-10-15 | 2022-10-11 | 2022-10-11 | 2023-02-17 | 2023-02-17 | [19 empty] | Requested | [11 empty] | TRUE | TRUE | 370 | 2021-10-12 | 2021-10-12 | 2021 | 2021 | 2021 |  |  |  | 2021-07-09 | Report
371 |  | Lanie Patterson | Brent Brooks | 2020-02-28 | [31 empty] | 5 - VASS |  | 861D9 | 346 |  | WITHDRAWN | WITHDRAWN |  | DV Patel | NEW ENGLAND SOLAR GARDEN CORP | 371 ME I Vassalboro Cemetery LLC | 109 Cemetery St Vassalboro | 2000148487 | 30012160906 | Solar | [5 empty] | 44.4713 | -69.6263 | 109 Cemetery Street |  |  | Vassalboro | 32 | VASSALBORO | 861D9 | 861T1 |  | FLOC-MISSING-01142021 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2020-03-05 | 2020-03-06 | 2020-03-13 | 2020-03-05 | 2020-03-12 | 2022-02-02 | 2022-02-04 | 2022-02-16 | 2022-02-04 | 2022-02-07 | 2022-02-07 | 2022-02-21 |  |  | 2022-02-08 | 2022-05-23 |  | CS | 2022-02-09 | RS | 2022-05-23 |  |  |  |  | CS |  |  | 2022-02-09 | 2022-05-23 | [10 empty] | 2022-02-24 | [7 empty] | 2022-02-14 | 2022-02-14 | [8 empty] | 2022-02-14 | 2022-05-31 | [10 empty] | 2022-04-20 | 2022-07-13 | [5 empty] | 2022-04-22 | [8 empty] | 2022-04-22 | [8 empty] | 2022-04-22 | [8 empty] | 2022-04-28 | [7 empty] | 2022-04-28 | [13 empty] | 2022-02-07 | 2022-02-14 |  |  |  | 4278888 | 2022-04-20 | 6968850 | 2022-06-28 | 2023-01-18 | [37 empty] | TRUE | TRUE | 371 | 0 | 0 | 1900 | 1900 | 1900 |  |  |  |  | 2022-05-25
372 |  | Rigel Paradise | Rick Duperre | 2020-02-28 | [31 empty] | 2 - BERW |  | 603D2 | 252 |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2020-08-31 | Tiffiny Chase | ASPEN POWER PARTNERS LLC | ME I Berwick Sophie’s Way LLC | 213 Rt 236 Berwick | 2000148487 | 30013411142 | Solar | 1750 | 1.75 | 2350 |  |  | 43.2476 | -70.8289 | 213 Route 236 |  |  | Berwick | 48 | BERWICK | 603D2 | 603T1 |  | 9310-L0214-0470-0147-ED00114 | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2020-03-05 | 2020-03-06 | 2020-03-13 | 2020-03-05 | 2020-03-12 | 2020-04-01 |  | 2020-04-15 |  | 2020-04-01 | 2020-04-06 | 2020-04-21 |  |  | 2020-04-08 |  |  | CS | 2020-04-08 | [6 empty] | CS |  |  | 2020-04-08 | [11 empty] | 2020-04-09 | [17 empty] | 2020-04-13 | [6 empty] | Pending |  |  |  |  | 2020-06-17 |  |  | 2021-06-21 | Addendum |  |  | 2020-06-16 | [8 empty] | 2020-06-08 | [17 empty] | 2020-06-15 | [15 empty] | 2020-06-22 |  | 2020-06-22 | [13 empty] | 2021-11-24: 2020-07-16; 2021-12-28: 2020-07-16; 2023-04-25: 2021-06-22; 2023-04-25: 2021-06-22 | [13 empty] | Q4 2020 |  |  | TBD | 10300687575 | [11 empty] | TRUE | TRUE | 372 | 2020-07-16 | 2020-07-16 | 2020 | 2020 | 2020 |  |  |  | 2021-06-21 14:36 | Addendum
373 |  | Govinda Neupane |  | 2020-02-28 | [31 empty] | 6 - LVFA |  | 428D3 | 307 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | DV Patel | ASPEN POWER PARTNERS | ME I Livermore Falls Pomeroy Hill LLC | 124 Pomeroy Hill Livermore Falls | 2000148487 | 30012160898 | Solar | [5 empty] | 44.4631 | -70.1623 | 124 Pomeroy Hill Road |  |  | Livermore Falls | 15 | LIVERMORE FALLS | 428D3 | 428T1 |  | FLOC-MISSING-01142021 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2020-03-06 | 2020-03-06 | 2020-03-13 | 2020-03-06 | 2020-03-12 | 2021-07-30 |  | 2021-08-13 |  | 2021-08-16 | 2021-08-16 | 2021-08-30 |  |  | 2021-08-19 |  |  | CS | 2021-08-24 | [6 empty] | CS |  |  | 2021-08-24 | [11 empty] | 2021-08-24 | [17 empty] | 2021-09-01 | [11 empty] | 2021-11-05 | [6 empty] | 2021-11-05 | [8 empty] | 2021-11-08 | [17 empty] | 2021-11-22 | [7 empty] | 2021-11-22 | [10 empty] | 2022-10-18 |  | 2022-10-18 | [9 empty] | 2024-05-10 | 2021-12-27 | 2021-12-30 | 2022-10-19 | 2022-10-19 | 2023-01-05 | 2023-01-06 | [19 empty] | Requested | [11 empty] | TRUE | TRUE | 373 | 2021-12-27 | 2021-12-27 | 2021 | 2021 | 2021
374 |  | Rigel Paradise | Rick Duperre | 2020-03-04 | [31 empty] | 2 - BUCO |  | 612D1 | 172 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN | 2022-06-27 | Peter Bay | EDF Renewables | EDF RENEWABLES | 14 Hazen Dr Springvale | 2000134214 | 30011961148 | Solar | [5 empty] | 43.46 | -70.8389 | 14 Hazen Drive |  |  | Springvale | 17 | BUTLER'S CORNER | 612D1 | 612T1 |  | 9310-L0225-5170-0031-ED00008 | Non-FERC | WITHDRAWN | WITHDRAWN | 325000 | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2020-03-09 | 2020-03-11 | 2020-03-18 | 2020-03-09 | 2020-03-18 | 2020-06-19 |  | 2020-07-06 |  | 2020-06-19 | 2020-06-19 | 2020-07-06 |  |  | 2020-07-06 |  |  | CS | 2020-07-06 | [6 empty] | CS |  |  | 2020-07-06 | [11 empty] | 2020-07-10 | [17 empty] | 2020-07-07 | [6 empty] | Pending |  |  |  |  | 2020-09-09 |  |  | 2021-06-14 | Addendum |  |  | 2020-09-09 | [8 empty] | 2020-09-08 | [17 empty] | 2020-09-09 | [14 empty] | 2022-06-14 | 2020-09-22 |  | 2020-09-24 | [12 empty] | 2023-10-13 | 2021-11-24: 2020-10-06; 2021-12-28: 2020-10-06; 2023-04-25: 2021-06-16; 2023-04-25: 2021-06-16 | [17 empty] | 10300721166 | [11 empty] | TRUE | TRUE | 374 | 2020-10-06 | 2020-10-06 | 2020 | 2020 | 2020 |  |  |  | 2021-06-14 | Addendum
375 |  | Govinda Neupane |  | 2020-03-04 | [31 empty] | 2 - BNHE |  | 120D1 | 87 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Nick Mazuroski | Dirigo/BNRG | BD SOLAR HAMPDEN LLC | 5 Old Coldbrook Rd Hampden | 2000146825 | 30012136385 | Solar | [5 empty] | 44.7694 | -68.8575 | 5 Old ColdBrook Rd |  |  | Hampden | 60 | BANGOR HYDRO (Versant) | 120D1 | Not Applicable | 12.47 | FLOC-MISSING-01142021 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2020-03-09 | 2020-03-11 | 2020-03-18 | 2020-03-09 | 2020-03-18 | 2021-12-03 | 2021-12-03 | 1900-01-12 | 2021-12-03 | 2021-12-08 | 2021-12-08 | 2021-12-20 |  |  | 2021-12-20 |  |  | CS | 2021-12-21 | [6 empty] | CS |  |  | 2021-12-21 | [20 empty] | 2022-01-04 | [8 empty] | 2022-01-04 | [11 empty] | 2022-03-10 | [6 empty] | 2022-03-10 | [8 empty] | 2022-03-10 | [8 empty] | 2022-03-14 | [8 empty] | 2022-03-15 | 2022-06-21 | [6 empty] | 2022-03-15 | 2022-06-21 | [6 empty] | 2022-09-22 |  | 2022-09-22 | 2023-04-11 | 2022-12-20 | 2023-04-11 | [5 empty] | 949733 | 2022-11-01 |  |  | 2024-09-06 | 2021-11-24: 2023-01-03; 2021-12-28: 2023-01-06; 2023-04-25: 2023-04-27; 2023-04-25: 2023-04-28 | [29 empty] | TRUE | TRUE | 375 | 2023-01-03 | 2023-01-03 | 2023 | 2023 | 2023 |  |  |  |  | 2022-03-15
376 |  |  | KRISTOFER COLEMAN | 2020-03-04 | [31 empty] | 2 - BRWE |  | 213D1 |  |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2020-10-05 | Rennie Friedman | SOL ALLIANCE DEVELOPMENT LLC | SCS HARPSWELL 012903 BRUNSWICK LLC | Harpswell Rd, Brunswick | 2000174265 | 30012548258 | Solar | 4999 | 4.999 | 6387.68 |  |  | 43.8983 | -69.9494 | Harpswell Road |  |  | Brunswick | 5 | BRUNSWICK WEST SIDE | 213D1 | 213T1 |  | 9310-L0030-0770-0138-ED00118 | Non-FERC | TRIGGERING | TRIGGERING | 325000 | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2020-03-09 | 2020-03-11 | 2020-03-18 | 2020-03-09 | 2020-03-18 | 2020-04-30 |  | 2020-05-14 |  | 2020-04-30 | 2020-04-30 | 2020-05-14 |  |  | 2020-05-01 |  |  | CS | 2020-05-01 | [6 empty] | CS |  |  | 2020-05-01 | 2022-07-21 | [10 empty] | 2020-05-14 | [17 empty] | 2020-05-15 | [6 empty] | Pending |  |  |  |  | 2020-07-21 | 2022-08-17 |  | 2021-06-03 | Addendum |  |  | 2020-07-21 | [8 empty] | 2020-07-21 | [17 empty] | 2020-07-27 | [15 empty] | 2020-07-29 |  | 2020-07-29 | [8 empty] | 378908 |  |  |  |  | 2021-11-24: 2020-08-20; 2021-12-28: 2020-08-20; 2023-04-25: 2021-07-08; 2023-04-25: 2021-07-08 | [17 empty] | 10300703532 | [11 empty] | TRUE | TRUE | 376 | 2020-08-20 | 2020-08-20 | 2020 | 2020 | 2020 |  |  |  | 2021-06-03 | Addendum
377 |  | Lanie Patterson | Brent Brooks | 2020-03-06 | 2022-08-16 | L2_Bump | [29 empty] | 2 - BOST |  | 263D1 | 213 | Yes | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2021-01-04 | Nate Niles | REVISION ENERGY INC | RE Pittston Solar LLC | 415 Kelley Rd Pittston | 2000148456 | 30013726440 | Solar | 4950 | 4.95 | 6359.04 |  |  | 44.1685 | -69.7144 | 415 Kelley Rd |  |  | Pittston | 30H | BOWMAN STREET | 263D1 | 34kV Bus at substation |  | 9310-L0102-4660-0031-ED00043 | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2020-03-11 | 2020-03-13 | 2020-03-20 | 2020-03-11 | 2020-03-11 | 2020-03-18 |  | 2020-04-01 |  | 2020-03-18 | 2020-03-18 | 2020-04-01 |  |  | 2020-03-25 | 2020-04-06 |  | CS | 2020-03-25 | RS | 2020-04-06 |  |  |  |  | CS |  |  | 2020-03-25 | 2020-04-06 | [10 empty] | 2020-04-22 | [17 empty] | 2020-04-23 | [6 empty] | Pending |  |  |  |  | 2020-06-26 |  |  | 2021-05-19 | Addendum |  |  | 2020-06-25 | [8 empty] | 2020-06-25 | [17 empty] | 2020-06-30 | [13 empty] | 2021-06-01 |  | 2020-07-22 |  | 2020-09-24 | 2023-01-18 |  | 2023-01-18 | [5 empty] | 1053410 |  | 992859 | 12/30/2022 |  | 2021-11-24: 2020-09-29; 2021-12-28: 2020-09-29; 2023-04-25: 2023-01-18; 2023-04-25: 2023-01-18 | [13 empty] | Q3 2021 |  |  |  | 10300720309 | [11 empty] | TRUE | TRUE | 377 | 2020-09-29 | 2020-09-29 | 2020 | 2020 | 2020 | 44348 |  |  | 2021-05-19 | Addendum
378 |  | Rigel Paradise | Rick Duperre | 2020-03-06 | [31 empty] | 2 - BDIP |  | 673D2 | 161 |  | WITHDRAWN | WITHDRAWN |  | Jamal Batar | Dimension Renewable Energy | DIMENSION ME 1 LLC | 1 Bakers Way Biddeford | 2000123007 | 30012167661 | Solar | [7 empty] | 1 Bakers Way |  |  | Biddeford | 19 | BIDDEFORD INDUSTRIAL PARK | 673D2 |  |  | 9310-L0344-0490-0297-ED00013 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2020-03-13 | 2020-03-20 |  |  |  |  | 1900-01-12 |  | 2020-07-02 | 2020-07-02 | [54 empty] | Pending | [65 empty] | 43353 | 2020-09-28 | 1046410 | 2020-12-30 | 2021-03-12 | [25 empty] | 10300731144 | [11 empty] | TRUE | TRUE | 378 | 0 | 0 | 1900 | 1900 | 1900
379 |  | Rigel Paradise | Rick Duperre | 2020-03-06 | [31 empty] | 1 - MAST |  | 634D1 |  |  | WITHDRAWN | WITHDRAWN |  | Mark Chrisos | Con Edison Clean Energy | CONSOLIDATED EDISON SOLUTIONS | 715 Alford Arundel | 2800000074 | 30012162530 | Solar/Battery | [7 empty] | 715 Alfred Rd |  |  | Arundel |  | MAY STREET | 634D1 |  |  | 9310-L0266-4180-0001-ED00037 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2020-03-13 | 2020-03-20 |  |  |  |  | 1900-01-12 | [57 empty] | Pending | [65 empty] | 106747 | 2020-06-23 | n/a | n/a | 2020-07-10 | [37 empty] | TRUE | TRUE | 379 | 0 | 0 | 1900 | #VALUE! | #VALUE!
380 |  | Eben Snow | Brent Brooks | 2020-03-06 | [31 empty] | 5 - CROW |  | 411D2 | 258 |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED |  | Jonovan (Jonny) Lizama | Luminace | Hayworth Solar Partners, LLC | 268 Old Webster Rd-Lewiston | 2000351927 | 30014933748 | Solar | 4999 | 4.999 | 6793.8 |  |  | 44.0721 | -70.1401 | 268 Old Webster Rd |  |  | Lewiston | 24 | CROWLEYS | 411D2 | 411T2 |  | 9310-SS0411-016 | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2020-03-11 | 2020-03-13 | 2020-03-20 | 2020-03-11 | 2020-03-20 | 2020-07-06 |  | 2020-07-20 |  | 2020-07-06 | 2020-07-06 | 2020-07-20 |  |  | 2020-07-10 |  |  | CS | 2020-07-10 | [6 empty] | CS |  |  | 2020-07-10 | [11 empty] | 2020-07-24 | [17 empty] | 2020-07-24 | [6 empty] | Pending |  |  |  |  | 2020-09-28 | [6 empty] | 2020-09-28 | [8 empty] | 2020-09-28 | [17 empty] | 2020-10-01 | [15 empty] | 2020-10-01 |  | 2020-10-02 | 2023-04-25 | [7 empty] | 461563 |  | 856872 | 2023-04-24 |  | 2021-11-24: 2020-10-19; 2021-12-28: 2020-10-19; 2023-04-25: 2021-07-20; 2023-04-25: 2021-07-20 | [13 empty] | Q4 2021 |  |  |  | 10300724955 | [11 empty] | TRUE | TRUE | 380 | 2020-10-19 | 2020-10-19 | 2020 | 2020 | 2020
381 |  |  | Anthony Boucher | 2020-03-10 | [31 empty] | 5 - BEWE |  | 803D3 | 369 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Nate Niles | REVISION ENERGY INC | REVISION ENERGY INC | 34 Parkhill Rd/ Belfast | 2800283645 | 30012176225 | Solar | [5 empty] | 44.4104 | -69.0825 | 34 Park Hill Rd |  |  | Belfast | 74 | BELFAST WEST SIDE | 803D6 | 34.5 kV Bus |  | 9310-L0383-0430-0013-ED00068 | FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2020-03-16 | 2020-03-17 | 2020-03-24 | 2020-03-16 | 2020-03-20 | 2021-08-26 | 2021-09-14 | 2021-09-10 | 2021-09-14 | 2021-09-15 | 2021-09-15 | 2021-09-29 |  |  | 2021-09-29 |  |  | CS | 2021-09-30 | [6 empty] | CS |  |  | 2021-09-30 | [19 empty] | 2021-10-27 | 2021-10-27 | 2022-02-18 | [7 empty] | 2021-11-02 | [11 empty] | 2022-01-07 | [6 empty] | 2022-01-12 | [8 empty] | 2022-01-17 | [8 empty] | 2022-01-19 | [8 empty] | 2022-01-25 | [7 empty] | 2022-01-25 | [7 empty] | 2022-02-15 | 2022-04-01 | 2022-05-10 |  | 2022-06-02 | [10 empty] | 2023-10-20 | 2021-11-24: 2022-05-10; 2021-12-28: 2022-06-03 | [17 empty] | Requested | [11 empty] | TRUE | TRUE | 381 | 2022-05-10 | 2022-05-10 | 2022 | 2022 | 2022 |  |  | 44652 |  | 2022-01-25
382 |  | Eben Snow | Brent Brooks | 2020-03-10 | [31 empty] | 3 - GRAY |  | 416D3 | 155 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN | 2020-11-20 | William Boyle | CleanTap Energy,LLC | CLEAN SOLAR GRAY LLC | PO Box 235 Cumberland | 2000186781 | 30012720345 | Solar/Battery | [5 empty] | 43.8738 | -70.3272 | PO Box 235 Cumberland |  |  | Gray | 195 | GRAY | 416D3 | 416T1 |  | 9310-SS0416 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2020-03-16 | 2020-03-17 | 2020-03-24 | 2020-03-16 | 2020-03-24 | 2020-04-15 |  | 2020-04-30 |  | 2020-04-15 | 2020-04-15 | 2020-04-30 |  |  | 2020-04-30 |  |  | CS | 2020-05-04 | [6 empty] | CS |  |  | 2020-05-04 |  |  | 2023-02-16 | [8 empty] | 2020-05-04 | [17 empty] | 2020-05-15 | [6 empty] | Pending |  |  |  |  | 2020-07-21 |  |  | 2021-06-11 | Addendum |  |  | 2020-07-16 | [8 empty] | 2020-07-20 | [17 empty] | 2020-07-22 | [15 empty] | 2020-09-29 |  | 2020-09-30 | [8 empty] | 162061 | 2020-07-16 |  |  | 2023-08-02 | 2021-11-24: 2020-10-16; 2021-12-28: 2020-10-16; 2023-04-25: 2021-06-16; 2023-04-25: 2021-06-16 | [17 empty] | 10300725822 | [11 empty] | TRUE | TRUE | 382 | 2020-10-16 | 2020-10-16 | 2020 | 2020 | 2020 |  |  |  | 2021-06-11 | Addendum
383 |  | Eben Snow | Brent Brooks | 2020-03-10 | [31 empty] | 2 - BRPO |  | 407D1 | 145 |  | WITHDRAWN | WITHDRAWN |  | Noah Gonzalez | Nexamp, Inc | NEXAMP SOLAR LLC | 180 Felt Rd/ Woodstock | 2000114877 |  | Solar | [7 empty] | 180 Felt Road |  |  | Woodstock |  | BRYANT POND | 407D1 |  |  | 9310-L0195-6475-0022-ED00018 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2020-03-17 | 2020-03-24 |  |  |  |  | 1900-01-12 | [127 empty] | 2020-05-06 | [37 empty] | TRUE | TRUE | 383 | 0 | 0 | 1900 | #VALUE! | #VALUE!
384 |  | Rigel Paradise | Rick Duperre | 2020-03-10 | [31 empty] | 3 - BUCO |  | 612D2 | 374 |  | WITHDRAWN | WITHDRAWN |  | Colin Derhammer | MELINK SOLAR DEVELOPMENT | MELINK SOLAR DEVELOPMENT | Kelly Orchard (Acton) | 2000150090 |  | Solar | [5 empty] | 43.5333 | -70.9133 | 82 Sanborn Rd |  |  | Acton |  | BUTLER'S CORNER | 612D2 |  |  | 9310-L0226-0020-0044-ED00118 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2020-03-17 | 2020-03-24 |  |  |  |  | 1900-01-12 | [57 empty] | Pending | [69 empty] | 2021-07-16 | [37 empty] | TRUE | TRUE | 384 | 0 | 0 | 1900 | #VALUE! | #VALUE!
385 |  | Eben Snow | Brent Brooks | 2020-03-10 | 2023-08-02 | wthdw | [29 empty] | 4 - GRAY |  | 416D1 | 382 | Yes | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2021-04-16 | Denise Murillo | Atlus Power LLC | GRAY YARMOUTH RD SOLAR LLC | Yarmouth Rd | 2000193116 | 30012803745 | Solar | 4999 | 4.999 | 6624 |  |  | 43.8863 | -70.1401 | 51 Yarmouth Rd |  |  | Gray | 21 | GRAY | 416D1 | 416T2 |  | 9310-SS0416 | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2020-03-17 | 2020-03-17 | 2020-03-24 | 2020-03-17 | 2020-03-24 | 2020-10-07 |  | 2020-10-22 |  | 2020-10-07 | 2020-10-07 | 2020-10-22 |  |  | 2020-10-19 |  |  | CS | 2020-10-19 | [6 empty] | CS |  |  | 2020-10-19 |  |  | 2023-08-04 | [26 empty] | 2020-10-19 | [6 empty] | Pending |  |  |  |  | 2020-12-23 |  |  | 2021-04-29 | Addendum |  |  | 2020-12-23 | [8 empty] | 2020-12-30 | [17 empty] | 2021-01-05 | [5 empty] | 2021-01-05 |  | 2021-01-05 | [6 empty] | 2021-04-29 | 2020-01-05 | 2021-04-29 | 2021-01-06 | [8 empty] | 123024 | 2020-12-16 | 158332 | 2023-08-23 |  | 2021-11-24: 2021-04-29; 2021-12-28: 2021-04-29; 2023-04-25: 2021-04-29; 2023-04-25: 2021-04-29 | [13 empty] | Q3 2021 |  |  |  | 10300779622 | [11 empty] | TRUE | TRUE | 385 | 2021-04-29 | 2021-04-29 | 2021 | 2021 | 2021 |  | 44315 | 44315 | 2021-04-29 | Addendum
386 |  | Govinda Neupane |  | 2020-03-13 | [31 empty] | 3 - SKSS |  | 854D1 | 298 |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2021-12-17 | Jonovan (Jonny) Lizama | Luminace | Front Street Solar Farm, LLC | 369 West Front Street Skowhegan | 2000150598 | 30012193253 | Solar | 3199 | 3.199 | 3875.95 |  |  | 44.7441 | -69.7442 | 369 West Front Street |  |  | Skowhegan | 58 | SKOWHEGAN SOUTH SIDE | 854D1 | 854T1 |  | 9310-SS0854 | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2020-03-20 | 2020-03-20 | 2020-03-27 | 2020-03-20 | 2020-03-27 | 2020-06-03 |  | 2020-06-17 |  | 2020-06-03 | 2020-06-03 | 2020-06-17 |  |  | 2020-06-11 |  |  | CS | 2020-06-11 | [6 empty] | CS |  |  | 2020-06-11 | [11 empty] | 2020-06-15 | [17 empty] | 2020-06-16 | [6 empty] | Pending |  |  |  |  | 2020-08-19 |  |  | 2021-05-24 | Addendum |  |  | 2020-08-18 | [8 empty] | 2020-03-17 | [17 empty] | 2020-03-20 | [15 empty] | 2020-03-20 |  | 2020-08-24 | [8 empty] | 337869 |  | 215795 | 2023-01-27 |  | 2020-09-11 | 2020-09-11 | 2021-06-23 | 2021-06-23 | 2023-01-30 | 2023-01-30 | 2023-02-08 | [14 empty] | Q2 2022 |  |  |  | 10300714122 | [11 empty] | TRUE | TRUE | 386 | 2020-09-11 | 2020-09-11 | 2020 | 2020 | 2020 |  |  |  | 2021-05-24 | Addendum
387 |  | Lanie Patterson | Brent Brooks | 2020-03-13 | [31 empty] | 4 - NOAU |  | 272D3 | 351 |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED |  | Juli Grenich | EcoPower | MEVS EXIT 112 LLC | 3176 LIONSHEAD AVE / CARLSBAD CA 92010-4708 | 2000278644 | 30013956427 | Solar | 996 | 0.996 |  |  |  | 44.3452 | -69.8083 | Exit 112 East I-95 |  |  | Augusta | 532 | NORTH AUGUSTA | 272D3 | 272T1 |  | 9310-L0106-0240-0259-ED00046 | Non-FERC | NOT IMPACTED | NOT IMPACTED |  | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2020-03-20 | 2020-03-20 | 2020-03-27 | 2020-03-20 | 2020-03-27 | 2021-07-28 | 2021-08-05 | 2021-08-11 | 2021-08-11 | 2021-08-18 | 2021-08-18 | 2021-09-01 |  |  | 2021-09-01 | 2021-12-09 |  | CS | 2021-09-01 | RS | 2021-12-09 |  |  |  |  | CS |  |  | 2021-09-01 | 2021-12-09 | [18 empty] | 2021-09-14 | 2021-09-14 | 2021-12-08 | [7 empty] | 2021-09-15 | 2021-12-10 | [10 empty] | 2021-11-19 | 2022-01-25 | [5 empty] | 2021-11-12 | 2022-01-20 | [7 empty] | 2021-11-12 | 2022-01-20 | [8 empty] | 2022-01-20 | [7 empty] | 2021-11-17 | 2022-01-24 | [6 empty] | 2021-11-17 | 2022-01-24 | [6 empty] | 2022-01-26 | 2022-01-25 | 2022-01-28 | 2022-07-15 | 2022-01-28 | [6 empty] | 62318 | 2021-11-10 | 61318 |  |  | 2022-01-28 | 2022-02-01 |  | 2022-06-03 | 2022-08-12 | 2022-08-12 | [15 empty] | Q3 2021 |  |  |  | Requested | [11 empty] | TRUE | TRUE | 387 | 2022-01-28 | 2022-01-28 | 2022 | 2022 | 2022 |  |  | 44586
388 |  | Lanie Patterson | Brent Brooks | 2020-03-13 | 2023-12-06 | L2_Bump | [29 empty] | 3 - BOND |  | 208D1 | 250 | Yes | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2021-01-04 | Mike Imoto | BAP POWER CORPORATION dba Cenergy | MEVS ASA LLC | Augusta Airport | 2000460978 | 30016481282 | Solar | 4875 | 4.875 | 7000 |  |  | 44.3307 | -69.7943 | 25 Bond Brook Rd |  |  | Augusta | 65 | BOND BROOK | 208D1 | 208T1 |  | 9310-L0021-0240-0265-ED00068 | Non-FERC | TRIGGERING | TRIGGERING | 325000 | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2020-03-20 | 2020-03-20 | 2020-03-27 | 2020-03-20 | 2020-03-20 | 2020-04-03 |  | 2020-04-17 |  | 2020-04-03 | 2020-04-07 | 2020-04-22 |  |  | 2020-04-07 |  |  | CS | 2020-04-07 | [6 empty] | CS |  |  | 2020-04-07 |  |  | 2023-12-26 | [11 empty] | 2024-01-05 | [8 empty] | 2024-01-05 | [5 empty] | 2020-04-15 |  |  | 2024-01-09 |  |  |  | Pending |  |  |  |  | 2020-06-19 |  |  | 2021-05-19 | Addendum |  |  | 2020-06-16 |  |  | 2024-03-05 | [5 empty] | 2020-06-16 | [17 empty] | 2020-06-22 | [13 empty] | 2021-06-03 |  | 2020-07-13 |  | 2020-07-13 | 2023-03-22 | [7 empty] | 374945 |  | 537986 | 2024-03-05 |  | 2020-08-24 | 2020-08-24 | 2021-08-18 | 2021-08-18 |  |  | 2024-03-07 | 2024-03-07 | [17 empty] | 10300704972 | [11 empty] | TRUE | TRUE | 388 | 2020-08-24 | 2020-08-24 | 2020 | 2020 | 2020 | 44350 |  |  | 2021-05-19 | Addendum
389 |  | Lanie Patterson | Brent Brooks | 2020-03-20 | 2023-07-07 | wthdw | [29 empty] | 5 - PDRD |  | 262D1 | 92 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Jeff Potter | Renewable Energy International LLC | Puddledock Road LLC | 0 Puddle Duck Rd Manchester | 2000240395 | 30013436925 | Solar | [5 empty] | 44.3345 | -69.8548 | 0 Puddledock Rd |  |  | Manchester | 18 | PUDDLEDOCK ROAD | 262D1 | 34.5 kV Bus | 12.47 | 9310-L0064-3540-0069-ED00024 | Non-FERC | WITHDRAWN | WITHDRAWN | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2020-03-25 | 2020-03-27 | 2020-04-03 | 2020-03-25 | 2020-04-07 | 2021-03-03 |  | 2021-03-17 |  | 2021-03-09 | 2021-03-09 | 2021-03-17 |  |  | 2021-03-23 | 2021-08-16 |  | CS | 2021-03-23 | RS | 2021-08-16 |  |  |  |  | CS |  |  | 2021-03-23 | 2024-07-23 |  | 2024-03-04 | [5 empty] | 2024-07-24 |  |  |  | 2024-07-26 |  | 2024-03-19 | [6 empty] | 2024-07-26 |  | 2024-04-15 | [5 empty] | 2021-04-02 | 2024-07-26 |  | 2024-04-15 | [8 empty] | 2021-06-08 | 2024-09-09 |  | 2021-07-06 | Report |  |  | 2021-07-06 | 2024-09-09 |  | 2024-06-07 | [5 empty] | 2021-07-06 | 2024-09-09 |  | 2024-06-10 | [6 empty] | 2024-09-09 | [7 empty] | 2021-07-13 | 2024-09-10 | [6 empty] | 2021-07-13 | 2024-09-10 | [6 empty] | 2024-09-10 |  |  | 2022-11-30 |  | 2022-12-08 | [5 empty] | 200322 |  | 371338 | 2024-06-06 | 2025-01-08 | 2021-10-13 | 2021-10-15 | 2022-12-08 | 2022-12-08 | 2024-09-19 | 2024-09-19 | [19 empty] | Requested | [11 empty] | TRUE | TRUE | 389 | 2021-10-13 | 2021-10-13 | 2021 | 2021 | 2021 |  |  |  | 2021-07-06 | Report
390 |  |  | Anthony Boucher | 2020-03-20 | 2022-06-22 | L2_Bump | [27 empty] | 2 - BUCK | 345 | 3 - BUCK |  | 806D2 | 345 | Yes | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED |  | Tom Holt | Ameresco, Inc | PENOBSCOT NARROWS SOLAR LLC | 109 RIVER RD (SOLAR) BUCKSPORT | 2000309463 | 30014380296 | Solar | 4980 | 4.98 | 7000 |  |  | 44.5882 | -68.803 | River Road(Off) & Silver Lake Road |  |  | Bucksport | 12 | BUCKSPORT | 806D2 | 806T3 | 34.5 | 9310-L0386-0790-0076-ED00284 | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2020-03-26 | 2020-03-27 | 2020-04-03 | 2020-03-26 | 2020-04-07 | 2020-08-03 |  | 2020-08-17 |  | 2020-08-03 | 2020-08-03 | 2020-08-17 |  |  | 2020-08-17 |  |  | CS | 2020-08-26 | [6 empty] | CS |  |  | 2020-08-26 |  |  | 2022-08-19 | [11 empty] | 2022-08-31 | [14 empty] | 2020-09-11 |  |  | 2022-08-30 | 2022-12-07 |  |  | Pending |  |  |  |  | 2020-11-16 |  |  | 2021-05-19 | Addendum |  |  | 2020-11-17 |  |  | 2022-10-12 | 2023-01-18 |  |  |  |  | 2020-11-17 |  |  | 2022-10-12 | 2023-01-18 | [8 empty] | 2023-01-26 |  |  |  |  | 2020-11-19 |  |  |  | 2023-01-30 | [9 empty] | 2021-06-01 |  | 2020-11-19 |  | 2020-11-19 | 2023-01-31 |  | 2023-02-06 | 2023-07-14 | 2023-07-14 |  |  |  | 163525 |  |  |  |  | 2021-11-24: 2020-12-03; 2021-12-28: 2020-12-03; 2023-04-25: 2023-02-08; 2023-04-25: 2023-02-08 |  |  | 2023-08-08 | 2023-08-08 | [13 empty] | 10300740849 | [11 empty] | FALSE | TRUE | 390 | 2020-12-03 | 2020-12-03 | 2020 | 2020 | 2020 | 44348 |  |  | 2021-05-19 | Addendum
391 |  | Lanie Patterson | Brent Brooks | 2020-03-20 | [31 empty] | 1 - CAST |  | 215D2 |  |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED |  | Juli Grenich | EcoPower | MEVS DOT LLC | EXIT 109 WEST | 2800062778 | 30012198245 | Solar | 500 | 0.5 | 711 |  |  | 44.311 | -69.8112 | Exit 109 East I-95 Site 1 |  |  | Augusta | 511 | CAPITOL STREET | 215D2 | 215T2 |  | 9310-L0038-0240-0389-ED00023 | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2020-03-26 | 2020-03-27 | 2020-04-03 | 2020-03-26 | 2020-03-26 | 2020-04-07 |  | 2020-04-22 |  | 2020-04-07 | 2020-04-07 | 2020-04-22 |  |  | 2020-04-07 |  |  | CS | 2020-04-07 | [6 empty] | CS |  |  | 2020-04-07 | [29 empty] | 2020-04-17 | [6 empty] | Pending |  |  |  |  | 2020-06-23 |  |  | 2021-05-18 | Addendum |  |  | 2020-06-16 | [8 empty] | 2020-06-16 | [17 empty] | 2020-06-22 | [13 empty] | 2021-05-25 |  | 2020-07-13 |  | 2020-07-13 | 2023-01-04 |  | 2023-01-04 | [5 empty] | 52335 |  | 93522 | 2022-12-13 |  | 2021-11-24: 2020-08-24; 2021-12-28: 2020-08-24; 2023-04-25: 2023-01-05; 2023-04-25: 2023-01-06 | [17 empty] | 10300704953 | [11 empty] | TRUE | TRUE | 391 | 2020-08-24 | 2020-08-24 | 2020 | 2020 | 2020 | 44341 |  |  | 2021-05-18 | Addendum
392 |  | Lanie Patterson | Brent Brooks | 2020-03-20 | [31 empty] | 2 - CAST |  | 215D3 | 391 |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2021-01-04 | Juli Grenich | EcoPower | MEVS DOT LLC | EXIT 109A | 2800062778 | 30012167166 | Solar | 1703 | 1.703 | 2152 |  |  | 44.3149 | -69.8083 | Exit 109 West I-95 Site 2 |  |  | Augusta | 60.3 | CAPITOL STREET | 215D3 | 215T2 |  | 9310-L0039-0240-0383-ED00352 | Non-FERC | TRIGGERING | TRIGGERING | 325000 | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2020-03-26 | 2020-03-27 | 2020-04-03 | 2020-03-26 | 2020-04-03 | 2020-04-07 |  | 2020-04-22 |  | 2020-04-07 | 2020-04-22 | 2020-04-07 |  |  | 2020-04-07 |  |  | CS | 2020-04-07 | [6 empty] | CS |  |  | 2020-04-07 | [29 empty] | 2020-04-17 | [6 empty] | Pending |  |  |  |  | 2020-06-23 |  |  | 2021-05-18 | Addendum |  |  | 2020-06-16 | [8 empty] | 2020-06-16 | [17 empty] | 2020-06-22 | [13 empty] | 2021-05-25 |  | 2020-07-13 |  | 2020-07-13 | 2023-01-05 |  | 2023-01-06 | [5 empty] | 403327 |  |  |  |  | 2021-11-24: 2020-08-24; 2021-12-28: 2020-08-24; 2023-04-25: 2021-06-07; 2023-04-25: 2021-06-07 | [17 empty] | 10300704910 | [11 empty] | TRUE | TRUE | 392 | 2020-08-24 | 2020-08-24 | 2020 | 2020 | 2020 | 44341 |  |  | 2021-05-18 | Addendum
393 |  |  | Anthony Boucher | 2020-03-20 | 2023-10-20 | wthdw | [29 empty] | 6 - BEWE |  | 803D6 | 381 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Tiffiny Chase | ASPEN POWER PARTNERS | ME I Belmont Augusta LLC | 153 Augusta Rd | 2000303745 | 30014304742 | Solar | [5 empty] | 44.4044 | -69.0986 | 2 Augusta Rd |  |  | Belmont | 6 | BELFAST WEST SIDE | 803D6 | 34.5 kV Bus | 34.5 | 9310-L0383-0450-0003-ED00015 | FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2020-04-01 | 2020-03-27 | 2020-04-03 | 2020-04-01 | 2020-04-07 | 2022-12-14 | 2022-12-13 | 2022-12-29 | 2022-12-14 | 2022-12-21 | 2022-12-23 | 2023-01-06 |  |  | 2023-01-06 |  |  | CS | [7 empty] | CS |  |  | 2023-01-17 | [11 empty] | 2023-01-05 | [8 empty] | 2023-01-06 | [8 empty] | 2023-01-24 | [11 empty] | 2023-03-29 | [6 empty] | 2023-03-28 | [8 empty] | 2023-03-28 | [8 empty] | 2023-03-30 | [8 empty] | 2023-03-30 | [7 empty] | 2023-03-30 | [7 empty] | 2023-03-30 |  | 2023-04-03 |  | 2023-04-04 | [6 empty] | 508034 | 2023-03-27 |  |  | 2024-04-17 | 2021-11-24: 2023-04-04; 2021-12-28: 2023-04-06 | [29 empty] | TRUE | TRUE | 393 | 2023-04-04 | 2023-04-04 | 2023 | 2023 | 2023
394 |  | Eben Snow | Brent Brooks | 2020-03-20 | [31 empty] | 6 - CROW |  | 411D1 | 380 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Clarke Fenner | NEW ENGLAND SOLAR GARDEN CORP | ME I Lewiston Old Lisbon LLC | 184 Old Lisbon Rd | 2000148928 | 30012168420 | Solar | [5 empty] | 44.067 | -70.1549 | 184 OLD LISBON RD |  |  | Lewiston | 29 | CROWLEYS | 411D1 | 411T2 |  | FLOC-MISSING-01142021 | Non-FERC | WITHDRAWN | WITHDRAWN | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2020-04-07 | 2020-03-27 | 2020-04-03 | 2020-04-07 | 2020-04-07 | 2020-10-23 |  | 2020-11-06 |  | 2020-10-23 | 2020-10-23 | 2020-11-06 |  |  | 2020-10-23 |  |  | CS | 2020-10-23 | [6 empty] | CS |  |  | 2020-10-23 | [29 empty] | 2020-10-26 | [6 empty] | Pending |  |  |  |  | 2020-12-31 |  |  | 2021-06-21 | Addendum |  |  | 2021-01-12 | [8 empty] | 2021-01-12 | [17 empty] | 2021-01-19 | [27 empty] | 2022-01-26 |  |  | 2022-10-25 | 2021-11-24: 2021-02-18; 2021-12-28: 2021-02-18; 2023-04-25: 2021-11-30; 2023-04-25: 2021-12-08 | [17 empty] | 10300758911 | [11 empty] | TRUE | TRUE | 394 | 2021-02-18 | 2021-02-18 | 2021 | 2021 | 2021 |  |  |  | 2021-06-21 14:37 | Addendum
395 |  |  | Anthony Boucher | 2020-03-20 | [31 empty] | 1 - PROS |  | 846D1 |  |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Clarke Fenner | NEW ENGLAND SOLAR GARDEN CORP | NEW ENGLAND SOLAR GARDEN CORP | 1084 Bangor Rd | 2000148928 | 30012168263 | Solar | [7 empty] | 1084 Bangor Rd |  |  | Prospect |  | PROSPECT | 846D1 |  |  | 9310-L0426-4770-0031-ED00018 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2020-03-27 | 2020-04-03 |  |  |  |  | 1900-01-12 | [50 empty] | 2020-04-23 | [6 empty] | Pending | [69 empty] | 2021-06-29 | 2021-11-24: 2020-08-04; 2021-12-28: 2020-08-04 | [17 empty] | 10300694856 | [11 empty] | TRUE | TRUE | 395 | 2020-08-04 | 2020-08-04 | 2020 | 2020 | 2020
396 |  |  | Anthony Boucher | 2020-03-20 | [31 empty] | 7 - BEWE |  | 803D6 | 393 |  | WITHDRAWN | WITHDRAWN |  | Tiffiny Chase | ASPEN POWER PARTNERS | ME ¦ Searsmont Appleton Ridge LLC | 131 Appleton Ridge Rd | 2000303773 | 30014304775 | Solar | [5 empty] | 44.3394 | -69.2108 | 131 APPLETON RIDGE RD |  |  | Searsmont | 32.5 | BELFAST WEST SIDE | 803D6 | 34.5 kV Bus |  | 9310-L0383-5215-0013-ED00020 (NEEDS TO BE CONFIRMED WITH DEVELOPER) | FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2020-04-07 | 2020-03-27 | 2020-04-03 | 2020-04-07 | 2020-04-07 | [130 empty] | 2022-12-13 | [37 empty] | TRUE | TRUE | 396 | 0 | 0 | 1900 | #VALUE! | #VALUE!
397 |  |  | Anthony Boucher | 2020-03-20 | [31 empty] | 8 - BEWE |  | 803D6 | 396 |  | WITHDRAWN | WITHDRAWN |  | Tiffiny Chase | ASPEN POWER PARTNERS | ME I Searsmont Borough LLC | 170 Borough Rd | 2000303776 | 30014304791 | Solar | [5 empty] | 44.4081 | 69.2099 | 170 BOROUGH RD |  |  | Searsmont | 3 | BELFAST WEST SIDE | 803D6 | 34.5 kV Bus |  | 9310-L0383-5215-0002-ED00154 | FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2020-04-07 | 2020-03-27 | 2020-04-03 | 2020-04-07 | 2020-04-07 | 2023-08-21 | 2023-09-01 | 2023-09-05 | [127 empty] | 2023-09-05 | [37 empty] | TRUE | TRUE | 397 | 0 | 0 | 1900 | #VALUE! | #VALUE!
398 |  | Lanie Patterson | Anthony Boucher | 2020-03-20 | 2023-10-20 | wthdw | [29 empty] | 9 - BEWE |  | 803D6 | 397 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Tiffiny Chase | Aspen Power Partners | ME I SEARSMONT 140 BELFAST LLC | 140 Belfast Augusta Rd | 2000303777 | 30014305004 | Solar | [5 empty] | 44.4081 | -69.2099 | 140 BELFAST AUGUSTA RD |  |  | Searsmont | 89.5 | BELFAST WEST SIDE | 803D6 | 34.5 kV Bus |  | 9310-L0383-5215-0002-ED00156 | FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2020-04-07 | 2020-03-27 | 2020-04-03 | 2020-04-07 | 2020-04-07 | 2023-04-06 | 2023-04-06 | 2023-04-20 | 2023-04-07 | 2023-04-20 | 2023-04-20 | 2023-05-04 |  |  | 2023-04-25 |  |  | CS | [7 empty] | CS |  |  | 2023-04-26 |  |  |  | 2024-01-31 | [7 empty] | 2023-04-14 |  |  | 2023-05-02 | 2024-02-06 |  |  |  |  | 2023-04-26 |  |  | 2023-08-15 | 2024-02-15 |  |  |  |  | 2023-05-02 |  |  | 2023-08-16 | 2024-02-16 | [7 empty] | 2023-07-07 | [6 empty] | 2023-07-07 |  |  |  | 2024-04-24 |  |  |  |  | 2023-07-07 |  |  |  | 2024-04-24 |  |  |  |  | 2023-07-07 |  |  |  | 2024-04-24 |  |  |  |  | 2023-07-12 |  |  |  | 2024-04-29 |  |  |  | 2023-07-12 |  |  |  | 2024-04-29 |  |  |  | 2023-07-12 |  | 2023-07-24 | 2024-04-29 | 2023-08-16 | 2024-04-30 | [5 empty] | 574444 | 2023-07-06 | 145351 | 2024-04-23 | 2024-08-15 | 2021-11-24: 2023-08-21; 2021-12-28: 2023-08-21; 2023-04-25: 2024-05-02; 2023-04-25: 2024-05-02 | [29 empty] | TRUE | TRUE | 398 | 2023-08-21 | 2023-08-21 | 2023 | 2023 | 2023
399 |  | Lanie Patterson | Anthony Boucher | 2020-03-20 | 2023-01-09 | L2_Bump |  |  |  |  | 2023-02-22 | wthdw | [23 empty] | 4 - SEAR |  | 850D1 | 244 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Tiffiny Chase | ASPEN POWER PARTNERS | ME I STOCKTON SPRINGS MCKENNEY LLC | 4 Mckenney Rd | 2000148928 | 30012168446 | Solar | [5 empty] | 44.4944 | -68.8435 | 4 McKenney Rd |  |  | Stockton Springs | 14 | SEARSPORT | 850D1 | 850T1 | 12.47 | 9310-L0427-5540-0006-ED00007 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2020-04-07 | 2020-03-27 | 2020-04-03 | 2020-04-07 | 2020-04-07 | 2020-07-08 |  | 2020-07-22 |  | 2020-07-08 | 2020-07-10 | 2020-07-24 |  |  | 2020-07-10 |  |  | CS | 2020-07-10 | [6 empty] | CS |  |  | 2020-07-10 |  |  | 2023-03-20 | 2023-07-10 | [7 empty] | 2020-07-14 |  |  | 2023-03-30 | 2023-07-11 | [7 empty] | 2023-04-12 | 2023-07-25 |  |  |  |  | 2020-07-20 |  |  | 2023-04-12 | 2023-07-28 |  |  | Pending |  |  |  |  | 2020-09-22 |  |  | 2021-05-19 | Addendum |  |  | 2020-09-15 |  |  | 2023-05-26 | 2023-09-14 |  |  |  |  | 2020-09-16 |  |  | 2023-05-26 | 2023-09-14 | [7 empty] | 2023-06-06 | 2023-09-15 |  |  |  |  | 2020-09-21 |  |  | 2023-06-06 | 2023-09-20 | [7 empty] | 2023-09-20 |  | 2021-05-28 |  | 2020-09-21 |  | 2020-09-21 | [8 empty] | 240002 |  | 223613 | 2021-11-02 | 2023-10-16 | 2021-11-24: 2020-09-23; 2021-12-28: 2020-09-23; 2023-04-25: 2021-11-02; 2023-04-25: 2021-11-18 | [17 empty] | 10300716679 | [11 empty] | TRUE | TRUE | 399 | 2020-09-23 | 2020-09-23 | 2020 | 2020 | 2020 | 44344 |  |  | 2021-05-19 | Addendum
400 |  |  | Anthony Boucher | 2020-03-20 | 2021-06-29 | wthdw | [29 empty] | 2 - PROS |  | 846D1 | 395 |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED |  | Tiffiny Chase | ASPEN POWER PARTNERS LLC | ME I Prospect Pond LLC | 1129 Bangor Rd | 2000227009 | 30013253205 | Solar | 4999 | 4.999 | 6736 |  |  | 44.5649 | -68.8671 | 1129 Bangor Rd |  |  | Prospect | 32 | PROSPECT | 846D1 | 846T1 |  | 9310-L0426-4770-0031-ED00028 | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2020-04-07 | 2020-03-27 | 2020-04-03 | 2020-04-07 | 2020-04-07 | 2020-04-21 |  | 2020-05-05 |  | 2020-04-21 | 2020-05-05 | 2020-04-21 |  |  | 2020-04-21 | 2021-07-12 |  | CS | 2020-04-21 | RS | 2021-07-12 |  |  |  |  | CS |  |  | 2020-04-21 | 2021-07-12 | [28 empty] | 2020-04-24 | 2021-07-20 | [5 empty] | Pending |  |  |  |  | 2020-06-29 | 2021-08-31 |  | 2021-05-20 | Addendum |  |  | 2020-06-26 | 2021-08-30 | [7 empty] | 2020-06-29 | 2021-08-30 | [16 empty] | 2020-07-06 | 2021-09-20 | [6 empty] | 2021-09-20 | [5 empty] | 2021-06-14 |  | 2020-07-27 |  | 2020-07-27 |  |  |  |  | 2023-07-31 |  |  |  | 278706 |  | 62601 | 2021-09-13 |  | 2021-11-24: 2020-08-04; 2021-12-28: 2020-08-04; 2023-04-25: 2021-09-22; 2023-04-25: 2021-09-23 |  |  | 2023-08-07 | 2023-08-08 | [13 empty] | 10300694833 | [11 empty] | TRUE | TRUE | 400 | 2020-08-04 | 2020-08-04 | 2020 | 2020 | 2020 | 44361 |  |  | 2021-05-20 | Addendum
401 |  | Govinda Neupane |  | 2020-03-20 | [31 empty] | 1 - BIGE |  | 882D1 |  |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2020-10-05 | Jonovan (Jonny) Lizama | Luminace | Carrabassett Solar 1 LLC | Carrabassett Dr, Carrabassett Valle | 2000307637 | 30014355744 | Solar | 4995 | 4.995 | 6760 |  |  | 45.1007 | -70.3539 | CARRABASSETT DR |  |  | Carrabassett Valley | 502 | BIGELOW | 882D1 | 882T1 |  | 9310-L0465-2940-0035-ED00176 | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2020-04-07 | 2020-03-27 | 2020-04-03 | 2020-04-07 | 2020-04-07 | 2020-04-21 |  | 2020-05-05 |  | 2020-04-21 | 2020-04-21 | 2020-05-05 |  |  | 2020-04-21 |  |  | CS | 2020-04-21 | [6 empty] | CS |  |  | 2020-04-21 | [11 empty] | 2020-04-24 | [17 empty] | 2020-05-05 | [6 empty] | Pending |  |  |  |  | 2020-07-09 |  |  | 2021-05-10 | Addendum |  |  | 2020-07-09 | [8 empty] | 2020-07-06 | [17 empty] | 2020-07-15 | [14 empty] | 2021-05-11 | 2021-05-12 |  | 2020-08-04 | [8 empty] | 83899 |  |  |  |  | 2021-11-24: 2020-08-20; 2021-12-28: 2020-08-20; 2023-04-25: 2020-05-12; 2023-04-25: 2020-05-12 | [17 empty] | 10300703636 | [11 empty] | TRUE | TRUE | 401 | 2020-08-20 | 2020-08-20 | 2020 | 2020 | 2020 |  | 44327 |  | 2021-05-10 | Addendum
402 |  | Eben Snow | Brent Brooks | 2020-03-24 | 2022-06-02 | L2_Bump |  | 2022-12-15 | L2_Bump |  | 2023-02-03 | L2_Bump |  | 2023-03-20 | L2_Bump |  | 2023-11-29 | wthdw |  |  |  |  | 2023-01-09 | wthdw | [11 empty] | 13 - HORD |  | 420D1 | 299 |  | WITHDRAWN | WITHDRAWN |  | Dan Ryan | Turning Point Energy | TPE DEVELOPMENT LLC | Minot Ave Auburn | 2000123236 | 30012200942 | Solar | [5 empty] | 44.8045 | -70.2816 | MINOT AVE |  |  | Auburn |  | HOTEL ROAD | 420D1 | 420T2 |  | FLOC-MISSING-01142021 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2020-04-07 | 2020-03-31 | 2020-04-07 | 2020-04-07 | 2020-04-07 | 2024-02-28 |  | 2024-03-13 | [127 empty] | 2024-03-06 | [37 empty] | TRUE | TRUE | 402 | 0 | 0 | 1900 | #VALUE! | #VALUE!
403 |  | Eben Snow | Brent Brooks | 2020-03-23 | 2022-07-09 | L2_Bump |  | 2022-10-20 | L2_Bump | [26 empty] | 1 - SRTP |  | 470D1 |  |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Jeffrey Lord | The Gray Pen Group, LLC | CASCO A,LLC | Roosevelt Trl/ Casco | 2800000074 | 30015177626 | Solar | [5 empty] | 43.9498 | -70.5526 | 643 Roosevelt Trail |  |  | Casco | 360H | SAND ROAD TAP | 470D1 | 470T1 | 12.47 | 9310-L0208-1060-0079-ED00054 | Non-FERC | WITHDRAWN | WITHDRAWN | 325000 | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2020-04-07 | 2020-03-30 | 2020-04-06 | 2020-04-07 | 2020-04-07 | 2020-04-22 |  | 2020-05-06 |  | 2020-04-22 | 2020-04-22 | 2020-05-06 |  |  | 2020-04-23 |  |  | CS | 2020-04-23 | [6 empty] | CS |  |  | 2020-04-23 |  |  | 2022-07-19 | 2022-10-21 | 2023-03-15 | [6 empty] | 2020-04-29 |  |  |  | 2022-11-03 | 2023-03-22 | [6 empty] | 2023-03-21 | [5 empty] | 2020-04-24 |  |  | 2022-10-06 | 2022-11-08 |  |  | Yes |  |  |  |  | 2020-06-29 | 2022-09-21 |  | 2021-05-20 | Addendum |  |  | 2020-06-29 |  |  |  | 2022-12-23 | 2023-06-15 |  |  |  | 2020-06-30 |  |  | 2022-12-29 |  | 2023-06-15 | [7 empty] | 2023-01-13 |  |  |  |  | 2020-07-07 |  |  |  |  | 2023-06-27 | [8 empty] | 2021-06-10 |  | 2020-07-20 |  | 2020-07-21 | 2023-07-06 |  | 2023-08-22 | [5 empty] | 491060 |  | 578692 | 2023-06-14 | 2024-07-29 | 2020-08-04 | 2020-08-04 | 2021-05-20 | 2021-05-20 | 2023-08-23 | 2023-08-23 | [16 empty] | 2021-07-20 |  |  | 10300695353 | [11 empty] | TRUE | TRUE | 403 | 2020-08-04 | 2020-08-04 | 2020 | 2020 | 2020 | 44357 |  |  | 2021-05-20 | Addendum
404 |  | Eben Snow | Brent Brooks | 2020-03-26 | 2022-06-08 | L2_Bump |  | 2022-07-27 | L2_Bump |  | 2023-01-18 | L2_With |  | 2023-07-10 | L2_Bump |  | 2023-09-26 | wthdw |  | 2023-10-05 | L2_Bump |  | 2024-01-17 | L2_Bump |  | wthdw |  | 2025-07-15 | wthdw |  |  |  |  | 4 - DEER | 329 | 5 - DEER |  | 412D3 | 329 | Yes | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Santiago Quijano | Bluewave MA, LLC | BWC GULF ISLAND POND LLC | 224 E Waterman Rd | 2000150155 | 30012186455 | Solar | [5 empty] | 44.1756 | -70.2233 | 224 E. Waterman Rd |  | E. Waterman Rd | Auburn | 21 | DEER RIPS | 412D3 | 412T4 | 12.47 | 9310-L0127-0230-0382-ED00007 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2020-04-07 | 2020-04-02 | 2020-04-09 | 2020-04-07 | 2020-04-07 | 2021-09-16 | 2021-09-17 | 2021-09-30 | 2021-09-17 | 2021-09-20 | 2021-09-22 |  |  |  |  | 2022-03-11 |  | CS | 2021-09-30 | RS | 2022-03-11 |  |  |  |  | CS |  |  | 2021-09-30 | 2022-03-11 |  | 2023-08-16 | 2024-05-13 | 2025-07-16 | [9 empty] | 2023-08-25 | 2024-06-03 | 2025-08-06 |  |  | 2021-12-03 | 2021-12-03 | 2022-03-18 |  | 2023-08-29 | 2024-06-03 | 2025-08-06 |  |  |  | 2021-12-09 | 2022-03-22 |  | 2023-09-01 | 2024-06-03 | 2025-08-06 | [6 empty] | 2021-02-11 | 2022-05-03 | [5 empty] | 2022-02-09 | 2022-05-04 |  |  | 2024-08-08 |  |  |  |  | 2022-02-09 | 2022-05-04 |  |  | 2024-08-02 |  |  |  |  | 2022-02-09 | 2022-05-05 | [7 empty] | 2022-02-16 | 2022-05-11 | [6 empty] | 2022-02-16 | 2022-05-11 | [6 empty] | 2022-06-03 |  | 2022-06-03 | 2024-08-13 | 2022-06-09 | 2024-08-20 | [7 empty] | 425506 | 2024-08-07 | 2025-09-22 | 2021-11-24: 2022-06-14; 2021-12-28: 2022-06-17; 2023-04-25: 2024-08-21; 2023-04-25: 2024-08-26 | [13 empty] | Q4 2025 | [15 empty] | FALSE | TRUE | 404 | 2022-06-14 | 2022-06-14 | 2022 | 2022 | 2022 |  |  |  |  | 2022-02-19
405 |  |  | Anthony Boucher | 2020-03-27 | [31 empty] | 3 - PROS |  | 846D1 | 400 |  | WITHDRAWN | WITHDRAWN |  | Matthew Doubleday | SunRaise Investments LLC | SUNRAISE DEVELOPMENT LLC | 0 Coles Corner Rd Winterport | 2000124937 | 30012203961 | Solar | [7 empty] | 321 Lebanon Rd |  |  | Winterport |  | PROSPECT | 846D1 |  |  | 9310-L0426-6440-0015-ED00178 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2020-04-03 | 2020-04-10 |  |  |  |  | 1900-01-12 | [57 empty] | Pending | [69 empty] | 2021-01-20 | [37 empty] | TRUE | TRUE | 405 | 0 | 0 | 1900 | #VALUE! | #VALUE!
406 |  | Govinda Neupane |  | 2020-03-27 | [31 empty] | 7 - SKNS |  | 853T1 | 289 |  | WITHDRAWN | WITHDRAWN |  | Matthew Doubleday | SunRaise Investments LLC | SUNRAISE DEVELOPMENT LLC | 585 Main St Corinth | 2000124937 | 30012203953 | Solar | [7 empty] | 585 Main St |  |  | Corinth |  | SKOWHEGAN NORTH SIDE | 853T1 |  |  | 86-Withdrawn-86d | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2020-04-03 | 2020-04-10 |  |  |  |  | 1900-01-12 | [57 empty] | Pending | [69 empty] | 2022-03-07 | [37 empty] | TRUE | TRUE | 406 | 0 | 0 | 1900 | #VALUE! | #VALUE!
407 |  | Lanie Patterson | Brent Brooks | 2020-03-27 |  |  |  | 2024-06-14 | wthdw | [25 empty] | 131 | 4 - RRPS |  | 873D2 | 132 | Yes | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Nick Mazuroski | Dirigo/BNRG | BD SOLAR HOLMES FARM LLC | County Rd Waterville | 2000148854 | 30012166895 | Solar | [5 empty] | 44.5778 | -69.663 | County Rd |  |  | Waterville | 705 | COUNTY RD (RICE RIPS) | 873D2 | 873T2 | 12.47 | FLOC-MISSING-01142021 | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2020-04-07 | 2020-04-03 | 2020-04-10 | 2020-04-07 | 2020-04-10 | 2020-12-15 |  | 2020-12-30 |  | 2020-12-15 | 2020-12-15 | 2020-12-30 |  |  | 2020-12-16 |  |  | CS | 2020-12-16 | [6 empty] | CS |  |  | 2020-12-16 |  |  | 2022-12-15 | 2024-06-19 | [10 empty] | 2022-12-22 | 2024-07-08 | [8 empty] | 2024-09-05 |  |  |  |  | 2021-01-04 |  |  | 2022-12-29 | 2024-09-05 | [7 empty] | 2021-03-10 |  |  | 2021-04-21 | Report |  |  | 2021-04-21 |  |  | 2024-11-11 | [5 empty] | 2021-06-24 |  |  | 2024-11-11 | [8 empty] | 2024-11-25 | [5 empty] | 2021-07-02 |  |  | 2024-12-05 |  |  |  |  | 2021-07-02 |  |  | 2024-12-05 | [7 empty] | 2023-02-09 |  |  | 2024-12-20 | 2024-12-20 |  |  |  | 138143 |  | 515254 | 2024-11-08 | 2025-10-24 | 2021-07-07 | 2021-07-07 | 2023-04-18 | 2023-04-18 | 2025-01-17 | 2025-01-17 | [15 empty] | Q4 2021 |  |  |  | Requested | [11 empty] | TRUE | TRUE | 407 | 2021-07-07 | 2021-07-07 | 2021 | 2021 | 2021 |  |  |  | 2021-04-21 | Report
408 |  | Eben Snow | Brent Brooks | 2020-03-27 | [17 empty] | RQP-5 | [9 empty] | RQP-5 |  |  |  | 4 - PATP |  | 409D1 | 228 |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2020-10-05 | Stephen Campbell | ISM Solar Development LLC | ISM SOLAR SHEPHARDS ACRES LLC | 24 Shepards Acres Estate So Paris | 2000170139 | 30012490394 | Solar | 3000 | 3 | 4493 |  |  | 44.2855 | -70.5226 | 24 Shepherds Acres Estate |  |  | South Paris | 5 | PARIS TAP | 409D1 | 409T1 |  | 9310-L0122-4500-0043-ED00011 | FERC | NOT IMPACTED | NOT IMPACTED | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2020-04-07 | 2020-04-03 | 2020-04-10 | 2020-04-07 | 2020-04-07 | 2020-04-23 |  | 2020-05-07 |  | 2020-04-23 | 2020-04-23 | 2020-05-07 |  |  | 2020-04-23 |  |  | CS | 2020-04-23 | [6 empty] | CS |  |  | 2020-04-23 | [11 empty] | 2020-05-01 | [17 empty] | 2020-05-06 | [6 empty] | Pending |  |  |  |  | 2020-07-10 |  |  | 2021-05-20 | Addendum |  |  | 2020-07-10 | [8 empty] | 2020-07-14 | [17 empty] | 2020-07-20 | [13 empty] | 2021-06-08 |  | 2020-07-21 |  | 2020-07-22 | [8 empty] | 313085 |  |  |  |  | 2021-11-24: 2020-07-27; 2021-12-28: 2020-07-27; 2023-04-25: 2021-06-17; 2023-04-25: 2021-06-17 | [13 empty] | Q3 2021 |  |  |  | 10300740899 | [11 empty] | TRUE | TRUE | 408 | 2020-07-27 | 2020-07-27 | 2020 | 2020 | 2020 | 44355 |  |  | 2021-05-20 | Addendum
409 |  | Govinda Neupane |  | 2020-03-27 | [31 empty] | 3 - ATHN |  | 827D1 | 282 |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2021-02-25 | Jess Roden | Greenbacker Capital | ME ATHENS RIDGE RD SOLAR LLC | E RIDGE RD ATHENS (solar) | 2000368721 | 30015152918 | Solar | 2864 | 2.864 | 3827 |  |  | 44.9141 | -69.664 | Ridge Rd |  |  | Athens | 21 | ATHENS | 827D1 | 827T1 |  | 9310-L0411-0200-0027-ED00018 | Non-FERC | COST SHARE | COST SHARE ( $305,000) | 71517 | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2020-04-07 | 2020-04-03 | 2020-04-10 | 2020-04-07 | 2020-04-10 | 2020-08-21 |  | 2020-09-04 |  | 2020-08-21 | 2020-08-21 | 2020-09-04 |  |  | 2020-08-21 |  |  | CS | 2020-08-21 | [6 empty] | CS |  |  | 2020-08-21 | [29 empty] | 2020-09-08 | [6 empty] | Pending |  |  |  |  | 2020-11-11 |  |  | 2021-06-08 | Addendum |  |  | 2020-11-12 | [8 empty] | 2020-11-12 | [17 empty] | 2020-11-18 | [13 empty] | 2021-06-10 |  | 2020-12-01 |  | 2020-12-01 | [8 empty] | 1679089 |  |  |  |  | 2021-11-24: 2020-12-08; 2021-12-28: 2020-12-08; 2023-04-25: 2021-06-11; 2023-04-25: 2021-06-11 | [17 empty] | 10300740956 | [11 empty] | TRUE | TRUE | 409 | 2020-12-08 | 2020-12-08 | 2020 | 2020 | 2020 | 44357 |  |  | 2021-06-08 | Addendum
410 |  | Eben Snow | Brent Brooks | 2020-03-30 | 2022-10-20 | wthdw |  | 2023-02-15 | L2_Bump | [26 empty] | 3 - LOVE |  | 430D1 | 234 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Colin Derhammer | MELINK SOLAR DEVELOPMENT | MELINK SOLAR DEVELOPMENT | Tree House Cove (Lovell) | 2000150090 | 30012185358 | Solar | [5 empty] | 44.1506 | -70.8882 | Tree House Cove |  |  | Lovell | 61 | LOVELL | 430D1 | 430T1 | 12.47 | 9310-L0164-3370-0030-ED00126 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2020-04-07 | 2020-04-06 | 2020-04-13 | 2020-04-07 | 2020-04-07 | 2021-08-10 | 2021-09-01 | 2021-08-24 | 2021-09-01 | 2021-09-02 | 2021-09-02 | 2021-09-17 |  |  | 2021-09-20 |  |  | CS | 2021-09-21 | [6 empty] | CS |  |  | 2021-09-21 |  |  | 2022-10-21 | [10 empty] | 2022-12-09 | [5 empty] | 2021-10-06 | 2021-10-06 | [8 empty] | 2021-10-06 | 2022-12-19 | [10 empty] | 2021-12-13 | 2022-02-03 | [5 empty] | 2021-12-03 | [8 empty] | 2021-12-03 | [8 empty] | 2021-12-03 | [8 empty] | 2021-12-06 | [7 empty] | 2021-12-06 | [7 empty] | 2021-12-14 |  | 2021-12-16 | 2022-09-20 | 2022-01-10 | 2022-10-18 | [9 empty] | 2023-04-06 | 2021-11-24: 2022-01-07; 2021-12-28: 2022-01-13; 2023-04-25: 2022-01-12; 2023-04-25: 2022-01-17 | [17 empty] | Requested | [11 empty] | TRUE | TRUE | 410 | 2022-01-07 | 2022-01-07 | 2022 | 2022 | 2022
411 |  |  | Anthony Boucher | 2020-03-30 | [31 empty] | 3 - THCR |  | 246D1 | 126 |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2021-03-30 | Tyler William Perkins | Nexamp, Inc | South Thomaston Solar LLC | Route 131 / South Thomaston | 2000114877 | 30013526139 | Solar | 4000 | 4 | 6513.48 |  |  | 44.5286 | -69.1702 | Route 131 |  |  | South Thomaston | 73 | THOMASTON CREEK | 246D1 | 34.5 kV Bus |  | 9310-L0081-5440-0048-ED00121 | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2020-04-08 | 2020-04-06 | 2020-04-13 | 2020-04-08 | 2020-04-08 | 2020-04-30 |  | 2020-05-14 |  | 2020-04-30 | 2020-04-30 | 2020-05-14 |  |  | 2020-05-13 | 2020-09-15 |  | CS | 2020-05-13 | RS | 2020-09-15 |  |  |  |  | CS |  |  | 2020-05-13 | 2020-09-15 | [10 empty] | 2020-06-03 | [17 empty] | 2020-06-04 | 2020-09-29 | [5 empty] | Pending |  |  |  |  | 2020-08-07 | 2020-11-11 |  | 2021-06-11 | Addendum |  |  | 2020-08-07 | 2020-11-16 | [7 empty] | 2020-08-07 | [17 empty] | 2020-08-11 | 2020-11-17 | [14 empty] | 2020-11-20 |  | 2020-11-22 | [8 empty] | 112874 | 2020-08-06 | 231228 | 2021-06-04 |  | 2021-11-24: 2020-12-01; 2021-12-28: 2020-12-01; 2023-04-25: 2021-08-27; 2023-04-25: 2021-09-16 | [17 empty] | 10300739364 | [11 empty] | TRUE | TRUE | 411 | 2020-12-01 | 2020-12-01 | 2020 | 2020 | 2020 |  |  |  | 2021-06-11 | Addendum
412 |  | Govinda Neupane |  | 2020-03-30 | 2022-05-31 | L2_Bump |  |  |  |  | 2024-12-09 | wthdw | [23 empty] | 4 - DOVE |  | 815D1 | 339 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | William Boyle | CleanTap Energy,LLC | Piscataquis Valley Solar LLC | 1123 W Main St, Dover Foxcroft | 2000146666 | 30013422545 | Solar | [5 empty] | 45.1813 | -69.2592 | 1123 West Main St |  |  | Dover-Foxcroft | 61 | DOVER | 815D1 | 815T1 | 12.47 | 9310-L0396-1650-0049-ED00030 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2020-04-07 | 2020-04-06 | 2020-04-13 | 2020-04-07 | 2020-04-13 | 2020-09-14 |  | 2020-09-28 |  | 2020-09-14 | 2020-09-14 | 2020-09-28 |  |  | 2020-09-25 | 2021-02-16 |  | CS | 2020-09-25 | RS | 2021-02-16 |  |  |  |  | CS |  |  | 2020-09-25 | 2021-02-16 |  | 2022-07-28 | [8 empty] | 2020-09-21 | 2021-02-16 |  | 2022-10-12 | [8 empty] | 2022-09-20 | [5 empty] | 2020-09-29 | 2021-03-01 |  | 2022-10-12 |  |  |  | Pending |  |  |  | 2022-09-09 | 2020-12-04 | 2021-04-12 |  | 2021-06-09 | Report |  |  | 2020-12-04 | 2021-06-09 |  | 2022-11-23 | [5 empty] | 2021-01-13 | 2021-06-09 |  | 2022-11-28 | [8 empty] | 2022-12-01 | [5 empty] | 2021-01-14 | 2021-07-13 |  | 2022-12-06 |  |  |  |  | 2021-01-14 | [7 empty] | 2021-07-14 |  | 2021-07-15 | 2023-01-19 | 2021-07-29 | 2023-01-23 | [5 empty] | 370149 | 2021-05-19 | 519411 | 2023-11-23 | 2024-12-18 | 2021-07-27 | 2021-07-27 | 2021-07-27 | 2021-07-27 | 2023-01-24 | 2023-01-24 | [19 empty] | Requested | [11 empty] | TRUE | TRUE | 412 | 2021-07-27 | 2021-07-27 | 2021 | 2021 | 2021 |  |  |  | 2021-06-09 | Report
413 |  | Lanie Patterson | Brent Brooks | 2020-04-01 | [31 empty] | 2 - RICH |  | 240D1 | 128 |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2021-01-04 | Jess Roden | RENESOLA POWER HOLDINGS | ME Richmond Lincoln St Solar LLC | Lincoln St Richmond | 2000149581 | 30015152579 | Solar | 1750 | 1.75 | 2464 |  |  | 44.1055 | -69.7961 | Lincoln Street |  |  | Richmond | 31 | RICHMOND | 240D1 | 240T1 |  | 9310-L0074-4940-0048-ED00027 | Non-FERC | TRIGGERING | TRIGGERING (325,000) | 206893 | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2020-04-08 | 2020-04-08 | 2020-04-15 | 2020-04-08 | 2020-04-08 | 2020-04-27 |  | 2020-05-11 |  | 2020-04-27 | 2020-04-27 | 2020-05-11 |  |  | 2020-05-07 |  |  | CS | 2020-05-07 | [6 empty] | CS |  |  | 2020-05-07 | [11 empty] | 2020-05-05 | [17 empty] | 2020-05-15 | [6 empty] | Pending |  |  |  |  | 2020-07-21 |  |  | 2021-05-18 | Addendum |  |  | 2020-07-15 | [8 empty] | 2020-07-16 | [17 empty] | 2020-07-20 | [13 empty] | 2021-05-19 |  | 2020-08-07 |  | 2020-08-13 | [8 empty] | 112522 | 2020-07-14 | 142031 | 2021-05-17 |  | 2021-11-24: 2020-08-18; 2021-12-28: 2020-08-18; 2023-04-25: 2021-06-18; 2023-04-25: 2021-06-18 | [17 empty] | 10300702814 | [11 empty] | TRUE | TRUE | 413 | 2020-08-18 | 2020-08-18 | 2020 | 2020 | 2020 | 44335 |  |  | 2021-05-18 | Addendum
414 |  | Rigel Paradise | Rick Duperre | 2020-04-01 | 2023-10-13 | L2_Bump | [29 empty] | 4 - LEBA |  | 695D2 | 98 | Yes | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2022-06-27 | Denise Murillo | Atlus Power LLC | ME West Lebanon Road Solar LLC | ME WEST LEBANON RD SOLAR LLC | 2000458967 | 30016451822 | Solar | 1998 | 1.998 | 2801 |  |  | 43.3667 | -70.9331 | W LEBANON RD |  |  | Lebanon | 26 | LEBANON | 695D2 | 695T1 | 12.47 | 9310-L0473-3190-0007-ED00093 | Non-FERC | TRIGGERING | TRIGGERING (255,000) | 102472 | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2020-04-08 | 2020-04-08 | 2020-04-15 | 2020-04-08 | 2020-04-15 | 2020-07-10 |  | 2020-07-24 |  | 2020-07-10 | 2020-07-13 | 2020-07-27 |  |  | 2020-07-27 |  |  | CS | 2020-07-27 | [6 empty] | CS |  |  | 2020-07-27 |  |  | 2023-10-16 | [20 empty] | 2023-12-05 | [5 empty] | 2020-08-14 |  |  | 2023-12-07 |  |  |  | Pending |  |  |  |  | 2020-10-20 |  |  | 2021-06-11 | Addendum |  |  | 2020-10-20 |  |  | 2024-03-01 | [5 empty] | 2020-10-21 |  |  | 2024-03-04 | [14 empty] | 2020-10-26 | [13 empty] | 2021-06-14 |  | 2020-11-04 |  | 2020-11-04 |  |  |  | 2024-06-14 |  |  |  |  | 155134 |  | 931486 |  |  | 2020-11-12 | 2020-11-12 | 2021-06-21 | 2021-06-21 | 2024-04-09 | 2024-04-09 | [19 empty] | 10300740956 | [11 empty] | TRUE | TRUE | 414 | 2020-11-12 | 2020-11-12 | 2020 | 2020 | 2020 | 44361 |  |  | 2021-06-11 | Addendum
415 |  |  | Anthony Boucher | 2020-04-01 | [31 empty] | 1 - BROO |  | 805D1 |  |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED |  | Spencer Egan | Encore Redevelopment, LLC | ER Brooks Solar | 96 Veterans Hwy, Brooks | 2000134579 | 30012542301 | Solar | 4000 | 4 | 6246 |  |  | 44.5445 | -69.1151 | 96 Veterans Highway |  |  | Brooks | 513 | BROOKS | 805D1 | 805T1 |  | 9310-L0384-0730-0024-ED00083 | Non-FERC | TRIGGERING | TRIGGERING | 330000 | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2020-04-08 | 2020-04-08 | 2020-04-15 | 2020-04-08 | 2020-04-08 | 2020-04-28 |  | 2020-05-12 |  | 2020-04-28 | 2020-04-28 | 2020-05-12 |  |  | 2020-05-11 |  |  | CS | 2020-05-11 | [6 empty] | CS |  |  | 2020-05-11 | [11 empty] | 2020-05-13 | [17 empty] | 2020-05-15 | [6 empty] | Pending |  |  |  |  | 2020-07-21 |  |  | 2021-05-04 | Addendum |  |  | 2020-07-20 | [8 empty] | 2020-07-20 | [17 empty] | 2020-07-23 | [13 empty] | 2021-05-10 |  | 2021-05-14 |  | 2020-07-28 |  |  |  | 2023-07-17 | 2023-07-17 |  |  |  | 787831 |  |  |  |  | 2021-11-24: 2020-08-18; 2021-12-28: 2020-08-18; 2023-04-25: 2021-05-18; 2023-04-25: 2021-05-18 |  |  |  | 2023-07-20 | [13 empty] | 10300700697 | [11 empty] | TRUE | TRUE | 415 | 2020-08-18 | 2020-08-18 | 2020 | 2020 | 2020 | 44326 |  |  | 2021-05-04 | Addendum
416 |  |  | Anthony Boucher | 2020-04-01 | [31 empty] | 1 - LINC |  | 800D1 |  |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2020-08-31 | Scott Moore | SunRaise Investments LLC | SEARSMONT RD LINCOLNVILLE SOLAR LLC | 105 Searsmont Rd, Lincolnville, Me | 2000163641 | 30012397854 | Solar | 4000 | 4 | 5752 |  |  | 44.3032 | -69.113 | 105 Searsmont Rd |  |  | Lincolnville | 5 5 | LINCOLNVILLE | 800D1 | 800T1 |  | 9310-L0378-3300-0084-ED00053 | Non-FERC | TRIGGERING | TRIGGERING | 375000 | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2020-04-08 | 2020-04-08 | 2020-04-15 | 2020-04-08 | 2020-04-08 | 2020-04-15 |  | 2020-04-30 |  | 2020-04-15 | 2020-04-15 | 2020-04-30 |  |  | 2020-04-21 |  |  | CS | 2020-04-21 | [6 empty] | CS |  |  | 2020-04-21 | [11 empty] | 2020-04-23 | [17 empty] | 2020-04-24 | [6 empty] | Yes |  |  |  |  | 2020-06-29 |  |  | 2021-05-21 | Addendum |  |  | 2020-06-29 | [8 empty] | 2020-06-30 | [17 empty] | 2020-07-06 | [13 empty] | 2021-06-15 |  | 2020-07-09 |  | 2020-07-09 | [8 empty] | 370997 |  |  |  |  | 2021-11-24: 2020-07-13; 2021-12-28: 2020-07-13; 2023-04-25: 2021-06-16; 2023-04-25: 2021-06-16 | [17 empty] | 10300690116 | [11 empty] | TRUE | TRUE | 416 | 2020-07-13 | 2020-07-13 | 2020 | 2020 | 2020 | 44362 |  |  | 2021-05-21 | Addendum
417 |  | Eben Snow | Brent Brooks | 2020-04-02 | [31 empty] | 7 - CROW |  | 411D1 | 394 |  | WITHDRAWN | WITHDRAWN |  | Rayo Bhumgara | Sustainable Strategies 2050 Inc | LEWISTON SOLAR 1 LLC | 2 Melissa Dr, Lewiston | 2000150062 | 30012184708 | Solar | [7 empty] | 2 Melissa Dr |  |  | Lewiston |  | CROWLEYS | 411D1 |  |  | FLOC-MISSING-01142021 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2020-04-09 | 2020-04-16 |  |  |  |  | 1900-01-12 | [127 empty] | 2021-02-18 | [37 empty] | TRUE | TRUE | 417 | 0 | 0 | 1900 | #VALUE! | #VALUE!
418 |  | Lanie Patterson | Brent Brooks | 2020-04-06 | 2023-12-06 | L2_Bump | [29 empty] | 4 - BOND |  | 208D2 | 388 | Yes | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Timothy Marvich | NEXTERA ENERGY RESOURCES | DG West River, LLC | 644 W River Rd Augusta | 2000147169 | 30015834069 | Solar | [5 empty] | 44.3569 | -69.7559 | 644 W River Rd |  |  | Augusta | 102 | BOND BROOK | 208D2 | 208T1 |  | 9310-L0022-0240-0381-ED00004 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2020-04-13 | 2020-04-13 | 2020-04-21 | 2020-04-13 | 2020-04-20 | 2020-07-28 |  | 2020-08-11 |  | 2020-07-28 | 2020-07-28 | 2020-08-11 |  |  | 2020-08-11 |  |  | CS | 2020-08-20 | FAC | [5 empty] | CS |  |  | 2020-08-20 |  | 2020-12-14 | 2024-03-11 | [8 empty] | 2020-08-17 |  |  | 2024-03-28 | [8 empty] | 2023-05-23 | [5 empty] | 2020-08-26 |  | 2020-12-18 | 2024-05-23 |  |  |  | Pending |  |  |  |  | 2020-10-30 |  | 2021-02-25 | 2021-05-18 | Addendum |  |  | 2020-10-30 |  | 2021-05-18 | 2024-07-24 | [5 empty] | 2020-10-30 |  | 2021-05-18 | 2024-07-24 | [8 empty] | 2024-08-05 | [5 empty] | 2020-11-09 |  |  | 2024-08-16 |  |  | 2020-11-09 |  | 2020-11-09 |  |  | 2024-08-16 |  |  | 2021-05-25 |  |  |  |  | 2022-08-30 |  | 2022-09-13 | [5 empty] | 1268402 |  | 1252482 | 2024-07-24 | 2025-05-28 | 2021-06-16 | 2021-06-16 | 2021-06-16 | 2021-06-16 | 2023-08-21 | 2023-08-21 |  |  |  |  | 2024-09-19 | 2024-09-19 | [9 empty] | Q4 2021 |  |  |  | 10300807117 | [11 empty] | FALSE | TRUE | 418 | 2021-06-16 | 2021-06-16 | 2021 | 2021 | 2021 | 44341 |  |  | 2021-05-18 | Addendum
419 |  | Govinda Neupane |  | 2020-04-06 | [31 empty] | 4 - ATHN |  | 827D1 | 409 |  | WITHDRAWN | WITHDRAWN |  | Mark Chrisos | Con Edison Clean Energy | CONSOLIDATED EDISON SOLUTIONS | #1 Harmony Rd Athens Solar Farm | 2800000074 | 30012230378 | Solar | [7 empty] | #1 Harmony Road |  |  | Athens |  | ATHENS | 827D1 |  |  | FLOC-MISSING-01142021 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2020-04-13 | 2020-04-21 |  |  |  |  | 1900-01-12 | [127 empty] | 2021-02-26 | [37 empty] | TRUE | TRUE | 419 | 0 | 0 | 1900 | #VALUE! | #VALUE!
420 |  | Govinda Neupane |  | 2020-04-06 | [31 empty] | 5 - ATHN |  | 827D1 | 419 |  | WITHDRAWN | WITHDRAWN |  | Mark Chrisos | Con Edison Clean Energy | CONSOLIDATED EDISON SOLUTIONS | #2 Harmony Rd Athens Solar Farms | 2800000074 | 30012230386 | Solar | [7 empty] | #2 Harmony Road |  |  | Athens |  | ATHENS | 827D1 |  |  | FLOC-MISSING-01142021 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2020-04-13 | 2020-04-21 |  |  |  |  | 1900-01-12 | [127 empty] | 2021-02-26 | [37 empty] | TRUE | TRUE | 420 | 0 | 0 | 1900 | #VALUE! | #VALUE!
421 |  | Govinda Neupane |  | 2020-04-06 | [31 empty] | 6 - ATHN |  | 827D1 | 420 |  | WITHDRAWN | WITHDRAWN |  | Mark Chrisos | Con Edison Clean Energy | CONSOLIDATED EDISON SOLUTIONS | #3 Harmony Rd Athens Solar Farms | 2800000074 | 30012230394 | Solar | [7 empty] | #3 Harmony Road |  |  | Athens |  | ATHENS | 827D1 |  |  | FLOC-MISSING-01142021 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2020-04-13 | 2020-04-21 |  |  |  |  | 1900-01-12 | [127 empty] | 2021-02-26 | [37 empty] | TRUE | TRUE | 421 | 0 | 0 | 1900 | #VALUE! | #VALUE!
422 |  | Govinda Neupane |  | 2020-04-06 | [31 empty] | 7 - ATHN |  | 827D1 | 421 |  | WITHDRAWN | WITHDRAWN |  | Mark Chrisos | Con Edison Clean Energy | CONSOLIDATED EDISON SOLUTIONS | #4 Harmony Rd Athens Solar Farms | 2800000074 | 30012230808 | Solar | [7 empty] | #4 Harmony Road |  |  | Athens |  | ATHENS | 827D1 |  |  | FLOC-MISSING-01142021 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2020-04-13 | 2020-04-21 |  |  |  |  | 1900-01-12 | [127 empty] | 2021-02-26 | [37 empty] | TRUE | TRUE | 422 | 0 | 0 | 1900 | 1900 | 1900
423 |  | Govinda Neupane |  | 2020-04-06 | [31 empty] | 8 - ATHN |  | 827D1 | 422 |  | WITHDRAWN | WITHDRAWN |  | Mark Chrisos | Con Edison Clean Energy | CONSOLIDATED EDISON SOLUTIONS | #5 Harmony Rd Athens Solar Farms | 2800000074 | 30012230816 | Solar | [7 empty] | #5 Harmony Road |  |  | Athens |  | ATHENS | 827D1 |  |  | FLOC-MISSING-01142021 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2020-04-13 | 2020-04-21 |  |  |  |  | 1900-01-12 | [127 empty] | 2021-02-26 | [37 empty] | TRUE | TRUE | 423 | 0 | 0 | 1900 | #VALUE! | #VALUE!
424 |  | Govinda Neupane |  | 2020-04-06 | [31 empty] | 9 - ATHN |  | 827D1 | 423 |  | WITHDRAWN | WITHDRAWN |  | Mark Chrisos | Con Edison Clean Energy | CONSOLIDATED EDISON SOLUTIONS | #6 Harmony Rd Athens Solar Farms | 2800000074 | 30012230824 | Solar | [7 empty] | #6 Harmony Road |  |  | Athens |  | ATHENS | 827D1 |  |  | FLOC-MISSING-01142021 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2020-04-13 | 2020-04-21 |  |  |  |  | 1900-01-12 | [127 empty] | 2021-02-26 | [37 empty] | TRUE | TRUE | 424 | 0 | 0 | 1900 | #VALUE! | #VALUE!
425 |  | Govinda Neupane |  | 2020-04-06 | [31 empty] | 10 - ATHN |  | 827D1 | 424 |  | WITHDRAWN | WITHDRAWN |  | Mark Chrisos | Con Edison Clean Energy | CONSOLIDATED EDISON SOLUTIONS | #7 Harmony Rd Athens Solar Farms | 2800000074 | 30012230832 | Solar | [7 empty] | #7 Harmony Road |  |  | Athens |  | ATHENS | 827D1 |  |  | FLOC-MISSING-01142021 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2020-04-13 | 2020-04-21 |  |  |  |  | 1900-01-12 | [127 empty] | 2021-02-26 | [37 empty] | TRUE | TRUE | 425 | 0 | 0 | 1900 | #VALUE! | #VALUE!
426 |  | Govinda Neupane |  | 2020-04-06 | [31 empty] | 11 - ATHN |  | 827D1 | 425 |  | WITHDRAWN | WITHDRAWN |  | Mark Chrisos | Con Edison Clean Energy | CONSOLIDATED EDISON SOLUTIONS | #8 Harmony Rd Athens Solar Farms | 2800000074 | 30012230840 | Solar | [7 empty] | #8 Harmony Road |  |  | Athens |  | ATHENS | 827D1 |  |  | FLOC-MISSING-01142021 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2020-04-13 | 2020-04-21 |  |  |  |  | 1900-01-12 | [127 empty] | 2021-02-26 | [37 empty] | TRUE | TRUE | 426 | 0 | 0 | 1900 | #VALUE! | #VALUE!
427 |  |  | Anthony Boucher | 2020-04-13 | [31 empty] | 4 - PROS |  | 846D1 | 405 |  | WITHDRAWN | WITHDRAWN |  | Nick Mazuroski | Dirigo/BNRG | BD SOLAR STOCKTON SPRINGS LLC | Old County Rd Stockton Springs | 2000152598 | 30012224314 | Solar | [7 empty] | Old County Rd |  |  | Stockton Springs |  | PROSPECT | 846D1 |  |  | 9310-L0426-5540-0016-ED00031 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2020-04-21 | 2020-04-28 |  |  |  |  | 1900-01-12 | [57 empty] | No Study | [69 empty] | 2022-01-19 | [37 empty] | TRUE | TRUE | 427 | 0 | 0 | 1900 | #VALUE! | #VALUE!
428 |  | Lanie Patterson | Brent Brooks | 2020-04-13 | [31 empty] | 3 - GARD |  | 226D2 | 221 |  | WITHDRAWN | WITHDRAWN |  | Jamal Batar | Dimension Renewable Energy | DIMENSION ME 1 LLC | 47 Market St, Gardiner Me | 2000123007 | 30012208408 | Solar | [7 empty] | 47 Market St |  |  | Gardiner |  | GARDINER | 226D2 |  |  | 9310-L0057-2190-0007-ED00006 | FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2020-04-21 | 2020-04-28 |  |  |  |  | 1900-01-12 | [57 empty] | Pending | [69 empty] | 2020-04-27 | [25 empty] | YES | [11 empty] | TRUE | TRUE | 428 | 0 | 0 | 1900 | #VALUE! | #VALUE!
429 |  | Lanie Patterson | Brent Brooks | 2020-04-13 | [31 empty] | 1 - WSST |  | 255D1 |  |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2021-01-04 | Liam McCormack | Summit Ridge Energy | GARDINER A LLC | Solar Farm West Hill Rd Gardiner | 2800000074 | 30015384636 | Solar | 4000 | 4 | 6989 |  |  | 44.2313 | -69.7913 | West Hill Rd |  |  | Gardiner | 3 | WEST STREET | 255D1 | 255T1 |  | 9310-L0093-2190-0131-ED00009 | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2020-04-20 | 2020-04-21 | 2020-04-28 | 2020-04-20 | 2020-04-20 | 2020-05-06 |  | 2020-05-20 |  | 2020-05-06 | 2020-05-06 | 2020-05-20 |  |  | 2020-05-11 |  |  | CS | 2020-05-11 | [6 empty] | CS |  |  | 2020-05-11 | [11 empty] | 2020-05-15 | [17 empty] | 2020-08-07 | [6 empty] | Pending |  |  |  |  | 2020-10-13 |  |  | 2021-05-24 | Addendum |  |  | 2020-10-13 | [8 empty] | 2020-07-20 | 2020-09-14 | [16 empty] | 2020-07-21 | 2020-09-17 | [12 empty] | 2021-06-15 |  | 2020-09-17 |  | 2020-09-18 | [8 empty] | 220835 |  |  |  |  | 2021-11-24: 2020-09-23; 2021-12-28: 2020-09-23; 2023-04-25: 2021-08-19; 2023-04-25: 2021-08-19 | [17 empty] | 10300716717 | [11 empty] | TRUE | TRUE | 429 | 2020-09-23 | 2020-09-23 | 2020 | 2020 | 2020 | 44362 |  |  | 2021-05-24 | Addendum
430 |  |  | Anthony Boucher | 2020-04-13 | [31 empty] | 2 - BROO |  | 805D1 | 415 |  | WITHDRAWN | WITHDRAWN |  | Justin Vanderbroeck | Renergetica USA | BROOKS ROAD SOLAR FARM LLC | 380 Monroe Hwy Brooks | 2000153782 | 30012242431 | Solar | [5 empty] | 44.5705 | -69.099 | 380 Monroe Hwy |  |  | Brooks |  | BROOKS | 805D1 |  |  | 9310-L0384-0730-0007-ED00053 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2020-04-21 | 2020-04-28 |  |  |  |  | 1900-01-12 | [57 empty] | Pending | [69 empty] | 2021-07-12 | [37 empty] | TRUE | TRUE | 430 | 0 | 0 | 1900 | #VALUE! | #VALUE!
431 |  | Govinda Neupane |  | 2020-04-13 | [31 empty] | 12 - ATHN |  | 827D2 | 426 |  | WITHDRAWN | WITHDRAWN |  | Nate Niles | REVISION ENERGY INC | REVISION ENERGY INC | 26 Gilman Farm Rd | 2000038393 | 30012244106 | Solar | [7 empty] | 26 Gilman Farm Rd |  |  | Athens |  | ATHENS | 827D2 |  |  | FLOC-MISSING-01142021 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2020-04-21 | 2020-04-28 |  |  |  |  | 1900-01-12 | [127 empty] | 2021-02-23 | [37 empty] | TRUE | TRUE | 431 | 0 | 0 | 1900 | #VALUE! | #VALUE!
432 |  | Govinda Neupane |  | 2020-04-17 | [31 empty] | 10 - STUR |  | 858D3 | 356 |  | WITHDRAWN | WITHDRAWN |  | Alan Tate | US Solar Development, LLC | USS FARMINGTON FALLS SOLAR LLC | Farmington Falls Rd Farmington | 2000154595 | 30012254915 | Solar | [5 empty] | 44.6292 | -70.0833 | Farmington Falls Rd |  |  | Farmington |  | STURTEVANT | 858D3 | 858T2 |  | 9310-L0440-2030-0125-ED00016 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2020-04-30 | 2020-04-27 | 2020-05-04 | 2020-04-30 | 2020-04-30 | 2022-09-05 | 2022-09-06 | 2022-09-20 | 2022-09-14 | 2022-09-14 | 2022-09-14 | 2022-09-28 | [123 empty] | 2022-09-28 | [37 empty] | TRUE | TRUE | 432 | 0 | 0 | 1900 | #VALUE! | #VALUE!
433 |  |  | Anthony Boucher | 2020-04-21 | [31 empty] | 3 - BROO |  | 805D1 | 430 |  | WITHDRAWN | WITHDRAWN |  | Daniel Serber | NEXTGRID INC | NEXTGRID INC | 20 Me-139 Monroe | 2000104939 | 30012228950 | Solar | [5 empty] | 44.61 | -69.02 | 20 ME-139 |  |  | Monroe |  | BROOKS | 805D1 | 805T1 |  | 9310-L0384-3750-0003-ED00084 (NEEDS TO BE CONFIRMED WITH DEVELOPER) | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  |  | 2020-04-28 | 2020-05-05 | 2020-04-30 | 2020-04-30 |  | 2021-07-12 | 1900-01-12 | 2021-07-16 | 2021-07-28 | 2021-07-28 | [6 empty] | CS | 2021-08-11 | [29 empty] | 2021-08-25 | 2021-08-25 | [8 empty] | 2021-08-31 | [11 empty] | 2021-11-04 | [57 empty] | 2022-05-16 | [6 empty] | 2022-01-24 | [25 empty] | STUDY | [11 empty] | TRUE | TRUE | 433 | 0 | 0 | 1900 | 1900 | 1900
434 |  | Lanie Patterson | Brent Brooks | 2020-04-21 | [9 empty] | 2024-11-06 | wthdw | [20 empty] | 5 - NOAU |  | 272D6 | 387 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Steve Buchsbaum | Solar Fields | SOLAR FIELDS LLC | 242 Manchester Rd Belgrade | 2000154736 | 30012256878 | Solar | [5 empty] | 44.4572 | -69.8479 | 242 Manchester Road |  |  | Belgrade | 24 | NORTH AUGUSTA | 272D6 | 272T2 | 34.5 | 9310-L0470-0440-0041-ED00032 (NEEDS TO BE CONFIRMED WITH DEVELOPER) | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2020-04-30 | 2020-04-28 | 2020-05-05 | 2020-04-30 | 2020-05-04 | 2022-02-02 | 2022-02-04 | 2022-02-16 | 2022-02-07 | 2022-02-10 | 2022-02-10 | 2022-02-25 |  |  | 2022-02-23 |  |  | CS | 2022-02-24 | [6 empty] | CS |  |  | 2022-02-24 |  | 2022-07-21 | [17 empty] | 2022-02-25 | 2022-02-25 | [8 empty] | 2022-03-01 | [11 empty] | 2022-05-04 | [6 empty] | 2022-05-09 | [8 empty] | 2022-05-09 | [8 empty] | 2022-05-16 | [8 empty] | 2022-05-16 | [7 empty] | 2022-05-16 | [7 empty] | 2022-07-28 |  | 2022-05-18 | 2022-07-28 | 2022-08-12 | 2022-08-12 | 2022-02-07 | 2022-02-14 | [7 empty] | 2024-12-16 | 2021-11-24: 2022-07-28; 2021-12-28: 2022-08-15 | [17 empty] | Requested | [11 empty] | TRUE | TRUE | 434 | 2022-07-28 | 2022-07-28 | 2022 | 2022 | 2022 |  |  |  |  | 2022-05-16
435 |  | Lanie Patterson | Brent Brooks | 2020-04-21 | [31 empty] | 1 - WEWA |  | 865D5 |  |  | WITHDRAWN | WITHDRAWN |  | Nate Niles | REVISION ENERGY INC | REVISION ENERGY INC | 519 Lincoln St (Waterville) | 2800283645 | 30012257066 | Solar | [7 empty] | 519 Lincoln St |  |  | Waterville |  | WEST WATERVILLE | 865D5 |  |  | 86-Withdrawn-86d | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2020-04-28 | 2020-05-05 |  |  |  |  | 1900-01-12 | [57 empty] | Yes | [69 empty] | 2021-08-19 | [37 empty] | TRUE | TRUE | 435 | 0 | 0 | 1900 | #VALUE! | #VALUE!
436 |  | Govinda Neupane |  | 2020-04-23 | [31 empty] | 2 - RUMF |  | 447D2 | 31 |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2020-11-20 | Chris Larkin | DSD Renewables | WYMAN HILL SOLAR LLC | Wyman Hill Rd Rumford | 2000154859 | 30012259476 | Solar | 3984 | 3.984 | 4800 |  |  | 44.5178 | -70.5181 | Wyman Hill Rd |  |  | Rumford | 39 | RUMFORD | 447D2 | 447T4 |  | 9310-L0187-5020-0151-ED00049 | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2020-04-30 | 2020-04-30 | 2020-05-07 | 2020-04-30 | 2020-04-30 | 2020-05-08 |  | 2020-05-22 |  | 2020-05-08 | 2020-05-08 | 2020-05-22 |  |  | 2020-05-12 |  |  | CS | 2020-05-12 | [6 empty] | CS |  |  | 2020-05-12 | [11 empty] | 2020-05-14 | [17 empty] | 2020-05-15 | [6 empty] | Pending |  |  |  |  | 2020-07-21 |  |  | 2021-05-21 | Addendum |  |  | 2020-07-21 | [8 empty] | 2020-07-21 | [17 empty] | 2020-07-27 | [15 empty] | 2020-08-03 |  | 2020-08-04 | [8 empty] | 145522 |  |  |  |  | 2021-11-24: 2020-08-26; 2021-12-28: 2020-08-26; 2023-04-25: 2021-06-10; 2023-04-25: 2021-06-10 | [17 empty] | 10300706416 | [11 empty] | TRUE | TRUE | 436 | 2020-08-26 | 2020-08-26 | 2020 | 2020 | 2020 |  |  |  | 2021-05-21 | Addendum
437 |  | Marshall Ripley | Rick Duperre | 2020-04-23 | [29 empty] | 1 - WSBR |  | 1 - WSBR |  | 674D2 |  |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2020-10-05 | Alyssa Hatigan Gattoni | CleanCapital Holdings LLC | Gorham Solar 1, LLC | 135 Brackett Rd, Gorham | 2000113260 | 30013394975 | Solar/Battery | 4990 | 4.99 | 7007 |  |  | 43.6638 | -70.4052 | 135 Brackett Rd |  |  | Gorham | 42 | WESTBROOK | 674D2 | 674T1 |  | 9310-L0339-2240-0007-ED00057 | Non-FERC | TRIGGERING | TRIGGERING | 325000 | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2020-04-30 | 2020-04-30 | 2020-05-07 | 2020-04-30 | 2020-04-30 | 2020-05-12 |  | 2020-05-27 |  | 2020-05-12 | 2020-05-13 | 2020-05-28 |  |  | 2020-05-19 |  |  | CS | 2020-05-19 | [6 empty] | CS |  |  | 2020-05-19 | [11 empty] | 2020-06-06 | [17 empty] | 2020-05-21 | [6 empty] | Pending |  |  |  |  | 2020-07-27 |  |  | 2021-06-09 | Addendum |  |  | 2020-07-27 | [8 empty] | 2020-07-30 | [17 empty] | 2020-08-04 | [13 empty] | 2021-06-22 |  | 2020-08-21 |  | 2020-08-24 | [8 empty] | 1076032 |  |  |  |  | 2021-11-24: 2020-08-26; 2021-12-28: 2020-08-26; 2023-04-25: 2021-08-03; 2023-04-25: 2021-08-03 | [17 empty] | 10300705938 | [11 empty] | FALSE | TRUE | 437 | 2020-08-26 | 2020-08-26 | 2020 | 2020 | 2020 | 44369 |  |  | 2021-06-09 | Addendum
438 |  | Ben Brooks | Anthony Boucher | 2020-04-23 | 2022-05-17 | L2_Bump |  | 2022-09-28 | L2_Bump | [26 empty] | 1 - PAST |  | 239D10 |  |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN | 2020-10-05 | Lulu Shao | ISM Solar Development LLC | ISM SOLAR BUTTERMILK FARM LLC | Buttermilk Ln (Thomaston) | 2000119678 | 30012490600 | Solar | [5 empty] | 44.86 | -69.143 | Dexter St |  |  | Thomaston | 12 | PARK STREET | 239D10 | 239T2 |  | 9310-L0071-5790-0007-ED00045 | Non-FERC | WITHDRAWN | WITHDRAWN | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2020-05-04 | 2020-04-30 | 2020-05-07 | 2020-05-04 | 2020-05-04 | 2020-05-18 |  | 2020-06-02 |  | 2020-05-18 | 2020-05-18 | 2020-06-02 |  |  | 2020-05-20 |  |  | CS | 2020-05-20 | [6 empty] | CS |  |  | 2020-05-20 |  |  | 2022-10-04 | [8 empty] | 2020-05-21 |  |  | 2022-10-03 | [14 empty] | 2020-05-22 |  |  | 2022-10-06 |  |  |  | Pending |  |  |  |  | 2020-07-28 | [6 empty] | 2020-07-28 |  |  | 2022-11-18 | [5 empty] | 2020-07-27 |  |  | 2022-11-21 | [14 empty] | 2020-08-03 | [15 empty] | 2020-08-03 |  | 2020-08-03 | 2022-12-01 |  | 2022-12-01 | [5 empty] | 141680 | 2022-07-28 | 239748 | 2022-11-18 | 2025-02-14 | 2020-08-10 | 2020-08-10 | 2021-10-06 | 2021-10-08 | 2022-12-05 | 2022-12-05 | [19 empty] | 10300701093 | [11 empty] | TRUE | TRUE | 438 | 2020-08-10 | 2020-08-10 | 2020 | 2020 | 2020
439 |  |  |  | 2020-04-23 | [31 empty] | 5 - WATE |  | 671T1 | 362 |  | WITHDRAWN | WITHDRAWN |  | Kevin Hu | NEXTERA ENERGY RESOURCES | SOLAR ROUND POND LLC | Do Not Use | 2000154905 | 30012260185 | Solar | [7 empty] | Lot 2 - Auburn Road |  |  | Turner |  | WATERBORO | 671T1 |  |  | 86-Withdrawn-86d | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2020-04-30 | 2020-05-07 |  |  |  |  | 1900-01-12 | [127 empty] | 2021-09-30 | [37 empty] | TRUE | TRUE | 439 | 0 | 0 | 1900 | #VALUE! | #VALUE!
440 |  | Eben Snow | Brent Brooks | 2020-04-23 | [31 empty] | 2 - NATP |  | 469D1 | 312 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Joseph Feole | Soltage LLC | NAPLES ROOSEVELT TRAIL SOLAR 1 LLC | Roosevelt Trail Naples | 2000176158 | 30012575780 | Solar | [5 empty] | 43.9644 | -70.5759 | Roosevelt Route 302 |  |  | Naples | 703 | NAPLES TAP | 469D1 | 469T1 |  | 9310-L0207-4040-0078-ED00359 | Non-FERC | WITHDRAWN | WITHDRAWN | 330000 | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2020-05-04 | 2020-04-30 | 2020-05-07 | 2020-05-04 | 2020-05-07 | 2020-09-08 |  | 2020-09-22 |  | 2020-09-08 | 2020-09-08 | 2020-09-22 |  |  | 2020-09-10 |  |  | CS | 2020-09-10 | [6 empty] | CS |  |  | 2020-09-10 | [29 empty] | 2020-09-14 | [6 empty] | Pending |  |  |  |  | 2020-11-17 |  |  | 2021-06-10 | Addendum |  |  | 2020-11-17 | [8 empty] | 2020-11-30 | [17 empty] | 2020-12-29 | [5 empty] | 2020-11-30 |  | 2020-11-30 | [7 empty] | 2020-12-29 |  | 2020-12-29 | [8 empty] | 754353 |  |  |  | 2024-05-08 | 2021-11-24: 2021-06-10; 2021-12-28: 2021-06-10; 2023-04-25: 2021-06-10; 2023-04-25: 2021-06-10 | [17 empty] | Requested | [11 empty] | TRUE | TRUE | 440 | 2021-06-10 | 2021-06-10 | 2021 | 2021 | 2021 |  |  |  | 2021-06-10 | Addendum
441 |  | Eben Snow | Brent Brooks | 2020-04-24 | 2022-06-08 | L2_Bump |  | 2022-07-27 | L2_Bump |  | 2023-01-18 | L2_With |  | 2023-07-10 | L2_Bump |  | 2023-09-26 | wthdw |  | 2023-10-05 | L2_Bump |  | 2024-01-17 | L2_Bump | [11 empty] | 6 - DEER |  | 412D3 | 404 |  | WITHDRAWN | WITHDRAWN |  | Kevin Hu | NEXTERA ENERGY RESOURCES | YOULAND SOLAR BARREL LLC | Lot 2 Auburn Rd Turner | 2000155531 | 30012269582 | Solar | [5 empty] | 44.2045 | -70.2458 | Lot 2 - Auburn Road |  |  | Turner |  | DEER RIPS | 412D3 | 412T4 |  | FLOC-MISSING-01142021 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2020-05-04 | 2020-05-01 | 2020-05-08 | 2020-05-04 | 2020-05-08 |  |  | 1900-01-12 | [127 empty] | 2024-04-05 | [37 empty] | TRUE | TRUE | 441 | 0 | 0 | 1900 | #VALUE! | #VALUE!
442 |  | Eben Snow | Brent Brooks | 2020-04-24 | 2022-06-08 | L2_Bump |  | 2022-07-27 | L2_Bump |  | 2023-01-18 | L2_With |  | 2023-07-10 | L2_Bump |  | 2023-09-26 | wthdw |  | 2023-10-05 | L2_Bump |  | 2024-01-17 | L2_Bump | [11 empty] | 7 - DEER |  | 412D3 | 441 |  | WITHDRAWN | WITHDRAWN |  | Kevin Hu | NEXTERA ENERGY RESOURCES | SOLAR ROUND POND LLC | Lot 11 Fern St Turner | 2000154905 | 30012260409 | Solar | [5 empty] | 44.1913 | -70.2458 | Lot 11 - Fern Street |  |  | Turner |  | DEER RIPS | 412D3 | 412T4 |  | FLOC-MISSING-01142021 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2020-05-04 | 2020-05-01 | 2020-05-08 | 2020-05-04 | 2020-05-08 |  |  | 1900-01-12 | [127 empty] | 2024-04-05 | [37 empty] | TRUE | TRUE | 442 | 0 | 0 | 1900 | #VALUE! | #VALUE!
443 |  | Eben Snow | Brent Brooks | 2020-04-24 | [31 empty] | 5 - GRAY |  | 416D1 | 385 |  | WITHDRAWN | WITHDRAWN |  | Christian L'Oranger | Fogler LLC | Fogler LLC | 0 Fickett Allen Rd Pownal | 2000174932 | 30012557176 | Solar | [5 empty] | 43.9351 | -70.208 | 0 Fickett Allen Rd |  |  | Pownal | 51 | GRAY | 416D1 | 416T2 |  | 9310-L0133-4743-0005-ED00010 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2020-05-04 | 2020-05-01 | 2020-05-08 | 2020-05-04 | 2020-05-08 | 2021-05-05 | 2021-05-04 | 2021-05-19 | 2021-05-05 | 2021-05-06 | 2021-05-06 | 2021-05-20 |  |  | 2021-05-26 | 2021-09-29 |  | CS | 2021-05-28 | RS | 2021-09-29 |  |  |  |  | CS |  |  | 2021-05-28 | 2021-09-29 | [10 empty] | 2021-05-28 | [7 empty] | 2021-05-28 | 2021-05-28 | 2021-10-10 | [7 empty] | 2021-06-03 | 2021-10-12 | [5 empty] | Yes Combined Study and Restudy performed |  |  |  |  | 2021-08-05 | 2021-11-24 | [5 empty] | 2021-08-13 | 2021-11-12 | [25 empty] | 2021-08-17 | 2021-11-12 | [6 empty] | 2021-08-17 | 2021-11-12 | [17 empty] | 2149037 | 2021-11-03 | n/a | n/a | 2022-02-01 | [25 empty] | Yes Combined Study and Restudy performed | [11 empty] | TRUE | TRUE | 443 | 0 | 0 | 1900 | 1900 | 1900
444 |  | Rigel Paradise | Rick Duperre | 2020-04-24 | [31 empty] | 2 - BRCM |  | 689D1 | 320 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN | 2022-06-27 | Nick Sampson | Dirigo/BNRG | BD SOLAR YORK LLC | Major Mcintire Rd, York | 2000155271 | 30012264963 | Solar | [5 empty] | 43.1596 | -70.71 | Major McIntire Rd |  |  | York | 10 | BRAGDON COMMONS | 689D1 | 689T1 |  | 9310-L0367-6660-0250-ED00002 | Non-FERC | WITHDRAWN | WITHDRAWN | NONE | Yes | 689D1 |  | K&L Engineering | Bruce Jagolinzer |  | 2020-05-04 | 2020-05-01 | 2020-05-08 | 2020-05-04 | 2020-05-04 | 2020-05-20 |  | 2020-06-04 |  | 2020-05-20 | 2020-05-20 | 2020-06-04 |  |  | 2020-06-02 |  |  | CS | 2020-06-02 | [6 empty] | CS |  |  | 2020-06-02 | [11 empty] | 2020-06-03 | [17 empty] | 2020-06-04 | [6 empty] | Pending |  |  |  |  | 2020-08-07 |  |  | 2021-06-21 | Addendum |  |  | 2020-08-06 | [8 empty] | 2020-08-07 | [17 empty] | 2020-08-11 | [14 empty] | 2022-06-16 | 2020-08-20 |  | 2020-08-24 | 2023-04-11 |  | 2023-04-11 | [5 empty] | 524563 |  | 1094354 | 2023-02-14 | 2023-06-02 | 2020-08-26 | 2020-08-26 | 2021-07-07 | 2021-07-07 | 2022-06-30 | 2022-07-27 | 2023-04-17 | 2023-04-18 | [17 empty] | 10300705913 | [11 empty] | TRUE | TRUE | 444 | 2020-08-26 | 2020-08-26 | 2020 | 2020 | 2020 |  |  |  | 2021-06-21 14:42 | Addendum
445 |  | Eben Snow | Brent Brooks | 2020-04-27 | [31 empty] | 6 - OXFO |  | 437D1 | 347 |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED |  | Liam McCormack | Summit Ridge Energy | SRE SOLAR ORIGINATION 2 LLC | Main St | 2000138691 | 30012264039 | Solar | 1625 | 1.625 | 2958 |  |  | 44.9289 | -70.2935 | Main Street |  |  | Oxford | 549 | OXFORD | 437D1 | 437T1 |  | 9310-L0178-4420-0064-ED00139 | Non-FERC | COST SHARE | COST SHARE (375,000) | 35607 | Yes | 437D1 |  | K&L Engineering | Bruce Jagolinzer |  | 2020-05-04 | 2020-05-04 | 2020-05-11 | 2020-05-04 | 2020-05-18 | 2020-06-17 |  | 2020-07-01 |  | 2020-06-17 | 2020-06-17 | 2020-07-01 |  |  | 2020-07-01 |  |  | CS | 2020-07-02 | RS | [5 empty] | CS |  |  | 2020-07-02 | [11 empty] | 2020-07-09 | [17 empty] | 2020-07-09 | 2020-11-10 | [5 empty] | Pending |  |  |  |  | 2020-09-11 | 2020-12-24 |  | 2021-05-19 | Addendum |  |  | 2020-09-11 | 2020-12-28 | [7 empty] | 2020-09-15 | 2021-02-03 | [16 empty] | 2020-09-16 | 2021-02-10 | [6 empty] | 2020-09-16 | 2021-02-10 |  |  |  |  | 2021-06-03 |  | 2021-06-03 | [5 empty] | 2023-07-13 |  |  |  |  | 421059 |  |  |  |  | 2021-11-24: 2021-06-03; 2021-12-28: 2021-06-03; 2023-04-25: 2021-06-03; 2023-04-25: 2021-06-03 |  |  |  | 2023-09-28 | 2025-07-14 | 2025-07-14 | [11 empty] | Requested | [11 empty] | TRUE | TRUE | 445 | 2021-06-03 | 2021-06-03 | 2021 | 2021 | 2021 | 44350 |  |  | 2021-05-19 | Addendum
446 |  | Rigel Paradise | Rick Duperre | 2020-04-27 | [31 empty] | 4 - BUCO |  | 612D1 | 384 |  | WITHDRAWN | WITHDRAWN |  | Mike Imoto | MEVS LLC AKA CENERGY | MEVS LLC | 987 Back Rd Shapleigh | 2000141275 | 30012270135 | Solar | [7 empty] | 987 Back Rd |  |  | Shapleigh |  | BUTLER'S CORNER | 612D1 |  |  | 9310-L0226-5300-0050-ED00015 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2020-05-04 | 2020-05-11 |  |  |  |  | 1900-01-12 | [127 empty] | 2020-06-08 | [37 empty] | TRUE | TRUE | 446 | 0 | 0 | 1900 | #VALUE! | #VALUE!
447 |  | Lanie Patterson | Brent Brooks | 2020-04-29 | [31 empty] | 3 - BOST |  | 263D1 | 377 |  | WITHDRAWN | WITHDRAWN |  | David Kane | LongRoad Development Company LLC | MAINE DG HOLDINGS LLC | 35 Togus Rd Chelsea | 2000149310 | 30012225584 | Solar | [7 empty] | 35 Togus Rd |  |  | Chelsea |  | BOWMAN STREET | 263D1 |  |  | 9310-L0102-1110-0025-ED00020 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2020-05-06 | 2020-05-13 |  |  |  |  | 1900-01-12 | [57 empty] | NO STUDY | [69 empty] | 2020-09-27 | [37 empty] | TRUE | TRUE | 447 | 0 | 0 | 1900 | #VALUE! | #VALUE!
448 |  | Rigel Paradise | Rick Duperre | 2020-04-30 | [31 empty] | 3 - BERW |  | 603D2 | 372 |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2022-06-27 | Jonathan Cole | Soltage LLC | BERWICK HUBBARD SOLAR 1 LLC | Hubbard Berwick | 2000176157 | 30012575772 | Solar | 3450 | 3.45 | 4345 |  |  | 43.3289 | -70.9075 | 424 Hubbard Rd |  |  | Berwick | 90 | BERWICK | 603D2 | 603T1 |  | 9310-L0214-0470-0037-ED00188 | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Yes | 603D2 |  | K&L Engineering | Bruce Jagolinzer |  | 2020-05-07 | 2020-05-07 | 2020-05-14 | 2020-05-07 | 2020-05-18 | 2020-07-21 |  | 2020-08-04 |  | 2020-07-21 | 2020-07-21 | 2020-08-04 |  |  | 2020-07-27 |  |  | CS | 2020-07-27 | [6 empty] | CS |  |  | 2020-07-27 | [11 empty] | 2020-08-17 | [17 empty] | 2020-07-27 | [6 empty] | Pending |  |  |  |  | 2020-09-29 | [6 empty] | 2020-09-29 | [8 empty] | 2020-10-01 | [17 empty] | 2020-10-07 | [15 empty] | 2020-10-28 |  | 2020-10-28 |  |  |  |  | 2024-05-30 |  |  |  | 650784 |  |  |  |  | 2020-11-14 | 2020-11-14 | 2021-07-28 | 2021-07-28 | 2023-10-27 | 2023-10-27 | 2024-06-12 | 2024-06-12 | 2024-06-19 | 2024-06-19 | [15 empty] | 10300735574 | [11 empty] | TRUE | TRUE | 448 | 2020-11-14 | 2020-11-14 | 2020 | 2020 | 2020
449 |  | Lanie Patterson | Brent Brooks | 2020-04-30 | [31 empty] | 3 - RICH |  | 240D1 | 413 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | James Marshall | Turning Point Energy | TPE ME RM02 LLC | Alexander Reed Rd, Richmond | 2000194698 | 30012825045 | Solar | [5 empty] | 44.1016 | -69.8157 | Alexander Reed Rd |  |  | Richmond | 31 | RICHMOND | 240D1 | 240T1 |  | 9310-L0074-4940-0002-ED00020 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes | 240D1 |  | K&L Engineering | Bruce Jagolinzer |  | 2020-05-07 | 2020-05-07 | 2020-05-14 | 2020-05-07 | 2020-05-18 | 2020-08-26 |  | 2020-09-10 |  | 2020-08-26 | 2020-08-26 | 2020-09-10 |  |  | 2020-08-26 |  |  | CS | 2020-08-26 | [6 empty] | CS |  |  | 2020-08-26 | [29 empty] | 2020-09-01 | [6 empty] | Pending |  |  |  |  | 2020-11-05 |  |  | 2021-05-18 | Addendum |  |  | 2020-11-05 | [8 empty] | 2020-11-05 | [17 empty] | 2020-11-10 | [13 empty] | 2021-05-24 |  | 2021-05-24 |  | 2020-11-10 | 2021-05-24 | 2021-06-21 | [6 empty] | 474641 | 2020-10-28 | 1022029 | 2023-02-15 | 2023-10-19 | 2020-11-12 | 2020-11-12 | 2021-06-22 | 2021-06-22 | 2022-09-15 | 2022-09-15 | [19 empty] | 10300733809 | [11 empty] | TRUE | TRUE | 449 | 2020-11-12 | 2020-11-12 | 2020 | 2020 | 2020 | 44340 |  |  | 2021-05-18 | Addendum
450 |  | Eben Snow | Brent Brooks | 2020-05-04 | 2023-01-09 | L2_Bump | [29 empty] | 2 - PAPO |  | 438D1 | 295 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Greg Rosshirt | BORREGO SOLAR SYSTEMS INC | 510 PV PROJECT DEVELOPMENT LLC | Bisbee Town Rd (Waterford) | 2000113260 | 30012249097 | Solar/Battery | [5 empty] | 44.2459 | -70.7334 | Bisbee Town Rd |  |  | Waterford | 5 | PAPOOSE POND | 438D1 | Tap off of Transmission Line |  | 9310-L0180-6205-0003-ED00002 | Non-FERC | WITHDRAWN | WITHDRAWN | NONE | Yes | 438D1 |  | K&L Engineering | Bruce Jagolinzer |  | 2020-05-14 | 2020-05-11 | 2020-05-18 | 2020-05-14 | 2020-05-18 | 2020-06-01 |  | 2020-06-15 |  | 2020-06-01 | 2020-06-01 | 2020-06-15 |  |  | 2020-06-01 |  |  | CS | 2020-06-01 | [6 empty] | CS |  |  | 2020-06-01 | [11 empty] | 2020-06-06 | [17 empty] | 2020-06-04 | [6 empty] | Pending |  |  |  |  | 2020-08-07 |  |  | 2021-05-20 | Addendum |  |  | 2020-08-06 | [8 empty] | 2020-08-06 | [17 empty] | 2020-08-10 | [13 empty] | 2021-06-07 |  | 2020-08-14 |  | 2020-08-17 | [8 empty] | 772915 |  |  |  | 2023-02-14 | 2020-11-14: 2020-08-20; 2020-11-14: 2020-08-20 | [15 empty] | 10300706442 | [11 empty] | TRUE | TRUE | 450 | 2020-08-20 | 2020-08-20 | 2020 | 2020 | 2020 | 44354 |  |  | 2021-05-20 | Addendum
451 |  | Rigel Paradise | Rick Duperre | 2020-05-04 | 2023-10-13 | L2_Bump | [28 empty] | 414 | 5 - LEBA |  | 695D1 | 414 | Yes | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2022-06-27 | Jonathan Cole | Soltage LLC | LEBANON WEST LEBANON SOLAR 1 LLC | West Lebanon Rd Lebanon | 2000176861 | 30012586423 | Solar | 1999 | 1.999 | 2949.75 |  |  | 43.3771 | -70.9452 | West Lebanon |  |  | Lebanon | 508 | LEBANON | 695D1 | 695T1 | 12.47 | 9310-L0472-3190-0005-ED00003 | Non-FERC | COST SHARE | COST SHARE (255,000) | 102523.13 | Yes | 695D1 |  | K&L Engineering | Bruce Jagolinzer |  | 2020-05-13 | 2020-05-11 | 2020-05-18 | 2020-05-13 | 2020-05-18 | 2020-11-19 |  | 2020-12-07 |  | 2020-11-19 | 2020-11-20 | 2020-12-08 |  |  | 2020-11-24 |  |  | CS | 2020-11-24 | [6 empty] | CS |  |  | 2020-11-24 |  |  | 2024-04-10 | [11 empty] | 2024-04-23 | [8 empty] | 2024-04-23 | [5 empty] | 2020-12-08 |  |  | 2024-04-22 | [8 empty] | 2021-02-12 |  |  | 2021-06-11 | Addendum |  |  | 2021-02-12 |  |  | 2024-05-17 | [5 empty] | 2021-02-19 |  |  | 2024-05-17 | [8 empty] | N/A | [5 empty] | 2021-02-24 |  |  | N/A |  |  |  |  | 2021-02-24 | [5 empty] | 2021-06-11 |  | 2021-06-16 | 2021-06-18 | 2021-06-18 | 2024-05-20 |  |  | 2023-08-08 | 2023-08-08 |  |  |  | 284262 |  | 544683.83 | 2024-05-17 |  | 2020-11-14: 2021-06-21; 2020-11-14: 2021-06-21; 2021-07-28: 2024-05-23; 2021-07-28: 2024-05-23 | 2023-10-11 | 2023-10-11 | [9 empty] | Q4 2021 |  |  |  | Requested | [11 empty] | TRUE | TRUE | 451 | 2021-06-21 | 2021-06-21 | 2021 | 2021 | 2021 | 44358 |  | 44365 | 2021-06-11 | Addendum
452 |  |  | KRISTOFER COLEMAN | 2020-05-04 | [31 empty] | 4 - TP34 |  | 250D1 | 222 |  | WITHDRAWN | WITHDRAWN |  | David Kane | LongRoad Development Company LLC | MAINE DG HOLDINGS LLC | Booker Rd Bowdoin | 2000149310 | 30012250665 | Solar | [7 empty] | Booker Rd |  |  | Bowdoin |  | TOPSHAM 34 KV | 250D1 |  |  | 9310-L0086-0570-0011-ED00041 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2020-05-11 | 2020-05-18 |  |  |  |  | 1900-01-12 | [57 empty] | No Study | [69 empty] | 2021-01-19 | [37 empty] | TRUE | TRUE | 452 | 0 | 0 | 1900 | #VALUE! | #VALUE!
453 |  | Marshall Ripley | Rick Duperre | 2020-05-04 | [31 empty] | 1 - PLHL |  | 644D2 |  |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2020-10-05 | Nate Niles | REVISION ENERGY INC | CITY OF SO PORTLAND | 929 Highland Ave | 2800031142 | 30012274020 | Solar | 2500 | 2.5 | 3873 |  |  | 43.6149 | -70.2823 | 929 Highland Ave |  |  | South Portland | 5 | PLEASANT HILL | 644D2 | 644T2 |  | 9310-L0286-5430-0494-PM00004 | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Yes | 644D2 |  | K&L Engineering | Bruce Jagolinzer |  | 2020-05-14 | 2020-05-11 | 2020-05-18 | 2020-05-14 | 2020-05-14 | 2020-05-29 |  | 2020-06-12 |  | 2020-05-29 | 2020-05-29 | 2020-06-12 |  |  | 2020-06-12 |  |  | CS | 2020-06-15 | [6 empty] | CS |  |  | 2020-06-15 | [11 empty] | 2020-06-29 | [17 empty] | 2020-07-02 | [6 empty] | Pending |  |  |  |  | 2020-09-04 |  |  | 2021-05-20 | Addendum |  |  | 2020-09-03 | [8 empty] | 2020-09-14 | [17 empty] | 2020-09-17 | [13 empty] | 2021-06-14 |  | 2020-10-12 | 2021-08-04 | 2020-10-15 | [8 empty] | 314174 |  | 166674 |  |  | 2020-11-14: 2020-10-15; 2020-11-14: 2020-10-15; 2021-07-28: 2021-08-04; 2021-07-28: 2021-10-27 | [15 empty] | 10300731288 | [11 empty] | TRUE | TRUE | 453 | 2020-10-15 | 2020-10-15 | 2020 | 2020 | 2020 | 44361 |  | 44412 | 2021-05-20 | Addendum
454 |  |  |  | 2020-05-05 | [31 empty] | 1 - PNSY | 1 - PNSY | PNSY |  |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED |  | Tom Holt | Ameresco, Inc | COMMANDER NAVY REGION |  | 2800862923 | 35012553034 | CTG/Battery | 6800 | 6.8 |  | 1000 | [6 empty] | Kittery |  | PNSY | PNSY | XXXDX3 |  | FLOC-MISSING-01142021 | Non-FERC | NOT IMPACTED | NOT IMPACTED |  |  | XXXDX |  | MEG SULLIVAN |  |  | 2020-05-14 | 2020-05-12 | 2020-05-19 | 2020-05-14 | 2020-05-14 | 2020-05-29 | 2020-05-29 | 2020-06-12 | 2020-05-29 | 2020-05-29 | 2020-05-29 | 2020-06-12 | [5 empty] | CS | [7 empty] | TX | [22 empty] | 2021-12-17 | 2021-12-17 | [8 empty] | 2021-12-17 | [18 empty] | 2021-12-17 | [26 empty] | 2021-12-17 | [7 empty] | 2021-12-17 | [7 empty] | 2021-12-17 |  | 2021-12-17 |  | 2021-12-17 | [11 empty] | 2020-11-14: 2021-12-17; 2020-11-14: 2022-01-07 | [15 empty] | Requested | [11 empty] | TRUE | TRUE | 454 | 2021-12-17 | 2021-12-17 | 2021 | 2022 | 2022
455 |  | Lanie Patterson | Brent Brooks | 2020-05-07 | [31 empty] | 3 - CAST |  | 215D2 | 392 |  | WITHDRAWN | WITHDRAWN |  | Lulu Shao | ISM Solar Development LLC | ISM SOLAR DEVELOPMENT LLC | Parkwoods Dr Augusta | 2000119678 | 30012297401 | Solar | [7 empty] | Parkwood Dr |  |  | Augusta |  | CAPITOL STREET | 215D2 |  |  | 9310-L0038-0240-0163-ED00006 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2020-05-14 | 2020-05-21 |  |  |  |  | 1900-01-12 | [127 empty] | 2020-08-24 | [37 empty] | TRUE | TRUE | 455 | 0 | 0 | 1900 | #VALUE! | #VALUE!
456 |  |  | Anthony Boucher | 2020-05-07 | [31 empty] | 4 - THCR |  | 246D3 | 411 |  | WITHDRAWN | WITHDRAWN |  | Santiago Quijano | Bluewave MA, LLC | BLUE WAVE PROJECT DEVELOPMENT | Beachwood Thomaston | 2000153960 | 30012244726 | Solar | [7 empty] | Beachwood Rd. |  |  | Thomaston |  | THOMASTON CREEK | 246D3 |  |  | 9310-L0083-5790-0003-ED00064 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2020-05-14 | 2020-05-21 |  |  |  |  | 1900-01-12 | [57 empty] | No Study | [69 empty] | 2020-12-01 | [37 empty] | TRUE | TRUE | 456 | 0 | 0 | 1900 | #VALUE! | #VALUE!
457 |  | Rigel Paradise | Rick Duperre | 2020-05-08 | [31 empty] | 1 - SOBE |  | 663D2 |  |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN | 2022-06-27 | Ryan Darlow | Norwich Solar Technologies | YORK SOLAR I LLC | 774 Witch Trot Rd York | 2000157335 | 30012299670 | Solar | [5 empty] | 43.1958 | -70.7475 | 74 Witchtrot Road |  |  | York | 14 | SOUTH BERWICK | 663D2 | 663T1 |  | 9310-L0332-6660-0305-ED00039 | FERC | WITHDRAWN | WITHDRAWN | NONE | Yes | 663D2 |  | K&L Engineering | Bruce Jagolinzer |  | 2020-05-18 | 2020-05-15 | 2020-05-22 | 2020-05-18 | 2020-05-18 | 2020-06-08 |  | 2020-06-22 |  | 2020-06-08 | 2020-06-08 | 2020-06-22 |  |  | 2020-06-12 |  |  | CS | 2020-06-12 | [6 empty] | CS |  |  | 2020-06-12 | [11 empty] | 2020-06-15 | [17 empty] | 2020-06-24 | [6 empty] | Pending |  |  |  |  | 2020-08-27 |  |  | 2021-06-04 | Addendum |  |  | 2020-08-27 | [8 empty] | 2020-08-28 | [17 empty] | 2020-09-08 | [13 empty] | 2021-06-17 |  | 2020-09-28 |  | 2020-09-30 | [8 empty] | 559769 |  | 1255044 | 2022-06-17 | 2023-08-03 | 2020-11-14: 2020-10-28; 2020-11-14: 2020-10-28; 2021-07-28: 2021-07-07; 2021-07-28: 2021-07-07 | [15 empty] | 10300731190 | 10300731190 | [10 empty] | TRUE | TRUE | 457 | 2020-10-28 | 2020-10-28 | 2020 | 2020 | 2020 | 44364 |  |  | 2021-06-04 | Addendum
458 |  | Govinda Neupane |  | 2020-05-08 | [31 empty] | 4 - SKSS |  | 854D1 | 386 |  | WITHDRAWN | WITHDRAWN |  | Nick Mazuroski | Dirigo/BNRG | BD SOLAR SUNSET HILL LLC | Sunset Hill Rd / Norridgewock | 2000155338 | 30012266711 | Solar | [7 empty] | SUNSET HILL RD |  |  | Norridgewock |  | SKOWHEGAN SOUTH SIDE | 854D1 |  |  | 86-Withdrawn-86d | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2020-05-15 | 2020-05-22 |  |  |  |  | 1900-01-12 | [127 empty] | 2020-06-29 | [37 empty] | TRUE | TRUE | 458 | 0 | 0 | 1900 | #VALUE! | #VALUE!
459 |  | Govinda Neupane |  | 2020-05-08 | [31 empty] | 1 - EWIL |  | 816D1 |  |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2021-06-01 | Jess Roden | Greenbacker Capital | ER Pleasant St. Solar, LLC | 15 Pleasant St Wilton | 2000190964 | 30016165331 | Solar | 3000 | 3 | 4137.12 |  |  | 44.6192 | -70.1912 | Pleasant Street |  |  | Wilton | 7 | EAST WILTON | 816D1 | 816T1 |  | 9310-L0398-6380-0075-ED00022 | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2020-05-20 | 2020-05-15 | 2020-05-22 | 2020-05-20 | 2020-05-20 | 2020-06-09 |  | 2020-06-23 |  | 2020-06-09 | 2020-06-09 | 2020-06-23 |  |  | 2020-06-11 |  |  | CS | 2020-06-11 | [6 empty] | CS |  |  | 2020-06-11 | [11 empty] | 2020-06-15 | [17 empty] | 2020-06-17 | [6 empty] | Pending |  |  |  |  | 2020-08-20 |  |  | 2021-06-08 | Addendum |  |  | 2020-08-20 | [8 empty] | 2020-08-19 | [17 empty] | 2020-08-24 | [15 empty] | 2020-08-26 |  | 2020-08-31 | [8 empty] | 195546 |  |  |  |  | 2020-11-14: 2020-09-16; 2020-11-14: 2020-09-16; 2021-07-28: 2021-06-11; 2021-07-28: 2021-06-11 | [15 empty] | 10300714006 | [11 empty] | TRUE | TRUE | 459 | 2020-09-16 | 2020-09-16 | 2020 | 2020 | 2020 |  |  |  | 2021-06-08 | Addendum
460 |  | Govinda Neupane |  | 2020-05-11 | 2022-05-31 | L2_Bump |  |  |  |  | 2024-12-09 | wthdw |  | 2024-12-18 | wthdw | [20 empty] | 5 - DOVE |  | 815D2 | 412 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Nate Niles | REVISION ENERGY INC | REVISION ENERGY INC | Summer St Dover Foxcroft | 2022346231 | 30012306426 | Solar | [5 empty] | 45.1947 | -69.2152 | Summer St |  |  | Dover-Foxcroft | 40 | DOVER | 815D2 | 815T2 | 12.47 | FLOC-MISSING-01142021 | FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2020-05-19 | 2020-05-18 | 2020-05-26 | 2020-05-19 | 2020-05-22 | 2021-08-12 |  | 2021-08-26 |  | 2021-09-02 | 2021-09-02 | 2021-09-17 |  |  | 2021-09-17 |  |  | CS | 2021-09-17 | [6 empty] | CS |  |  | 2021-09-17 |  |  | 2023-02-17 | [11 empty] | 2023-02-21 | [8 empty] | 2023-04-05 | [5 empty] | 2021-09-30 |  |  | 2023-04-05 | [8 empty] | 2021-12-07 | [9 empty] | 2023-05-18 | [5 empty] | 2021-12-07 |  |  | 2023-05-18 |  |  |  |  | 2021-12-06 |  |  |  | 2023-05-19 | [7 empty] | 2021-12-07 | 2023-05-25 | [12 empty] | 2021-12-13 |  | 2021-12-13 | 2023-06-08 |  | 2023-06-08 | [7 empty] | 296368 | 2023-05-12 | 2025-01-06 | 2020-11-14: 2021-12-13; 2020-11-14: 2021-12-16; 2021-07-28: 2023-06-09; 2021-07-28: 2023-06-09 | [15 empty] | Requested | [11 empty] | TRUE | TRUE | 460 | 2021-12-13 | 2021-12-13 | 2021 | 2021 | 2021
461 |  | Govinda Neupane |  | 2020-05-11 | 2023-07-20 | L2_Bump | [29 empty] | 2 - WILT |  | 885D1 | 83 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | David Watts | US Solar Development, LLC | USS MAPLE SOLAR LLC | Weld Rd, Wilton | 2000157553 | 30012302870 | Solar | [5 empty] | 44.6218 | -70.278 | Weld Rd |  |  | Wilton |  | WILTON | 885D1 | 885T1 |  | 9310-L0467-6380-0118-ED00177 | Non-FERC | WITHDRAWN | WITHDRAWN | 330000 | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2020-05-20 | 2020-05-18 | 2020-05-26 | 2020-05-20 | 2020-05-20 | 2020-06-10 |  | 2020-06-24 |  | 2020-06-10 | 2020-06-10 | 2020-06-24 |  |  |  | 2023-12-13 |  | FS | 2020-06-22 | IS | 2020-09-17 |  |  |  |  | Split | 2020-06-22 | 2020-09-17 |  | 2023-12-13 |  | 2023-07-20 | [7 empty] | 2020-06-29 |  | 2023-12-26 |  | 2023-08-14 | [6 empty] | 2023-12-26 |  | 2023-08-14 |  |  |  | 2020-07-02 | 2020-09-29 |  | 2023-12-26 |  | 2023-08-17 | [6 empty] | 2020-08-07 | 2020-11-11 |  | 2023-02-08 |  | 2021-04-30 | Addendum | 2020-08-06 | 2020-11-12 |  | 2024-02-08 |  | 2023-09-29 | 2024-02-08 |  |  | 2020-09-08 | 2020-12-03 |  | 2024-02-08 |  | 2023-10-13 | 2024-02-08 | [5 empty] | 2024-02-20 |  | 2023-10-13 | 2024-02-12 |  |  | 2020-09-10 | 2020-12-08 |  | 2024-02-20 |  | 2023-10-17 | 2024-02-20 |  | 2020-12-08 |  |  | 2024-02-20 |  | 2023-10-17 | 2024-02-02 |  | 2021-05-25 |  | 2020-12-10 |  |  | 2023-01-09 | [7 empty] | 1433623 |  | 952785 | 2023-09-29 | 2024-10-30 | 2021-08-30 | 2021-08-30 | 2021-08-30 | 2021-08-30 | 2024-04-09 | 2024-04-09 | [19 empty] | Requested | [11 empty] | TRUE | TRUE | 461 | 2021-08-30 | 2021-08-30 | 2021 | 2021 | 2021 | 44341 |  |  | 2021-04-30 | Addendum
462 |  | Lanie Patterson | Brent Brooks | 2020-05-11 | [31 empty] | 6 - NOAU |  | 272D2 | 434 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Gemma Sherman | SunRaise Investments LLC | SUNRAY POWER LLC | Commerce Dr Augusta | 2000157866 | 30012307564 | Solar | [5 empty] | 44.3637 | -69.7975 | Commerce Dr |  |  | Augusta | #9.1 | NORTH AUGUSTA | 272D2 | 272T1 |  | 9310-L0105-0240-0182-MH00012 (NEEDS TO BE CONFIRMED WITH DEVELOPER) | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2020-05-20 | 2020-05-18 | 2020-05-26 | 2020-05-20 | 2020-05-26 | 2022-08-15 | 2022-08-17 | 2022-08-17 | 2022-08-17 | 2022-08-17 | 2022-08-18 | 2022-08-31 |  |  | 2022-08-30 |  |  | CS | 2022-08-25 | [6 empty] | CS |  |  | 2022-09-13 | [11 empty] | 2022-08-31 | [8 empty] | 2022-09-28 | [8 empty] | 2022-09-29 | [11 empty] | 2022-12-07 | [6 empty] | 2022-12-06 | [8 empty] | 2022-12-07 | [8 empty] | 2022-12-07 | [7 empty] | 2022-12-12 | [7 empty] | 2022-12-12 | [8 empty] | 2023-01-04 |  | 2023-01-04 | 2023-01-04 | 2023-01-13 | [6 empty] | 629538 | 2022-12-05 |  |  | 2024-04-22 | 2020-11-14: 2023-01-13; 2020-11-14: 2023-01-13 | [15 empty] | Requested | [11 empty] | TRUE | TRUE | 462 | 2023-01-13 | 2023-01-13 | 2023 | 2023 | 2023
463 |  | Govinda Neupane |  | 2020-05-13 | 2022-11-08 | L2_Bump |  | 2023-01-09 | L2_bump |  | 2023-05-08 | L2_bump |  | 2023-07-18 | L2_Bump |  | 2023-10-05 | L2_Bump | [17 empty] | 11 - STUR |  | 858D4 | 432 |  | WITHDRAWN | WITHDRAWN |  | William Boyle | CleanTap Energy,LLC | CLEANTAP ENERGY LLC | 291 Maple Ave Farmington Me | 2000146666 | 30012134588 | Solar/Battery | [5 empty] | 44.5517 | -70.1289 | Cascade Leisure Park Road |  |  | Farmington | 10 | STURTEVANT | 858D4 | 858T2 | 12.47 | 9310-L0441-2030-0085-ED00047 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2020-05-21 | 2020-05-20 | 2020-05-28 | 2020-05-21 | 2020-05-28 | 2022-09-28 | 2022-09-29 | 2022-10-13 | 2022-10-10 | 2022-10-10 | 2022-10-10 | 2022-10-25 |  |  | 2022-10-25 |  |  | CS | 2022-10-25 | [9 empty] | 2022-11-08 | [7 empty] | 2024-06-10 |  |  |  | 2024-06-07 | [8 empty] | 2024-06-10 | [8 empty] | 2024-06-10 | [11 empty] | 2024-08-14 | [6 empty] | 2024-08-07 | [8 empty] | 2024-08-07 | [8 empty] | N/A | [8 empty] | N/A | [7 empty] | N/A | [7 empty] | 2024-08-21 |  | 2024-08-21 | [8 empty] | 152124 | 2024-08-06 |  |  | 2024-10-14 | [37 empty] | TRUE | TRUE | 463 | 0 | 0 | 1900 | #VALUE! | #VALUE!
464 |  | Marshall Ripley | Rick Duperre | 2020-05-13 | [31 empty] | 3 - SWRD |  | 682D1 | 202 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | James Marshall | Turning Point Energy | TPE ME WH02 LLC | Swett Rd Windham | 2000194097 | 30012817448 | Solar | [5 empty] | 43.7637 | -70.4048 | Swett Rd |  |  | Windham |  | SWETT ROAD | 682D1 | 682T1 |  | 9310-L0361-6390-0108-ED00006 | Non-FERC | WITHDRAWN | WITHDRAWN | 325000 | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2020-05-21 | 2020-05-20 | 2020-05-28 | 2020-05-21 | 2020-05-28 | 2020-08-03 |  | 2020-08-17 |  | 2020-08-03 | 2020-08-03 | 2020-08-17 |  |  | 2020-08-05 |  |  | CS | 2020-08-05 | [6 empty] | CS |  |  | 2020-08-05 | [11 empty] | 2020-08-11 | [17 empty] | 2020-08-10 | [6 empty] | Pending |  |  |  |  | 2020-10-14 |  |  | 2021-05-20 | Addendum |  |  | 2020-10-14 | 2022-07-28 | [7 empty] | 2020-10-27 | [17 empty] | 2020-11-03 | [13 empty] | 2021-06-07 |  | 2020-11-10 |  | 2020-11-12 | [8 empty] | 776964 |  |  |  | 2023-10-19 | 2020-11-14: 2020-11-14; 2020-11-14: 2020-11-14; 2021-07-28: 2021-06-29; 2021-07-28: 2021-06-29 | [15 empty] | 10300740222 | [11 empty] | TRUE | TRUE | 464 | 2020-11-14 | 2020-11-14 | 2020 | 2020 | 2020 | 44354 |  |  | 2021-05-20 | Addendum
465 |  | Eben Snow | Brent Brooks | 2020-05-13 | [31 empty] | 3 - PAPO |  | 438D1 | 450 |  | WITHDRAWN | WITHDRAWN |  | Nate Niles | REVISION ENERGY INC | REVISION ENERGY INC | 1008 Valley Rd Waterford | 2800182538 |  | Solar | [7 empty] | 1008 Valley Rd |  |  | Waterford |  | PAPOOSE POND | 438D1 |  |  | 9310-L0180-6205-0088-ED00054 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2020-05-20 | 2020-05-28 |  |  |  |  | 1900-01-12 | [57 empty] | Pending | [69 empty] | 2021-05-26 | [37 empty] | TRUE | TRUE | 465 | 0 | 0 | 1900 | #VALUE! | #VALUE!
466 |  | Rigel Paradise | Rick Duperre | 2020-05-13 | [31 empty] | 2 - HIST |  | 626D1 | 9 |  | WITHDRAWN | WITHDRAWN |  | Mike Imoto | MEVS LLC AKA CENERGY | MAINE SOLAR DEVELOPMENT LLC | Main St Sanford | 2000141274 | 30012311012 | Solar | [7 empty] | Main St |  |  | Sanford |  | HIGH STREET | 626D1 |  |  | 9310-L0321-5170-0220-ED00400 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2020-05-20 | 2020-05-28 |  |  |  |  | 1900-01-12 | [127 empty] | 2020-11-08 | [37 empty] | TRUE | TRUE | 466 | 0 | 0 | 1900 | #VALUE! | #VALUE!
467 |  | Lanie Patterson | Brent Brooks | 2020-05-14 | 2022-10-20 | L2_Bump | [29 empty] | 2 - WSST |  | 255D2 | 429 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Brent Buchberger | Summit Ridge Energy | West Gardiner PV LLC | 453 Lewiston Rd W Gardiner | 2000149310 | 30013891772 | Solar | [5 empty] | 44.2072 | -69.8444 | 453 Lewiston Rd |  |  | West Gardiner | 109 | WEST STREET | 255D2 | 255T1 |  | 9310-L0094-6300-0055-ED00025 | Non-FERC | WITHDRAWN | WITHDRAWN | 325000 | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2020-05-21 | 2020-05-21 | 2020-05-29 | 2020-05-21 | 2020-05-29 | 2020-10-13 |  | 2020-10-27 |  | 2020-10-13 | 2020-10-15 | 2020-10-29 |  |  | 2020-10-29 | 2021-08-16 |  | CS | 2020-11-20 | RS | 2021-08-16 |  |  |  |  | CS |  |  | 2020-11-20 | 2021-08-16 |  | 2022-10-24 | [11 empty] | 2022-10-15 | [14 empty] | 2020-12-14 | 2021-09-02 |  | 2022-11-17 | [8 empty] | 2020-12-16 | 2021-10-18 |  | 2021-05-18 | Addendum |  |  | 2021-02-22 | 2021-10-20 | [7 empty] | 2021-02-22 | 2021-10-20 | [16 empty] | 2021-03-01 | 2021-11-01 | [12 empty] | 2021-06-11 |  |  |  | 2022-01-18 | 2023-01-06 |  | 2023-01-09 | [5 empty] | 657016 |  | 420327 | 2023-01-04 | 2024-05-14 | 2020-11-14: 2022-01-18; 2020-11-14: 2022-01-19; 2021-07-28: 2023-01-10; 2021-07-28: 2023-01-10 | [15 empty] | Requested | [11 empty] | TRUE | TRUE | 467 | 2022-01-18 | 2022-01-18 | 2022 | 2022 | 2022 | 44358 |  |  | 2021-05-18 | Addendum
468 |  | Govinda Neupane |  | 2020-05-14 | [31 empty] | 2 - RILE |  | 449D2 | 218 |  | WITHDRAWN | WITHDRAWN |  | Zac Gordon | Energy Management, Inc. | JAY FIELDS SOLAR LLC | 239 Main St Jay | 2000162999 | 30012387830 | Solar | [7 empty] | 239 Main St |  |  | Jay |  | RILEY | 449D2 |  |  | 9310-L0191-2920-0085-ED00206 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2020-05-21 | 2020-05-29 |  |  |  |  | 1900-01-12 | [57 empty] | Pending | [69 empty] | 2021-05-03 | [25 empty] | STUDY | [11 empty] | TRUE | TRUE | 468 | 0 | 0 | 1900 | #VALUE! | #VALUE!
469 |  | Rigel Paradise | Rick Duperre | 2020-05-18 | [31 empty] | 1 - SASW |  | 657D4 |  |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN | 2022-06-27 | Mike Imoto | MEVS LLC AKA CENERGY | MSD Sanford LLC | Main St Sanford | 2000141274 | 30012624315 | Solar | [5 empty] | 43.4417 | -70.7702 | 5 Ledgewood Ave |  |  | Sanford |  | SANFORD SWITCH | 657D4 | 657T1 |  | 9310-L0321-5170-0220-ED00400 | Non-FERC | WITHDRAWN | WITHDRAWN | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2020-05-26 | 2020-05-26 | 2020-06-02 | 2020-05-26 | 2020-05-26 | 2020-06-16 |  | 2020-06-30 |  | 2020-06-16 | 2020-06-16 | 2020-06-30 |  |  | 2020-06-19 |  |  | CS | 2020-06-19 | [6 empty] | CS |  |  | 2020-06-19 | [11 empty] | 2020-06-22 | [17 empty] | 2020-06-24 | [6 empty] | Pending |  |  |  |  | 2020-08-27 |  |  | 2021-05-19 | Addendum |  |  | 2020-08-27 | [8 empty] | 2020-08-28 | [17 empty] | 2020-09-02 | [13 empty] | 2021-06-03 |  | 2021-06-03 |  | 2020-09-03 | [8 empty] | 139657 |  |  |  | 2023-03-28 | 2020-11-14: 2020-09-09; 2020-11-14: 2020-09-09; 2021-07-28: 2021-06-07; 2021-07-28: 2021-06-07 | [15 empty] | 10300710338 | [11 empty] | TRUE | TRUE | 469 | 2020-09-09 | 2020-09-09 | 2020 | 2020 | 2020 | 44350 |  |  | 2021-05-19 | Addendum
470 |  | Govinda Neupane |  | 2020-05-20 | [31 empty] | 13 - ATHN |  | 827D2 | 431 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Ben Ransom | Emeren | RENESOLA POWER HOLDINGS | Athens Rd Harmony | 2000149581 | 30012297997 | Solar | [5 empty] | 44.9636 | -69.5747 | Athens Rd |  |  | Harmony |  | ATHENS | 827D2 | 827T1 |  | FLOC-MISSING-01142021 | Non-FERC | WITHDRAWN | WITHDRAWN | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2020-05-28 | 2020-05-28 | 2020-06-04 | 2020-05-28 | 2020-06-04 | 2021-02-26 |  | 2021-03-12 |  | 2021-03-08 | 2021-03-31 | 2021-03-22 |  |  | 2021-03-29 | 2021-08-19 |  | CS | 2021-03-29 | RS | 2021-08-19 |  |  |  |  | CS |  |  | 2021-03-29 | 2021-08-19 | [28 empty] | 2021-03-29 | 2021-09-02 | [10 empty] | 2021-06-08 | 2021-10-18 |  | 2021-07-12 |  |  |  | 2021-07-12 | 2021-10-07 | [7 empty] | 2021-07-12 | 2021-10-07 | [16 empty] | 2021-07-13 | [7 empty] | 2021-07-13 | [13 empty] | 2023-05-15 |  |  |  |  | 265040 | 2021-09-30 | 914921 | 2023-02-16 | 2025-01-21 | 2020-11-14: 2021-10-26; 2020-11-14: 2021-11-05 | [15 empty] | Requested | [11 empty] | TRUE | TRUE | 470 | 2021-10-26 | 2021-10-26 | 2021 | 2021 | 2021 |  |  |  | 2021-07-12
471 |  |  | Anthony Boucher | 2020-05-22 | [31 empty] | 5 - THCR |  | 246D1 | 456 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Brent Buchberger | Summit Ridge Energy | South Thomaston PV, LLC | 662 St George Rd, S Thomaston | 2000149310 | 30013891756 | Solar | [5 empty] | 44.0434 | -69.1798 | 662 St George Rd |  |  | South Thomaston | 103.01 | THOMASTON CREEK | 246D1 | 34.5 kV Bus | 34.5 | 9310-L0081-5440-0048-ED00013 | Non-FERC | WITHDRAWN | WITHDRAWN | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2020-06-01 | 2020-06-01 | 2020-06-08 | 2020-06-01 | 2020-06-09 | 2020-12-08 |  | 2020-12-22 |  | 2020-12-08 | 2020-12-09 | 2020-12-23 |  |  | 2020-12-11 | 2021-08-16 |  | CS | 2020-12-11 | RS | 2021-08-16 |  |  |  |  | CS |  |  | 2020-12-11 | 2021-08-16 | [28 empty] | 2021-01-14 | 2021-09-02 | [10 empty] | 2021-03-22 | 2021-10-18 |  | 2021-06-17 | Report |  |  | 2021-06-17 | 2021-11-05 | [7 empty] | 2021-06-17 | 2021-11-05 | [17 empty] | 2021-11-17 | [14 empty] | 2021-11-04 |  | 2022-01-18 |  |  |  | 2024-08-23 | 2024-08-23 |  |  |  | 230442 | 2021-11-04 | 390942 | 2022-08-22 | 2024-10-09 | 2020-11-14: 2022-01-18; 2020-11-14: 2022-01-19 | [15 empty] | Requested | [11 empty] | TRUE | TRUE | 471 | 2022-01-18 | 2022-01-18 | 2022 | 2022 | 2022 |  |  |  | 2021-06-17 | Report
472 |  | Lanie Patterson | Brent Brooks | 2020-05-26 | 2022-09-08 | L2_Bump |  | 2024-06-14 | wthdw | [26 empty] | 5 - RRPS |  | 873D1 | 407 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Xander Neve | Syncarpha Solar LLC | OAKLAND SOLAR II | East Pond Rd Oakland | 2000157338 | 30012299803 | Solar | [5 empty] | 43.5919 | -69.7592 | East Pond Rd |  |  | Oakland | 21 | COUNTY RD (RICE RIPS) | 873D1 | 873T1 | 12.47 | FLOC-MISSING-01142021 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2020-06-02 | 2020-06-02 | 2020-06-09 | 2020-06-02 | 2020-06-09 | 2021-07-14 | 2021-07-15 | 2021-07-28 | 2021-07-21 | 2021-07-28 | 2021-07-28 | 2021-08-10 |  |  | 2021-08-11 |  |  | CS | 2021-08-11 | [6 empty] | CS |  |  | 2021-08-11 |  |  | 2023-01-16 | [8 empty] | 2021-08-23 |  |  | 2023-02-22 |  |  |  |  | 2021-08-25 | 2021-08-25 |  |  | 2023-02-01 | [5 empty] | 2021-09-01 |  |  | 2023-02-22 | [8 empty] | 2021-11-05 | [6 empty] | 2021-11-09 |  |  | 2023-04-05 | [5 empty] | 2021-11-08 |  |  | 2023-04-05 | [8 empty] | 2023-04-14 | [5 empty] | 2021-11-15 |  |  | 2023-05-03 |  |  |  |  | 2021-11-15 | [7 empty] | 2021-12-08 |  | 2021-12-08 | 2023-05-25 | 2021-12-23 | 2023-06-22 | [5 empty] | 271428 | 2021-10-25 | 968273 | 2023-04-05 | 2024-10-24 | 2020-11-14: 2022-01-11; 2020-11-14: 2022-01-12; 2021-07-28: 2023-06-22; 2021-07-28: 2023-06-26 | [15 empty] | Requested | [11 empty] | TRUE | TRUE | 472 | 2022-01-11 | 2022-01-11 | 2022 | 2022 | 2022
473 |  | Lanie Patterson | Brent Brooks | 2020-05-26 | [31 empty] | 2 - BURN |  | 807D1 | 120 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Bruce Metrick | Summit Ridge Energy | Snakeroot Solar LLC | 1345 Main Street Pittsfield | 2000182030 | 30012655913 | Solar | [5 empty] | 44.7218 | -69.4125 | 411 Webb Rd |  |  | Pittsfield | 3H | BURNHAM | 807D1 | 807T1 |  | FLOC-MISSING-01142021 | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2020-06-03 | 2020-06-02 | 2020-06-09 | 2020-06-03 | 2020-06-03 | 2020-06-22 |  | 2020-07-07 |  | 2020-06-22 | 2020-06-22 | 2020-07-07 |  |  | 2020-07-02 |  |  | CS | 2020-07-02 | [6 empty] | CS |  |  | 2020-07-02 | [29 empty] | 2020-07-09 | [6 empty] | Pending |  |  |  |  | 2020-09-11 |  |  | 2021-05-25 | Addendum |  |  | 2020-09-10 | [8 empty] | 2020-09-09 | [17 empty] | 2020-09-14 | [8 empty] | 2020-09-14 |  |  |  |  | 2021-06-03 |  | 2021-06-04 |  | 2020-09-15 | [8 empty] | 205100 | 2020-08-30 | 298743 | 2023-03-22 | 2025-10-08 | 2020-09-18 | 2020-09-18 | 2021-06-17 | 2021-06-17 | 2022-07-06 | 2022-07-06 | [15 empty] | Q4 2025 |  |  |  | 10300715714 | [11 empty] | TRUE | TRUE | 473 | 2020-09-18 | 2020-09-18 | 2020 | 2020 | 2020 | 44350 |  |  | 2021-05-25 | Addendum
474 |  | Govinda Neupane |  | 2020-05-26 | 2022-02-13 | [28 empty] | 1 - FAFA |  | 2 - FAFA |  | 818D1 | 251 | Yes | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2021-06-01 | Provas Mondal | Catalyze Holdings, LLC | ME SANDY RIVER LLC | West Glen Harris Rd, New Sharon Me | 2000273079 | 30013884413 | Solar | 3750 | 3.75 | 4821 |  |  | 44.6594 | -69.9913 | W Glenn Harris Rd |  |  | New Sharon |  | FARMINGTON FALLS | 818D1 | 818T1 |  | 9310-L0402-4075-0036-ED00094 | Non-FERC | NOT IMPACTED | NOT IMPACTED | 250000 | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2020-06-04 | 2020-06-02 | 2020-06-09 | 2020-06-04 | 2020-06-04 | 2020-06-24 | 2020-06-23 | 2020-07-09 | 2020-06-23 | 2020-06-24 | 2020-06-24 | 2020-07-09 |  |  | 2020-07-02 | 2022-02-13 |  | CS | 2020-07-02 | RS | 2022-02-13 |  |  |  |  | CS |  |  | 2020-07-02 | 2022-02-13 | [10 empty] | 2020-07-16 | Trigg | [6 empty] | 2020-07-16 | 2020-07-16 | 2022-03-18 | [7 empty] | 2020-07-24 | 2022-03-21 | [5 empty] | Pending |  |  |  |  | 2020-09-28 | 2022-05-03 |  | 2021-05-18 | Addendum |  |  | 2020-09-28 | 2022-04-29 | [7 empty] | 2020-09-25 | 2022-04-29 | [7 empty] | 2020-09-25 | 2022-05-16 | [7 empty] | 2020-09-29 | 2022-05-24 | [6 empty] | 2020-09-29 | 2022-05-24 |  |  |  |  | 2021-06-02 |  | 2020-10-15 |  | 2020-10-22 | 2022-06-15 | 2020-10-29 |  | 2022-02-07 | 2022-02-14 |  |  |  | 1657162 |  |  |  |  | 2020-11-14 | 2020-11-14 | 2021-06-11 | 2021-06-11 | 2022-06-20 | 2022-06-23 | [19 empty] | 10300733806 | [11 empty] | FALSE | TRUE | 474 | 2020-11-14 | 2020-11-14 | 2020 | 2020 | 2020 | 44349 |  |  |  | 2020-09-29
475 |  | Lanie Patterson | Brent Brooks | 2020-05-26 | [31 empty] | 3 - SHAW |  | 852D1 | 10 |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2021-12-17 | Jonovan (Jonny) Lizama | Luminace | MEVS Richards LLC | 419 Skowhegan Rd (Fairfield) | 2000182829 | 30012667272 | Solar | 1000 | 1 | 1993 |  |  | 44.6422 | -69.6051 | 419 Skowhegan Rd. |  |  | Fairfield | 58 | SHAWMUT | 852D1 | 852T3 |  | FLOC-MISSING-01142021 | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2020-06-04 | 2020-06-02 | 2020-06-09 | 2020-06-04 | 2020-06-04 | 2020-06-25 |  | 2020-07-10 |  | 2020-06-25 | 2020-06-25 | 2020-07-10 |  |  | 2020-07-10 | 2021-08-19 |  | CS | 2020-07-10 | RS | 2021-08-19 |  |  |  |  | CS |  |  | 2020-07-10 | 2021-08-19 | [10 empty] | 2020-07-10 | [17 empty] | 2020-07-17 | 2021-09-16 | [5 empty] | Pending |  |  |  |  | 2020-09-21 | 2021-09-29 | [5 empty] | 2020-09-15 | 2021-10-14 | [7 empty] | 2020-09-15 | 2021-10-14 | [16 empty] | 2020-09-21 | 2021-10-21 | [14 empty] | 2020-09-21 | 2022-05-31 | 2020-09-21 | 2022-05-31 | 2022-06-27 | 2022-06-28 | [5 empty] | 157938 | 2020-09-15 | 150210 | 2022-04-18 |  | 2020-11-14: 2020-09-23; 2020-11-14: 2020-09-23; 2021-07-28: 2021-10-22; 2021-07-28: 2021-11-05; 2023-10-27: 2022-07-18 | [15 empty] | 10300716706 | [11 empty] | TRUE | TRUE | 475 | 2020-09-23 | 2020-09-23 | 2020 | 2020 | 2020
476 |  | Lanie Patterson | Brent Brooks | 2020-05-26 | [31 empty] | 2 - WEWA |  | 865D5 | 435 |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2021-12-17 | Jonovan (Jonny) Lizama | Luminace | MEVS Waterville LLC | 2 Lefleur Rd Waterville | 2000192408 | 30012794647 | Solar | 4950 | 4.95 | 6790 |  |  | 44.5373 | -69.6759 | 2 Lefleur Rd |  |  | Waterville |  | WEST WATERVILLE | 865D5 | 865T2 |  | FLOC-MISSING-01142021 | Non-FERC | TRIGGERING | TRIGGERING | 325000 | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2020-06-04 | 2020-06-02 | 2020-06-09 | 2020-06-04 | 2020-06-09 | 2020-07-14 |  | 2020-07-28 |  | 2020-07-14 | 2020-07-14 | 2020-07-28 |  |  | 2020-07-27 |  |  | CS | 2020-07-27 | [6 empty] | CS |  |  | 2020-07-27 | [11 empty] | 2020-07-29 | [17 empty] | 2020-08-03 | [6 empty] | Pending |  |  |  |  | 2020-10-06 |  |  | 2021-06-11 | Addendum |  |  | 2020-10-06 | [8 empty] | 2020-10-07 | [17 empty] | 2020-10-14 | [15 empty] | 2020-10-14 |  | 2020-10-16 | [8 empty] | 495853 |  |  |  |  | 2020-11-14: 2020-10-19; 2020-11-14: 2020-10-19; 2021-07-28: 2021-07-06; 2021-07-28: 2021-07-06 | [15 empty] | 10300725150 | [11 empty] | TRUE | TRUE | 476 | 2020-10-19 | 2020-10-19 | 2020 | 2020 | 2020 |  |  |  | 2021-06-11 | Addendum
477 |  | Govinda Neupane |  | 2020-05-27 | 2023-06-27 | L2_Bump | [29 empty] | 1 - ANDO |  | 400D1 |  | Yes | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED |  | Nate Niles | REVISION ENERGY INC | RE Andover Solar LLC | 61 Roxbury Pond Rd Andover | 2000457362 | 30016426451 | Solar | 999 | 0.999 | 1338.48 |  |  | 44.6359 | -70.7342 | 170 Route 120 |  |  | Andover |  | ANDOVER | 400D1 | 400T1 |  | FLOC-MISSING-01142021 | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2020-06-04 | 2020-06-03 | 2020-06-10 | 2020-06-04 | 2020-06-04 | 2020-06-26 |  | 2020-07-13 |  | 2020-06-26 | 2020-06-26 | 2020-07-13 |  |  | 2020-07-10 |  |  | CS | 2020-07-10 | [6 empty] | CS |  |  | 2020-07-10 |  |  | 2023-06-30 | [8 empty] | 2020-07-23 |  |  | 2023-08-11 | [8 empty] | 2023-08-21 | [5 empty] | 2020-07-24 |  |  | 2023-08-25 |  |  |  | Pending |  |  |  |  | 2020-09-28 |  |  | 2021-05-24 | Addendum |  |  | 2020-09-28 |  |  | 2023-10-09 | [5 empty] | 2020-09-28 |  |  | 2023-10-09 | [14 empty] | 2020-09-29 |  |  | 2023-10-26 | [10 empty] | 2021-06-16 |  | 2020-10-14 |  | 2020-10-15 | 2023-10-30 |  | 2023-11-01 | [5 empty] | 260360 |  | 116181 | 2023-10-22 |  | 2020-11-14: 2020-11-10; 2020-11-14: 2020-11-10; 2021-07-28: 2023-11-03; 2021-07-28: 2023-11-03 | [11 empty] | Q4 2025 |  |  |  | 10300732906 | [11 empty] | TRUE | TRUE | 477 | 2020-11-10 | 2020-11-10 | 2020 | 2020 | 2020 | 44363 |  |  | 2021-05-24 | Addendum
478 |  | Lanie Patterson | Brent Brooks | 2020-05-28 | [31 empty] | 2 - AGK5 |  | 200D3 | 94 |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2021-01-04 | Nate Niles | REVISION ENERGY INC | Community Solar New England, LLC | 2495 N Belfast Ave / Augusta | 2000202157 | 30015018853 | Solar | 2000 | 2 | 2750 |  |  | 44.3319 | -69.7178 | 495 N BELFAST AVE |  |  | Augusta |  | AUGUSTA K5 | 200D3 |  |  | 9310-L0020-0240-0252-ED00567 | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2020-06-04 | 2020-06-04 | 2020-06-11 | 2020-06-04 | 2020-06-11 | 2020-07-16 |  | 2020-07-30 |  | 2020-07-16 | 2020-07-16 | 2020-07-30 |  |  | 2020-07-27 |  |  | CS | 2020-07-27 | [6 empty] | CS |  |  | 2020-07-27 | [11 empty] | 2020-07-24 | [17 empty] | 2020-07-27 | [6 empty] | Pending |  |  |  |  | 2020-09-29 |  |  | 2021-06-21 | Addendum |  |  | 2020-09-29 | [8 empty] | 2020-09-29 | [17 empty] | 2020-10-08 | [15 empty] | 2020-10-23 |  | 2020-10-23 | [9 empty] | 2021-06-06 | 85262 | 2022-09-20 |  | 2020-11-14: 2020-10-26; 2020-11-14: 2020-10-26 | [15 empty] | 10300727686 | [11 empty] | TRUE | TRUE | 478 | 2020-10-26 | 2020-10-26 | 2020 | 2020 | 2020 |  |  |  | 2021-06-21 14:44 | Addendum
479 |  | Lanie Patterson | Brent Brooks | 2020-05-28 | [31 empty] | 3 - CONY |  | 216D1 | 301 |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2021-01-04 | David Watts | Novel ME SPV 2 LLC | USS TOGUS SOLAR LLC | Smith Rd, Chelsea | 2000160742 | 30012353808 | Solar | 4999 | 4.999 | 6897 |  |  | 44.2814 | -69.7344 | Smith Rd |  |  | Chelsea | 3 | CONY ROAD | 216D1 | 216T1 |  | 9310-L0043-1110-0004-ED00003 | Non-FERC | TRIGGERING | TRIGGERING | 325000 | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2020-06-09 | 2020-06-04 | 2020-06-11 | 2020-06-09 | 2020-06-09 | 2020-06-29 |  | 2020-07-14 |  | 2020-06-29 | 2020-06-29 | 2020-07-14 | [5 empty] | FS | 2020-07-23 | IS | 2020-09-17 |  |  |  |  | Split | 2020-07-23 | 2020-09-17 | [11 empty] | 2020-07-27 | [16 empty] | 2020-08-03 | 2020-09-29 | [10 empty] | 2020-09-08 | 2020-11-11 |  |  |  | 2021-06-10 | Addendum | 2020-09-08 | 2020-11-12 | [7 empty] | 2020-09-08 | 2020-11-12 | [16 empty] | 2020-09-09 | 2020-11-16 | [6 empty] | 2020-09-09 | 2020-11-16 | [8 empty] | 2020-11-16 |  | 2020-11-17 | [8 empty] | 369154 | 2020-11-11 | 703726 | 2025-08-19 |  | 2020-11-14: 2020-11-24; 2020-11-14: 2020-11-24 | [15 empty] | 10300735927 | [11 empty] | TRUE | TRUE | 479 | 2020-11-24 | 2020-11-24 | 2020 | 2020 | 2020 |  |  |  | 2021-06-10 | Addendum
480 |  |  | KRISTOFER COLEMAN | 2020-06-04 | [31 empty] | 2 - EDGE |  | 223D1 | 366 |  | WITHDRAWN | WITHDRAWN |  | Peter Bay | EDF Renewables | EDF RENEWABLES | 49 Dodge Rd | 2000134214 | 30012326515 | Solar | [7 empty] | 49 DODGE RD |  |  | Edgecomb | 45 | EDGECOMB | 223D1 | 223T1 |  | 9310-L0052-1810-0041-ED00018 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2020-06-11 | 2020-06-18 |  |  |  |  | 1900-01-12 | [57 empty] | Pending | [65 empty] | 435872 | 2020-11-09 | n/a | n/a | 2021-01-12 | [37 empty] | TRUE | TRUE | 480 | 0 | 0 | 1900 | 1900 | 1900
481 |  | Lanie Patterson | Brent Brooks | 2020-06-04 | 2022-09-08 | L2_Bump |  | 2024-06-14 | wthdw |  | 2024-10-24 | wthdw | [22 empty] | 472 | 6 - RRPS |  | 873D1 | 472 | Yes | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Xander Neve | Syncarpha Solar LLC | OAKLAND SOLAR I LLC | Thomasville Rd Oakland | 2000157336 | 30012299688 | Solar | [5 empty] | 45.501 | -69.2605 | Thomasville Rd |  |  | Oakland | 4 | COUNTY RD (RICE RIPS) | 873D1 | 873T1 | 12.47 | FLOC-MISSING-01142021 | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2020-06-11 | 2020-06-11 | 2020-06-18 | 2020-06-11 | 2020-06-23 |  | 2022-01-20 | 1900-01-12 | 2022-01-26 | 2022-01-28 | 2022-01-28 | 2022-02-11 |  |  | 2022-01-31 | 2024-03-05 |  | CS | 2022-02-11 | RS | 2024-03-05 |  |  |  |  | CS |  |  | 2022-02-11 | 2024-03-05 |  | 2023-06-29 | 2025-01-20 |  |  |  |  | 2024-03-05 |  |  |  | 2024-03-13 |  | 2023-08-03 | 2025-02-05 |  |  |  |  | 2022-02-28 | 2024-03-14 |  | 2023-08-08 | 2025-02-05 |  |  |  |  | 2022-03-07 | 2024-03-18 |  | 2023-08-22 | 2025-02-05 | [7 empty] | 2022-05-10 | 2024-04-26 | [5 empty] | 2022-05-10 | 2024-04-26 |  | 2023-10-04 | 2025-04-04 |  |  |  |  | 2022-05-11 | 2024-04-29 |  | 2023-10-05 | 2025-04-04 |  |  |  |  | 2022-05-11 |  |  | 2023-10-23 | 2025-04-16 |  |  |  |  | 2022-05-17 | 2024-05-09 |  | 2023-10-25 | 2025-04-22 |  |  |  | 2022-05-17 | 2024-05-09 |  | 2023-10-25 | 2025-04-22 |  |  |  | 2022-06-06 |  | 2022-06-09 | 2024-06-03 | 2022-06-20 |  | 2022-02-07 | 2022-02-14 |  |  |  | 226084 | 2023-10-04 | 427817 | 2025-04-03 | 2025-10-28 | 2020-11-14: 2022-06-21; 2020-11-14: 2022-06-22; 2021-07-28: 2025-06-12; 2021-07-28: 2025-06-13 | [15 empty] | Requested | [11 empty] | TRUE | TRUE | 481 | 2022-06-21 | 2022-06-21 | 2022 | 2022 | 2022 |  |  |  |  | 2022-05-17
482 |  | Govinda Neupane |  | 2020-06-05 | 2023-07-20 | L2_Bump | [29 empty] | 3 - WILT |  | 885D1 | 461 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Allen Tate | US Solar Development, LLC | USS WELD SOLAR LLC | Tobin Flat Rd Wilton, Me | 2000159929 | 30012341118 | Solar | [5 empty] | 44.6332 | -70.3055 | Tobin Flats Rd |  |  | Wilton |  | WILTON | 885D1 | 885T1 |  | 9310-L0467-6380-0118-ED00052 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2020-06-11 | 2020-06-12 | 2020-06-19 | 2020-06-11 | 2020-06-23 | 2021-08-31 |  | 2021-09-15 |  | 2021-09-13 | 2021-09-13 | 2021-09-28 |  |  | 2021-09-27 |  |  | CS | 2021-09-28 | [6 empty] | CS |  |  | 2021-09-28 | [29 empty] | 2021-10-08 | [11 empty] | 2021-12-15 | [6 empty] | 2021-12-03 | [8 empty] | 2021-12-03 | [8 empty] | 2021-12-03 | [8 empty] | 2021-12-07 | [17 empty] | 2021-12-09 | [12 empty] | 2023-09-06 | 2020-11-14: 2021-12-10; 2020-11-14: 2021-12-13 | [15 empty] | Requested | [11 empty] | TRUE | TRUE | 482 | 2021-12-10 | 2021-12-10 | 2021 | 2021 | 2021
483 |  | Rigel Paradise | Rick Duperre | 2020-06-08 | [31 empty] | 2 - SASW |  | 657D3 | 469 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN | 2022-06-27 | Mike Imoto | MEVS LLC AKA CENERGY | MEVS BROWN LLC | 987 Back Rd Shapleigh | 2000163045 | 30012388655 | Solar | [5 empty] | 43.4958 | -70.8114 | 987 Back Rd |  |  | Shapleigh |  | SANFORD SWITCH | 657D3 | 657T1 |  | 9310-L0226-5300-0047-ED00106 | Non-FERC | WITHDRAWN | WITHDRAWN | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2020-06-10 | 2020-06-15 | 2020-06-22 | 2020-06-10 | 2020-06-23 | 2020-09-15 |  | 2020-09-29 |  | 2020-09-15 | 2020-09-15 | 2020-09-29 |  |  | 2020-09-25 |  |  | CS | 2020-09-25 | [6 empty] | CS |  |  | 2020-09-25 | [29 empty] | 2020-10-05 | [6 empty] | Pending |  |  |  |  | 2020-12-10 |  |  | 2021-05-05 | Addendum |  |  | 2021-01-07 | [8 empty] | 2021-01-07 | [17 empty] | 2021-01-13 | [7 empty] | 2021-01-13 | [5 empty] | 2021-05-11 |  | 2021-05-11 | 2021-05-11 | [9 empty] | 1434786 |  |  |  | 2022-10-07 | 2020-11-14: 2021-01-26; 2020-11-14: 2021-01-26; 2021-07-28: 2021-05-13; 2021-07-28: 2021-05-13 | [15 empty] | 10300751600 | [11 empty] | TRUE | TRUE | 483 | 2021-01-26 | 2021-01-26 | 2021 | 2021 | 2021 | 44327 |  | 44327 | 2021-05-05 | Addendum
484 |  | Govinda Neupane |  | 2020-06-16 | 2022-07-19 | L2_Bump | [29 empty] | 7 - WSTN |  | 866D2 | 331 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Meron Demissie | Sunrise Energy Ventures, LLC | ME PROJECT CO 1 LLC | Stevens Rd, Skowhegan | 2000162664 | 30012382872 | Solar | [5 empty] | 44.7453 | -69.7106 | Stevens Rd. |  |  | Skowhegan | 10 | WESTON HYDRO | 866D2 | 866T2 |  | FLOC-MISSING-01142021 | Non-FERC | WITHDRAWN | WITHDRAWN | NONE | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2020-06-23 | 2020-06-23 | 2020-06-30 | 2020-06-23 | 2020-06-30 | 2020-10-06 |  | 2020-10-21 |  | 2020-10-06 | 2020-10-07 | 2020-10-22 |  |  | 2020-10-20 |  |  | CS | 2020-10-20 | [6 empty] | CS |  |  | 2020-10-20 |  |  | 2022-07-22 | [11 empty] | 2022-08-16 | [14 empty] | 2020-11-02 |  |  | 2022-08-29 |  |  |  | Pending |  |  |  |  | 2021-01-08 | [6 empty] | 2021-01-11 | [8 empty] | 2021-01-18 | [17 empty] | 2021-01-20 | [7 empty] | 2021-01-20 | [7 empty] | 2021-02-08 |  | 2021-02-09 |  | 2021-02-26 | [6 empty] | 456974 |  |  |  | 2023-12-15 | 2020-11-14: 2021-03-01; 2020-11-14: 2021-03-01; 2021-07-28: 2021-07-15; 2021-07-28: 2021-09-15 | [15 empty] | Requested | [11 empty] | TRUE | TRUE | 484 | 2021-03-01 | 2021-03-01 | 2021 | 2021 | 2021
485 |  | Marshall Ripley | Rick Duperre | 2020-06-15 | [31 empty] | 2 - BRML |  | 678D1 | 180 |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2021-09-03 | Tyler William Perkins | Nexamp, Inc | MEVS HANSON LLC | Salmon Falls Rd Hollis | 2000182840 | 30012667298 | Solar | 4950 | 4.95 | 7238 |  |  | 43.607 | -70.5648 | Salmon Falls Rd |  |  | Hollis |  | BAR MILLS | 678D1 | 678T4 |  | 9310-L0355-2647-0086-ED00002 | Non-FERC | COST SHARE | COST SHARE ( $375,000 ) | 252551 | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2020-06-23 | 2020-06-22 | 2020-06-29 | 2020-06-23 | 2020-06-23 | 2020-07-10 |  | 2020-07-24 |  | 2020-07-10 | 2020-07-10 | 2020-07-24 |  |  | 2020-07-24 |  |  | CS | 2020-07-24 | [6 empty] | CS |  |  | 2020-07-24 | [11 empty] | 2020-07-28 | [17 empty] | 2020-08-03 | [6 empty] | Pending |  |  |  |  | 2020-10-06 |  |  | 2021-06-11 | Addendum |  |  | 2020-10-06 | [8 empty] | 2020-10-06 | [17 empty] | 2020-10-13 | [13 empty] | 2021-06-21 |  | 2020-10-14 |  | 2020-10-15 | [8 empty] | 534145 |  |  |  |  | 2020-11-14: 2020-10-19; 2020-11-14: 2020-10-19; 2021-07-28: 2021-07-20; 2021-07-28: 2021-07-20 | [15 empty] | 10300724999 | [11 empty] | TRUE | TRUE | 485 | 2020-10-19 | 2020-10-19 | 2020 | 2020 | 2020 | 44368 |  |  | 2021-06-11 | Addendum
486 |  | Govinda Neupane |  | 2020-06-15 | [31 empty] | 3 - NOAN |  | 838D2 | 332 |  | WITHDRAWN | WITHDRAWN |  | Nick Mazuroski | Dirigo/BNRG | BD SOLAR NORTH ANSON 2 LLC | Union St N Anson | 2000161812 | 30012370364 | Solar | [7 empty] | Union St |  |  | North Anson |  | NORTH ANSON | 838D2 |  |  | 9310-L0421-0150-0001-ED00070 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2020-06-22 | 2020-06-29 |  |  |  |  | 1900-01-12 | [50 empty] | 2020-11-12 | [6 empty] | No Study | [69 empty] | 2020-10-19 | [37 empty] | TRUE | TRUE | 486 | 0 | 0 | 1900 | #VALUE! | #VALUE!
487 |  | Govinda Neupane |  | 2020-06-15 | [31 empty] | 5 - SKSS |  | 854D1 | 458 |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2021-12-17 | Abby Broedlin | Nautilus US Power Holdco, LLC | BD SOLAR NORRIDGEWOCK LLC | Winding Hill Rd Norridgewock | 2000161371 | 30012363385 | Solar | 2318 | 2.318 | 3633 |  |  | 44.7175 | -69.8088 | Winding Hill Rd |  |  | Norridgewock | 48 | SKOWHEGAN SOUTH SIDE | 854D1 | 854T1 |  | FLOC-MISSING-01142021 | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2020-06-23 | 2020-06-22 | 2020-06-29 | 2020-06-23 | 2020-06-29 | 2020-07-14 |  | 2020-07-28 |  | 2020-07-14 | 2020-07-14 | 2020-07-28 |  |  | 2020-07-16 | 2020-11-02 |  | CS | 2020-07-16 | RS | 2020-11-02 |  |  |  |  | CS |  |  | 2020-07-16 | 2020-11-02 | [10 empty] | 2020-08-14 | [17 empty] | 2020-07-24 | 2020-11-10 | [5 empty] | Pending |  |  |  |  | 2020-09-28 | 2020-12-24 |  | 2021-05-05 | Addendum |  |  | 2020-09-28 | 2020-12-28 | [7 empty] | 2020-09-30 | 2021-01-18 | [16 empty] | 2020-10-01 | [5 empty] | 2020-10-01 | 2021-01-27 | 2020-10-01 | 2021-01-27 |  |  |  |  | 2021-05-11 |  | 2021-05-11 | 2021-05-11 |  | 2022-11-03 |  |  | 2023-04-11 | 2023-04-11 |  |  |  | 281814 |  | 454241 | 2022-09-19 |  | 2020-11-14: 2021-05-13; 2020-11-14: 2021-05-13; 2021-07-28: 2021-05-13; 2021-07-28: 2021-05-13; 2023-10-27: 2022-08-04 | 2023-04-18 | 2023-04-18 | [13 empty] | Requested | [11 empty] | TRUE | TRUE | 487 | 2021-05-13 | 2021-05-13 | 2021 | 2021 | 2021 | 44327 |  | 44327 | 2021-05-05 | Addendum
488 |  |  | Anthony Boucher | 2020-06-15 | [31 empty] | 2 - PAST |  | 239D5 | 438 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Nate Niles | REVISION ENERGY INC | KNOX COUNTY REGIONAL AIRPORT | 5 Airport Rd Owls Head Me | 2800608221 | 30012387764 | Solar | [5 empty] | 44.7248 | -69.1067 | 5 Airport Rd |  |  | Owls Head |  | PARK STREET | 239D5 |  |  | 9310-L0069-4400-0061-ED00036 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2020-06-22 | 2020-06-29 |  |  |  |  | 1900-01-12 | [50 empty] | 2020-09-08 | [76 empty] | 2021-11-01 | 2020-11-14: 2021-06-11; 2020-11-14: 2021-06-11; 2021-07-28: 2021-06-11; 2021-07-28: 2021-06-11 | [27 empty] | TRUE | TRUE | 488 | 2021-06-11 | 2021-06-11 | 2021 | 2021 | 2021
489 |  | Lanie Patterson | Brent Brooks | 2020-06-15 | [31 empty] | 4 - SHAW |  | 852D1 | 475 |  | WITHDRAWN | WITHDRAWN |  | Sachin Patel | LastMile Energy | CLINTON LUMBERT | Lot 36b Route 201, Fairfield | 2800607651 | 30012379167 | Solar | [5 empty] | 44.6181 | -60.5947 | Lot 36B - Route 201 |  |  | Fairfield | 34 | SHAWMUT | 852D1 |  |  | FLOC-MISSING-01142021 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2020-06-22 | 2020-06-29 |  |  |  |  | 1900-01-12 | [123 empty] | 8038353 | 2021-06-18 | n/a | n/a | 2021-09-21 | [37 empty] | TRUE | TRUE | 489 | 0 | 0 | 1900 | 1900 | 1900
490 |  | Lanie Patterson | Brent Brooks | 2020-06-16 | [31 empty] | 5 - DETR |  | 812D1 | 300 |  | WITHDRAWN | WITHDRAWN |  | Jay Smith | Standard Solar | NORTHERN LIGHTS SOLAR LLC | 323 Ill Hill Rd Palmyra | 2000139226 |  | Solar | [7 empty] | 323 Ell Hill Rd |  |  | Palmyra |  | DETROIT | 812D1 |  |  | 86-Withdrawn-86d | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2020-06-23 | 2020-06-30 |  |  |  |  | 1900-01-12 | [57 empty] | Yes | [69 empty] | 2020-07-08 | [37 empty] | TRUE | TRUE | 490 | 0 | 0 | 1900 | #VALUE! | #VALUE!
491 |  |  | KRISTOFER COLEMAN | 2020-06-16 | [31 empty] | 2 - BRIS |  | 210D2 | 343 |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED |  | Travis Scott | EDPR | C2 BRISTOL I LLC | 1442 Bristol rd BRISTOL | 2000302312 | 30014283458 | Solar | 3500 | 3.5 | 4484 |  |  | 43.9459 | -69.5183 | 1442 Bristol Rd |  |  | Bristol |  | BRISTOL | 210D2 | 210T1 |  | 9310-L0478-0710-0020-ED00100 | Non-FERC | TRIGGERING | TRIGGERING (250,000) | 159120 | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2020-06-23 | 2020-06-23 | 2020-06-30 | 2020-06-23 | 2020-06-23 | 2020-07-13 |  | 2020-07-27 |  | 2020-07-13 | 2020-07-13 | 2020-07-27 |  |  | 2020-07-27 |  |  | CS | 2020-07-27 | [6 empty] | CS |  |  | 2020-07-27 | [11 empty] | 2020-07-27 | [17 empty] | 2020-08-05 | [6 empty] | Pending |  |  |  |  | 2020-10-08 |  |  | 2021-07-13 | Addendum |  |  | 2020-10-06 | [8 empty] | 2020-10-07 | [17 empty] | 2020-10-19 | [7 empty] | 2021-07-13 | [5 empty] | 2021-07-13 |  | 2020-10-20 |  | 2020-10-21 |  |  |  | 2024-08-23 | 2024-08-23 |  |  |  | 231610 |  |  |  |  | 2020-11-14: 2020-11-04; 2020-11-14: 2020-11-04; 2021-07-28: 2021-07-13; 2021-07-28: 2021-07-13 | [15 empty] | 10300731430 | [11 empty] | TRUE | TRUE | 491 | 2020-11-04 | 2020-11-04 | 2020 | 2020 | 2020 | 44390 |  |  | 2021-07-13 | Addendum
492 |  | Rigel Paradise | Rick Duperre | 2020-06-22 | [31 empty] | 5 - LIME |  | 632D2 | 349 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Brett Pingree | Soltage LLC | LIMERICK EAST RANGE SOLAR 1 LLC | East Range Limerick | 2000176860 | 30012586415 | Solar | [5 empty] | 43.6724 | -70.8009 | 122 Range Rd |  |  | Limerick | 29 | LIMERICK | 632D2 | 632T1 | 12.47 | 9310-L0264-3260-0155-ED00030 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2020-07-08 | 2020-06-29 | 2020-07-07 | 2020-07-08 | 2020-07-08 | 2020-09-17 |  | 2020-10-01 |  | 2020-09-17 | 2020-09-17 | 2020-10-01 |  |  | 2020-09-18 |  |  | CS | 2020-09-18 | RS | [5 empty] | CS |  |  | 2020-09-18 | [11 empty] | 2020-09-18 | [17 empty] | 2020-10-05 | 2021-01-15 | [5 empty] | Pending |  |  |  |  | 2020-12-10 | 2021-03-02 |  | 2021-06-11 | Report |  |  | 2020-12-15 | 2021-06-11 | [7 empty] | 2020-12-15 | 2021-06-11 | [16 empty] | 2020-12-21 | [7 empty] | 2020-12-21 | [13 empty] | 2023-07-03 | 2023-07-11 |  |  |  | 110326 | 2021-05-23 | 166300 | 2023-03-22 | 2024-10-09 | 2020-11-14: 2021-06-21; 2020-11-14: 2021-06-21; 2021-07-28: 2021-06-21; 2021-07-28: 2021-06-21 | 2023-10-10 | 2023-10-11 | [13 empty] | Requested | [11 empty] | TRUE | TRUE | 492 | 2021-06-21 | 2021-06-21 | 2021 | 2021 | 2021 |  |  |  | 2021-06-11 | Report
493 |  | Lanie Patterson | Brent Brooks | 2020-06-23 | [31 empty] | 2 - BRCR |  | 211D2 | 209 |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2021-02-25 | Liam McCormack | Summit Ridge Energy | RE Gardiner Solar LLC | 329 River Rd Gardiner | 2000261774 | 30013726416 | Solar | 3875 | 3.875 | 4636 |  |  | 44.2039 | -69.7648 | 329 River Rd |  |  | Gardiner | 49 | BROWNS CROSSING | 211D2 | 211T1 |  | 9310-L0029-2190-0106-ED00146 | Non-FERC | COST SHARE | COST SHARE (395,000) | 175429.82 | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2020-07-08 | 2020-06-30 | 2020-07-08 | 2020-07-08 | 2020-07-08 | 2020-07-21 |  | 2020-08-04 |  | 2020-07-21 | 2020-07-21 | 2020-08-04 |  |  | 2020-07-27 |  |  | CS | 2020-07-27 | RS | [5 empty] | CS |  |  | 2020-07-27 | [11 empty] | 2020-08-17 | [17 empty] | 2020-08-13 | 2020-12-07 | [5 empty] | Pending |  |  |  |  | 2020-10-19 | 2021-01-19 |  | 2021-05-04 | Addendum |  |  | 2020-10-19 | 2021-01-19 | [7 empty] | 2020-10-19 | 2020-12-02 | [16 empty] | 2020-10-22 | 2020-12-02 |  |  |  |  | 2020-10-22 |  | 2020-10-22 | [5 empty] | 2021-05-10 |  | 2020-12-09 |  | 2020-12-09 | [8 empty] | 914701 |  |  |  |  | 2020-12-09 | 2020-12-09 | 2021-06-08 | 2021-06-08 | 2022-01-17 | 2022-01-17 | [19 empty] | 10300741664 | [11 empty] | TRUE | TRUE | 493 | 2020-12-09 | 2020-12-09 | 2020 | 2020 | 2020 | 44326 |  |  | 2021-05-04 | Addendum
494 |  | Lanie Patterson | Brent Brooks | 2020-06-23 | [31 empty] | 4 - GARD |  | 226D2 | 428 |  | WITHDRAWN | WITHDRAWN |  | Nate Niles | REVISION ENERGY INC | REVISION ENERGY INC | 246 Marston Rd Gardiner | 2800693910 | 30012408701 | Solar | [7 empty] | 246 Marston Rd |  |  | Gardiner |  | GARDINER | 226D2 |  |  | 9310-L0057-2190-0072-ED00072 | FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2020-06-30 | 2020-07-08 |  |  |  |  | 1900-01-12 | [57 empty] | Pending | [69 empty] | 2020-04-27 | [37 empty] | TRUE | TRUE | 494 | 0 | 0 | 1900 | #VALUE! | #VALUE!
495 |  |  | Anthony Boucher | 2020-06-24 | 2021-06-29 |  |  | 2022-12-01 | L2_Bump | [26 empty] | 5 - PROS |  | 846D1 | 427 | Yes | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Melissa Reed | FFP ORIGINATION LLC | FFP ORIGINATION LLC | 872 Bangor Rd Prospect Me | 2000165043 | 30012417553 | Solar | [5 empty] | 44.546 | -68.866 | 872 Bangor Road |  |  | Prospect | 13 | PROSPECT | 846D1 | 846T1 | 12.47 | 9310-L0426-4770-0001-ED00006 | Non-FERC | WITHDRAWN | WITHDRAWN | NONE | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2020-07-08 | 2020-07-01 | 2020-07-09 | 2020-07-08 | 2020-07-09 | 2021-01-20 | 2021-02-03 | 2021-02-03 | 2021-02-08 | 2021-02-09 | 2021-02-10 | 2021-02-25 |  |  | 2021-02-25 | 2021-09-29 |  | CS | 2021-03-01 | RS | 2021-09-29 |  |  |  |  | CS |  |  | 2021-03-01 | 2022-05-20 |  | 2022-12-02 | [11 empty] | 2023-01-01 |  |  |  |  | 2021-03-10 | 2021-03-10 | 2021-11-04 |  | 2023-01-13 | [5 empty] | 2021-03-10 | 2021-11-04 |  | 2023-01-17 | [8 empty] | 2021-05-13 | 2021-12-20 |  | 2021-07-08 | Report |  |  | 2021-07-08 | 2021-12-20 |  | 2023-02-21 | [5 empty] | 2021-07-08 | 2021-12-21 |  | 2023-02-21 | [5 empty] | 2022-01-14 | 2022-01-14 | [7 empty] | 2021-07-19 | 2021-12-20 | [6 empty] | 2021-07-19 | 2021-12-20 | [6 empty] | 2022-08-03 |  | 2022-08-23 | 2023-03-20 | 2022-09-15 | 2023-03-20 | [7 empty] | 446200 | 2023-03-20 | 2025-04-04 | 2020-11-14: 2022-09-15; 2020-11-14: 2022-09-15; 2021-07-28: 2023-03-20; 2021-07-28: 2023-03-21 | [15 empty] | Requested | [11 empty] | TRUE | TRUE | 495 | 2022-09-15 | 2022-09-15 | 2022 | 2022 | 2022 |  |  |  |  | 2021-07-19
496 |  |  | Anthony Boucher | 2020-06-24 | [29 empty] | 1 - BROO |  | 4 - BROO |  | 805D1 | 433 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Melissa Reed | FFP ORIGINATION LLC | FFP ORIGINATION LLC | 47 Brown Rd Monroe Me | 2000165043 | 30012417561 | Solar | [5 empty] | 44.5694 | -69.0986 | 47 Brown Road |  |  | Monroe | 46 | BROOKS | 805D1 | 805T1 |  | 9310-L0384-0730-0007-ED00060 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2020-07-08 | 2020-07-01 | 2020-07-09 | 2020-07-08 | 2020-07-09 | 2022-01-26 | 2022-01-24 | 2022-02-09 | 2022-01-24 | 2022-01-26 | 2022-01-26 | 2022-02-09 | 2022-02-09 |  |  |  |  | FS | 2022-02-10 | IS | 2022-07-14 |  |  |  |  | FS | 2022-02-10 | 2022-08-25 | [7 empty] | 2022-03-15 |  |  |  | 2022-03-30 | 2022-09-02 | [7 empty] | 2022-03-30 | 2022-03-30 | [6 empty] | 2022-03-30 | 2022-09-08 | [10 empty] | 2022-05-05 | 2022-10-20 | [5 empty] | 2022-05-05 | 2022-10-19 | [7 empty] | 2022-05-05 | 2022-10-19 | [7 empty] | 2022-05-16 | 2022-10-24 | [7 empty] | 2022-05-16 | 2022-10-24 | [6 empty] | 2022-05-16 | 2022-10-24 | [8 empty] | 2022-11-18 |  | 2022-12-13 | 2023-01-18 | 2023-01-17 | 2023-01-18 | 2022-02-07 | 2022-02-14 |  |  |  | 506754 | 2022-10-18 |  |  | 2025-04-04 | 2020-11-14: 2023-01-23; 2020-11-14: 2023-01-24 | [15 empty] | Requested | [11 empty] | FALSE | TRUE | 496 | 2023-01-23 | 2023-01-23 | 2023 | 2023 | 2023
497 |  | Eben Snow | Brent Brooks | 2020-06-24 | [31 empty] | 4 - R115 |  | 445D2 | 354 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | David Kane | Summit Ridge Energy | MAINE DG HOLDINGS LLC | 612 Meadow Rd (Rte 121) Casco | 2000149310 | 30012382922 | Solar | [5 empty] | 43.9786 | -70.5153 | 621 MEADOW Rd RTE 121 |  |  | Casco |  | RAYMOND 115 KV | 445D2 | 445T2 |  | 9310-L0185-1060-0052-ED00064 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2020-07-08 | 2020-07-01 | 2020-07-09 | 2020-07-08 | 2020-07-09 | 2020-08-27 |  | 2020-09-11 |  | 2020-08-27 | 2020-08-27 | 2020-09-11 |  |  | 2020-09-10 |  |  | CS | 2020-09-10 | [6 empty] | CS |  |  | 2020-09-10 | [29 empty] | 2020-09-23 | [6 empty] | Yes |  |  |  |  | 2020-11-30 | 2022-07-29 |  | 2021-06-24 | Addendum |  |  | 2020-12-01 | 2022-07-29 | [7 empty] | 2020-12-02 | [17 empty] | 2020-12-08 | [5 empty] | 2020-12-08 | [9 empty] | 2020-12-10 |  | 2020-12-22 | [8 empty] | 405631 |  |  |  | 2024-04-17 | 2020-11-14: 2021-01-19; 2020-11-14: 2021-01-19; 2021-07-28: 2021-07-28; 2021-07-28: 2021-07-28; 2023-10-27: 2022-08-09 | [15 empty] | TBD | [11 empty] | TRUE | TRUE | 497 | 2021-01-19 | 2021-01-19 | 2021 | 2021 | 2021 |  |  |  | 2021-06-24 | Addendum
498 |  | Govinda Neupane |  | 2020-06-26 | 2022-09-09 |  |  | 2022-12-01 | L2_Bump |  | 2023-10-06 | L2_Bump |  | 2023-12-06 | L2_Bump | [20 empty] | 5 - GUIL |  | 821D1 | 230 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Melissa Reed | FFP ORIGINATION LLC | FFP ORIGINATION LLC | 375 Me-Rt 150 Parkman Me | 2000165043 | 30012417579 | Solar | [5 empty] | 45.1477 | -69.415 | 375 ME-RT 150 |  |  | Parkman |  | GUILFORD | 821D1 | 821T1 |  | FLOC-MISSING-01142021 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2020-07-08 | 2020-07-06 | 2020-07-13 | 2020-07-08 | 2020-07-13 | 2021-09-16 | 2021-10-25 | 2021-09-30 | 2021-10-25 | 2021-10-26 | 2021-10-26 | 2021-11-10 | [5 empty] | FS | 2021-11-09 | IS | 2022-02-23 |  |  |  |  | Split | 2021-11-09 | 2022-02-23 |  |  |  | 2022-03-09 | 2024-08-30 |  |  | 2021-11-21 | 2022-03-09 |  |  | 2021-11-23 | 2022-03-14 | [6 empty] | 2021-11-21 | 2022-03-09 | 2022-03-09 | [6 empty] | 2021-11-23 | 2022-03-14 | [10 empty] | 2021-12-30 | 2022-04-26 | [5 empty] | 2021-12-28 | 2022-04-26 | [7 empty] | 2021-12-29 | 2022-04-27 | [7 empty] | 2022-01-14 | 2022-04-29 | [7 empty] | 2022-02-01 | 2022-05-09 | [6 empty] | 2022-02-01 | 2022-05-09 | [8 empty] | 2022-06-24 |  | 2022-06-24 |  | 2022-08-02 | [10 empty] | 2024-10-04 | 2020-11-14: 2022-08-04; 2020-11-14: 2022-08-04 | [15 empty] | Requested | [11 empty] | TRUE | TRUE | 498 | 2022-08-04 | 2022-08-04 | 2022 | 2022 | 2022
499 |  | Marshall Ripley | Rick Duperre | 2020-07-01 | 2023-02-02 | L2_Bump | [29 empty] | 2 - SCAR |  | 693D1 | 40 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Peter Bay | EDF Renewables | BARRENS SOLAR PARTNERS LLC | 1 Green Rd Scarborough | 2000134214 | 30014894254 | Solar | [5 empty] | 43.6356 | -70.3724 | 1 Green Rd |  |  | Scarborough | 3 | SCARBOROUGH | 693D1 | 693T1 |  | 9310-L0373-5200-0064-ED00003 | Non-FERC | WITHDRAWN | WITHDRAWN | 325000 | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2020-07-09 | 2020-07-09 | 2020-07-16 | 2020-07-09 | 2020-07-16 | 2020-07-22 |  | 2020-08-05 |  | 2020-07-22 | 2020-07-22 | 2020-08-05 |  |  | 2020-07-27 |  |  | CS | 2020-07-27 | [6 empty] | CS |  |  | 2020-07-27 |  |  | 2023-02-06 | 2023-05-22 | [7 empty] | 2020-07-31 |  |  | 2023-03-17 | 2023-06-06 | [7 empty] | 2023-03-09 | [5 empty] | 2020-08-03 |  |  | 2023-03-09 | 2023-06-23 |  |  | Pending |  |  |  |  | 2020-10-06 |  |  | 2021-06-08 | Addendum |  |  | 2020-10-06 |  |  | 2023-04-21 | 2023-07-03 |  |  |  |  | 2020-10-13 |  |  | 2023-04-24 | [9 empty] | 2023-05-01 |  |  |  |  | 2020-10-21 | [15 empty] | 2020-11-03 |  | 2020-11-04 | 2023-07-14 |  | 2023-07-14 | [5 empty] | 1359989 |  |  |  | 2025-02-04 | 2020-11-05 | 2020-11-05 | 2021-06-24 | 2021-06-24 | 2023-07-17 | 2023-07-17 | [19 empty] | 10300733087 | [11 empty] | TRUE | TRUE | 499 | 2020-11-05 | 2020-11-05 | 2020 | 2020 | 2020 |  |  |  | 2021-06-08 | Addendum
500 |  | Govinda Neupane |  | 2020-07-01 | 2022-11-08 | [30 empty] | 12 - STUR |  | 858D3 | 463 |  | WITHDRAWN | WITHDRAWN |  | Mike Imoto | MEVS LLC AKA CENERGY | MEVS LLC | Hodey Rd Farmington | 2000141275 | 30012406010 | Solar | [5 empty] | 44.6403 | -70.0805 | Hodey Rd |  |  | Farmington |  | STURTEVANT | 858D3 | 858T2 |  | 9310-L0440-2030-0057-ED00006 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2020-07-09 | 2020-07-09 | 2020-07-16 | 2020-07-09 | 2020-07-16 |  |  | 1900-01-12 | [127 empty] | 2022-12-07 | [37 empty] | TRUE | TRUE | 500 | 0 | 0 | 1900 | #VALUE! | #VALUE!
501 |  | Marshall Ripley | Rick Duperre | 2020-07-01 | [31 empty] | 3 - SCAR |  | 693D1 | 499 |  | WITHDRAWN | WITHDRAWN |  | Mike Imoto | MEVS LLC AKA CENERGY | MEVS LLC | 22 W Beech Ridge Rd (Scarborough) | 2000141275 |  | Solar | [7 empty] | 22 W Beech Ridge Rd |  |  | Scarborough |  | SCARBOROUGH | 693D1 |  |  | 86-Withdrawn-86d | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2020-07-09 | 2020-07-16 |  |  |  |  | 1900-01-12 | [57 empty] | No Study | [69 empty] | 2020-04-10 | [37 empty] | TRUE | TRUE | 501 | 0 | 0 | 1900 | 1900 | 1900
502 |  | Govinda Neupane |  | 2020-07-02 | 2022-11-08 | L2_Bump |  | 2023-01-09 | L2_bump |  | 2023-05-08 | L2_bump |  | 2023-07-18 | L2_Bump |  | 2023-10-05 | L2_Bump | [17 empty] | 13 - STUR |  | 858D1A | 500 |  | WITHDRAWN | WITHDRAWN |  | Kevin Hu | NEXTERA ENERGY RESOURCES | DG MAINE CS LLC | 107 Vacation Estates Ln / Farmingto | 2000147169 | 30012365448 | Solar | [5 empty] | 44.707 | -70.1458 | 107 Vacation Estates Ln |  |  | Farmington |  | STURTEVANT | 858D1A | 858T1 |  | 9310-L0439-2030-0068-ED00031 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2020-07-10 | 2020-07-10 | 2020-07-17 | 2020-07-10 | 2020-07-17 |  |  | 1900-01-12 | [127 empty] | 2024-04-05 | [37 empty] | TRUE | TRUE | 502 | 0 | 0 | 1900 | #VALUE! | #VALUE!
503 |  | Eben Snow | Brent Brooks | 2020-07-02 | 2022-06-02 |  |  | 2022-12-15 | L2_Bump |  | 2023-02-03 | L2_Bump |  | 2023-03-20 | L2_Bump |  | 2023-11-29 | wthdw |  |  |  |  | 2023-01-09 | wthdw | [11 empty] | 14 - HORD |  | 420D4 | 402 |  | WITHDRAWN | WITHDRAWN |  | Daniel Serber | NEXTGRID INC | NEXTGRID INC | 100 Torrey Rd Auburn | 2000104939 | 30012264005 | Solar | [5 empty] | 44.0375 | -70.3141 | 100 Torrey Rd |  |  | Auburn | 9 | HOTEL ROAD | 420D4 | 420T1 | 34.5 | 9310-L0140-0230-0530-ED00009 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2020-07-13 | 2020-07-10 | 2020-07-17 | 2020-07-13 | 2020-07-20 | 2024-03-06 | 2024-03-11 | 2024-03-20 | [127 empty] | 2024-03-19 | [37 empty] | TRUE | TRUE | 503 | 0 | 0 | 1900 | #VALUE! | #VALUE!
504 |  | Govinda Neupane |  | 2020-07-08 | [31 empty] | 3 - TPCO |  | 453D1 | 235 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Mike Imoto | MEVS LLC AKA CENERGY | MEVS COFFIN LLC | Corner Main St/Bethel Rd W Paris | 2000192409 | 30012794654 | Solar | [5 empty] | 44.3312 | -70.5571 | Int. Main St and Bethel |  |  | West Paris | 505 | TRAP CORNER | 453D1 | 453T1 |  | 9310-L0195-6315-0023-ED00059 | Non-FERC | WITHDRAWN | WITHDRAWN | NONE | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2020-07-15 | 2020-07-15 | 2020-07-22 | 2020-07-15 | 2020-07-22 | 2020-07-30 |  | 2020-08-13 |  | 2020-07-30 | 2020-07-30 | 2020-08-13 |  |  | 2020-08-13 |  |  | CS | 2020-08-18 | RS | [5 empty] | CS |  |  | 2020-08-18 | [29 empty] | 2020-08-19 | 2020-11-23 | [5 empty] | Yes |  |  |  |  | 2020-10-23 | 2021-01-08 |  | 2021-05-01 | Addendum |  |  | 2020-10-23 | 2021-01-08 | [7 empty] | 2020-10-27 | 2021-01-18 | [16 empty] | 2020-11-04 | 2021-01-21 | [6 empty] | 2020-11-04 | 2021-01-21 |  |  |  |  | 2021-05-05 |  |  | 2021-05-05 |  |  | 2022-08-15 | 2022-08-16 | [5 empty] | 211412 | 2020-10-12 | 202754 | 2022-08-10 | 2024-01-30 | 2020-11-14: 2021-05-06; 2020-11-14: 2021-05-06; 2021-07-28: 2021-05-06; 2021-07-28: 2021-05-06; 2023-10-27: 2022-08-23 | [15 empty] | 10300781152 | [11 empty] | TRUE | TRUE | 504 | 2021-05-06 | 2021-05-06 | 2021 | 2021 | 2021 | 44321 |  | 44321 | 2021-05-01 | Addendum
505 |  |  | KRISTOFER COLEMAN | 2020-07-09 | [31 empty] | 1 - TPOL |  | 249D1 |  |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Dan Ryan | Turning Point Energy | TPE DEVELOPMENT LLC | Old Portland Rd, Brunswick | 2000123236 | 30012454572 | Solar | [5 empty] | 43.9089 | -70.0329 | Old Portland Rd |  |  | Brunswick | 23 | TOPHAM OLD | 249D1 | 213T1 |  | 9310-L0032-0770-0105-ED00031 | Non-FERC | WITHDRAWN | WITHDRAWN | 325000 | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2020-07-16 | 2020-07-16 | 2020-07-23 | 2020-07-16 | 2020-07-23 | 2020-08-26 |  | 2020-09-10 |  | 2020-08-26 | 2020-08-26 | 2020-09-10 |  |  | 2020-08-26 |  |  | CS | 2020-08-26 | [6 empty] | CS |  |  | 2020-08-26 | [29 empty] | 2020-09-01 | 2022-11-18 | [5 empty] | Yes |  |  |  |  | 2020-11-05 | 2023-01-14 |  | 2021-06-03 | Addendum |  |  | 2020-11-05 | [8 empty] | 2020-11-05 | [17 empty] | 2020-11-10 | [15 empty] | 2020-11-23 |  | 2020-11-23 | 2022-01-25 | [7 empty] | 761212 |  | 1219211 | 2022-12-16 | 2024-02-26 | 2020-12-01 | 2020-12-01 | 2021-06-04 | 2021-06-04 | 2023-01-31 | 2023-02-01 | [19 empty] | 10300738502 | [11 empty] | TRUE | TRUE | 505 | 2020-12-01 | 2020-12-01 | 2020 | 2020 | 2020 |  |  |  | 2021-06-03 | Addendum
506 |  | Govinda Neupane |  | 2020-07-09 | [31 empty] | 3 - RUIP |  | 466D1 | 62 |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2021-02-25 | Scott Moore | REA Investments | Canton GLC Solar LLC | Edmonds Rd Solar Canton | 2000255318 | 30013640310 | Solar | 3000 | 3 | 4318 |  |  | 44.4435 | -70.3167 | 62 Pleasant St |  |  | Canton | 3H | RUMFORD INDUSTRIAL PARK | 466D1 | 466T1 |  | 9310-L0205-0990-0006-ED00124 | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2020-07-16 | 2020-07-16 | 2020-07-23 | 2020-07-16 | 2020-07-23 | 2020-07-30 |  | 2020-08-13 |  | 2020-07-30 | 2020-07-30 | 2020-08-13 |  |  | 2020-08-13 |  |  | CS | 2020-08-17 | [6 empty] | CS |  |  | 2020-08-17 | [29 empty] | 2020-08-20 | [6 empty] | Yes |  |  |  |  | 2020-10-26 |  |  | 2021-05-20 | Addendum |  |  | 2020-10-26 | [8 empty] | 2020-10-26 | 2020-10-28 | [16 empty] | 2020-11-05 | [13 empty] | 2021-06-15 |  | 2020-11-05 |  | 2020-11-08 | 2023-06-05 | [7 empty] | 384492 | 2020-10-20 |  |  |  | 2020-12-08 | 2020-12-08 | 2021-07-08 | 2021-07-08 | 2023-12-13 | 2023-12-13 | [19 empty] | 10300743832 | [11 empty] | TRUE | TRUE | 506 | 2020-12-08 | 2020-12-08 | 2020 | 2020 | 2020 | 44362 |  |  | 2021-05-20 | Addendum
507 |  | Marshall Ripley | Rick Duperre | 2020-07-13 | [31 empty] | 4 - SCAR |  | 693D1 | 501 |  | WITHDRAWN | WITHDRAWN |  | Peter Bay | EDF Renewables | EDF RENEWABLES | 1 Green Rd Scarborough | 2000134214 |  | Solar | [7 empty] | 1 Greed Rd |  |  | Scarborough |  | SCARBOROUGH | 693D1 |  |  | 86-Withdrawn-86d | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2020-07-20 | 2020-07-27 |  |  |  |  | 1900-01-12 | [127 empty] | 2020-07-13 | [37 empty] | TRUE | TRUE | 507 | 0 | 0 | 1900 | #VALUE! | #VALUE!
508 |  | Rigel Paradise | Rick Duperre | 2020-07-13 | [31 empty] | 3 - BDIP |  | 673D1 | 378 |  | WITHDRAWN | WITHDRAWN |  | Santiago Quijano | Bluewave MA, LLC | BWC BATSON RIVER LLC | Mountain Rd Arundel | 2000167276 | 30012451180 | Solar | [5 empty] | 43.4293 | -70.4951 | Mountain Rd |  |  | Arundel |  | BIDDEFORD INDUSTRIAL PARK | 673D1 |  |  | 9310-L0343-4180-0013-ED00054 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2020-07-20 | 2020-07-27 |  |  |  |  | 1900-01-12 | [127 empty] | 2020-11-18 | [25 empty] | NO | [11 empty] | TRUE | TRUE | 508 | 0 | 0 | 1900 | #VALUE! | #VALUE!
509 |  | Eben Snow | Brent Brooks | 2020-07-13 | [31 empty] | 5 - PATP |  | 409D1 | 408 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Payne Morgan | Encore Redevelopment, LLC | ER HAMLIN SOLAR, LLC | 188 Ryerson Hill Rd Paris | 2000134579 | 30012921687 | Solar | [5 empty] | 44.2788 | -70.4953 | 188 Ryerson Hill Rd |  |  | Paris | 24 | PARIS TAP | 409D1 | 409T1 |  | 9310-L0122-4500-0004-ED00014 | FERC | WITHDRAWN | WITHDRAWN | NONE | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2020-07-20 | 2020-07-20 | 2020-07-27 | 2020-07-20 | 2020-07-27 | 2020-08-06 |  | 2020-08-20 |  | 2020-08-06 | 2020-08-06 | 2020-08-20 |  |  | 2020-08-20 |  |  | CS | 2020-08-26 | [6 empty] | CS |  |  | 2020-08-26 | [11 empty] | 2020-08-21 | [17 empty] | 2020-09-08 | [6 empty] | Yes |  |  |  |  | 2020-11-11 |  |  | 2021-05-04 | Addendum |  |  | 2020-11-11 | [8 empty] | 2020-12-28 | [17 empty] | 2020-12-29 | [5 empty] | 2020-12-29 |  | 2020-12-29 | [5 empty] | 2021-05-11 |  | 2021-05-11 | 2021-05-11 | 2020-12-29 | [8 empty] | 531423 |  |  |  | 2024-07-19 | 2020-11-14: 2021-05-19; 2020-11-14: 2021-05-19; 2021-07-28: 2021-05-19; 2021-07-28: 2021-05-19 | [15 empty] | 10300785665 | [11 empty] | TRUE | TRUE | 509 | 2021-05-19 | 2021-05-19 | 2021 | 2021 | 2021 | 44327 |  | 44327 | 2021-05-04 | Addendum
510 |  | Govinda Neupane |  | 2020-07-14 | 2022-11-08 | [30 empty] | 14 - STUR |  | 858D2 | 502 |  | WITHDRAWN | WITHDRAWN |  | Jeffrey Lord | Con Edison Clean Energy | CONSOLIDATED EDISON SOLUTIONS | Route 27 (New Portland) | 2800000074 | 30012463557 | Solar/Battery | [5 empty] | 44.9161 | -70.1225 | Rt. 27 Pole 297 |  |  | New Portland | 297 | STURTEVANT | 858D2 | 858T1 |  | 9310-L0439-4060-0026-ED00108 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2020-07-21 | 2020-07-21 | 2020-07-28 | 2020-07-21 | 2020-07-28 |  |  | 1900-01-12 | [127 empty] | 2023-05-08 | [37 empty] | TRUE | TRUE | 510 | 0 | 0 | 1900 | #VALUE! | #VALUE!
511 |  |  | KRISTOFER COLEMAN | 2020-07-20 | [31 empty] | 3 - BRIS | 1 - BRIS | 210D1 | 491 |  | EXECUTED | EXECUTED |  | Nathaniel Curtis | MIDCOAST SOLAR LLC | C2 BRISTOL II LLC | 1829 Bristol Rd, Bristol | 2000162495 | 30014505306 | Solar | 1999 | 1.999 | 3173.04 |  |  | 43.9213 | -69.5198 | 1829 Bristol Rd |  |  | Bristol | 69 | BRISTOL | 210D1 | 210T1 |  | 9310-L0027-0710-0093-ED00231 | Non-FERC | COST SHARE | COST SHARE (250,000) | 90880 | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2020-07-27 | 2020-07-27 | 2020-08-03 | 2020-07-27 | 2020-08-03 | 2020-11-12 |  | 2020-11-30 |  | 2020-11-12 | 2020-11-13 | 2020-12-01 |  |  | 2020-11-16 | 2021-08-24 |  | CS | 2020-11-16 | RS | 2021-08-24 |  |  |  |  | CS |  |  | 2020-11-16 | 2021-08-24 | [28 empty] | 2020-11-17 | 2021-09-16 | [10 empty] | 2021-01-26 | 2021-10-31 |  | 2021-06-15 | Addendum |  |  | 2021-01-26 | 2021-10-27 | [7 empty] | 2021-01-26 | 2021-10-27 | [16 empty] | 2021-02-01 | 2021-11-03 | [6 empty] | 2021-02-01 | 2021-11-03 |  |  |  |  | 2021-07-13 |  |  |  | 2021-11-24 |  |  |  | 2024-08-23 | 2024-08-23 |  |  |  | 462420 | 2021-06-11 | 152733 | 2021-10-15 |  | 2020-11-14: 2021-11-24; 2020-11-14: 2021-12-03 | [11 empty] | Q3 2026 |  |  |  | Requested | [11 empty] | TRUE | TRUE | 511 | 2021-11-24 | 2021-11-24 | 2021 | 2021 | 2021 | 44390 |  |  | 2021-06-15 | Addendum
512 |  | Govinda Neupane |  | 2020-07-22 | 2022-05-31 | L2_Bump | [29 empty] | 6 - DOVE |  | 815D2 | 460 |  | WITHDRAWN | WITHDRAWN |  | Melissa Reed | FFP ORIGINATION LLC | FFP ORIGINATION LLC | 107 Park St / Dover-Foxcroft | 2000165043 | 30012590045 | Solar | [5 empty] | 45.1927 | -69.241 | 107 Park St |  |  | Dover-Foxcroft | 15 | DOVER | 815D2 | 815T2 |  | 9310-L0397-1650-0084-ED00027 | FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2020-07-29 | 2020-07-29 | 2020-08-05 | 2020-07-29 | 2020-08-05 | 2021-12-16 | 2021-01-06 | 2022-01-03 | 2021-01-06 | 2021-01-14 | 2021-01-14 | 2021-01-29 | 2022-01-26 | 2022-05-25 |  |  |  | FS | 2022-01-26 | IS | 2022-05-25 |  |  |  |  | Split | 2022-01-26 | 2022-05-25 |  |  |  | 2023-06-09 | [7 empty] | 2022-03-02 |  |  |  | 2023-08-07 | [8 empty] | 2023-08-23 |  |  |  | 2022-03-02 |  |  |  |  | 2023-08-28 | [64 empty] | 2022-02-07 | 2022-02-14 | [7 empty] | 2024-01-09 | [37 empty] | TRUE | TRUE | 512 | 0 | 0 | 1900 | 1900 | 1900
513 |  | Marshall Ripley | Rick Duperre | 2020-07-22 | [31 empty] | 3 - BRML |  | 678D1 | 485 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Mike Imoto | MEVS LLC AKA CENERGY | MEVS LLC | 192 Salmon Falls Rd Hollis Me | 2000141275 | 30012493497 | Solar | [5 empty] | 43.607 | -70.5648 | 192 Salmon Falls Rd |  |  | Hollis | 6 | BAR MILLS | 678D1 |  |  | 9310-L0355-2647-0086-ED00006 | Non-FERC | WITHDRAWN | WITHDRAWN |  |  |  |  | K&A Engineering | Bruce Jagolinzer |  | 2020-07-29 | 2020-07-29 | 2020-08-05 | 2020-07-29 | 2020-08-05 | 2020-11-12 |  | 2020-11-30 |  | 2020-11-12 | 2020-11-13 | 2020-12-01 |  |  | 2020-12-01 |  |  | CS | 2020-12-02 | [6 empty] | CS |  |  | 2020-12-02 | [29 empty] | 2020-12-08 | [6 empty] | Pending |  |  |  |  | 2021-02-12 |  |  | 2021-06-11 | Report |  |  | 2021-06-11 | [8 empty] | 2021-06-11 | [17 empty] | 2021-06-23 | [7 empty] | 2021-06-23 | [18 empty] | 441068 |  |  |  | 2022-03-23 | 2020-11-14: 2021-07-06; 2020-11-14: 2021-07-06; 2021-07-28: 2021-07-06; 2021-07-28: 2021-07-06 | [15 empty] | 10300804630 | [11 empty] | TRUE | TRUE | 513 | 2021-07-06 | 2021-07-06 | 2021 | 2021 | 2021 |  |  |  | 2021-06-11 | Report
514 |  | Govinda Neupane |  | 2020-07-22 | [31 empty] | 3 - BNHE |  | 120D1 | 375 |  | WITHDRAWN | WITHDRAWN |  | Cate Parker | Summit Ridge Energy | SRE SOLAR ORIGINATION 2 LLC | 175 Billings Rd Hermon | 2000138691 | 30012370760 | Solar/Battery | [5 empty] | 44.8202 | -68.8972 | 175 Billings Rd |  |  | Hermon | 33 | BANGOR HYDRO (Versant) | 120D1 | Not Applicable |  | FLOC-MISSING-01142021 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2020-07-29 | 2020-07-29 | 2020-08-05 | 2020-07-29 | 2020-08-05 | 2023-01-06 |  | 2023-01-20 | [127 empty] | 2023-01-13 | [37 empty] | TRUE | TRUE | 514 | 0 | 0 | 1900 | #VALUE! | #VALUE!
515 |  | Govinda Neupane |  | 2020-07-22 | 2023-02-28 | L2_Bump |  | 2023-03-06 | L2_Bump | [26 empty] | 3 - RUMF |  | 447D2 | 436 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Cate Parker | Summit Ridge Energy | SRE SOLAR ORIGINATION 2 LLC | 164 Wyman Hill Rd | 2000138691 | 30012370752 | Solar/Battery | [5 empty] | 44.31 | -70.3043 | 164 Wyman Hill Rd |  |  | Rumford | 45 | RUMFORD | 447D2 | 447T4 |  | 9310-L0187-5020-0151-ED00056 | Non-FERC | WITHDRAWN | WITHDRAWN | NONE | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2020-07-29 | 2020-07-29 | 2020-08-05 | 2020-07-29 | 2020-08-05 | 2020-09-03 |  | 2020-09-18 |  | 2020-09-03 | 2020-09-03 | 2020-09-18 |  |  | 2020-09-18 |  |  | CS | 2020-09-18 | [6 empty] | CS |  |  | 2020-09-18 |  |  | 2023-03-01 | [11 empty] | 2023-03-28 | [8 empty] | 2023-04-04 | [5 empty] | 2020-09-28 |  |  | 2023-04-04 |  |  |  | Yes |  |  |  |  | 2020-12-03 |  |  | 2021-05-21 | Addendum |  |  | 2020-12-04 |  |  | 2023-05-17 | [5 empty] | 2020-12-10 |  |  | 2023-05-18 | [14 empty] | 2020-12-16 | [5 empty] | 2020-12-16 | [7 empty] | 2021-06-15 |  | 2020-12-21 | [10 empty] | 825174 |  | 1252857 | 2023-05-17 | 2023-06-26 | 2020-11-14: 2021-02-02; 2020-11-14: 2021-02-02; 2021-07-28: 2021-06-15; 2021-07-28: 2021-06-15 | [15 empty] | 10300758910 | [11 empty] | TRUE | TRUE | 515 | 2021-02-02 | 2021-02-02 | 2021 | 2021 | 2021 | 44362 |  |  | 2021-05-21 | Addendum
516 |  | Lanie Patterson | Anthony Boucher | 2020-07-24 | 2021-06-29 |  |  | 2022-12-01 | L2_Bump | [26 empty] | 6 - PROS |  | 846D1 | 495 |  | WITHDRAWN | WITHDRAWN |  | Tiffiny Chase | Aspen Power Partners | ME I PROSPECT HAWES BRIDGE LLC | 200 Hawes Bridge Rd Prospect | 2000148928 | 30013277006 | Solar | [5 empty] | 44.5472 | -68.8819 | 200 Hawes Bridge Rd |  |  | Prospect | 7 | PROSPECT | 846D1 | 846T1 | 12.47 | 9310-L0426-4770-0018-ED00031 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2020-07-31 | 2020-07-31 | 2020-08-07 | 2020-07-31 | 2020-08-07 | 2022-09-15 | 2022-09-15 | 2022-09-29 | 2022-09-29 | 2022-09-29 | 2022-09-29 | 2022-10-14 |  |  | 2022-10-07 |  |  | CS | 2022-10-07 | [6 empty] | CS |  |  | 2023-04-16 | [7 empty] | 2022-10-18 |  |  | 2022-10-14 | 2023-04-14 | [8 empty] | 2023-04-19 | [8 empty] | 2023-04-26 | [11 empty] | 2023-06-30 | [6 empty] | 2023-06-08 | [8 empty] | 2023-06-08 | [8 empty] | N/A | [8 empty] | N/A | [30 empty] | 2023-06-30 | [37 empty] | TRUE | TRUE | 516 | 0 | 0 | 1900 | #VALUE! | #VALUE!
517 |  | Rigel Paradise | Rick Duperre | 2020-07-24 | [31 empty] | 3 - LOUD |  | 633D1 | 103 |  | WITHDRAWN | WITHDRAWN |  | Greg Rosshirt | BORREGO SOLAR SYSTEMS INC | 510 PV PROJECT DEVELOPMENT LLC | 568 Boom Rd Saco | 2000113260 | 30012094790 | Solar/Battery | [7 empty] | 568 Boom Rd |  |  | Saco |  | LOUDEN | 633D1 |  |  | 9310-L0265-5090-0022-ED00142 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2020-07-31 | 2020-08-07 |  |  |  |  | 1900-01-12 | [57 empty] | Yes | [69 empty] | 2020-08-30 | [37 empty] | TRUE | TRUE | 517 | 0 | 0 | 1900 | #VALUE! | #VALUE!
518 |  | Eben Snow | Brent Brooks | 2020-07-24 | [31 empty] | 3 - FRYT |  | 405D1 | 96 |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED |  | JOHN WEBSTER | Bold Coast Energy | Saco River Hydro LLC | Swansfalls Rd Fryeburg | 2800622053 | 30014906421 | Hydro | 600 | 0.6 |  |  |  | 44.0405 | -70.994 | Swansfalls Rd |  |  | Fryeburg | 211 | FRYEBURG TAP | 405D1 | 405T1 |  | 9310-L0116-2130-0097-ED00132 | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2020-07-31 | 2020-07-31 | 2020-08-07 | 2020-07-31 | 2020-08-07 | 2020-10-28 |  | 2020-11-12 |  | 2020-10-28 | 2020-10-28 | 2020-11-11 |  |  | 2020-11-04 | 2021-07-12 |  | CS | 2020-11-04 | RS | 2021-07-12 |  |  |  |  | CS |  |  | 2020-11-04 | 2021-07-12 | [28 empty] | 2020-11-13 | 2021-07-19 | [5 empty] | Pending |  |  |  |  | 2021-01-22 | 2021-08-30 |  | 2021-05-12 | Report |  |  | 2021-05-12 | 2021-08-30 | [7 empty] | 2021-01-29 | 2021-08-30 | [16 empty] | 2021-02-02 | 2021-09-15 | [6 empty] | 2021-02-02 | 2021-09-15 |  |  |  |  | 2021-05-17 |  | 2021-10-06 |  | 2021-10-06 | [8 empty] | 208001 | 2021-08-27 |  |  |  | 2020-11-14: 2021-10-06; 2020-11-14: 2021-11-05 | [15 empty] | Requested | [11 empty] | TRUE | TRUE | 518 | 2021-10-06 | 2021-10-06 | 2021 | 2021 | 2021 | 44333 |  |  | 2021-05-12 | Report
519 |  | Eben Snow | Brent Brooks | 2020-07-28 | 2023-06-28 | L2_Bump | [29 empty] | 2 - SABA |  | 450D1 | 271 | Yes | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED |  | Mike Imoto | MEVS LLC AKA CENERGY | MEVS PULK LLC | 69 Lisbon Rd, Sabattus | 2000182843 | 30012667306 | Solar | 4950 | 4.95 | 7367 |  |  | 44.1063 | -70.1103 | 69 Lisbon Rd |  |  | Sabattus | 14 | SABATTUS | 450D1 | 450T1 | 12.47 | 9310-L0192-6230-0049-ED00008 | Non-FERC | TRIGGERING | TRIGGERING | 325000 | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2020-08-11 | 2020-08-04 | 2020-08-11 | 2020-08-04 | 2020-08-11 | 2020-08-14 |  | 2020-08-28 |  | 2020-08-14 | 2020-08-14 | 2020-08-28 |  |  | 2020-08-19 | 2023-11-03 |  | CS | 2020-08-19 | [6 empty] | CS |  |  | 2020-08-19 | 2023-11-03 |  | 2023-07-03 | [9 empty] | 2023-11-09 |  | 2023-08-19 | [6 empty] | 2023-11-17 |  | 2023-08-29 | [5 empty] | 2020-08-20 | 2023-11-22 |  | 2023-08-31 |  |  |  | Yes |  |  |  |  | 2020-10-26 | 2024-01-09 |  | 2021-05-20 | Addendum |  |  | 2020-10-26 | 2024-01-09 |  | 2023-10-16 | [5 empty] | 2020-10-28 | 2024-01-09 |  | 2023-10-17 | [14 empty] | 2020-11-05 | [15 empty] | 2020-11-05 |  | 2020-11-05 | 2024-01-23 | [7 empty] | 568570 |  | 646473 | 2023-10-16 |  | 2020-11-10 | 2020-11-10 | 2021-07-22 | 2021-07-22 | 2022-07-12 | 2022-07-27 |  |  |  |  | 2025-09-08 | 2025-09-08 | [13 empty] | 10300733101 | [11 empty] | TRUE | TRUE | 519 | 2020-11-10 | 2020-11-10 | 2020 | 2020 | 2020 |  |  |  | 2021-05-20 | Addendum
520 |  | Eben Snow | Brent Brooks | 2020-07-28 | [31 empty] | 6 - NORW |  | 435D1 | 317 |  | WITHDRAWN | WITHDRAWN |  | Nate Niles | REVISION ENERGY INC | REVISION ENERGY INC | 239 E Oxford Rd So Paris | 2000038393 | 30012500556 | Solar | [5 empty] | 44.2049 | -70.4945 | 239 East Oxford Rd |  |  | South Paris |  | NORWAY | 435D1 |  |  | 9310-L0170-4500-0026-ED00052 | FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2020-08-04 | 2020-08-11 |  |  |  |  | 1900-01-12 | [57 empty] | No Study | [69 empty] | 2021-08-26 | [37 empty] | TRUE | TRUE | 520 | 0 | 0 | 1900 | #VALUE! | #VALUE!
521 |  | Govinda Neupane |  | 2020-07-29 | [31 empty] | 8 - NEWP |  | 837D2 | 211 |  | WITHDRAWN | WITHDRAWN |  | Matthew Doubleday | SunRaise Investments LLC | SUNRAISE DEVELOPMENT LLC | 125 Valley Rd Plymouth | 2000124937 |  | Solar/Battery | [7 empty] | 125 Valley Rd |  |  | Plymouth |  | NEWPORT | 837D2 |  |  | 9310-L0419-4695-0023-ED00002 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2020-08-05 | 2020-08-12 |  |  |  |  | 1900-01-12 | [127 empty] | 2021-06-24 | [37 empty] | TRUE | TRUE | 521 | 0 | 0 | 1900 | #VALUE! | #VALUE!
522 |  | Rigel Paradise | Rick Duperre | 2020-07-30 | [31 empty] | 6 - LIME |  | 632D2 | 492 |  | WITHDRAWN | WITHDRAWN |  | Christian L'Oranger | Fogler LLC | Fogler LLC | 66 Water St Newfield | 2000174932 | 30012557168 | Solar | [5 empty] | 43.6403 | -70.9013 | 66 Water St |  |  | Newfield |  | LIMERICK | 632D2 |  |  | 9310-L0264-4110-0045-ED00058. | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2020-08-06 | 2020-08-13 |  |  |  |  | 1900-01-12 | [50 empty] | 2021-07-12 | [6 empty] | Study performed | [65 empty] | 5796665 | 2021-08-12 |  |  | 2021-12-21 | [25 empty] | STUDY | [11 empty] | TRUE | TRUE | 522 | 0 | 0 | 1900 | #VALUE! | #VALUE!
523 |  | Govinda Neupane |  | 2020-07-31 | [31 empty] | 2 - EMDE |  | 868D1 | 344 |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED |  | Jonovan (Jonny) Lizama | Luminace | MEVS Kiger LLC | Murphy Rd, Embden | 2000182847 | 30012667363 | Solar | 1000 | 1 | 1388.4 |  |  | 44.9628 | -69.8926 | Murphy Rd. |  |  | Embden | 22.1 | EMBDEN | 868D1 | 868T1 |  | 9310-L0452-1870-0006-ED00015 | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2020-08-14 | 2020-08-07 | 2020-08-14 | 2020-08-07 | 2020-08-14 | 2020-08-19 |  | 2020-09-02 |  | 2020-08-19 | 2020-08-19 | 2020-09-02 |  |  | 2020-08-26 | 2021-08-19 |  | CS | 2020-08-26 | RS | 2021-08-19 |  |  |  |  | CS |  |  | 2020-08-26 | 2021-08-19 | [10 empty] | 2020-08-25 | [17 empty] | 2020-08-28 | 2021-08-31 | [5 empty] | Yes |  |  |  |  | 2020-11-03 | 2021-10-14 | [5 empty] | 2020-11-03 | [8 empty] | 2020-11-12 | [17 empty] | 2020-11-16 | [7 empty] | 2020-11-16 | [7 empty] | 2020-11-16 |  | 2020-11-16 | [8 empty] | 406066 |  | 282849 | 2021-10-18 |  | 2020-11-14: 2020-11-17; 2020-11-14: 2020-11-17; 2021-07-28: 2021-11-02; 2021-07-28: 2021-11-05 | [15 empty] | 10300735575 | [11 empty] | TRUE | TRUE | 523 | 2020-11-17 | 2020-11-17 | 2020 | 2020 | 2020
524 |  | Rigel Paradise | Rick Duperre | 2020-08-07 | 2022-11-07 | wthdw | [29 empty] | 5 - BDPP | 1 - BDPP | 605D1 | 47 | Yes | EXECUTED | EXECUTED |  | Greg Leighton | THE MAINE WATER COMPANY | THE MAINE WATER COMPANY | 439 South St, Solar | 2800184220 | 30012499403 | Solar | 840 | 0.84 | 1134 |  |  | 43.4934 | -70.5041 | 439 South St |  |  | Biddeford | 9 | BIDDEFORD PUMP | 605D1 | 605T1 |  | 9310-L0215-0490-0312-ED00006 | Non-FERC | COST SHARE | COST SHARE (355,000) | 51149 | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2020-08-21 | 2020-08-14 | 2020-08-21 | 2020-08-14 | 2020-08-21 | 2020-08-27 |  | 2020-09-11 |  | 2020-08-27 | 2020-08-27 | 2020-09-11 |  |  | 2020-09-08 | 2021-07-19 |  | CS | 2020-09-08 | RS | 2021-07-19 |  |  |  |  | CS |  |  | 2020-09-08 |  |  | 2022-11-08 | [11 empty] | 2022-11-30 | [14 empty] | 2020-09-14 | 2022-12-02 |  | 2022-12-02 |  |  |  | Yes |  |  |  |  | 2020-11-17 | 2023-01-17 | [5 empty] | 2020-11-17 | 2021-09-14 |  | 2023-01-18 | [5 empty] | 2020-11-19 | 2021-09-14 |  | 2023-01-18 | [8 empty] | 2023-02-03 | [5 empty] | 2020-11-24 | 2021-09-16 |  | 2023-02-08 |  |  |  |  | 2020-11-24 | 2021-11-03 | [6 empty] | 2020-12-08 |  | 2020-12-08 |  |  |  | 2025-06-10 | 2025-06-10 |  |  |  | 1594176 | 2021-01-06 | 89335 | 2021-09-07 |  | 2020-11-14: 2021-11-24; 2020-11-14: 2021-12-16; 2021-07-28: 2023-02-20 | [11 empty] | Q4 2025 |  |  |  | TBD | [11 empty] | TRUE | TRUE | 524 | 2021-11-24 | 2021-11-24 | 2021 | 2021 | 2021
525 |  | Eben Snow | Brent Brooks | 2020-08-07 |  |  |  | 2023-01-05 | L2_Bump | [26 empty] | 7 - LEED |  | 471D2 | 294 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Jack Kenworthy | Walden Renewables | WALDEN SOLAR MAINE V LLC | ROUTE 106/ LEEDS | 2000120551 | 30011735872 | Solar/Battery | [5 empty] | 44.3577 | -70.1411 | Route 106 |  |  | Leeds | 10 | LEEDS | 471D2 | 471T1 | 34.5 | 9310-L0210-3210-0034-ED00256 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2020-08-21 | 2020-08-14 | 2020-08-21 | 2020-08-14 | 2020-08-21 | 2022-03-22 | 2022-03-23 | 2022-04-05 | 2022-03-24 | 2022-03-29 | 2022-03-29 | 2022-04-12 | 2022-03-31 |  | 2022-03-30 |  |  | CS | 2022-03-30 | [6 empty] | CS |  |  | 2022-03-30 |  |  | 2024-07-01 |  |  |  |  | 2022-03-31 |  |  |  |  | 2022-04-06 |  | 2024-07-15 | [5 empty] | 2022-04-06 |  |  | 2024-09-12 | [5 empty] | 2022-04-06 |  |  | 2024-09-13 | [8 empty] | 2022-06-10 | [6 empty] | 2022-06-03 |  |  | 2024-11-19 | [5 empty] | 2022-06-03 | 2022-08-25 |  | 2024-11-19 | [5 empty] | 2022-06-08 | 2022-09-12 |  | 2024-11-25 | [5 empty] | 2022-06-14 | 2022-09-12 |  | 2024-12-03 |  |  |  |  | 2022-06-14 |  |  | 2024-12-09 |  |  |  |  | 2022-06-27 |  | 2022-10-24 |  | 2022-10-28 | [10 empty] | 2025-01-06 | 2020-11-14: 2022-10-31; 2020-11-14: 2022-11-01 | [15 empty] | Requested | [11 empty] | TRUE | TRUE | 525 | 2022-10-31 | 2022-10-31 | 2022 | 2022 | 2022
526 |  | Govinda Neupane |  | 2020-08-10 | 2023-05-22 | L2_Bump | [29 empty] | 3 - MONS |  | 834D2 | 318 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Melissa Reed | FFP ORIGINATION LLC | MY POWER CORP FFP ORIGINATION LLC | 385 MOOSEHEAD LK RD GREENVILLE | 2000165043 | 30012540503 | Solar | [5 empty] | 45.4317 | -69.595 | 385 MOOSEHEAD LK RD GREENVILLE |  |  | Greenville | 45 | MONSON | 834D2 | 34.5 kV Bus |  | 9310-L0415-2340-0076-ED00076 | FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2020-08-24 | 2020-08-17 | 2020-08-24 | 2020-08-17 | 2020-08-24 | 2020-10-12 |  | 2020-10-26 |  | 2020-10-12 | 2020-10-15 | 2020-10-29 |  |  | 2020-10-28 |  |  | CS | 2020-10-28 | [6 empty] | CS |  |  | 2020-10-28 |  |  | 2023-10-17 | [11 empty] | 2023-12-22 | [8 empty] | 2023-12-22 | [5 empty] | 2020-11-04 |  |  | 2023-12-26 | [8 empty] | 2021-01-12 |  |  | 2021-05-14 | Addendum |  |  | 2021-01-12 | [8 empty] | 2021-02-04 | [17 empty] | 2021-02-09 | [7 empty] | 2021-02-09 | [5 empty] | 2021-05-25 |  | 2021-07-26 |  | 2021-07-26 | 2023-03-29 |  | 2023-03-29 | [5 empty] | 362360 |  | 483954 | 2023-01-31 | 2024-03-05 | 2020-11-14: 2021-07-21; 2020-11-14: 2021-07-21; 2021-07-28: 2023-03-30; 2021-07-28: 2023-03-30 | [15 empty] | Requested | [11 empty] | TRUE | TRUE | 526 | 2021-07-21 | 2021-07-21 | 2021 | 2021 | 2021 | 44341 |  |  | 2021-05-14 | Addendum
527 |  | Lanie Patterson | Brent Brooks | 2020-08-10 | [31 empty] | 5 - SHAW |  | 852D1 | 489 |  | WITHDRAWN | WITHDRAWN |  | Melissa Reed | FFP ORIGINATION LLC | FFP ORIGINATION LLC | 25 OLD COUNTY RD FAIRFIELD | 2000165043 | 30012540495 | Solar | [5 empty] | 44.6232 | -69.5947 | 25 Old County Rd |  |  | Fairfield | 503 | SHAWMUT | 852D1 | 852T3 |  | 9310-L0429-2000-0059-ED00009 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2020-08-24 | 2020-08-17 | 2020-08-24 | 2020-08-17 | 2020-08-24 | 2021-11-05 | 2021-11-12 | 2021-11-22 | 2021-11-12 | 2021-11-18 | 2021-11-18 | 2021-12-03 | [5 empty] | FS | 2021-12-07 | [6 empty] | Split | 2021-12-07 | [12 empty] | 2021-12-30 | [7 empty] | 2021-12-30 | [8 empty] | 2022-01-05 | [18 empty] | 2022-02-03 | [26 empty] | 2022-02-13 | [28 empty] | n/a | n/a | n/a | n/a | 2022-02-14 | [37 empty] | TRUE | TRUE | 527 | 0 | 0 | 1900 | 1900 | 1900
528 |  | Eben Snow | Brent Brooks | 2020-08-10 | 2023-03-09 | wthdw | [29 empty] | 3 - DENM |  | 413D2 | 283 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Brent Buchberger | Summit Ridge Energy | Denmark PV LLC | HEADS HILL RD DENMARK | 2000149310 | 30012535370 | Solar | [5 empty] | 43.9793 | -70.7824 | Heads Hill Rd |  |  | Denmark | 4 | DENMARK | 413D2 | 413T1 | 12.47 | 9310-L0130-1580-0022-ED00009 | Non-FERC | WITHDRAWN | WITHDRAWN | 325000 | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2020-08-24 | 2020-08-17 | 2020-08-24 | 2020-08-17 | 2020-08-24 | 2020-08-24 |  | 2020-09-08 |  | 2020-08-24 | 2020-08-24 | 2020-09-08 |  |  | 2020-08-26 |  |  | CS | 2020-08-26 | [6 empty] | CS |  |  | 2020-08-26 | [29 empty] | 2020-08-28 | [6 empty] | Yes |  |  |  |  | 2020-11-03 |  |  | 2021-05-19 | Addendum |  |  | 2020-11-03 | [8 empty] | 2020-11-03 | [17 empty] | 2020-11-06 | [13 empty] | 2021-05-27 |  | 2020-11-06 |  | 2020-11-08 |  |  |  | 2023-07-03 | 2023-07-11 |  |  |  | 675176 |  |  |  | 2023-10-09 | 2020-11-14: 2020-11-22; 2020-11-14: 2020-11-22; 2021-07-28: 2021-07-14; 2021-07-28: 2021-07-14 | [15 empty] | 10300740225 | [11 empty] | TRUE | TRUE | 528 | 2020-11-22 | 2020-11-22 | 2020 | 2020 | 2020 | 44343 |  |  | 2021-05-19 | Addendum
529 |  | Eben Snow | Brent Brooks | 2020-08-11 | 2022-06-02 |  |  | 2022-12-15 | L2_Bump |  | 2023-02-03 | L2_Bump |  | 2023-03-20 | L2_Bump |  | 2023-11-29 | wthdw |  |  |  |  | 2023-01-09 | wthdw | [11 empty] | 15 - HORD |  | 420D7 | 503 |  | WITHDRAWN | WITHDRAWN |  | Dan Csaplar | US Solar Development, LLC | USS RICKER SOLAR LLC | 257 RICKER RD NEW GLOUCESTER | 2000168122 | 30012463128 | Solar | [5 empty] | 44.026 | -70.3003 | 257 RICKER RD |  |  | New Gloucester | 26 | HOTEL ROAD | 420D7 | 420T1 | 12.47 | 9310-L0143-0230-0288-ED00016 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2020-08-25 | 2020-08-18 | 2020-08-25 | 2020-08-18 | 2020-08-25 |  |  | 1900-01-12 | [127 empty] | 2024-03-27 | [37 empty] | TRUE | TRUE | 529 | 0 | 0 | 1900 | #VALUE! | #VALUE!
530 |  | Lanie Patterson | Brent Brooks | 2020-08-11 | [31 empty] | 7 - NOAU |  | 272D6 | 462 |  | WITHDRAWN | WITHDRAWN |  | Allen Tate | US Solar Development, LLC | USS BELGRADE SOLAR LLC | BELGRADE RD SIDNEY | 2000173697 | 30012540370 | Solar | [5 empty] | 44.3931 | -69.8028 | BELGRADE RD |  |  | Sidney | 633 | NORTH AUGUSTA | 272D6 | 272T2 |  | 9310-L0470-5320-0025-ED00021 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2020-08-25 | 2020-08-18 | 2020-08-25 | 2020-08-18 | 2020-08-25 | 2023-01-13 | 2023-01-19 | 2023-01-30 | [127 empty] | 2023-01-24 | [37 empty] | TRUE | TRUE | 530 | 0 | 0 | 1900 | #VALUE! | #VALUE!
531 |  | Eben Snow | Brent Brooks | 2020-08-12 | [31 empty] | 3 - BRPO |  | 407D1 | 383 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Mike Imoto | MEVS LLC AKA CENERGY | MEVS LLC | S MAIN ST, BRYANT POND ME | 2000141275 | 30012450406 | Solar | [5 empty] | 44.3872 | -70.6321 | S Main Street |  |  | Bryant Pond | 16 | BRYANT POND | 407D1 | 407T1 |  | 9310-L0121-6475-0036-ED00010 | Non-FERC | WITHDRAWN | WITHDRAWN | NONE | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2020-08-26 | 2020-08-19 | 2020-08-26 | 2020-08-19 | 2020-08-26 | 2020-08-28 |  | 2020-09-14 |  | 2020-08-28 | 2020-08-28 | 2020-09-14 |  |  | 2020-09-14 | 2022-06-15 |  | CS | 2020-09-15 | [6 empty] | CS |  |  | 2020-09-15 | 2022-06-16 | [28 empty] | 2020-09-17 | [6 empty] | Yes |  |  |  |  | 2020-11-20 |  |  | 2021-05-01 | Addendum |  |  | 2020-11-20 | [8 empty] | 2020-12-03 | [17 empty] | 2020-12-09 | [5 empty] | 2020-12-09 |  | 2020-12-09 | [5 empty] | 2021-05-05 |  | 2020-12-10 | 2021-05-05 | [9 empty] | 655034 |  |  |  | 2023-03-03 | 2020-11-14: 2021-05-05; 2020-11-14: 2021-05-05 | [15 empty] | 10300781163 | [11 empty] | TRUE | TRUE | 531 | 2021-05-05 | 2021-05-05 | 2021 | 2021 | 2021 | 44321 |  | 44321 | 2021-05-01 | Addendum
532 |  | Lanie Patterson | Brent Brooks | 2020-08-13 | [31 empty] | 6 - DETR |  | 812D2 | 490 |  | WITHDRAWN | WITHDRAWN |  | Ben Ransom | RENESOLA POWER HOLDINGS | RENESOLA POWER HOLDINGS | 125 NORTH RD DETROIT | 2000149581 | 30012540925 | Solar | [7 empty] | 125 North Rd |  |  | Detroit |  | DETROIT | 812D2 |  |  | 9310-L0393-1600-0019-ED00052 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2020-08-20 | 2020-08-27 |  |  |  |  | 1900-01-12 | [57 empty] | Yes | [69 empty] | 2020-12-03 | [37 empty] | TRUE | TRUE | 532 | 0 | 0 | 1900 | #VALUE! | #VALUE!
533 |  | Rigel Paradise | Rick Duperre | 2020-08-17 | [31 empty] | 4 - BDIP |  | 673D1 | 508 |  | WITHDRAWN | WITHDRAWN |  | David Kane | LongRoad Development Company LLC | MAINE DG HOLDINGS LLC | Proctor Rd Arundel | 2000149310 | 30012554793 | Solar | [5 empty] | 43.4576 | -70.4931 | 31 Proctor Rd |  |  | Arundel |  | BIDDEFORD INDUSTRIAL PARK | 673D1 |  |  | 9310-L0343-4180-0013-ED00016 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2020-08-24 | 2020-08-31 |  |  |  |  | 1900-01-12 | [127 empty] | 2021-08-03 | [37 empty] | TRUE | TRUE | 533 | 0 | 0 | 1900 | #VALUE! | #VALUE!
534 |  | Govinda Neupane |  | 2020-08-19 | [31 empty] | 2 - WYHY |  | 872D1 | 118 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Spencer Egan | Encore Redevelopment, LLC | ER HIGH STREET SOLAR LLC | 1 HIGH ST BINGHAM ME | 2000134579 | 30012567076 | Solar | [5 empty] | 45.0625 | -69.8766 | 1 High Street |  |  | Bingham | 7 | WYMAN HYDRO | 872D1 | 872T11 |  | 9310-L0455-0510-0012-ED00011 | Non-FERC | WITHDRAWN | WITHDRAWN | NONE | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2020-09-01 | 2020-08-26 | 2020-09-02 | 2020-08-25 | 2020-09-01 | 2020-09-06 | 2020-09-06 | 2020-09-21 | 2020-09-06 | 2020-09-06 | 2020-09-10 | 2020-09-24 |  |  | 2020-09-24 | 2021-09-17 |  | CS | 2020-09-25 | RS | 2021-09-17 |  |  |  |  | CS |  |  | 2020-09-25 | 2021-09-17 | [18 empty] | 2020-12-14 | 2020-12-14 | 2021-09-22 | [7 empty] | 2020-12-17 | 2021-09-30 | [10 empty] | 2021-02-22 | 2021-11-15 |  | 2021-06-18 | Report |  |  | 2021-06-18 | 2021-11-10 | [7 empty] | 2021-06-18 | 2021-11-10 | [16 empty] | 2021-06-24 | 2021-11-10 | [6 empty] | 2021-06-24 | 2021-11-12 | [6 empty] | 2021-12-21 |  | 2021-12-21 |  | 2022-01-19 | [10 empty] | 2023-02-24 | 2020-11-14: 2022-01-19; 2020-11-14: 2022-01-20 | [15 empty] | Requested | [11 empty] | TRUE | TRUE | 534 | 2022-01-19 | 2022-01-19 | 2022 | 2022 | 2022 |  |  |  | 2021-06-18 | Report
535 |  | Marshall Ripley | Rick Duperre | 2020-08-19 | [31 empty] | 4 - BRML |  | 678D2 | 364 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Morgan Kerns | NEXTERA ENERGY RESOURCES | DG Maine CS LLC | 1069 LONG PLAINS RD BUXTON | 2000147169 | 30012508872 | Solar | [5 empty] | 43.6435 | -70.5311 | 1069 Long Plains Rd |  |  | Buxton | 69 | BAR MILLS | 678D2 | 678T4 | 12.47 | 9310-L0356-0820-0045-ED00253 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2020-09-02 | 2020-08-26 | 2020-09-02 | 2020-08-26 | 2020-09-02 | 2021-09-22 | 2021-10-20 | 2021-10-06 | 2021-11-07 | 2021-11-09 | 2021-11-09 | 2021-11-24 |  |  | 2021-11-09 |  |  | CS | 2021-11-09 | FC | 2022-02-18 |  |  |  |  | CS |  |  | 2021-11-09 |  | 2022-02-21 | [7 empty] | 2022-03-09 | [9 empty] | 2021-11-24 | 2021-11-24 |  | 2022-03-09 | [6 empty] | 2021-11-29 |  | 2022-03-09 | [9 empty] | 2021-02-02 |  | 2022-05-12 |  |  |  |  | 2022-02-02 |  | 2022-05-18 | [6 empty] | 2022-02-02 |  | 2022-05-19 | [15 empty] | 2022-02-07 | [7 empty] | 2022-02-07 | [7 empty] | 2022-08-16 |  | 2022-08-16 |  | 2022-09-01 | [10 empty] | 2024-09-16 | 2020-11-14: 2022-09-02; 2020-11-14: 2022-09-02 | [15 empty] | Requested | [11 empty] | TRUE | TRUE | 535 | 2022-09-02 | 2022-09-02 | 2022 | 2022 | 2022 |  |  |  |  | 2022-02-07
536 |  | Govinda Neupane |  | 2020-08-19 | 2023-04-07 | L2_Bump |  | 2023-07-17 | wthdw |  | 2023-08-14 | L2_bump |  | 2023-09-14 | L2_Bump | [20 empty] | 9 - NEWP |  | 837D2 | 521 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Tyler Adkins | UGE USA INC | UGE USA INC | Elm St Newport ME 04953 | 2000142913 | 30012565997 | Solar | [5 empty] | 44.8242 | -69.2484 | Elm Street |  |  | Newport | 57 | NEWPORT | 837D2 | 837T2 |  | 9310-L0419-4125-0003-ED00046 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2020-09-02 | 2020-08-26 | 2020-09-02 | 2020-08-26 | 2020-09-02 | 2021-06-24 | 2021-07-08 | 2021-07-09 | 2021-07-08 | 2021-07-08 | 2021-07-08 | 2021-07-22 |  |  | 2021-07-22 | 2021-11-17 |  | CS | 2021-07-22 | RS | 2021-11-17 |  |  |  |  | CS |  |  | 2021-07-22 | 2021-11-17 | [10 empty] | 2021-07-28 | [7 empty] | 2021-07-28 | 2021-07-28 | 2021-12-07 | [7 empty] | 2021-07-28 | 2021-12-02 | [10 empty] | 2021-09-30 | 2022-01-14 | [5 empty] | 2021-09-27 | 2022-01-18 | [7 empty] | 2021-09-28 | 2022-01-18 | [7 empty] | 2021-09-27 | 2022-01-19 | [7 empty] | 2021-09-29 | 2022-01-26 | [6 empty] | 2021-09-29 | 2022-01-26 | [6 empty] | 2022-03-03 |  | 2022-03-23 | 2022-06-16 | 2022-04-20 | 2022-06-16 | [9 empty] | 2024-01-19 | 2020-11-14: 2022-06-14; 2020-11-14: 2022-06-17 | [15 empty] | Requested | [11 empty] | TRUE | TRUE | 536 | 2022-06-14 | 2022-06-14 | 2022 | 2022 | 2022 |  |  |  |  | 2021-09-29
537 |  | Eben Snow | Brent Brooks | 2020-08-21 | [31 empty] | 2 - FRYE |  | 415D2 | 74 |  | WITHDRAWN | WITHDRAWN |  | David Kane | LongRoad Development Company LLC | MAINE DG HOLDINGS LLC | 333 Portland St Fryeburg | 2000149310 | 30012554900 | Solar | [5 empty] | 44.1119 | -70.965 | 333 Portland St |  |  | Fryeburg |  | FRYEBURG | 415D2 |  |  | 9310-L0132-2130-0074-ED00048 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2020-08-28 | 2020-09-04 |  |  |  |  | 1900-01-12 | [127 empty] | 2021-08-03 | [35 empty] | MA |  | TRUE | TRUE | 537 | 0 | 0 | 1900 | #VALUE! | #VALUE!
538 |  | Eben Snow | Brent Brooks | 2020-08-21 | [31 empty] | 3 - GRFA |  | 436D6 | 34 |  | WITHDRAWN | WITHDRAWN |  | Noah Gonzalez | Nexamp, Inc | NEXAMP SOLAR LLC | 1553 RIVERSIDE DR AUBURN | 2000114877 | 30012571193 | Solar | [5 empty] | 44.405 | -70.1934 | 1553 RIVERSIDE DR |  |  | Auburn | 144 | GREAT FALLS | 436D6 | 436T1 |  | 9310-L0176-0230-0483-ED00042 | FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2020-09-04 | 2020-08-28 | 2020-09-04 | 2020-08-28 | 2020-09-04 | 2020-11-17 | 2020-11-09 | 2020-12-03 | 2020-11-16 | 2020-11-17 | 2020-11-18 | 2020-12-04 |  |  | 2020-11-19 | 2022-02-16 | 2021-03-15 | CS | 2020-11-19 | RS | 2022-02-16 | FC | 2021-03-15 |  |  | CS |  |  | 2020-11-19 | 2022-02-16 | 2021-03-15 | [7 empty] | 2021-04-02 | [9 empty] | 2020-12-04 | 2020-12-04 | 2022-02-25 | 2021-04-02 | [6 empty] | 2020-12-04 | 2022-03-02 | 2021-04-07 | [9 empty] | 2021-02-10 | 2022-04-13 | 2021-06-11 | 2021-06-28 | Report |  |  | 2021-02-10 | 2022-04-15 | 2021-04-02 | [6 empty] | 2021-02-17 | 2022-06-01 | 2022-06-01 | [6 empty] | 2020-02-20 | 2022-06-01 | [7 empty] | 2021-02-22 | 2022-06-06 |  |  | 2025-02-26 |  |  |  | 2021-02-22 | 2022-06-27 | 2022-01-26 |  | 2025-02-26 | [9 empty] | 2022-02-07 | 2022-02-14 | [7 empty] | 2022-06-30 | [35 empty] | NE |  | TRUE | TRUE | 538 | 0 | 0 | 1900 | 1900 | 1900 |  |  |  |  | 2021-02-22
539 |  | Govinda Neupane |  | 2020-08-31 | 2023-05-22 | L2_Bump |  | 2024-03-05 | wthdw | [26 empty] | 4 - MONS |  | 834D2 | 526 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Melissa Reed | FFP ORIGINATION LLC | FFP ORIGINATION LLC | 110 Greenville Rd, Monson | 2000165043 | 30012590037 | Solar | [5 empty] | 45.3054 | -69.5225 | 110 Greenville Rd |  |  | Monson | 29 | MONSON | 834D2 | 34.5 kV Bus |  | 9310-L0415-3760-0017-ED00029 | FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2020-09-14 | 2020-09-08 | 2020-09-15 | 2020-09-08 | 2020-09-14 | 2021-07-24 | 2021-08-27 | 2021-08-06 | 2021-08-30 | 2021-09-02 | 2021-09-02 | 2021-09-17 |  |  | 2021-09-17 |  |  | FS | 2021-09-20 | IS | 2022-01-12 |  |  |  |  | Split | 2021-09-20 | 2022-01-13 |  |  |  | 2024-03-11 | [7 empty] | 2021-10-15 | 2022-01-25 |  |  | 2024-03-25 | [8 empty] | 2024-04-16 |  |  |  | 2021-10-15 | 2022-01-25 |  |  |  | 2024-04-16 | [6 empty] | 2021-10-26 | 2022-02-28 | [5 empty] | 2021-11-29 | 2022-03-09 |  |  |  | 2024-06-11 |  |  |  | 2021-12-03 | 2022-03-09 |  |  |  | 2024-06-12 |  |  |  | 2021-12-03 | 2022-03-11 |  |  |  | 2024-06-12 |  |  |  | 2021-12-08 | 2022-03-15 |  |  |  | 2024-06-27 |  |  | 2021-12-08 | 2022-03-15 |  |  |  | 2024-06-27 |  |  |  |  | 2022-05-16 |  | 2022-05-16 | 2023-03-27 | 2022-06-16 | 2023-03-27 | [5 empty] | 107615 | 2023-03-23 | 168851 | 2024-06-11 | 2024-08-15 | 2020-11-14: 2022-06-16; 2020-11-14: 2022-06-17; 2021-07-28: 2023-03-29; 2021-07-28: 2023-03-29 | [15 empty] | Requested | [11 empty] | TRUE | TRUE | 539 | 2022-06-16 | 2022-06-16 | 2022 | 2022 | 2022 |  |  |  | 2022-03-15
540 |  |  |  | 2020-09-04 | 2023-08-14 | L2_Bump |  | 2023-12-13 | L2_Bump | [26 empty] | 2 - LULA | 1 - LULA | 461D1 |  | Yes | EXECUTED | EXECUTED |  | Emily Byrne | Citizens Energy Corporation | SWAN RIVER SOLAR LLC | Canton pt rd Dixfield me | 2000177227 | 30012591696 | Solar | 975 | 0.975 | 1418.04 |  |  | 44.5159 | -70.4111 | Swan River |  |  | Dixfield | 7 | LUDDEN LANE | 461D1 | 461T3 |  | 9310-L0205-1620-0026-ED00003 | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2020-09-21 | 2020-09-14 | 2020-09-21 | 2020-09-14 | 2020-09-21 | 2020-12-14 |  | 2020-12-29 |  | 2020-12-14 | 2020-12-14 | 2020-12-29 |  |  | 2020-12-23 | 2021-08-16 |  | CS | 2020-12-23 | RS | 2021-08-16 |  |  |  |  | CS |  |  | 2020-12-23 | 2021-08-16 |  | 2023-08-15 | 2023-12-14 | [10 empty] | 2023-08-23 | 2023-12-15 | [7 empty] | 2023-12-14 | [5 empty] | 2021-01-08 | 2021-08-19 |  | 2023-09-01 | 2023-12-22 | [7 empty] | 2021-03-16 | 2021-10-01 |  | 2021-06-22 | Report |  |  | 2021-06-22 | 2021-09-29 |  | 2023-10-17 | 2024-02-26 |  |  |  |  | 2021-06-22 | 2021-09-29 |  | 2023-10-17 | 2024-02-26 | [7 empty] | 2023-10-24 | [5 empty] | 2021-06-29 | 2021-10-04 |  | 2023-11-02 |  |  |  |  | 2021-06-29 |  |  | 2023-11-02 |  |  |  |  | 2021-11-08 |  | 2021-11-10 | [10 empty] | 167851 | 2024-03-07 |  | 2020-11-14: 2021-11-08; 2020-11-14: 2021-11-18; 2021-07-28: 2022-08-24; 2023-10-27: 2024-03-12; 2023-10-27: 2024-03-12 | [11 empty] | Q4 2025 |  |  |  | Requested | [11 empty] | TRUE | TRUE | 540 | 2021-11-08 | 2021-11-08 | 2021 | 2021 | 2021 |  |  |  | 2021-06-22 | Report
541 |  | Rigel Paradise | Rick Duperre | 2020-09-08 | [31 empty] | 3 - SAIP |  | 656D2 | 328 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN | 2022-06-27 | Santiago Quijano | Bluewave MA, LLC | BWC BAUNEG BEG POND LLC | SAM ALLEN RD SANFORD | 2000204736 | 30012952955 | Solar | [5 empty] | 43.3752 | -70.6858 | SAM ALLEN RD |  |  | Sanford | 3.3 | SANFORD INDUSTRIAL PARK | 656D2 | 656T1 |  | 9310-L0317-5170-0357-ED00006 | FERC | WITHDRAWN | WITHDRAWN | 250000 | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2020-09-22 | 2020-09-15 | 2020-09-22 | 2020-09-15 | 2020-09-22 | 2020-10-01 |  | 2020-10-16 |  | 2020-10-01 | 2020-10-07 | 2020-10-22 |  |  | 2020-10-06 |  |  | CS | 2020-10-06 | [6 empty] | CS |  |  | 2020-10-06 | [29 empty] | 2020-10-16 | [6 empty] | Pending |  |  |  |  | 2020-12-22 |  |  | 2021-05-20 | Addendum |  |  | 2020-12-22 | [8 empty] | 2020-12-29 | [17 empty] | 2021-01-11 | [5 empty] | 2021-01-07 |  | 2021-01-07 | [5 empty] | 2021-06-09 |  | 2021-01-11 |  | 2021-01-11 | [8 empty] | 1217828 |  |  |  | 2022-12-09 | 2020-11-14: 2021-07-01; 2020-11-14: 2021-07-01; 2021-07-28: 2021-07-01; 2021-07-28: 2021-07-01 | [15 empty] | 10300804592 | [11 empty] | TRUE | TRUE | 541 | 2021-07-01 | 2021-07-01 | 2021 | 2021 | 2021 | 44356 |  |  | 2021-05-20 | Addendum
542 |  | Govinda Neupane |  | 2020-09-10 | [31 empty] | 3 - EMDE |  | 868D1 | 523 |  | WITHDRAWN | WITHDRAWN |  | Nick Ford | Hexagon Energy LLC | RIVER RUNE SOLAR LLC | 154 FERRY ST SOLON | 2000180713 | 30012638398 | Solar | [5 empty] | 44.9404 | -69.8657 | 154 Ferry St |  |  | Solon |  | EMBDEN | 868D1 |  |  | 9310-L0452-5370-0013-ED00067 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2020-09-17 | 2020-09-24 |  |  |  |  | 1900-01-12 | [127 empty] | 2021-06-30 | [37 empty] | TRUE | TRUE | 542 | 0 | 0 | 1900 | #VALUE! | #VALUE!
543 |  | Rigel Paradise | Rick Duperre | 2020-09-11 | [31 empty] | 1 - YOBE |  | 676D2 |  |  | WITHDRAWN | WITHDRAWN |  | Dan Ryan | Turning Point Energy | TPE DEVELOPMENT LLC | AVON AVE YORK ME | 2000123236 | 30012639974 | Solar | [7 empty] | AVON AVE |  |  | York |  | YORK BEACH | 676D2 |  |  | 9310-L0352-6660-0005-ED00011 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2020-09-18 | 2020-09-25 |  |  |  |  | 1900-01-12 | [57 empty] | Pending | [69 empty] | 2021-05-05 | [25 empty] | STUDY | [11 empty] | TRUE | TRUE | 543 | 0 | 0 | 1900 | #VALUE! | #VALUE!
544 |  | Lanie Patterson | Brent Brooks | 2020-09-11 | [31 empty] | 7 - DETR |  | 812D2 | 532 |  | WITHDRAWN | WITHDRAWN |  | Rayo Bhumgara | Sustainable Strategies 2050 Inc | PITTSFIELD SOLAR II LLC | Orchard St | 2000179381 | 30012619976 | Solar | [7 empty] | Orchard St |  |  | Pittsfield |  | DETROIT | 812D2 |  |  | 9310-L0393-4650-0022-ED00011 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2020-09-18 | 2020-09-25 |  |  |  |  | 1900-01-12 | [127 empty] | 2020-12-03 | [25 empty] | NO STUDY | [11 empty] | TRUE | TRUE | 544 | 0 | 0 | 1900 | #VALUE! | #VALUE!
545 |  | Govinda Neupane |  | 2020-09-11 | 2022-05-31 |  |  | 2023-01-09 | wthdw | [26 empty] | 7 - DOVE |  | 815D1 | 512 |  | WITHDRAWN | WITHDRAWN |  | Tyler Adkins | UGE USA INC | UGE USA INC | 975 WEST MAIN ST DOVER-FOXCROFT | 2000142913 | 30012417058 | Solar | [5 empty] | 45.1854 | -69.2476 | 975 WEST MAIN ST |  |  | Dover-Foxcroft | 34.4 | DOVER | 815D1 | 815T1 |  | 9310-L0396-1650-0117-ED00053 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2020-09-25 | 2020-09-18 | 2020-09-25 | 2020-09-18 | 2020-09-25 | 2024-01-09 | 2023-01-15 | 2024-01-24 | [123 empty] | n/a | n/a | n/a | n/a | 2024-03-11 | [37 empty] | TRUE | TRUE | 545 | 0 | 0 | 1900 | #VALUE! | #VALUE!
546 |  |  | Anthony Boucher | 2020-09-15 | [31 empty] | 1 - CAMD |  | 214D4 |  |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Ryan Darlow | Norwich Solar Technologies | LINCOLNVILLE SOLAR 1 LLC | S Ridge Rd | 2000179369 | 30012619943 | Solar | [5 empty] | 44.2531 | -69.0303 | S Ridge Road |  |  | Lincolnville | 105 | CAMDEN | 214D4 | 214T1 |  | 9310-L0037-3300-0002-ED00010 | Non-FERC | WITHDRAWN | WITHDRAWN | NONE | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2020-09-29 | 2020-09-22 | 2020-09-29 | 2020-09-22 | 2020-09-29 | 2020-10-07 |  | 2020-10-22 |  | 2020-10-07 | 2020-10-07 | 2020-10-22 |  |  | 2020-10-22 |  |  | CS | 2020-10-22 | [6 empty] | CS |  |  | 2020-10-22 | [29 empty] | 2020-10-23 | [6 empty] | Pending |  |  |  |  | 2020-12-30 |  |  | 2021-05-10 | Addendum |  |  | 2020-12-30 | [8 empty] | 2020-12-31 | [17 empty] | 2021-01-07 | [5 empty] | 2021-01-07 |  | 2021-01-07 | [5 empty] | 2021-05-14 |  | 2021-05-14 |  | 2021-01-07 | [8 empty] | 240777 |  |  |  | 2023-06-14 | 2020-11-14: 2021-05-17; 2020-11-14: 2021-05-17; 2021-07-28: 2021-07-07; 2021-07-28: 2021-07-07 | [15 empty] | 10300784488 | [11 empty] | TRUE | TRUE | 546 | 2021-05-17 | 2021-05-17 | 2021 | 2021 | 2021 | 44330 |  |  | 2021-05-10 | Addendum
547 |  |  | KRISTOFER COLEMAN | 2020-09-17 | 2022-10-20 |  |  | 2022-12-30 | L2_Bump |  | 2023-02-15 | L2_Bump | [23 empty] | 5 - TP34 |  | 249D1 | 452 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | David Kane | Summit Ridge Energy | Topsham PV LLC | LOVERS LN TOPSHAM | 2000149310 | 30012535388 | Solar | [5 empty] | 43.9357 | -69.9298 | LOVERS LN |  |  | Topsham | 10.1 | TOPHAM OLD | 249D1 | 249T1 | 12.47 | 9310-L0087-5840-0015-ED00004 | Non-FERC | WITHDRAWN | WITHDRAWN | 325000 | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2020-10-01 | 2020-09-24 | 2020-10-01 | 2020-09-24 | 2020-10-01 | 2020-10-12 |  | 2020-10-26 |  | 2020-10-12 | 2020-10-15 | 2020-10-29 |  |  | 2020-10-16 |  |  | CS | 2020-10-16 | [6 empty] | CS |  |  | 2020-10-16 |  |  | 2022-10-24 | 2022-01-09 | 2023-02-17 | [11 empty] | 2023-02-17 | [12 empty] | 2020-10-22 | [6 empty] | Pending |  |  |  |  | 2020-12-29 |  |  | 2021-06-15 | Addendum |  |  | 2020-12-29 |  |  | 2022-12-08 | [5 empty] | 2021-01-08 | [17 empty] | 2021-01-11 | [13 empty] | 2021-06-17 |  |  |  |  | 2022-12-27 | [7 empty] | 1202778 |  |  |  | 2024-05-13 | 2020-11-14: 2021-07-09; 2020-11-14: 2021-07-09 | [15 empty] | Requested | [11 empty] | TRUE | TRUE | 547 | 2021-07-09 | 2021-07-09 | 2021 | 2021 | 2021 | 44364 |  |  | 2021-06-15 | Addendum
548 |  | Lanie Patterson | Brent Brooks | 2020-09-24 | [31 empty] | 4 - MCCO |  | 237D1 | 337 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Doug Lucas | Sunvest Solar Inc. | Vassalboro CSG 1 LLC | WEBBER POND RD, VASSALBORO | 2000183337 | 30012673528 | Solar | [5 empty] | 44.4308 | -69.6505 | WEBBER POND RD |  |  | Vassalboro | 7 | MCCOYS | 237D1 | 237T1 |  | 9310-L0067-6030-0060-ED00116 | Non-FERC | WITHDRAWN | WITHDRAWN | 325000 | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2020-10-09 | 2020-10-01 | 2020-10-08 | 2020-10-01 | 2020-10-09 | 2020-10-15 |  | 2020-10-29 |  | 2020-10-15 | 2020-10-16 | 2020-10-30 |  |  | 2020-10-28 |  |  | CS | 2020-10-28 | RS | [5 empty] | CS |  |  | 2020-10-28 | [29 empty] | 2020-11-04 | 2021-03-31 | [10 empty] | 2021-01-12 | 2021-05-13 | 2022-08-04 | 2021-07-20 | Report |  |  | 2021-02-05 | 2021-07-13 | [7 empty] | 2021-02-05 | 2021-07-12 | [16 empty] | 2021-02-22 | 2021-07-20 |  |  |  |  | 2021-02-22 |  | 2021-02-15 | 2021-07-20 | [6 empty] | 2021-08-05 |  | 2021-08-05 | [8 empty] | 606455 | 2021-01-19 | 978161 | 2021-07-02 | 2022-07-20 | 2020-11-14: 2021-09-01; 2020-11-14: 2021-09-01 | [15 empty] | Requested | [11 empty] | TRUE | TRUE | 548 | 2021-09-01 | 2021-09-01 | 2021 | 2021 | 2021 |  |  |  | 2021-07-20 | Report
549 |  | Lanie Patterson | Brent Brooks | 2020-09-24 | [31 empty] | 4 - SOWA |  | 855D2 | 360 |  | WITHDRAWN | WITHDRAWN |  | Sachin Patel | LastMile Energy | TRAFTON PROPERTIES LLC | 977 w river rd pvt undgrd | 2800326501 | 35015996925 | Solar | [7 empty] | 977 RIVER RD |  |  | Waterville |  | SOUTH WATERVILLE | 855D2 |  |  | 9310-L0435-6210-0262-ED00052 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2020-10-01 | 2020-10-08 |  |  |  |  | 1900-01-12 | [57 empty] | Study performed | [69 empty] | 2021-05-05 | [37 empty] | TRUE | TRUE | 549 | 0 | 0 | 1900 | #VALUE! | #VALUE!
550 |  | Rigel Paradise | Rick Duperre | 2020-09-28 | 2022-12-09 | wthdw | [29 empty] | 4 - SAIP |  | 656D2 | 541 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Simon Courtney | ME WHITE PINE SOLAR LLC | SOLAR PROVIDER GROUP LLC | 316 KENNEBUNK RD, SANFORD | 2000157464 | 30013923799 | Solar | [5 empty] | 43.4028 | -70.668 | 316 KENNEBUNK RD |  |  | Sanford | 36 | SANFORD INDUSTRIAL PARK | 656D2 | 656T1 | 12.47 | 9310-L0317-5170-0192-ED00043 | FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2020-10-14 | 2020-10-05 | 2020-10-13 | 2020-10-05 | 2020-10-14 | 2021-07-20 |  | 2021-08-03 |  | 2021-08-10 | 2021-08-10 | 2021-08-24 |  |  | 2021-08-23 |  |  | CS | 2021-08-24 | [6 empty] | CS |  |  | 2021-08-24 |  |  | 2022-12-13 | [8 empty] | 2021-08-25 |  |  | 2022-11-07 | [14 empty] | 2021-09-01 | [11 empty] | 2021-11-05 | [6 empty] | 2021-10-22 | [8 empty] | 2021-10-22 | [17 empty] | 2021-11-09 | [7 empty] | 2021-11-09 | [9 empty] | 2021-12-07 | [8 empty] | 500962 | 2021-10-21 |  |  | 2023-01-09 | 2020-11-14: 2021-12-08; 2020-11-14: 2021-12-10; 2021-07-28: 2022-06-03 | [15 empty] | Requested | [11 empty] | TRUE | TRUE | 550 | 2021-12-08 | 2021-12-08 | 2021 | 2021 | 2021
551 |  | Rigel Paradise | Rick Duperre | 2020-09-28 | 2023-10-13 | L2_Bump | [29 empty] | 6 - LEBA |  | 695D2 | 451 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Tom Kiggen | EDF Renewables | EDF RENEWABLES | 272 DEPOT RD LEBANON | 2000134214 | 30012607633 | Solar | [5 empty] | 43.4272 | -70.8799 | 272 DEPOT ROAD |  |  | Lebanon | 43 | LEBANON | 695D2 | 695T1 |  | 9310-L0473-3190-0063-ED00088 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2020-10-14 | 2020-10-05 | 2020-10-13 | 2020-10-05 | 2020-10-14 | 2021-06-21 |  | 2021-07-06 |  | 2021-08-18 | 2021-08-18 | 2021-09-01 |  |  | 2021-08-31 |  |  | CS | 2021-09-01 | [6 empty] | CS |  |  | 2021-09-01 | [29 empty] | 2021-09-16 | [11 empty] | 2021-11-22 | [6 empty] | 2021-11-23 | [8 empty] | 2021-11-28 | [44 empty] | 375727 |  |  |  | 2024-05-01 | 2020-11-14: 2021-12-21; 2020-11-14: 2021-12-30 | [15 empty] | Requested | [11 empty] | TRUE | TRUE | 551 | 2021-12-21 | 2021-12-21 | 2021 | 2021 | 2021
552 |  |  | Anthony Boucher | 2020-09-29 | [31 empty] | 2 - WARR |  | 253D1 | 220 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Nate Niles | REVISION ENERGY INC | REVISION ENERGY INC | 1011 North Pond Rd, Warren | 2800182538 | 30012681190 | Solar | [5 empty] | 44.1441 |  | 1011 North Pond Rd |  |  | Warren | 13 | WARREN | 253D1 | 253T1 |  | 9310-L0092-6160-0073-ED00005 | Non-FERC | WITHDRAWN | WITHDRAWN | 350000 | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2020-10-15 | 2020-10-06 | 2020-10-14 | 2020-10-06 | 2020-10-15 | 2020-10-23 |  | 2020-11-06 |  | 2020-10-23 | 2020-10-23 | 2020-11-06 |  |  | 2020-11-04 |  |  | CS | 2020-11-04 | [6 empty] | CS |  |  | 2020-11-04 | [29 empty] | 2020-11-23 | [6 empty] | yes |  |  |  |  | 2021-02-01 |  |  | 2021-05-04 | Addendum |  |  | 2021-02-01 | [8 empty] | 2021-02-02 | [17 empty] | 2021-02-09 | [7 empty] | 2021-02-09 | [5 empty] | 2021-05-06 | [12 empty] | 1751615 |  |  |  | 2022-04-05 | 2020-11-14: 2021-06-30; 2020-11-14: 2021-06-30; 2021-07-28: 2021-06-30; 2021-07-28: 2021-06-30 | [15 empty] | 10300803147 | [11 empty] | TRUE | TRUE | 552 | 2021-06-30 | 2021-06-30 | 2021 | 2021 | 2021 | 44322 |  |  | 2021-05-04 | Addendum
553 |  | Govinda Neupane |  | 2020-09-29 | [31 empty] | 5 - CARM |  | 808D2 | 274 |  | WITHDRAWN | WITHDRAWN |  | Jacob Fraatz | Dimension Renewable Energy | DIMENSION ME 1 LLC | 31 PERRY LN CARMEL ME | 2000123007 | 30011951487 | Solar | [5 empty] | 44.8059 |  | 31 PERRY LN |  |  | Carmel |  | CARMEL | 808D2 | 808T1 |  | 9310-L0389-1020-0049-ED00205 | Non-FERC | WITHDRAWN | WITHDRAWN | [7 empty] | 2020-10-15 | 2020-10-06 | 2020-10-14 | 2020-10-06 | 2020-10-15 |  |  | 1900-01-12 | [57 empty] | No Study | [69 empty] | 2022-06-01 | [37 empty] | TRUE | TRUE | 553 | 0 | 0 | 1900 | #VALUE! | #VALUE!
554 |  | Ben Brooks | KRISTOFER COLEMAN | 2020-09-30 | 2023-02-15 | L2_Bump | [29 empty] | 1 - FREE |  | 225D4 |  | Yes | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Paula Fitzgerald | Novel Energy Solutions LLC | RTE 1 Freeport Solar LLC | Route 1 | 2000174932 | 30015182808 | Solar | [5 empty] | 43.8344 | -70.1277 | Route 1 |  |  | Freeport | 89 | FREEPORT | 225D4 | 225T1 |  | 9310-L0056-2110-0214-ED00191. | Non-FERC | WITHDRAWN | WITHDRAWN | NONE | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2020-10-16 | 2020-10-07 | 2020-10-15 | 2020-10-07 | 2020-10-16 | 2020-10-20 |  | 2020-11-03 |  | 2020-10-20 | 2020-10-22 | 2020-11-05 |  |  | 2020-11-04 |  |  | CS | 2020-11-04 | [6 empty] | CS |  |  | 2020-11-04 |  |  | 2024-01-31 | [11 empty] | 2024-02-05 | [8 empty] | 2024-02-13 | [5 empty] | 2020-11-06 |  |  | 2024-02-13 | [8 empty] | 2021-01-14 |  |  | 2021-05-04 | Addendum |  |  | 2021-01-14 |  |  | 2024-04-17 | [5 empty] | 2021-01-15 |  |  | 2024-04-18 | [8 empty] | 2024-05-03 | [5 empty] | 2021-01-20 |  |  | 2024-05-09 | [7 empty] | 2024-05-09 |  |  |  | 2021-05-21 | 2021-01-25 | 2021-05-04 | 2021-01-25 |  |  |  | 2025-06-10 | 2025-06-10 |  |  |  | 345444 |  | 110986 | 2024-04-17 | 2025-09-30 | 2020-11-14: 2021-05-05; 2020-11-14: 2021-05-05; 2021-07-28: 2021-09-28; 2021-07-28: 2021-09-30 | 2025-07-08 | 2025-07-08 | [9 empty] | Q2 2021 |  |  |  | 10300781036 | [11 empty] | TRUE | TRUE | 554 | 2021-05-05 | 2021-05-05 | 2021 | 2021 | 2021 |  | 44337 | 44320 | 2021-05-04 | Addendum
555 |  | Lanie Patterson | Anthony Boucher | 2020-09-30 | 2022-05-17 |  |  | 2022-09-28 | L2_Bump |  | 2023-03-20 | L2_Bump |  | 2023-09-06 | L2_Bump |  | 2024-01-18 | L2_Bump | [17 empty] | 3 - PAST | 1 - PAST | 239D7 | 488 | Yes | EXECUTED | EXECUTED |  | Paula Fitzgerald | Novel Energy Solutions LLC | 200 New County Rd 2 Solar LLC | 200 New County Rd Thomaston | 2000174932 | 30015683300 | Solar | 999 | 0.999 | 7492 |  |  | 44.955 | -69.1354 | 200 New County Rd |  |  | Thomaston | 10 | PARK STREET | 239D7 | 239T2 |  | 9310-L0495-5790-0004-ED00007 | Non-FERC | NOT IMPACTED | NOT IMPACTED |  | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2020-10-16 | 2020-10-07 | 2020-10-15 | 2020-10-07 | 2020-10-16 | 2021-06-15 |  | 2021-06-30 |  | 2021-06-24 | 2021-06-24 | 2021-07-08 |  |  | 2021-07-08 |  |  | CS | 2021-07-09 | [6 empty] | CS |  |  | 2021-07-09 |  |  | 2022-12-19 |  | 2023-09-14 | 2024-01-22 | [5 empty] | 2021-07-06 | [5 empty] | 2024-02-04 | [6 empty] | 2023-05-30 | 2023-11-01 | 2024-02-08 |  |  | 2021-07-15 |  |  | 2023-01-06 | 2023-05-30 | 2023-11-01 | 2024-02-08 | [5 empty] | 2021-09-17 | [6 empty] | 2021-09-21 |  |  | 2023-02-15 | 2023-07-10 | 2023-12-22 | 2024-04-16 |  |  | 2021-09-21 |  |  | 2023-02-21 | 2023-07-11 | 2023-12-22 | 2024-04-17 | [8 empty] | 2024-04-17 |  |  | 2021-09-23 | [7 empty] | 2021-09-23 | [7 empty] | 2021-10-19 |  |  | 2023-02-22 |  | 2023-02-22 | [5 empty] | 242248 |  | 342807 | 2023-12-18 |  | 2021-10-26 | 2021-10-27 | 2023-02-27 | 2023-02-28 | 2024-06-12 | 2024-06-12 | [15 empty] | Q1 2026 |  |  |  | Requested | [11 empty] | TRUE | TRUE | 555 | 2021-10-26 | 2021-10-26 | 2021 | 2021 | 2021
556 |  | Govinda Neupane |  | 2020-10-01 | 2022-07-19 | L2_Bump |  | 2023-12-15 | wthdw | [26 empty] | 8 - WSTN |  | 866D2 | 484 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Haley Orvedal | Engie | Hinckley PV I, LLC | Middle Rd Skowhegan | 2000184852 | 30012693393 | Solar | [5 empty] | 44.7447 | -69.6928 | Middle Rd |  |  | Skowhegan | 25 | WESTON HYDRO | 866D2 | 866T2 |  | 9310-L0451-5330-0112-ED00068 | Non-FERC | WITHDRAWN | WITHDRAWN | NONE | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2020-10-19 | 2020-10-08 | 2020-10-16 | 2020-10-09 | 2020-10-19 | 2021-03-01 |  | 2021-03-15 |  | 2021-03-15 | 2021-03-15 | 2021-03-29 |  |  | 2021-04-02 | 2021-08-16 |  | CS | 2021-04-02 | RS | 2021-08-16 |  |  |  |  | CS |  |  | 2021-04-02 | 2021-08-16 |  | 2022-12-27 | [11 empty] | 2023-01-09 | [8 empty] | 2023-01-16 | [5 empty] | 2021-04-16 | 2021-09-10 |  | 2023-01-17 | [8 empty] | 2021-06-21 | 2021-10-25 |  | 2021-07-12 | Report |  |  | 2021-07-12 | 2021-10-22 |  | 2023-02-28 | [5 empty] | 2021-07-12 | 2021-10-22 |  | 2023-02-28 | [8 empty] | 2023-03-06 | [5 empty] | 2021-07-22 | 2021-11-01 |  | 2023-03-10 |  |  |  |  | 2021-07-22 | 2021-11-01 | [6 empty] | 2021-11-24 |  | 2021-11-24 | 2023-03-29 |  | 2023-03-30 | [5 empty] | 8861803 | 2021-07-12 | 703508 | 2023-03-27 | 2024-02-02 | 2020-11-14: 2021-11-24; 2020-11-14: 2021-12-28; 2021-07-28: 2023-03-31; 2021-07-28: 2023-03-31 | [15 empty] | Requested | [11 empty] | TRUE | TRUE | 556 | 2021-11-24 | 2021-11-24 | 2021 | 2021 | 2021 |  |  |  | 2021-07-12 | Report
557 |  |  | Anthony Boucher | 2020-10-01 | [31 empty] | 3 - MERO |  | 270D2 | 256 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Shyam Sunder | HODSON INC | HODSON ROCKPORT SOLAR PROJECT LLC | 00 Mt Pleasent St Rockport | 2000183292 | 30012672710 | Solar | [5 empty] | 44.1959 | -69.1839 | 00 MT PLEASANT ST |  |  | Rockport | 39 | MEADOW ROAD | 270D2 | 270T2 |  | FLOC-MISSING-01142021 | Non-FERC | WITHDRAWN | WITHDRAWN | NONE | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2020-10-19 | 2020-10-08 | 2020-10-16 | 2020-10-09 | 2020-10-19 | 2020-10-28 |  | 2020-11-12 |  | 2020-10-28 | 2020-10-30 | 2020-11-13 | [5 empty] | FS | 2020-12-02 | IS | 2021-01-22 |  |  |  |  | Split | 2020-12-02 | 2021-01-22 | [28 empty] | 2020-11-30 | 2021-02-04 | [10 empty] | 2021-01-06 | 2021-03-19 |  |  |  | 2021-06-24 | Report | 2021-01-06 | 2021-06-24 | [7 empty] | 2021-01-06 | 2021-06-24 | [16 empty] | 2021-01-12 | 2021-06-29 | [6 empty] | 2021-01-12 | 2021-06-29 | [8 empty] | 2021-07-27 |  | 2021-07-27 | [8 empty] | 559769 |  |  |  | 2023-03-09 | 2020-11-14: 2021-08-02; 2020-11-14: 2021-08-02 | [15 empty] | Requested | [11 empty] | TRUE | TRUE | 557 | 2021-08-02 | 2021-08-02 | 2021 | 2021 | 2021 |  |  |  | 2021-06-24 | Report
558 |  |  | KRISTOFER COLEMAN | 2020-10-05 | 2023-04-05 | L2_Bump | [29 empty] | 2 - LSFA |  | 232D1 | 215 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Simon Courtney | SOLAR PROVIDER GROUP LLC | SOLAR PROVIDER GROUP LLC | 11 FORBES RD / LISBON | 2000157464 | 30012693252 | Solar | [5 empty] | 44.0128 | -70.0523 | 11 FORBES RD |  |  | Lisbon | 56.4 | LISBON FALLS | 232D1 | 232T1 |  | 9310-L0061-3310-0091-ED00068. | Non-FERC | WITHDRAWN | WITHDRAWN | NONE | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2020-10-20 | 2020-10-13 | 2020-10-20 | 2020-10-13 | 2020-10-20 | 2020-11-11 |  | 2020-11-25 |  | 2020-11-11 | 2020-11-12 | 2020-11-30 |  |  | 2020-11-24 |  |  | CS | 2020-11-24 | [6 empty] | CS |  |  | 2020-11-24 | [29 empty] | 2020-11-30 | [11 empty] | 2021-02-04 |  |  | 2021-06-10 | Addendum |  |  | 2021-02-04 | [8 empty] | 2021-02-08 | [17 empty] | 2021-02-16 | [7 empty] | 2021-02-16 | [7 empty] | 2021-02-16 |  |  | 2023-02-27 | [7 empty] | 524314 |  | 661447 | 2023-03-23 | 2023-04-10 | 2020-11-14: 2021-06-29; 2020-11-14: 2021-06-29; 2021-07-28: 2022-07-05 | [15 empty] | 10300802402 | [11 empty] | TRUE | TRUE | 558 | 2021-06-29 | 2021-06-29 | 2021 | 2021 | 2021 |  |  |  | 2021-06-10 | Addendum
559 |  | Lanie Patterson | Brent Brooks | 2020-10-06 | [31 empty] | 4 - CONY |  | 216D2 | 479 |  | WITHDRAWN | WITHDRAWN |  | Ben Vanderlan | Bluewave MA, LLC | BLUE WAVE PROJECT DEVOLPMENT LLC | 0 BEECH STREET CHELSEA ME 04330 | 2000183318 |  | Solar | [7 empty] | 0 Beech St |  |  | Chelsea |  | CONY ROAD | 216D2 | 216T1 |  | 9310-L0044-1110-0051-ED00123 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2020-10-14 | 2020-10-21 |  |  |  |  | 1900-01-12 | [57 empty] | No Study | [65 empty] | n/a |  |  |  | 2020-12-08 | [37 empty] | TRUE | TRUE | 559 | 0 | 0 | 1900 | #VALUE! | #VALUE!
560 |  | Eben Snow | Brent Brooks | 2020-10-06 | 2024-04-17 | wthdw | [29 empty] | 5 - R115 |  | 445D1 | 497 | Yes | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Santiago Quijano | Bluewave MA, LLC | BWC Lake Floria, LLC | 0 DAMON RD RAYMOND ME 04071 | 2000210133 | 30013021495 | Solar | [5 empty] | 43.9397 | -70.4507 | 0 Damon Rd |  |  | Raymond | 133 | RAYMOND 115 KV | 445D1 | 445T1 | 12.47 | 9310-L0184-4900-0105-ED00058. | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2020-10-21 | 2020-10-14 | 2020-10-21 | 2020-10-14 | 2020-10-21 | 2021-01-26 |  | 2021-02-09 |  | 2021-01-26 | 2021-01-26 | 2021-02-09 |  |  | 2021-02-03 |  |  | CS | 2021-02-03 | [6 empty] | CS |  |  | 2021-02-03 |  |  | 2024-04-19 | 2024-05-14 | [7 empty] | 2021-02-03 |  |  | 2024-05-03 | N/A | [7 empty] | 2023-05-03 | 2024-05-15 |  |  |  |  | 2021-02-08 |  |  | 2023-05-03 | 2024-05-15 | [7 empty] | 2021-04-13 |  |  | 2021-06-29 | Report |  |  | 2021-06-29 |  |  |  | 2024-07-19 |  |  |  |  | 2021-06-29 |  |  |  | 2024-07-22 | [8 empty] | 2024-07-24 |  |  |  |  | 2021-07-01 |  |  |  | 2024-07-26 |  |  |  | 2021-07-01 |  |  |  | 2024-07-26 | [6 empty] | 2024-07-31 |  | 2024-08-02 | 2024-11-21 |  |  |  |  | 691313 |  | 508968 | 2024-07-19 | 2025-11-25 | 2020-11-14: 2021-07-01; 2020-11-14: 2021-07-01; 2021-07-28: 2024-08-07; 2021-07-28: 2024-08-07 | [11 empty] | Q4 2025 |  |  |  | 10300803648 | [11 empty] | TRUE | TRUE | 560 | 2021-07-01 | 2021-07-01 | 2021 | 2021 | 2021 |  |  |  | 2021-06-29 | Report
561 |  |  |  | 2020-10-13 | 2023-03-29 | L2_Bump | [28 empty] | 478 | 3 - AGK5 |  | 200D2 | 478 | Yes | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED |  | Rocky Ackroyd | Green Sun LLC | NEW GEN VENTURES | LAJOIE ST AUGUSTA | 2800555735 | 30012681331 | Solar | 1900 | 1.9 | 2326 |  |  | 44.3435 | -69.7537 | LAJOIE ST |  |  | Augusta | 86 | AUGUSTA K5 | 200D2 | 200T1 | 12.47 | 9310-L0014-0240-0203-ED00002 | Non-FERC | TRIGGERING | TRIGGERING | 375000 | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2020-10-27 | 2020-10-20 | 2020-10-27 | 2020-11-08 | 2020-10-27 | 2020-11-04 |  | 2020-11-19 |  | 2020-11-04 | 2020-11-04 | 2020-11-18 |  |  | 2020-11-18 |  |  | CS | 2020-12-07 | [6 empty] | CS |  |  | 2020-12-07 |  |  | 2023-04-28 | [20 empty] | 2023-08-14 | [5 empty] | 2020-12-14 |  |  | 2023-08-14 | [8 empty] | 2021-02-19 |  |  | 2021-06-08 | Addendum |  |  | 2021-02-19 |  |  | 2023-09-28 | [5 empty] | 2021-02-22 |  |  | 2023-09-29 | [8 empty] | 2023-10-16 | [5 empty] | 2021-03-02 |  |  | 2023-10-17 |  |  |  |  | 2021-03-02 |  |  | 2023-10-17 | [7 empty] | 2023-11-03 | 2022-09-21 | 2023-11-04 | [5 empty] | 444395 |  | 573076 | 2023-10-25 |  | 2021-07-13 | 2021-07-13 | 2021-07-13 | 2021-07-13 | 2022-09-22 | 2022-09-22 | 2023-11-07 | 2023-11-14 | [13 empty] | Q2 2025 |  |  |  | Requested | [11 empty] | TRUE | TRUE | 561 | 2021-07-13 | 2021-07-13 | 2021 | 2021 | 2021 |  |  |  | 2021-06-08 | Addendum
562 |  |  | KRISTOFER COLEMAN | 2020-10-15 | 2024-10-18 | wthdw | [29 empty] | 2 - LISB |  | 231D1 | 198 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Kelsey Haley | New Leaf Energy, Inc | 510 PV PROJECT DEVELOPMENT LLC | 101 Frost Hill Ave Lisbon | 2000113260 | 30012454028 | Solar/Battery | [5 empty] | 44.0126 | -70.0239 | 101 Frost Hill Ave |  |  | Lisbon | 71 | LISBON | 231D1 | 231T1 |  | 9310-L0061-3310-0080-ED00295 | Non-FERC | WITHDRAWN | WITHDRAWN | 325000 | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2020-10-29 | 2020-10-22 | 2020-10-29 | 2020-11-08 | 2020-10-29 | 2020-11-03 |  | 2020-11-18 |  | 2020-11-03 | 2020-11-03 | 2020-11-17 |  |  | 2020-11-09 | 2021-08-17 |  | CS | 2020-11-09 | RS | 2021-08-17 |  |  |  |  | CS |  |  | 2020-11-09 | 2021-08-17 |  | 2024-10-22 | [26 empty] | 2020-11-12 | 2021-08-23 | [10 empty] | 2021-01-21 | 2021-10-05 |  | 2021-05-06 | Addendum |  |  | 2021-01-21 | [8 empty] | 2021-01-21 | 2021-10-05 | [16 empty] | 2021-01-27 | [7 empty] | 2021-01-27 | [5 empty] | 2021-05-12 |  | 2021-06-04 |  | 2021-06-04 | 2022-08-16 |  |  | 2023-07-18 | 2023-07-18 |  |  |  | 538295 |  | 426031 | 2023-01-03 | 2024-10-31 | 2021-07-13: 2021-10-14; 2021-07-13: 2021-10-18 | [17 empty] | Requested | [11 empty] | TRUE | TRUE | 562 | 2021-10-14 | 2021-10-14 | 2021 | 2021 | 2021 | 44328 |  |  | 2021-05-06 | Addendum
563 |  | Govinda Neupane |  | 2020-10-15 | [31 empty] | 5 - HART |  | 824D1 | 323 |  | WITHDRAWN | WITHDRAWN |  | Robert Snow | BORREGO SOLAR SYSTEMS INC | 510 PV PROJECT DEVELOPMENT LLC | HARTLAND RD SOLAR HARTLAND | 2000113260 | 30012621394 | Solar | [7 empty] | HARTLAND RD |  |  | Hartland |  | HARTLAND | 824D1 |  |  | 9310-L0409-2540-0004-ED00045 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2020-10-22 | 2020-10-29 |  |  |  |  | 1900-01-12 | [57 empty] | No Study | [69 empty] | 2020-12-11 | [37 empty] | TRUE | TRUE | 563 | 0 | 0 | 1900 | #VALUE! | #VALUE!
564 |  | Lanie Patterson | Brent Brooks | 2020-10-15 | 2023-11-28 | wthdw | [29 empty] | 5 - COMR |  | 230D1 | 363 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Kelsey Haley | New Leaf Energy, Inc | 510 PV PROJECT DEVELOPMENT LLC | 0 Griffin Rd Windsor | 2000113260 | 30012679269 | Solar/Battery | [5 empty] | 44.2688 | -69.5686 | 0 Griffin Rd |  |  | Windsor | 31/49 | COOPERS MILLS ROAD | 230D2 | 230T2 |  | 9310-L0474-6400-0001-ED00035 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2020-10-29 | 2020-10-22 | 2020-10-29 | 2020-10-23 | 2020-10-28 | 2021-12-21 | 2021-12-22 | 2022-01-06 | 2022-01-05 | 2022-01-05 | 2022-01-05 | 2022-01-20 |  |  | 2022-01-17 |  |  | CS | 2022-01-18 | [6 empty] | CS |  |  | 2022-01-18 |  |  |  | 2022-01-31 |  |  |  | 2022-01-31 |  |  |  | 2022-01-25 | [7 empty] | 2022-01-31 | 2022-01-31 | [8 empty] | 2022-02-01 | [11 empty] | 2022-04-06 | [6 empty] | 2022-03-25 | [8 empty] | 2022-03-25 | [8 empty] | 2022-03-28 | [8 empty] | 2022-04-04 | [7 empty] | 2022-04-04 | [7 empty] | 2022-04-27 |  | 2022-04-27 | 2023-03-27 | 2022-05-20 | 2023-04-13 | [5 empty] | 342978 | 2022-03-24 | 310050 | 2023-03-23 | 2023-12-04 | 2021-07-13: 2022-05-23; 2021-07-13: 2022-05-23; 2021-07-13: 2023-04-17; 2021-07-13: 2023-04-17 | [17 empty] | Requested | [11 empty] | TRUE | TRUE | 564 | 2022-05-23 | 2022-05-23 | 2022 | 2022 | 2022 |  |  |  |  | 2022-04-04
565 |  | Marshall Ripley | Rick Duperre | 2020-10-15 | 2023-10-19 | wthdw | [29 empty] | 4 - SWRD |  | 682D1 | 464 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Simon Courtney | SOLAR PROVIDER GROUP LLC | SOLAR PROVIDER GROUP LLC | 9 Webb Rd Windham |  | 30013874059 | Solar | [5 empty] | 43.7538 | -70.4083 | 9 Webb Rd |  |  | Windham | 9 | SWETT ROAD | 682D1 | 682T1 |  | 9310-L0251-6390-0121-ED00068 | Non-FERC | WITHDRAWN | WITHDRAWN | 325000 | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2020-10-29 | 2020-10-22 | 2020-10-29 | 2020-11-08 | 2020-10-28 | 2020-11-24 |  | 2020-12-10 |  | 2020-11-24 | 2020-11-24 | 2020-12-10 |  |  | 2020-12-07 | 2021-08-16 |  | CS | 2020-12-07 | RS | 2021-08-16 |  |  |  |  | CS |  |  | 2020-12-07 | 2021-08-16 | [28 empty] | 2020-12-18 | 2021-08-23 | [10 empty] | 2021-02-25 | 2021-10-05 |  | 2021-06-11 | Report |  |  | 2021-06-11 | 2021-10-05 | [7 empty] | 2021-06-11 | 2021-10-05 | [16 empty] | 2021-07-22 | [7 empty] | 2021-07-22 | [7 empty] | 2021-11-11 |  | 2021-11-11 | 2022-06-14 | [7 empty] | 685836 | 2021-09-22 |  |  | 2024-01-23 | 2021-11-11 | 2021-12-10 | 2022-01-12 | 2022-01-17 |  | 2022-06-14 | [19 empty] | Requested | [11 empty] | TRUE | TRUE | 565 | 2021-11-11 | 2021-11-11 | 2021 | 2021 | 2021 |  |  |  | 2021-06-11 | Report
566 |  |  |  | 2020-10-15 | 2023-08-14 | L2_Bump | [29 empty] | 1 - LULA |  | 461D1 | 540 | Yes | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2021-07-15 | Tyler William Perkins | Nexamp, Inc | Dixfield Solar LLC | 528 Wilton Rd Dixfield | 2000236406 | 30013382939 | Solar/Battery | 2500 | 2.5 | 3043 |  | 2000 | 44.5177 | -70.4127 | 528 Wilton Rd Dixfield |  |  | Dixfield | 504 | LUDDEN LANE | 461D1 | 461T3 |  | 9310-L0205-1620-0017-ED00217 | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2020-10-29 | 2020-10-22 | 2020-10-29 | 2020-11-08 | 2020-10-29 | 2020-11-11 |  | 2020-11-25 |  | 2020-11-11 | 2020-11-13 | 2020-12-01 |  |  | 2020-11-14 |  |  | CS | 2020-11-14 | [6 empty] | CS |  |  | 2020-11-14 | [29 empty] | 2020-11-23 | [11 empty] | 2021-02-01 |  |  | 2021-05-21 | Addendum |  |  | 2020-02-01 | [8 empty] | 2021-02-05 | [17 empty] | 2021-02-08 | [7 empty] | 2021-02-08 | [5 empty] | 2021-06-02 |  | 2021-02-11 | 2021-07-26 | 2021-02-11 | [8 empty] | 185974 |  |  |  |  | 2021-07-13: 2021-03-01; 2021-07-13: 2021-03-01; 2021-07-13: 2021-07-08; 2021-07-13: 2021-07-08 | [13 empty] | Q4 2021 |  |  |  | 10300760148 | [11 empty] | TRUE | TRUE | 566 | 2021-03-01 | 2021-03-01 | 2021 | 2021 | 2021 | 44349
567 |  | Rigel Paradise | Rick Duperre | 2020-10-19 | [31 empty] | 3 - HIST |  | 626D5 | 466 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN | 2022-06-27 | Ben Ransom | RENESOLA POWER HOLDINGS | RENESOLA POWER HOLDINGS | MT HOPE RD SANFORD | 2000149581 | 30012670912 | Solar | [5 empty] | 43.4196 | -70.7848 | MT HOPE RD |  |  | Sanford | 10H | HIGH STREET | 626D5 | 626T2 |  | 9310-L0253-5170-0241-ED00005 | Non-FERC | WITHDRAWN | WITHDRAWN | 325000 | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2020-11-02 | 2020-10-26 | 2020-11-02 | 2020-11-08 | 2020-11-02 | 2020-11-11 |  | 2020-11-25 |  | 2020-11-11 | 2020-11-12 | 2020-11-30 |  |  | 2020-11-16 | 2021-08-16 |  | CS | 2020-11-16 | RS | 2021-08-16 |  |  |  |  | CS |  |  | 2020-11-16 | 2021-08-16 | [28 empty] | 2020-11-23 | 2021-08-19 | [10 empty] | 2021-02-01 | 2021-10-01 |  | 2021-05-20 | Addendum |  |  | 2021-02-01 | 2021-09-20 | [7 empty] | 2021-02-03 | 2021-09-20 | [16 empty] | 2021-02-10 | 2021-09-22 | [6 empty] | 2021-02-10 | 2021-09-22 |  |  |  |  | 2021-06-04 |  |  |  | 2021-09-23 | 2022-11-01 |  | 2022-12-02 | 2023-08-02 | 2023-08-02 |  |  |  | 729612 |  | 528006 | 2022-10-31 | 2024-02-13 | 2021-07-13: 2021-09-23; 2021-07-13: 2021-09-30; 2021-07-13: 2022-12-05; 2021-07-13: 2022-12-07 |  |  | 2023-08-23 | 2023-08-23 | [13 empty] | Requested | [11 empty] | TRUE | TRUE | 567 | 2021-09-23 | 2021-09-23 | 2021 | 2021 | 2021 | 44351 |  |  | 2021-05-21 | Addendum
568 |  | Rigel Paradise | Rick Duperre | 2020-10-19 | [31 empty] | 2 - SOBE |  | 663D2 | 457 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN | 2022-06-27 | Andrew Kellar | NEW ENGLAND SOLAR GARDEN CORP | NESG SCF MAINE 1 HOLDCO LLC | 6 Punnkintown Rd So Berwick | 2000148487 | 30012743891 | Solar | [5 empty] | 43.1983 | -70.7912 | 6 Punnkintown Rd |  |  | South Berwick | 4.1 | SOUTH BERWICK | 663D2 | 663T1 |  | 9310-L0332-5410-0042-ED00011 | FERC | WITHDRAWN | WITHDRAWN | NONE | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2020-11-02 | 2020-10-26 | 2020-11-02 | 2020-11-08 | 2020-11-02 | 2020-11-05 |  | 2020-11-20 |  | 2020-11-05 | 2020-11-05 | 2020-11-19 |  |  | 2020-11-04 | 2021-08-16 |  | CS | 2020-11-04 | RS | 2021-08-16 |  |  |  |  | CS |  |  | 2020-11-04 | 2021-08-16 | [28 empty] | 2021-01-07 | 2021-09-02 | [10 empty] | 2021-03-15 | 2021-10-18 |  | 2021-06-22 | Report |  |  | 2021-06-22 | 2021-10-12 | [7 empty] | 2021-06-22 | 2021-10-13 | [16 empty] | 2021-06-28 | 2021-10-18 | [6 empty] | 2021-06-28 | 2021-10-18 | [6 empty] | 2021-10-18 |  | 2021-10-18 | [8 empty] | 240252 |  |  |  | 2022-10-20 | 2021-07-13: 2021-10-22; 2021-07-13: 2021-10-22; 2021-07-13: 2022-08-04 | [17 empty] | Requested | [11 empty] | TRUE | TRUE | 568 | 2021-10-22 | 2021-10-22 | 2021 | 2021 | 2021 |  |  |  | 2021-05-20 | Addendum
569 |  | Eben Snow | Brent Brooks | 2020-10-19 | [31 empty] | 6 - GRAY |  | 416D1 | 443 |  | WITHDRAWN | WITHDRAWN |  | Christian L'Oranger | Fogler LLC | FOLGER LLC - Pownal | 0 fickett allen rd pownal | 2000144160 | 30012266844 | Solar | [7 empty] | 0 Fickett Allen Rd |  |  | Pownal |  | GRAY | 416D1 |  |  | FLOC-MISSING-01142021 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2020-10-26 | 2020-11-02 |  |  |  |  | 1900-01-12 | [123 empty] | n/a | n/a | n/a | n/a | 2020-02-23 | [37 empty] | TRUE | TRUE | 569 | 0 | 0 | 1900 | #VALUE! | #VALUE! |  |  |  | 2021-06-22 | Report
570 |  | Govinda Neupane |  | 2020-10-21 | 2022-07-28 |  |  | 2023-03-06 | L2_Bump | [26 empty] | 2 - PHST |  | 841D1 | 264 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Daniel Serber | NEXTGRID INC | NEXTGRID INC | 25 STRONG ROAD / STRONG ME 04983 | 2000104936 | 30012481666 | Solar | [5 empty] | 44.8007 | -70.2154 | 25 STRONG RD |  |  | Strong | 2 | PHILLIPS/STRONG | 841D1 | 841T1 | 12.47 | 9310-L0424-5580-0030-ED00004 | Non-FERC | WITHDRAWN | WITHDRAWN | 325000 | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2020-11-04 | 2020-10-28 | 2020-11-04 | 2020-11-08 | 2020-11-04 | 2020-11-11 |  | 2020-11-25 |  | 2020-11-11 | 2020-11-12 | 2020-11-30 |  |  | 2020-11-30 | 2021-08-16 |  | CS | 2020-12-07 | RS | 2021-08-16 |  |  |  |  | CS |  |  | 2020-12-07 | 2021-08-16 |  | 2022-07-29 | 2023-03-13 | [10 empty] | 2022-08-10 |  | 2023-08-10 | [7 empty] | 2023-05-09 | 2023-08-01 |  |  |  | 2020-12-18 | 2021-08-25 |  | 2022-08-23 | 2023-05-09 | 2023-08-11 | [6 empty] | 2021-02-25 | 2021-10-07 |  | 2021-06-22 | Report |  |  | 2021-06-22 | 2021-10-06 |  | 2022-10-04 | 2023-06-21 | 2023-09-25 |  |  |  | 2021-06-22 | 2021-10-06 |  |  |  | 2023-09-26 | [7 empty] | 2023-06-29 |  |  |  |  | 2021-06-29 | 2021-11-22 |  |  |  | 2023-09-29 |  |  | 2021-06-29 | 2021-11-22 |  |  |  | 2023-09-29 |  |  | 2021-11-22 |  | 2021-11-24 | 2022-11-03 | 2021-11-24 | 2022-11-04 | [5 empty] | 39353 | 2021-09-23 | 3120486 | 2023-09-25 | 2024-01-09 | 2021-07-13: 2021-11-24; 2021-07-13: 2021-11-29; 2021-07-13: 2022-11-04; 2021-07-13: 2022-11-08 | [17 empty] | Requested | [11 empty] | TRUE | TRUE | 570 | 2021-11-24 | 2021-11-24 | 2021 | 2021 | 2021
571 |  | Govinda Neupane |  | 2020-10-21 | [31 empty] | 3 - PHST |  | 841D1 | 570 |  | WITHDRAWN | WITHDRAWN |  | Daniel Serber | NEXTGRID INC | NEXTGRID INC | 251 STRONG ROAD / STRONG ME 049 | 2000104939 | 30012481674 | Solar | [5 empty] | 44.7949 | -70.2172 | 251 STRONG RD |  |  | Strong |  | PHILLIPS/STRONG | 841D1 |  |  | 9310-L0424-5580-0030-ED00096 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2020-10-28 | 2020-11-04 | 2020-10-28 | 2020-11-04 |  |  | 1900-01-12 | [127 empty] | 2022-01-20 | [25 empty] | NO STUDY | [11 empty] | TRUE | TRUE | 571 | 0 | 0 | 1900 | 1900 | 1900 |  |  |  | 2021-06-22 | Report
572 |  | Govinda Neupane |  | 2020-10-29 | 2023-05-22 | L2_Bump | [29 empty] | 5 - MONS |  | 834D1 | 539 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Nick Mazuroski | Dirigo/BNRG | BD SOLAR MONSON LLC | Water St, Monson | 2000188871 | 30012748478 | Solar | [5 empty] | 45.2384 | -69.4886 | Water St, Monson |  |  | Monson | 513.3 | MONSON | 834D1 | 834T1 | 12.47 | 9310-L0414-3760-0042-ED00023 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2020-11-13 | 2020-11-05 | 2020-11-13 | 2020-11-08 | 2020-11-13 | 2022-06-17 | 2022-07-28 | 2022-07-05 | 2022-08-03 | 2022-08-03 | 2022-08-03 | 2022-08-17 |  |  | 2022-08-17 |  |  | CS | 2022-08-17 | [6 empty] | CS |  |  | 2022-08-18 | 2022-12-19 | [10 empty] | 2022-08-30 | 2022-12-22 | [7 empty] | 2022-09-08 | 2022-12-22 | [7 empty] | 2022-08-31 | 2022-12-23 | [10 empty] | 2022-11-04 | 2023-02-08 | [5 empty] | 2022-10-31 | 2023-01-25 | [7 empty] | 2022-10-31 | 2022-01-25 | [7 empty] | 2022-11-09 | [8 empty] | 2022-11-14 | [15 empty] | 2023-03-02 |  | 2023-03-02 |  | 2023-03-28 | [6 empty] | 588108 | 2023-01-25 |  |  | 2023-12-06 | 2021-07-13: 2023-03-29; 2021-07-13: 2023-03-29 | [17 empty] | Requested | [11 empty] | TRUE | TRUE | 572 | 2023-03-29 | 2023-03-29 | 2023 | 2023 | 2023
573 |  |  | Anthony Boucher | 2020-10-30 | 2023-10-20 | wthdw | [29 empty] | 10 - BEWE |  | 803D6 | 398 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Tiffiny Chase | Aspen Power Partners | ME I Searsmont 180 Belfast LLC | 180 belfast augusta road searmont | 2000303779 | 30014305020 | Solar | [5 empty] | 44.4076 | -69.207 | 180 Belfast Augusta Rd |  |  | Searsmont | 86.1 | BELFAST WEST SIDE | 803D6 | 34.5 kV Bus | 34.5 | 9310-L0383-5215-0002-ED00122 | FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2020-11-16 | 2020-11-06 | 2020-11-16 | 2020-11-08 | 2020-11-16 | 2022-08-15 | 2022-08-16 | 2022-08-18 | 2022-08-18 | 2022-08-18 | 2022-08-18 | 2022-09-01 |  |  | 2022-08-23 |  |  | CS | 2022-08-23 | [6 empty] | CS |  |  | 2022-08-26 |  |  | 2023-10-26 |  |  |  |  | 2023-08-23 |  |  |  | 2022-08-16 |  |  | 2023-11-03 | [5 empty] | 2022-08-24 |  |  | 2023-11-07 | [5 empty] | 2022-08-29 |  |  | 2023-11-07 | [8 empty] | 2022-11-02 | [6 empty] | 2022-11-02 | [8 empty] | 2022-11-09 | [8 empty] | 2022-11-10 | [8 empty] | 2022-11-10 | [7 empty] | 2022-11-11 | [7 empty] | 2022-12-05 |  | 2022-12-07 | 2024-01-19 | 2022-12-08 | 2024-01-19 | [5 empty] | 384884 | 2022-11-02 |  |  | 2024-08-15 | 2021-07-13: 2022-12-12; 2021-07-13: 2022-12-12; 2021-07-13: 2024-01-23; 2021-07-13: 2024-01-24 | [17 empty] | Requested | [11 empty] | TRUE | TRUE | 573 | 2022-12-12 | 2022-12-12 | 2022 | 2022 | 2022
574 |  | Lanie Patterson | Brent Brooks | 2020-11-03 | [31 empty] | 8 - DETR |  | 812D1 | 544 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Chris Anthony | CHRISTOPHER ANTHONY | CHRISTOPHER ANTHONY | Waverly St HDO | 2800648257 | 30010299003 | Hydro | [5 empty] | 44.7953 | -69.3857 | Waverly Ave |  |  | Pittsfield | 16.1 | DETROIT | 812D1 | 812T2 |  | 9310-L0392-4650-0107-ED00011 | Non-FERC | WITHDRAWN | WITHDRAWN | NONE | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2020-11-18 | 2020-11-10 | 2020-11-18 | 2020-11-10 | 2020-11-18 | 2020-12-03 |  | 2020-12-17 |  | 2020-12-03 | 2020-12-04 | 2020-12-18 |  |  | 2020-12-18 |  |  | FS | 2021-01-12 | [6 empty] | CS | 2021-01-12 |  | 2021-01-12 | [29 empty] | 2021-01-20 | [11 empty] | 2021-03-25 |  |  | 2021-07-12 | Report |  |  | 2021-07-12 | [8 empty] | 2021-07-12 | [17 empty] | 2021-07-13 | [7 empty] | 2021-07-13 | [7 empty] | 2021-08-26 |  | 2021-08-26 | [12 empty] | 2023-12-12 | 2021-07-13: 2021-08-26; 2021-07-13: 2021-10-05 | [17 empty] | Requested | [11 empty] | TRUE | TRUE | 574 | 2021-08-26 | 2021-08-26 | 2021 | 2021 | 2021
575 |  | Govinda Neupane |  | 2020-11-03 | 2022-02-13 |  |  |  | wthdw | [26 empty] | 3 - FAFA |  | 818D1 | 474 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Ben Aparo | Summit Ridge Energy | FARMINGTON FALLS PV LLC | 258 FARMINGTON FALLS RD NEW SHARON | 2000192254 | 30012792609 | Solar | [5 empty] | 44.6384 | -70.0438 | 258 Farmington Falls Rd |  |  | New Sharon | 65 | FARMINGTON FALLS | 818D1 | 818T1 |  | 9310-L0402-4075-0029-ED00141 | Non-FERC | WITHDRAWN | WITHDRAWN | NONE | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2020-11-18 | 2020-11-10 | 2020-11-18 | 2020-11-10 | 2020-11-18 | 2020-12-02 | 2020-12-01 | 2020-12-16 | 2020-12-01 | 2020-12-02 | 2020-12-02 | 2020-12-16 |  |  | 2020-12-09 | 2021-08-16 |  | CS | 2020-12-09 | RS | 2021-08-16 |  |  |  |  | CS |  |  | 2020-12-09 | 2021-08-16 | [18 empty] | 2020-12-11 | 2020-12-11 | 2021-08-16 | [7 empty] | 2020-12-17 | 2021-08-17 | [60 empty] | 2021-10-05 |  | 2021-10-05 |  | 2021-10-05 | [10 empty] | 2022-02-18 | 2021-07-13: 2021-10-05; 2021-07-13: 2021-10-07 | [29 empty] | TRUE | TRUE | 575 | 2021-10-05 | 2021-10-05 | 2021 | 2021 | 2021 |  |  |  | 2021-07-12 | Report
576 |  | Govinda Neupane |  | 2020-11-06 | [31 empty] | 4 - RUMF |  | 447D2 | 515 |  | WITHDRAWN | WITHDRAWN |  | Zac Gordon | Energy Management, Inc. | RUMFORD TRANSIT SOLAR LLC | 1022 OLD US RT 1 RUMFORD ME | 2000187125 | 30012725179 | Solar | [5 empty] | 44.5199 | -70.5582 | 1022 Old US Route 2 |  |  | Rumford |  | RUMFORD | 447D2 |  |  | 9310-L0187-5020-0139-ED00008 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2020-11-16 | 2020-11-23 |  |  |  |  | 1900-01-12 | [127 empty] | 2021-07-28 | [37 empty] | TRUE | TRUE | 576 | 0 | 0 | 1900 | 1900 | 1900
577 |  | Lanie Patterson | Brent Brooks | 2020-11-12 | 2022-09-08 | L2_Bump |  | 2024-06-14 | wthdw |  | 2024-10-24 | wthdw | [22 empty] | 481 | 7 - RRPS |  | 873D1 | 481 | Yes | WITHDRAWN | WITHDRAWN |  | Haley Orvedal | Galehead Development | WATERVILLE PV I LLC | 407 FAIRFIELD ST / OAKLAND | 2000192706 | 30012798135 | Solar/Battery | [5 empty] | 44.5681 | -69.6898 | 407 Fairfield St |  |  | Oakland | 61 | COUNTY RD (RICE RIPS) | 873D1 | 873T1 | 34.5 | 9310-L0456-4300-0044-ED00089 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2020-11-23 | 2020-11-19 | 2020-11-30 | 2020-11-16 | 2020-11-23 | 2025-06-13 | 2025-06-19 | 2025-06-30 | [127 empty] | 2025-07-01 | [37 empty] | TRUE | TRUE | 577 | 0 | 0 | 1900 | #VALUE! | #VALUE!
578 |  | Marshall Ripley | Rick Duperre | 2020-11-12 | 2023-10-19 | wthdw |  | 2023-01-23 | wthdw | [26 empty] | 5 - SWRD |  | 682D1 | 565 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Haley Orvedal | Engie | PLEASANT RIVER PV I LLC | 469 River Rd Windham | 2000192705 | 30012798366 | Solar | [5 empty] | 43.7525 | -70.4299 | 469 River Rd |  |  | Windham | 17 | SWETT ROAD | 682D1 | 682T1 | 12.47 | 9310-L0251-6390-0083-ED00005 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2020-11-23 | 2020-11-19 | 2020-11-30 | 2020-11-16 | 2020-11-23 | 2021-12-10 | 2021-12-17 | 2021-12-27 | 2021-12-21 | 2022-01-06 | 2022-01-06 | 2022-01-20 |  |  | 2022-01-20 |  | 2023-01-31 | CS | 2022-01-21 | [6 empty] | CS |  |  | 2022-01-21 | 2022-10-17 | 2023-02-01 | 2024-01-30 | [9 empty] | 2022-10-25 | 2023-02-15 | [5 empty] | 2022-02-04 | 2022-02-04 | 2022-10-19 | 2023-02-15 | [6 empty] | 2022-02-05 | 2022-10-27 | 2023-02-20 | [9 empty] | 2022-04-11 | 2022-12-13 | 2023-04-25 |  |  |  |  | 2022-04-21 | 2022-12-12 | 2023-05-26 | [6 empty] | 2022-04-21 | 2022-12-19 | 2023-05-31 | [6 empty] | 2022-04-25 | 2023-01-04 | 2023-06-01 | [6 empty] | 2022-05-09 | 2023-01-06 | 2023-06-08 | [5 empty] | 2022-05-09 | 2023-01-06 | 2023-06-08 | [5 empty] | 2023-06-12 |  | 2023-06-14 |  | 2023-06-23 | [6 empty] | 677334 | 2023-05-26 |  |  | 2024-02-02 | 2021-07-13: 2023-07-05; 2021-07-13: 2023-07-05 | [29 empty] | TRUE | TRUE | 578 | 2023-07-05 | 2023-07-05 | 2023 | 2023 | 2023
579 |  | Eben Snow | Brent Brooks | 2020-11-12 | [31 empty] | 1 - WEBR |  | 458D1 |  |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Robert Snow | New Leaf Energy, Inc | 510 PV PROJECT DEVELOPMENT LLC | 0 North High St Bridgeton | 2000113260 | 30012744089 | Solar/Battery | [5 empty] | 44.0645 | -70.8354 | 0 North High Street |  |  | Bridgton | 523 | WEST BRIDGTON | 458D1 | 458T1 | 34.5 | 9310-L0201-0690-0133-ED00086 | Non-FERC | WITHDRAWN | WITHDRAWN | NONE | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2020-11-30 | 2020-11-19 | 2020-11-30 | 2020-11-19 | 2020-11-30 | 2020-12-04 |  | 2020-12-18 |  | 2020-12-04 | 2020-12-04 | 2020-12-18 |  |  | 2020-12-09 |  |  | CS | 2020-12-09 | [6 empty] | CS |  |  | 2020-12-09 | [29 empty] | 2020-12-15 | [11 empty] | 2021-02-22 |  |  | 2021-06-09 | Report |  |  | 2021-06-09 | [8 empty] | 2021-06-09 | [17 empty] | 2021-06-21 | [7 empty] | 2021-06-21 | [7 empty] | 2021-07-14 |  | 2021-07-14 |  | 2021-07-14 | [6 empty] | 739841 |  |  |  | 2023-02-02 | 2021-07-13: 2021-07-20; 2021-07-13: 2021-07-20 | [17 empty] | 10300809360 | [11 empty] | TRUE | TRUE | 579 | 2021-07-20 | 2021-07-20 | 2021 | 2021 | 2021 |  |  |  |  | 2022-05-09
580 |  | Govinda Neupane |  | 2020-11-12 | [31 empty] | 4 - EMDE |  | 868D1 | 542 |  | WITHDRAWN | WITHDRAWN |  | Nick Ford | Hexagon Energy LLC | CHESTNUT SOLAR LLC | North Main St Solon | 2000193718 | 30012811631 | Solar | [5 empty] | 44.96 | -69.858 | 0 N Main St |  |  | Solon |  | EMBDEN | 868D1 |  |  | 9310-L0452-5370-0004-ED00043 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2020-11-19 | 2020-11-30 |  |  |  |  | 1900-01-12 | [127 empty] | 2021-07-26 | [25 empty] | NO STUDY | [11 empty] | TRUE | TRUE | 580 | 0 | 0 | 1900 | 1900 | 1900 |  |  |  | 2021-06-09 | Report
581 |  | Govinda Neupane |  | 2020-11-12 | [31 empty] | 3 - RILE |  | 449D2 | 468 |  | WITHDRAWN | WITHDRAWN |  | Nick Ford | Hexagon Energy LLC | GRANTIE HILL SOLAR | main st jay | 2000193751 | 30012811649 | Solar | [5 empty] | 44.519 | -70.227 | 0 Main St |  |  | Jay |  | RILEY | 449D2 |  |  | 9310-L0191-2920-0085-ED00098 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2020-11-19 | 2020-11-30 |  |  |  |  | 1900-01-12 | [127 empty] | 2021-10-29 | [25 empty] | STUDY | [11 empty] | TRUE | TRUE | 581 | 0 | 0 | 1900 | #VALUE! | #VALUE!
582 |  | Marshall Ripley | Rick Duperre | 2020-11-12 | [31 empty] | 2 - PLHL |  | 644D2 | 453 |  | WITHDRAWN | WITHDRAWN |  | Nick Ford | Hexagon Energy LLC | PLEASANT HILL SOLAR LLC | highland ave south portland | 2000193752 | 30012811656 | Solar | [5 empty] | 43.6 | -70.288 | 0 Highland Ave |  |  | South Portland |  | PLEASANT HILL | 644D2 |  |  | 9310-L0286-5430-0180-ED00044 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2020-11-19 | 2020-11-30 |  |  |  |  | 1900-01-12 | [127 empty] | 2021-08-12 | [25 empty] | STUDY | [11 empty] | TRUE | TRUE | 582 | 0 | 0 | 1900 | #VALUE! | #VALUE!
583 |  | Rigel Paradise | Rick Duperre | 2020-11-12 | [31 empty] | 1 - ELIO |  | 687D1 |  |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN | 2021-07-15 | Andrew Kellar | New Hampshire Solar Garden | ODIORNE LANE SOLAR LLC | 10 ODIORNE LANE, ELIOT | 2000193758 | 30012812407 | Solar | [5 empty] | 43.1623 | -70.767 | 10 ODIORNE LANE |  |  | Eliot | 4 | ELIOT | 687D1 | 687T1 |  | 9310-L0364-1830-0046-ED00005 | Non-FERC | WITHDRAWN | WITHDRAWN | 325000 | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2020-11-30 | 2020-11-19 | 2020-11-30 | 2020-11-19 | 2020-11-30 | 2020-12-09 |  | 2020-12-23 |  | 2020-12-09 | 2020-12-09 | 2020-12-23 |  |  | 2020-12-10 | 2021-07-21 |  | CS | 2020-12-10 | RS | 2021-07-21 |  |  |  |  | CS |  |  | 2020-12-10 | 2021-07-21 | [28 empty] | 2020-12-17 | 2021-07-23 | [10 empty] | 2021-02-24 | 2021-09-03 |  | 2021-06-09 | Report |  |  | 2021-06-09 | 2021-09-03 | [7 empty] | 2021-06-09 | 2021-09-02 | [17 empty] | 2021-09-08 | [7 empty] | 2021-09-08 | [6 empty] | 2021-09-09 |  | 2021-09-09 | 2023-03-29 |  | 2023-03-31 | [7 empty] | 396762 | 2023-03-27 | 2024-01-03 | 2021-07-13: 2021-09-09; 2021-07-13: 2021-09-16 | [17 empty] | Requested | [11 empty] | TRUE | TRUE | 583 | 2021-09-09 | 2021-09-09 | 2021 | 2021 | 2021
584 |  | Eben Snow | Brent Brooks | 2020-11-12 | [31 empty] | 4 - BALD |  | 691D1 | 130 |  | WITHDRAWN | WITHDRAWN |  | Andrew Kellar | New Hampshire Solar Garden | Sebago Road Solar | 300 Baldwin Rd, Sebago | 2000193759 | 30012816044 | Solar | [5 empty] | 43.8492 | -70.6457 | 300 Baldwin Rd |  |  | Sebago |  | BALDWIN | 691D1 |  |  | 9310-L0371-5230-0016-ED00009 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2020-11-19 | 2020-11-30 |  |  |  |  | 1900-01-12 | [127 empty] | 2021-09-09 | [37 empty] | TRUE | TRUE | 584 | 0 | 0 | 1900 | #VALUE! | #VALUE! |  |  |  | 2021-06-09 | Report
585 |  |  | Anthony Boucher | 2020-11-13 | [31 empty] | 2 - CAMD |  | 214D3 | 546 |  | WITHDRAWN | WITHDRAWN |  | Robert Snow | BORREGO SOLAR SYSTEMS INC | 510 PV PROJECT DEVELOPMENT LLC | 799 Commercial St Rockport | 2000113260 | 30012800667 | Solar | [7 empty] | 799 Commercial St |  |  | Rockport |  | CAMDEN | 214D3 |  |  | 9310-L0036-4980-0006-ED00269 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2020-11-20 | 2020-12-01 |  |  |  |  | 1900-01-12 | [57 empty] | No Study | [69 empty] | 2021-05-17 | [37 empty] | TRUE | TRUE | 585 | 0 | 0 | 1900 | 1900 | 1900
586 |  |  |  | 2020-11-13 | [31 empty] | 4 - SMRD |  | 660D2 | 166 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Jacqueline Fedida | Greenbacker Capital | ORCHARD ROAD SOLAR LLC | 3 Orchard Rd Standish | 2000203988 | 30012942766 | Solar | [5 empty] | 43.7339 | -70.5419 | 3 Orchard Rd |  |  | Standish | 3 | SHAWS MILL ROAD | 660D2 | 660T1 |  | 9310-L0493-5500-0075-ED00002 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2020-12-01 | 2020-11-20 | 2020-12-01 | 2020-11-20 | 2020-12-01 | 2020-12-10 |  | 2020-12-24 |  | 2020-12-10 | 2020-12-11 | 2020-12-28 |  |  | 2020-12-11 | 2021-07-21 |  | CS | 2020-12-11 | RS | 2021-07-21 |  |  |  |  | CS |  |  | 2020-12-11 | 2021-07-21 | [28 empty] | 2020-12-15 | 2021-07-23 | [10 empty] | 2021-02-22 | 2021-09-03 |  | 2021-06-11 | Report |  |  | 2021-06-11 | 2021-09-07 | [7 empty] | 2021-06-11 | 2021-09-07 | [17 empty] | 2021-09-08 | [7 empty] | 2021-09-08 | [8 empty] | 2021-10-20 |  |  |  | 2024-11-21 | [8 empty] | 2025-01-17 | 2021-07-13: 2021-10-22; 2021-07-13: 2021-10-22; 2021-07-13: 2022-09-07; 2021-07-13: 2022-09-07 | [17 empty] | Requested | [11 empty] | TRUE | TRUE | 586 | 2021-10-22 | 2021-10-22 | 2021 | 2021 | 2021
587 |  | Eben Snow | Brent Brooks | 2020-11-13 |  |  |  | 2023-01-05 | L2_Bump |  | 2025-01-06 | wthdw | [21 empty] | 2 - LEED | 525 | 8 - LEED |  | 471D1 | 525 | Yes | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Will Bliss | VC Renewables LLC | ELP LIVERMORE SOLAR LLC | 73 CANTON RD LIVERMORE | 2000193411 | 30012808199 | Solar | [5 empty] | 44.3815 | -70.2527 | 73 CANTON RD |  |  | Livermore | 7 | LEEDS | 471D1 | 471T1 | 34.5 | 9310-L0209-3345-0012-ED00107 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2020-12-01 | 2020-11-20 | 2020-12-01 | 2020-11-20 | 2020-12-01 | 2022-11-01 | 2022-11-02 | 2022-11-16 | 2022-11-03 | 2022-11-07 | 2022-11-10 | 2022-11-22 |  |  | 2022-11-23 |  |  | CS | 2022-11-23 | [6 empty] | CS |  |  | 2022-11-28 |  |  | 2025-01-08 | [8 empty] | 2022-12-05 |  |  | 2025-01-20 | [5 empty] | 2022-12-07 |  |  | 2025-01-22 | [5 empty] | 2022-12-07 |  |  | 2025-01-22 | [8 empty] | 2023-02-13 | [6 empty] | 2023-02-07 |  |  | 2025-03-25 | [5 empty] | 2023-02-08 |  |  | 2025-03-25 | [5 empty] | 2023-02-10 |  |  | 2025-04-07 | [5 empty] | 2023-02-14 |  |  | 2025-04-11 | [7 empty] | 2025-04-11 |  |  |  |  | 2023-03-06 |  | 2023-03-08 | 2025-05-09 | 2023-03-27 | [6 empty] | 621251 | 2023-02-07 | 680215 | 2025-03-25 | 2025-11-25 | 2021-07-13: 2023-03-30; 2021-07-13: 2023-03-30; 2021-07-13: 2025-06-11; 2021-07-13: 2025-06-12 | [13 empty] | Q3 2021 |  |  |  | Requested | [11 empty] | FALSE | TRUE | 587 | 2023-03-30 | 2023-03-30 | 2023 | 2023 | 2023 |  |  |  | 2021-06-11 | Report
588 |  | Rigel Paradise | Rick Duperre | 2020-11-19 | 2022-11-09 | L2_Bump | [29 empty] | 6 - BASS |  | 602D2 | 361 | Yes | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Jacqueline Fedida | Greenbacker Capital | 259 SCHOOL STREET SOLAR LLC | 259 School St Berwick | 2000194990 | 30012828510 | Solar | [5 empty] | 43.2825 | -70.8377 | 259 School St |  |  | Berwick | 70 | BASSETT | 602D2 | 602T1 | 12.47 | 9310-L0211-0470-0080-ED00111 | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2020-12-07 | 2020-11-30 | 2020-12-07 | 2020-11-30 | 2020-12-07 | 2021-02-26 |  | 2021-03-12 |  | 2021-02-26 | 2021-02-26 | 2021-03-12 |  |  | 2021-03-01 | 2021-07-21 |  | CS | 2021-03-01 | RS | 2021-07-21 |  |  |  |  | CS |  |  | 2021-03-01 | 2021-07-21 | 2022-10-17 | 2022-11-10 | [11 empty] | 2022-12-12 | [14 empty] | 2021-03-03 | 2021-07-23 | 2022-10-18 | 2022-12-19 | [8 empty] | 2021-05-06 | 2021-09-03 |  | 2021-06-25 | Report |  |  | 2021-06-25 | 2021-09-03 |  | 2023-02-01 | [5 empty] | 2021-06-25 | 2021-09-02 |  | 2023-02-01 | [8 empty] | 2023-02-03 | [6 empty] | 2021-09-08 |  | 2023-02-08 | [5 empty] | 2021-09-08 |  | 2023-02-08 |  |  |  |  | 2021-09-22 |  | 2021-09-22 | 2023-02-13 |  | 2023-02-17 | [5 empty] | 232677 | 2021-08-13 | 531503 | 2023-01-31 | 2025-11-21 | 2021-07-13: 2021-09-22; 2021-07-13: 2021-09-30; 2021-07-13: 2023-02-18; 2021-07-13: 2023-02-20 | [17 empty] | Requested | [11 empty] | TRUE | TRUE | 588 | 2021-09-22 | 2021-09-22 | 2021 | 2021 | 2021
589 |  | Govinda Neupane |  | 2020-11-19 | 2022-09-09 |  |  | 2022-12-01 | L2_Bump |  | 2023-10-06 | L2_Bump |  | 2023-12-06 | L2_Bump |  | 2024-10-04 | wthdw | [17 empty] | 6 - GUIL |  | 821D1 | 498 |  | WITHDRAWN | WITHDRAWN |  | Melissa Reed | FFP ORIGINATION LLC | FFP ORIGINATION LLC | ME-150 Parkman | 2000165043 | 30012798531 | Solar | [5 empty] | 45.1586 | -69.3922 | ME-150 Parkman |  |  | Parkman | 31 | GUILFORD | 821D1 | 821T1 | 12.47 | 9310-L0405-4520-0020-ED00020 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2020-12-07 | 2020-11-30 | 2020-12-07 | 2020-11-30 | 2020-12-07 | 2022-08-04 |  | 2024-08-22 |  | 2022-08-19 | 2022-08-19 | [20 empty] | 2024-10-07 | [103 empty] | 2024-11-14 | [37 empty] | TRUE | TRUE | 589 | 0 | 0 | 1900 | #VALUE! | #VALUE! |  |  |  | 2021-06-25 | Report
590 |  | Govinda Neupane |  | 2020-11-24 | 2023-03-09 | wthdw |  | 2023-09-08 | L2_Bump |  | 2023-10-03 | L2_bump | [23 empty] | 6 - CARM |  | 808D1 | 553 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Ben Vanderlan | Bluewave MA, LLC | BWC ETNA POND, LLC | 1298 MAIN RD CARMEL ME | 2000183318 | 30014263997 | Solar/Battery | [5 empty] | 44.8127 | -69.0875 | 1298 MAIN RD |  |  | Carmel | 167 | CARMEL | 808D1 | 808T1 | 12.47 | 9310-L0388-1020-0049-ED00143 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2020-12-10 | 2020-12-03 | 2020-12-10 | 2020-12-03 | 2020-12-10 | 2022-06-01 | 2022-06-20 | 2022-06-15 | 2022-06-23 | 2022-06-23 | 2022-06-28 | 2022-07-12 |  |  | 2022-06-27 |  |  | CS | 2022-06-27 | [6 empty] | CS |  |  | 2022-07-06 | 2022-10-17 | [7 empty] | 2022-10-14 |  |  | 2022-07-12 | 2022-10-27 | [7 empty] | 2022-07-12 | 2022-11-01 | [7 empty] | 2022-07-13 | 2022-11-01 | [10 empty] | 2022-09-14 | 2022-12-16 | [5 empty] | 2022-09-15 | 2022-12-12 | [7 empty] | 2022-09-15 | 2022-12-13 | [7 empty] | 2022-09-26 | 2022-12-16 | [7 empty] | 2022-09-26 | 2022-12-21 | [6 empty] | 2022-09-26 | [7 empty] | 2022-12-27 |  | 2022-12-27 |  | 2022-12-27 | [6 empty] | 282324 | 2022-09-14 | 252262 | 2022-12-12 | 2023-10-17 | 2021-07-13: 2023-01-05; 2021-07-13: 2023-01-06 | [29 empty] | TRUE | TRUE | 590 | 2023-01-05 | 2023-01-05 | 2023 | 2023 | 2023
591 |  | Rigel Paradise | Rick Duperre | 2020-11-24 | 2024-01-03 | wthdw | [29 empty] | 2 - ELIO |  | 687D1 | 583 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Simon Courtney | SOLAR PROVIDER GROUP LLC | SOLAR PROVIDER GROUP LLC | Brook Rd Eliot | 2000157464 | 30012836349 | Solar | [5 empty] | 43.1333 | -70.7793 | Rook Rd |  |  | Eliot | 4 | ELIOT | 687D1 | 687T1 | 12.47 | 9310-L0364-1830-0149-ED00004 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2020-12-10 | 2020-12-03 | 2020-12-10 | 2020-12-03 | 2020-12-10 | 2021-09-16 |  | 2021-09-30 |  | 2021-09-23 | [7 empty] | CS | 2021-09-24 | [6 empty] | CS |  |  | 2021-09-24 |  |  | 2024-01-11 | [26 empty] | 2021-10-13 | [11 empty] | 2021-12-17 | [6 empty] | 2021-11-16 | [8 empty] | 2021-11-16 | [7 empty] | 2021-11-17 | [9 empty] | 2021-11-22 | [7 empty] | 2021-11-22 | [9 empty] | 2021-12-07 | [8 empty] | 364353 | 2021-10-25 |  |  | 2024-02-27 | 2021-07-13: 2021-12-08; 2021-07-13: 2021-12-10; 2021-07-13: 2022-06-16 | [17 empty] | Requested | [11 empty] | TRUE | TRUE | 591 | 2021-12-08 | 2021-12-08 | 2021 | 2021 | 2021
592 |  | Lanie Patterson | Brent Brooks | 2020-11-30 | [31 empty] | 3 - FAIR |  | 817D3 | 183 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Matt Doubleday | REWILD RENEWABLES LLC | REWILD RENEWABLES LLC | 176 Norridgewock Rd Fairfield | 2000198992 | 30012880420 | Solar/DC BESS | [5 empty] | 44.6062 | -69.6623 | 0 Norridgewock Rd |  |  | Fairfield | 801.2 | FAIRFIELD | 817D3 | 817T1 | 12.47 | 9310-L0401-2000-0093-ED00001 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2020-12-14 | 2020-12-07 | 2020-12-14 | 2020-12-07 | 2020-12-14 | 2020-12-11 |  | 2020-12-28 |  | 2020-12-11 | 2020-12-11 | 2020-12-28 |  |  | 2020-12-11 | 2021-08-06 |  | CS | 2020-12-11 | RS | 2021-08-06 |  |  |  |  | CS |  |  | 2020-12-11 | 2021-08-06 | [10 empty] | 2021-07-16 | [17 empty] | 2020-12-17 | 2021-08-10 | [10 empty] | 2021-02-24 | 2021-09-22 |  | 2021-06-17 | Report |  |  | 2021-06-17 | 2021-09-20 | [7 empty] | 2021-06-17 | 2021-09-20 | [16 empty] | 2021-06-28 | 2021-09-23 | [6 empty] | 2021-06-28 | 2021-09-23 | [17 empty] | 136425 |  | 11475956 | 2021-05-20 | 2022-06-30 | 2021-07-13: 2021-10-14; 2021-07-13: 2021-10-15 | [17 empty] | Requested | [11 empty] | TRUE | TRUE | 592 | 2021-10-14 | 2021-10-14 | 2021 | 2021 | 2021
593 |  | Govinda Neupane |  | 2020-12-08 | 2022-09-09 | [30 empty] | 7 - GUIL |  | 821D1 | 589 |  | WITHDRAWN | WITHDRAWN |  | Melissa Reed | FFP ORIGINATION LLC | FFP ORIGINATION LLC | ME-150 Parkman | 2000165043 |  | Solar | [7 empty] | ME-150 |  |  | Parkman |  | GUILFORD | 821D1 |  |  | 86-Withdrawn-86d |  | WITHDRAWN | WITHDRAWN | [8 empty] | 2020-12-15 | 2020-12-22 |  |  |  |  | 1900-01-12 | [127 empty] | 2020-02-08 | [37 empty] | TRUE | TRUE | 593 | 0 | 0 | 1900 | #VALUE! | #VALUE! |  |  |  | 2021-06-17 | Report
594 |  | Rigel Paradise | Rick Duperre | 2020-12-08 | 2023-02-28 | L2_Bump | [29 empty] | 2 - MAST |  | 634D1 | 379 | Yes | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Nick Mazuroski | Dirigo/BNRG | BD SOLAR BIDDEFORD LLC | DREWS MILLS RD BIDDEFORD | 2000193885 | 30012814627 | Solar | [5 empty] | 43.4808 | -70.5362 | Drews Mills Rd |  |  | Biddeford | 9 | MAY STREET | 634D1 | 634T1 | 12.47 | 9310-L0266-4180-0010-ED00013 | Non-FERC | WITHDRAWN | WITHDRAWN | NONE | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2020-12-22 | 2020-12-15 | 2020-12-22 | 2020-12-15 | 2020-12-22 | 2021-01-07 |  | 2021-01-22 |  | 2021-01-07 | 2021-01-07 | 2021-01-22 |  |  | 2021-01-15 |  |  | CS | 2021-01-15 | [6 empty] | CS |  |  | 2021-01-15 |  |  | 2023-03-03 | [11 empty] | 2023-03-15 | [8 empty] | 2023-04-12 | [5 empty] | 2021-02-01 |  |  | 2023-04-12 | [8 empty] | 2021-04-06 |  |  | 2021-05-10 | Report |  |  | 2021-05-10 |  |  | 2023-05-26 | [5 empty] | 2021-05-10 |  |  | 2023-05-26 | [8 empty] | 2023-06-01 | [5 empty] | 2021-05-17 |  |  | 2023-06-13 |  |  |  |  | 2021-05-17 | [5 empty] | 2021-05-17 |  |  |  |  | 2023-06-30 |  |  | 2025-06-10 | 2025-06-10 |  |  |  | 336216 | 2021-04-15 | 463170 | 2023-05-24 | 2025-08-07 | 2021-06-07 | 2021-06-07 | 2021-06-07 | 2021-06-07 | 2023-07-31 | 2023-07-31 |  |  |  |  | 2025-07-14 | 2025-07-14 | [9 empty] | Q3 2025 |  |  |  | Requested | [11 empty] | TRUE | TRUE | 594 | 2021-06-07 | 2021-06-07 | 2021 | 2021 | 2021 | 44333
595 |  | Lanie Patterson | Brent Brooks | 2020-12-08 | [31 empty] | 4 - BOST |  | 263D1 | 447 |  | WITHDRAWN | WITHDRAWN |  | Ben Vanderlan | Bluewave MA, LLC | BLUE WAVE PROJECT DEVOLPMENT LLC | 0 BEECH STREET CHELSEA ME 04330 | 2000183318 |  | Solar | [7 empty] | 0 Beech St |  |  | Chelsea |  | BOWMAN STREET | 263D1 |  |  | 9310-L0044-1110-0051-ED00123 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2020-12-15 | 2020-12-22 |  |  |  |  | 1900-01-12 |  |  | 2020-12-17 | [54 empty] | No Study | [69 empty] | 2021-01-07 | [37 empty] | TRUE | TRUE | 595 | 0 | 0 | 1900 | 1900 | 1900 |  |  |  | 2021-05-10 | Report
596 |  | Rigel Paradise | Rick Duperre | 2020-12-08 | 2024-07-01 | wthdw | [29 empty] | 4 - HITP |  | 692D1 | 260 | Yes | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Tejas Sinthalapad Jayakumar | Nexamp, Inc | Cornish Solar LLC | Cumberland St Cornish | 2000462720 | 30016503937 | Solar | [5 empty] | 43.8055 | -70.7862 | Cumberland Street |  |  | Cornish | 29 | HIRAM TAP | 692D1 | 692T1 | 34.5 | 9310-L0372-1240-0027-ED00046 | FERC | WITHDRAWN | WITHDRAWN | 325000 | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2020-12-22 | 2020-12-15 | 2020-12-22 | 2020-12-15 | 2020-12-22 | 2020-12-29 |  | 2021-01-13 |  | 2020-12-29 | 2020-12-29 | 2021-01-13 |  |  | 2021-01-12 |  |  | FS | 2021-01-12 | [6 empty] | CS | 2021-01-12 |  | 2021-01-12 |  |  | 2024-07-30 | [11 empty] | 2024-08-09 | [8 empty] | 2024-08-09 | [5 empty] | 2021-01-20 |  |  | 2024-08-12 | [8 empty] | 2021-03-25 |  |  | 2021-06-22 | Report |  |  | 2021-06-22 |  |  | 2024-10-16 | [5 empty] | 2021-06-27 |  |  | 2024-10-17 | [8 empty] | 2024-10-21 | [5 empty] | 2021-06-28 |  |  | 2024-10-28 |  |  |  |  | 2021-06-28 |  |  | 2024-10-28 |  |  |  |  | 2021-07-20 |  | 2021-07-20 | 2022-12-07 |  | 2022-12-07 | [5 empty] | 6708418 | 2021-05-27 | 248890 | 2024-10-16 | 2025-05-14 | 2021-08-18 | 2021-08-18 |  | 2022-12-08 | 2025-01-08 | 2025-01-08 | [15 empty] | Q2 2022 |  |  |  | Requested | [11 empty] | TRUE | TRUE | 596 | 2021-08-18 | 2021-08-18 | 2021 | 2021 | 2021
597 |  | Govinda Neupane |  | 2020-12-09 | 2023-05-22 | L2_Bump | [29 empty] | 7 - LVFA |  | 428D2 | 373 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Melissa Reed | FFP ORIGINATION LLC | FFP ORIGINATION LLC | 545 PARK ST / LIVERMORE FALLS | 2000165043 | 30012837503 | Solar | [5 empty] | 44.445 | -70.1538 | 545 Park St |  |  | Livermore Falls | 104 | LIVERMORE FALLS | 428D2 | 428T1 | 34.5 | 9310-L0161-3350-0024-ED00006 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2020-12-23 | 2020-12-16 | 2020-12-23 | 2020-12-16 | 2020-12-23 | 2021-12-30 | 2022-01-06 | 2022-01-14 | 2022-01-07 | 2022-01-14 | 2022-01-14 | 2022-01-31 |  |  | 2022-01-28 |  |  | CS | 2022-01-28 | [6 empty] | CS |  |  | 2022-01-28 |  |  | 2023-05-24 | [11 empty] | 2023-07-05 |  |  |  |  | 2022-03-02 | 2022-03-02 |  |  | 2023-07-06 | [5 empty] | 2022-03-02 | [11 empty] | 2022-05-05 | [6 empty] | 2022-04-29 |  |  | 2023-08-21 | [5 empty] | 2022-04-29 |  |  | 2023-08-23 | [5 empty] | 2022-05-16 |  |  | 2023-09-19 | [5 empty] | 2022-05-19 |  |  | 2023-09-28 |  |  |  |  | 2022-05-19 |  |  | 2023-09-28 |  |  |  |  | 2022-06-15 |  | 2022-06-15 |  | 2022-07-13 |  | 2022-02-07 | 2022-02-14 | [5 empty] | 321702 | 2023-08-21 | 2023-11-14 | 2021-07-13: 2022-07-14; 2021-07-13: 2022-07-15 | [17 empty] | Requested | [11 empty] | TRUE | TRUE | 597 | 2022-07-14 | 2022-07-14 | 2022 | 2022 | 2022 |  |  |  | 2021-06-22 | Report
598 |  | Lanie Patterson | Brent Brooks | 2020-12-09 | [31 empty] | 8 - NOAU |  | 272D6 | 530 |  | WITHDRAWN | WITHDRAWN |  | Cindy Mickune | Louth Callan Renewables | PENNEY RD SOLAR LLC | MAP 02 LOT 21D/3230 / BELGRADE | 2000199323 | 30012884190 | Solar | [5 empty] | 44.4084 | -69.8393 | Penny Rd |  |  | Belgrade | 20 | NORTH AUGUSTA | 272D6 | 272T2 | 34.5 | 9310-L0470-0445-0005-ED00008 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2020-12-23 | 2020-12-16 | 2020-12-23 | 2020-12-16 | 2020-12-23 | 2023-01-24 | 2023-01-27 | 2023-02-07 | 2023-01-30 | [126 empty] | 2023-02-20 | [37 empty] | TRUE | TRUE | 598 | 0 | 0 | 1900 | #VALUE! | #VALUE!
599 |  | Eben Snow | Brent Brooks | 2020-12-09 | 2023-12-08 | L2_Bump | [29 empty] | 1 - CH12 |  | 421D2 |  | Yes | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED |  | Boris Piskun | Greenday Finance LLC | LEWISTON SOLAR II LLC | 24 FERRY RD LEWISTON | 2000198357 | 30015872986 | Solar | 1975 | 1.975 | 2916.84 |  |  | 44.0679 | -70.1741 | 24 FERRY RD |  |  | Lewiston | 18 | CHALLENGER 12 KV | 421D2 | 421T1 | 12.47 | 9310-L0145-3230-0120-ED00002 | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2020-12-23 | 2020-12-16 | 2020-12-23 | 2020-12-16 | 2020-12-23 | 2020-12-30 |  | 2021-01-14 |  | 2020-12-30 | 2020-12-30 | 2021-01-14 |  |  | 2021-01-14 |  |  | CS | 2021-01-06 | [6 empty] | CS |  |  | 2021-01-06 | [29 empty] | 2021-01-12 |  |  | 2024-01-22 | [8 empty] | 2021-03-18 |  |  | 2021-06-09 | Report |  |  | 2021-06-09 |  |  | 2024-03-22 | [5 empty] | 2021-06-09 |  |  | 2024-03-22 | [8 empty] | 2024-03-22 | [5 empty] | 2021-06-21 |  |  | 2024-03-29 |  |  |  |  | 2021-06-21 |  |  | 2024-03-29 | [6 empty] | 2022-11-29 | 2023-04-27 |  | 2023-04-27 | 2023-08-10 | 2023-08-10 |  |  |  | 446675 |  | 194130 | 2023-11-28 |  | 2021-07-13: 2021-07-07; 2021-07-13: 2021-07-07; 2021-07-13: 2023-04-27; 2021-07-13: 2023-04-28 |  |  | 2023-08-22 | 2023-08-22 | [9 empty] | Q1 2022 |  |  |  | Requested | [11 empty] | TRUE | TRUE | 599 | 2021-07-07 | 2021-07-07 | 2021 | 2021 | 2021
600 |  | Marshall Ripley | Rick Duperre | 2020-12-09 | [31 empty] | 1 - PRCO |  | 647D1 |  |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Simon Courtney | SOLAR PROVIDER GROUP LLC | ME WHITE PINE SOLAR LLC | Lunt Dr Westbrook ME | 2000157464 | 30012875255 | Solar | [5 empty] | 43.7175 | -70.3231 | Lunt Dr |  |  | Westbrook | 4 | PRIDES CORNER | 647D1 | 647T2 | 12.47 | 9310-L0304-6320-0022-ED00004 | Non-FERC | WITHDRAWN | WITHDRAWN | NONE | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2020-12-23 | 2020-12-16 | 2020-12-23 | 2020-12-16 | 2020-12-23 | 2021-01-06 |  | 2021-01-21 |  | 2021-01-06 | 2021-01-06 | 2021-01-21 |  |  | 2021-01-12 |  |  | CS | 2021-01-12 | [6 empty] | CS |  |  | 2021-01-12 | [29 empty] | 2021-01-25 | [11 empty] | 2021-03-30 |  |  | 2021-06-25 | Report |  |  | 2021-06-25 | [8 empty] | 2021-06-25 | [17 empty] | 2021-07-07 | [7 empty] | 2021-07-08 | [9 empty] | 2021-07-08 | 2022-06-14 | [7 empty] | 122279 |  | 268016 | 2022-09-09 | 2024-09-04 | 2021-07-08 | 2021-07-12 | 2022-01-31 | 2022-02-01 | 2022-06-14 | 2022-06-14 | 2022-11-09 | 2022-11-15 | [15 empty] | 2022-02-01 |  | 10300805104 | [11 empty] | TRUE | TRUE | 600 | 2021-07-08 | 2021-07-08 | 2021 | 2021 | 2021 |  |  |  | 2021-06-09 | Report
601 |  | Ben Brooks | KRISTOFER COLEMAN | 2020-12-09 | [31 empty] | 2 - FREE |  | 225D3 | 554 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Andrew Kellar | NEW HAMPSHIRE SOLAR GARDEN | PROUT ROAD SOLAR LLC | 3 Prout Rd Freeport ME 04032 | 2000198765 | 30012877582 | Solar | [5 empty] | 43.8795 | -70.0802 | 3 Prout Rd |  |  | Freeport | 1 | FREEPORT | 225D3 | 225T2 | 12.47 | 9310-L0055-2110-0170-ED00051 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2020-12-23 | 2020-12-16 | 2020-12-23 | 2020-12-16 | 2020-12-23 | 2021-05-26 |  | 2021-06-10 |  | 2021-05-26 | 2021-05-26 | 2021-06-10 |  |  | 2021-06-01 | 2021-07-21 |  | CS | 2021-06-04 | RS | 2021-07-21 |  |  |  |  | CS |  |  | 2021-06-04 | [11 empty] | 2021-06-15 | [17 empty] | 2021-06-09 | 2021-07-22 | [10 empty] | 2021-08-13 | 2021-09-01 | [5 empty] | 2021-07-14 | 2021-09-02 | [7 empty] | 2021-07-21 | 2021-09-02 | [17 empty] | 2021-09-08 | [7 empty] | 2021-09-08 | [6 empty] | 2021-10-21 |  | 2021-10-20 | [8 empty] | 499335 | 2021-08-16 | 515835 | 2021-08-16 | 2022-08-16 | 2021-07-13: 2021-10-20; 2021-07-13: 2021-10-22 | [17 empty] | Requested | [11 empty] | TRUE | TRUE | 601 | 2021-10-20 | 2021-10-20 | 2021 | 2021 | 2021 |  |  |  | 2021-06-25 | Report
602 |  | Govinda Neupane |  | 2020-12-14 | [31 empty] | 2 - ANDO |  | 400D1 | 477 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Geoffrey Sparrow | GREEN LANTERN DEVELOPMENT LLC | TROTTING PARK GLC SOLAR LLC | 436 South Main St. Andover | 2000249820 | 30013566739 | Solar | [5 empty] | 44.6208 | -70.7469 | 436 South Main St. |  |  | Andover | 16.13 | ANDOVER | 400D1 | 400T1 | 12.47 | 9310-L0112-0120-0002-ED00187 | Non-FERC | WITHDRAWN | WITHDRAWN | NONE | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2020-12-29 | 2020-12-21 | 2020-12-29 | 2020-12-21 | 2020-12-29 | 2021-01-04 |  | 2021-01-19 |  | 2021-01-04 | 2021-01-04 | 2021-01-19 |  |  | 2021-01-19 | 2021-07-12 |  | CS | 2021-01-04 | RS | 2021-07-12 |  |  |  |  | CS |  |  | 2021-01-04 | [11 empty] | 2021-01-05 | [17 empty] | 2021-01-07 | 2021-07-19 | [10 empty] | 2021-03-15 | 2021-08-30 |  | 2021-06-08 | Report |  |  | 2021-06-08 | 2021-08-30 | [7 empty] | 2021-06-08 | 2021-08-30 | [16 empty] | 2021-06-15 | 2021-08-31 | [6 empty] | 2021-06-15 | 2021-08-31 |  |  |  |  | 2021-06-15 |  | 2021-09-09 |  | 2021-09-09 | [8 empty] | 896393 |  |  |  | 2022-08-25 | 2021-07-13: 2021-09-16; 2021-07-13: 2021-09-30 | [17 empty] | Requested | [11 empty] | TRUE | TRUE | 602 | 2021-09-16 | 2021-09-16 | 2021 | 2021 | 2021 | 44362
603 |  |  | KRISTOFER COLEMAN | 2020-12-14 | [31 empty] | 1 - SHEE |  | 241D1 |  |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED |  | Alana Martell | SunRay Power, LLC | Alna Community Solar LLC | 1077 Alna Rd Alna | 2000162495 | 30013443285 | Solar | 2875 | 2.875 | 3844 |  |  | 44.0381 | -69.636 | 1077 Alna Rd |  |  | Alna | 127 | SHEEPSCOT | 241D1 | 241T1 | 12.47 | 9310-L0075-0090-0022-ED00068 | Non-FERC | NOT IMPACTED | NOT IMPACTED | NONE | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2020-12-29 | 2020-12-21 | 2020-12-29 | 2020-12-21 | 2020-12-29 | 2021-01-12 |  | 2021-01-27 |  | 2021-01-12 | 2021-01-12 | 2021-01-27 |  |  | 2021-01-21 |  |  | CS | 2021-01-21 | [6 empty] | CS |  |  | 2021-01-21 | [29 empty] | 2021-02-04 | [11 empty] | 2021-04-09 |  |  | 2021-05-12 | Report |  |  | 2021-05-12 | [8 empty] | 2021-05-12 | [17 empty] | 2021-05-13 | [7 empty] | 2021-05-13 | [5 empty] | 2021-05-13 |  | 2021-07-28 | 2021-07-29 | 2021-07-28 | 2023-03-01 | 2023-03-20 |  | 2024-08-23 | 2024-08-23 |  |  |  | 906326 |  | 980158 | 2023-02-15 |  | 2021-07-13: 2021-07-28; 2021-07-13: 2021-09-14; 2021-07-13: 2023-03-23; 2021-07-13: 2023-03-23 |  |  | 2024-09-03 | 2024-09-03 | [13 empty] | 10301037175 | [11 empty] | TRUE | TRUE | 603 | 2021-07-28 | 2021-07-28 | 2021 | 2021 | 2021 | 44329 |  | 44406 | 2021-06-08 | Report
604 |  | Eben Snow | Brent Brooks | 2020-12-14 | [31 empty] | 7 - MEFA |  | 431D1 | 370 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Geoffrey Sparrow | GREEN LANTERN DEVELOPMENT LLC | Mechanic Falls GLC Solar, LLC | Lewiston St Mechanic Falls 04256 | 2000197005 | 30013701567 | Solar | [5 empty] | 44.1073 | -70.3732 | Lewiston St |  |  | Mechanic Falls | 48 | MECHANIC FALLS | 431D1 | 431T2 | 12.47 | 9310-L0165-3610-0032-ED00055 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2020-12-29 | 2020-12-21 | 2020-12-29 | 2020-12-21 | 2020-12-29 | 2021-10-15 |  | 2021-10-29 |  | 2021-10-20 | 2021-10-20 | 2021-11-03 |  |  | 2021-10-22 |  |  | CS | 2021-10-22 | [6 empty] | CS |  |  | 2021-10-22 | [29 empty] | 2021-10-28 | [11 empty] | 2022-01-04 | [6 empty] | 2021-12-09 | [8 empty] | 2021-12-13 | [8 empty] | 2021-12-13 | [10 empty] | 2021-12-17 | [28 empty] | 2022-08-12 | 2021-07-13: 2021-01-18; 2021-07-13: 2021-01-19 | [17 empty] | Requested | [11 empty] | TRUE | TRUE | 604 | 2021-01-18 | 2021-01-18 | 2021 | 2021 | 2021 |  |  |  | 2021-05-12 | Report
605 |  | Govinda Neupane |  | 2020-12-15 | [31 empty] | 2 - EWIL |  | 816D1 | 459 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Troy McBride | Norwich Solar Technologies | WILTON ROUTE 2 SOLAR LLC |  | 2000196335 | 30012847163 | Solar | [5 empty] | 44.6175 | -70.1724 | RTE 2 |  |  | Wilton | 34 | EAST WILTON | 816D1 | 816T1 | 12.47 | 9310-L0398-6380-0040-ED00062 | Non-FERC | WITHDRAWN | WITHDRAWN | NONE | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2020-12-30 | 2020-12-22 | 2020-12-30 | 2020-12-22 | 2020-12-30 | 2021-01-14 |  | 2021-01-29 |  | 2021-01-14 | 2021-01-14 | 2021-01-29 |  |  | 2021-01-19 |  |  | CS | 2021-01-19 | [6 empty] | CS |  |  | 2021-01-19 | [29 empty] | 2021-01-21 | [11 empty] | 2021-03-26 |  |  | 2021-06-28 | Report |  |  | 2021-06-28 | [8 empty] | 2021-06-28 | [17 empty] | 2021-07-02 | [7 empty] | 2021-07-21 | [7 empty] | 2021-07-13 |  | 2021-07-13 | 2023-03-28 |  | 2023-04-19 | [5 empty] | 151343 | 2021-06-24 | 182800 | 2023-03-27 | 2024-02-22 | 2021-07-13: 2021-08-02; 2021-07-13: 2021-08-02; 2021-07-13: 2021-07-13; 2021-07-13: 2021-07-13 | [17 empty] | Requested | [11 empty] | TRUE | TRUE | 605 | 2021-08-02 | 2021-08-02 | 2021 | 2021 | 2021
606 |  | Govinda Neupane |  | 2020-12-15 | 2023-02-28 | L2_Bump |  | 2023-03-06 | L2_Bump |  | 2023-11-07 | L2_Bump | [23 empty] | 5 - RUMF |  | 447D1 | 576 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Troy McBride | Norwich Solar Technologies | RUMFORD CEDAR LN SOLAR LLC |  | 2000196337 | 30012847189 | Solar | [5 empty] | 44.5797 | -70.5776 | 24 CEDAR LANE |  |  | Rumford | 8 | RUMFORD | 447D1 | 447T3 | 12.47 | 9310-L0186-5020-0016-ED00019 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2020-12-30 | 2020-12-22 | 2020-12-30 | 2020-12-22 | 2020-12-30 | 2021-08-03 |  | 2021-08-17 |  | 2021-08-19 | 2021-08-19 | 2021-09-02 |  |  | 2021-08-30 |  |  | CS | 2021-08-31 | [6 empty] | CS |  |  | 2021-08-31 |  |  | 2023-06-29 | [11 empty] | 2023-07-13 | [8 empty] | 2023-09-15 | [5 empty] | 2021-09-10 |  |  | 2023-09-19 | [8 empty] | 2021-11-16 | [6 empty] | 2021-11-10 |  |  | 2023-11-02 | [5 empty] | 2021-11-10 |  |  | 2023-11-02 | [14 empty] | 2021-11-17 | [7 empty] | 2021-11-17 | [10 empty] | 2022-11-15 |  | 2022-11-15 | [7 empty] | 547830 | 2023-11-01 | 2023-12-19 | 2021-07-13: 2021-11-26; 2021-07-13: 2021-12-16 | [17 empty] | Requested | [11 empty] | TRUE | TRUE | 606 | 2021-11-26 | 2021-11-26 | 2021 | 2021 | 2021 |  |  |  | 2021-06-28 | Report
607 |  | Lanie Patterson | Brent Brooks | 2020-12-15 | 2023-03-29 | L2_Bump |  | 2023-12-08 | L2_Bump | [26 empty] | 5 - WINT |  | 256D2 | 348 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Troy McBride | Norwich Solar Technologies | WINTHROP BOONS TRAIL LLC |  | 2000196609 | 30012850639 | Solar | [5 empty] | 44.316 | -70.0006 | 324 Turkey Lane |  |  | Winthrop | 43.2 | WINTHROP | 256D2 | 256T1 | 12.47 | 9310-L0096-6450-0165-ED00074 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2020-12-30 | 2020-12-22 | 2020-12-30 | 2020-12-22 | 2020-12-30 | 2021-06-16 |  | 2021-07-01 |  | 2021-06-24 | 2021-06-24 | 2021-07-08 |  |  | 2021-06-28 |  |  | CS | 2021-06-29 | [6 empty] | CS |  |  | 2021-06-29 | [11 empty] | 2021-07-12 | [17 empty] | 2021-07-28 | [11 empty] | 2021-09-30 | [6 empty] | 2021-09-22 | [8 empty] | 2021-09-22 | [17 empty] | 2021-09-30 | [7 empty] | 2021-09-30 | [7 empty] | 2021-10-18 |  | 2021-11-24 | [8 empty] | 384941 | 2021-09-22 | 368441 | 2021-10-01 | 2024-01-22 | 2021-07-13: 2021-11-24; 2021-07-13: 2021-12-16 | [17 empty] | Requested | [11 empty] | TRUE | TRUE | 607 | 2021-11-24 | 2021-11-24 | 2021 | 2021 | 2021
608 |  | Lanie Patterson | KRISTOFER COLEMAN | 2020-12-15 | 2023-03-28 | L2_Bump | [29 empty] | 2 - MESS |  | 238D1 | 189 | Yes | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED |  | Nash Sultan | Norwich Solar Technologies | WISCASSET GARDINER SOLAR LLC |  | 2000196608 | 30012850605 | Solar | 975 | 0.975 | 1728 |  |  | 44.0249 | -69.6705 | 394 Gardiner RD |  |  | Wiscasset | 54 | MESSINA | 238D1 | 238T1 | 12.47 | 9310-L0068-6463-0041-ED00178 | Non-FERC | COST SHARING | COST SHARING (325,000) | 53481 | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2020-12-30 | 2020-12-22 | 2020-12-30 | 2020-12-22 | 2020-12-30 | 2021-01-11 |  | 2021-01-26 |  | 2021-01-11 | 2021-01-11 | 2021-01-26 |  |  | 2021-01-19 | 2023-12-14 | 2023-06-20 | CS | 2021-01-19 | [6 empty] | CS |  |  | 2021-01-19 | 2023-12-14 | 2023-06-22 | 2023-04-01 | [5 empty] | 2023-12-12 |  |  |  | 2023-12-22 |  | 2023-04-18 | [6 empty] | 2023-12-22 |  | 2023-04-24 | [5 empty] | 2021-01-21 | 2023-12-27 | 2023-07-19 | 2023-04-26 | [8 empty] | 2021-03-26 | 2024-02-08 | 2023-09-21 | 2021-06-17 | Report |  |  | 2021-06-17 | 2024-02-08 | 2023-09-11 | 2023-06-07 | [5 empty] | 2021-06-17 | 2024-02-08 | 2023-09-12 | 2023-06-09 | [6 empty] | 2024-02-16 | 2023-10-03 | [6 empty] | 2021-06-24 | 2024-02-21 | 2023-10-10 | [5 empty] | 2021-06-24 | 2024-02-21 | 2023-10-10 | [5 empty] | 2021-07-13 |  | 2021-07-13 | 2022-11-15 |  | 2022-11-15 | 2024-08-23 | 2024-08-23 |  |  |  | 461705 | 2021-05-28 | 572172 | 2024-02-08 |  | 2021-08-02 | 2021-08-02 | 2021-07-13 | 2021-07-13 | 2022-11-17 | 2022-11-17 | 2024-02-23 | 2024-02-26 | [13 empty] | Q4 2025 |  |  |  | Requested | [11 empty] | TRUE | TRUE | 608 | 2021-08-02 | 2021-08-02 | 2021 | 2021 | 2021
609 |  |  | Anthony Boucher | 2020-12-15 | [31 empty] | 3 - WALD |  | 252D1 | 191 |  | WITHDRAWN | WITHDRAWN |  | Emily Byrne | CITIZENS ENERGY CORPORATION | PORTAGE RIVER SOLAR LLC | 161 Old Augusta Rd Waldoboro | 2000200287 |  | Solar | [5 empty] | 44.1698 | -69.3252 | 161 Old Augusta Rd |  |  | Waldoboro |  | WALDOBORO | 252D1 |  |  | 9310-L0090-6130-0043-ED00002 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2020-12-22 | 2020-12-30 |  |  |  |  | 1900-01-12 | [57 empty] | Study performed | [69 empty] | 2021-12-21 | [25 empty] | STUDY - REFILLED AS PRJ 693 | [11 empty] | TRUE | TRUE | 609 | 0 | 0 | 1900 | #VALUE! | #VALUE! |  |  |  | 2021-06-17 | Report
610 |  | Marshall Ripley | Rick Duperre | 2020-12-17 | [31 empty] | 4 - FOHI |  | 624D2 | 255 |  | WITHDRAWN | WITHDRAWN |  | Emily Byrne | CITIZENS ENERGY CORPORATION | GORHAM LANDFILL SOLAR LLC | Public Works dr Gorham | 2000200302 | 30012896053 | Solar | [5 empty] | 43.7246 | -70.4525 | Public Works Dr |  |  | Gorham |  | FORT HILL | 624D2 |  |  | 9310-L0251-2240-0175-ED00006 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2020-12-24 | 2021-01-04 |  |  |  |  | 1900-01-12 | [57 empty] | No Study | [69 empty] | 2021-06-24 | [37 empty] | TRUE | TRUE | 610 | 0 | 0 | 1900 | #VALUE! | #VALUE!
611 |  | Eben Snow | Brent Brooks | 2020-12-17 | 2022-06-08 | L2_Bump |  | 2022-07-27 | L2_Bump |  | 2023-01-18 | L2_With |  | 2023-07-10 | L2_Bump |  | 2023-09-26 | wthdw |  | 2023-10-05 | L2_Bump |  | 2024-01-17 | L2_Bump |  | wthdw | [9 empty] | 8 - DEER |  | 412D3 | 442 |  | WITHDRAWN | WITHDRAWN |  | Emily Byrne | CITIZENS ENERGY CORPORATION | YOULAND SOLAR LLC | Airport Rd Turner | 2000200300 | 30012896046 | Solar | [5 empty] | 44.1885 | -70.2353 | Airport Rd |  |  | Turner | 07H | DEER RIPS | 412D3 | 412T4 | 12.47 | 9310-L0127-5880-0179-ED00039 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2020-01-04 | 2020-12-24 | 2021-01-04 | 2020-12-24 | 2020-01-04 | 2024-08-26 |  | 2024-09-10 | [127 empty] | 2024-08-28 | [37 empty] | TRUE | TRUE | 611 | 0 | 0 | 1900 | #VALUE! | #VALUE!
612 |  | Govinda Neupane |  | 2020-12-17 | 2022-11-08 | L2_Bump |  | 2023-01-09 | L2_bump |  | 2023-05-08 | L2_bump |  | 2023-07-18 | L2_Bump |  | 2023-10-05 | L2_Bump |  | 2024-10-14 | wthdw | [14 empty] | 15 - STUR |  | 858D4 | 510 |  | WITHDRAWN | WITHDRAWN |  | Emily Byrne | CITIZENS ENERGY CORPORATION | TITCOMB ROOST LLC | Titcomb Hill Rd Farmington | 2000200288 | 30012896020 | Solar | [5 empty] | 44.7031 | -70.12 | Titcomb Hill Rd |  |  | Farmington | 69 | STURTEVANT | 858D4 | 858T2 | 12.47 | 9310-L0441-2030-0150-ED00127 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2020-01-04 | 2020-12-24 | 2021-01-04 | 2020-12-24 | 2020-01-04 | 2024-10-14 | 2024-10-14 | 2024-10-29 | [127 empty] | 2024-10-15 | [37 empty] | TRUE | TRUE | 612 | 0 | 0 | 1900 | #VALUE! | #VALUE!
613 |  | Rigel Paradise | Rick Duperre | 2020-12-17 | [31 empty] | 7 - PRAT |  | 661D1 | 292 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN | 2022-06-27 | Tiffiny Chase | ASPEN POWER PARTNERS | ME I N. Berwick Valley LLC | OAKWOODS RD NORTH BERWICK | 2000228148 | 30013268815 | Solar | [5 empty] | 43.3251 | -70.7375 | OAKWOODS RD |  |  | North Berwick | 41 | PRATT & WHITNEY | 661D1 | 661T1 | 12.47 | 9310-L0334-4160-0077-ED00105 | Non-FERC | WITHDRAWN | WITHDRAWN | NONE | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2020-01-04 | 2020-12-24 | 2021-01-04 | 2020-12-24 | 2020-01-04 | 2021-01-20 |  | 2021-02-03 |  | 2021-01-20 | 2021-01-20 | 2021-02-03 |  |  | 2021-01-20 | 2021-08-16 |  | CS | 2021-01-20 | RS | 2021-08-16 |  |  |  |  | CS |  |  | 2021-01-20 | 2021-08-16 | [28 empty] | 2021-02-08 | 2021-08-25 | [10 empty] | 2021-04-13 | 2021-10-07 |  | 2021-06-21 | Report |  |  | 2021-06-21 | 2021-09-29 | [7 empty] | 2021-06-17 | 2021-09-29 | [16 empty] | 2021-06-24 | [7 empty] | 2021-06-24 | [10 empty] | 2023-03-03 |  | 2023-03-28 | 2023-08-04 | 2023-08-04 |  |  |  | 6613056 | 2025-05-28 | 1229905 | 2023-03-08 | 2023-11-01 | 2021-07-13: 2021-10-12; 2021-07-13: 2021-10-15; 2021-07-13: 2023-03-29; 2021-07-13: 2023-03-29 |  |  | 2023-08-28 | 2023-08-29 | [13 empty] | Requested | [11 empty] | TRUE | TRUE | 613 | 2021-10-12 | 2021-10-12 | 2021 | 2021 | 2021
614 |  | Ben Brooks | Anthony Boucher | 2020-12-21 | 2022-05-17 |  |  | 2022-09-28 | L2_Bump |  | 2023-03-20 | L2_Bump | [23 empty] | 4 - PAST |  | 239D6 | 555 |  | WITHDRAWN | WITHDRAWN |  | Greg Rosshirt | New Leaf Energy, Inc | 510 PV PROJECT DEVELOPMENT LLC | 78 West Meadown Rd | 2000113260 | 30012519457 | Solar/DC BESS | [5 empty] | 44.1144 | -69.1414 | 64 West Meadow Rd |  |  | Rockland | 58 | PARK STREET | 239D6 | 239T2 | 12.47 | 9310-L0070-4970-0222-ED00050 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2021-01-06 | 2020-12-29 | 2021-01-06 | 2020-12-29 | 2021-01-06 | 2021-10-27 | 2021-11-08 | 2021-11-10 | 2021-11-08 | 2021-11-12 | 2021-11-05 | 2021-11-22 |  |  | 2021-11-22 |  |  | CS | 2021-11-29 | [6 empty] | CS |  |  | 2021-11-29 |  |  | 2022-07-19 | 2023-03-08 | [15 empty] | 2021-12-10 | 2021-12-10 | [8 empty] | 2021-12-13 | [11 empty] | 2022-02-17 | [6 empty] | 2022-02-17 | [8 empty] | 2022-02-17 | [8 empty] | 2022-02-17 | [8 empty] | 2022-02-22 | [7 empty] | 2022-02-22 | [7 empty] | 2022-03-29 |  | 2022-03-29 | [12 empty] | 2023-08-03 | [37 empty] | TRUE | TRUE | 614 | 0 | 0 | 1900 | 1900 | 1900 |  |  |  | 2021-06-21 | Report
615 |  | Govinda Neupane |  | 2020-12-21 | [31 empty] | 6 - HART |  | 824D1 | 563 |  | WITHDRAWN | WITHDRAWN |  | Greg Rosshirt | BORREGO SOLAR SYSTEMS INC | 510 PV PROJECT DEVELOPMENT LLC | 1630 Canaan Rd SOLAR HARTLAND | 2000113260 | 30012612394 | Solar/DC BESS | [7 empty] | 1630 Canaan Rd |  |  | Hartland |  | HARTLAND | 824D1 |  |  | 9310-L0409-2540-0004-ED00045 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2020-12-29 | 2021-01-06 |  |  |  |  | 1900-01-12 |  | 2021-01-13 | 2021-01-13 | [124 empty] | 2021-01-28 | [37 empty] | TRUE | TRUE | 615 | 0 | 0 | 1900 | #VALUE! | #VALUE!
616 |  |  | Anthony Boucher | 2020-12-21 | [31 empty] | 4 - BUCK |  | 806D2 | 390 |  | WITHDRAWN | WITHDRAWN |  | Haley Orvedal | Galehead Development | FLYING MOOSE PVI LLC | 0 NORTH PENOBSCOT RD PENOBSCOT ME | 2000200431 | 30012898059 | Solar/DC BESS | [7 empty] | 0 NORTH PENOBSCOT RD |  |  | Penobscot |  | BUCKSPORT | 806D2 |  |  | 9310-L0386-4580-0066-ED00012 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2020-12-29 | 2021-01-06 |  |  |  |  | 1900-01-12 | [127 empty] | 2021-02-09 | [37 empty] | TRUE | TRUE | 616 | 0 | 0 | 1900 | #VALUE! | #VALUE!
617 |  |  | Anthony Boucher | 2020-12-21 | [31 empty] | 2 - LINC |  | 800D1 | 416 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Brent Buchberger | Summit Ridge Energy | Lincolnville PV, LLC | 51 Slab City Rd Lincolnville | 2000149310 | 30013891467 | Solar | [5 empty] | 44.2909 | -69.0321 | 51 Slab City Rd |  |  | Lincolnville | 505 | LINCOLNVILLE | 800D1 | 800T1 | 34.5 | 9310-L0378-3300-0085-ED00075 | Non-FERC | WITHDRAWN | WITHDRAWN | 375000 | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2021-01-06 | 2020-12-29 | 2021-01-06 | 2020-12-29 | 2021-01-06 | 2021-01-19 |  | 2021-02-02 |  | 2021-01-19 | 2021-01-19 | 2021-02-02 |  |  | 2021-01-26 | 2021-08-16 |  | CS | 2021-01-26 | RS | 2021-08-16 |  |  |  |  | CS |  |  | 2021-01-26 | 2021-08-16 | [28 empty] | 2021-02-04 | 2021-09-02 | [10 empty] | 2021-04-09 | 2021-10-18 |  | 2021-06-15 | Report |  |  | 2021-06-15 | 2021-10-18 | [7 empty] | 2021-06-15 | 2021-10-18 | [16 empty] | 2021-11-01 | [15 empty] | 2021-07-08 |  | 2022-01-18 | 2022-11-28 |  | 2022-12-12 | 2024-08-26 |  |  |  |  | 346624 | 2022-01-14 | 544895 | 2022-11-14 | 2024-10-09 | 2021-07-13: 2021-01-18; 2021-07-13: 2021-01-19; 2021-07-13: 2022-12-13; 2021-07-13: 2022-12-13 | [17 empty] | Requested | [11 empty] | TRUE | TRUE | 617 | 2021-01-18 | 2021-01-18 | 2021 | 2021 | 2021
618 |  | Lanie Patterson | Brent Brooks | 2020-12-21 | [31 empty] | 9 - DETR |  | 812D1 | 574 |  | WITHDRAWN | WITHDRAWN |  | Tyler Adkins | UGE USA INC | UGE USA INC | HARTLAND AVE PITTSFIELD | 2000142913 | 30012869076 | Solar | [5 empty] | 44.8052 | -69.3971 | Hartland Ave |  |  | Pittsfield |  | DETROIT | 812D1 |  |  | 9310-L0392-4650-0048-ED00011 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2020-12-29 | 2021-01-06 |  |  |  |  | 1900-01-12 | [127 empty] | 2021-11-18 | [37 empty] | TRUE | TRUE | 618 | 0 | 0 | 1900 | #VALUE! | #VALUE! |  |  |  | 2021-06-15 | Report
619 |  | Marshall Ripley | Rick Duperre | 2020-12-21 | [31 empty] | 2 - WSBR |  | 674D2 | 437 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Nathaniel Curtis | C2 ENERGY DEVELOPMENT LLC | C2 ENERGY DEVELOPMENT LLC | 98 Eleanor Ave Westbrook ME | 2000200909 | 30012904402 | Solar | [5 empty] | 43.6535 | -70.3865 | 98 Eleanor Ave |  |  | Westbrook |  | WESTBROOK | 674D2 | 674T2 | 12.47 | 9310-L0347-6320-0052-ED00003 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2021-01-06 | 2020-12-29 | 2021-01-06 | 2020-12-29 | 2021-01-06 | 2021-08-03 | 2021-07-14 | 2021-08-17 | 2021-07-26 | 2021-07-27 | 2021-07-28 | 2021-08-11 |  |  | 2021-08-10 | 2021-12-10 |  | CS | 2021-08-10 | RS | 2021-12-10 |  |  |  |  | CS |  |  | 2021-08-10 | 2021-12-10 | [18 empty] | 2021-08-23 | 2021-08-23 | 2022-01-07 | [7 empty] | 2021-08-24 | 2022-01-07 | [10 empty] | 2021-10-28 | 2022-02-22 | [5 empty] | 2021-10-21 | 2022-02-21 | [7 empty] | 2021-10-22 | 2022-02-21 | [16 empty] | 2021-10-27 | 2022-02-21 | [6 empty] | 2021-10-27 | 2022-02-24 | [6 empty] | 2022-05-05 |  | 2022-05-05 |  | 2022-05-26 | [10 empty] | 2024-10-31 | 2021-07-13: 2022-05-26; 2021-07-13: 2022-05-31 | [17 empty] | Requested | [11 empty] | TRUE | TRUE | 619 | 2022-05-26 | 2022-05-26 | 2022 | 2022 | 2022
620 |  | Marshall Ripley | Rick Duperre | 2020-12-21 | 2024-09-04 | wthdw | [27 empty] | 2 - PRCO | 600 | 2 - PRCO | 1 - PRCO | 647D3 | 600 | Yes | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED |  | David Kane | EDP RENEWABLES | ME Rocky Hill Solar, LLC | 1196 Methodist Rd Westbrook ME | 2000464751 | 30016532654 | Solar | 999 | 0.999 | 1.3478 |  |  | 43.7364 | -70.3565 | 1196 Methodist Rd | 1196 | Methodist Rd | Westbrook | 183H | PRIDES CORNER | 647D3 | 674T2 | 12.47 | 9310-L0306-6320-0131-ED00154 |  | TRIGGERING | TRIGGERING | 255000 | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2021-01-06 | 2020-12-29 | 2021-01-06 | 2020-12-29 | 2021-01-06 | 2022-07-20 | 2022-08-15 | 2022-08-03 | 2022-08-19 | 2022-08-19 | 2022-08-19 | 2022-09-02 |  |  | 2022-08-29 | 2023-01-12 |  | CS | 2022-08-29 | [6 empty] | CS |  |  | 2022-09-01 | 2023-01-12 |  | 2024-09-06 | [6 empty] | 2024-09-20 |  | 2022-09-15 | 2023-02-09 |  | 2024-09-20 | [5 empty] | 2022-09-21 |  |  | 2024-09-20 | [5 empty] | 2022-09-23 | 2023-02-09 |  | 2024-09-20 | [8 empty] | 2022-12-01 | 2023-03-24 | [5 empty] | 2022-12-01 | 2023-03-21 |  | 2024-11-26 | [5 empty] | 2022-12-05 | 2023-03-22 |  | 2024-11-26 | [5 empty] | 2022-12-20 | 2023-03-22 |  | 2024-01-08 | [5 empty] | 2022-12-21 | 2023-03-28 | [6 empty] | 2022-12-21 | [7 empty] | 2023-04-07 |  | 2023-04-07 | 2023-04-25 | 2023-04-27 | 2023-04-27 | [5 empty] | 583316 | 2023-04-21 | 728430 | 2024-11-22 |  | 2021-07-13: 2023-05-01; 2021-07-13: 2023-05-01; 2021-07-13: 2025-04-09; 2021-07-13: 2025-04-09 | [13 empty] | Q4 2025 | [15 empty] | FALSE | TRUE | 620 | 2023-05-01 | 2023-05-01 | 2023 | 2023 | 2023
621 |  | Govinda Neupane |  | 2020-12-21 | [31 empty] | 1 - NWVI |  | 836D1 |  |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Nathaniel Curtis | C2 ENERGY DEVELOPMENT LLC | ME New Vineyard Solar LLC | 1716 New Vineyard Rd New Vineyard | 2000200909 | 30012904188 | Solar | [5 empty] | 44.8078 | -70.117 | 1716 New Vineyard Rd New Vineyard |  |  | New Vineyard | 9 | NEW VINEYARD | 836D1 | 836T1 | 12.47 | 9310-L0417-4080-0011-ED00127 | Non-FERC | WITHDRAWN | WITHDRAWN | NONE | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2021-01-06 | 2020-12-29 | 2021-01-06 | 2020-12-29 | 2021-01-06 | 2021-01-20 |  | 2021-02-03 |  | 2021-01-20 | 2021-01-20 | 2021-02-03 |  |  | 2021-02-03 |  |  | CS | 2021-02-03 | [6 empty] | CS |  |  | 2021-02-03 | [29 empty] | 2021-02-08 | [11 empty] | 2021-04-13 |  |  | 2021-06-22 | Report |  |  | 2021-06-22 | [8 empty] | 2021-06-22 | [17 empty] | 2021-06-28 | [7 empty] | 2021-06-28 | [7 empty] | 2021-09-14 |  | 2021-09-17 | [8 empty] | 149353 |  |  |  | 2023-10-10 | 2021-07-13: 2021-10-12; 2021-07-13: 2021-10-18 | [17 empty] | Requested | [11 empty] | TRUE | TRUE | 621 | 2021-10-12 | 2021-10-12 | 2021 | 2021 | 2021
622 |  |  | Anthony Boucher | 2020-12-23 | [31 empty] | 1 - MARO |  | 234D1 |  |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Nate Niles | REVISION ENERGY INC | REVISION ENERGY INC | 475 MANKTOWN RD, WALDOBORO | 2800283645 | 30012911431 | Solar | [5 empty] | 44.1283 | -69.3079 | 475 MANKTOWN RD |  |  | Waldoboro | 20 | MANKTOWN ROAD | 234D1 | 234T1 | 12.47 | 9310-L0065-6130-0044-ED00022 | Non-FERC | WITHDRAWN | WITHDRAWN | NONE | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2021-01-08 | 2020-12-31 | 2021-01-08 | 2020-12-31 | 2021-01-08 | 2021-01-21 |  | 2021-02-04 |  | 2021-01-21 | 2021-01-22 | 2021-02-05 |  |  | 2021-02-05 | 2021-08-04 |  | CS | 2021-02-10 | RS | 2021-08-04 |  |  |  |  | CS |  |  | 2021-02-10 | 2021-08-04 | [28 empty] | 2021-02-17 | 2021-08-10 | [10 empty] | 2021-04-22 | 2021-09-22 |  | 2021-06-28 | Report |  |  | 2021-06-28 | 2021-09-22 | [7 empty] | 2021-06-28 | 2021-09-22 | [16 empty] | 2021-06-30 | 2021-09-27 | [6 empty] | 2021-06-30 | [18 empty] | 95319 | 2021-08-26 |  |  | 2023-09-20 | 2021-07-13: 2021-10-28; 2021-07-13: 2021-11-05 | [17 empty] | Requested | [11 empty] | TRUE | TRUE | 622 | 2021-10-28 | 2021-10-28 | 2021 | 2021 | 2021 |  |  |  | 2021-06-22 | Report
623 |  | Govinda Neupane |  | 2020-12-29 | [31 empty] | 8 - LVFA |  | 428D2 | 597 |  | WITHDRAWN | WITHDRAWN |  | Simon Courtney | SOLAR PROVIDER GROUP LLC | SOLAR PROVIDER GROUP LLC | GIBBS MILL RD LIVERMORE ME 04253 | 2000157464 | 30012899198 | Solar | [5 empty] | 44.4434 | -70.2023 | GIBBS MILL RD |  |  | Livermore | 3 | LIVERMORE FALLS | 428D2 | 428T1 | 12.47 | 9310-L0161-3340-0010-ED00046 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2021-01-13 | 2021-01-06 | 2021-01-13 | 2021-01-06 | 2021-01-13 | 2022-07-15 | 2022-07-27 | 2022-07-29 | 2022-08-08 | [126 empty] | 2022-08-04 | [37 empty] | TRUE | TRUE | 623 | 0 | 0 | 1900 | #VALUE! | #VALUE! |  |  |  | 2021-06-28 | Report
624 |  | Eben Snow | Brent Brooks | 2020-12-29 | [31 empty] | 1 - HIHY |  | 419D1 |  |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Simon Courtney | SOLAR PROVIDER GROUP LLC | ME WHITE PINE SOLAR LLC | 145 WARDS HILL RD WEST BALDWIN ME | 2000269739 | 30013976136 | Solar | [5 empty] | 43.8745 | -70.7706 | 145 WARDS HILL RD |  |  | West Baldwin | 9 | HIRAM HYDRO | 419D1 | 419T3 | 12.47 | 9310-L0136-2605-0023-ED00013 | Non-FERC | WITHDRAWN | WITHDRAWN | NONE | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2021-01-13 | 2021-01-06 | 2021-01-13 | 2021-01-06 | 2021-01-13 | 2021-01-25 |  | 2021-02-08 |  | 2021-01-25 | 2021-01-25 | 2021-02-08 |  |  | 2021-02-03 | 2021-08-16 |  | CS | 2021-02-03 | RS | 2021-08-16 |  |  |  |  | CS |  |  | 2021-02-03 | 2021-08-16 | [28 empty] | 2021-02-15 | 2021-08-23 | [10 empty] | 2021-04-20 | 2021-10-05 |  | 2021-06-28 | Report |  |  | 2021-06-28 | 2021-09-29 | [7 empty] | 2021-06-28 | 2021-09-29 | [16 empty] | 2021-06-30 | [7 empty] | 2021-06-30 | [7 empty] | 2021-11-11 |  | 2021-11-11 | [8 empty] | 592124 | 2021-09-22 |  |  | 2024-09-04 | 2021-07-13: 2021-12-09; 2021-07-13: 2021-12-19; 2021-07-13: 2022-06-14; 2021-07-13: 2000-06-14 | [17 empty] | Requested | [11 empty] | TRUE | TRUE | 624 | 2021-12-09 | 2021-12-09 | 2021 | 2021 | 2021
625 |  |  | Anthony Boucher | 2021-01-05 | [31 empty] | 11 - BEWE |  | 803D6 | 573 |  | WITHDRAWN | WITHDRAWN |  | Haley Orvedal | Galehead Development | BELFAST PV TWO LLC | 255 Belmont Ave Belfast | 2000200220 | 30012895246 | Solar | [5 empty] | 44.412 | -69.0676 | 256 Belmont Ave |  |  | Belfast | 124 | BELFAST WEST SIDE | 803D6 | 34.5 kV Bus | 34.5 | 9310-L0383-0430-0013-ED00034 | FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2021-01-20 | 2021-01-12 | 2021-01-20 | 2021-01-12 | 2021-01-20 | 2023-09-05 | 2023-09-11 | 2023-09-19 | 2023-09-13 | 2023-09-20 | 2023-09-20 | 2023-10-04 | [123 empty] | 2023-09-22 | [37 empty] | TRUE | TRUE | 625 | 0 | 0 | 1900 | #VALUE! | #VALUE! |  |  |  | 2021-06-28 | Report
626 |  | Marshall Ripley | Rick Duperre | 2021-01-07 | 2023-07-03 | L2_Bump | [29 empty] | 3 - DUNS |  | 617D3 | 78 | Yes | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED | 2021-11-08 | Mike Imoto | MEVS LLC AKA CENERGY | MEVS LLC | 22 W Beech Ridge Rd (Scarborough) | 2000141275 | 30012422322 | Solar | 1950 | 1.95 | 2622.62 |  |  | 43.5927 | -70.3959 | Cranberry Pines Rd |  |  | Scarborough | 18 | DUNSTAN | 617D3 | 617T1 | 12.47 | 9310-L0107-0240-0211-ED00090 |  | NOT IMPACTED | NOT IMPACTED | NONE | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2021-01-22 | 2021-01-14 | 2021-01-22 | 2021-01-14 | 2021-01-22 | 2021-01-29 |  | 2021-02-12 |  | 2021-01-29 | 2021-01-29 | 2021-02-12 |  |  | 2021-02-10 |  |  | CS | 2021-02-10 | [6 empty] | CS |  |  | 2021-02-10 |  |  | 2023-07-07 | [11 empty] | 2023-07-12 | [8 empty] | 2023-08-10 | [5 empty] | 2021-02-17 |  |  | 2023-08-10 | [8 empty] | 2021-04-22 |  |  | 2021-06-29 | Report |  |  | 2021-06-29 |  |  | 2023-11-02 | [5 empty] | 2021-06-29 | [17 empty] | 2021-07-07 | [7 empty] | 2021-07-07 | [10 empty] | 2023-11-30 |  | 2023-11-30 | [5 empty] | 685539 |  | 639306 | 2023-11-21 |  | 2021-07-13: 2021-07-07; 2021-07-13: 2021-07-07; 2021-07-13: 2021-12-01; 2021-07-13: 2023-12-04 | [17 empty] | 10300804610 | [11 empty] | TRUE | TRUE | 626 | 2021-07-07 | 2021-07-07 | 2021 | 2021 | 2021
627 |  | Lanie Patterson |  | 2021-01-07 | [31 empty] | 5 - CONY |  | 216D2 | 559 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Ben Vanderlan | Bluewave MA, LLC | BWC TOGUS POND LLC | 0 BEECH STREET CHELSEA ME 04330 | 2000204737 | 30012952963 | Solar | [5 empty] | 44.2928 | -69.7698 | 0 Beech St |  |  | Chelsea | 69 | CONY ROAD | 216D2 | 216T1 | 34.5 | 9310-L0044-1110-0051-ED00120 | Non-FERC | WITHDRAWN | WITHDRAWN | 325000 | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2021-01-22 | 2021-01-14 | 2021-01-22 | 2021-01-14 | 2021-01-22 | 2021-02-15 |  | 2021-03-01 |  | 2021-02-15 | 2021-02-15 | 2021-03-01 |  |  | 2021-02-16 | 2021-08-16 |  | CS | 2021-02-16 | RS | 2021-08-16 |  |  |  |  | CS |  |  | 2021-02-16 | 2021-08-16 | [10 empty] | 2021-02-23 | [17 empty] | 2021-02-25 | 2021-08-23 | [10 empty] | 2021-04-30 | 2021-10-05 |  | 2021-06-24 | Report |  |  | 2021-06-24 | 2021-10-05 | [7 empty] | 2021-06-24 | 2021-10-05 | [16 empty] | 2021-10-21 | [7 empty] | 2021-10-22 | [18 empty] | 159147 | 2021-06-24 | 314417 | 2022-08-22 | 2025-01-30 | 2021-07-13: 2021-10-26; 2021-07-13: 2021-10-27; 2022-09-22: 2024-09-10 |  |  | 2024-09-10 | 2024-09-10 | [13 empty] | Requested | [11 empty] | TRUE | TRUE | 627 | 2021-10-26 | 2021-10-26 | 2021 | 2021 | 2021 |  |  |  | 2021-06-29 | Report
628 |  |  | Anthony Boucher | 2021-01-13 | 2024-10-09 | wthdw | [29 empty] | 6 - THCR |  | 246D3 | 471 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Gary LaPlante | Maine Department of Corrections | MAINE STATE PRISON | Solar Farm | 2800367676 | 30012953730 | Solar | [5 empty] | 44.0684 | -69.2331 | 475 Cushing Rd |  |  | Warren | 124 | THOMASTON CREEK | 246D3 | 246T1 | 12.47 | 9310-L0083-6160-0036-ED00032 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2021-01-28 | 2021-01-21 | 2021-01-28 | 2021-01-21 | 2021-01-28 | 2022-01-18 | 2022-01-26 | 2022-02-01 | 2022-01-26 | 2022-02-03 | 2022-02-03 | 2022-02-17 |  |  | 2022-02-03 |  |  | CS | 2022-02-03 | [6 empty] | CS |  |  | 2022-02-03 |  |  | 2024-10-09 | [16 empty] | 2022-02-11 | 2022-02-11 | [8 empty] | 2022-02-16 | [11 empty] | 2022-04-22 | [6 empty] | 2022-04-25 | [8 empty] | 2022-06-01 | [8 empty] | 2022-06-01 | [8 empty] | 2022-06-07 | [7 empty] | 2022-06-07 | [7 empty] | 2022-06-16 |  | 2022-06-16 | 2022-06-16 | 2022-06-22 |  | 2022-02-07 | 2022-02-14 |  |  |  | 305783 | 2022-04-25 | 220247 | 2023-03-27 | 2024-10-29 | 2021-07-13: 2022-07-14; 2021-07-13: 2022-07-15; 2021-07-13: 2023-04-20; 2021-07-13: 2023-04-20 | [17 empty] | Requested | [11 empty] | TRUE | TRUE | 628 | 2022-07-14 | 2022-07-14 | 2022 | 2022 | 2022 |  |  |  | 2021-06-24 | Report
629 |  | Eben Snow | Brent Brooks | 2021-01-13 | [31 empty] | 3 - BRID |  | 406D1 | 171 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Ryan Bailey | BORREGO SOLAR SYSTEMS INC | 510 PV PROJECT DEVELOPMENT LLC | 61 Chadburn Hill Rd Bridgeton | 2000113260 | 30012744097 | Solar | [5 empty] | 44.0987 | -70.7055 | 61 Chadburn Hill Rd |  |  | Bridgton | 12 | BRIDGTON | 406D1 | 406T1 | 12.47 | 9310-L0118-0690-0017-ED00005 | Non-FERC | WITHDRAWN | WITHDRAWN | NONE | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2021-01-28 | 2021-01-21 | 2021-01-28 | 2021-01-21 | 2021-01-28 | 2020-02-10 |  | 2020-02-25 |  | 2020-02-10 | 2021-02-15 | 2021-03-01 |  |  | 2021-02-16 | 2021-08-16 |  | CS | 2021-02-16 | RS | 2021-08-16 |  |  |  |  | CS |  |  | 2021-02-16 | 2021-08-16 | [28 empty] | 2021-03-05 | 2021-08-19 | [10 empty] | 2021-05-10 | 2021-10-01 |  | 2021-06-28 | Report |  |  | 2021-06-28 | 2021-09-20 | [7 empty] | 2021-06-28 | 2021-09-20 | [16 empty] | 2021-07-01 | 2021-09-22 | [6 empty] | 2021-07-01 | 2021-09-22 | [17 empty] | 394340 | 2021-09-07 |  |  | 2023-04-20 | 2021-07-13: 2021-10-12; 2021-07-13: 2021-10-15 | [17 empty] | Requested | [11 empty] | TRUE | TRUE | 629 | 2021-10-12 | 2021-10-12 | 2021 | 2021 | 2021
630 |  | Lanie Patterson | KRISTOFER COLEMAN | 2021-01-25 | 2022-12-08 | L2_Bump | [29 empty] | 1 - BATH |  | 261D3 |  |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Troy McBride | Norwich Solar Technologies | WEST BATH TONAL SOLAR LLC | 13 TONAL LANE | 2000205316 | 30012960842 | Solar | [5 empty] | 43.918 | -69.8486 | 13 TONAL LANE |  |  | West Bath | 6 | BATH 34 | 261D3 | 261T2 | 12.47 | 9310-L0099-6280-0048-ED00015 | Non-FERC | WITHDRAWN | WITHDRAWN | NONE | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2021-02-01 | 2021-02-01 | 2021-02-08 | 2021-01-25 | 2021-02-01 | 2021-02-15 |  | 2021-03-01 |  | 2021-02-15 | 2021-02-15 | 2021-03-01 |  |  | 2021-02-16 | 2021-08-16 | 2023-02-28 | CS | 2021-03-01 | RS | 2021-08-16 | FAC | 2023-02-28 |  |  | CS |  |  | 2021-03-01 | 2021-08-16 | 2023-03-02 | 2022-12-13 | [11 empty] | 2022-12-22 | [14 empty] | 2021-03-12 | 2021-08-23 | 2023-05-10 | 2022-12-29 | [8 empty] | 2021-05-17 | 2021-10-05 | 2023-07-17 | 2021-07-12 | Report |  |  | 2021-07-12 | 2021-10-05 | 2023-06-16 | 2023-02-13 | [5 empty] | 2021-07-12 | 2021-10-05 | 2023-07-05 | 2023-02-13 | [7 empty] | 2023-08-01 | [6 empty] | 2021-07-21 | 2021-11-02 | 2023-08-03 | [5 empty] | 2021-07-21 | 2021-11-02 | 2023-08-03 | [5 empty] | 2021-10-27 |  | 2021-10-28 | 2022-11-15 |  | 2022-11-15 | [7 empty] | 620924 | 2023-06-13 | 2024-07-26 | 2021-07-13: 2021-10-28; 2021-07-13: 2021-11-29; 2022-09-22: 2023-10-12; 2022-09-22: 2023-10-12 | [17 empty] | Requested | [11 empty] | TRUE | TRUE | 630 | 2021-10-28 | 2021-10-28 | 2021 | 2021 | 2021 |  |  |  | 2021-06-28 | Report
631 |  | Marshall Ripley | Rick Duperre | 2021-01-25 | 2023-07-03 | L2_Bump |  | 2026-05-22 | L2_with | [26 empty] | 4 - DUNS | 1 - DUNS | 617D2 | 626 | Yes | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED |  | Nash Sultan | Bridge Energy | West Scarborough Solar 1 LLC | 720 US Route 1 Scarborough | 2000495960 | 30012744071 | Solar | 999 | 0.999 | 1728 |  |  | 43.5624 | -70.3984 | 720 US Rt 1 |  |  | Scarborough | 273 | DUNSTAN | 617D2 | 617T1 | 12.47 | 9310-L0231-5200-0127-ED00302 | Non-FERC | NOT IMPACTED | NOT IMPACTED |  | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2021-02-08 | 2021-02-01 | 2021-02-08 | 2021-02-01 | 2021-02-08 | 2021-07-14 |  | 2021-07-28 |  | 2021-07-28 | 2021-07-29 | 2021-08-11 |  |  | 2021-08-10 |  |  | CS | 2021-08-10 | [6 empty] | CS |  |  | 2021-08-10 |  |  | 2023-08-22 | [11 empty] | 2024-09-09 | [14 empty] | 2021-08-20 |  |  | 2024-09-10 | [8 empty] | 2021-10-26 | [6 empty] | 2021-10-26 |  |  | 2024-11-11 | [5 empty] | 2021-10-27 |  |  | 2024-11-11 | [30 empty] | 2021-11-21 |  | 2021-11-11 | 2022-11-09 |  | 2022-12-30 | 2025-06-10 | 2025-06-10 |  |  |  | 132545 | 2021-10-25 | 191458 | 2024-11-13 |  | 2021-11-11 | 2021-11-23 | 2023-01-05 | 2023-01-06 | 2024-11-26 | 2024-11-26 | [15 empty] | Q3 2026 |  |  |  | Requested | [11 empty] | FALSE | TRUE | 631 | 2021-11-11 | 2021-11-11 | 2021 | 2021 | 2021 |  |  |  | 2021-07-12 | Report
632 |  | Govinda Neupane |  | 2021-01-26 | [31 empty] | 4 - ANSO |  | 801D1 | 313 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Shalin Soni | Nexamp, Inc | NEXAMP SOLAR LLC | 52 LYNES RD STARK | 2000114877 | 30012963903 | Solar | [5 empty] | 44.7489 | -69.9064 | 52 Lynds Road |  |  | Starks | 15 | ANSON | 801D1 | 801T1 | 12.47 | 9310-L0379-5510-0017-ED00008 | Non-FERC | WITHDRAWN | WITHDRAWN | NONE | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2021-02-09 | 2021-02-02 | 2021-02-09 | 2021-02-02 | 2021-02-09 | 2021-02-17 |  | 2021-03-03 |  | 2021-02-17 | 2021-02-18 | 2021-03-03 |  |  | 2021-03-02 |  |  | CS | 2021-03-02 | [6 empty] | CS |  |  | 2021-03-02 | [29 empty] | 2021-03-10 | [11 empty] | 2021-05-13 |  |  | 2021-07-12 | Report |  |  | 2021-07-12 | [8 empty] | 2021-07-12 | [17 empty] | 2021-07-13 | [7 empty] | 2021-07-13 | [7 empty] | 2021-08-05 |  | 2021-08-05 | [8 empty] | 1803728 | 2021-07-06 | 2900881 | 2023-03-20 | 2023-08-18 | 2021-07-13: 2021-09-01; 2021-07-13: 2021-09-14 | [17 empty] | Requested | [11 empty] | TRUE | TRUE | 632 | 2021-09-01 | 2021-09-01 | 2021 | 2021 | 2021
633 |  | Rigel Paradise | Rick Duperre | 2021-01-27 | 2023-03-28 | wthdw |  | 2023-04-18 | L2_Bump | [26 empty] | 3 - SASW |  | 657D3 | 483 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Simon Courtney | SOLAR PROVIDER GROUP LLC | ME WHITE PINE SOLAR LLC | 208 Grammar Rd Sanford | 2000269739 | 30013976169 | Solar | [5 empty] | 43.4502 | -70.7482 | 208 Grammar Rd |  |  | Sanford | 39.03 | SANFORD SWITCH | 657D3 | 657T1 | 12.47 | 9310-L0320-5170-0130-ED00108 | Non-FERC | WITHDRAWN | WITHDRAWN | NONE | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2021-02-10 | 2021-02-03 | 2021-02-10 | 2021-02-03 | 2021-02-10 | 2021-02-17 |  | 2021-03-03 |  | 2021-02-17 | 2021-02-19 | 2021-03-05 |  |  | 2021-03-05 |  |  | CS | 2021-03-01 | [6 empty] | CS |  |  | 2021-03-01 | 2022-10-10 |  | 2023-04-04 | [9 empty] | 2022-10-25 | [10 empty] | 2023-04-27 | [5 empty] | 2021-03-03 | 2022-10-28 |  | 2023-05-02 | [8 empty] | 2021-05-06 | 2022-12-14 |  | 2021-06-30 | Report |  |  | 2021-06-30 | 2022-12-12 |  | 2023-06-09 | [5 empty] | 2021-06-30 | 2022-12-13 |  | 2023-06-12 | [6 empty] | N/A | [7 empty] | 2021-07-07 | N/A | [6 empty] | 2021-07-07 | [7 empty] | 2021-07-08 |  | 2021-07-08 | 2022-12-13 | 2021-07-20 | 2022-06-30 | [5 empty] | 725823 |  | 1123154 | 2023-06-09 | 2024-09-04 | 2021-07-20 | 2021-07-20 | 2022-06-30 | 2022-07-05 | 2022-12-14 | 2022-12-15 | 2023-07-31 | [18 empty] | 10300806404 | [11 empty] | TRUE | TRUE | 633 | 2021-07-20 | 2021-07-20 | 2021 | 2021 | 2021 |  |  |  | 2021-07-12 | Report
634 |  | Lanie Patterson | Brent Brooks | 2021-01-27 | [31 empty] | 4 - RICH |  | 240D1 | 449 |  | WITHDRAWN | WITHDRAWN |  | Shalin Soni | Nexamp, Inc | NEXAMP SOLAR LLC | 590 LINCOLN ST RICHMOND | 2000114877 | 30012931157 | Solar | [7 empty] | 590 Lincoln St |  |  | Richmond | 10 | RICHMOND | 240D1 |  |  |  |  | WITHDRAWN | WITHDRAWN | [8 empty] | 2021-02-03 | 2021-02-10 |  |  |  |  | 1900-01-12 | [123 empty] | n/a | n/a | n/a | n/a | 2021-02-05 | [37 empty] | TRUE | TRUE | 634 | 0 | 0 | 1900 | #VALUE! | #VALUE! |  |  |  | 2021-06-30 | Report
635 |  | Govinda Neupane |  | 2021-01-29 | 2022-07-28 | L2_Bump |  | 2023-03-06 | L2_Bump |  | 2023-01-09 | wthdw | [23 empty] | 4 - PHST |  | 841D1 | 571 |  | WITHDRAWN | WITHDRAWN |  | Christian L'Oranger | NBD SOLAR MAINE LLC | Rangeley Rd Solar LLC | Rangeley Rd Avon | 2000174932 | 30012557200 | Solar | [5 empty] | 44.801 | -70.2693 | 0 Rangley Rd |  |  | Avon | 54 | PHILLIPS/STRONG | 841D1 | 841T1 | 12.47 | 9310-L0424-0260-0012-ED00140 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2021-02-12 | 2021-02-05 | 2021-02-12 | 2021-02-05 | 2021-02-12 | 2022-01-24 | 2022-02-04 | 2022-02-07 | 2022-02-04 | 2022-02-08 | 2022-02-08 | 2022-02-22 |  |  | 2022-02-15 |  |  | CS | 2022-02-15 | [6 empty] | CS |  |  | 2022-02-15 | 2022-07-14 |  | 2022-11-10 | [11 empty] | 2023-01-09 |  |  |  |  | 2022-03-07 | 2022-03-07 |  |  | 2023-01-09 | [5 empty] | 2022-03-07 | 2022-07-15 |  | 2023-01-13 | [8 empty] | 2022-05-10 | 2023-08-26 | [5 empty] | 2022-05-02 | [8 empty] | 2022-05-02 | [8 empty] | 2022-05-02 | [8 empty] | 2022-05-04 | [7 empty] | 2022-05-04 | [13 empty] | 2022-02-07 | 2022-02-14 | [7 empty] | 2024-02-22 | [37 empty] | TRUE | TRUE | 635 | 0 | 0 | 1900 | 1900 | 1900
636 |  | Marshall Ripley | Rick Duperre | 2021-02-02 | [31 empty] | 3 - PRCO |  | 647D2 | 620 |  | WITHDRAWN | WITHDRAWN |  | Glenn Walker | Walker Capital LLC | ACADIA ENERGY LLC | 20 Hereford Ln | 2000207294 | 30012986995 | Solar | [5 empty] | 43.7142 | -70.3873 | 20 Hereford Ln |  |  | Windham | 37.1 | PRIDES CORNER | 647D2 | 647T2 | 12.47 | 9310-L0305-6390-0100-ED00473 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2021-02-16 | 2021-02-09 | 2021-02-17 | 2021-02-10 | 2021-02-16 | 2022-01-20 | 2022-01-20 | 2022-01-20 | 2023-05-05 | 2023-05-05 | 2023-05-05 | 2023-05-19 |  |  | 2023-05-19 |  |  | CS | [7 empty] | CS |  |  | 2023-05-19 | [11 empty] | 2022-01-27 | [8 empty] | 2023-06-14 | [8 empty] | 2023-06-15 | [11 empty] | 2023-08-21 | [6 empty] | 2023-08-23 | [8 empty] | 2023-08-23 | [8 empty] | 2023-08-24 | [8 empty] | 2023-09-06 | [26 empty] | 1421374 | 2023-08-22 |  |  | 2023-09-28 | [37 empty] | TRUE | TRUE | 636 | 0 | 0 | 1900 | 1900 | 1900
637 |  | Marshall Ripley | Rick Duperre | 2021-02-02 | [31 empty] | 1 - CAEL | 1 - CAEL | 613D1 |  |  | EXECUTED | EXECUTED |  | Spencer Egan | Encore Redevelopment, LLC | ER CAPE LAND FILL SOLAR LLC | 21 Dennison Dr Cape Elizabeth | 2000199067 | 30012881360 | Solar | 900 | 0.9 | 1238 |  |  | 43.5867 | -70.2415 | 21 Dennison Dr |  |  | Cape Elizabeth | 5 | CAPE ELIZABETH | 613D1 | 613T1 |  |  | Non-FERC | GFOV TBD During Study Phase | T-GFOV TBD During Study Phase | NONE | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2021-02-16 | 2021-02-09 | 2021-02-17 | 2021-02-09 | 2021-02-16 | 2021-02-22 |  | 2021-03-08 |  | 2021-02-22 | 2021-02-23 | 2021-03-08 |  |  | 2021-03-01 |  |  | CS | 2021-03-01 | [6 empty] | CS |  |  | 2021-03-01 | [29 empty] | 2021-03-09 | [11 empty] | 2021-05-12 |  |  | 2021-06-29 | Report |  |  | 2021-06-29 | [8 empty] | 2021-06-29 | [17 empty] | 2021-07-02 | [7 empty] | 2021-07-02 | [7 empty] | 2021-07-22 |  | 2021-07-22 | 2022-09-07 | 2021-07-28 |  | 2025-06-10 | 2025-06-10 |  |  |  | 54853 |  |  |  |  | 2021-07-13: 2021-07-29; 2021-07-13: 2021-07-29; 2021-07-13: 2022-09-12; 2021-07-13: 2022-09-13 |  |  | 2025-07-24 | 2025-07-24 | [9 empty] | Q4 2025 |  |  |  | Requested | [11 empty] | TRUE | TRUE | 637 | 2021-07-29 | 2021-07-29 | 2021 | 2021 | 2021
638 |  | Govinda Neupane |  | 2021-02-03 | 2023-04-07 | L2_Bump |  | 2023-07-17 | wthdw |  | 2023-08-14 | L2_bump |  | 2023-09-14 | L2_Bump |  | 2023-01-19 | wthdw | [17 empty] | 10 - NEWP |  | 837D1 | 536 |  | WITHDRAWN | WITHDRAWN |  | John Rush | GL Investment LLC | NEWPORT SOLAR ENERGY | 59 SOUTH ST / NEWPORT | 2000206304 | 30012973753 | Solar | [5 empty] | 44.8339 | -69.2829 | 59 South St |  |  | Newport | 3 | NEWPORT | 837D1 | 837T1 | 12.47 | 9310-L0418-4125-0091-ED00010 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2021-02-17 | 2021-02-10 | 2021-02-18 | 2021-02-10 | 2021-02-17 | 2022-06-17 | 2022-07-27 | 2022-07-05 | 2022-08-02 | 2022-08-02 | 2022-08-02 | 2022-08-16 |  |  | 2022-08-03 |  | 2023-02-01 | CS | 2022-08-03 | FAC | 2023-02-01 |  |  |  |  | CS |  |  | 2022-08-05 | 2022-11-11 | 2023-02-20 | 2024-01-24 | [8 empty] | 2022-08-11 | 2022-11-21 | 2023-02-17 | 2024-02-12 | [5 empty] | 2022-08-11 | 2022-11-30 |  | 2024-03-20 | [5 empty] | 2022-08-11 | 2022-11-30 | 2023-02-22 | 2024-03-21 | [8 empty] | 2022-10-13 | 2022-01-13 | 2023-04-27 |  |  |  |  | 2022-10-13 | 2023-01-12 |  | 2024-05-17 | [5 empty] | 2022-10-18 | 2023-01-16 |  | 2024-05-17 | [5 empty] | 2022-10-28 | 2023-01-18 |  | 2024-06-03 | [5 empty] | 2022-10-28 | 2023-01-23 |  | 2024-06-06 |  |  |  |  | 2022-10-28 | 2023-01-23 |  | 2024-06-06 | [15 empty] | 3041046 | 2022-10-14 | 3273330 | 2024-05-13 | 2024-07-31 | [37 empty] | TRUE | TRUE | 638 | 0 | 0 | 1900 | #VALUE! | #VALUE! |  |  |  | 2021-06-29 | Report
639 |  | Marshall Ripley | Rick Duperre | 2021-02-11 | [31 empty] | 1 - NOWI |  | 639D2 |  |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Geoffrey Sparrow | GREEN LANTERN DEVELOPMENT LLC | GREEN LANTERN DEVELOPMENT LLC | 994 ROOSEVELT TRL / WINDHAM | 2000197005 | 30012980758 | Solar | [5 empty] | 43.8591 | -70.4578 | 994 Roosevelt Trail |  |  | Windham | 345 | NORTH WINDHAM | 639D2 | 639T2 | 12.47 | 9310-L0276-6390-0101-ED00545 | FERC | WITHDRAWN | WITHDRAWN | NONE | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2021-02-26 | 2021-02-19 | 2021-02-26 | 2021-02-19 | 2021-02-26 | 2021-02-26 |  | 2021-03-12 |  | 2021-03-02 | 2021-03-02 | 2021-03-16 |  |  | 2021-03-02 | 2021-08-06 |  | CS | 2021-03-02 | RS | 2021-08-06 |  |  |  |  | CS |  |  | 2021-03-02 | 2021-08-06 | [28 empty] | 2021-03-03 | 2021-08-18 | [10 empty] | 2021-05-06 | 2021-09-30 |  | 2021-06-18 | Report |  |  | 2021-06-18 | 2021-09-29 | [7 empty] | 2021-06-18 | 2021-09-29 | [16 empty] | 2021-06-24 | 2021-10-04 | [6 empty] | 2021-06-24 | [7 empty] | 2021-10-12 | 2021-10-12 | 2021-10-14 |  | 2021-10-18 | [6 empty] | 39353 |  |  |  | 2022-08-31 | 2021-07-13: 2021-10-20; 2021-07-13: 2021-10-20 | [17 empty] | Requested | [11 empty] | TRUE | TRUE | 639 | 2021-10-20 | 2021-10-20 | 2021 | 2021 | 2021 |  |  | 44481
640 |  | Lanie Patterson | KRISTOFER COLEMAN | 2021-02-02 | 2023-04-05 | L2_Bump | [29 empty] | 3 - LSFA |  | 232D2 | 558 | Yes | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Martha Staskus | Norwich Solar Technologies | Pinkham Brook GLC Solar, LLC | 360 PINKHAM BROOK RD / DURHAM | 2000197005 | 30012983091 | Solar | [5 empty] | 43.9682 | -70.0609 | 360 Pinkham Brook Rd |  |  | Durham | 84S | LISBON FALLS | 232D2 | 232T2 |  | 9310-L0062-1680-0082-ED00301 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2021-02-16 | 2021-02-09 | 2021-03-01 | 2021-02-09 | 2021-02-16 | 2021-07-08 | 2021-07-08 | 2021-07-22 | 2021-07-12 | 2021-07-19 | 2021-07-19 | 2021-08-02 |  |  | 2021-07-21 | 2021-10-26 |  | CS | 2021-07-23 | RS | 2021-10-26 |  |  |  |  | CS |  |  | 2021-07-23 | 2021-10-26 | [10 empty] | 2021-07-26 | [7 empty] | 2021-07-26 | 2021-07-26 | 2021-10-22 | [7 empty] | 2021-07-28 | 2021-10-28 |  | 2023-05-04 | [8 empty] | 2021-09-30 | 2021-12-13 | [5 empty] | 2021-09-29 | 2021-12-10 |  | 2023-06-16 | [5 empty] | 2021-09-29 | 2021-12-13 |  | 2023-06-16 |  |  |  | 2021-12-13 | [10 empty] | 2021-10-07 | 2021-12-10 | [6 empty] | 2021-10-07 | 2021-12-10 | [6 empty] | 2022-01-12 |  | 2022-01-13 |  | 2022-01-13 | [10 empty] | 2025-11-06 | 2021-07-13: 2022-01-13; 2021-07-13: 2022-01-17 | [13 empty] | Q4 2022 |  |  |  | Requested | [11 empty] | TRUE | TRUE | 640 | 2022-01-13 | 2022-01-13 | 2022 | 2022 | 2022 |  |  |  | 2021-06-18 | Report
641 |  |  | Anthony Boucher | 2021-02-15 |  | L2_Bump | [29 empty] | 5 - SEAR |  | 850D2 | 399 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Katie Kearney | SolAmerica Energy | SOL AMERICA ENERGY LLC | Old Rte 1 Searsport | 2000209571 | 30013014938 | Solar | [5 empty] | 44.4652 | -68.9048 | Old Rte 1 |  |  | Searsport |  | SEARSPORT | 850D2 | 850T1 |  | PENDING POI ATTESTATION | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2021-03-01 | 2021-02-22 | 2021-03-01 | 2021-02-22 | 2021-03-01 | 2021-03-01 |  | 2021-03-15 |  | 2021-03-10 | 2021-03-23 | 2021-03-24 |  |  | 2021-03-24 | 2021-08-16 |  | CS | 2021-03-24 | RS | 2021-08-16 |  |  |  |  | CS |  |  | 2021-03-24 | 2021-08-16 | [28 empty] | 2021-04-13 | 2021-08-31 | [10 empty] | 2021-06-10 | 2021-10-14 |  | 2021-07-15 | Report |  |  | 2021-07-14 | 2021-10-15 | [7 empty] | 2021-07-15 | 2021-10-15 | [16 empty] | 2021-07-16 | 2021-10-20 | [6 empty] | 2021-07-16 | [7 empty] | 2021-11-12 |  | 2021-11-12 |  | 2021-12-13 | [10 empty] | 2023-01-10 | 2021-07-13: 2021-12-21; 2021-07-13: 2021-12-30 | [17 empty] | Requested | [11 empty] | TRUE | TRUE | 641 | 2021-12-21 | 2021-12-21 | 2021 | 2021 | 2021
642 |  |  | KRISTOFER COLEMAN | 2021-02-15 | 2023-10-13 | L2_Bump | [29 empty] | 3 - DAMS |  | 219D2 | 359 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Troy McBride | Norwich Solar Technologies | NEWCASTLE ROUTE ONE SOLAR LLC | ROUTE 1, NEWCASTLE | 2000208824 | 30013005167 | Solar | [5 empty] | 44.0239 | -69.5717 | Route 1 |  |  | Newcastle | 27 | DAMARISCOTTA MILLS | 219D2 | 219T1 | 12.47 | 9310-L0051-4100-0074-ED00042 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2021-03-01 | 2021-02-22 | 2021-03-01 | 2021-02-22 | 2021-03-01 | 2021-03-01 |  | 2021-03-15 |  | 2021-03-15 | 2021-03-24 | 2021-03-29 |  |  | 2021-03-24 | 2021-08-16 |  | CS | 2021-03-24 | RS | 2021-08-16 |  |  |  |  | CS |  |  | 2021-03-24 | 2021-08-16 | [28 empty] | 2021-03-29 | 2021-08-23 | [10 empty] | 2021-06-17 | 2021-10-05 |  | 2021-06-28 | Report |  |  | 2021-06-28 | 2021-10-05 | [7 empty] | 2021-06-28 | 2021-10-05 | [16 empty] | 2021-07-01 | 2021-10-12 | [6 empty] | 2021-07-01 | 2021-10-12 | [6 empty] | 2021-10-27 |  | 2021-10-27 |  | 2021-11-24 | [6 empty] | 145396 |  | 145396 | 2021-10-05 | 2024-04-08 | 2021-07-13: 2021-11-29; 2021-07-13: 2021-11-29 | [17 empty] | Requested | [11 empty] | TRUE | TRUE | 642 | 2021-11-29 | 2021-11-29 | 2021 | 2021 | 2021 |  |  |  | 2021-07-15 | Report
643 |  |  | KRISTOFER COLEMAN | 2021-02-15 | 2023-04-05 | L2_Bump | [29 empty] | 4 - LSFA |  | 232D2 | 640 | Yes | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Jack Green | Norwich Solar Technologies | TOPSHAM LEWISTON SOLAR LLC | 571 LEWISTON RD TOPSHAM | 2000208123 | 30012997281 | Solar | [5 empty] | 43.9608 | -70.0096 | 571 Lewiston Rd |  |  | Topsham | 07 | LISBON FALLS | 232D2 | 232T2 | 12.47 | PENDING POI ATTESTATION | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2021-03-01 | 2021-02-22 | 2021-03-01 | 2021-02-22 | 2021-03-04 | 2022-01-18 | 2022-01-26 | 2022-02-01 | 2022-01-26 | 2022-01-28 | 2022-01-28 | 2022-02-11 |  |  | 2022-01-31 |  |  | CS | 2022-01-31 | [6 empty] | CS |  |  | 2022-01-31 |  | 2022-07-06 | 2023-07-14 | [8 empty] | 2022-02-02 |  | 2022-07-25 | 2023-07-21 |  |  |  |  | 2022-01-31 | 2022-01-31 |  |  | 2023-07-25 | [5 empty] | 2022-02-02 |  | 2022-07-28 | 2023-08-11 | [8 empty] | 2022-04-06 |  | 2022-09-30 |  |  |  |  | 2022-04-14 |  | 2022-10-07 | 2023-09-26 | [5 empty] | 2022-04-14 |  | 2022-10-07 | 2023-10-10 | [5 empty] | 2022-04-14 |  | 2022-10-07 | 2023-10-12 | [5 empty] | 2022-04-21 |  | 2022-10-13 | 2023-10-16 |  |  |  |  | 2022-04-21 | 2022-10-20 |  | 2023-10-16 |  |  |  |  | 2022-11-03 |  | 2022-11-03 | 2022-11-15 | 2022-11-15 | 2022-11-15 | [5 empty] | 811329 | 2022-04-06 | 668963 | 2023-12-13 | 2025-02-19 | 2021-07-13: 2022-11-17; 2021-07-13: 2022-11-17; 2021-07-13: 2024-02-02; 2021-07-13: 2024-02-06 | [29 empty] | TRUE | TRUE | 643 | 2022-11-17 | 2022-11-17 | 2022 | 2022 | 2022 |  |  |  | 2021-06-28 | Report
644 |  |  | KRISTOFER COLEMAN | 2021-02-16 | 2022-12-08 | L2_Bump |  | 2024-07-26 | wthdw | [26 empty] | 2 - BATH |  | 261D3 | 630 | Yes | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Paul Williamson | Walden Renewables | NEW MEADOWS SOLAR LLC | AURTHUR J RENO SR RD WESTBATH ME | 2000208714 | 30013003790 | Solar | [5 empty] | 45.501 | -69.2505 | Arthur J Reno Sr Rd |  |  | West Bath | 5 | BATH 34 | 261D3 | 261T2 | 12.47 | PENDING POI ATTESTATION | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2021-03-02 | 2021-02-23 | 2021-03-02 | 2021-02-23 | 2021-03-04 | 2021-11-29 | 2021-12-20 | 2021-12-13 | 2022-01-13 | 2022-01-19 | 2022-01-19 | 2022-02-02 |  |  | 2022-01-31 |  |  | CS | 2022-01-31 | [6 empty] | CS |  |  | 2022-01-31 | 2022-05-17 |  | 2023-10-12 | 2024-07-29 | [7 empty] | 2022-02-01 |  |  | 2023-10-24 | 2024-08-08 |  |  |  | 2022-02-02 | 2022-02-02 |  |  | 2023-10-27 | 2024-08-08 |  |  |  |  | 2022-02-02 | 2022-05-31 |  | 2023-10-24 | 2024-08-08 | [7 empty] | 2022-04-07 | 2022-07-13 | [5 empty] | 2022-04-14 | 2022-07-11 |  | 2023-12-12 | 2024-09-27 |  |  |  |  | 2022-04-14 | 2022-07-11 |  | 2023-12-13 | 2024-09-30 |  |  |  |  | 2022-04-14 | 2022-07-27 |  | 2023-12-28 | 2024-09-30 |  |  |  |  | 2022-04-20 | 2022-07-27 |  | 2024-01-03 | 2024-10-04 |  |  |  | 2022-04-20 |  |  | 2024-01-03 | 2024-10-07 |  |  |  | 2022-07-27 |  | 2022-07-29 | 2024-01-08 | 2022-07-29 | 2024-01-30 | [7 empty] | 222977 | 2024-09-27 | 2025-03-24 | 2022-07-29 | 2022-07-29 | 2024-01-31 | 2024-02-06 | 2024-11-27 | 2024-11-27 | [15 empty] | Q4 2026 |  |  |  | Requested | [11 empty] | TRUE | TRUE | 644 | 2022-07-29 | 2022-07-29 | 2022 | 2022 | 2022
645 |  | Eben Snow | Brent Brooks | 2021-02-18 | [31 empty] | 3 - NATP |  | 469D1 | 440 |  | WITHDRAWN | WITHDRAWN |  | Santiago Quijano | Bluewave MA, LLC | BLUE WAVE PROJECT DEVELOPMENT LLC | 233 RIVER RD NAPLES | 2000183318 |  | Solar | [7 empty] | 233 River Road |  |  | Naples |  | NAPLES TAP | 469D1 |  |  | 9310-L0208-4040-0077-ED00025 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2021-02-25 | 2021-03-04 |  |  |  |  | 1900-01-12 | [127 empty] | 2022-01-19 | [37 empty] | TRUE | TRUE | 645 | 0 | 0 | 1900 | 1900 | 1900
646 |  | Govinda Neupane |  | 2021-02-18 | [31 empty] | 6 - SKSS |  | 854D2 | 487 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Haley Orvedal | Galehead Development | SOMERSET PV 1 LLC | 243 WATERVILLE RD SKOWHEGAN ME | 2000209812 | 30013017436 | Solar | [5 empty] | 44.7609 | -69.6936 | 243 Waterville Road |  |  | Skowhegan | 47 | SKOWHEGAN SOUTH SIDE | 854D2 | 854T1 | 34.5 | 9310-L0433-5330-0200-ED00102 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2021-03-03 | 2021-02-25 | 2021-03-04 | 2021-02-24 | 2021-03-04 | 2021-05-20 | 2021-05-14 | 2021-06-04 | 2021-05-14 | 2021-05-20 | 2021-05-20 | 2021-06-04 |  |  | 2021-06-04 | 2021-11-03 | 2016-06-14 | CS | 2021-06-03 | RS | 2021-11-03 |  |  |  |  | CS |  |  | 2021-06-03 | 2021-11-03 | 2021-06-14 | [9 empty] | 2021-06-17 | [7 empty] | 2021-06-17 | 2021-06-17 | 2021-11-17 | [7 empty] | 2021-06-22 | 2021-11-29 | [10 empty] | 2021-09-01 | 2022-01-11 | [5 empty] | 2021-08-26 | 2022-01-10 | [7 empty] | 2021-08-26 | 2022-01-10 | [8 empty] | 2022-01-24 | [7 empty] | 2021-09-08 | 2022-01-10 | [6 empty] | 2021-09-08 | 2022-01-10 | [6 empty] | 2022-02-07 |  | 2022-02-07 | 2022-06-14 | 2022-08-09 | 2022-08-09 | [5 empty] | 3506869 |  | 675136 | 2023-03-27 | 2024-02-02 | 2021-07-13: 2022-08-10; 2021-07-13: 2022-08-11; 2021-07-13: 2023-04-28; 2021-07-13: 2023-04-28 | [17 empty] | Requested | [11 empty] | TRUE | TRUE | 646 | 2022-08-10 | 2022-08-10 | 2022 | 2022 | 2022
647 |  | Govinda Neupane |  | 2021-02-18 | 2022-11-08 | L2_Bump |  | 2023-01-09 | L2_bump |  | 2023-05-08 | L2_bump |  | 2023-07-18 | L2_Bump |  | 2023-10-05 | L2_Bump | [17 empty] | 16 - STUR |  | 858D3 | 612 |  | WITHDRAWN | WITHDRAWN |  | Charlie Branham | NEXTERA ENERGY RESOURCES | BOULEVARD ASSOCIATES LLC | 179 Dump Rd farmington | 2000209383 | 30013012510 | Solar | [5 empty] | 44.6403 | -70.0937 | 179 Dump Rd |  |  | Farmington | 43 | STURTEVANT | 858D3 | 858T2 | 12.47 | 9310-L0437-2030-0043-ED00037 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2021-03-04 | 2021-02-25 | 2021-03-04 | 2021-02-25 | 2021-03-04 |  |  | 1900-01-12 | [112 empty] | 2022-06-29 |  | 2022-06-30 |  | 2022-07-05 | [10 empty] | 2024-04-05 | [37 empty] | TRUE | TRUE | 647 | 0 | 0 | 1900 | 1900 | 1900
648 |  | Lanie Patterson | Brent Brooks | 2021-02-24 | 2022-12-01 | L2_bump |  | 2023-05-21 | L2_Bump |  | 2023-10-06 | L2_bump |  | 2023-01-05 | L2_bump | [20 empty] | 5 - MANC |  | 233D2 | 350 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Troy McBride | Norwich Solar Technologies | HALLOWELL WINTHROP SOLAR LLC | Winthrop Rd | 2000208124 | 30012007299 | Solar | [5 empty] | 44.3073 | -69.8251 | Winthrop Street |  |  | Winthrop | 90 | MANCHESTER | 233D2 | 233T1 | 12.47 | 9310-L0064-2450-0061-ED00124 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2021-03-10 | 2021-03-03 | 2021-03-10 | 2021-03-04 | 2021-03-10 | 2021-12-28 | 2022-01-06 | 2022-01-12 | 2022-01-06 | 2022-01-13 | 2022-01-13 | 2022-01-19 |  |  | 2022-01-24 |  |  | CS | 2022-01-24 | [6 empty] | CS |  |  | 2022-01-24 |  |  |  | 2023-09-21 | [7 empty] | 2022-01-27 | [7 empty] | 2022-01-27 | 2022-01-27 | [8 empty] | 2022-01-27 | [11 empty] | 2022-04-01 | [6 empty] | 2022-03-16 | [8 empty] | 2022-03-16 | [8 empty] | 2022-03-17 | [8 empty] | 2022-03-22 | [7 empty] | 2022-03-22 | [9 empty] | 2022-06-30 |  | 2022-07-01 | [10 empty] | 2024-09-05 | 2021-07-13: 2022-07-06; 2021-07-13: 2022-07-06 | [17 empty] | Requested | [11 empty] | TRUE | TRUE | 648 | 2022-07-06 | 2022-07-06 | 2022 | 2022 | 2022
649 |  | Eben Snow | Brent Brooks | 2021-03-02 | 2023-06-28 | L2_Bump | [29 empty] | 3 - SABA |  | 450D2 | 519 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Xander Neve | Syncarpha Solar LLC | Lewiston Solar III, LLC | 42 tarr ave lewiston | 2000212328 | 30013050304 | Solar | [5 empty] | 44.1061 | -70.1597 | 42 Tarr Ave |  |  | Lewiston | 13 | SABATTUS | 450D2 | 450T1 | 12.47 | 9310-L0193-3230-0021-ED00008 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2021-03-16 | 2021-03-09 | 2021-03-16 | 2021-03-09 | 2021-03-16 | 2021-03-16 | 2021-03-19 | 2021-03-30 | 2021-03-22 | 2021-03-23 | 2021-03-23 | 2021-04-06 |  |  | 2021-04-02 | 2021-09-20 |  | CS | 2021-04-02 | RS | 2021-09-20 |  |  |  |  | CS |  |  | 2021-04-02 | 2024-08-01 |  | 2024-04-19 | [5 empty] | 2024-08-01 |  |  |  | 2024-08-19 |  | 2024-05-03 |  |  |  |  | 2021-04-13 | 2021-04-13 | 2024-08-19 |  | 2023-03-22 | [5 empty] | 2021-04-13 | 2024-08-19 |  | 2024-05-03 | [8 empty] | 2021-06-17 | 2024-10-02 |  | 2021-07-16 | Report |  |  | 2021-07-16 | 2024-09-30 |  | 2024-07-02 | [5 empty] | 2021-07-16 | 2024-09-30 |  | 2024-07-02 | [6 empty] | 2024-10-10 | [7 empty] | 2021-07-16 | 2024-10-14 | [6 empty] | 2021-07-21 | 2024-10-14 |  |  |  |  | 2021-07-21 |  | 2022-01-05 |  | 2022-01-05 |  | 2022-01-31 | [6 empty] | 450802 |  | 334628 | 2024-07-02 | 2024-11-12 | 2021-07-13: 2022-01-31; 2021-07-13: 2022-02-01 | [17 empty] | Requested | [11 empty] | TRUE | TRUE | 649 | 2022-01-31 | 2022-01-31 | 2022 | 2022 | 2022 | 44398
650 |  | Eben Snow | Brent Brooks | 2021-03-10 | [31 empty] | 4 - PAPO |  | 438D1 | 465 |  | WITHDRAWN | WITHDRAWN |  | Nate Niles | REVISION ENERGY INC | REVISION ENERGY INC | 1008 Valley Rd Waterford | 2800182538 |  | Solar | [5 empty] | 44.2342 | -70.7715 | 1008 Valley Rd |  |  | Waterford |  | PAPOOSE POND | 438D1 |  |  | 9310-L0180-6205-0081-ED00001 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2021-03-17 | 2021-03-24 |  |  |  |  | 1900-01-12 | [127 empty] | 2021-10-15 | [37 empty] | TRUE | TRUE | 650 | 0 | 0 | 1900 | 1900 | 1900 |  |  |  | 2021-07-16 | Report
651 |  | Rigel Paradise | Rick Duperre | 2021-03-15 | [31 empty] | 1 - KITT |  | 688D1 |  |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN | 2021-11-23 | Dan Band | Louth Callan Renewables | LOUTH CALLAN RENEWABLES | Parsons Lane Solar | 2000199323 | 30013056616 | Solar | [5 empty] | 43.1329 | 70.7045 | 506 US-1 |  |  | Kittery | 157 | KITTERY | 688D1 | 688T1 | 12.47 | 9310-L0365-3100-0152-ED00096 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2021-03-29 | 2021-03-22 | 2021-03-29 | 2021-03-22 | 2021-03-29 | 2021-03-29 | 2021-04-05 | 2021-04-12 | 2021-04-05 | 2021-04-06 | 2021-04-06 | 2021-04-21 |  |  | 2021-04-30 |  |  | CS | 2021-04-30 | [6 empty] | CS |  |  | 2021-04-30 | [19 empty] | 2021-05-23 | 2021-05-23 | [8 empty] | 2021-05-25 | [18 empty] | 2021-07-12 | [26 empty] | 2021-07-13 | [7 empty] | 2021-07-13 | [7 empty] | 2021-07-16 |  | 2021-07-22 |  | 2021-07-22 | [10 empty] | 2022-03-01 | 2021-07-13: 2021-08-16; 2021-07-13: 2021-07-23; 2021-07-13: 2021-08-16; 2021-07-13: 2021-08-16 | [29 empty] | TRUE | TRUE | 651 | 2021-08-16 | 2021-08-16 | 2021 | 2021 | 2021
652 |  | Lanie Patterson | Anthony Boucher | 2021-03-24 | 2022-06-22 | L2_Bump | [27 empty] | 3 - BUCK | 390 | 5 - BUCK |  | 806D1 | 616 | Yes | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED |  | Zach Good | Aligned Solar Partners 6 LP c/o Aligned Climate Capital LLC | Bucksport Solar 1, LLC | 258 RT 1 BUCKSPORT ME | 2000113260 | 30015780460 | Solar/Battery | 1990 | 1.99 | 2550.12 |  | 1990 | 44.5696 | -68.7678 | 258 Route 1 |  |  | Bucksport | 81 | BUCKSPORT | 806D1 | 806T5 | 12.47 | 9310-L0385-0790-0057-ED00143 | Non-FERC | NOT IMPACTED | NOT IMPACTED |  | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2021-04-07 | 2021-03-31 | 2021-04-07 | 2021-03-31 | 2021-04-07 | 2021-04-07 |  | 2021-04-22 |  | 2021-04-21 | 2021-04-21 | 2021-05-05 |  |  | 2021-04-28 | 2021-08-17 |  | CS | 2021-04-28 | RS | 2021-08-17 |  |  |  |  | CS |  |  | 2021-04-28 | 2021-08-17 |  | 2023-02-09 | [11 empty] | 2023-02-28 | [8 empty] | 2023-03-02 | [5 empty] | 2021-05-04 | 2021-08-19 |  | 2023-03-02 | [8 empty] | 2021-07-07 | 2021-10-01 |  | 2021-07-12 | Report |  |  | 2021-07-12 | 2021-10-01 |  | 2023-04-12 | [5 empty] | 2021-07-12 | 2021-10-01 | [16 empty] | 2021-07-13 | 2021-10-05 | [6 empty] | 2021-07-13 | 2021-10-05 | [6 empty] | 2021-10-25 |  | 2021-11-03 | 2023-04-28 | 2021-12-07 |  | 2023-07-18 | 2023-07-18 |  |  | 0 | 78879 |  | 111827 | 2023-04-12 |  | 2021-07-13: 2021-12-07; 2021-07-13: 2021-12-07 |  |  | 2023-08-16 | 2023-08-16 | [13 empty] | Requested | [11 empty] | FALSE | TRUE | 652 | 2021-12-07 | 2021-12-07 | 2021 | 2021 | 2021
653 |  | Lanie Patterson | Brent Brooks | 2021-03-26 | 2023-03-29 | L2_Bump |  | 2023-12-08 | L2_Bump |  | 2023-01-22 | wthdw | [21 empty] | 1 - WINT |  | 6 - WINT | 1 - WINT | 256D2 | 607 | Yes | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED |  | Troy McBride | Norwich Solar Technologies | WINTHROP TURKEY LANE SOLAR LLC | TURKEY LANE WINTHROP ME | 2000214694 | 30013082364 | Solar | 975 | 0.975 | 1382.4 |  |  | 44.3198 | -70.003 | Turkey Lane |  |  | Winthrop | 54 | WINTHROP | 256D2 | 256T1 | 12.47 | 9310-L0096-6450-0165-ED00103 | Non-FERC | COST SHARING | COST SHARING ($330,000) | 92590 | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2021-04-09 | 2021-04-02 | 2021-04-09 | 2021-04-02 | 2021-04-09 | 2021-12-16 | 2021-12-28 | 2022-01-03 | 2021-12-30 | 2022-01-06 | 2022-01-06 | 2022-01-14 |  |  | 2021-01-14 |  |  | CS | 2022-01-14 | [6 empty] | CS |  |  | 2022-01-14 |  | 2022-07-13 | 2024-01-25 | [8 empty] | 2022-01-18 |  | 2022-07-27 | 2024-02-08 |  |  |  |  | 2022-01-19 | 2022-01-19 |  | 2022-07-13 | 2024-02-28 | [5 empty] | 2022-01-21 |  | 2022-07-28 | 2024-02-28 | [8 empty] | 2022-03-28 |  | 2022-09-30 |  |  |  |  | 2022-03-04 |  | 2022-10-03 | 2024-04-29 | [5 empty] | 2022-03-04 |  | 2022-10-03 | 2024-04-29 | [5 empty] | 2022-03-04 |  | 2022-10-03 | 2024-05-06 | [5 empty] | 2022-03-09 |  | 2022-10-06 | [5 empty] | 2022-03-09 | 2022-10-20 | [6 empty] | 2022-11-03 |  | 2022-11-03 |  | 2022-11-15 |  |  |  | 2022-03-21 | 2022-05-09 | 12051 | 400886 | 2022-10-03 | 379722 | 2024-04-24 |  | 2021-07-13: 2022-11-21; 2021-07-13: 2022-11-28; 2021-07-13: 2024-05-30; 2021-07-13: 2024-05-31 | [13 empty] | Q3 2025 | [15 empty] | FALSE | TRUE | 653 | 2022-11-21 | 2022-11-21 | 2022 | 2022 | 2022 |  |  |  | 2021-07-12 | Report
654 |  | Govinda Neupane |  | 2021-03-26 | [31 empty] | 6 - RUMF |  | 447D1 | 606 |  | WITHDRAWN | WITHDRAWN |  | Hillel Halberstam | Synergen Solar | SYNERGEN ROXBURY LLC | 1034 Roxbury Rd, Roxbury | 2000215915 | 30013098436 | Solar | [5 empty] | 44.6184 | -70.5792 | 1034 Roxbury Road |  |  | Roxbury |  | RUMFORD | 447D1 |  |  | 9310-L0186-5010-0019-ED00143 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2021-04-02 | 2021-04-09 | 2021-04-02 | 2021-04-09 |  | 2021-12-28 |  | 2022-01-03 | 2022-01-04 | 2022-01-04 | [6 empty] | N/A | [47 empty] | No Study | [69 empty] | 2022-01-04 | [25 empty] | NO STUDY | [11 empty] | TRUE | TRUE | 654 | 0 | 0 | 1900 | 1900 | 1900
655 |  |  | Anthony Boucher | 2021-03-29 | 2022-06-22 | L2_Bump | [29 empty] | 6 - BUCK |  | 806D1 | 652 |  | WITHDRAWN | WITHDRAWN |  | Haley Orvedal | Galehead Development | BUCKSPORT PV 1 LLC | 288 Upper Falls Rd Orland | 2000215673 | 30013094765 | Solar/Battery | [5 empty] | 44.5925 | -68.7251 | Upper Falls Road |  |  | Orland | 8 | BUCKSPORT | 806D1 | 806T5 | 12.47 | 9310-L0385-4330-0028-ED00075 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2021-04-12 | 2021-04-05 | 2021-04-12 | 2021-04-05 | 2021-04-12 | 2021-12-07 | 2021-12-17 | 2021-12-21 | 2021-12-21 | 2022-01-06 | 2022-01-06 | 2022-01-21 |  |  | 2022-01-20 |  |  | CS | 2022-01-21 | [6 empty] | CS |  |  | 2022-01-21 |  |  | 2023-05-30 | [16 empty] | 2022-02-04 | 2022-02-04 | [8 empty] | 2022-02-04 | [11 empty] | 2022-04-11 | [6 empty] | 2022-04-14 | [8 empty] | 2022-04-21 | [8 empty] | 2022-04-27 | [8 empty] | 2022-05-09 | [7 empty] | 2022-05-09 | [22 empty] | 2023-06-12 | [37 empty] | TRUE | TRUE | 655 | 0 | 0 | 1900 | 1900 | 1900
656 |  | Eben Snow | Brent Brooks | 2021-03-30 | 2024-04-17 | wthdw | [29 empty] | 6 - R115 |  | 445D2 | 560 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Santiago Quijano | Bluewave MA, LLC | BWC Nirvana Lake, LLC | 233 RIVER RD NAPLES | 2000261870 | 30013727794 | Solar | [5 empty] | 44.0117 | -70.5805 | 233 River Road |  |  | Naples | 25 | RAYMOND 115 KV | 445D2 | 445T2 | 34.5 | 9310-L0208-4040-0077-ED00025 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2021-04-13 | 2021-04-06 | 2021-04-13 | 2021-04-06 | 2021-04-13 | 2021-07-14 |  | 2021-07-28 |  | 2021-06-24 | 2021-06-24 | 2021-08-05 |  |  | 2021-08-05 |  |  | CS | 2021-08-09 | [6 empty] | CS |  |  | 2021-08-09 |  |  | 2024-08-07 | [8 empty] | 2021-08-09 | [17 empty] | 2021-08-10 | [11 empty] | 2021-10-14 | [6 empty] | 2021-10-19 | [8 empty] | 2021-10-19 | [17 empty] | 2021-10-25 | [7 empty] | 2021-10-25 | [7 empty] | 2021-11-04 |  | 2021-11-04 |  | 2021-11-05 | [6 empty] | 1085144 |  |  | 2021-10-18 | 2024-08-24 | 2021-07-13: 2021-11-05; 2021-07-13: 2021-11-12 | [17 empty] | REquested | [11 empty] | TRUE | TRUE | 656 | 2021-11-05 | 2021-11-05 | 2021 | 2021 | 2021
657 |  | Govinda Neupane |  | 2021-04-02 | 2022-12-13 | L2_Bump |  | 2023-07-18 | L2_Bump |  | 2024-01-04 | L2_bump |  | 2024-10-21 | L2 With |  | 2025-08-07 | wthdw | [15 empty] | 1 - DEXT |  | 5 - DEXT | 2 - DEXT | 813D3 | 309 | Yes | EXECUTED | EXECUTED |  | Jeff Kelly | Boston Environmental | KME UNLIMITED LLC | Railroad Ave, Dexter | 2000215637 | 30013094914 | Solar/Battery | 996 | 0.996 | 2999.56 |  | 1210 | 45.0007 | -69.2962 | Railroad Avenue |  |  | Dexter | 33 | DEXTER | 813D3 | 813T2 | 12.47 | 9310-L0395-1610-0057-ED00011 | Non-FERC | GFOV TBD During Study Phase | T-GFOV TBD During Study Phase |  | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2021-04-16 | 2021-04-09 | 2021-04-16 | 2021-04-09 | 2021-04-16 | 2021-09-29 | 2021-10-07 | 2021-10-14 | 2021-10-28 | 2021-11-01 | 2021-11-01 | 2021-11-16 |  |  | 2021-11-04 | 2022-03-09 |  | CS | 2021-11-09 | RS | 2022-03-09 |  |  |  |  | CS |  |  | 2021-11-09 |  |  | 2025-02-12 | 2026-01-07 | [10 empty] | 2025-03-27 | 2026-02-09 |  |  |  |  | 2021-11-12 | 2022-03-23 |  | 2025-04-16 | 2026-02-09 |  |  |  |  | 2021-11-23 | 2022-03-30 |  | 2025-04-16 | 2026-02-09 | [7 empty] | 2022-01-28 | 2022-05-11 | [5 empty] | 2022-01-28 | 2022-05-11 |  | 2025-06-18 | 2026-03-20 |  |  |  |  | 2022-01-28 | 2022-05-11 |  | 2025-06-18 | 2026-03-20 |  |  |  |  | 2022-01-31 | 2022-05-16 |  | 2025-07-01 | [5 empty] | 2022-02-07 | 2022-05-18 |  | 2025-07-02 |  |  |  |  | 2022-02-07 | 2022-05-08 | [6 empty] | 2022-06-07 |  | 2022-06-08 | 2023-04-14 | 2022-07-05 | 2023-04-18 | [5 empty] | 313290 | 2023-05-10 | 661170 | 2026-03-20 |  | 2022-07-06 | 2022-07-06 | 2023-04-19 | 2023-04-19 | 2026-03-27 | 2026-03-27 | [19 empty] | Requested | [11 empty] | FALSE | TRUE | 657 | 2022-07-06 | 2022-07-06 | 2022 | 2022 | 2022
658 |  | Rigel Paradise | Rick Duperre | 2021-04-02 | 2022-10-20 | wthdw | RQP-1 | 2023-09-14 | wthdw | [24 empty] | 1 - SOBE |  | 3 - SOBE |  | 663D2 | 568 | Yes | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Muhammad Omar Sohail | Novel Energy SPV 4 LLC | 15B Old South Rd Solar LLC | 1 Old So Rd So Berwick | 2000174932 | 30013610032 | Solar | [5 empty] | 43.2137 | -70.792 | 0 Old South Road | 0 | Old South Road | South Berwick | 313.4 | SOUTH BERWICK | 663D2 | 663T1 | 12.47 | 9310-L0332-5410-0098-ED00164 | FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2021-04-16 | 2021-04-09 | 2021-04-16 | 2021-04-09 | 2021-04-16 | 2021-10-25 | 2021-11-30 | 2021-11-08 | 2021-11-30 | 2021-12-01 | 2021-12-01 |  |  |  | 2021-12-01 |  |  | CS | 2021-12-14 | RS | 2022-03-25 |  |  |  |  | CS |  |  | 2021-12-14 |  |  | 2022-10-24 | 2023-07-06 | [10 empty] | 2023-02-14 | 2023-06-16 | 2023-12-06 |  |  |  | 2022-01-03 |  |  | 2023-04-19 | 2023-07-05 |  |  |  |  | 2022-01-04 | 2022-05-25 |  | 2023-04-20 | 2023-07-21 | 2023-12-22 | [6 empty] | 2022-03-10 | 2022-07-11 | [5 empty] | 2022-03-11 | 2022-07-15 |  | 2023-06-05 | 2023-09-01 | 2024-02-29 |  |  |  | 2022-03-11 | 2022-07-15 |  | 2023-06-05 | 2023-09-05 | 2024-02-29 |  |  |  |  | 2022-07-19 | [7 empty] | 2022-03-17 | 2022-07-19 |  |  |  | 2024-03-06 |  |  | 2022-03-17 |  |  |  |  | 2024-03-06 |  |  | 2022-07-19 |  | 2022-07-25 |  | 2022-07-25 | [6 empty] | 337720 | 2022-07-22 |  |  | 2025-09-09 | 2021-07-13: 2022-07-25; 2021-07-13: 2022-07-26; 2021-07-13: 2024-04-23; 2021-07-13: 2024-04-23 | [13 empty] | Q3 2025 |  |  |  | Requested | [11 empty] | FALSE | TRUE | 658 | 2022-07-25 | 2022-07-25 | 2022 | 2022 | 2022
659 |  | Lanie Patterson | Brent Brooks | 2021-04-12 | [31 empty] | 11 - MONM |  | 457D2 | 267 |  | WITHDRAWN | WITHDRAWN |  | Bobby Snow | BORREGO SOLAR SYSTEMS INC | 510 PV PROJECT DEVELOPMENT LLC | 430 COBBOSSEECONTEE RD MONMOUTH | 2000113260 | 30013066573 | Solar/Battery | [5 empty] | 44.2201 | -69.9958 | 430 COBBOSSEECONTEE RD |  |  | Monmouth |  | MONMOUTH | 457D2 |  |  | 9310-L0199-3740-0081-ED00079 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2021-04-20 | 2021-04-27 |  |  |  |  | 1900-01-12 | [127 empty] | 2021-11-15 | [37 empty] | TRUE | TRUE | 659 | 0 | 0 | 1900 | 1900 | 1900
660 |  |  | KRISTOFER COLEMAN | 2021-04-15 | [31 empty] | 1 - COCO |  | 217D3 |  |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Nathaniel Curtis | C2 ENERGY DEVELOPMENT LLC | C2 ENERGY DEVELOPMENT LLC | 160 JORDAN AVE BRUNSWICK | 2000200909 | 30013095952 | Solar | [5 empty] | 43.9083 | -69.94 | Jordan Avenue |  |  | Brunswick | 60 | COOKS CORNER | 217D3 | Pending | 34.5 | 9310-L0048-0770-0160-ED00073 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2021-04-29 | 2021-04-23 | 2021-04-30 | 2021-04-22 | 2021-04-29 | 2021-05-06 |  | 2021-05-20 |  | 2021-05-06 | 2021-05-06 |  |  |  | 2021-05-06 |  |  | CS | 2021-05-07 | [6 empty] | CS |  |  | 2021-05-07 | [29 empty] | 2021-05-11 | [11 empty] | 2021-07-14 |  |  | 2021-07-16 | Report |  |  | 2021-07-16 | [8 empty] | 2021-07-16 | [17 empty] | 2021-07-22 | [7 empty] | 2021-07-22 | [7 empty] | 2021-08-10 |  | 2021-08-10 |  | 2021-08-24 | [6 empty] | 253064 | 2021-07-08 | 384717 | 2021-09-22 | 2023-10-10 | 2021-07-13: 2021-08-10; 2021-07-13: 2021-08-30; 2021-07-13: 2021-08-30; 2021-07-13: 2021-08-30 | [17 empty] | Requested | [11 empty] | TRUE | TRUE | 660 | 2021-08-10 | 2021-08-10 | 2021 | 2021 | 2021
661 |  | Govinda Neupane |  | 2021-04-22 | 2022-09-09 | L2_Bump |  | 2022-12-01 | L2_Bump |  | 2023-10-06 | L2_Bump |  | 2023-12-06 | L2_Bump |  | 2024-10-04 | wthdw |  | 2024-11-14 | wthdw | [14 empty] | 8 - GUIL |  | 821D3 | 593 |  | WITHDRAWN | WITHDRAWN |  | Nick Wigglesworth | UGE USA INC | UGE USA INC | MCPHETERS RD SOLAR SANGERVILLE | 2000142913 | 30013133803 | Solar | [5 empty] | 45.161 | -69.3592 | Mcpheters Rd |  |  | Sangerville | 49 | GUILFORD | 821D3 |  | 34.5 | 9310-L0407-5180-0041-ED00044 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2021-05-06 | 2021-04-29 | 2021-05-06 | 2021-04-29 | 2021-05-06 | 2024-11-14 | 2024-11-14 | 2024-12-02 | [127 empty] | 2024-11-14 | [37 empty] | TRUE | TRUE | 661 | 0 | 0 | 1900 | 1900 | 1900 |  |  |  | 2021-07-16 | Report
662 |  |  | KRISTOFER COLEMAN | 2021-04-22 | [31 empty] | 1 - BANE |  | 206D1 |  |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Andy Cerrato | NEXTERA ENERGY RESOURCES | DG MAINE CS LLC | 206 N Bath Rd, Bath | 2000147169 | 30013157042 | Solar | [5 empty] | 43.9465 | -69.8427 | 206 North Bath Road |  |  | Bath | 53 | BATH NORTH END | 206D1 | 206T1 | 12.47 | 9310-L0018-0410-0115-ED00077 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2021-05-06 | 2021-04-29 | 2021-05-06 | 2021-04-29 | 2021-05-06 | 2021-05-14 | 2021-05-14 | 2021-05-28 | 2021-05-14 | 2021-05-18 | 2021-05-18 | 2021-06-02 |  |  | 2021-05-28 |  |  | CS | 2021-05-28 | FC | 2021-08-27 |  |  |  |  | CS |  |  | 2021-05-28 |  | 2021-09-08 | [9 empty] | 2021-06-09 | [7 empty] | 2021-06-10 | 2021-06-10 |  | 2021-09-20 | [6 empty] | 2021-06-16 |  | 2021-09-29 | [5 empty] | 2021-10-06 | 2021-11-05 |  |  | 2021-08-13 |  | 2021-12-06 |  |  |  |  | 2021-08-16 |  | 2022-01-06 | [6 empty] | 2021-08-16 |  | 2022-01-07 | [6 empty] | 2021-08-16 |  | 2022-02-07 | [6 empty] | 2021-08-19 |  | 2022-01-06 | [5 empty] | 2021-08-19 |  | 2022-01-06 | [5 empty] | 2022-02-16 | 2022-02-07 | 2022-02-28 | 2022-05-11 | 2022-03-03 | 2022-06-03 | [5 empty] | 595890 | 2022-03-18 | 543410 | 2022-05-11 | 2025-03-10 | 2021-07-13: 2022-06-03; 2021-07-13: 2022-06-03 | [17 empty] | Requested | [11 empty] | TRUE | TRUE | 662 | 2022-06-03 | 2022-06-03 | 2022 | 2022 | 2022 |  |  | 44599
663 |  | Govinda Neupane |  | 2021-04-22 | [31 empty] | 7 - SKSS |  | 854D2 | 646 |  | WITHDRAWN | WITHDRAWN |  | Andy Cerrato | NEXTERA ENERGY RESOURCES | DG MAINE CS LLC | 627 Waterville Rd, Skowhegan | 2000147169 | 30013157034 | Solar | [5 empty] | 44.7431 | -69.6701 | 627 Waterville Road |  |  | Skowhegan | 83 | SKOWHEGAN SOUTH SIDE | 854D2 | 854T1 | 12.47 | 9310-L0433-5330-0200-ED00198 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2021-05-06 | 2021-04-29 | 2021-05-06 | 2021-04-29 | 2021-05-06 | 2022-08-11 | 2022-08-17 | 2022-08-25 | 2022-08-26 | 2022-08-26 | 2022-08-26 | 2022-09-12 |  |  | 2022-08-26 |  |  | CS | 2022-08-26 | [6 empty] | CS |  |  | 2022-08-29 |  | 2022-12-19 | [9 empty] | 2022-09-09 | [8 empty] | 2022-09-09 | [8 empty] | 2022-09-09 |  | 2022-12-29 | [9 empty] | 2022-11-15 |  | 2022-03-08 |  |  |  |  | 2022-11-08 |  | 2023-05-26 | [6 empty] | 2022-11-09 |  | 2023-05-30 | [6 empty] | 2022-11-11 |  | 2023-06-01 | [6 empty] | 2022-11-11 |  | 2023-06-08 | [5 empty] | 2022-11-11 |  | 2023-06-08 | [20 empty] | 2023-10-19 | [37 empty] | TRUE | TRUE | 663 | 0 | 0 | 1900 | 1900 | 1900
664 |  |  | KRISTOFER COLEMAN | 2021-04-30 | [31 empty] | 3 - BATH |  | 261D3 | 644 |  | WITHDRAWN | WITHDRAWN |  | Andy Cerrato | NEXTERA ENERGY RESOURCES | DG MAINE CS LLC | 206 N Bath Rd, Bath ic2 | 2000147169 | 30013182602 | Solar | [5 empty] | 43.9465 | -69.8427 | 206 North Bath Road |  |  | Bath | 1 | BATH 34 | 261D3 | 206T1 | 12.47 | 9310-L0018-0410-0115-ED00077 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2021-05-14 | 2021-05-07 | 2021-05-14 | 2021-05-07 | 2021-05-14 | 2022-08-01 | 2022-08-01 | 2022-08-08 | 2022-08-08 | 2022-08-08 | 2022-08-08 | 2022-08-22 | [123 empty] | 2022-08-30 | [37 empty] | TRUE | TRUE | 664 | 0 | 0 | 1900 | 1900 | 1900
665 |  | Eben Snow | Brent Brooks | 2021-04-30 | 2022-08-22 | L2_Bump | [29 empty] | 2 - RA34 |  | 444D1 | 319 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Sachin Patel | Mainely Solar LLC | ALLEN SOLAR LLC | 1565 ROOSEVELT TRL RAYMOND | 2000219534 | 30013148686 | Solar | [5 empty] | 43.9095 | -70.5005 | 1565 Roosevelt Trail |  |  | Raymond | 472 | RAYMOND 34 KV | 444D1 | 444T1 | 12.47 | 9310-L0181-4900-0084-ED00095 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2021-05-14 | 2021-05-07 | 2021-05-14 | 2021-05-07 | 2021-05-14 | 2021-05-14 |  | 2021-05-28 |  | 2021-06-01 | 2021-06-01 | 2021-06-15 |  |  | 2021-06-16 |  |  | CS | 2021-06-16 | [6 empty] | CS |  |  | 2021-06-16 | [11 empty] | 2021-06-21 | [17 empty] | 2021-06-24 | [11 empty] | 2021-08-26 | [6 empty] | 2021-08-13 | [8 empty] | 2021-08-27 | [17 empty] | 2021-09-01 | [7 empty] | 2021-09-01 | [7 empty] | 2021-09-01 |  | 2021-09-01 |  | 2021-09-03 | [6 empty] | 74099 |  |  |  | 2023-06-01 | 2021-07-13: 2021-09-01; 2021-07-13: 2021-09-16 | [17 empty] | Requested | [11 empty] | TRUE | TRUE | 665 | 2021-09-01 | 2021-09-01 | 2021 | 2021 | 2021
666 |  | Marshall Ripley | Rick Duperre | 2021-04-30 | [31 empty] | 2 - MOSH |  | 635D2 | 276 |  | WITHDRAWN | WITHDRAWN |  | Ian Clark | Dichotomy Power | Presumpscot Hydro LLC | Olde Canal Way Gorham | 2000220628 |  | Hydro | [5 empty] | 43.702 | -70.3989 | 95 Olde Canal Way |  |  | Gorham |  | MOSHERS | 635D2 |  |  |  |  | WITHDRAWN | WITHDRAWN | [8 empty] | 2021-05-07 | 2021-05-14 |  |  |  |  | 1900-01-12 | [123 empty] | n/a |  |  |  | 2021-05-12 | [37 empty] | TRUE | TRUE | 666 | 0 | 0 | 1900 | 1900 | 1900
667 |  | Marshall Ripley | Rick Duperre | 2021-04-30 | [31 empty] | 2 - NOWI |  | 639D2 | 639 |  | WITHDRAWN | WITHDRAWN |  | Ian Clark | Dichotomy Power | Presumpscot Hydro LLC | Middle Jam Rd Standish | 2000220628 |  | Hydro | [5 empty] | 43.8257 | -70.4532 | 50 Middle Jam Rd |  |  | Standish |  | NORTH WINDHAM | 639D2 |  |  |  |  | WITHDRAWN | WITHDRAWN | [8 empty] | 2021-05-07 | 2021-05-14 |  |  |  |  | 1900-01-12 | [127 empty] | 2021-05-12 | [37 empty] | TRUE | TRUE | 667 | 0 | 0 | 1900 | 1900 | 1900
668 |  | Eben Snow | Brent Brooks | 2021-04-30 | 2022-07-09 | L2_Bump |  | 2022-10-20 | L2_Bump | [26 empty] | 2 - SRTP |  | 470D1 | 403 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Sachin Patel | Mainely Solar LLC | SPRING MOUNTAIN SOLAR LLC | 791 Roosevelt Trail, Casco | 2000154859 | 30013175325 | Solar | [5 empty] | 43.9535 | -70.5542 | 791 Roosevelt Trail |  |  | Casco | 340 | SAND ROAD TAP | 470D1 | 470T1 | 12.47 | 9310-L0208-1060-0079-ED00265 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2021-05-14 | 2021-05-07 | 2021-05-14 | 2021-05-07 | 2021-05-14 | 2021-05-14 |  | 2021-05-28 |  | 2021-06-01 | 2021-06-01 | 2021-06-15 |  |  | 2021-06-16 | 2021-09-17 |  | CS | 2021-06-16 | RS | 2021-09-17 |  |  |  |  | CS |  |  | 2021-06-16 | 2021-09-17 | [10 empty] | 2021-06-21 | [17 empty] | 2021-06-24 | 2021-09-23 | [10 empty] | 2021-08-26 | 2021-11-05 | [5 empty] | 2021-08-30 | 2021-11-09 | [7 empty] | 2021-08-30 | 2021-11-09 | [16 empty] | 2021-08-31 | 2021-11-15 | [6 empty] | 2021-08-31 | 2021-11-15 | [6 empty] | 2021-12-09 |  | 2021-12-09 |  | 2021-12-13 | [10 empty] | 2023-09-13 | 2021-07-13: 2021-12-10; 2021-07-13: 2021-12-16 | [17 empty] | Requested | [11 empty] | TRUE | TRUE | 668 | 2021-12-10 | 2021-12-10 | 2021 | 2021 | 2021
669 |  | Lanie Patterson | Brent Brooks | 2021-05-25 | 2022-12-01 | L2_bump |  | 2023-05-21 | L2_Bump |  | 2023-10-06 | L2_bump |  | 2023-01-05 | L2_bump |  |  |  |  | 2024-09-05 | wthdw | [12 empty] | 2 - MANC | 648 | 6 - MANC | 2 - MANC | 233D1 | 648 | Yes | EXECUTED | EXECUTED |  | Robel Arega | Nexamp, Inc | NEXAMP SOLAR LLC | 30 Association Dr / Manchester | 2000505615 | 30017107522 | Solar | 975 | 0.975 | 1291.68 |  |  | 44.3227 | -69.8369 | 30 Association Dr |  |  | Manchester | 504 | MANCHESTER | 233D1 | 233T1 | 12.47 | 9310-L0063-3540-0062-ED00012 | Non-FERC | COST SHARING | COST SHARING (325,000) | 42442 | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2021-06-09 | 2021-06-02 | 2021-06-09 | 2021-06-02 | 2021-06-09 | 2022-07-06 | 2022-07-28 | 2022-07-20 | 2022-08-17 | 2022-08-17 | 2022-08-17 | 2022-08-31 |  |  | 2022-08-31 |  |  | CS | 2022-08-31 | [6 empty] | CS |  |  | 2022-09-01 |  |  | 2024-10-11 |  |  |  |  | 2022-08-31 |  |  |  | 2022-09-08 |  |  | 2024-10-18 | [5 empty] | 2022-09-14 |  |  | 2024-10-18 | [5 empty] | 2022-09-15 |  |  | 2024-10-18 | [8 empty] | 2022-11-21 | [6 empty] | 2022-11-21 |  |  | 2024-12-16 | [5 empty] | 2022-11-21 |  |  | 2024-12-17 | [8 empty] | 2024-12-20 | [8 empty] | 2025-01-02 | [7 empty] | 2025-01-02 |  |  |  |  | 2025-01-06 |  | 2025-01-06 | 2025-10-09 | 2025-01-07 | [8 empty] | 464010 | 2024-12-12 |  | 2021-07-13: 2025-01-08; 2021-07-13: 2025-01-08 | [13 empty] | Q4 2023 |  |  |  | Requested | [11 empty] | FALSE | TRUE | 669 | 2025-01-08 | 2025-01-08 | 2025 | 2025 | 2025
670 |  |  | Anthony Boucher | 2021-05-28 | [31 empty] | 1 - THTP |  | 857D1 |  |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Andy | NEXTERA ENERGY RESOURCES | DG MAINE CS LLC | s/s bailey rd throndike rd | 2000147169 | 30013258972 | Solar | [5 empty] | 44.5653 | -69.2842 | Bailey Road |  |  | Thorndike | 22 | THORNDIKE TAP | 857D1 | 857T1 | 12.47 | 9310-L0436-5800-0020-ED00030 | FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2021-06-14 | 2021-06-07 | 2021-06-14 | 2021-06-07 | 2021-06-14 | 2021-06-16 | 2021-06-29 | 2021-07-01 | 2021-06-29 | 2021-06-30 | 2021-06-30 | 2021-07-15 |  |  | 2021-07-07 | 2021-11-28 | 2022-02-03 | CS | 2021-07-14 | RS | 2021-11-28 | FC | 2022-02-02 |  |  | CS |  |  | 2021-07-14 | 2021-11-28 | 2022-02-03 | [9 empty] | 2021-07-12 | [7 empty] | 2021-07-23 | 2021-07-23 | 2021-11-24 | 2022-02-10 | [6 empty] | 2021-07-28 | 2021-12-02 | 2022-02-10 | [9 empty] | 2021-09-30 | 2022-01-14 | 2022-04-15 |  |  |  |  | 2021-10-12 | 2022-01-18 | 2022-04-22 | [6 empty] | 2021-10-12 | 2022-01-18 | [7 empty] | 2022-01-18 | 2022-01-18 | [7 empty] | 2021-10-25 | 2022-01-18 | [6 empty] | 2021-10-25 | 2022-01-18 | [6 empty] | 2022-01-18 |  | 2022-01-18 | 2022-06-13 | 2022-01-20 | 2022-07-07 | [9 empty] | 2025-03-10 | 2021-07-13: 2022-07-08; 2021-07-13: 2022-07-11 | [17 empty] | Requested | [11 empty] | TRUE | TRUE | 670 | 2022-07-08 | 2022-07-08 | 2022 | 2022 | 2022
671 |  | Lanie Patterson | Brent Brooks | 2021-05-28 | [31 empty] | 5 - RICH |  | 240D1 | 634 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Robel Arega | Nexamp, Inc | NEXAMP SOLAR LLC | 590 Lincoln St, Richmond | 2000114877 | 30013230906 | Solar | [5 empty] | 44.1231 | -69.817 | 590 Lincoln Street |  |  | Richmond | 10 | RICHMOND | 240D1 | 240D1 | 12.47 | 9310-L0418-4125-0047-ED00072 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2021-06-14 | 2021-06-07 | 2021-06-14 | 2021-06-07 | 2021-06-14 | 2021-06-14 | 2021-06-23 | 2021-06-29 | 2021-06-24 | 2021-07-01 | 2021-07-01 | 2021-07-15 |  |  | 2021-07-15 | 2021-11-09 |  | CS | 2021-07-16 | RS | 2021-11-09 |  |  |  |  | CS |  |  | 2021-07-16 | 2021-11-09 | [10 empty] | 2021-07-15 | 2021-10-26 | [6 empty] | 2021-07-23 | 2021-07-23 | 2021-11-16 | [7 empty] | 2021-07-28 | 2021-11-29 | [10 empty] | 2021-09-30 | 2022-01-11 | [5 empty] | 2021-09-29 | 2022-01-24 | [7 empty] | 2021-09-29 | 2022-01-24 | [7 empty] | 2021-09-30 | 2022-01-24 | [7 empty] | 2021-10-04 | 2022-01-24 | [6 empty] | 2021-10-04 | 2022-01-24 | [6 empty] | 2022-02-03 |  | 2022-02-04 |  | 2022-02-11 | [10 empty] | 2023-07-18 | 2021-07-13: 2022-02-04; 2021-07-13: 2022-02-15 | [17 empty] | Requested | [11 empty] | TRUE | TRUE | 671 | 2022-02-04 | 2022-02-04 | 2022 | 2022 | 2022
672 |  | Govinda Neupane |  | 2021-06-21 | 2023-04-07 | L2_Bump |  | 2023-07-17 | wthdw |  | 2023-08-14 | L2_bump |  | 2023-09-14 | L2_Bump |  | 2023-01-19 | wthdw | [17 empty] | 11 - NEWP |  | 837D1 | 638 |  | WITHDRAWN | WITHDRAWN |  | Robel Arega | Nexamp, Inc | NEXAMP SOLAR LLC | 335 Williams Rd, Newport | 2000114877 | 30013230930 | Solar | [5 empty] | 44.8832 | -69.2945 | 335 Williams Road |  |  | Newport | 34 | NEWPORT | 837D1 | 837T1 | 7.2 | 9310-L0418-4125-0047-ED00072 | Non-FERC | WITHDRAWN | WITHDRAWN |  |  |  |  | K&A Engineering | Bruce Jagolinzer |  | 2021-07-05 | 2021-06-28 | 2021-07-06 | 2021-06-28 | 2021-07-05 | 2024-07-31 | 2024-08-01 | 2024-08-14 | [127 empty] | 2024-08-05 | [37 empty] | TRUE | TRUE | 672 | 0 | 0 | 1900 | 1900 | 1900
673 |  | Marshall Ripley | Rick Duperre | 2021-06-21 | [31 empty] | 3 - MOSH |  | 635D2 | 666 |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED |  | Ian Clark | Elevate Power | Presumpscot Hydro LLC | Olde Canal Way Gorham | 2000220628 | 30014949868 | Hydro | 3990 | 3.99 |  |  |  | 43.702 | -70.3989 | 95 Olde Canal Way |  |  | Gorham | 10 | MOSHERS | 635D2 | 635T2 |  | 9310-L0271-2240-0390-ED00010 |  | GFOV TBD During Study Phase | T-GFOV TBD During Study Phase |  |  |  |  | K&A Engineering | Bruce Jagolinzer |  | 2021-07-05 | 2021-06-28 | 2021-07-06 | 2021-06-28 | 2021-07-05 | 2021-07-05 | 2021-07-15 | 2021-07-19 | 2021-07-19 | 2021-07-29 | 2021-07-29 | 2021-08-11 |  |  | 2021-08-11 |  |  | CS | 2021-08-11 | [6 empty] | CS |  |  | 2021-08-11 | [11 empty] | 2021-08-12 | [7 empty] | 2021-08-12 | 2021-08-12 | [8 empty] | 2021-08-13 | [11 empty] | 2021-10-20 | [6 empty] | 2021-10-19 | [8 empty] | 2021-10-19 | [17 empty] | 2021-11-15 | [7 empty] | 2021-11-15 | [7 empty] | 2021-12-03 |  | 2021-12-07 | 2023-03-09 | 2022-01-15 | 2023-03-16 | 2025-06-10 | 2025-06-10 |  |  |  | 62783 |  | 145056 | 2022-09-07 |  | 2021-07-13: 2021-12-08; 2021-07-13: 2022-01-17 | [17 empty] | Requested | [11 empty] | TRUE | TRUE | 673 | 2021-12-08 | 2021-12-08 | 2021 | 2022 | 2022
674 |  | Marshall Ripley | Rick Duperre | 2021-06-21 | 2023-05-30 | L2_Bump |  | 2023-07-18 | L2_Bump |  | 2025-07-09 | L2_With | [23 empty] | 3 - NOWI |  | 639D3 | 667 | Yes | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED |  | Ian Clark | Elevate Power | Presumpscot Hydro LLC | Middle Jam Rd Standish | 2000220628 | 30013163792 | Hydro | 4200 | 4.2 |  |  |  | 43.8257 | -70.4532 | 50 Middle Jam Rd |  |  | Standish | 205 | NORTH WINDHAM | 639D3 | 639T2 | 12.47 | 9310-L0277-5500-0041-ED00129 | Non-FERC | NOT IMPACTED | NOT IMPACTED |  |  |  |  | K&A Engineering | Bruce Jagolinzer |  | 2021-07-05 | 2021-06-28 | 2021-07-06 | 2021-06-28 | 2021-07-05 | 2021-10-21 | 2021-11-15 | 2021-11-04 | 2021-11-15 | 2021-12-02 | 2021-12-02 | 2021-12-16 |  |  | 2021-12-02 |  |  | CS | 2021-12-02 | [6 empty] | CS |  |  | 2021-12-02 |  |  | 2023-06-01 | [11 empty] | 2023-06-16 | 2023-10-09 |  |  |  | 2021-12-15 | 2021-12-15 |  |  | 2023-06-07 | 2024-04-25 |  |  |  |  | 2021-12-21 |  |  | 2023-06-30 | 2024-04-25 | [7 empty] | 2022-02-28 | [6 empty] | 2022-02-28 |  |  |  | 2024-07-01 |  |  |  |  | 2022-02-28 |  |  |  | 2024-07-01 |  |  |  |  | 2022-02-28 |  |  | 2024-07-15 | [5 empty] | 2022-03-07 | [7 empty] | 2022-03-07 | [7 empty] | 2022-03-24 |  | 2022-03-24 | 2024-07-26 | 2022-03-25 | 2024-08-13 | [5 empty] | 494280 | 2022-02-28 | 319986 | 2024-06-26 |  | 2021-07-13: 2022-03-25; 2021-07-13: 2022-03-25; 2021-07-13: 2024-08-15; 2021-07-13: 2024-08-15 | [13 empty] | Q4 2025 |  |  |  | Requested | [11 empty] | FALSE | TRUE | 674 | 2022-03-25 | 2022-03-25 | 2022 | 2022 | 2022
675 |  |  | KRISTOFER COLEMAN | 2021-07-02 | [31 empty] | 1 - BOOT |  | 209D3 |  |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Matt Doubleday | ReWild Renewables LLC | ReWild Renewables LLC | 586 Wiscasset Rd | 2000198992 | 30013350761 | Solar | [5 empty] | 43.9006 | -69.6158 | 586 Wiscasset Rd |  |  | Boothbay | 108 | BOOTHBAY HARBOR | 209D3 | 639T2 | 12.47 | 9310-L0026-0550-0162-ED00016 | Non-FERC | WITHDRAWN | WITHDRAWN |  |  |  |  | K&A Engineering | Bruce Jagolinzer |  | 2021-07-19 | 2021-07-12 | 2021-07-19 | 2021-07-12 | 2021-07-19 | 2021-07-19 |  | 2021-08-02 |  | 2021-07-27 | 2021-07-28 | 2021-08-10 |  |  | 2021-07-29 |  |  | CS | 2021-07-29 | [6 empty] | CS |  |  | 2021-07-29 | [11 empty] | 2021-07-30 | [17 empty] | 2021-08-10 | [11 empty] | 2021-10-14 | [6 empty] | 2021-10-14 | [8 empty] | 2021-10-14 | [17 empty] | 2021-10-20 | [7 empty] | 2021-10-20 | [7 empty] | 2021-10-26 |  | 2021-10-26 |  | 2021-10-26 | [6 empty] | 114141 |  |  |  | 2022-06-28 | 2021-07-13: 2021-10-26; 2021-07-13: 2021-10-27 | [17 empty] | Requested | [11 empty] | TRUE | TRUE | 675 | 2021-10-26 | 2021-10-26 | 2021 | 2021 | 2021
676 |  |  | Anthony Boucher | 2021-07-02 | 2024-10-09 | wthdw | [29 empty] | 3 - LINC |  | 800D1 | 617 | Yes | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Alex | REVISION ENERGY INC | REVISION ENERGY INC | WHITNEY ST / LINCOLNVILLE | 2000038393 | 30013320244 | Solar | [5 empty] | 44.2983 | -69.0124 | Whitney Road |  |  | Lincolnville | 6 | LINCOLNVILLE | 800D1 | 800T1 | 34.5 | 9310-L0378-3300-0095-ED00013 |  | WITHDRAWN | WITHDRAWN |  |  |  |  | K&A Engineering | Bruce Jagolinzer |  | 2021-07-19 | 2021-07-12 | 2021-07-19 | 2021-07-12 | 2021-07-19 | 2022-01-19 | 2022-01-27 | 2022-02-02 | 2022-01-27 | 2022-01-28 | 2022-01-28 | 2022-02-11 |  |  | 2022-02-11 | 2022-07-01 |  | CS | 2022-02-11 | RS | 2022-07-01 |  |  |  |  | CS |  |  | 2022-02-11 | 2022-07-26 |  | 2024-10-09 | [9 empty] | 2022-07-01 |  | 2024-10-23 | [5 empty] | 2022-03-07 | 2022-07-27 |  | 2024-10-31 | [5 empty] | 2022-04-22 | 2022-08-12 |  | 2024-10-31 | [8 empty] | 2022-06-28 | 2022-09-26 | [5 empty] | 2022-05-23 | 2022-09-22 |  | 2025-01-10 | [5 empty] | 2022-05-23 | 2022-09-23 |  | 2025-01-10 | [5 empty] | 2022-05-24 | 2022-09-28 | [7 empty] | 2022-06-01 | 2022-09-28 | [6 empty] | 2022-06-01 | 2022-09-28 | [6 empty] | 2022-10-03 |  | 2022-10-05 | 2023-03-02 | 2022-10-13 | 2023-03-03 | 2022-02-07 | 2022-02-14 |  |  |  | 579351 | 2023-02-22 | 786940 | 2025-01-14 | 2025-04-25 | 2022-10-14 | 2022-10-17 | 2023-03-03 | 2023-03-06 | 2025-02-27 | 2025-02-27 | [15 empty] | Q4 2025 | [15 empty] | TRUE | TRUE | 676 | 2022-10-14 | 2022-10-14 | 2022 | 2022 | 2022
677 |  | Lanie Patterson | Brent Brooks | 2021-07-07 | 2022-07-28 | L2_Bump |  | 2022-09-15 | L2_Bump | [26 empty] | 12 - MONM |  | 457D1 | 659 |  | WITHDRAWN | WITHDRAWN |  | Christian L'Oranger | NBD SOLAR MAINE LLC | Gardiner Rd Solar LLC | 0 GARDINER RD WALES | 2000226285 | 30013242646 | Solar | [5 empty] | 44.174 | -70.0046 | 0 Gardiner Rd |  |  | Wales | 31H | MONMOUTH | 457D1 | 457T1 | 12.47 | 9310-L0198-6140-0017-ED00254 | Non-FERC | WITHDRAWN | WITHDRAWN |  |  |  |  | K&A Engineering | Bruce Jagolinzer |  | 2021-07-21 | 2021-07-14 | 2021-07-21 | 2021-07-14 | 2021-07-22 | 2022-03-10 | 2022-03-21 | 2022-03-24 | 2022-03-22 | 2022-03-22 | 2022-03-22 | 2022-04-05 |  |  | 2022-04-05 |  |  | CS | 2022-04-05 | RS | [5 empty] | CS |  |  | 2022-04-05 | 2022-07-22 |  | 2022-12-16 | [11 empty] | 2023-01-06 | [5 empty] | 2022-04-05 |  |  | 2023-01-12 | [5 empty] | 2022-04-06 | 2022-07-27 |  | 2023-01-13 | [8 empty] | 2022-06-10 | 2022-09-07 | [5 empty] | 2022-06-03 |  |  | 2023-02-27 | [5 empty] | 2022-06-03 |  |  | 2023-02-27 | [5 empty] | 2022-06-13 | [8 empty] | 2022-06-15 | [7 empty] | 2022-06-15 | [22 empty] | 2023-03-22 | [37 empty] | TRUE | TRUE | 677 | 0 | 0 | 1900 | 1900 | 1900
678 |  | Rigel Paradise | Rick Duperre | 2021-07-16 | 2023-10-13 | wthdw | [29 empty] | 5 - BUCO |  | 612D2 | 446 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Colin Derhammer | MELINK SOLAR DEVELOPMENT | Acton Solar LLC | Kelly Orchard (Acton) | 2000150090 | 30012185333 | Solar | [5 empty] | 43.5333 | 70.9133 | 82 Sanborn Rd |  |  | Acton | 8 | BUTLER'S CORNER | 612D2 | 612T1 | 12.47 | 9310-L0226-0020-0044-ED00118 | Non-FERC | WITHDRAWN | WITHDRAWN | 325000 | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2021-07-30 | 2021-07-23 | 2021-07-30 | 2021-07-23 | 2021-07-30 | 2021-07-30 | 2021-08-06 | 2021-08-13 | 2021-08-06 | 2021-08-19 | 2021-08-19 | 2021-09-02 |  |  | 2021-08-26 |  |  | CS | 2021-08-26 | [6 empty] | CS |  |  | 2021-08-26 | [19 empty] | 2021-09-10 | 2021-09-10 | [8 empty] | 2021-09-14 | [11 empty] | 2021-11-18 | [6 empty] | 2021-11-12 | [8 empty] | 2021-11-12 | [17 empty] | 2021-11-15 | [7 empty] | 2021-11-15 | [7 empty] | 2021-11-16 |  | 2021-11-18 | 2022-09-12 | 2021-12-07 | 2022-10-18 | [9 empty] | 2023-12-11 | 2021-07-13: 2021-12-08; 2021-07-13: 2022-01-07; 2021-07-13: 2022-10-19; 2021-07-13: 2022-10-19 | [17 empty] | Requested | [11 empty] | TRUE | TRUE | 678 | 2021-12-08 | 2021-12-08 | 2021 | 2022 | 2022
679 |  | Marshall Ripley | Rick Duperre | 2021-07-20 | [31 empty] | 8 - BONE |  | 610D2 | 364 |  | WITHDRAWN | WITHDRAWN |  | Dan Band | Louth Callan Renewables | 326 LONG PLAINS ROAD SOLAR LLC. | Plains Rd Buxton | 2000199323 | 30014539479 | Solar | [5 empty] | 43.6773 | -70.5831 | 320 Long Plains Rd |  |  | Buxton |  | BONNY EAGLE | 610D2 | 610T4 | 12.47 | 9310-L0221-0820-0045-ED00157 | Non-FERC | WITHDRAWN | WITHDRAWN |  |  |  |  | K&L Engineering | Bruce Jagolinzer |  | 2021-08-03 | 2021-07-27 | 2021-08-03 | 2021-07-27 | 2021-08-03 | 2022-02-15 | 2022-02-28 | 2022-03-02 | 2022-03-21 | 2022-03-24 | 2022-03-24 | 2022-04-07 |  |  | 2022-03-29 |  |  | CS | 2022-03-29 | [6 empty] | CS |  |  | 2022-04-05 | [29 empty] | 2022-06-06 | [11 empty] | 2022-08-10 | [6 empty] | 2022-07-26 | [8 empty] | 2022-08-12 | [8 empty] | 2022-08-26 | [8 empty] | 2022-08-26 | [7 empty] | 2022-08-26 | [7 empty] | 2022-09-19 |  | 2022-09-20 |  |  |  | 2022-02-07 | 2022-02-14 | [7 empty] | 2022-11-14 | [37 empty] | TRUE | TRUE | 679 | 0 | 0 | 1900 | 1900 | 1900
680 |  | Govinda Neupane |  | 2021-07-20 | [31 empty] | 9 - LVFA |  | 428D2 | 623 |  | WITHDRAWN | WITHDRAWN |  | Dan Band | Louth Callan Renewables | LOUTH CALLAN RENEWABLES | Diamond Rd Livermore Falls | 2000199323 | 30013374407 | Solar | [5 empty] | 44.4276 | -70.1582 | Diamond Rd |  |  | Livermore Falls | 25.1 | LIVERMORE FALLS | 428D1 | 428T1 | 12.47 | 9310-L0161-3350-0096-ED00032 | FERC | WITHDRAWN | WITHDRAWN |  |  |  |  | K&L Engineering | Bruce Jagolinzer |  | 2021-08-03 | 2021-07-27 | 2021-08-03 | 2021-07-27 | 2021-08-03 | 2022-08-04 | 2022-08-24 | 2022-08-18 | 2022-08-30 | 2022-08-30 | 2022-08-30 | [124 empty] | 2022-09-13 | [37 empty] | TRUE | TRUE | 680 | 0 | 0 | 1900 | 1900 | 1900
681 |  | Rigel Paradise | Rick Duperre | 2021-07-22 | [31 empty] | 1 - KENN |  | 629D3 |  |  | WITHDRAWN | WITHDRAWN |  | Graham Basecke | Louth Callan Renewables | LOUTH CALLAN RENEWABLES | 34 mill stream arundel | 2000199323 | 30013374423 | Solar | [5 empty] | 43.4293 | -70.4951 | 34 Mill Stream LN |  |  | Arundel |  | KENNEBUNKPORT | 629D3 | 629T2 | 12.47 | TBD | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&L Engineering | Bruce Jagolinzer |  | 2021-08-05 | 2021-07-29 | 2021-08-05 | 2021-07-29 | 2021-08-05 | 2021-08-06 | 2021-09-17 | 2021-08-20 | 2021-09-28 | 2021-09-29 | 2021-09-29 | 2021-10-08 |  |  | 2021-10-14 |  |  | FS | 2021-11-12 | [6 empty] | Split | 2021-11-12 | [20 empty] | 2021-11-11 | [8 empty] | 2021-11-24 | [8 empty] | Yes |  |  |  |  | 2022-01-28 |  |  |  |  | 2021-12-28 | [26 empty] | 2022-01-04 | [7 empty] | 2022-01-04 | [24 empty] | 2022-03-09 | [37 empty] | TRUE | TRUE | 681 | 0 | 0 | 1900 | 1900 | 1900
682 |  | Govinda Neupane |  | 2021-08-11 | [31 empty] | 3 - CORI |  | 811D1 | 306 |  | WITHDRAWN | WITHDRAWN |  | Nicholas Mazuroski | Dirigo/BNRG | BD SOLAR CORINNA LLC | MILL ST CORINNA | 2000138859 |  | Solar | [5 empty] | 44.9158 | -69.2561 | 52 Mill Street |  |  | Corinna |  | CORINNA | 811D1 | 811T1 |  | 9310-L0391-1220-0051-ED00001 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2021-08-18 | 2021-08-25 | 2021-08-18 | 2021-08-25 |  | 2021-09-07 | 1900-01-12 | 2021-09-07 | 2021-09-21 | 2021-09-21 | [6 empty] | CS | 2021-12-03 | [9 empty] | 2021-12-03 | [19 empty] | 2021-12-17 | 2021-12-17 | [8 empty] | 2021-12-23 | [11 empty] | 2022-03-03 | [60 empty] | n/a | n/a | n/a | n/a | 2022-01-12 | [25 empty] | Partial Study | [11 empty] | TRUE | TRUE | 682 | 0 | 0 | 1900 | 1900 | 1900
683 |  |  | KRISTOFER COLEMAN | 2021-08-16 | [31 empty] | 2 - BOOT |  | 209D2 | 675 |  | WITHDRAWN | WITHDRAWN |  | Nathaniel Curtis | MIDCOAST SOLAR LLC | MIDCOAST SOLAR LLC | 63 giles rd boothbay harbor | 2000162495 | 30013472698 | Solar | [5 empty] | 43.8663 | -69.6072 | 63 Giles Rd |  |  | Boothbay Harbor |  | BOOTHBAY HARBOR | 209D2 |  |  | 9310-L0025-0560-0021-ED00048 |  | WITHDRAWN | WITHDRAWN | [8 empty] | 2021-08-23 | 2021-08-30 |  |  |  |  | 1900-01-12 | [127 empty] | 2021-12-03 | [37 empty] | TRUE | TRUE | 683 | 0 | 0 | 1900 | 1900 | 1900
684 |  | Lanie Patterson | Brent Brooks | 2021-08-16 | [31 empty] | 2 - CLIN |  | 810D1 | 219 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Shalin/Henry | Nexamp, Inc | CLINTON RENEWABLES LLC | 65 Mutton Ln Clinton | 2000285248 | 30014045477 | Solar | [5 empty] | 44.65 | -69.5 | 65 Mutton Lane |  |  | Clinton | 1 | CLINTON | 810D1 | 209T2 |  | 9310-L0390-1170-0043-ED00001 |  | WITHDRAWN | WITHDRAWN |  |  |  |  | K&L Engineering | Bruce Jagolinzer |  | 2021-08-30 | 2021-08-23 | 2021-08-30 | 2021-08-23 | 2021-08-30 | 2021-08-30 | 2021-09-10 | 2021-09-14 | 2021-09-13 | 2021-09-16 | 2021-09-16 | 2021-09-30 |  |  | 2021-09-30 |  |  | CS | 2021-10-08 | [6 empty] | CS |  |  | 2021-10-08 | [11 empty] | 2021-10-15 | [7 empty] | 2021-10-15 | 2021-10-15 | [8 empty] | 2021-10-15 | [11 empty] | 2021-12-21 | [6 empty] | 2021-11-30 | [8 empty] | 2021-12-03 | [8 empty] | 2021-12-03 | [8 empty] | 2021-12-08 | [7 empty] | 2021-12-08 | [7 empty] | 2021-12-30 | 2021-12-21 | 2022-01-03 |  | 2022-01-27 | [6 empty] | 221657 |  |  |  | 2024-07-19 | 2021-07-13: 2022-01-03; 2021-07-13: 2022-02-02; 2021-07-13: 2022-05-03 | [17 empty] | Requested | [11 empty] | TRUE | TRUE | 684 | 2022-01-03 | 2022-01-03 | 2022 | 2022 | 2022 |  |  | 44551
685 |  | Marshall Ripley | Rick Duperre | 2021-08-24 | [31 empty] | 2 - ELM |  | 620D2 | 357 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Nathaniel Curtis | C2 ENERGY DEVELOPMENT LLC | C2 ENERGY DEVELOPMENT LLC | 269 Sligo Rd Yarmouth | 2000200909 | 30013512477 | Solar | [5 empty] | 43.8128 | -70.2058 | 269 Sligo Rd | 269 | Sligo Rd | Yarmouth | 21 | ELM STREET | 620D2 | 620T3 | 12.47 | 9310-L0236-6650-0126-ED00026 | FERC | WITHDRAWN | WITHDRAWN |  |  |  |  | K&L Engineering | Bruce Jagolinzer |  | 2021-09-08 | 2021-08-31 | 2021-09-08 | 2021-08-31 | 2021-09-08 | 2021-09-22 | 2021-10-27 | 2021-10-06 | 2021-11-04 | 2021-11-05 | 2021-11-05 | 2021-11-19 |  |  | 2021-11-22 |  |  | CS | 2021-11-29 | [6 empty] | CS |  |  | 2021-11-29 |  |  | 2023-04-03 | [11 empty] | 2023-04-14 |  |  |  |  | 2021-12-14 | 2021-12-14 |  |  | 2023-04-12 | [5 empty] | 2021-12-15 |  |  | 2023-04-19 | [8 empty] | 2022-02-22 | [6 empty] | 2022-02-22 | [8 empty] | 2022-03-07 | [8 empty] | 2022-03-08 | [8 empty] | 2022-02-24 | [7 empty] | 2022-02-24 | [7 empty] | 2022-05-05 |  | 2022-05-05 | 2023-03-02 | 2022-05-26 | [6 empty] | 747789 | 2022-02-21 | 606176 | 2023-02-16 | 2024-03-14 | 2021-07-13: 2022-05-26; 2021-07-13: 2022-05-31; 2021-07-13: 2023-03-03; 2021-07-13: 2023-03-06 | [17 empty] | Requested | [11 empty] | TRUE | TRUE | 685 | 2022-05-26 | 2022-05-26 | 2022 | 2022 | 2022
686 |  | Marshall Ripley | Rick Duperre | 2021-09-14 | [31 empty] | 4 - PRCO |  | 647D3 | 636 |  | WITHDRAWN | WITHDRAWN |  | Dan Band | Louth Callan Renewables | LOUTH CALLAN RENEWABLES | 44 LAND OF NOD WINDHAM | 2000199323 | 30013386666 | Solar | [5 empty] | 43.7472 | -70.37 | 44 Land of Nod Rd | 44 | Land of Nod Rd | Windham | 515 | PRIDES CORNER | 647D3 | 647T2 | 7.2 | 9310-L0306-6390-0070-ED00074 |  | WITHDRAWN | WITHDRAWN |  |  |  |  | K&L Engineering | Bruce Jagolinzer |  | 2021-09-28 | 2021-09-21 | 2021-09-28 | 2021-09-21 | 2021-09-28 |  |  | 1900-01-12 | [127 empty] | 2023-09-19 | [37 empty] | TRUE | TRUE | 686 | 0 | 0 | 1900 | 1900 | 1900
687 |  | Govinda Neupane |  | 2021-10-19 | [31 empty] | 5 - EMDE |  | 868D1 | 580 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Tejas Sinthalapad Jayakumar | Nexamp, Inc | NEXAMP SOLAR LLC | 610 Kennebec River Rd Embden | 2000114877 | 30013664831 | Solar | [5 empty] | 44.9259 | 69.8677 | 610 Kennebec River Rd | 610 | Kennebec River Rd | Embden | 16 | EMBDEN | 868D1 | 868T1 | 12.47 | 9310-L0452-1870-0034-ED00167 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2021-10-26 | 2021-10-26 | 2021-11-02 | 2021-10-19 | 2021-11-02 | 2021-11-05 | 2021-11-22 | 2021-11-22 | 2021-12-01 | 2021-12-03 | 2021-12-03 | 2021-12-17 |  |  | 2021-12-10 |  |  | CS | 2021-12-10 | [6 empty] | CS |  |  | 2021-12-10 | [19 empty] | 2021-12-23 | 2021-12-23 | [8 empty] | 2022-01-03 | [11 empty] | 2022-03-09 | [6 empty] | 2022-03-09 | [8 empty] | 2022-03-09 | [8 empty] | 2022-03-10 | [8 empty] | 2022-03-15 | [7 empty] | 2022-03-15 | [7 empty] | 2022-10-24 |  | 2022-10-22 |  | 2022-11-01 | [10 empty] | 2023-12-28 | 2021-07-13: 2022-11-02; 2021-07-13: 2022-11-03 | [29 empty] | TRUE | TRUE | 687 | 2022-11-02 | 2022-11-02 | 2022 | 2022 | 2022
688 |  | Marshall Ripley | Rick Duperre | 2021-10-25 | 2023-05-30 | L2_Bump |  | 2023-07-18 | L2_bump | [26 empty] | 4 - NOWI |  | 639D2 | 674 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Geoff Sparrow | GREEN LANTERN DEVELOPMENT LLC | FREEMAN HILL GLC SOLAR LLC | 960 ROOSEVELT TRL / WINDHAM | 2000197005 | 30013697500 | Solar | [5 empty] | 43.8566 | -70.4526 | 960 Roosevelt Trail | 960 | Roosevelt Trail | Windham | 334.1 | NORTH WINDHAM | 639D2 | 639T2 | 12.47 | 9310-L0276-6390-0101-ED00526 | FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2021-11-08 | 2021-11-01 | 2021-11-08 | 2021-11-01 | 2021-11-08 | 2022-03-25 | 2022-03-28 | 2022-04-08 | 2022-04-12 | 2022-04-12 | 2022-04-12 | 2022-04-26 |  |  | 2022-04-27 | 2022-09-01 |  | CS | 2022-04-27 | RS | 2022-09-19 |  |  |  |  | CS |  |  | 2022-04-27 | 2022-09-19 | [11 empty] | 2022-09-19 | [7 empty] | 2022-05-02 | 2022-09-21 | [7 empty] | 2022-05-17 | 2022-09-21 | [10 empty] | 2022-07-15 | 2022-11-03 | [5 empty] | 2022-07-14 | 2022-11-01 | [7 empty] | 2022-07-15 | 2022-11-02 | [7 empty] | 2022-08-17 | 2022-11-07 | [7 empty] | 2022-08-24 | 2022-11-07 | [6 empty] | 2022-08-24 | [7 empty] | 2022-11-23 |  | 2022-11-28 |  | 2022-11-29 | [6 empty] | 460827 | 2022-10-31 |  |  | 2023-07-20 | 2021-07-13: 2022-11-29; 2021-07-13: 2022-11-29 | [17 empty] | Requested | [11 empty] | TRUE | TRUE | 688 | 2022-11-29 | 2022-11-29 | 2022 | 2022 | 2022
689 |  | Rigel Paradise | Rick Duperre | 2021-11-30 | 2023-10-13 | L2_Bump |  | 2024-05-01 | wthdw | [26 empty] | 7 - LEBA |  | 695D2 | 551 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Paula Fitzgerald | Novel Energy Solutions LLC | LEBANON MAINE SOLAR LLC | 0 UPPER CROSS RD / LEBANON | 2000228561 | 30015023275 | Solar | [5 empty] | 43.4075 | -70.8886 | 0 Upper Cross Road | 0 | Upper Cross Road | Lebanon | 34 | LEBANON | 695D2 | 695T1 | 12.47 | 9310-L0473-3190-0066-ED00035 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2021-12-07 | 2021-12-07 | 2021-12-14 | 2021-12-07 | 2021-12-14 | 2021-12-14 | 2022-01-18 | 2021-12-29 | 2022-01-18 | 2022-01-19 | 2022-01-19 | 2022-02-02 |  |  | 2022-01-21 |  |  | CS | 2022-01-21 | [6 empty] | CS |  |  | 2022-01-21 |  |  | 2024-05-23 |  |  |  | 2022-02-01 |  |  |  |  | 2022-01-25 | [7 empty] | 2022-02-01 | 2022-02-01 | [8 empty] | 2022-02-02 | [11 empty] | 2022-04-07 | [6 empty] | 2022-03-25 | [8 empty] | 2022-03-25 | [8 empty] | 2022-03-28 | [8 empty] | 2022-03-29 | [7 empty] | 2022-03-30 | [7 empty] | 2022-07-12 |  | 2022-07-12 |  | 2022-08-11 | [10 empty] | 2024-06-11 | 2021-07-13: 2022-08-12; 2021-07-13: 2022-08-12 | [17 empty] | Requested | [11 empty] | TRUE | TRUE | 689 | 2022-08-12 | 2022-08-12 | 2022 | 2022 | 2022
690 |  | Marshall Ripley | Rick Duperre | 2021-11-30 | [31 empty] | 3 - ELM |  | 620D4 | 685 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Chris Byers | Branch Renewable Energy | YARMOUTH WATER DISTRICT | 238 SWEETSER RD N YARMOUTH | 2000265402 | 30013777336 | Solar | [5 empty] | 43.8255 | -70.2274 | 238 Sweetser Rd | 238 | Sweetser Rd | North Yarmouth | 9 | ELM STREET | 620D4 | 620T2 | 12.47 | 9310-L0238-4200-0034-ED00023 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2021-12-07 | 2021-12-07 | 2021-12-14 | 2021-12-07 | 2021-12-14 | 2022-05-31 | 2022-06-20 | 2022-06-14 | 2022-06-21 | 2022-06-22 | 2022-06-22 | 2022-07-07 |  |  | 2022-07-11 |  |  | CS | 2022-07-11 | [6 empty] | CS |  |  | 2022-07-12 | [11 empty] | 2022-07-19 | [8 empty] | 2022-07-19 | [8 empty] | 2022-07-19 | [11 empty] | 2022-09-21 | [6 empty] | 2022-09-21 | [8 empty] | 2022-09-22 | [8 empty] | 2022-09-26 | [8 empty] | 2022-09-26 | [7 empty] | 2022-09-26 | [7 empty] | 2022-10-17 |  | 2022-10-18 |  | 2022-11-15 | [6 empty] | 122293 | 2022-09-20 |  |  | 2023-03-28 | 2021-07-13: 2022-11-17; 2021-07-13: 2022-11-17 | [29 empty] | TRUE | TRUE | 690 | 2022-11-17 | 2022-11-17 | 2022 | 2022 | 2022
691 |  | Eben Snow | Brent Brooks | 2021-12-01 | 2023-06-28 | L2_Bump | [29 empty] | 4 - SABA |  | 450D1 | 649 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Viqui Carballo | Novel Energy Solutions LLC | ME L HEUREUX CSG LLC | 20 OLD CHADBOURNE ST LEWISTON | 2000250310 | 30014193582 | Solar | [5 empty] | 44.1044 | -70.1223 | 16 Old Chadbourne Rd | 16 | Old Chadbourned Rd | Lewiston | 2 | SABATTUS | 450D1 | 450T1 | 12.47 | 9310-L0192-3230-0295-ED00013 | Non-FERC | WITHDRAWN | WITHDRAWN |  |  |  |  | K&A Engineering | Bruce Jagolinzer |  | 2021-12-08 | 2021-12-08 | 2021-12-15 | 2021-12-08 | 2021-12-15 | 2022-02-02 | 2022-02-04 | 2022-02-16 | 2022-02-07 | 2022-02-10 | 2022-02-10 | 2022-02-25 |  |  | 2022-03-01 |  |  | CS | 2022-03-02 | [6 empty] | CS |  |  | 2022-03-02 |  |  |  | 2022-03-15 |  |  |  | 2022-03-15 |  |  |  | 2022-03-05 | [7 empty] | 2022-03-15 | 2022-03-15 | [8 empty] | 2022-03-16 | [11 empty] | 2022-05-18 | [6 empty] | 2022-05-12 | [8 empty] | 2022-05-23 | [8 empty] | 2022-05-23 | [8 empty] | 2022-05-26 | [7 empty] | 2022-05-26 | [7 empty] | 2022-05-26 |  | 2022-05-31 | 2022-06-14 | 2022-06-17 | 2022-06-17 | 2022-02-07 | 2022-02-14 | [7 empty] | 2023-10-03 | 2021-07-13: 2022-06-14; 2021-07-13: 2022-06-17 | [17 empty] | Requested | [11 empty] | TRUE | TRUE | 691 | 2022-06-14 | 2022-06-14 | 2022 | 2022 | 2022
692 |  | Lanie Patterson | Brent Brooks | 2021-12-13 | 2023-07-07 | wthdw | [29 empty] | 6 - PDRD |  | 262D1 | 389 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Ryan Darlow | Norwich Solar Technologies | READFIELD MAIN STREET SOLAR LLC | MAINE ST READFIELD | 2000259899 | 30013700890 | Solar | [5 empty] | 44.3563 | -69.8906 | 0 Main St | 0 | Main St | Readfield | 104 | PUDDLEDOCK ROAD | 262D1 | 34.5kV Bus | 12.47 | 9310-L0101-4910-0057-ED00001 | Non-FERC | WITHDRAWN | WITHDRAWN |  |  |  |  | K&A Engineering | Bruce Jagolinzer |  | 2021-12-20 | 2021-12-20 | 2021-12-28 | 2021-12-20 | 2021-12-28 | 2021-12-28 | 2022-01-18 | 2022-01-12 | 2022-01-19 | 2022-01-20 | 2022-01-20 | 2022-02-02 |  |  | 2022-01-27 |  | 2022-07-05 | CS | 2022-01-27 | FC | 2022-07-05 |  |  |  |  | CS |  |  | 2022-01-27 |  | 2022-07-05 | [9 empty] | 2022-02-02 |  | 2022-07-26 | [5 empty] | 2022-01-31 | 2022-01-31 | [8 empty] | 2022-02-02 |  | 2022-07-27 | [9 empty] | 2022-04-07 |  | 2022-09-29 |  |  |  |  | 2022-03-29 |  | 2022-08-31 | [6 empty] | 2022-03-28 | [10 empty] | 2022-09-13 | [8 empty] | 2022-09-13 | [7 empty] | 2022-09-13 | [5 empty] | 2022-10-06 |  | 2022-11-03 | 2023-02-15 | 2022-11-15 | 2023-02-16 | [5 empty] | 365407 | 2022-03-16 | 319726 | 2022-08-28 | 2024-09-05 | 2021-07-13: 2022-11-17; 2021-07-13: 2022-11-17; 2021-07-13: 2023-02-16; 2021-07-13: 2023-02-16 | [17 empty] | Requested | [11 empty] | TRUE | TRUE | 692 | 2022-11-17 | 2022-11-17 | 2022 | 2022 | 2022
693 |  |  | Anthony Boucher | 2021-12-21 | [31 empty] | 4 - WALD |  | 252D1 | 609 |  | WITHDRAWN | WITHDRAWN |  | Emily Byrne | CITIZENS ENERGY CORPORATION | PORTAGE RIVER SOLAR LLC | 161 Old Augusta Rd Waldoboro | 2000200287 | 30012896004 | Solar | [5 empty] | 44.1698 | -69.3252 | 161 Old Augusta Rd |  |  | Waldoboro | 005 | WALDOBORO | 252D1 | 252T1 | 12.47 | 9310-L0090-6130-0043-ED00002 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  |  | 2021-12-29 | 2022-01-06 | 2021-12-29 | 2022-01-06 | 2022-01-05 | 2022-01-18 | 2022-01-20 | 2022-01-18 | 2022-01-20 | 2022-01-20 | 2022-02-03 |  |  | 2022-02-08 |  | 2022-08-01 | CS | 2022-02-08 | FC | 2022-08-01 |  |  |  |  | CS |  |  | 2022-02-08 | [19 empty] | 2022-02-09 | 2022-02-09 | [8 empty] | 2022-02-16 | [11 empty] | 2022-04-22 | [6 empty] | 2022-04-25 | [8 empty] | 2022-06-01 |  | 2022-09-01 | [6 empty] | 2022-06-16 |  | 2022-09-13 | [6 empty] | 2022-06-27 |  | 2022-09-13 | [5 empty] | 2022-06-27 |  | 2022-09-15 | [5 empty] | 2022-11-03 | [14 empty] | 2022-11-15 | [37 empty] | TRUE | TRUE | 693 | 0 | 0 | 1900 | 1900 | 1900
694 |  | Govinda Neupane |  | 2021-12-22 | [31 empty] | 2 - STRA |  | 877D1 | 261 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Kelsey Haley | New Leaf Energy, Inc | 510 PV PROJECT DEVELOPMENT LLC | 510 PV PROJECT DEVELOPMENT LLC | 2000113260 | 30013835266 | Solar/DC BESS | [5 empty] | 45.1502 | -70.4576 | Vaughn Road |  | Vaughn Road | Eustis | 8 | STRATTON | 877D1 | 877T1 | 7.2 | 9310-L0462-1900-0033-ED00016 | FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2021-12-30 | 2021-12-30 | 2022-01-07 | 2021-12-30 | 2022-01-07 | 2022-01-07 | 2022-01-18 | 2022-01-24 | 2022-01-18 | 2022-01-20 | 2022-01-20 | 2022-02-03 |  |  | 2022-02-17 |  |  | CS | 2022-02-18 | [6 empty] | CS |  |  | 2022-02-18 |  |  | 2021-03-08 |  |  |  | 2021-03-08 |  |  |  |  | 2021-03-17 | [7 empty] | 2022-03-17 | 2022-03-17 | [8 empty] | 2022-03-21 | [11 empty] | 2022-05-24 | [6 empty] | 2022-05-18 | [8 empty] | 2022-05-19 | [8 empty] | 2022-07-12 | [8 empty] | 2022-07-12 | [7 empty] | 2022-07-12 | [7 empty] | 2022-07-12 |  | 2022-07-12 |  | 2022-08-04 |  | 2022-02-07 | 2022-02-14 | [7 empty] | 2024-11-06 | 2021-07-13: 2022-08-08; 2021-07-13: 2022-08-09 | [17 empty] | Requested | [11 empty] | TRUE | TRUE | 694 | 2022-08-08 | 2022-08-08 | 2022 | 2022 | 2022
695 |  | Govinda Neupane |  | 2022-01-07 | 2022-07-19 | L2_Bump | [29 empty] | 9 - WSTN |  | 866D2 | 556 |  | WITHDRAWN | WITHDRAWN |  | Jonathan W. Spohn | YSG Solar | YSG Solar | Meadow Rd Skowhegan | 2000187633 | 30012732498 | Solar | [5 empty] | 44.7504 | -69.702 | 42 Middle Road |  | Middle Road | Skowhegan | 7H | WESTON HYDRO | 866D2 | 866T2 | 12.47 | 9310-L0451-5330-0112-ED00215 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes |  |  | K&A Engineering | Bruce Jagolinzer |  | 2022-01-14 | 2022-01-14 | 2022-01-24 | 2022-01-07 | 2022-01-24 | 2022-01-24 | 2022-01-26 | 2022-02-07 | 2022-01-26 | 2022-01-27 | 2022-01-27 | 2022-02-10 |  |  | 2022-02-01 |  |  | CS | 2022-02-01 | [6 empty] | CS |  |  | 2022-02-01 |  |  | 2023-03-31 | [11 empty] | 2023-04-17 |  |  |  |  | 2022-02-09 | 2022-02-09 |  |  | 2023-04-14 | [5 empty] | 2022-02-14 | 2022-06-28 |  | 2023-04-17 | [8 empty] | 2022-04-20 | 2022-08-09 | [5 empty] | 2022-04-20 | [8 empty] | 2022-04-21 | 2022-08-01 | [7 empty] | 2022-04-25 | [8 empty] | 2022-04-25 | [7 empty] | 2022-04-25 | [22 empty] | 2023-05-12 | [37 empty] | TRUE | TRUE | 695 | 0 | 0 | 1900 | 1900 | 1900
696 |  | Rigel Paradise | Rick Duperre | 2022-01-12 | [31 empty] | 3 - ELIO |  | 687D1 | 591 |  | WITHDRAWN | WITHDRAWN |  |  | AGGREGATE RECYCLING | WHEELABRATOR HOLDCO 1 INC | 434 dow hwy Elliot | 2000282181 | 30014001009 | Solar | [5 empty] | 43.1466 | -70.7822 | 434 Dow Hwy | 434 | Dow Hwy | Eliot | 7.1 | ELIOT | 687D1 | 687T1 | 12.47/7.2 | 9310-L0364-1830-0144-ED00009 | Non-FERC | WITHDRAWN | WITHDRAWN | [7 empty] | 2022-01-20 | 2022-01-20 | 2022-01-27 | 2022-01-20 | 2022-01-27 | 2022-01-27 | 2022-02-04 | 2022-02-10 | 2022-02-07 | 2022-02-10 | 2022-02-10 | 2022-02-25 | 2022-02-22 |  |  |  |  | FS | 2022-02-24 | [6 empty] | FS | 2022-02-24 |  |  |  |  | 2022-03-14 |  |  |  | 2022-03-14 |  |  |  | 2022-03-14 | [7 empty] | 2022-03-17 | [8 empty] | 2022-03-21 | 2022-06-28 | [10 empty] | 2022-05-11 | [6 empty] | 2022-04-26 | [8 empty] | 2022-04-26 | [8 empty] | 2022-04-29 | 2022-08-18 | [7 empty] | 2022-05-03 | 2022-08-18 | [6 empty] | 2022-05-03 | 2022-08-18 | [14 empty] | 2022-02-07 | 2022-02-14 | [7 empty] | 2022-09-07 | [37 empty] | TRUE | TRUE | 696 | 0 | 0 | 1900 | 1900 | 1900
697 |  | Govinda Neupane |  | 2022-01-24 | [31 empty] | 14 - ATHN |  | 827D1 | 470 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Sakshi Shirsat | Nexamp, Inc | NEXAMP SOLAR LLC | 13 Eaton Corner rd Eaton | 2000114877 | 30013875718 | Solar | [5 empty] | 44.926 | -69.6792 | 13 Eaton Corner Rd | 13 | Eaton Corner | Athens | 3.2 | ATHENS | 827D1 | 827T1 | 12.47 | 9310-L0411-0200-0001-ED00020 |  | WITHDRAWN | WITHDRAWN | [7 empty] | 2022-01-31 | 2022-01-31 | 2022-02-07 | 2022-01-31 | 2022-02-07 | 2022-02-07 | 2022-02-08 | 2022-02-22 | 2022-02-09 | 2022-02-09 | 2022-02-09 | 2022-02-23 | [5 empty] | CS | 2022-02-23 | [9 empty] | 2022-02-23 | [19 empty] | 2022-03-02 | 2022-03-02 | [8 empty] | 2022-03-08 | [11 empty] | 2022-05-11 | [6 empty] | 2022-05-03 | [8 empty] | 2022-05-03 | [8 empty] | 2022-05-05 | [8 empty] | 2022-05-09 | [7 empty] | 2022-05-09 | [7 empty] | 2022-05-19 |  | 2022-05-31 | 2022-06-14 | 2022-06-15 |  | 2022-02-07 | 2022-02-14 | [7 empty] | 2023-06-29 | 2021-07-13: 2022-06-14; 2021-07-13: 2022-06-16 | [17 empty] | Requested | [11 empty] | TRUE | TRUE | 697 | 2022-06-14 | 2022-06-14 | 2022 | 2022 | 2022
698 |  | Lanie Patterson | Brent Brooks | 2022-01-24 | 2022-07-09 | L2_Bump | [27 empty] | 1 - OAKL | 265 | 4 - OAKL | 4 - OAKL | 839D2 | 265 | Yes | EXECUTED | EXECUTED |  | Muhammad Omar Sohail | Novel Energy SPV 4 LLC | OAKLAND FIRST PARK SOLAR LLC | 0 First Park Dr, Oakland 04963 | 2000273465 | 30013888984 | Solar | 999 | 0.999 | 1388.4 |  |  | 44.5515 | -69.6823 | First Park Drive | 0 | First Park Drive | Oakland | Manhole 7 | OAKLAND | 839D2 | 839T1 | 12.47 | 9310-L0423-4300-0047-PM00010 | Non-FERC | COST SHARING | COST SHARING (330,000) | 97709 | [6 empty] | 2022-01-31 | 2022-01-31 | 2022-02-07 | 2022-01-31 | 2022-02-07 | 2022-02-07 | 2022-03-04 | 2022-02-22 | 2022-03-04 | 2022-03-07 | 2022-03-07 | 2022-03-21 | [5 empty] | CS | 2022-03-18 | [6 empty] | CS |  |  | 2022-12-21 | [20 empty] | 2023-01-13 | [8 empty] | 2023-02-06 | [11 empty] | 2023-04-12 | [6 empty] | 2023-04-11 | [8 empty] | 2023-04-12 | [8 empty] | 2023-04-12 | [8 empty] | 2023-04-12 | [15 empty] | 2023-04-12 |  | 2023-04-14 |  | 2023-05-02 |  | 2022-02-07 | 2022-02-14 |  |  |  | 215582 | 2023-04-11 |  |  |  | 2021-07-13: 2023-05-03; 2021-07-13: 2023-05-03 | [13 empty] | Q2 2026 |  |  |  | REQUESTED | [11 empty] | FALSE | TRUE | 698 | 2023-05-03 | 2023-05-03 | 2023 | 2023 | 2023
699 |  | Eben Snow | Brent Brooks | 2022-01-24 | [29 empty] | 1 - OXFO |  | 7 - OXFO |  | 437D1 | 445 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Kyzer Gardiola | Louth Callan Renewables | 119 Main Street Solar LLC | 119 main st oxford | 2000429687 | 30016003789 | Solar | [5 empty] | 44.1158 | -70.4367 | Main St | 119 | Main | Oxford | 64 | OXFORD | 437D1 | 437T1 | 12.47 | y | FERC | WITHDRAWN | WITHDRAWN | [7 empty] | 2022-01-31 | 2022-01-31 | 2022-02-07 | 2022-01-31 | 2022-02-07 | 2022-02-07 | 2022-02-07 | 2022-02-22 | 2022-02-07 | 2022-02-14 | 2022-02-14 | 2022-02-28 | [5 empty] | CS | 2022-03-01 | [6 empty] | CS |  |  | 2022-03-01 | [6 empty] | 2022-03-16 |  |  |  |  | 2022-03-15 | [7 empty] | 2022-03-15 | 2022-03-15 | [8 empty] | 2022-03-16 | [11 empty] | 2022-05-19 | [6 empty] | 2022-05-18 | [8 empty] | 2022-05-19 | [8 empty] | 2022-05-19 | [8 empty] | 2022-05-25 | [7 empty] | 2022-05-25 | [7 empty] | 2022-06-13 |  | 2022-06-14 | 2024-06-19 | 2022-07-13 | [8 empty] | 456981 | 2024-05-18 | 2026-01-02 | 2021-07-13: 2022-07-14; 2021-07-13: 2022-07-15 | [13 empty] | Q1 2026 |  |  |  | Requested | [11 empty] | FALSE | TRUE | 699 | 2022-07-14 | 2022-07-14 | 2022 | 2022 | 2022
700 |  | Govinda Neupane |  | 2022-01-25 | 2022-07-19 | L2_Bump | [29 empty] | 10 - WSTN |  | 866D1 | 695 |  | WITHDRAWN | WITHDRAWN |  | Stephanie Loucas | WILDCAT RENEWABLES LLC | WILDCAT RENEWABLES LLC | 879 | 2000274213 | 30013899544 | Solar | [5 empty] | 44.7764 | -69.6579 | Canaan Road | 0 | Canaan Road | Skowhegan | 115 | WESTON HYDRO | 866D1 | 866T2 | 12.47 | 9310-L0450-5330-0025-ED00024 | FERC | WITHDRAWN | WITHDRAWN | [7 empty] | 2022-02-01 | 2022-02-01 | 2022-02-08 | 2022-02-01 | 2022-02-08 | 2023-05-12 | 2023-05-16 | 2023-05-31 | 2023-05-22 | 2023-05-23 | 2023-05-23 | 2023-06-07 | [5 empty] | CS | [7 empty] | CS |  |  | 2023-06-07 | [11 empty] | 2023-06-22 | [8 empty] | 2023-07-26 | [8 empty] | 2023-07-28 | [11 empty] | 2023-10-04 | [6 empty] | 2023-10-04 | [8 empty] | 2023-10-05 | [8 empty] | 2023-10-17 | [8 empty] | 2023-10-19 | [7 empty] | 2023-10-19 | [18 empty] | 4235616 | 2023-10-04 |  |  | 2023-11-14 | [37 empty] | TRUE | TRUE | 700 | 0 | 0 | 1900 | 1900 | 1900
701 |  | Eben Snow | Brent Brooks | 2022-02-01 | 2022-06-08 | L2_Bump |  | 2022-07-27 | L2_Bump |  | 2023-01-18 | L2_With |  | 2023-07-10 | L2_Bump |  | 2023-09-26 | wthdw |  | 2023-10-05 | L2_Bump |  | 2024-01-17 | L2_Bump |  | wthdw | [7 empty] | 8 - DEER | 611 | 9 - DEER |  | 412D4 | 611 | Yes | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Frank DuBose | Nexamp, Inc | NEXAMP SOLAR LLC | 128 Merrill Rd Lewiston | 2000114877 | 30013883241 | Solar | [5 empty] | 44.1479 | -70.1823 | 128 Merrill Rd | 128 | Merrill Rd | Lewiston | 9S | DEER RIPS | 412D4 | 412T4 | 12.47 | 9310-L0128-3230-0255-ED00047 | Non-FERC | WITHDRAWN | WITHDRAWN | [7 empty] | 2022-02-01 | 2022-02-08 | 2022-02-15 | 2022-02-01 | 2022-02-08 | 2024-08-28 | 2024-08-30 | 2024-09-12 | 2024-09-03 | 2024-09-05 | 2024-09-05 | 2024-09-19 |  |  | 2024-09-13 |  |  | CS | 2024-09-13 | [6 empty] | CS |  |  | 2024-09-16 | [7 empty] | 2024-09-23 |  |  |  | 2024-09-20 | [8 empty] | 2024-09-23 | [8 empty] | 2024-09-23 | [11 empty] | 2024-11-29 | [6 empty] | 2024-11-27 | [8 empty] | 2024-11-27 | [8 empty] | 2024-12-13 | [8 empty] | 2024-12-17 | [7 empty] | 2024-12-17 | [7 empty] | 2025-01-06 |  | 2025-01-07 |  | 2025-02-04 | [6 empty] | 12219231 | 2024-11-27 |  |  | 2025-07-15 | 2021-07-13: 2025-02-05; 2021-07-13: 2025-02-05 | [13 empty] | Q4 2025 | [15 empty] | FALSE | TRUE | 701 | 2025-02-05 | 2025-02-05 | 2025 | 2025 | 2025
702 |  |  | Anthony Boucher | 2022-02-04 | 2022-06-22 | L2_Bump | RQP-1 | 2023-06-12 | wthdw | [24 empty] | 5 - BUCK | 655 | 7 - BUCK |  | 806D2 | 655 | Yes | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Julia Wang | Ameresco, Inc | Penobscot Narrows Solar II LLC | Route 15 Drake Lane Boxsport | 2000149605 | 30013903726 | Solar | [5 empty] | 44.1479 | -70.1823 | 111 Spleen #410 | 111 | Spleen #410 | Bucksport | 13 | BUCKSPORT | 806D2 | 806T3 | 34.5 | 9310-L0386-0790-0076-ED00284 |  | WITHDRAWN | WITHDRAWN | [7 empty] | 2022-02-04 | 2022-02-11 | 2022-02-18 | 2022-02-11 | 2022-02-18 | 2023-06-12 | 2023-06-26 | 2023-06-27 | 2023-07-14 | 2023-07-18 | 2023-07-18 | 2023-08-01 | [5 empty] | CS | [10 empty] | 2023-07-26 | [11 empty] | 2023-08-14 | [8 empty] | 2023-08-14 | [8 empty] | 2023-08-17 | [11 empty] | 2023-10-23 | [6 empty] | 2023-10-23 | [8 empty] | 2023-10-23 | [8 empty] | 2023-10-25 | [8 empty] | 2023-11-01 | [7 empty] | 2023-11-01 | [7 empty] | 2023-11-27 |  | 2023-12-28 |  | 2024-01-29 | [6 empty] | 426132 | 2023-11-02 | 626487 | 2024-06-27 | 2025-11-26 | 2021-07-13: 2024-01-29; 2021-07-13: 2024-01-31 | [13 empty] | Q4 2024 |  |  |  | Requested | [11 empty] | FALSE | TRUE | 702 | 2024-01-29 | 2024-01-29 | 2024 | 2024 | 2024
703 |  | Eben Snow | Brent Brooks | 2022-02-09 | 2023-06-16 | wthdw | [29 empty] | 5 - BALD |  | 691D1 | 584 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Andrew Kellar | NEW HAMPSHIRE SOLAR GARDEN | SEBAGO ROAD SOLAR LLC |  | 2000193759 | 30012816044 | Solar | [5 empty] | 43.9262 | -70.6196 | 6 Carl Burnell Rd | 6 | Carl Burnell | Baldwin | 115 | BALDWIN | 691D1 | 691T1 | 34.5 | 9310-L0371-0365-0010-ED00005 | Non-FERC | WITHDRAWN | WITHDRAWN | [8 empty] | 2022-02-16 | 2022-02-24 | 2022-02-16 | 2022-02-24 | 2022-02-24 | 2022-03-03 | 2022-03-10 | 2022-03-04 | 2022-03-04 | 2022-03-04 | 2022-03-18 | [5 empty] | CS | 2022-03-04 | [6 empty] | CS |  |  | 2022-03-04 | [19 empty] | 2022-03-04 | 2022-03-04 | [8 empty] | 2022-03-14 | [11 empty] | 2022-05-17 | [6 empty] | 2022-05-09 | [8 empty] | 2022-05-10 | [8 empty] | 2022-05-10 | [8 empty] | 2022-05-18 | [7 empty] | 2022-05-18 | [7 empty] | 2022-05-18 |  | 2022-05-18 | 2023-02-16 | 2022-05-18 | 2023-02-17 | [5 empty] | 571419 | 2022-05-05 | 513605 | 2023-02-16 | 2023-06-21 | 2021-07-13: 2022-05-18; 2021-07-13: 2022-05-23; 2021-07-13: 2023-02-18; 2021-07-13: 2023-02-20 | [17 empty] | Requested | [11 empty] | TRUE | TRUE | 703 | 2022-05-18 | 2022-05-18 | 2022 | 2022 | 2022
704 |  | Govinda Neupane |  | 2022-02-16 | [31 empty] | 2 - LOMS |  | 429D1 | 365 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Frank DeBose | Nexamp, Inc | NEXAMP SOLAR LLC | 57 Paris Rd Bethel | 2000114877 | 30013884819 | Solar | [5 empty] | 44.408 | -70.708 | 57 Paris Rd | 57 | Paris Rd | Bethel | 7 | LOCKES MILLS | 429D1 | 429T1 | 12.47 | 9310-L0163-0485-0011-ED00112 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2022-02-24 | 2022-03-03 | 2022-02-24 | 2022-03-01 | 2022-03-01 | 2022-03-18 | 2022-03-15 | 2022-03-22 | 2022-03-22 | 2022-03-22 | 2022-04-05 | [5 empty] | CS | 2022-03-25 | RS | [5 empty] | CS |  |  | 2022-03-25 | 2022-07-25 | [19 empty] | 2022-03-31 | [8 empty] | 2022-04-05 | 2022-07-27 | [10 empty] | 2022-06-09 | 2022-09-07 | [5 empty] | 2022-06-03 | 2022-09-07 | [7 empty] | 2022-06-05 | 2022-09-08 | [7 empty] | 2022-06-08 | 2022-09-15 | [7 empty] | 2022-06-09 | 2022-06-15 | [6 empty] | 2022-06-13 | 2022-09-19 | [6 empty] | 2022-09-28 |  | 2022-09-28 |  | 2022-10-13 | [10 empty] | 2023-10-09 | 2021-07-13: 2022-10-18; 2021-07-13: 2022-10-18 | [17 empty] | Requested | [11 empty] | TRUE | TRUE | 704 | 2022-10-18 | 2022-10-18 | 2022 | 2022 | 2022
705 |  | Govinda Neupane |  | 2022-02-17 | [31 empty] | 4 - RUIP |  | 466D1 | 506 |  | WITHDRAWN | WITHDRAWN |  | Geoffrey Sparrow | Green Lantern DEVELOPMENT LLC | PERU GLC SOLAR LLC | 74 OLD VALLEY RD PERU | 2000277827 | 30013945057 | Solar | [7 empty] | Old Valley Rd. |  |  | Peru |  | RUMFORD INDUSTRIAL PARK | 466D1 | 466T1 | 12.47 | 9310-L0205-4610-0018-ED00003 | FERC | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2022-02-25 | 2022-03-04 | 2022-02-25 | 2022-03-02 | 2022-03-02 | 2022-03-18 | 2022-03-16 | 2022-03-18 | 2022-03-24 | 2022-03-24 | 2022-04-07 |  |  | 2022-03-24 |  |  | CS | 2022-03-24 | [6 empty] | CS |  |  | 2022-03-24 | [19 empty] | 2022-03-28 | 2022-03-28 | [8 empty] | 2022-03-30 | [11 empty] | 2022-06-03 | [6 empty] | 2022-05-25 | [8 empty] | 2022-05-26 | [8 empty] | 2022-06-06 | [8 empty] | 2022-06-07 | [7 empty] | 2022-06-07 | [22 empty] | 2022-06-14 | [37 empty] | TRUE | TRUE | 705 | 0 | 0 | 1900 | 1900 | 1900
706 | 1151 | Eben Snow | Brent Brooks | 2022-03-10 | [29 empty] | 1 - BRPO |  | 4 - BRPO |  | 407D1 | 531 |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED |  | Tyler William Perkins | Nexamp, Inc | Felt Road Solar, LLC | 180 Felt Rd/ Woodstock | 2000462663 | 30016503325 | Solar | 1968 | 1.968 | 2811.84 |  | 4000 | 44.3856 | -70.6034 | 180 Felt Road | 180 | 180 Felt Road | Woodstock | 15 | BRYANT POND | 407D1 | 407T1 | 12.47 | 9310-L0195-6475-0022-ED00018 | Non-FERC | NOT IMPACTED | NOT IMPACTED |  | BRIDGTON | [6 empty] | 2022-03-17 | 2022-03-24 | 2022-03-10 | 2022-03-10 | 2022-03-10 | 2022-03-10 | 2022-03-24 | 2022-03-10 | 2022-03-10 | 2022-03-10 | 2022-03-10 |  |  | 2022-03-10 |  |  | CS | 2022-03-10 | [6 empty] | CS |  |  | 2022-03-10 | [19 empty] | 2022-03-10 | 2022-03-10 | [8 empty] | 2022-03-10 | [11 empty] | 2022-05-13 | [6 empty] | 2022-05-11 | [8 empty] | 2022-05-11 | [49 empty] | 2021-07-13: 2023-06-12; 2021-07-13: 2023-06-12 | [29 empty] | FALSE | TRUE | 706 | 2023-06-12 | 2023-06-12 | 2023 | 2023 | 2023
707 | 1169 | Govinda Neupane |  | 2022-03-10 | 2023-02-28 | L2_Bump |  | 2023-03-06 | L2_Bump |  | 2023-11-07 | L2_Bump |  | 2023-12-19 | wthdw | [18 empty] | 1 - RUMF | 606 | 7 - RUMF |  | 447D1 | 654 | Yes | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Dustin Thaler | VC Renewables LLC | Roxbury Solar Farm LLC | 1034 Roxbury Rd, Roxbury | 2000215915 | 30013098436 | Solar | [5 empty] | 44.6184 | -70.5792 | 1034 Roxbury Road | 1034 | Roxbury Road | Roxbury | 80 | RUMFORD | 447D1 | 447T3 | 12.47 | 9310-L0186-5010-0019-ED00143 | Non-FERC | NOT IMPACTED | NOT IMPACTED |  | FARMINGTON | [6 empty] | 2022-03-17 | 2022-03-24 | 2022-03-10 | 2022-03-10 | 2022-03-10 | 2022-03-10 | 2022-03-24 | 2022-03-10 | 2022-03-10 | 2022-03-10 | 2022-03-10 |  |  | 2022-03-10 |  |  | CS | 2022-03-10 | [6 empty] | CS |  |  | 2022-03-10 |  |  | N/A | [11 empty] | N/A |  |  |  |  | 2022-03-10 | 2022-03-10 |  |  | 2024-04-19 | [5 empty] | 2022-03-10 |  |  | 2024-04-19 | [8 empty] | 2022-05-13 | [6 empty] | 2022-04-27 |  |  | 2024-06-18 | [5 empty] | 2022-04-27 | [8 empty] | 2022-04-27 |  |  | 2024-07-22 | [8 empty] | 2024-07-29 | [27 empty] | 2026-06-03 | 2021-07-13: 2023-09-26; 2021-07-13: 2023-09-26; 2021-07-13: 2025-08-05; 2021-07-13: 2025-08-05 | [29 empty] | FALSE | TRUE | 707 | 2023-09-26 | 2023-09-26 | 2023 | 2023 | 2023
708 |  | Eben Snow | Brent Brooks | 2022-03-17 | [31 empty] | 4 - FRYT |  | 405D1 | 518 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Frank DuBose | Nexamp, Inc | NEXAMP SOLAR LLC | 129 Lovell Rd Fryeburg | 2000114877 | 30013989527 | Solar | [5 empty] | 44.0728 | -70.945 | 129 Lovell Rd | 129 | Lovell Rd | Fryeburg | 503H | FRYEBURG TAP | 405D1 | 405T1 | 12.47 | 9310-L0116-2130-0050-ED00114 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2022-03-24 | 2022-03-31 | 2022-03-22 | 2022-03-30 | 2022-04-01 | 2022-03-31 | 2022-04-15 | 2022-04-05 | 2022-04-05 | 2022-04-05 | 2022-04-19 |  |  | 2022-04-06 |  |  | CS | 2022-04-06 | RS | 2022-06-15 |  |  |  |  | CS |  |  | 2022-04-06 | 2022-06-16 | [11 empty] | 2022-06-16 | [16 empty] | 2022-04-20 | 2022-06-21 | [10 empty] | 2022-06-24 | 2022-08-02 | [5 empty] | 2022-05-23 | 2022-07-15 | [7 empty] | 2022-05-23 | 2022-07-15 | [7 empty] | 2022-05-23 | 2022-07-20 | [7 empty] | 2022-05-26 | 2022-07-20 | [6 empty] | 2022-05-26 | 2022-07-20 | [6 empty] | 2022-07-28 |  | 2022-07-28 | 2023-04-10 | 2022-08-02 | 2023-04-10 | [5 empty] | 508711 | 2022-07-14 | 457076 | 2023-03-28 | 2023-08-14 | 2021-07-13: 2022-08-04; 2021-07-13: 2022-08-04; 2021-07-13: 2023-04-13; 2021-07-13: 2023-04-14 | [17 empty] | Requested | [11 empty] | TRUE | TRUE | 708 | 2022-08-04 | 2022-08-04 | 2022 | 2022 | 2022
709 |  |  | KRISTOFER COLEMAN | 2022-03-18 | [31 empty] | 2 - WOOL |  | 258D1 | 290 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Daniel Passarello | Nexamp, Inc | NEXAMP SOLAR LLC | 134 Nequasset Rd Woolwich | 2000114877 | 30014003492 | Solar | [5 empty] | 43.9417 | -69.7836 | 134 Nequasset Rd | 134 | Nequasset Rd | Woolwich | 22 | WOOLWICH | 258D1 | 258T1 | 12.47 | 9310-L0098-6490-0053-ED00028 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2022-03-25 | 2022-04-01 | 2022-03-22 | 2022-03-30 | 2022-04-01 | 2022-04-05 | 2022-04-15 | 2022-04-06 | 2022-04-06 | 2022-04-06 | 2022-04-20 |  |  | 2022-04-11 |  |  | CS | 2022-04-11 | [6 empty] | CS |  |  | 2022-04-11 | [29 empty] | 2022-04-13 | [11 empty] | 2022-06-17 | [6 empty] | 2022-06-06 | [8 empty] | 2022-06-13 | [8 empty] | 2022-06-14 | [8 empty] | 2022-06-16 | [7 empty] | 2022-06-16 | [7 empty] | 2022-07-07 |  | 2022-07-07 |  | 2022-08-03 | [10 empty] | 2022-09-19 | 2021-07-13: 2022-08-04; 2021-07-13: 2022-08-04 | [29 empty] | TRUE | TRUE | 709 | 2022-08-04 | 2022-08-04 | 2022 | 2022 | 2022
710 |  |  | KRISTOFER COLEMAN | 2022-03-31 | 2022-10-20 | L2_Bump |  | 2022-12-30 | L2_Bump | [26 empty] | 6 - TP34 |  | 250D1 | 547 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Matthew Doubleday | SunRaise Investments LLC | AUGUSTA ROAD TOPSHAM SOLAR LLC | 449 Augusta Road | 2000200720 | 30012901788 | Solar | [5 empty] | 43.9755 | -69.9594 | 449 Augusta Road | 449 | Augusta Road | Topsham | 83 | TOPSHAM 34 KV | 250D1 | 250T2 | 12.47 | 9310-L0086-5840-0003-ED00143 | FERC | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2022-04-07 | 2022-04-14 | 2022-04-07 | 2022-04-13 | 2022-04-13 | 2022-04-14 | 2022-04-28 | 2022-04-19 | 2022-04-19 | 2022-04-19 | 2022-05-03 |  |  | 2022-04-28 |  |  | CS | 2022-04-28 | [6 empty] | CS |  |  | 2022-05-10 | [11 empty] | 2022-05-13 | [8 empty] | 2022-06-30 | [8 empty] | 2022-06-30 | [11 empty] | 2022-09-01 | [6 empty] | 2022-08-26 | [8 empty] | 2022-08-26 | [8 empty] | 2022-08-29 | [8 empty] | 2022-08-30 | [7 empty] | 2022-08-30 | [7 empty] | 2022-09-08 |  | 2022-09-08 | 2022-09-15 | 2022-09-08 | 2022-09-15 | [9 empty] | 2023-01-06 | 2021-07-13: 2022-09-08; 2021-07-13: 2022-09-08; 2021-07-13: 2022-09-15; 2021-07-13: 2022-09-15 | [17 empty] | Requested | [11 empty] | TRUE | TRUE | 710 | 2022-09-08 | 2022-09-08 | 2022 | 2022 | 2022
711 |  | Eben Snow | Brent Brooks | 2022-04-07 | 2024-04-17 | wthdw |  | 2024-08-23 | wthdw | [26 empty] | 7 - R115 |  | 445D1 | 656 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Sachin Patel | LastMile Energy | HACKERS HILL SOLAR LLC | Route 121 Casco | 2000285358 | 30014046525 | Solar | [5 empty] | 43.9785 | -70.5153 | Route 121 | 0 | Route 121 | Casco | 522 | RAYMOND 115 KV | 445D1 | 445T2 | 34.5 | 9310-L0184-1060-0052-ED00064 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2022-04-14 | 2022-04-22 | 2022-04-13 | 2022-04-20 | 2022-04-20 | 2022-04-20 | 2022-05-04 | 2022-04-28 | 2022-04-28 | 2022-04-28 | 2022-05-12 |  |  | 2022-05-10 |  |  | CS | 2022-04-29 | [6 empty] | CS |  |  | 2022-05-11 |  |  | 2024-08-26 | [8 empty] | 2022-05-11 | [8 empty] | 2022-05-11 | [8 empty] | 2022-05-17 | [11 empty] | 2022-07-22 | [6 empty] | 2022-07-27 | [8 empty] | 2022-08-02 | [8 empty] | 2022-08-03 | [8 empty] | 2022-08-02 | [15 empty] | 2022-08-15 |  | 2022-08-17 | 2022-12-01 | 2022-09-09 | 2022-12-06 | [5 empty] | 1344432 | 2022-07-22 | 1308733 | 2022-11-30 | 2024-09-10 | 2021-07-13: 2022-09-09; 2021-07-13: 2022-09-09; 2021-07-13: 2022-12-07; 2021-07-13: 2022-12-08 | [17 empty] | Requested | [11 empty] | TRUE | TRUE | 711 | 2022-09-09 | 2022-09-09 | 2022 | 2022 | 2022
712 |  |  | KRISTOFER COLEMAN | 2022-04-07 | 2023-04-05 | L2_Bump |  | 2025-02-19 | wthdw | [24 empty] | 2 - LSFA | 643 | 5 - LSFA | 1 - LSFA | 232D1 | 643 | Yes | EXECUTED | EXECUTED |  | Frank DuBose | Nexamp, Inc | Lisbon Falls Solar, LLC | Bowdoinham rd Lisbon | 2000463160 | 30016509934 | Solar | 999 | 0.999 | 1305.72 |  |  | 44.0408 | -70.0386 | 283 Bowdoinham Rd | 283 | Bowdoinham Rd | Lisbon | 5 | LISBON FALLS | 232D1 | 232T1 | 12.47 | 9310-L0061-3310-0148-ED00066 | Non-FERC | NOT IMPACTED | NOT IMPACTED |  | Yes | [6 empty] | 2022-04-14 | 2022-04-22 | 2022-04-14 | 2022-04-20 | 2022-11-17 | 2022-11-28 | 2022-12-05 | 2022-11-29 | 2022-12-01 | 2022-12-01 | 2022-12-15 |  |  | 2022-12-07 |  |  | CS | [7 empty] | CS |  |  | 2022-12-16 |  |  | 2024-02-12 | [8 empty] | 2022-12-30 |  |  | 2024-03-01 | [5 empty] | 2023-12-27 |  |  | 2024-03-18 | [5 empty] | 2023-01-13 |  |  | 2024-03-19 | [8 empty] | 2023-03-23 | [6 empty] | 2023-03-20 |  |  | 2024-05-23 | [5 empty] | 2023-03-20 |  |  | 2024-05-23 | [5 empty] | 2023-03-27 |  |  | N/A | [5 empty] | 2023-03-31 |  |  | N/A |  |  |  |  | 2023-03-31 |  |  | N/A |  |  |  |  | 2024-05-24 |  | 2024-05-24 | 2025-01-14 | 2024-05-24 | [6 empty] | 373497 | 2024-05-22 |  |  |  | 2021-07-13: 2024-05-28; 2021-07-13: 2024-05-28 | [13 empty] | Q3 2026 |  |  |  | Requested | [11 empty] | FALSE | TRUE | 712 | 2024-05-28 | 2024-05-28 | 2024 | 2024 | 2024
713 |  | Eben Snow | Brent Brooks | 2022-04-20 | [31 empty] | 4 - GRFA |  | 436D6 | 538 |  | WITHDRAWN | WITHDRAWN |  | Viqui Carballo | Novel Energy Solutions LLC | Novel Energy Solutions | Penley corner Rd Auburn | 2000250310 | 30013883498 | Solar | [7 empty] | n/a Penley corner RD |  |  | Auburn |  | GREAT FALLS | 436D6 |  |  | 9310-L0176-0230-0154-ED00072 | FERC | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2022-04-27 | 2022-05-04 | 2022-04-27 | 2022-05-04 | [60 empty] | MISSING DATE | [69 empty] | 2022-05-17 | [37 empty] | TRUE | TRUE | 713 | 0 | 0 | 1900 | 1900 | 1900
714 |  | Govinda Neupane |  | 2022-04-28 | [31 empty] | 6 - SKTP |  | 864D1 | 335 |  | WITHDRAWN | WITHDRAWN |  | Viqui Carballo | Novel Energy Solutions LLC | Novel Energy solutions | Norridgewock Ave Skowhegan | 2000250310 | 30013923468 | Solar | [7 empty] | n/a Norridgewock Ave |  |  | Skowhegan |  | SKOWHEGAN TAP | 864D1 |  |  | 9310-L0446-5330-0125-ED00013 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2022-05-05 | 2022-05-12 | 2022-05-03 | 2022-05-12 | [130 empty] | 2022-06-07 | [37 empty] | TRUE | TRUE | 714 | 0 | 0 | 1900 | 1900 | 1900
715 |  | Govinda Neupane |  | 2022-05-06 | [29 empty] | 1 - HART |  | 7 - HART |  | 824D1 | 615 |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED |  | Tyler William Perkins | Nexamp, Inc | HARTLAND SOLAR LLC | 876 Beans Corner Road Hartland | 2000334648 | 30014720418 | Solar | 860 | 0.86 | 1212.64 |  |  | 44.8569 | -69.475 | 876 Beans Corner Road | 876 | Beans Corner Road | Hartland | 015 | HARTLAND | 824D1 | 824T1 | 12.47 | 9310-L0409-2540-0044-ED00008 | Non-FERC | TRIGGERING | TRIGGERING (460.000) | 460000 | Yes | [6 empty] | 2022-05-13 | 2022-05-20 | 2022-05-13 | 2022-05-19 | 2022-05-19 | 2022-05-16 | 2022-06-03 | 2022-05-19 | 2022-05-19 | 2022-05-19 | 2022-06-02 |  |  | 2022-05-19 |  |  | CS | 2022-05-19 | [6 empty] | CS |  |  | 2022-05-23 | [11 empty] | 2022-05-31 | [8 empty] | 2022-05-31 | [8 empty] | 2022-06-17 | [11 empty] | 2022-07-15 | [6 empty] | 2022-07-14 | [8 empty] | 2022-07-15 | [8 empty] | 2022-07-20 | [8 empty] | 2022-07-20 | [7 empty] | 2022-07-20 | [7 empty] | 2022-08-10 |  | 2022-08-11 | 2022-12-12 | 2022-09-08 | 2022-12-13 | [5 empty] | 563959 | 2022-07-14 | 554182 | 2022-12-09 |  | 2021-07-13: 2022-09-08; 2021-07-13: 2022-09-08; 2021-07-13: 2022-12-13; 2021-07-13: 2022-12-14 | [17 empty] | Requested | [11 empty] | FALSE | TRUE | 715 | 2022-09-08 | 2022-09-08 | 2022 | 2022 | 2022
716 |  |  | Anthony Boucher | 2022-05-11 | 2023-01-09 | L2_Bump |  | 2023-01-10 | wthdw |  | 2023-02-22 | wthdw | [23 empty] | 6 - SEAR |  | 850D1 | 641 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Bradley Parsons | VCP REALTY LLC | Searsport Solar One LLC | 386 East Main Street Searsport | 2000262503 | 30013737173 | Solar | [5 empty] | 44.4798 | -68.8772 | 386 East Main Street | 386 | East Main Street | Searsport | 45 | SEARSPORT | 850D1 | 850T1 | 12.47 | 9310-L0427-5220-0068-ED00076 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2022-05-18 | 2022-05-25 | 2022-05-17 | 2022-05-24 | 2022-05-24 | 2022-05-25 | 2022-06-08 | 2022-05-31 | 2022-05-31 | 2022-05-31 | 2022-06-22 |  |  | 2022-06-28 |  |  | CS | 2022-06-28 | [6 empty] | CS |  |  | 2022-06-28 |  |  | 2023-10-17 |  |  |  |  | 2022-07-01 |  |  |  | 2022-07-07 |  |  | 2023-11-06 | [5 empty] | 2022-07-07 |  |  | 2023-11-20 | [5 empty] | 2022-07-12 |  |  | 2023-11-22 | [8 empty] | 2022-09-13 | [6 empty] | 2022-09-07 |  |  | 2024-01-31 | [5 empty] | 2022-09-09 |  |  | 2024-01-31 | [5 empty] | 2022-09-12 |  |  | 2024-02-01 | [5 empty] | 2022-09-19 |  |  | 2024-02-09 |  |  |  |  | 2022-09-19 |  |  | 2024-02-09 |  |  |  |  | 2022-09-27 |  | 2022-10-11 | 2024-03-01 | 2022-10-26 | 2024-03-12 | [7 empty] | 294797 | 2024-01-31 | 2024-11-26 | 2021-07-13: 2022-11-01; 2021-07-13: 2022-11-01; 2021-07-13: 2024-03-15; 2021-07-13: 2024-03-15 | [17 empty] | Requested | [11 empty] | TRUE | TRUE | 716 | 2022-11-01 | 2022-11-01 | 2022 | 2022 | 2022
717 |  | Rigel Paradise | Rick Duperre | 2022-05-13 | 2022-11-07 | Wthdw | [29 empty] | 6 - BDPP |  | 605D2 | 524 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Frank DuBose | Nexamp, Inc | NEXAMP SOLAR LLC | 9 BUZZELL RD BIDDEFORD 04005 | 2000114877 | 30014139247 | Solar | [5 empty] | 43.5067 | -70.5322 | 9 Buzzell Rd | 9 | Buzzell Rd | Biddeford | 5 | BIDDEFORD PUMP | 605D2 | 605T2 | 12.47 | 9310-L0215-0490-0035-ED00014 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2022-05-20 | 2022-05-27 | 2022-05-19 | 2022-05-25 | 2022-05-25 | 2022-05-25 | 2022-06-09 | 2022-06-01 | 2022-06-01 | 2022-06-01 | 2022-06-15 |  |  | 2022-06-15 |  |  | CS | 2022-06-15 | [6 empty] | CS |  |  | 2022-06-15 | 2022-10-13 |  | 2023-03-03 |  |  |  |  | 2022-06-15 |  |  |  | 2022-06-16 | 2022-10-20 |  | 2023-03-15 | [5 empty] | 2022-06-15 | 2022-10-20 |  | 2023-03-20 | [5 empty] | 2022-06-17 |  |  | 2023-03-21 | [8 empty] | 2022-08-23 | [6 empty] | 2022-08-25 |  |  | 2023-05-03 | [5 empty] | 2022-09-01 |  |  | 2023-05-03 | [5 empty] | 2022-09-15 |  |  | 2023-05-10 | [5 empty] | 2022-09-15 |  |  | 2023-05-15 |  |  |  |  | 2022-09-15 | [7 empty] | 2023-05-23 |  | 2023-05-25 |  | 2023-06-02 | [6 empty] | 680562 | 2023-05-03 |  |  | 2023-10-26 | 2021-07-13: 2023-06-06; 2021-07-13: 2023-06-06 | [29 empty] | TRUE | TRUE | 717 | 2023-06-06 | 2023-06-06 | 2023 | 2023 | 2023
718 |  | Lanie Patterson | Brent Brooks | 2022-05-16 | 2022-07-28 | L2_Bump |  | 2022-09-15 | L2_Bump |  |  |  |  | 2024-08-12 | wthdw | [20 empty] | 13 - MONM | 1 - MONM | 457D2 | 677 | Yes | EXECUTED | EXECUTED |  | Karl Wiedenmann | SOLAMERICA ENERGY LLC | Kennebec County ME S1, LLC | 235 South Monmouth Road Monmouth | 2000209571 | 30015668301 | Solar | 999 | 0.999 | 1311 |  |  | 44.1971 | -69.9939 | 235 South Monmouth Road | 235 | South Monmouth Road | Monmouth | 20 | MONMOUTH | 457D2 | 457T2 | 12.47 | 9310-L0199-3740-0015-ED00024 | Non-FERC | COST SHARING | COST SHARING (375,000) | 57652 | Yes | [6 empty] | 2022-05-23 | 2022-05-31 | 2022-05-19 | 2022-05-26 | 2023-03-22 | 2023-03-24 | 2023-04-05 | 2023-03-27 | 2023-03-29 | 2023-03-29 | 2023-04-12 |  |  | 2023-04-11 |  |  | CS | 2023-04-11 | [6 empty] | CS |  |  | 2023-04-24 |  |  | 2024-08-13 | [11 empty] | 2024-08-19 | [5 empty] | 2023-04-24 | [8 empty] | 2023-05-04 | [11 empty] | 2023-07-11 | [6 empty] | 2023-07-06 |  |  | 2024-10-30 | [5 empty] | 2023-07-06 |  |  | 2024-11-04 | [5 empty] | 2023-07-17 |  |  | 2024-11-06 | [5 empty] | 2023-07-19 |  |  | 2024-11-11 | [7 empty] | 2024-11-11 |  |  |  |  | 2023-07-17 |  | 2023-07-24 |  | 2023-08-17 | [6 empty] | 130172 | 2023-07-05 | 267084 | 2024-10-29 |  | 2023-08-22 | 2023-08-22 | 2024-02-09 | 2024-02-09 | 2025-01-23 | 2025-01-23 | [15 empty] | Q4 2025 | [15 empty] | FALSE | TRUE | 718 | 2023-08-22 | 2023-08-22 | 2023 | 2023 | 2023
719 |  | Eben Snow | Brent Brooks | 2022-05-23 | [31 empty] | 5 - GRFA |  | 436D6 | 713 |  | WITHDRAWN | WITHDRAWN |  | Paula J Fitzgerald | Novel Energy Solutions LLC | NOVEL ENERGY SOLUTIONS | ME Penley Corner CSG LLC | 2000250310 | 30013717332 | Solar | [5 empty] | 44.04 | -70.2083 | Penley Corner Road |  | Penley Corner Road | Auburn | 618 | GREAT FALLS | 436D6 | 436T1 | 12.47 | 9310-L0176-0230-0154-ED00074 | FERC | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2022-05-31 | 2022-06-07 | 2022-05-27 | 2022-06-06 | 2022-06-06 | 2022-07-12 | 2022-06-21 | 2022-07-13 | 2022-07-14 | 2022-07-18 | 2022-08-01 |  |  | 2022-07-29 |  |  | CS | 2022-07-29 | [6 empty] | CS |  |  | 2022-08-02 | [11 empty] | 2022-08-09 | [8 empty] | 2022-08-04 | [8 empty] | 2022-08-04 | [11 empty] | 2022-10-07 | [6 empty] | 2022-10-06 | [8 empty] | 2022-10-07 | [8 empty] | 2022-10-11 | [8 empty] | 2022-10-11 | [7 empty] | 2022-10-20 | [22 empty] | 2022-11-15 | [37 empty] | TRUE | TRUE | 719 | 0 | 0 | 1900 | 1900 | 1900
720 |  | Lanie Patterson | Brent Brooks | 2022-05-31 | 2023-03-29 | L2_Bump |  | 2023-12-08 | L2_Bump |  | 2023-01-22 | wthdw | [23 empty] | 7 - WINT |  | 256D1 | 653 |  | WITHDRAWN | WITHDRAWN |  | Nicholas Ford | Hexagon Energy LLC | FOXGLOVE SOLAR LLC | US ROUTE 202 WINTHROP | 2000279592 | 30013967325 | Solar | [5 empty] | 44.313 | -69.9452 | 1920 US-202 | 1920 | US-202 | Winthrop | 019 | WINTHROP | 256D1 | 256T2 | 12.47 | 9310-L0095-6450-0003-ED00016 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2022-06-07 | 2022-06-14 | 2022-06-03 | 2022-06-13 | 2022-11-28 | 2022-11-28 | 2022-12-12 | 2022-11-28 | 2022-11-30 | 2022-11-30 | 2022-12-14 |  |  | 2022-12-14 |  |  | CS | 2022-12-14 | [6 empty] | CS |  |  | 2022-12-15 |  |  | 2024-06-03 | [8 empty] | 2023-01-03 | [8 empty] | 2023-01-06 | [8 empty] | 2023-01-12 | [11 empty] | 2023-03-20 | [6 empty] | 2023-03-20 | [8 empty] | 2023-03-20 | [8 empty] | 2023-03-20 | [8 empty] | 2023-03-24 | [30 empty] | 2024-06-03 | [37 empty] | TRUE | TRUE | 720 | 0 | 0 | 1900 | 1900 | 1900
721 |  | Govinda Neupane |  | 2022-05-31 | [31 empty] | 5 - ANSO |  | 801D1 | 632 |  | WITHDRAWN | WITHDRAWN |  | Nicholas Ford | Hexagon Energy LLC | Red Solar, LLC | ANSON RD STARKS | 2000279590 | 30013967317 | Solar | [5 empty] | 44.7555 | -69.9098 | 896 Anson Road | 896 | Anson Road | Starks | 026 | ANSON | 801D1 | 801T1 | 12.47 | 9310-L0379-5510-0017-ED00021 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2022-06-07 | 2022-06-14 | 2022-06-03 | 2022-06-13 | 2022-06-10 | 2022-06-29 | 2022-06-28 | 2022-07-11 | 2022-07-11 | 2022-07-11 | 2022-07-25 |  |  | 2022-07-25 |  |  | CS | 2022-07-25 | [6 empty] | CS |  |  | 2022-08-08 | [11 empty] | 2022-08-18 | [8 empty] | 2022-08-25 | [8 empty] | 2022-08-25 | [11 empty] | 2022-10-27 | [60 empty] | n/a | n/a | n/a | n/a | 2022-08-26 | [37 empty] | TRUE | TRUE | 721 | 0 | 0 | 1900 | 1900 | 1900
722 |  |  | KRISTOFER COLEMAN | 2022-06-03 | 2023-10-20 | L2_Bump | [29 empty] | 3 - BOOT |  | 209D3 | 683 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Matthew Doubleday | ReWild Renewables LLC | ReWild Renewables LLC |  | 2000198992 | 30013350761 | Solar | [5 empty] | 43.9016 | -69.6154 | 586 Wiscasset Road | 586 | Wiscasset Road | Boothbay | 109 | BOOTHBAY HARBOR | 209D3 | 209T1 | 12.47 | 9310-L0026-0550-0162-ED00018 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2022-06-10 | 2022-06-17 | 2022-06-08 | 2022-06-15 | 2022-06-15 | 2022-06-20 | 2022-06-30 | 2022-06-23 | 2022-06-23 | 2022-06-23 | 2022-07-08 |  |  | 2022-07-06 |  |  | CS | 2022-07-06 | [6 empty] | CS |  |  | 2022-07-06 | [11 empty] | 2022-07-22 | [8 empty] | 2022-07-25 | [8 empty] | 2022-07-25 | [11 empty] | 2022-09-26 | [6 empty] | 2022-09-22 | [8 empty] | 2022-09-22 | [8 empty] | 2022-09-23 | [8 empty] | 2022-09-23 | [7 empty] | 2022-09-23 | [7 empty] | 2022-09-23 |  | 2022-09-26 |  | 2022-09-26 | [10 empty] | 2022-11-28 | 2021-07-13: 2022-09-27; 2021-07-13: 2022-09-27 | [17 empty] | Requested | [11 empty] | TRUE | TRUE | 722 | 2022-09-27 | 2022-09-27 | 2022 | 2022 | 2022
723 |  | Govinda Neupane |  | 2022-06-08 | 2022-09-09 | L2_Bump |  | 2022-12-01 | L2_Bump |  | 2023-10-06 | L2_Bump |  | 2023-12-06 | L2_Bump |  | 2024-10-04 | wthdw |  | 2024-11-14 | wthdw |  | 2024-12-16 | wthdw |  | 2024-11-19 | studywaived | [6 empty] | 4 - GUIL | 661 | 9 - GUIL |  | 821D1 | 661 |  | WITHDRAWN | WITHDRAWN |  | Frank DuBose | Nexamp, Inc | NEXAMP SOLAR LLC | 629 Route 150, Parkman | 2000114877 | 30014203746 | Solar | [5 empty] | 45.1356 | -69.4303 | 629 Route 150 | 629 | Route 150 | Parkman | 98 | GUILFORD | 821D1 | 821T1 | 12.47 | 9310-L0405-4520-0020-ED00127 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2022-06-15 | 2022-06-23 | 2022-06-14 | 2022-06-20 | 2024-11-14 | 2024-11-15 | 2024-12-02 | 2024-11-19 | 2024-11-21 | 2024-11-21 | 2024-12-09 |  |  | 2024-12-05 |  |  | CS | 2024-12-05 | [6 empty] | CS |  |  | 2023-12-19 | [7 empty] | 2024-12-13 |  |  |  | 2024-12-19 | [8 empty] | 2024-12-27 | [8 empty] | 2025-01-30 | [11 empty] | 2025-04-07 | [6 empty] | 2024-04-04 | [8 empty] | 2024-04-04 | [44 empty] | 10650278 | 2025-04-03 |  |  | 2025-04-08 | [21 empty] | Q4 2026 | [15 empty] | FALSE | TRUE | 723 | 0 | 0 | 1900 | 1900 | 1900
724 |  | Lanie Patterson | Brent Brooks | 2022-06-08 | [29 empty] | 1 - FAIR |  | 4 - FAIR | 1 - FAIR | 817D3 | 592 |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED |  | Josh Brosnan | Sunwealth | ROUTE 139 FAIRFIELD SOLAR LLC | 0 Norridgewock Rd Fairfield | 2000529413 | 30017451235 | Solar | 996 | 0.996 | 1808.3 |  |  | 44.6062 | -69.6591 | 176 Norridgewock Rd | 176 | Norridgewock Rd | Fairfield | 801.2 | FAIRFIELD | 817D3 | 817T1 | 12.47 | 9310-L0401-2000-0103-ED00003 | Non-FERC | COST SHARE | COST SHARE (325,000) | 31531.26 | Yes | [6 empty] | 2022-06-15 | 2022-06-23 | 2022-06-14 | 2022-06-21 | 2022-06-21 | 2022-06-28 | 2022-07-06 | 2022-06-30 | 2022-06-30 | 2022-06-30 | 2022-07-15 |  |  | 2022-07-07 |  |  | CS | 2022-07-07 | [6 empty] | CS |  |  | 2022-07-07 | [11 empty] | 2022-07-22 | [8 empty] | 2022-07-22 | [8 empty] | 2022-07-25 | [11 empty] | 2022-09-26 | [6 empty] | 2022-09-22 | [8 empty] | 2022-09-22 | [8 empty] | 2022-09-23 | [8 empty] | 2022-09-23 | [7 empty] | 2022-09-23 | [7 empty] | 2022-09-23 |  | 2022-09-26 |  | 2022-09-26 | [11 empty] | 2021-07-13: 2022-09-27; 2021-07-13: 2022-09-27 | [13 empty] | Q3 2025 |  |  |  | Requested | [11 empty] | FALSE | TRUE | 724 | 2022-09-27 | 2022-09-27 | 2022 | 2022 | 2022
725 |  | Lanie Patterson | Brent Brooks | 2022-06-09 | [29 empty] | 1 - SOCH |  | 4 - SOCH | 1 - SOCH | 244D2 | 277 |  | EXECUTED | EXECUTED |  | Paula J Fitzgerald | Novel Energy Solutions LLC | ME CHINA HASKELL1 CSG LLC | PARMENTER HILL RD SO CHINA | 2000250310 | 30014726852 | Solar | 975 | 0.975 | 1244.16 |  |  | 44.423 | -69.4801 | Parmenter Hill Rd |  | Parmenter Hill Rd | South China | 26 | SOUTH CHINA | 244D2 | 244T1 | 12.47 | 9310-L0480-1150-0165-ED00023 | Non-FERC | NOT IMPACTED | NOT IMPACTED |  | Yes | [6 empty] | 2022-06-16 | 2022-06-24 | 2022-06-14 | 2022-06-22 | 2022-06-10 | 2022-07-07 | 2022-07-07 | 2022-07-12 | 2022-07-12 | 2022-07-12 | 2022-07-26 | 2022-07-15 | 2022-09-22 |  |  |  | FS | 2022-07-15 | IS | 2022-09-22 |  |  |  |  | FS | [13 empty] | 2022-07-15 | 2022-10-07 | [6 empty] | 2022-07-07 | 2022-07-07 | [7 empty] | 2022-08-08 | 2022-10-12 | [10 empty] | 2022-09-19 | 2022-11-28 | [5 empty] | 2022-09-14 | 2022-11-09 | [7 empty] | 2022-09-20 | 2022-11-10 | [7 empty] | 2022-09-21 | 2022-11-12 | [7 empty] | 2022-09-21 | 2022-11-15 | [6 empty] | 2022-09-21 | 2022-11-15 | [8 empty] | 2022-11-22 |  | 2022-11-28 |  | 2023-01-06 | [6 empty] | 576568 | 2022-11-09 |  |  |  | 2021-07-13: 2023-01-09; 2021-07-13: 2023-01-09 | [13 empty] | Q4 2025 |  |  |  | Requested | [11 empty] | FALSE | TRUE | 725 | 2023-01-09 | 2023-01-09 | 2023 | 2023 | 2023
726 |  | Lanie Patterson | Brent Brooks | 2022-06-09 | 2022-12-01 | L2_bump |  | 2023-05-21 | L2_Bump |  | 2023-10-06 | L2_bump |  | 2023-01-05 | L2_bump | [20 empty] | 7 - MANC |  | 233D2 | 669 |  | WITHDRAWN | WITHDRAWN |  | Glenn Walker | ACADIA ENERGY LLC | ACADIA ENERGY LLC | End Of Sylvester Dr / Manchester | 2000207294 | 30013954687 | Solar | [5 empty] | 44.3324 | -69.8508 | 17 Sylvester Drive | 17 | Sylvester Drive | Manchester | 17.2 | MANCHESTER | 233D2 | 233T1 | 12.47 | 9310-L0064-3540-0069-ED00019 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2022-06-16 | 2022-06-24 | 2022-06-14 | 2022-06-23 | [130 empty] | 2024-01-09 | [37 empty] | TRUE | TRUE | 726 | 0 | 0 | 1900 | 1900 | 1900
727 |  | Lanie Patterson | Brent Brooks | 2022-06-13 | [31 empty] | 5 - BLRD |  | 207D1 | 314 |  | WITHDRAWN | WITHDRAWN |  | Katie Kearney | SOLAMERICA ENERGY LLC | SOLAMERICA ENERGY LLC | 235 South Monmouth Rd | 2000209571 | 30014005828 | Solar | [5 empty] | 44.3765 | -69.7174 | 1019 RIVERSIDE DR | 1019 | Riverside Dr | Vassalboro | 252 | BLAIR ROAD | 207D1 | 207T1 | 12.47 | 9310-L0019-6030-0001-ED00008 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2022-06-21 | 2022-06-28 | 2022-06-14 | 2022-06-27 | 2022-06-27 | 2022-06-28 | 2022-07-12 | 2022-06-29 | 2022-06-29 | 2022-06-29 | 2022-07-14 |  |  | 2022-06-30 |  |  | CS | 2022-06-30 | [6 empty] | CS |  |  | 2022-07-01 | [11 empty] | 2022-07-18 | [8 empty] | 2022-07-18 | [8 empty] | 2022-07-21 | [11 empty] | 2022-09-23 | [6 empty] | 2022-09-21 | [8 empty] | 2022-09-22 | [8 empty] | 2022-09-28 | [8 empty] | 2022-09-28 | [7 empty] | 2022-09-28 | [22 empty] | 2022-10-18 | [37 empty] | TRUE | TRUE | 727 | 0 | 0 | 1900 | 1900 | 1900
728 |  | Lanie Patterson | Brent Brooks | 2022-06-13 | 2022-08-16 | L2_Bump |  | 2023-10-26 | L2_bump |  | 2025-11-26 | L2_With | [23 empty] | 5 - BOST | 1 - BOST | 263D1 | 595 | Yes | EXECUTED | EXECUTED |  | Paula J Fitzgerald | Novel Energy Solutions LLC | ME HEMBREE CSG LLC | 900 Wiscasset Rd / Pittston | 2000297866 | 30014223199 | Solar | 975 | 0.975 | 1334.88 |  |  | 44.1638 | -69.7348 | 900 Wiscasset Rd | 900 | Wiscasset Rd | Pittston | 73.2 | BOWMAN STREET | 263D1 | 34kV Bus No. 2 | 34.5 | 9310-L0102-4660-0051-ED00319 | Non-FERC | NOT IMPACTED | NOT IMPACTED |  | Yes | [6 empty] | 2022-06-21 | 2022-06-28 | 2022-06-15 | 2022-06-27 | 2022-06-27 | 2022-06-28 | 2022-07-12 | 2022-06-30 | 2022-06-30 | 2022-06-30 | 2022-07-15 |  |  | 2022-06-30 |  |  | CS | 2022-06-30 | [6 empty] | CS |  |  | 2022-07-07 |  |  | 2023-01-19 | 2023-11-08 | 2026-01-06 | [6 empty] | 2022-07-07 |  |  |  | 2023-12-07 | 2026-02-17 |  |  |  | 2022-07-08 |  |  | 2023-01-20 | 2023-12-07 | 2026-02-23 |  |  |  | 2022-07-21 |  |  | 2023-01-21 | 2023-12-07 | 2026-02-23 | [6 empty] | 2022-09-23 | [6 empty] | 2022-09-22 |  |  | 2023-03-06 | 2024-03-05 | 2026-04-22 | [6 empty] | 2023-03-06 | 2024-03-05 | 2026-04-22 | [7 empty] | 2024-03-06 | 2026-05-07 | [7 empty] | 2024-03-14 | [7 empty] | 2024-04-04 |  |  |  | 2023-03-10 |  | 2023-03-10 | 2024-04-01 | 2023-03-13 | 2024-04-01 | [5 empty] | 367574 | 2023-03-02 | 271390 | 2026-04-22 |  | 2023-03-14 | 2023-03-14 | 2024-04-02 | 2024-05-01 | 2026-07-08 | 2026-07-09 | [15 empty] | Q1 2027 |  |  |  | Requested | [11 empty] | FALSE | TRUE | 728 | 2023-03-14 | 2023-03-14 | 2023 | 2023 | 2023
729 |  | Lanie Patterson | Brent Brooks | 2022-06-20 | [31 empty] | 7 - PDRD |  | 262D1 | 692 |  | WITHDRAWN | WITHDRAWN |  | Nicholas Ford | Hexagon Energy LLC | Mayflower Solar, LLC | 615 MAIN ST READFIELD ME | 2000299508 | 30014243403 | Solar | [5 empty] | 44.3706 | -69.9296 | 615 Main St | 615 | Main St | Readfield | 174 | PUDDLEDOCK ROAD | 262D1 | 34.5kV Bus | 34.5 | 9310-L0101-4910-0057-ED00089 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2022-06-27 | 2022-07-05 | 2022-06-24 | 2022-07-01 | 2022-11-17 | 2022-11-28 | 2022-12-05 | 2022-12-01 | 2022-12-05 | 2022-12-05 | 2022-12-19 | [123 empty] | 2022-12-20 | [37 empty] | TRUE | TRUE | 729 | 0 | 0 | 1900 | 1900 | 1900
730 |  |  | KRISTOFER COLEMAN | 2022-06-29 | 2024-02-08 | L2_Bump | [27 empty] | 1 - BRIS |  | 4 - BRIS |  | 210D2 | 511 | Yes | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Nathaniel Curtis | MIDCOAST SOLAR LLC | Bristol Community Solar LLC | 83 CHRISTIAN HILL RD BRISTOL | 2000433022 | 30016054774 | Solar | [5 empty] | 43.9677 | -69.5256 | 83 Christian Hill Road | 83 | Christian Hill Road | Bristol | 11 | BRISTOL | 210D2 | 210T1 | 12.47 | 9310-L0478-0710-0070-ED00013 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2022-07-07 | 2022-07-14 | 2022-07-01 | 2022-07-11 | 2022-07-12 | 2022-07-12 | 2022-07-25 | 2022-07-21 | 2022-07-21 | 2022-07-21 | 2022-08-04 |  |  | 2022-07-27 |  |  | CS | 2022-07-27 | [6 empty] | CS |  |  | 2022-07-27 |  |  | 2024-02-13 | [8 empty] | 2022-08-01 |  |  | 2024-02-29 | [5 empty] | 2022-08-01 |  |  | 2024-03-19 | [5 empty] | 2022-08-08 |  |  | 2024-03-20 | [8 empty] | 2022-10-12 | [6 empty] | 2022-10-12 |  |  | 2024-05-22 | [5 empty] | 2022-10-12 |  |  | 2024-05-22 | [5 empty] | 2022-10-17 | [8 empty] | 2022-10-17 | [7 empty] | 2022-10-17 | [7 empty] | 2022-11-02 |  | 2022-11-08 | 2024-06-06 | 2022-11-09 | 2024-07-30 | [5 empty] | 452050 |  | 411337 | 2024-05-21 | 2025-05-15 | 2021-07-13: 2022-11-14; 2021-07-13: 2022-11-15; 2021-07-13: 2024-08-01; 2021-07-13: 2024-08-01 | [13 empty] | Q4 2026 | [15 empty] | FALSE | TRUE | 730 | 2022-11-14 | 2022-11-14 | 2022 | 2022 | 2022
731 |  | Lanie Patterson | Brent Brooks | 2022-07-11 |  | L2_Bump |  | 2023-01-18 | wthdw |  | 2023-03-27 | wthdw |  | 2025-06-06 | L2_With | [19 empty] | 371 | 6 - VASS | 1 - VASS | 861D8 | 371 | Yes | EXECUTED | EXECUTED |  | Paula J Fitzgerald | Novel Energy Solutions LLC | ME Vassalboro Cain CS LLC | 2235 riverside rd, Vassalboro ME | 2000250310 | 30015802611 | Solar | 975 | 0.975 | 1360.8 |  |  | 44.4567 | -69.6751 | Riverside Drive |  | Riverside Drive | Vassalboro | 04 | VASSALBORO | 861D8 | 861T1 | 12.47 | 9310-L0444-6035-0027-ED00006 | Non-FERC | COST SHARE | COST SHARE($250,000) | 29017 | Yes | [6 empty] | 2022-07-18 | 2022-07-25 | 2022-07-14 | 2022-07-20 | 2023-01-18 | 2023-01-25 | 2023-02-01 | 2023-01-25 | 2023-01-31 | 2023-01-31 | 2023-02-14 |  |  | 2023-02-13 |  |  | CS | [7 empty] | CS |  |  | 2023-02-14 |  |  | 2023-12-14 | 2025-06-30 | [7 empty] | 2023-03-01 |  |  | 2023-12-20 | 2025-08-05 |  |  |  |  | 2023-03-07 |  |  | 2024-01-08 | 2025-08-06 |  |  |  |  | 2024-01-08 |  |  | 2024-01-08 | 2025-08-06 | [7 empty] | 2024-03-05 | [6 empty] | 2024-03-05 |  |  | 2024-03-05 | 2025-10-07 | [7 empty] | 2024-03-05 | 2025-10-07 | [7 empty] | 2024-03-06 | 2025-10-22 | [7 empty] | 2024-03-13 | 2025-10-24 | [6 empty] | 2024-03-13 | 2025-10-24 |  |  |  | 2024-03-21 |  | 2024-03-22 | 2025-11-20 | 2024-03-26 | 2025-11-20 | [5 empty] | 679341 | 2024-03-04 | 667046 | 2025-10-06 |  | 2021-07-13: 2024-03-27; 2021-07-13: 2024-03-27; 2021-07-13: 2025-11-21; 2021-07-13: 2025-11-21 | [13 empty] | Q2 2026 | [15 empty] | TRUE | FALSE |  | 2024-03-27 | 2024-03-27 | 2024 | 2024 | 2024
732 |  | Govinda Neupane |  | 2022-07-18 | 2023-05-22 | L2_Bump |  | 2023-11-14 | wthdw |  | 2024-05-10 | wthdw |  |  |  |  | 2025-07-15 | wthdw | [15 empty] | 3 - LVFA | 680 | 10 - LVFA | 1 - LVFA | 428D3 | 680 | Yes | EXECUTED | EXECUTED |  | Paula J Fitzgerald | Novel Energy Solutions LLC | ME CLEAR BROOK ROAD 1 CSG LLC | CLAYBROOK RD JAY | 2000305351 | 30014325853 | Solar | 999 | 0.999 | 1388.4 |  |  | 44.4888 | -70.1659 | Claybrook Road |  | Claybrook Road | Jay | 15 | LIVERMORE FALLS | 428D3 | 428T1 | 12.47 | 9310-L0162-2920-0025-ED00008 | FERC | NOT IMPACTED | NOT IMPACTED |  | Yes | [6 empty] | 2022-07-25 | 2022-08-01 | 2022-07-22 | 2022-07-27 | 2022-09-14 | 2022-09-14 | 2022-09-28 | 2022-09-29 | 2022-09-29 | 2022-09-29 | 2022-10-14 |  |  | 2022-09-30 |  |  | CS | 2022-09-30 | [6 empty] | CS |  |  | 2022-10-03 |  |  | 2023-11-16 | 2024-05-13 | 2025-07-17 | [7 empty] | 2023-03-03 |  | 2023-12-07 | 2024-05-31 | 2025-08-06 |  |  |  | 2022-11-14 | 2023-02-14 |  | 2023-12-07 | 2024-05-31 | 2025-08-06 |  |  |  | 2022-11-15 | 2023-03-06 |  | 2023-12-27 | 2024-05-31 | 2025-08-06 | [6 empty] | 2023-01-23 | 2023-04-17 | [5 empty] | 2023-01-17 | 2023-04-10 |  | 2024-03-04 | 2024-08-02 | 2025-10-08 |  |  |  | 2023-01-17 | 2023-04-10 |  | 2024-03-04 | 2024-08-05 | 2025-10-08 |  |  |  | 2022-01-18 | 2023-04-11 |  | 2024-03-06 | 2024-08-06 | 2025-10-14 |  |  |  | 2023-01-24 | 2023-04-14 |  | 2024-03-12 | 2024-08-09 | 2025-10-16 |  |  | 2023-01-24 | 2023-04-14 |  | 2024-03-12 | 2024-08-09 | 2025-10-16 |  |  | 2023-04-18 |  | 2023-04-18 | 2024-03-14 | 2023-04-19 | [6 empty] | 480887 | 2023-04-07 | 391715 | 2025-10-08 |  | 2023-04-19 | 2023-04-20 | 2024-03-15 | 2024-03-15 | 2024-09-05 | 2024-09-05 | 2025-11-20 | 2025-11-21 | [13 empty] | Q4 2025 |  |  |  | Requested | [11 empty] | FALSE | FALSE |  | 2023-04-19 | 2023-04-19 | 2023 | 2023 | 2023
733 |  | Lanie Patterson | Brent Brooks | 2022-07-21 | [31 empty] | 5 - MCCO |  | 237D1 | 548 |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED |  | Cara Koontz | Sunvest Solar Inc. | VASSALBORO CSG 1 LLC | WEBBER POND RD, VASSALBORO | 2000346962 | 30014868308 | Solar | 1000 | 1 | 1272 |  |  | 44.4338 | -69.653 | 1077 Webber Pond Rd | 1077 | Webber Pond Rd | Vassalboro | 6 | MCCOYS | 237D1 | 237T1 | 12.47 | 9310-L0067-6030-0060-ED00093 | Non-FERC |  |  |  | Yes | [6 empty] | 2022-07-28 | 2022-08-04 | 2022-07-27 | 2022-07-28 | 2022-07-29 | 2022-08-08 | 2022-08-12 | 2022-08-12 | 2022-08-12 | 2022-08-12 | 2022-08-26 |  |  | 2022-08-26 |  |  | CS | 2022-08-26 | [6 empty] | CS |  |  | 2022-09-12 | [11 empty] | 2022-09-14 | [8 empty] | 2022-10-04 | [8 empty] | 2022-10-04 | [11 empty] | 2022-12-12 | [6 empty] | 2022-12-12 | [8 empty] | 2022-12-13 | [8 empty] | 2022-12-13 | [8 empty] | 2022-12-15 | [7 empty] | 2022-12-15 | [7 empty] | 2022-12-19 |  | 2022-12-19 |  | 2022-12-27 | [6 empty] | 324604 | 2022-12-12 |  |  |  | 2021-07-13: 2022-12-28; 2021-07-13: 2022-12-28 | [17 empty] | Requested | [11 empty] | TRUE | FALSE |  | 2022-12-28 | 2022-12-28 | 2022 | 2022 | 2022
734 |  |  | Eben Snow | 2022-07-22 | [31 empty] | 1 - MIDD |  | 451D8 |  |  | WITHDRAWN | WITHDRAWN |  | Jacques Guillet | NUPOWER BATTERY STORAGE LLC | NUPOWER BATTERY STORAGE LLC | 25 Middle St Lewiston | 2000291110 | 30014131178 | Battery | [5 empty] | 44.1019 | -70.2186 | 25 Middle Street | 25 | Middle Street | Lewiston | 2 | MIDDLE STREET | 451D8 | 451T2 | 12.47 | 9310-L0487-3230-0014-ED00004 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2022-07-29 | 2022-08-05 | 2022-07-27 | 2022-08-01 | 2022-08-01 | 2022-08-01 | 2022-08-15 | 2022-08-05 | 2022-08-05 | 2022-08-05 | 2022-08-19 |  |  | 2022-08-19 |  |  | CS | 2022-08-19 | [6 empty] | CS |  |  | 2022-08-22 | [11 empty] | 2022-08-23 | 2022-12-23 | [7 empty] | 2022-08-22 | 2022-12-23 | [7 empty] | 2022-08-25 | 2023-01-10 | [10 empty] | 2022-10-31 | 2022-02-23 | [5 empty] | 2022-11-01 | 2023-02-20 | [7 empty] | 2022-11-02 | [8 empty] | 2022-11-03 | [8 empty] | 2022-11-08 | [30 empty] | 2023-03-30 | [37 empty] | TRUE | FALSE |  | 0 | 0 | 1900 | 1900 | 1900
735 |  | Eben Snow | Brent Brooks | 2022-07-25 | 2023-06-06 | L2_Bump | [29 empty] | 8 - MEFA |  | 431D1 | 604 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Geoffrey Sparrow | MECHANIC FALLS GLC SOLAR LLC | MECHANIC FALLS GLC SOLAR LLC | PO Box 658 | 2000259944 | 30013701567 | Solar | [5 empty] | 44.1073 | -70.3732 | Lewiston St. |  | Lewiston St. | Mechanic Falls | 48 | MECHANIC FALLS | 431D1 | 431T2 | 12.47 | 9310-L0165-3610-0032-ED00055 | FERC | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2022-08-01 | 2022-08-08 | 2022-07-27 | 2022-08-01 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-12 | 2022-08-12 | 2022-08-12 | 2022-08-26 |  |  | 2022-08-15 |  |  | CS | 2022-08-15 | [6 empty] | CS |  |  | 2022-08-22 | [11 empty] | 2022-08-30 | [8 empty] | 2022-08-30 | [8 empty] | 2022-09-06 | [11 empty] | 2022-11-09 | [6 empty] | 2022-11-08 | [8 empty] | 2022-11-09 | [8 empty] | 2022-11-14 | [8 empty] | 2022-11-17 | [7 empty] | 2022-11-18 | [7 empty] | 2022-11-17 |  | 2022-11-29 |  | 2022-11-29 | [6 empty] | 210092 | 2022-11-08 |  |  | 2023-06-14 | 2021-07-13: 2022-11-29; 2021-07-13: 2022-11-29 | [17 empty] | Requested | [11 empty] | TRUE | FALSE |  | 2022-11-29 | 2022-11-29 | 2022 | 2022 | 2022
736 |  |  | KRISTOFER COLEMAN | 2022-07-26 | [31 empty] | 4 - DAMS |  | 219D2 | 642 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Nathaniel Curtis | MIDCOAST SOLAR LLC | MIDCOAST SOLAR LLC |  | 2000162495 | 30014346503 | Solar/Battery | [5 empty] | 44.0222 | -69.5761 | 750 US RT 1 | 50 | US Route 1 | Newcastle | 34 | DAMARISCOTTA MILLS | 219D2 | 219T1 | 12.47 | 9310-L0051-4100-0074-ED00052 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2022-08-02 | 2022-08-09 | 2022-07-27 | 2022-08-01 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-16 | 2022-08-16 | 2022-08-16 | 2022-08-30 |  |  | 2022-08-29 |  |  | CS | 2022-08-29 | [6 empty] | CS |  |  | 2022-08-29 | [11 empty] | 2022-09-08 | [8 empty] | 2022-09-09 | [8 empty] | 2022-09-12 | [11 empty] | 2022-11-16 | [6 empty] | 2022-11-09 | [8 empty] | 2022-11-09 | [8 empty] | 2022-11-10 | [8 empty] | 2022-11-14 | [7 empty] | 2022-11-15 | [7 empty] | 2022-11-29 |  | 2022-11-29 |  | 2022-11-30 | [6 empty] | 784953 | 2022-11-08 |  |  | 2023-05-23 | 2021-07-13: 2022-11-30; 2021-07-13: 2022-12-01 | [17 empty] | Requested | [11 empty] | TRUE | FALSE |  | 2022-11-30 | 2022-11-30 | 2022 | 2022 | 2022
737 |  | Govinda Neupane |  | 2022-07-29 | 2023-12-23 | wthdw | [29 empty] | 8 - SKNS | 1 - SKNS | 853D1 | 406 | Yes | EXECUTED | EXECUTED |  | Paula J Fitzgerald | Novel Energy Solutions LLC | ME Madison Kandiko CSG LLC | Lakewood Road | 2000250310 | 30014726894 | Solar | 975 | 0.975 |  |  |  | 44.8183 | -69.7777 | Lakewood Road |  | Lakewood Road | Madison | 122 | SKOWHEGAN NORTH SIDE | 853D1 | 853T1 | 12.47 | 9310-L0430-3510-0027-ED00219 | Non-FERC | COST SHARING | COST SHARING (325,000) | 53042 | Yes | [6 empty] | 2022-08-05 | 2022-08-12 | 2022-08-04 | 2022-08-04 | 2022-08-04 | 2022-08-04 | 2022-08-18 | 2022-08-11 | 2022-08-11 | 2022-08-11 | 2022-08-25 |  |  | 2022-08-19 |  |  | CS | 2022-08-19 | [6 empty] | CS |  |  | 2022-08-22 |  |  | 2023-12-29 | [8 empty] | 2022-08-22 |  |  | 2024-02-06 | [5 empty] | 2022-08-22 |  |  | 2024-02-07 | [5 empty] | 2022-08-24 |  |  | 2024-02-07 | [8 empty] | 2022-10-26 | [6 empty] | 2022-10-31 |  |  | 2024-04-11 | [5 empty] | 2022-11-14 |  |  | 2024-04-11 | [5 empty] | 2022-11-14 |  |  | 2024-04-15 | [5 empty] | 2022-11-17 |  |  | 2024-04-19 |  |  |  |  | 2022-11-17 |  |  | 2024-04-19 |  |  |  |  | 2022-12-12 |  | 2022-12-15 | 2024-05-24 | 2023-01-06 | 2024-06-20 | [5 empty] | 271597 | 2022-10-08 | 158179 | 2024-04-10 |  | 2021-07-13: 2023-01-09; 2021-07-13: 2023-01-09; 2021-07-13: 2024-06-21; 2021-07-13: 2024-06-21 | [13 empty] | Q3 2025 |  |  |  | Requested | [11 empty] | TRUE | FALSE |  | 2023-01-09 | 2023-01-09 | 2023 | 2023 | 2023
738 |  | Govinda Neupane |  | 2022-08-09 | 2023-06-27 | L2_Bump | [29 empty] | 3 - ANDO |  | 400D1 | 602 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Geoffrey Sparrow | GREEN LANTERN DEVELOPMENT LLC | Trotting Park GLC Solar, LLC | 436 s main st andover | 2000249820 | 30013566739 | Solar | [5 empty] | 44.6208 | -70.7469 | 436 South Main Street | 436 | South Main Street | Andover | 91.3 | ANDOVER | 400D1 | 400T1 | 12.47 | 9310-L0112-0120-0002-ED00187 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2022-08-16 | 2022-08-23 | 2022-08-11 | 2022-08-11 | 2022-08-11 | 2022-08-15 | 2022-08-29 | 2022-08-25 | 2022-08-25 | 2022-08-25 | 2022-09-09 |  |  | 2022-08-25 |  |  | CS | 2022-08-25 | [6 empty] | CS |  |  | 2022-08-30 | [11 empty] | 2022-08-30 | [8 empty] | 2022-08-30 | [8 empty] | 2022-09-09 | [11 empty] | 2022-11-15 | [6 empty] | 2022-11-10 | [8 empty] | 2022-11-10 | [8 empty] | 2022-11-14 | [8 empty] | 2022-11-17 | [7 empty] | 2022-11-18 | [7 empty] | 2022-12-08 |  | 2022-12-08 |  | 2022-12-12 | [6 empty] | 439388 | 2022-11-08 |  |  | 2023-07-20 | 2021-07-13: 2022-12-12; 2021-07-13: 2022-12-13 | [17 empty] | 10300988224 | [11 empty] | TRUE | FALSE |  | 2022-12-12 | 2022-12-12 | 2022 | 2022 | 2022
739 |  |  | KRISTOFER COLEMAN | 2022-08-11 | 2023-03-28 | L2_Bump | [29 empty] | 3 - MESS |  | 238D1 | 608 |  | WITHDRAWN | WITHDRAWN |  | Santiago Quijano | Bluewave MA, LLC | BLUEWAVE ORIGINATION LLC |  | 2000310625 | 30014395724 | Solar/Battery | [5 empty] | 44.0234 | -69.6619 | 284 Federal St | 284 | Federal St | Wiscasset | 3 | MESSINA | 238D1 | 238T1 | 12.47/7.2 | 9310-L0068-6463-0041-ED00180 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2022-08-18 | 2022-08-25 | 2022-08-15 | 2022-08-24 | 2022-08-24 | 2022-08-24 | 2022-09-08 | 2022-08-30 | 2022-08-30 | 2022-08-31 | 2022-09-14 |  |  | 2022-09-13 |  |  | CS | 2022-09-13 | [6 empty] | CS |  |  | 2022-09-20 | [7 empty] | 2022-09-21 |  |  |  | 2022-09-21 | [8 empty] | 2022-09-21 | 2023-01-24 | [7 empty] | 2022-09-23 | 2023-01-24 | [10 empty] | 2022-12-01 | 2023-03-08 | [5 empty] | 2022-12-01 | 2023-03-07 | [7 empty] | 2022-12-01 | 2023-03-08 | [7 empty] | 2022-12-02 | N/A | [7 empty] | 2022-12-15 | N/A | [6 empty] | 2022-12-15 | [18 empty] | 3423065 | 2022-12-01 | 3139885 | 2023-03-06 | 2024-03-14
740 |  | Eben Snow | Brent Brooks | 2022-08-18 | 2022-08-22 | L2_Bump |  | 2024-02-22 | wthdw | [26 empty] | 3 - RA34 |  | 444D1 | 665 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Sachin Patel | Mainely Solar LLC | ALLEN SOLAR LLC | 1565 ROOSEVELT TRL RAYMOND | 2000219534 | 30013148686 | Solar/Battery | [5 empty] | 43.9096 | -70.501 | 1565 Roosevelt Trail | 1565 | Roosevelt Trail | Raymond | 469 | RAYMOND 34 KV | 444D1 | 444T1 | 12.47 | 9310-L0181-4900-0084-ED00255 | Non-FERC | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2022-08-25 | 2022-09-01 | 2022-08-22 | 2022-08-24 | 2023-06-01 | 2023-06-01 | 2023-06-15 | 2023-06-06 | 2023-06-09 | 2023-06-09 | 2023-06-23 |  |  | 2023-06-15 |  |  | CS | [7 empty] | CS |  |  | 2023-06-22 |  |  | 2024-02-27 | [8 empty] | 2023-07-05 |  |  | 2024-03-12 | [5 empty] | 2023-07-11 |  |  | 2024-03-12 | [5 empty] | 2023-07-11 |  |  | 2024-03-12 | [8 empty] | 2023-09-13 | [6 empty] | 2023-09-13 |  |  | 2024-05-15 | [5 empty] | 2023-09-14 |  |  | 2024-05-16 | [5 empty] | 2023-09-26 |  |  | 2024-05-16 | [5 empty] | 2023-09-28 |  |  | 2024-05-21 |  |  |  |  | 2023-09-28 |  |  | 2024-05-21 |  |  |  |  | 2023-10-18 |  | 2023-10-30 |  | 2023-11-08 | [6 empty] | 163713 | 2023-09-13 | 406986 | 2024-05-01 | 2024-05-23 | 2021-07-13: 2023-11-22; 2021-07-13: 2023-11-27 | [9 empty] | -5 | [19 empty] | TRUE | FALSE |  | 2023-11-22 | 2023-11-22 | 2023 | 2023 | 2023
741 |  | Govinda Neupane |  | 2022-08-18 | [29 empty] | 3 - SKTP |  | 7 - SKTP |  | 864D1 | 714 |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED |  | Tyler William Perkins | Nexamp, Inc | Mercer Renewables 2, LLC | 1053 Mercer Road, SOLAR | 2000311674 | 30014588658 | Solar | 999 | 0.999 | 1319.76 |  |  | 44.6804 | -69.8877 | 1053 Mercer Rd | 1053 | Mercer Rd | Mercer | 122 | SKOWHEGAN TAP | 864D1 | 864T1 | 12.47 | 9310-L0446-3640-0002-ED00035 | FERC | COST SHARING | COST SHARING (290,000) | 145219 | Yes | [6 empty] | 2022-08-25 | 2022-09-01 | 2022-08-22 | 2022-08-24 | 2022-08-25 | 2022-08-25 | 2022-09-09 | 2022-09-06 | 2022-09-06 | 2022-09-20 | 2021-10-04 |  |  | 2022-10-05 | 2023-03-13 |  | CS | 2022-10-05 | [6 empty] | CS |  |  | 2022-10-05 | 2023-03-13 | [10 empty] | 2022-10-20 | 2023-03-31 | [7 empty] | 2022-10-19 | 2023-04-13 | [7 empty] | 2022-10-26 | 2023-04-18 | [10 empty] | 2023-01-05 | 2023-05-31 | [5 empty] | 2023-01-05 | 2023-05-30 | [7 empty] | 2022-01-05 | 2023-05-30 | [7 empty] | 2023-01-11 | 2023-06-05 | [7 empty] | 2023-01-31 | 2023-06-08 | [6 empty] | 2022-02-01 | 2023-06-08 | [6 empty] | 2023-06-08 |  | 2023-06-08 |  | 2023-06-21 | [6 empty] | 981812 | 2023-05-18 |  |  |  | 2021-07-13: 2023-07-31; 2021-07-13: 2023-08-01 | [9 empty] | -1 |  |  |  | Q4 2025 | [15 empty] | FALSE | FALSE |  | 2023-07-31 | 2023-07-31 | 2023 | 2023 | 2023
742 |  | Govinda Neupane |  | 2022-08-18 | [31 empty] | 8 - SKTP |  | 864D1 | 741 |  | WITHDRAWN | WITHDRAWN |  | Henry Barrett | Nexamp, Inc | Mercer Renewables, LLC | 1053 Mercer Road, SOLAR, Mercer | 2000114877 | 30014588492 | Solar | [5 empty] | 44.6834 | -69.8784 | 953 Mercer Road | 953 | Mercer Road | Mercer | 115 | SKOWHEGAN TAP | 864D1 | 864T1 | 12.47 | 9310-L0446-3640-0002-ED00027 | FERC | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2022-08-25 | 2022-09-01 | 2022-08-23 | 2022-08-24 | 2023-08-01 | 2023-08-08 | 2023-08-15 | 2023-08-28 | 2023-09-11 | 2023-09-11 | 2023-09-25 |  |  | 2023-09-13 |  |  | CS | [7 empty] | CS |  |  | 2023-09-21 | [11 empty] | 2023-10-02 | [17 empty] | 2023-12-12 | [11 empty] | 2024-02-16 | [6 empty] | 2024-02-16 | [8 empty] | 2024-02-16 | [8 empty] | 2024-02-22 | [35 empty] | 1245540 | 2024-02-16 |  |  | 2024-04-02 | [17 empty] | 0 | [19 empty] | TRUE | FALSE |  | 0 | 0 | 1900 | 1900 | 1900
743 |  |  | Anthony Boucher | 2022-08-26 | 2024-10-09 | wthdw | [28 empty] | 676 | 4 - LINC |  | 800D1 | 676 | Yes | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Bradley Parsons | VCP REALTY LLC | NORTHPORT SOLAR ONE LLC | 711 BANGOR RD / PROSPECT | 2000345504 | 30014850470 | Solar | [5 empty] | 44.3111 | -68.9819 | 185 Atlantic Highway | 185 | Atlantic Highway | Northport | 252 | LINCOLNVILLE | 800D1 | 800T1 | 12.47 | 9310-L0378-4210-0001-ED00233 | FERC | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2022-09-02 | 2022-09-12 | 2022-08-31 | 2022-09-07 | 2022-10-17 | 2022-10-17 | 2022-10-31 | 2022-10-21 | 2022-10-21 | 2022-10-21 | 2022-11-04 |  |  | 2022-10-24 |  |  | CS | 2022-10-24 | [6 empty] | CS |  |  | 2022-10-24 |  |  | 2025-04-02 | [17 empty] | 2022-11-11 | [8 empty] | 2022-11-11 | [11 empty] | 2023-01-20 | [6 empty] | 2023-01-11 | [8 empty] | 2023-01-11 | [8 empty] | 2023-01-17 | [8 empty] | 2023-01-23 | [7 empty] | 2023-01-23 | [7 empty] | 2023-02-06 |  | 2023-02-07 | 2023-02-24 | 2023-02-24 | 2023-02-24 | [5 empty] | 190841 | 2023-01-11 |  |  | 2025-04-16 | 2021-07-13: 2023-02-24; 2021-07-13: 2023-02-24 | [9 empty] | 0 |  |  |  | Q4 2024 |  |  |  | Requested | [11 empty] | TRUE | FALSE |  | 2023-02-24 | 2023-02-24 | 2023 | 2023 | 2023
744 |  | Marshall Ripley | Rick Duperre | 2022-08-30 | 2023-05-30 | L2_Bump | [29 empty] | 5 - NOWI |  | 639D2 | 688 |  | WITHDRAWN | WITHDRAWN |  | Geoffrey Sparrow | GREEN LANTERN DEVELOPMENT LLC | ROOSEVELT TRL GLC SOLAR LLC | 994 ROOSEVELT TRL WINDHAM | 2000259634 | 30013697286 | Solar | [5 empty] | 43.8591 | -70.4578 | 994 Roosevelt Trail | 994 | Roosevelt Trail | Windham | 345 | NORTH WINDHAM | 639D2 | 639T2 | 12.47 | 9310-L0276-6390-0101-ED00545 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2022-09-07 | 2022-09-14 | 2022-08-31 | 2022-09-07 | 2022-11-28 | 2022-12-12 | 2022-12-12 | 2022-12-13 | 2022-12-15 | 2022-12-15 | 2022-12-30 |  |  | 2022-12-15 |  |  | CS | [7 empty] | CS |  |  | 2022-12-16 | [11 empty] | 2022-12-19 | [8 empty] | 2023-01-06 | [8 empty] | 2023-01-09 | [11 empty] | 2023-03-15 | [6 empty] | 2023-03-16 | [8 empty] | 2023-03-17 | [8 empty] | 2023-03-17 | [8 empty] | 2023-03-23 | [7 empty] | 2023-03-28 | [7 empty] | 2023-04-14 |  | 2023-04-17 | 2023-05-11 |  | 2023-05-12 | [5 empty] | 452019 | 2023-03-13 |  |  | 2023-06-06 | [17 empty] | 0 | [19 empty] | TRUE | FALSE |  | 0 | 0 | 1900 | 1900 | 1900
745 |  | Lanie Patterson | Brent Brooks | 2022-09-08 | [30 empty] | 725 | 5 - SOCH |  | 244D1 | 725 |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED |  | John Calabro | Madison Energy Holdings | Madison Energy Holdings LLC | PIT RD CHINA | 2000465208 | 30016538560 | Solar | 975 | 0.975 | 1552.32 |  |  | 44.3849 | -69.5727 | Pit Road |  | Pit Road | South China | 14.3 | SOUTH CHINA | 244D1 | 244T1 | 12.47 | 9310-L0078-1150-0120-ED00030 |  | TRIGGERING | TRIGGERING | 220000 | Yes | [6 empty] | 2022-09-15 | 2022-09-22 | 2022-09-13 | 2022-09-20 | 2023-01-09 | 2023-01-09 | 2024-01-24 | 2023-01-10 | 2023-01-13 | 2023-01-13 | 2023-01-30 |  |  | 2023-02-26 |  |  | CS | [7 empty] | CS |  |  | 2023-04-13 | [11 empty] | 2023-04-08 | [8 empty] | 2023-04-28 | [8 empty] | 2023-05-01 | [11 empty] | 2023-07-06 | [6 empty] | 2023-07-07 | [8 empty] | 2023-07-07 | [8 empty] | 2023-07-10 | [8 empty] | 2023-07-13 | [7 empty] | 2023-07-13 | [7 empty] | 2023-07-27 |  | 2023-07-27 |  | 2023-08-23 | [6 empty] | 400663 | 2023-07-06 |  |  |  | 2021-07-13: 2023-08-24; 2021-07-13: 2023-08-24; 2021-07-13: 2023-12-12; 2021-07-13: 2023-12-13 | [9 empty] | 0 |  |  |  | Q2 2025 | [15 empty] | TRUE | FALSE |  | 2023-08-24 | 2023-08-24 | 2023 | 2023 | 2023
746 |  | Lanie Patterson | Brent Brooks | 2022-09-08 | 2023-07-27 | L2_Bump | [29 empty] | 6 - SHAW | 1 - SHAW | 852D1 | 527 | Yes | EXECUTED | EXECUTED |  | Paula J Fitzgerald | Novel Energy Solutions LLC | ME FAIRFIELD EMERY 1 CSG LLC | OLD COUNTY RD, FAIRFIELD 04937 | 2000296139 | 30014199969 | Solar | 500 | 0.5 | 649.2 |  |  | 44.6234 | -69.5967 | Old County Rd |  | Old County Rd | Fairfield | 503 | SHAWMUT | 852D1 | 852T1 | 12.47 | 9310-L0429-2000-0059-ED00009 |  | NOT IMPACTED | NOT IMPACTED | NONE | Yes | [6 empty] | 2022-09-15 | 2022-09-22 | 2022-09-13 | 2022-09-20 | 2022-09-20 | 2022-09-20 | 2022-10-04 | 2022-09-27 | 2022-09-27 | 2022-09-27 | 2022-10-12 |  |  | 2022-10-10 |  |  | CS | 2022-10-10 | [6 empty] | CS |  |  | 2022-10-10 |  |  | 2023-07-31 | [8 empty] | 2022-10-19 |  |  | 2024-12-20 | [5 empty] | 2022-11-02 |  |  | 2024-03-25 | [5 empty] | 2022-11-02 |  |  | 2024-03-25 | [8 empty] | 2023-01-11 | [6 empty] | 2023-01-10 |  |  | 2024-05-29 | [5 empty] | 2023-01-11 |  |  | 2024-05-30 | [5 empty] | 2023-01-18 |  |  | 2024-06-17 | [5 empty] | 2023-01-19 |  |  | 2024-06-21 |  |  |  |  | 2023-01-19 |  |  | 2024-06-21 |  |  |  |  | 2023-01-23 |  | 2023-01-23 | 2024-07-16 | 2023-02-09 | [6 empty] | 378041 | 2023-01-10 | 459865 | 2024-05-29 |  | 2021-07-13: 2023-02-13; 2021-07-13: 2023-02-13; 2021-07-13: 2024-08-28; 2021-07-13: 2024-08-28 | [9 empty] | 0 |  |  |  | Q4 2025 |  |  |  | Requested | [11 empty] | FALSE | FALSE |  | 2023-02-13 | 2023-02-13 | 2023 | 2023 | 2023
747 |  | Eben Snow | Brent Brooks | 2022-10-07 | 2022-10-20 | wthdw |  | 2023-02-15 | L2_Bump | [26 empty] | 4 - LOVE |  | 430D1 | 410 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Sai Chandra Munagal | Nexamp, Inc | NEXAMP SOLAR LLC | 1011 Knights Hill Rd Sweden | 2000114877 | 30014526336 | Solar | [5 empty] | 44.1235 | -70.8617 | 1011 Knights Hill Road | 1011 | Knights Hill Road | Sweden | 117 | LOVELL | 430D1 | 430T1 | 12.47 | 9310-L0164-5640-0004-ED00022 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2022-10-17 | 2022-10-24 | 2022-10-10 | 2022-10-14 | 2023-04-06 | 2023-04-20 | 2023-04-20 | 2023-04-14 | 2023-04-28 | 2023-04-28 | 2023-05-12 |  |  | 2023-04-28 |  |  | CS | [7 empty] | CS |  |  | 2023-05-01 | [11 empty] | 2023-05-16 | [8 empty] | 2023-05-16 | [8 empty] | 2023-05-17 | [11 empty] | 2023-07-24 | [6 empty] | 2023-07-12 | [8 empty] | 2023-07-12 | [8 empty] | 2023-07-18 | [8 empty] | 2023-07-24 | [7 empty] | 2023-07-24 | [7 empty] | 2023-08-14 |  | 2023-08-14 |  | 2023-09-12 | [6 empty] | 349486 | 2023-07-12 |  |  | 2024-05-20 | 2021-07-13: 2023-09-15; 2021-07-13: 2023-09-18 | [9 empty] | -3 | [7 empty] | REQUESTED | [11 empty] | TRUE | FALSE |  | 2023-09-15 | 2023-09-15 | 2023 | 2023 | 2023
748 |  | Eben Snow | Brent Brooks | 2022-10-07 | 2022-10-20 | wthdw |  | 2023-02-15 | L2_Bump | [26 empty] | 5 - LOVE |  | 430D1 | 747 |  | WITHDRAWN | WITHDRAWN |  | Frank DuBose | Nexamp, Inc | NEXAMP SOLAR LLC | 748 Lovell Rd Sweden | 2000114877 | 30014526351 | Solar | [5 empty] | 44.1255 | -70.8742 | 748 Lovell Road | 748 | Lovell Road | Sweden | 123 | LOVELL | 430D1 | 430T1 | 12.47 | 9310-L0164-5640-0004-ED00029 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2022-10-17 | 2022-10-24 | 2022-10-10 | 2022-10-14 | 2023-09-18 | 2023-09-20 | 2023-10-02 | 2023-10-05 | 2023-10-10 | 2023-10-10 | 2023-10-24 | [123 empty] | 2023-10-24 | [17 empty] | 0 | [19 empty] | TRUE | FALSE |  | 0 | 0 | 1900 | 1900 | 1900
749 |  | Eben Snow | Brent Brooks | 2022-10-07 | 2022-10-20 | wthdw |  | 2023-02-15 | L2_Bump |  | 2023-10-24 | [24 empty] | 6 - LOVE |  | 430D1 | 748 |  | WITHDRAWN | WITHDRAWN |  | Frank DuBose | Nexamp, Inc | NEXAMP SOLAR LLC | 1013 Knights Hill Rd Sweden | 2000114877 | 30014526344 | Solar | [5 empty] | 44.121 | -70.8692 | 1013 Knights Hill Road | 1013 | Knights Hill Road | Sweden | 114 | LOVELL | 430D1 | 430T1 | 12.47 | 9310-L0164-5640-0004-ED00019 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2022-10-17 | 2022-10-24 | 2022-10-10 | 2022-10-14 | [130 empty] | 2024-05-20 | [17 empty] | 0 | [19 empty] | TRUE | FALSE |  | 0 | 0 | 1900 | 1900 | 1900
750 |  | Govinda Neupane |  | 2022-10-12 | 2023-03-09 | wthdw |  | 2023-09-08 | L2_Bump |  | 2023-10-03 | L2_bump |  | 2023-10-27 | wthdw | [20 empty] | 7 - CARM |  | 808D3 | 590 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Katie Kearney | SOLAMERICA ENERGY LLC | Penobscot County ME S2, LLC. | 235 South Monmouth Rd | 2000209571 | 30015545582 | Solar | [5 empty] | 44.845 | -69.0253 | Irish Road |  | Irish Road | Levant | 63 | CARMEL | 808D3 | Carmel Substation Section 35 Tap | 12.47 | 9310-L0506-3220-0017-ED00003 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2022-10-19 | 2022-10-26 | 2022-10-13 | 2022-10-19 | 2023-01-06 | 2022-01-09 | 2023-01-20 | 2022-01-09 | 2023-01-12 | 2023-01-12 | 2023-01-27 |  |  | 2023-01-23 |  |  | CS | [7 empty] | CS |  |  | 2023-01-24 |  |  | 2023-11-01 | [8 empty] | 2/2/203 | [8 empty] | 2023-02-06 | [8 empty] | 2023-02-07 |  |  | 2023-12-01 | [8 empty] | 2023-04-12 | [6 empty] | 2023-04-11 |  |  | 2024-02-06 | [5 empty] | 2023-04-11 |  |  | 2024-02-06 | [5 empty] | N/A |  |  | 2024-02-06 | [5 empty] | N/A |  |  | 2024-02-16 | [7 empty] | 2024-02-16 |  |  |  |  | 2024-03-11 |  | 2024-03-11 |  | 2024-04-08 | [6 empty] | 575567 | 2023-04-07 | 1199595 | 2024-02-06 | 2024-11-27 | 2021-07-13: 2024-04-11; 2021-07-13: 2024-04-11 | [9 empty] | 0 | [7 empty] | Requested | [11 empty] | TRUE | FALSE |  | 2024-04-11 | 2024-04-11 | 2024 | 2024 | 2024
751 |  | Govinda Neupane |  | 2022-10-17 |  |  |  | 2023-12-15 | wthdw |  | 2024-02-02 | wthdw | [22 empty] | 700 | 11 - WSTN |  | 866D2 | 700 | Yes | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Paula J Fitzgerald | Novel Energy Solutions LLC | ME Skowhegan Dostie 1 CSG LLC | Dostie 1 Back Rd Skowhegan | 2000311940 | 30014413261 | Solar | [5 empty] | 44.7197 | -69.7007 | Back Rd |  | Back Rd | Skowhegan | 9 | WESTON HYDRO | 866D2 | 866T2 | 12.47 | 9310-L0451-5330-0190-ED00072 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2022-10-24 | 2022-10-31 | 2022-10-19 | 2022-10-24 | 2023-11-14 | 2024-02-06 | 2023-11-30 | 2024-02-06 | 2024-02-09 | 2024-02-09 | 2024-02-26 |  |  | 2024-02-13 |  |  | CS | [7 empty] | CS |  |  | 2024-02-15 | [11 empty] | 2024-03-13 | [8 empty] | 2024-03-11 | [8 empty] | 2024-04-04 | [11 empty] | 2024-06-10 | [6 empty] | 2024-06-05 | [8 empty] | 2024-06-05 | [8 empty] | 2024-06-06 | [8 empty] | 2024-06-17 | [7 empty] | 2024-06-17 | [7 empty] | 2024-07-10 |  | 2024-07-11 |  | 2024-08-08 | [6 empty] | 469765 | 2024-06-04 |  |  | 2026-03-31 | 2021-07-13: 2024-08-12; 2021-07-13: 2024-08-12 | [9 empty] | 0 |  |  |  | Q2 2025 | [15 empty] | TRUE | FALSE |  | 2024-08-12 | 2024-08-12 | 2024 | 2024 | 2024
752 |  | Eben Snow | Brent Brooks | 2022-10-19 | [6 empty] | 2023-01-18 | L2_With |  | 2023-07-10 | L2_Bump | [20 empty] | 10 - DEER |  | 412D2 | 701 |  | WITHDRAWN | WITHDRAWN |  | Michael McNeley | Bloom Energy Corporation | Lewiston Community Energy I, LLC | 798 Main St | 2000324594 | 30014579285 | Fuel Cell | [5 empty] | 44.1286 | -70.1997 | 798 Main St | 798 | Main St | Lewiston | 125.1 | DEER RIPS | 412D2 | 412T2 | 12.47 | 9310-L0126-3230-0243-ED00197 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2022-10-26 | 2022-11-02 | 2022-10-25 | 2022-10-31 | [130 empty] | 2023-08-24 | [17 empty] | 0 | [19 empty] | TRUE | FALSE |  | 0 | 0 | 1900 | 1900 | 1900
753 |  | Marshall Ripley | Rick Duperre | 2022-10-19 | [31 empty] | 3 - PLHL |  | 644D4 | 582 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Michael McNeley | Bloom Energy Corporation | Scarborough Community Energy I, LLC | 33 Pleasant Hill Rd | 2000324596 | 30014579509 | Fuel Cell | [5 empty] | 43.6094 | -70.3103 | 33 Pleasant Hill Rd | 33 | Pleasant Hill Rd | Scarborough | 9 | PLEASANT HILL | 644D4 | 644T3 | 12.47 | 9310-L0288-5200-0125-ED00223 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2022-10-26 | 2022-11-02 | 2022-10-25 | 2022-10-31 | 2022-10-31 | 2022-11-02 | 2022-11-15 | 2022-11-04 | 2022-11-09 | 2022-11-09 | 2022-11-28 |  |  | 2022-11-28 |  |  | CS | [7 empty] | CS |  |  | 2022-12-12 | [11 empty] | 2022-11-29 | [8 empty] | 2022-11-10 | [8 empty] | 2022-12-23 | [11 empty] | 2023-03-02 | [6 empty] | 2023-02-27 | [8 empty] | 2023-02-27 | [8 empty] | 2023-02-28 | [8 empty] | 2023-03-03 | [7 empty] | 2023-03-03 | [7 empty] | 2023-03-23 |  | 2023-03-24 |  | 2023-04-21 | [6 empty] | 110827 | 2023-01-27 |  |  | 2023-08-24 | 2021-07-13: 2023-04-26; 2021-07-13: 2023-04-26 | [9 empty] | 0 | [19 empty] | TRUE | FALSE |  | 2023-04-26 | 2023-04-26 | 2023 | 2023 | 2023
754 |  | Rigel Paradise | Rick Duperre | 2022-10-19 | 2023-06-06 | L2_Bump | [29 empty] | 5 - BDIP |  | 673D1 | 533 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Michael McNeley | Bloom Energy Corporation | Biddeford Community Energy I, LLC | 631 Elm St | 2000324590 | 30014579251 | Fuel Cell | [5 empty] | 43.4632 | -70.4891 | 631 Elm Street | 631 | Elm Steet | Biddeford | 140.2 | BIDDEFORD INDUSTRIAL PARK | 673D1 | 673T2 | 12.47 | 9310-L0343-0490-0086-ED00114 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2022-10-26 | 2022-11-02 | 2022-10-25 | 2022-10-31 | 2022-10-31 | 2022-11-02 | 2022-11-15 | 2022-11-04 | 2022-11-09 | 2022-11-09 | 2022-11-28 |  |  | 2022-11-28 |  |  | CS | [7 empty] | CS |  |  | 2022-12-12 | [11 empty] | 2022-11-29 | [8 empty] | 2022-11-10 | [8 empty] | 2022-12-23 | [11 empty] | 2023-03-02 | [6 empty] | 2023-02-27 | [8 empty] | 2023-02-27 | [8 empty] | 2023-02-28 | [8 empty] | 2023-03-02 | [7 empty] | 2023-03-02 | [7 empty] | 2023-03-30 |  | 2023-03-30 |  | 2023-04-27 | [6 empty] | 345827 | 2023-02-27 |  |  | 2023-08-24 | 2021-07-13: 2023-04-28; 2021-07-13: 2023-04-28 | [9 empty] | 0 | [19 empty] | TRUE | FALSE |  | 2023-04-28 | 2023-04-28 | 2023 | 2023 | 2023
755 |  | Rigel Paradise | Rick Duperre | 2022-10-19 | 2023-03-28 | Wthdw |  | 2023-04-18 | L2_Bump | [26 empty] | 4 - SASW |  | 657D4 | 633 |  | WITHDRAWN | WITHDRAWN |  | Michael McNeley | Bloom Energy Corporation | Sanford Community Energy I, LLC | 639 Main St | 2000324569 | 30014579236 | Fuel Cell | [5 empty] | 43.4543 | -70.7893 | 639 Main St | 639 | Main Street | Sanford | 108 | SANFORD SWITCH | 657D4 | 657T1 | 12.47 | 9310-L0321-5170-0220-ED00316 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2022-10-26 | 2022-11-02 | 2022-10-25 | 2022-10-31 | 2022-10-31 | 2022-11-02 | 2022-11-15 | 2022-11-04 | 2022-11-10 | 2022-11-10 | 2022-11-29 |  |  | 2022-11-28 |  |  | CS | [7 empty] | CS |  |  | 2022-12-12 | [11 empty] | 2022-11-29 | [8 empty] | 2022-11-10 | [8 empty] | 2022-12-23 | [11 empty] | 2023-03-02 | [6 empty] | 2023-02-27 | [8 empty] | 2023-02-27 | [8 empty] | 2023-02-28 | [8 empty] | 2023-03-02 | [7 empty] | 2023-03-02 | [7 empty] | 2023-03-30 |  | 2023-03-31 | [12 empty] | 2023-08-24 | [17 empty] | 0 | [19 empty] | TRUE | FALSE |  | 0 | 0 | 1900 | 1900 | 1900
756 |  | Lanie Patterson | Brent Brooks | 2022-10-19 | [31 empty] | 4 - CAST |  | 215D3 | 756 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Michael McNeley | Bloom Energy Corporation | Augusta Community Energy I, LLC | 65 Western Ave | 2000324564 | 30014578949 | Fuel Cell | [5 empty] | 43.312 | -69.7875 | 65 Western Ave | 65 | Western Avenue | Augusta | 17 | CAPITOL STREET | 215D3 | 215T2 | 12.47 | 9310-L0039-0240-0383-ED00258 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2022-10-26 | 2022-11-02 | 2022-10-25 | 2022-10-31 | 2022-10-31 | 2022-11-02 | 2022-11-15 | 2022-11-04 | 2022-11-10 | 2022-11-10 | 2022-11-29 |  |  | 2022-11-28 |  |  | CS | 2022-11-28 | [6 empty] | CS |  |  | 2022-12-12 | [11 empty] | 2022-11-29 | [8 empty] | 2022-11-10 | [8 empty] | 2022-12-23 | [11 empty] | 2023-03-02 | [6 empty] | 2023-02-15 | [8 empty] | 2023-02-15 | [8 empty] | 2023-02-16 | [8 empty] | 2023-02-22 | [7 empty] | 2023-02-22 | [7 empty] | 2023-03-15 |  | 2023-03-16 |  | 2023-04-13 | [6 empty] | 229152 | 2023-02-15 |  |  | 2023-08-24 | 2021-07-13: 2023-04-17; 2021-07-13: 2023-04-18 | [9 empty] | -1 | [7 empty] | Requested | [11 empty] | TRUE | FALSE |  | 2023-04-17 | 2023-04-17 | 2023 | 2023 | 2023
757 |  | Lanie Patterson | Brent Brooks | 2022-12-12 | [9 empty] | 2024-08-12 | wthdw | [19 empty] | 718 | 14 - MONM |  | 457D2 | 718 | Yes | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Geoff Sparrow | GREEN LANTERN DEVELOPMENT LLC | Monmouth GLS-ME Solar, LLC | FISH HATCHERY RD | 2000259695 | 30015649376 | Solar | [5 empty] | 44.1998 | -69.9958 | 47 Fish Hatchery Road | 47 | Fish Hatchery Road | Monmouth | 9 | MONMOUTH | 457D2 | 457T2 | 12.47 | 9310-L0199-3740-0030-ED00020 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2022-12-19 | 2022-12-27 | 2022-12-16 | 2022-12-23 | 2023-08-22 | 2023-09-01 | 2023-09-06 | 2023-09-07 | 2023-09-12 | 2023-09-12 | 2023-09-26 |  |  | 2023-09-26 |  |  | CS | [7 empty] | CS |  |  | 2023-09-26 | [11 empty] | 2023-09-28 | [8 empty] | 2023-11-17 | [8 empty] | 2023-10-18 | [11 empty] | 2023-12-26 | [6 empty] | 2023-12-27 | [8 empty] | 2023-12-27 | [8 empty] | 2024-01-02 | [8 empty] | 2024-01-09 | [7 empty] | 2024-01-09 | [7 empty] | 2024-01-09 |  | 2024-01-10 |  | 2024-02-12 | [6 empty] | 367746 | 2023-12-27 |  |  | 2025-04-15 | 2021-07-13: 2024-02-12; 2021-07-13: 2024-02-13 | [9 empty] | -1 |  |  |  | Q3 2025 |  |  |  | Requested | [11 empty] | TRUE | FALSE |  | 2024-02-12 | 2024-02-12 | 2024 | 2024 | 2024
758 |  | Rigel Paradise | Rick Duperre | 2022-11-04 | 2022-12-09 | wthdw |  | 2023-02-28 | L2_Bump |  | 2023-04-05 | L2_Bump | [21 empty] | 1 - SAIP |  | 5 - SAIP |  | 656D2 | 550 | Yes | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED |  | Santiago Quijano | Bluewave MA, LLC | BWC BAUNEG BEG POND LLC | SAM ALLEN RD SANFORD | 2000204736 | 30012952955 | Solar | 990 | 0.99 | 1228.5 |  |  | 43.3751 | -70.6937 | Sam Allen Road |  | Sam Allen Road | Sanford | 3.3 | SANFORD INDUSTRIAL PARK | 656D2 | 656T1 | 12.47 | 9310-L0317-5170-0357-ED00006 |  | COST SHARE | COST SHARE (250,000) | 22527 | Yes | [6 empty] | 2022-11-14 | 2022-11-21 | 2022-11-08 | 2022-11-16 | 2022-01-09 | 2022-01-09 | 2022-01-24 | 2022-01-09 | 2023-01-13 | 2023-01-13 | 2023-01-30 |  |  | 2023-01-13 |  |  | cs | [7 empty] | CS |  |  | 2023-01-19 | [11 empty] | 2023-01-23 | [8 empty] | 2023-02-09 | [8 empty] | 2023-04-12 | [11 empty] | 2023-06-14 | [6 empty] | 2023-06-16 | [8 empty] | 2023-06-16 | [8 empty] | 2023-06-27 | [8 empty] | 2023-06-27 | [7 empty] | 2023-06-27 | [7 empty] | 2023-06-27 |  | 2023-07-24 | 2023-09-01 | 2023-08-01 | 2023-09-05 | [5 empty] | 268611 | 2023-06-27 |  |  |  | 2021-07-13: 2023-08-02; 2021-07-13: 2023-08-04; 2021-07-13: 2023-09-05; 2021-07-13: 2023-09-05 | [9 empty] | -2 |  |  |  | Q4 2025 |  |  |  | REQUESTED | [11 empty] | FALSE | FALSE |  | 2023-08-02 | 2023-08-02 | 2023 | 2023 | 2023
759 |  |  |  | 2022-11-04 | [31 empty] | 1 - LAST |  | 631D1 |  |  | WITHDRAWN | WITHDRAWN |  | Peter Whitney | BOLD COAST ENERGY, LLC | 66 MILLIKEN STREET FUEL CELL LLC |  | 2000329261 | 30014644246 | Fuel Cell | [5 empty] | 43.7049 | -70.3052 | 66 Milliken ST | 66 | Milliken ST | Portland | 4 | LAMBERT STREET | 631D1 | 631T1 | 12.47 | 9310-L0260-4730-0289-ED00007 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2022-11-14 | 2022-11-21 | 2022-11-08 | 2022-11-16 | 2022-11-16 | 2022-11-16 | 2022-12-05 | 2022-11-18 | 2022-11-21 | 2022-11-21 | 2022-12-07 |  |  | 2022-11-22 |  |  | CS | [10 empty] | 2022-12-12 | [11 empty] | 2022-11-30 | [8 empty] | 2022-12-14 | [8 empty] | 2022-12-14 | [11 empty] | 2023-02-21 | [6 empty] | 2023-02-21 | [8 empty] | 2023-02-04 | [8 empty] | 2023-03-02 | [8 empty] | 2023-03-09 | [7 empty] | 2023-03-09 | [22 empty] | 2023-03-23 | [17 empty] | 0 | [19 empty] | TRUE | FALSE |  | 0 | 0 | 1900 | 1900 | 1900
760 |  | Marshall Ripley | Rick Duperre | 2022-11-07 | 2023-02-15 | L2_Bump | [29 empty] | 2 - MURD |  | 636D2 | 15 |  | WITHDRAWN | WITHDRAWN |  | Peter Whitney | BOLD COAST ENERGY, LLC | MAINE DG ENERGY LLC | 2 Cummings Rd | 2000330578 | 30014661836 | Fuel Cell | [5 empty] | 43.6265 | -70.3477 | 2 Cummings RD | 2 | Cummings RD | Scarborough | 100.1 | MUSSEY ROAD | 636D2 | 636T1 | 34.5 | 9310-L0273-5200-0149-ED00002 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2022-11-15 | 2022-11-22 | 2022-11-08 | 2022-11-16 | 2022-11-16 | 2022-11-16 | 2022-12-05 | 2022-11-18 | 2022-11-21 | 2022-11-21 | 2022-12-07 |  |  | 2022-12-05 |  |  | CS | [10 empty] | 2022-12-12 | [11 empty] | 2022-12-07 | [8 empty] | 2022-12-14 | [8 empty] | 2022-12-14 | [11 empty] | 2022-02-21 | [64 empty] | 2023-03-23 | [17 empty] | 0 | [19 empty] | TRUE | FALSE |  | 0 | 0 | 1900 | 1900 | 1900
761 |  | Lanie Patterson | Brent Brooks | 2022-11-07 | [31 empty] | 5 - FAIR |  | 817D2 | 724 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Michael McNeley | Bloom Energy Corporation | Fairfield Community Energy I, LLC | 89 Main St Fairfield | 2000325170 | 30014588740 | Fuel Cell | [5 empty] | 44.5833 | -69.5997 | 89 Main St | 89 | Main St | Fairfield | 131.1 | FAIRFIELD | 817D2 | 817T2 | 12.47 | 9310-L0400-2000-0077-ED00046 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2022-11-15 | 2022-11-22 | 2022-11-09 | 2022-11-16 | 2022-11-16 | 2022-11-16 | 2022-12-05 | 2022-10-18 | 2022-11-18 | 2022-11-18 | 2022-12-06 |  |  | 2022-12-06 |  |  | CS | [10 empty] | 2022-12-16 | [20 empty] | 2023-01-31 | [8 empty] | 2023-01-31 | [11 empty] | 2023-04-04 | [6 empty] | 2023-04-04 | [8 empty] | 2023-04-06 | [8 empty] | 2023-04-12 | [8 empty] | 2023-04-12 | [7 empty] | 2023-04-12 | [7 empty] | 2023-05-04 |  | 2023-05-05 |  | 2023-06-02 | [6 empty] | 139016 | 2023-04-03 |  |  | 2023-08-24 | 2021-07-13: 2023-06-06; 2021-07-13: 2023-06-06 | [9 empty] | 0 | [19 empty] | TRUE | FALSE |  | 2023-06-06 | 2023-06-06 | 2023 | 2023 | 2023
762 |  |  | Anthony Boucher | 2022-11-07 | [31 empty] | 8 - BUCK |  | 806D1 | 702 |  | WITHDRAWN | WITHDRAWN |  | Michael McNeley | Bloom Energy Corporation | Bucksport Community Energy I, LLC | 120 US RT 1 BUCKSPORT | 2000325321 | 30014590902 | Fuel Cell | [5 empty] | 44.5703 | -68.7786 | 120 US Rt 1 | 120 | US Rt 1 | Bucksport | 60 | BUCKSPORT | 806D1 | 806T5 | 12.47 | 9310-L0400-2000-0077-ED00046 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2022-11-15 | 2022-11-22 | 2022-11-09 | 2022-11-16 | [130 empty] | 2023-08-24 | [17 empty] | 0 | [19 empty] | TRUE | FALSE |  | 0 | 0 | 1900 | 1900 | 1900
763 |  | Lanie Patterson | Brent Brooks | 2022-11-17 | [31 empty] | 3 - WSST |  | 255D2 | 467 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Ryan Coughlin | SHANACHIE PARTNERS LLC | PERENNIAL RENEWABLES | 424 Lewiston Rd West Gardiner | 2000142784 | 30014859299 | Solar | [5 empty] | 44.2051 | -69.8411 | 424 Lewiston Road | 424 | Lewiston Road | West Gardiner | 107 | WEST STREET | 255D2 | 255T1 | 12.47 | 9310-L0094-6300-0055-ED00019 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2022-11-28 | 2022-12-05 | 2022-11-28 | 2022-12-05 | 2022-01-10 | 2022-01-16 | 2023-01-25 | 2022-01-17 | 2023-01-19 | 2023-01-19 | 2023-02-02 |  |  | 2023-02-14 |  |  | CS | [7 empty] | CS |  |  | 2023-02-14 | [11 empty] | 2023-03-28 | [8 empty] | 2023-04-25 | [8 empty] | 2023-04-25 | [11 empty] | 2023-06-29 | [6 empty] | 2023-06-28 | [8 empty] | 2023-06-28 | [8 empty] | 2023-07-07 | [8 empty] | 2023-07-11 | [7 empty] | 2023-07-12 | [7 empty] | 2023-07-27 |  | 2023-07-27 |  | 2023-08-23 | [6 empty] | 316843 | 2023-06-28 |  |  | 2024-02-02 | 2021-07-13: 2023-08-24; 2021-07-13: 2023-08-24 | [9 empty] | 0 | [7 empty] | REQUESTED | [11 empty] | TRUE | FALSE |  | 2023-08-24 | 2023-08-24 | 2023 | 2023 | 2023
764 |  | Rigel Paradise | Rick Duperre | 2022-11-18 | 2023-07-05 | L2_Bump |  | 2023-10-26 | wthdw | [26 empty] | 7 - BDPP |  | 605D2 | 717 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Robert Fogio | Nexamp, Inc | NEXAMP SOLAR LLC | 9 BUZZELL RD, #2 / BIDDEFORD | 2000114877 | 30014661943 | Solar | [5 empty] | 43.5067 | -70.5321 | 9 Buzzell Road | 9 | Buzzell Rd | Biddeford | 4 | BIDDEFORD PUMP | 605D2 | 605T1 | 12.47 | 9310-L0215-0490-0035-ED00014 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2022-11-29 | 2022-12-06 | 2022-11-28 | 2022-12-06 | 2023-06-05 | 2023-06-09 | 2023-06-20 | 2023-06-13 | 2023-06-15 | 2023-06-19 | 2023-06-30 |  |  | 2023-06-27 |  |  | CS | [7 empty] | CS |  |  | 2023-08-16 |  |  | 2023-10-23 | [8 empty] | 2023-09-05 |  |  | 2023-11-17 | [8 empty] | 2023-11-17 | [5 empty] | 2023-11-15 |  |  | 2023-11-15 | [15 empty] | 2024-01-25 |  |  | 2024-01-25 | [8 empty] | 2024-01-25 | [8 empty] | 2024-01-29 | [8 empty] | 2024-02-07 | [7 empty] | 2024-02-07 |  |  |  |  | 2024-02-29 |  | 2024-03-06 |  | 2024-04-05 | [6 empty] | 584126 | 2024-03-06 |  |  | 2024-11-25 | 2021-07-13: 2024-04-09; 2021-07-13: 2024-04-09 | [9 empty] | 0 | [7 empty] | Requested | [11 empty] | TRUE | FALSE |  | 2024-04-09 | 2024-04-09 | 2024 | 2024 | 2024
765 |  | Ben Brooks | Anthony Boucher | 2022-11-21 | [31 empty] | 3 - B115 | 1 - B115 | 874D1 | 367 | Yes | EXECUTED | EXECUTED |  | Paula J Fitzgerald | Novel Energy Solutions LLC | ME BELFAST KEENE 3 CSG LLC | 139 SHEPARD RD / BELFAST | 2000324635 | 30014579749 | Solar/Battery | 800 | 0.8 |  |  | 800 | 44.4426 | -69.0758 | 139 Shepard Rd | 139 | Shepard Rd | Belfast | 10 | BELFAST 115 | 874D1 | 874T2 | 12.47 | 9310-L0458-0430-0157-ED00059 |  |  |  |  | Yes | [6 empty] | 2022-11-30 | 2022-12-07 | 2022-11-29 | 2022-12-06 | 2022-12-06 | 2022-12-16 | 2022-12-20 | 2022-12-28 | 2022-12-29 | 2022-12-29 | 2022-01-13 |  |  | 2023-01-06 |  |  | CS | [7 empty] | CS |  |  | 2023-01-09 | [11 empty] | 2023-01-17 | [8 empty] | 2023-02-05 | [8 empty] | 2023-01-24 | [11 empty] | 2023-03-29 | [6 empty] | 2023-03-28 | [8 empty] | 2023-03-28 | [8 empty] | 2023-03-28 | [8 empty] | 2023-03-28 | [7 empty] | 2023-03-28 | [7 empty] | 2023-03-28 |  | 2023-03-29 |  | 2023-03-29 | [6 empty] | 110827 | 2023-03-28 |  |  |  | 2021-07-13: 2023-03-30; 2021-07-13: 2023-03-30 | [9 empty] | 0 |  |  |  | Q4 2025 |  |  |  | Requested | [11 empty] | TRUE | FALSE |  | 2023-03-30 | 2023-03-30 | 2023 | 2023 | 2023
766 |  |  |  | 2022-11-23 | [31 empty] | 6 - CONY |  | 216D1 |  |  | WITHDRAWN | WITHDRAWN |  | Compton Donohue | EAST POINT ENERGY, LLC | EAST POINT ENERGY |  | 2000329282 | 30014644378 | Battery | [5 empty] | 44.2819 | -69.7553 | 235 Hallowell Rd | 235 | Hallowell Rd | Chelsea |  | CONY ROAD | 216D1 | 216T1 |  |  |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2022-12-02 | 2022-12-09 | 2022-11-23 | 2022-11-23 | [126 empty] | n/a | n/a | n/a | n/a | 2022-11-23 | [17 empty] | 0 | [19 empty] | TRUE | FALSE |  | 0 | 0 | 1900 | 1900 | 1900
767 |  | Rigel Paradise | Rick Duperre | 2022-11-29 | 2023-01-09 | L2_Bump |  | 2023-02-15 | L2_Bump |  | 2023-03-13 | L2_Bump | [23 empty] | 2 - GOOS |  | 630D2 | 333 |  | WITHDRAWN | WITHDRAWN |  | Peter Whitney | BOLD COAST ENERGY, LLC | 74 INDUSTRIAL PARK RD FUEL CELL LLC | 74 INDUSTRIAL PARK RD / SACO | 2000330952 | 30014666546 | Fuel Cell | [5 empty] | 43.5318 | -70.4455 | 74 Industrial Park Road | 74 | Industrial Park Road | Saco | 31.1 | GOOSEFARE | 630D2 | 630T1 | 12.47 | 9310-L0258-5090-0126-ED00059 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2022-12-06 | 2022-12-13 | 2022-12-02 | 2022-12-08 | 2022-12-08 | 2022-12-21 | 2022-12-22 | 2022-12-22 | 2022-12-27 | 2022-12-27 | 2023-01-12 |  |  | 2023-01-20 |  |  | cs | [7 empty] | CS |  |  | 2023-01-20 | [20 empty] | 2023-02-01 | [8 empty] | 2023-02-03 | [11 empty] | 2023-04-10 | [6 empty] | 2023-04-10 | [53 empty] | n/a |  |  |  | 2023-03-23 | [17 empty] | 0 | [19 empty] | TRUE | FALSE |  | 0 | 0 | 1900 | 1900 | 1900
768 |  |  | Anthony Boucher | 2022-12-05 | 2023-01-09 | L2_Bump |  | 2023-01-10 | wthdw |  | 2023-02-22 | wthdw |  | 2024-11-26 | wthdw | [20 empty] | 7 - SEAR |  | 850D1 | 716 | Yes | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Chrissi Ramsey | SOLAMERICA ENERGY LLC | SOLAMERICA ENERGY LLC | 235 South Monmouth Rd | 2000209571 | 30014005828 | Solar | [5 empty] | 44.477 | -68.8919 | 32 Turnpike Road | 32 | Turnpike Road | Searsport | 7 | SEARSPORT | 850D1 | 850T1 | 12.47 | 9310-L0427-5220-0075-ED00019 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2022-12-12 | 2022-12-19 | 2022-12-08 | 2022-12-15 | 2022-12-15 | 2022-12-08 | 2022-12-26 | 2023-01-03 | 2023-01-05 | 2023-01-05 | 2023-01-20 | [5 empty] | CS | [7 empty] | CS |  |  | 2024-03-19 |  |  | 2024-11-26 |  |  |  |  | 2024-04-19 |  |  |  | 2024-04-03 |  |  | 2024-12-10 | [5 empty] | 2024-04-19 |  |  | 2024-12-10 | [5 empty] | 2024-04-19 |  |  | 2024-12-10 | [8 empty] | 2024-06-25 | [6 empty] | 2024-06-17 |  |  | 2025-02-14 | [5 empty] | 2024-06-17 |  |  | 2025-02-14 | [5 empty] | 2024-06-18 |  |  | 2025-02-18 | [5 empty] | 2024-06-25 |  |  | 2024-02-24 |  |  |  |  | 2024-06-25 |  |  | 2024-02-24 |  |  |  |  | 2024-07-16 |  | 2024-07-16 | 2025-03-14 | 2024-08-16 | 2025-04-07 | [5 empty] | 152939 | 2024-06-13 | 459399 | 2025-02-11 | 2026-07-13 | 2021-07-13: 2024-08-19; 2021-07-13: 2024-08-20; 2021-07-13: 2025-04-07; 2021-07-13: 2025-04-07 | [9 empty] | -1 |  |  |  | Q3 2026 | [15 empty] | FALSE | FALSE |  | 2024-08-19 | 2024-08-19 | 2024 | 2024 | 2024
769 |  | Lanie Patterson | Brent Brooks | 2022-12-20 |  |  |  | 2024-04-22 | wthdw |  |  |  |  | 2024-11-06 | wthdw |  | 2024-12-16 | wthdw | [17 empty] | 9 - NOAU |  | 272D4 | 598 | Yes | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Stephanie Loucas | RENEWABLE PROPERTIES LLC | RPME Solar 1, LLC | BOG RD, AUGUSTA | 2000445520 | 30016237031 | Solar | [5 empty] | 44.2755 | -69.7924 | Bog Road |  | Bog Road | Augusta | 11H | NORTH AUGUSTA | 272D4 | 272T1 | 12.47 | 9310-L0107-0240-0025-ED00057 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2022-12-28 | 2023-01-05 | 2022-12-23 | 2023-01-04 | 2023-02-21 | 2023-02-20 | 2023-03-07 | 2023-02-27 | 2023-03-02 | 2023-03-02 | 2023-03-16 |  |  | 2023-03-15 |  |  | CS | [7 empty] | CS |  |  | 2023-03-15 |  |  | 2024-04-25 | 2024-12-17 |  |  |  | 2024-05-09 |  |  |  | 2023-04-03 |  |  | 2024-05-10 | 2024-12-24 |  |  |  |  | 2023-05-09 |  |  | 2024-05-10 | 2024-12-27 |  |  |  |  | 2023-05-09 |  |  | 2024-05-10 | 2024-12-27 | [7 empty] | 2023-07-14 | [6 empty] | 2023-07-10 |  |  | 2024-07-12 | 2025-03-04 |  |  |  |  | 2023-07-12 |  |  | 2024-07-12 | 2025-03-04 |  |  |  |  | 2023-07-31 |  |  | 2024-07-23 | 2025-03-07 |  |  |  |  | 2023-08-03 |  |  | 2024-07-24 | 2025-03-20 |  |  |  | 2023-08-03 |  |  | 2024-07-24 | 2025-03-20 |  |  |  | 2023-08-08 |  | 2023-08-14 | 2024-08-15 | 2023-08-24 | [6 empty] | 370790 | 2023-08-10 | 770790 | 2025-02-28 | 2025-12-30 | 2023-09-26 | 2023-09-27 | 2024-09-27 | 2024-09-27 | 2025-05-09 | 2025-05-09 | [11 empty] | -1 |  |  |  | Q2 2025 | [15 empty] | TRUE | FALSE |  | 2023-09-26 | 2023-09-26 | 2023 | 2023 | 2023
770 |  | Govinda Neupane |  | 2022-12-29 | [31 empty] | 2 - BIGE |  |  | 770 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Nick Sampson | BNRG MAINE LLC | BD SOLAR CV LLC | Carrabasset Dr SOLAR | 2000336637 | 30014744947 | Solar/Battery | [5 empty] | 45.0902 | -70.3321 | Carrabassett Drive (Route 27/Route 16) |  | Carrabassett Drive (Route 27/Route 16) | Carrabassett Valley | 25H | BIGELOW | 882D2 | 882T1 | 34.5 | 9310-L0465-2940-0035-ED00266 |  | TRIGGERING | TRIGGERING (375,000) | 375000 | Yes | [6 empty] | 2023-01-06 | 2023-01-13 | 2023-01-04 | 2023-01-11 | 2023-01-11 | 2023-01-12 | 2023-01-26 | 2023-01-13 | 2023-01-19 | 2023-01-19 | 2023-02-02 |  |  | 2023-02-02 |  |  | CS | [7 empty] | CS |  |  | 2023-02-20 | [20 empty] | 2023-03-27 | [8 empty] | 2023-03-27 | [11 empty] | 2023-06-01 | [6 empty] | 2023-05-30 | [8 empty] | 2023-05-30 | [8 empty] | 2023-06-05 | [8 empty] | 2023-06-14 | [7 empty] | 2023-06-14 | [7 empty] | 2023-07-10 |  | 2023-08-14 |  | 2023-08-22 | [6 empty] | 630715 | 2023-05-30 |  |  | 2025-12-18 | 2021-07-13: 2023-08-24; 2021-07-13: 2023-08-24 | [9 empty] | 0 | [19 empty] | TRUE | FALSE |  | 2023-08-24 | 2023-08-24 | 2023 | 2023 | 2023
771 |  |  | KRISTOFER COLEMAN | 2023-01-04 | 2024-02-08 | L2_Bump | [29 empty] | 5 - BRIS |  | 210D1 | 730 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Travis Scott | EDPR NA Distributed Generation LLC | EDPRNA DG Bristol Solar, LLC | BRISTOL RD BRISTOL ME | 2000326789 | 30015565580 | Solar | [5 empty] | 43.9453 | -69.5188 | 0 Bristol Road | 0 | Bristol Road | Bristol | 1 | BRISTOL | 210D1 | 210T1 | 12.47 | 9310-L0027-0710-0118-ED00053 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2023-01-11 | 2023-01-19 | 2023-01-09 | 2023-01-11 | 2023-01-11 | 2023-01-12 | 2023-01-26 | 2023-01-12 | 2023-01-20 | 2023-01-20 | 2022-02-03 |  |  | 2023-01-20 |  |  | CS | [7 empty] | CS |  |  | 2023-02-01 | [11 empty] | 2023-02-07 | [8 empty] | 2023-02-13 | [8 empty] | 2023-02-13 | [11 empty] | 2023-04-19 | [6 empty] | 2023-04-17 | [8 empty] | 2023-04-17 | [8 empty] | 2023-04-18 | [8 empty] | 2023-04-21 | [7 empty] | 2023-04-21 | [7 empty] | 2023-04-21 |  | 2023-04-24 |  | 2023-04-24 | [6 empty] | 166199 | 2023-04-17 |  |  | 2024-05-15 | 2021-07-13: 2023-04-25; 2021-07-13: 2023-04-25 | [9 empty] | 0 | [7 empty] | Requested | [11 empty] | TRUE | FALSE |  | 2023-04-25 | 2023-04-25 | 2023 | 2023 | 2023
772 |  | Lanie Patterson | Brent Brooks | 2023-01-05 | [30 empty] | 761 | 6 - FAIR |  | 817D3 | 761 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Paula J Fitzgerald | Novel Energy Solutions LLC | ME Fairfield Kissinger CSG LLC | 0 CENTER RD FAIRFIELD | 2000336495 | 30014742461 | Solar | [5 empty] | 44.5919 | -69.642 | Sanderson Drive | 0 | Sanderson Drive | Fairfield | 4 | FAIRFIELD | 817D3 | 817T1 | 12.47 | 9310-L0401-2000-0128-ED00004 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2023-01-12 | 2023-01-20 | 2023-01-09 | 2023-01-12 | 2023-06-06 | 2023-06-06 | 2023-06-22 | 2023-06-07 | 2023-06-12 | 2023-06-12 | 2023-06-27 |  |  | 2023-06-15 |  |  | CS | [7 empty] | CS |  |  | 2023-06-16 | [29 empty] | 2023-10-30 | [11 empty] | 2024-01-08 | [6 empty] | 2024-01-08 | [8 empty] | 2024-01-08 | [8 empty] | 2024-01-17 | [8 empty] | 2024-01-22 | [7 empty] | 2024-01-22 | [7 empty] | 2024-01-24 |  | 2024-01-27 |  | 2024-01-29 | [6 empty] | 374693 | 2024-01-09 |  |  | 2025-07-15 | 2021-07-13: 2024-01-30; 2021-07-13: 2024-01-30 | [9 empty] | 0 |  |  |  | Q2 2026 |  |  |  | Requested | [11 empty] | TRUE | FALSE |  | 2024-01-30 | 2024-01-30 | 2024 | 2024 | 2024
773 |  | Rigel Paradise | Rick Duperre | 2023-01-09 | 2023-02-28 | L2_Bump | [29 empty] | 3 - MAST |  | 634D1 | 594 |  | WITHDRAWN | WITHDRAWN |  | Peter Whitney | BOLD COAST ENERGY, LLC | 17 POMERLEAU STREET FUEL CELL LLC | 17 POMERLEAU ST / BIDDEFORD ME 0400 | 2000338266 | 30014765629 | Fuel Cell | [5 empty] | 43.4825 | -70.4839 | 19 Pomerleau St | 19 | Pomerleau St | Biddeford | 5H | MAY STREET | 634D1 | 634T1 | 12.47 | 9310-L0266-0490-0247-ED00017 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2023-01-17 | 2023-01-24 | 2023-01-13 | 2023-01-18 | 2023-01-18 | 2023-01-19 | 2023-02-01 | 2023-01-19 | 2023-01-27 | 2023-01-27 | 2023-02-10 |  |  | 2022-01-28 |  |  | CS | [7 empty] | CS |  |  | 2023-01-31 | [11 empty] | 2023-02-03 | [8 empty] | 2023-02-13 | [8 empty] | 2023-02-13 | [11 empty] | 2023-04-19 | [6 empty] | 2023-04-19 | [53 empty] | n/a | n/a | n/a | n/a | 2023-03-23 | [17 empty] | 0 | [19 empty] | TRUE | FALSE |  | 0 | 0 | 1900 | 1900 | 1900
774 |  |  | KRISTOFER COLEMAN | 2023-01-11 | [31 empty] | 4 - BOOT |  | 209D3 | 722 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Rayomand Bhumgara | SUSTAINABLE STRATEGIES 2050 INC | SUSTAINABLE STRATEGIES 2050 INC | WISCASSET RD BOOTHBAY | 2000326789 | 30014768102 | Solar | [5 empty] | 43.9115 | -69.615 | 0 Wiscasset Road | 0 | Wiscasset Road | Boothbay | 134 | BOOTHBAY HARBOR | 209D3 | 209T1 | 12.47 | 9310-L0026-0550-0162-ED00079 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2023-01-19 | 2023-01-26 | 2023-01-18 | 2023-01-25 | 2023-01-25 | 2023-01-26 | 2023-02-08 | 2022-01-26 | 2023-02-01 | 2023-02-03 | 2023-02-15 |  |  | 2023-02-03 |  |  | CS | [7 empty] | CS |  |  | 2023-03-01 | [11 empty] | 2023-03-03 | [8 empty] | 2023-03-06 | [8 empty] | 2023-03-06 | [11 empty] | 2023-05-08 | [6 empty] | 2023-05-03 | [8 empty] | 2023-05-03 | [8 empty] | 2023-05-03 | [8 empty] | 2023-05-03 | [7 empty] | 2023-05-03 | [7 empty] | 2023-05-03 |  | 2023-05-03 |  | 2023-05-04 | [6 empty] | 110827 | 2023-05-02 |  |  | 2023-09-11 | 2021-07-13: 2023-05-04; 2021-07-13: 2023-05-04 | [9 empty] | 0 | [19 empty] | TRUE | FALSE |  | 2023-05-04 | 2023-05-04 | 2023 | 2023 | 2023
775 |  |  | KRISTOFER COLEMAN | 2023-01-12 | [31 empty] | 4 - BATH |  | 261D4 | 664 |  | WITHDRAWN | WITHDRAWN |  | Peter Whitney | BOLD COAST ENERGY, LLC | 10 STATE RD FUEL CELL LLC | 10 Bath Rd Bath | 2000339218 | 30014776832 | Fuel Cell | [5 empty] | 43.9061 | -69.8319 | 10 State RD | 10 | State RD | Bath | 32 | BATH 34 | 261D4 | 261T2 | 12.47 | 9310-L0100-0410-0110-ED00042 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2023-01-20 | 2023-01-27 | 2023-01-18 | 2023-01-25 | 2023-01-25 |  | 2023-02-08 | [127 empty] | 2023-03-23 | [17 empty] | 0 | [19 empty] | TRUE | FALSE |  | 0 | 0 | 1900 | 1900 | 1900
776 |  | Eben Snow | Brent Brooks | 2023-01-23 | [31 empty] | 2 - CH12 |  | 421D2 | 599 |  | WITHDRAWN | WITHDRAWN |  | Peter Whitney | BOLD COAST ENERGY, LLC | 74 Westminster Street Fuel Cell, LLC | 74 Westminster St | 2000340527 | 30014790775 | Fuel Cell | [5 empty] | 44.0791 | -70.1714 | 74 Westminster Street | 74 | Westminster Street | Lewiston | 1 | CHALLENGER 12 KV | 421D2 | 421T1 | 12.47 | 9310-L0145-3230-0524-ED00001 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2023-01-30 | 2023-02-06 | 2023-01-27 | 2023-02-03 | 2023-02-03 | 2023-02-07 | 2023-02-22 | 2023-02-07 | 2023-02-16 | 2023-02-16 | 2023-03-03 |  |  | 2023-02-17 |  |  | CS | [7 empty] | CS |  |  | 2023-02-17 | [106 empty] | 2023-03-23 | [17 empty] | 0 | [19 empty] | TRUE | FALSE |  | 0 | 0 | 1900 | 1900 | 1900
777 |  | Eben Snow | Brent Brooks | 2023-01-24 | 2023-06-06 | L2_Bump | [29 empty] | 9 - MEFA |  | 431D1 | 735 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Geoff Sparrow | GREEN LANTERN DEVELOPMENT LLC | GREEN LANTERN DEVELOPMENT LLC | 157 Lewiston st, Mechanic Falls | 2000259695 | 30014792573 | Solar | [5 empty] | 44.108 | -70.3759 | Lewiston St |  | Lewiston St | Mechanic Falls | 42 | MECHANIC FALLS | 431D1 | 431T2 | 12.47 | 9310-L0165-3610-0032-ED00046 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2023-01-31 | 2023-02-07 | 2023-01-27 | 2023-02-03 | 2023-02-03 | 2023-02-07 | 2023-02-22 | 2023-02-08 | 2023-02-17 | 2023-02-17 | 2023-03-06 |  |  | 2023-02-21 |  |  | CS | [7 empty] | CS |  |  | 2023-02-21 | [11 empty] | 2023-02-28 | [8 empty] | 2023-03-02 | [8 empty] | 2023-03-02 | [11 empty] | 2023-05-05 | [6 empty] | 2023-05-02 | [8 empty] | 2023-05-03 | [8 empty] | 2023-05-08 | [8 empty] | 2023-05-10 | [7 empty] | 2023-05-10 | [7 empty] | 2023-06-01 |  | 2023-06-01 |  | 2023-06-28 | [6 empty] | 215265 | 2023-05-02 |  |  | 2023-07-20 | 2021-07-13: 2023-06-29; 2021-07-13: 2023-06-29 | [9 empty] | 0 | [19 empty] | TRUE | FALSE |  | 2023-06-29 | 2023-06-29 | 2023 | 2023 | 2023
778 |  | Eben Snow | Brent Brooks | 2023-01-27 | 2023-05-04 | L2_Bump |  | 2024-10-23 | L2_with | [26 empty] | 6 - GRFA |  | 436D6 | 719 | Yes | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Santiago Quijano | Bluewave MA, LLC | Soper Mill Brook, LLC | 371 Penley Corner Rd Auburn | 2000310625 | 30015866095 | Solar | [5 empty] | 44.0446 | -70.2125 | 371 Penley Corner Rd | 371 | Penley Corner Rd | Auburn | 24 | GREAT FALLS | 436D6 | 436T1 | 12.47 | 9310-L0176-0230-0154-ED00043 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2023-02-03 | 2023-02-10 | 2023-02-01 | 2023-02-08 | 2023-02-08 | 2023-02-09 | 2023-02-23 | 2023-02-09 | 2023-02-17 | 2023-02-17 | 2023-03-06 |  |  | 2023-02-23 |  |  | CS |  | RS | 2024-02-05 |  |  |  |  | CS |  |  | 2023-02-27 |  |  | 2023-10-06 | 2025-04-11 |  |  |  | 2023-03-07 | 2024-03-05 |  |  |  | 2024-03-07 |  | 2023-10-25 | 2025-04-22 |  |  |  |  | 2023-03-08 | 2024-03-07 |  | 2023-11-01 | 2025-04-22 |  |  |  |  | 2023-03-08 | 2024-03-07 |  | 2023-11-07 | 2025-04-22 | [7 empty] | 2023-05-09 | 2024-04-19 | [5 empty] | 2023-05-09 | 2024-04-22 |  | 2024-01-03 | 2025-06-19 | [5 empty] | 2024-04-22 |  | 2024-01-04 | 2025-06-19 |  |  |  |  | 2024-04-23 |  |  | 2024-01-04 | 2025-06-25 | [5 empty] | 2024-04-26 |  | 2024-01-10 | 2025-06-30 |  |  |  |  | 2024-04-26 |  | 2024-01-10 | 2025-06-30 |  |  |  | 2024-04-26 |  | 2024-05-01 | 2025-07-25 | 2024-05-07 | [6 empty] | 710551 | 2024-01-04 | 851508 | 2025-06-18 | 2025-09-22 | 2021-07-13: 2024-05-08; 2021-07-13: 2024-05-13 | [9 empty] | -5 |  |  |  | Q4 2025 |  |  |  | Requested | [11 empty] | TRUE | FALSE |  | 2024-05-08 | 2024-05-08 | 2024 | 2024 | 2024
779 |  | Govinda Neupane |  | 2023-01-31 | 2023-05-22 | L2_Bump |  | 2024-03-05 | wthdw | [26 empty] | 6 - MONS |  | 834D1 | 572 |  | WITHDRAWN | WITHDRAWN |  | Rayomand Bhumgara | SUSTAINABLE STRATEGIES 2050 INC | SUSTAINABLE STRATEGIES 2050 INC | Chapin Ave Monson Me | 2000326789 | 30014788126 | Solar | [5 empty] | 45.2884 | -69.4974 | 0 Chapin Ave | 0 | Chapin Ave | Monson | 4 | MONSON | 834D1 | 834T1 | 12.47 | 9310-L0414-3760-0007-ED00008 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2023-02-07 | 2023-02-14 | 2023-02-03 | 2023-02-10 | 2023-03-29 | 2023-04-07 | 2023-04-12 | 2023-04-12 | 2023-04-14 | 2023-04-14 | 2023-05-01 |  |  | 2023-04-14 |  |  | CS | [7 empty] | CS |  |  | 2023-04-14 | [11 empty] | 2023-04-21 | [8 empty] | 2023-04-27 | [8 empty] | 2023-04-27 | [11 empty] | 2023-07-03 | [6 empty] | 2023-07-03 | [57 empty] | 2024-08-16 | [17 empty] | 0 | [19 empty] | TRUE | FALSE |  | 0 | 0 | 1900 | 1900 | 1900
780 |  | Ben Brooks | Anthony Boucher | 2023-02-02 |  |  |  | 2022-09-28 | L2_Bump |  | 2023-03-20 | L2_Bump | [23 empty] | 5 - PAST |  | 239D6 | 614 |  | WITHDRAWN | WITHDRAWN |  | Rayomand Bhumgara | SUSTAINABLE STRATEGIES 2050 INC | SUSTAINABLE STRATEGIES 2050 INC | 392 OLD COUNTY RD ROCKLAND | 2000326789 | 30014807827 | Solar | [5 empty] | 44.1186 | -69.1261 | 392 Old County Road | 392 | Old County Road | Rockland | 87H | PARK STREET | 239D6 | 239T2 | 12.47 | 9310-L0070-4970-0141-ED00143 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2023-02-09 | 2023-02-16 | 2023-02-08 | 2023-02-15 | 2023-08-03 | 2023-08-04 | 2023-08-17 | [127 empty] | 2023-08-24 | [17 empty] | 0 | [19 empty] | TRUE | FALSE |  | 0 | 0 | 1900 | 1900 | 1900
781 |  | Govinda Neupane |  | 2023-02-02 | 2023-05-22 | L2_Bump |  | 2023-11-14 | wthdw |  | 2024-05-10 | wthdw | L2_Bump | 2024-12-09 | L2_Bump |  | 2025-07-15 | wthdw | [16 empty] | 732 | 11 - LVFA | 2 - LVFA | 428D2 | 732 | Yes | EXECUTED | EXECUTED |  | Caili Orem | EDPRNA DG Energy Development, LLC | EDPRNA DG Livermore Solar, LLC | DIAMOND RD LIVERMORE FALLS | 2000471582 | 30016625763 | Solar | 950 | 0.95 | 1291.68 |  |  | 44.4421 | -70.1616 | 0 Diamond Road | 0 | Diamond Road | Livermore Falls | 9 | LIVERMORE FALLS | 428D2 | 428T1 | 12.47 | 9310-L0161-3350-0096-ED00030 |  | NOT IMPACTED | NOT IMPACTED |  | Yes | [6 empty] | 2023-02-09 | 2023-02-16 | 2023-02-08 | 2023-02-15 | 2023-04-20 | 2023-04-25 | 2023-05-04 | 2023-04-26 | 2023-04-27 | 2023-04-27 | 2023-05-11 |  |  | 2023-04-27 |  |  | CS | [7 empty] | CS |  |  | 2023-04-27 |  |  | 2024-09-05 | 2024-12-09 | 2025-11-21 | [6 empty] | 2023-05-05 |  |  | N/A | 2024-12-16 | 2025-12-01 |  |  |  | 2023-05-05 |  |  |  | 2024-12-16 | 2025-12-01 |  |  |  | 2023-05-05 |  |  | 2024-09-16 | 2024-12-16 | 2025-12-01 | [6 empty] | 2023-07-12 | [6 empty] | N/A |  |  | 2024-11-15 | 2025-02-19 | 2025-02-04 | [6 empty] | 2024-11-15 | 2025-02-19 | 2025-02-04 | [6 empty] | 2024-11-20 | 2024-02-26 | 2025-02-18 | [6 empty] | 2024-12-02 | 2026-02-20 | [6 empty] | 2024-12-02 | 2026-02-20 |  |  |  | 2024-12-02 |  | 2024-12-03 | 2026-02-20 | 2024-12-03 | 2025-03-06 | [5 empty] | 192977 | 2024-11-15 | 354536 | 2026-02-04 |  | 2024-12-03 | 2024-12-03 | 2025-03-10 | 2025-03-10 | 2026-02-26 | 2026-02-26 | [11 empty] | 0 |  |  |  | Q3 2024 | [15 empty] | FALSE | FALSE |  | 2024-12-03 | 2024-12-03 | 2024 | 2024 | 2024
782 |  | Govinda Neupane |  | 2023-02-07 | 2023-06-05 | L2_Bump | [29 empty] | 5 - RUIP |  | 466D1 | 705 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Rayomand Bhumgara | SUSTAINABLE STRATEGIES 2050 INC | SUSTAINABLE STRATEGIES 2050 INC | 711 AUBURN RD PERU | 2000326789 | 30014807819 | Solar | [5 empty] | 44.5055 | -70.4041 | 711 Auburn Road | 711 | Auburn Road | Peru | 143 | RUMFORD INDUSTRIAL PARK | 466D1 | 466T1 | 34.5 | 9310-L0205-4610-0005-ED00060 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2023-02-14 | 2023-02-22 | 2023-02-13 | 2023-02-17 | 2023-02-17 | 2022-02-20 | 2023-03-06 | 2022-02-20 | 2023-03-03 | 2023-03-06 | 2023-03-17 |  |  | 2023-03-06 |  |  | CS | [7 empty] | CS |  |  | 2023-03-06 | [11 empty] | 2023-03-09 | [8 empty] | 2023-03-24 | [8 empty] | 2023-03-24 | [11 empty] | 2023-05-31 | [6 empty] | 2023-05-26 | [8 empty] | 2023-05-26 | [8 empty] | 2023-06-19 | [8 empty] | 2023-06-19 | [15 empty] | 2023-06-19 |  | 2023-06-19 |  | 2023-07-17 | [6 empty] | 167215 | 2023-05-25 |  |  | 2023-10-23 | 2021-07-13: 2023-07-18; 2021-07-13: 2023-07-19 | [9 empty] | -1 | [19 empty] | TRUE | FALSE |  | 2023-07-18 | 2023-07-18 | 2023 | 2023 | 2023
783 |  | Rigel Paradise | Rick Duperre | 2023-02-09 | 2023-02-28 | L2_Bump | [29 empty] | 4 - MAST |  | 634D3 | 773 |  | WITHDRAWN | WITHDRAWN |  | Peter Whitney | MAINE COMMUNITY ENERGY, LLC | 4 SPRUCE STREET FUEL CELL LLC | 4 SPRUCE ST BIDDEFORD | 2000343387 | 30014825233 | Fuel Cell | [5 empty] | 43.4961 | -70.4587 | 4 Spruce St | 4 | Spruce St | Biddeford | 3 | MAY STREET | 634D3 | 634T2 | 12.47 | 9310-L0268-0490-0273-ED00003 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2023-02-16 | 2023-02-24 | 2023-02-15 | 2023-02-22 | [126 empty] | n/a |  |  |  | 2023-03-23 | [17 empty] | 0 | [19 empty] | TRUE | FALSE |  | 0 | 0 | 1900 | 1900 | 1900
784 |  |  |  | 2023-02-10 | [31 empty] | 1 - L115 |  | 424D5 |  |  | WITHDRAWN | WITHDRAWN |  | Peter Whitney | MAINE COMMUNITY ENERGY, LLC | 85 EAST AVE FUEL CELL LLC | 85 EAST AVE LEWISTON | 2000343388 | 30014825241 | Fuel Cell | [5 empty] | 44.09 | -70.1994 | 85 East Ave | 85 | East Ave | Lewiston | 16 | LEWISTON LOWER 115 | 424D5 | 424T3 | 12.47 | 9310-L0151-3230-0106-ED00105 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2023-02-17 | 2023-02-27 | 2023-02-15 | 2023-02-24 | 2023-02-24 | 2023-02-27 | 2023-03-10 | [127 empty] | 2023-03-23 | [17 empty] | 0 | [19 empty] | TRUE | FALSE |  | 0 | 0 | 1900 | 1900 | 1900
785 |  |  |  | 2023-02-10 | [31 empty] | 1 - BOLT |  | 685D2 |  |  | WITHDRAWN | WITHDRAWN |  | Peter Whitney | MAINE COMMUNITY ENERGY, LLC | 70 ROUTE 236 FUEL CELL LLC | 70 ROUTE 236 KITTERY | 2000343445 | 30014825266 | Fuel Cell | [5 empty] | 43.1167 |  | 70 Route 236 | 70 | Route 236 | Kittery | 11 | BOLT HILL | 685D2 | 685T1 | 12.47 | 9310-L0363-3100-0147-ED00003 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2023-02-17 | 2023-02-27 | 2023-02-15 | 2023-02-24 | 2023-02-24 | 2023-02-27 | 2023-03-10 | 2023-02-27 | 2023-03-10 | 2023-03-10 | 2023-03-24 |  |  | 2023-03-16 |  |  | CS | [7 empty] | CS |  |  | 2023-03-17 | [106 empty] | 2023-03-23 | [17 empty] | 0 | [19 empty] | TRUE | FALSE |  | 0 | 0 | 1900 | 1900 | 1900
786 |  | Eben Snow | Brent Brooks | 2023-02-10 | [31 empty] | 5 - SABA |  | 450D2 | 691 |  | WITHDRAWN | WITHDRAWN |  | Peter Whitney | MAINE COMMUNITY ENERGY, LLC | MAINE COMMUNITY ENERGY LLC | 1022 SABATTUS ST LEWISTON | 2000343440 | 30014825258 | Fuel Cell | [5 empty] | 44.1014 |  | 1022 Sabattus Street | 1022 | Sabattus Street | Lewiston | 127 | SABATTUS | 450D2 | 450T1 | 12.47 | 9310-L0193-3230-0352-ED00065 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2023-02-17 | 2023-02-27 | 2023-02-15 | 2023-02-24 | 2023-02-24 | 2023-02-27 | 2023-03-10 | 2023-02-27 | 2023-02-28 | 2023-02-28 | 2023-03-14 |  |  | 2023-02-28 |  |  | CS | [7 empty] | CS |  |  | 2023-03-10 | [106 empty] | 2023-03-23 | [17 empty] | 0 | [19 empty] | TRUE | FALSE |  | 0 | 0 | 1900 | 1900 | 1900
787 |  | Eben Snow | Brent Brooks | 2023-02-10 | [31 empty] | 3 - CH12 |  | 421D2 | 776 |  | WITHDRAWN | WITHDRAWN |  | Peter Whitney | MAINE COMMUNITY ENERGY, LLC | 74 ALFRED PLOURDE PKWY FUEL CELL LLC | 74 ALFRED PLOURDE PKWY LEWISTON | 2000330951 | 30014666520 | Fuel Cell | [5 empty] | 44.0066 | -70.185 | 74 Alfred Plourde Parkway | 74 | Alfred Plourde Parkway | Lewiston | 1 | CHALLENGER 12 KV | 421D2 | 421T1 | 12.47 | 9310-L0145-3230-0074-ED00007 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2023-02-17 | 2023-02-27 | 2023-02-15 | 2023-02-24 | [130 empty] | 2023-03-23 | [17 empty] | 0 | [19 empty] | TRUE | FALSE |  | 0 | 0 | 1900 | 1900 | 1900
788 |  |  | KRISTOFER COLEMAN | 2023-02-22 | [31 empty] | 5 - BATH |  | 261D3 | 775 |  | WITHDRAWN | WITHDRAWN |  | Rayomand Bhumgara | SUSTAINABLE STRATEGIES 2050 INC | SUSTAINABLE STRATEGIES 2050 INC | ARTHUR J RENO SR RD WEST BATH | 2000326789 | 30014834318 | Solar | [5 empty] | 43.9072 | -69.8548 | Arthur J Reno Sr Road |  | Arthur J Reno Sr Road | West Bath | 8 | BATH 34 | 261D3 | 261T2 | 12.47 | 9310-L0099-6280-0041-ED00010 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2023-03-01 | 2023-03-08 | 2023-02-28 | 2023-03-07 | 2024-02-06 |  | 2024-02-21 | [127 empty] | 2024-02-15 | [17 empty] | 0 | [19 empty] | TRUE | FALSE |  | 0 | 0 | 1900 | 1900 | 1900
789 |  |  | KRISTOFER COLEMAN | 2023-03-03 | [31 empty] | 6 - LSFA |  | 232D1 | 712 |  | WITHDRAWN | WITHDRAWN |  | Peter R Whitney | MAINE COMMUNITY ENERGY, LLC | 577 LISBON STREET FUEL CELL LLC | 577 LISBON ST / FALMOUTH | 2000346692 | 30014865023 | Fuel Cell | [5 empty] | 44.0043 | -70.0746 | 577 Lisbon Street | 577 | Lisbon Street | Lisbon | 2 | LISBON FALLS | 232D1 | 232T1 | 12.47 | 9310-L0061-3310-0026-ED00006 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2023-03-10 | 2023-03-17 | 2023-03-09 | 2023-03-16 | [130 empty] | 2023-03-23 | [17 empty] | 0 | [19 empty] | TRUE | FALSE |  | 0 | 0 | 1900 | 1900 | 1900
790 |  | Govinda Neupane |  | 2023-03-03 | 2023-03-09 | wthdw |  | 2023-09-08 | L2_Bump |  | 2023-10-03 | L2_bump |  | 2023-10-27 | wthdw |  | 2025-01-22 | L2_With | [17 empty] | 8 - CARM |  | 808D2 | 750 |  | WITHDRAWN | WITHDRAWN |  | Paula J Fitzgerald | Novel Energy Solutions LLC | ME TURNER RT 2 CSG LLC | 559 US RT 2 CARMEL | 2000339487 | 30014779828 | Solar | [5 empty] | 44.8075 | -69.0246 | 559 US Route 2 | 559 | US Route 2 | Carmel | 64 | CARMEL | 808D2 | 808T1 | 12.47 | 9310-L0389-1020-0049-ED00246 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2023-03-10 | 2023-03-17 | 2023-03-09 | 2023-03-16 | 2024-04-11 | 2024-04-18 | 2024-04-26 | 2024-04-26 | 2024-04-30 | 2024-04-30 | 2024-05-14 |  |  | 2024-05-15 |  |  | CS | 2024-05-15 | [6 empty] | CS |  |  | 2024-05-16 | 2024-10-03 |  | 2024-12-02 | 2025-01-22 |  |  |  |  | 2024-11-20 |  |  | 2024-05-31 | 2024-11-16 |  | N/A | [5 empty] | 2024-05-31 | 2024-11-20 |  | 2024-12-09 | [5 empty] | 2024-05-31 | 2024-11-20 |  | 2024-12-09 | [8 empty] | 2024-08-06 | 2025-01-07 | [5 empty] | 2024-08-01 | [8 empty] | 2024-08-01 | [8 empty] | 2024-08-15 | [8 empty] | 2024-08-21 | [7 empty] | 2024-08-21 | [22 empty] | 2025-02-04 | [17 empty] | 0 | [19 empty] | TRUE | FALSE |  | 0 | 0 | 1900 | 1900 | 1900
791 |  | Eben Snow | Brent Brooks | 2023-03-03 | 2023-06-06 | L2_Bump |  | 2023-07-20 | wthdw |  | 2024-05-10 | wthdw |  | 2024-10-21 | wthdw |  | 2024-10-30 | studywaived | [17 empty] | 10 - MEFA |  | 431D2 | 777 |  | WITHDRAWN | WITHDRAWN |  | Rachael Chicoine | Correlate Inc. | SENERGY SOLAR 1 HOLDCO LLC | 553 WEST MINOT RD | 2000309510 | 30014381138 | Solar | [5 empty] | 44.1593 | -70.3753 | 576 West Minot Road | 576 | West Minot Road | Minot | 72H | MECHANIC FALLS | 431D2 | 431T1 | 12.47 | 9310-L0166-3710-0056-ED00149 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2023-03-10 | 2023-03-17 | 2023-03-09 | 2023-03-16 | 2024-05-10 | 2024-05-14 | 2024-05-24 | 2024-05-15 | 2024-05-21 | 2024-05-21 | 2024-06-05 |  |  | 2024-05-28 |  |  | CS | 2024-05-28 | FAC | 2024-10-10 |  |  |  |  | CS |  |  | 2024-05-28 |  | 2024-10-14 | [5 empty] | 2024-06-18 |  |  |  | 2024-06-04 | [8 empty] | 2024-06-18 | [8 empty] | 2024-06-18 | [11 empty] | 2024-08-22 | [6 empty] | 2024-08-16 | [8 empty] | 2024-08-19 | [8 empty] | 2024-09-03 | [8 empty] | 2024-09-09 | [7 empty] | 2024-09-09 | [18 empty] | 506423 | 2024-08-16 |  |  | 2024-12-18 | [17 empty] | 0 | [19 empty] | TRUE | FALSE |  | 0 | 0 | 1900 | 1900 | 1900
792 |  | Eben Snow | Brent Brooks | 2023-03-14 | 2023-08-02 | wthdw | [29 empty] | 7 - GRAY |  | 416D3 | 569 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Santiago Quijano | BWC HOLDINGS, INC | BLUEWAVE ORIGINATION LLC | 134 Long Hill Road | 2000310625 | 30014870635 | Solar | [5 empty] | 43.8541 | -70.3051 | 134 Long Hill Road | 134 | Long Hill Road | Gray | 44 | GRAY | 416D3 | 416T1 | 12.47 | 9310-L0135-2305-0012-ED00057 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2023-03-21 | 2023-03-28 | 2023-03-21 | 2023-03-27 | 2023-03-27 | 2023-03-28 | 2023-04-11 | 2023-03-30 | 2023-03-30 | 2023-03-30 | 2023-04-13 |  |  | 2023-04-10 |  |  | CS | [7 empty] | CS |  |  | 2023-04-17 |  |  | 2023-10-18 | [8 empty] | 2023-04-28 | [8 empty] | 2023-04-28 | [8 empty] | 2023-05-02 | [11 empty] | 2023-07-07 | [6 empty] | 2023-07-07 | [8 empty] | 2023-07-07 | [8 empty] | 2023-07-11 | [8 empty] | 2023-07-13 | [7 empty] | 2023-07-13 | [7 empty] | 2023-07-13 |  | 2023-07-17 |  | 2023-07-27 | [6 empty] | 879460 | 2023-07-05 |  |  | 2023-10-19 | 2021-07-13: 2023-07-31; 2021-07-13: 2023-07-31 | [9 empty] | 0 | [19 empty] | TRUE | FALSE |  | 2023-07-31 | 2023-07-31 | 2023 | 2023 | 2023
793 |  |  |  | 2023-03-23 | [31 empty] | 1 - BWST |  | 204D6 |  |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Peter R Whitney | BOLD COAST ENERGY, LLC | GIRI SEBASCO SOLAR LLC | 110 Route 217 Phippsburg | 2000349384 | 30014903592 | Solar | [5 empty] | 43.7643 | -69.8482 | 110 Sebasco RD | 110 | Sebasco RD | Phippsburg | 20 | WASHINGTON ST (BATH) | 204D6 | 34kV Bus No. 1 | 12.47 | 9310-L0017-4630-0081-ED00014 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2023-03-30 | 2023-04-06 | 2023-03-29 | 2023-04-05 | 2023-04-05 | 2023-04-05 | 2023-04-20 | 2023-04-06 | 2023-04-13 | 2023-04-13 | 2023-04-28 |  |  | 2023-04-18 |  |  | CS | 2023-04-18 | [6 empty] | CS |  |  | 2023-04-26 | [20 empty] | 2023-05-08 | [8 empty] | 2023-05-10 | [11 empty] | 2023-07-17 | [6 empty] | 2023-07-14 | [8 empty] | 2023-07-17 | [8 empty] | 2023-07-17 | [8 empty] | 2023-07-17 | [7 empty] | 2023-07-17 | [7 empty] | 2023-07-17 |  | 2023-07-27 |  | 2023-07-31 | [6 empty] | 110986 | 2023-07-14 |  |  | 2024-04-01 | 2021-07-13: 2023-08-01; 2021-07-13: 2023-08-03 | [9 empty] | -2 | [19 empty] | TRUE | FALSE |  | 2023-08-01 | 2023-08-01 | 2023 | 2023 | 2023
794 |  | Lanie Patterson | KRISTOFER COLEMAN | 2023-03-27 | [31 empty] | 7 - TP34 |  | 250K3 | 710 |  | WITHDRAWN | WITHDRAWN |  | Keyla Vera | Freedom Solar Holdings LLC | GOODWINS VOLVO MAZDA INC |  | 2800241577 | 35013961467 | Solar | [5 empty] | 43.9627 | -69.8852 | 91 MAIN ST | 91 | MAIN ST | Topsham | 50 | TOPSHAM 34 KV | 250K3 | 34 kV Bus No. 1 | 12.47 | 9310-L0084-5840-0098-ED00048 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2023-04-03 | 2023-04-10 | 2023-03-31 | 2023-04-06 | 2023-04-06 | 2023-04-07 | 2023-04-21 | 2023-04-07 | 2023-04-13 | 2023-04-13 | [29 empty] | 2023-05-17 | [8 empty] | 2023-05-04 | [85 empty] | 2023-06-05 | [17 empty] | 0 | [19 empty] | TRUE | FALSE |  | 0 | 0 | 1900 | 1900 | 1900
795 |  | Eben Snow |  | 2023-03-28 | 2023-08-14 | L2_Bump |  | 2023-12-13 | L2_Bump | [26 empty] | 3 - LULA | 2 - LULA | 461D1 | 566 | Yes | EXECUTED | EXECUTED |  | Julia Pons | BNRG MAINE LLC | BD SOLAR DIXFIELD LLC | CANTON POINT RD / DIXFIELD | 2000348798 | 30014895202 | Solar | 990 | 0.99 | 1392 |  |  | 44.5145 | -70.4014 | Canton Point Road |  | Canton Point Road | Dixfield | 514 | LUDDEN LANE | 461D1 | 461T3 | 34.5 | 9310-L0500-1620-0003-ED00074 |  | NOT IMPACTED | NOT IMPACTED |  | Yes | [6 empty] | 2023-04-04 | 2023-04-11 | 2023-03-31 | 2023-04-10 | 2023-04-10 | 2023-04-10 | 2023-04-25 | 2023-04-10 | 2023-04-26 | 2023-04-26 | 2023-05-10 |  |  | 2023-05-03 |  |  | CS | [7 empty] | CS |  |  | 2023-05-03 |  |  | 2024-03-13 | [8 empty] | 2023-05-17 |  |  | 2024-03-18 | [5 empty] | 2023-05-17 |  |  | 2024-03-22 | [5 empty] | 2023-05-19 |  |  | 2024-03-22 | [8 empty] | 2023-07-26 | [6 empty] | 2023-07-21 |  |  | 2024-05-17 | [5 empty] | 2023-07-28 |  |  | 2024-05-17 | [5 empty] | 2023-08-08 |  |  | N/A | [5 empty] | 2023-08-08 |  |  | N/A |  |  |  |  | 2023-08-10 |  |  | N/A |  |  |  |  | 2024-05-22 |  | 2024-05-22 |  | 2024-05-22 | [6 empty] | 422851 | 2023-07-20 | 145351 |  |  | 2021-07-13: 2024-05-29; 2021-07-13: 2024-05-29 | [9 empty] | 0 |  |  |  | Q1 2026 |  |  |  | Requested | [11 empty] | TRUE | FALSE |  | 2024-05-29 | 2024-05-29 | 2024 | 2024 | 2024
796 |  | Marshall Ripley | Rick Duperre | 2023-03-28 | 2024-03-14 | wthdw | [28 empty] | 685 | 4 - ELM |  | 620D4 | 690 | Yes | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED |  | Jacob Fraatz | Dimension ME 1, LLC | Water Line Solar, LLC | 238 Sweester Rd N yarmouth | 2000414651 | 30015772566 | Solar | 999 | 0.999 | 1179.36 |  |  | 43.8264 | -70.2266 | 238 Sweetser Road | 238 | Sweetser Road | North Yarmouth | 11 | ELM STREET | 620D4 | 620T2 | 12.47 | 9310-L0238-4200-0034-ED00003 |  | TRIGGERING | TRIGGERING (375,000) | 125000 | Yes | [6 empty] | 2023-04-04 | 2023-04-11 | 2023-04-04 | 2023-04-10 | 2023-05-02 | 2023-05-02 | 2023-05-16 | 2023-05-04 | 2023-05-08 | 2023-05-08 | 2023-05-22 |  |  | 2023-05-16 |  |  | CS | [7 empty] | CS |  |  | 2023-05-16 |  |  | 2024-03-19 | [11 empty] | 2023-03-27 | [5 empty] | 2023-05-17 |  |  | 2023-03-28 | [5 empty] | 2023-05-22 |  |  | 2024-03-28 | [8 empty] | 2023-07-27 | [6 empty] | 2023-07-19 |  |  | 2024-06-03 | [5 empty] | 2023-07-19 |  |  | 2024-06-04 | [5 empty] | 2023-07-19 |  |  | 2024-06-05 | [5 empty] | 2023-07-21 |  |  | 2024-06-12 |  |  | 2023-07-21 |  |  |  |  | 2024-06-12 |  |  |  |  | 2023-08-11 |  | 2023-08-14 |  | 2023-09-13 | [6 empty] | 588846 | 2023-07-17 | 564001 | 2024-06-15 |  | 2023-09-15 | 2023-09-15 | 2023-09-29 | 2023-09-29 | 2024-07-01 | 2024-07-01 | [11 empty] | 0 |  |  |  | Q2 2025 |  |  |  | Requested | [11 empty] | TRUE | FALSE |  | 2023-09-15 | 2023-09-15 | 2023 | 2023 | 2023
797 |  |  | Anthony Boucher | 2023-03-29 | [31 empty] | 9 - BUCK |  | 806D2 | 762 |  | WITHDRAWN | WITHDRAWN |  | Corwin Lavoie | Nexamp, Inc | NEXAMP SOLAR LLC | 33 Town Farm Rd, Bucksport | 2000114877 | 30014911611 | Solar | [5 empty] | 44.6245 | -68.7915 | 33 Town Farm Rd | 33 | Town Farm Rd | Bucksport | 8 | BUCKSPORT | 806D2 | 806T3 | 12.47 | 9310-L0386-0790-0083-ED00125 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2023-04-05 | 2023-04-12 | 2023-04-04 | 2023-04-10 | 2024-01-31 | 2024-02-06 | 2024-02-14 | 2024-02-07 | 2024-02-16 | 2024-02-16 | 2024-03-04 |  |  | 2024-02-19 |  |  | CS | [7 empty] | CS |  |  | 2024-02-22 | [7 empty] | 2024-03-07 |  |  |  | 2024-03-01 |  |  | 2024-03-27 | [5 empty] | 2024-03-07 | [8 empty] | 2024-03-07 | [11 empty] | 2024-05-10 | [6 empty] | 2024-05-10 | [8 empty] | 2024-05-10 | [44 empty] | 3415022 | 2024-05-09 |  |  | 2024-05-23 | [17 empty] | 0 | [19 empty] | TRUE | FALSE |  | 0 | 0 | 1900 | 1900 | 1900
798 |  | Marshall Ripley | Rick Duperre | 2023-03-29 | 2024-03-14 | wthdw | [28 empty] | 796 | 5 - ELM |  | 620D4 | 796 | Yes | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED |  | Jacob Fraatz | Dimension ME 1, LLC | Boundary Line Solar, LLC | 0 Doughty Rd, No Yarmouth | 2000414648 | 30015772558 | Solar | 999 | 0.999 | 1134 |  |  | 43.8096 | -70.2368 | 0 Doughty Road | 0 | Doughty Road | North Yarmouth | 11 | ELM STREET | 620D4 | 620T2 | 12.47 | 9310-L0238-4200-0004-ED00003 |  | COST SHARING | COST SHARING (375,000) | 125000 | Yes | [6 empty] | 2023-04-05 | 2023-04-12 | 2023-04-05 | 2023-04-10 | 2023-09-15 | 2023-09-20 | 2023-09-29 | 2023-09-26 | 2023-09-28 | 2023-09-28 | 2023-10-16 |  |  | 2023-10-02 |  |  | CS | [7 empty] | CS |  |  | 2023-10-02 |  |  | 2024-07-01 | [8 empty] | 2023-10-03 |  |  | 2024-07-10 | [5 empty] | 2023-10-03 |  |  | 2024-07-10 | [5 empty] | 2023-10-05 |  |  | 2024-07-10 | [8 empty] | 2023-12-13 | [6 empty] | 2023-12-13 |  |  | 2024-09-11 | [5 empty] | 2023-12-13 | [8 empty] | 2023-12-13 | [8 empty] | 2023-12-15 | [7 empty] | 2023-12-15 | [7 empty] | 2023-12-15 |  | 2023-12-18 | 2024-10-01 | 2023-12-18 | 2024-11-11 | [5 empty] | 522106 | 2023-12-12 |  |  |  | 2021-07-13: 2023-12-19; 2021-07-13: 2023-12-19; 2021-07-13: 2024-11-12; 2021-07-13: 2024-11-12 | [9 empty] | 0 |  |  |  | Q3 2025 |  |  |  | Requested | [11 empty] | TRUE | FALSE |  | 2023-12-19 | 2023-12-19 | 2023 | 2023 | 2023
799 |  |  | Anthony Boucher | 2023-03-29 | [31 empty] | 10 - BUCK |  | 806D2 | 797 |  | WITHDRAWN | WITHDRAWN |  | Daniel Passarello | Nexamp, Inc | NEXAMP SOLAR LLC | 33 Town Farm Rd, Bucksport | 2000114877 | 30014911637 | Solar | [5 empty] | 44.6245 | -68.7915 | 33 Town Farm Rd | 33 | Town Farm Rd | Bucksport | 7 | BUCKSPORT | 806D2 | 806T3 | 12.47 | 9310-L0386-0790-0083-ED00124 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2023-04-05 | 2023-04-12 | 2023-04-05 | 2023-04-10 | 2024-05-23 |  | 2024-06-07 | [127 empty] | 2024-05-28 | [17 empty] | 0 | [19 empty] | TRUE | FALSE |  | 0 | 0 | 1900 | 1900 | 1900
800 |  | Eben Snow | Eben Snow | 2023-04-12 | [31 empty] | 2 - MIDD |  | 451D8 | 734 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Jacques Guillet | NUPOWER BATTERY STORAGE LLC | NUPOWER BATTERY STORAGE LLC | 25 Middle St Lewiston | 2000291110 | 30014131178 | Battery | [5 empty] | 44.1018 | 0 | 25 Middle Street | 25 | Middle Street | Lewiston | 2 | MIDDLE STREET | 451D8 | 451T2 | 12.47 | 9310-L0487-3230-0014-ED00004 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2023-04-20 | 2023-04-27 | 2023-04-17 | 2023-04-21 | 2023-04-12 | 2023-04-25 | 2023-04-26 | 2023-04-25 | 2023-05-03 | 2023-05-03 | 2023-05-17 |  |  | 2023-05-04 |  | 2023-08-02 | CS | 2023-05-04 | FAC | 2023-08-02 |  |  |  |  | CD |  |  | 2023-05-09 |  | 2023-08-29 | [11 empty] | 2023-09-20 | [6 empty] | 2023-05-09 |  | 2023-09-20 | [6 empty] | 2023-05-16 |  | 2023-09-22 | [9 empty] | 2023-07-21 |  | 2023-11-30 |  |  |  |  | 2023-06-28 |  | 2023-12-07 | [6 empty] | 2023-06-28 |  | 2023-12-07 | [6 empty] | 2023-06-29 |  | 2023-12-14 | [6 empty] | 2023-07-12 |  | 2023-12-27 | [5 empty] | 2023-07-12 |  | 2023-12-27 | [5 empty] | 2024-01-02 |  | 2024-01-04 |  | 2024-01-09 | [6 empty] | 551137 |  | 392448 | 2023-12-07 | 2025-12-02 | 2021-07-13: 2024-01-10; 2021-07-13: 2024-01-11 | [9 empty] | -1 | [7 empty] | Requested | [11 empty] | TRUE | FALSE |  | 2024-01-10 | 2024-01-10 | 2024 | 2024 | 2024
801 |  | Rigel Paradise | Rick Duperre | 2023-04-19 | 2023-11-01 | Wthdw | [29 empty] | 8 - PRAT | 1 - PRAT | 661D1 | 613 | Yes | EXECUTED | EXECUTED |  | Tyler William Perkins | Nexamp, Inc | SANFORD RENEWABLE LLC | QUARRY RD / SANFORD | 2000470458 | 30016610666 | Solar | 999 | 0.999 | 1319.76 |  |  | 43.3425 | -70.7225 | Quarry Road |  | Quarry Road | South Sanford | 712 | PRATT & WHITNEY | 661D1 | 661T1 | 12.47 | 9310-L0329-5170-0455-ED00007 |  | COST SHARE | COST SHARE (340,000) | 31024 | Yes | [6 empty] | 2023-04-26 | 2023-05-03 | 2023-04-25 | 2023-05-02 | 2023-05-02 | 2023-05-04 | 2023-05-16 | 2023-05-09 | 2023-05-11 | 2023-05-11 | 2023-05-25 |  |  | 2023-05-15 |  |  | CS | 2023-05-15 | [6 empty] | CS |  |  | 2023-05-17 | 2023-09-26 |  | 2023-11-28 | [8 empty] | 2023-05-26 | 2023-10-02 |  | 2023-12-01 | [5 empty] | 2023-05-11 | 2023-10-02 |  | 2023-12-12 | [5 empty] | 2023-06-12 | 2023-10-10 |  | 2023-12-14 | [8 empty] | 2023-08-16 | 2023-11-22 | [5 empty] | 2023-08-15 |  |  | 2024-02-21 | [5 empty] | 2023-08-16 |  |  | 2024-02-21 | [5 empty] | 2023-08-30 |  |  | 2024-02-26 | [5 empty] | 2023-08-31 |  |  | 2024-03-07 |  |  |  |  | 2023-08-31 |  |  | 2024-03-07 |  |  |  |  | 2024-03-26 |  | 2024-03-27 |  | 2024-04-25 | [6 empty] | 1047083 | 2023-08-16 | 870,052.41. | 2024-02-21 |  | 2021-07-13: 2024-04-29; 2021-07-13: 2024-04-29; 2021-07-13: 2025-03-18; 2021-07-13: 2025-03-19 | [9 empty] | 0 |  |  |  | Q4 2026 | [15 empty] | TRUE | FALSE |  | 2024-04-29 | 2024-04-29 | 2024 | 2024 | 2024
802 |  | Eben Snow | Brent Brooks | 2023-04-20 | [31 empty] | 4 - BRID |  | 406D1 | 629 |  | WITHDRAWN | WITHDRAWN |  | Michael Brigandi | New Leaf Energy, Inc | 510 PV PROJECT DEVELOPMENT | 61 Chadborne Hill Rd BRIGTON | 2000113260 | 30014968074 | Solar | [5 empty] | 44.0988 | -70.7057 | 61 Chadbourne Hill Rd | 61 | Chadbourne Hill Rd | Bridgton | 12 | BRIDGTON | 406D1 | 406T1 | 12.47 | 9310-L0118-0690-0017-ED00005 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2023-04-27 | 2023-05-04 | 2023-04-25 | 2023-05-04 | 2023-05-04 | 2023-05-04 | 2023-05-18 | 2023-05-05 | 2023-05-10 | 2023-05-10 | 2023-05-24 |  |  | 2023-05-23 |  |  | CS | 2023-05-23 | [6 empty] | CS |  |  | 2023-06-06 | [11 empty] | 2023-06-20 | [8 empty] | 2023-06-06 | [8 empty] | 2023-07-12 | [11 empty] | 2023-09-14 | [6 empty] | 2023-09-18 |  |  | 2023-09-18 | [5 empty] | 2023-09-18 | [8 empty] | 2023-09-19 | [8 empty] | 2023-10-02 | [7 empty] | 2023-10-02 | [7 empty] | 2023-10-24 |  | 2023-11-03 | [8 empty] | 3176337 | 2023-11-02 |  |  | 2023-12-20 | [17 empty] | 0 | [19 empty] | TRUE | FALSE |  | 0 | 0 | 1900 | 1900 | 1900
803 |  | Ben Brooks | Anthony Boucher | 2023-04-21 | 2023-10-20 | Wthdw |  | 2024-08-15 | wthdw | [25 empty] | 625 | 12 - BEWE | 1 - BEWE | 803D4 | 625 | Yes | EXECUTED | EXECUTED |  | Nash Sultan | Bridge Energy | PE Thompson Brook Solar LLC | 30 Waterville Rd Belfast | 2000353673 | 30014955196 | Solar | 999 | 0.999 | 1412.4 |  |  | 44.4383 | -69.035 | 30 Waterville Road | 30 | Waterville Road | Belfast | 36 | BELFAST WEST SIDE | 803D4 | 803T1 | 12.47 | 9310-L0381-0430-0173-ED00110 |  | COST SHARING | COST SHARING (375,000) | 56475.04 | Yes | [6 empty] | 2023-04-28 | 2023-05-05 | 2023-04-27 | 2023-05-04 | 2023-09-22 | 2023-09-28 | 2023-10-06 | 2023-10-10 | 2023-10-11 | 2023-10-11 | 2023-10-25 |  |  | 2023-10-13 |  |  | CS | [7 empty] | CS |  |  | 2024-05-02 |  |  | 2024-08-19 |  |  |  |  | 2024-05-14 |  |  |  | 2024-10-19 |  |  | 2024-09-03 | [5 empty] | 2024-05-14 |  |  | 2024-09-03 | [5 empty] | 2024-05-14 |  |  | 2024-09-03 | [8 empty] | 2024-07-19 | [6 empty] | 2024-07-17 | [8 empty] | 2024-07-17 | [8 empty] | 2024-07-24 | [8 empty] | 2024-07-30 | [7 empty] | 2024-07-30 | [7 empty] | 2024-09-16 |  | 2024-09-16 |  | 2024-09-17 | [6 empty] | 150961 | 2024-07-16 |  |  |  | 2021-07-13: 2024-09-19; 2021-07-13: 2024-09-19 | [9 empty] | 0 |  |  |  | Q4 2025 | [15 empty] | FALSE | FALSE |  | 2024-09-19 | 2024-09-19 | 2024 | 2024 | 2024
804 |  | Rigel Paradise | Rick Duperre | 2023-04-24 | [31 empty] | 3 - GOOS |  | 630D4 | 767 |  | WITHDRAWN | WITHDRAWN |  | Patrick Khosravan | Freedom Solar Holdings LLC | GROUP 1 REALTY INC | 783 PORTLAND RD MGS / SACO ME 04072 | 2000270546 | 30013852543 | Solar | [5 empty] | 43.5302 | -70.425 | 783 Portland Rd | 783 | Portland Rd | Saco | 132.01 | GOOSEFARE | 630D4 | 630T1 | 12.47 | 9310-L0481-5090-0221-PM00002 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2023-05-01 | 2023-05-08 | 2023-04-27 | 2023-05-05 | 2023-05-05 | 2023-05-05 | 2023-05-24 | 2023-05-24 | [122 empty] | na/a | na/a | na/a | na/a | 2023-06-26 | [17 empty] | 0 | [19 empty] | TRUE | FALSE |  | 0 | 0 | 1900 | 1900 | 1900
805 |  | Lanie Patterson | Brent Brooks | 2023-04-25 |  |  |  | 2023-05-21 | L2_Bump |  | 2023-10-06 |  |  |  | L2_bump |  | 2024-01-09 | wthdw |  | 2024-09-05 | wthdw | [12 empty] | 4 - MANC | 726 | 8 - MANC |  | 233D2 | 726 | Yes | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Nathaniel Curtis | MIDCOAST SOLAR LLC | MIDCOAST SOLAR LLC | 315 PRESCOTT RD MANCHESTER ME | 2000162495 | 30014977455 | Solar/Battery | [5 empty] | 44.339 | -69.8439 | 315 Prescott Rd. | 315 | Prescott Rd. | Manchester | 21 | MANCHESTER | 233D2 | 233T1 | 12.47 | 9310-L0064-3540-0068-ED00018 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2023-05-02 | 2023-05-09 | 2023-04-27 | 2023-05-05 | 2025-01-08 | 2025-01-08 | 2025-01-23 | 2025-01-08 | 2025-01-14 | 2025-01-14 | 2025-01-29 |  |  | 2025-01-29 |  |  | CS | 2025-01-29 | [6 empty] | CS |  |  | 2025-01-29 | [7 empty] | 2025-02-19 |  |  |  | 2025-02-17 | [8 empty] | 2025-02-19 | [8 empty] | 2025-02-19 | [11 empty] | 2025-04-24 | [6 empty] | 2025-04-17 | [8 empty] | 2025-04-17 | [8 empty] | 2025-04-23 | [8 empty] | 2025-04-29 | [7 empty] | 2025-04-29 | [7 empty] | 2025-05-22 |  | 2025-05-23 |  | 2025-07-24 | [6 empty] | 838116 | 2025-04-16 |  |  | 2026-03-03 | 2021-07-13: 2025-07-25; 2021-07-13: 2025-07-29 | [9 empty] | -4 |  |  |  | Q2 2026 | [15 empty] | FALSE | FALSE |  | 2025-07-25 | 2025-07-25 | 2025 | 2025 | 2025
806 |  | Lanie Patterson | Kristofer Coleman | 2023-04-27 | 2023-10-13 | L2_Bump |  | 2023-04-08 | wthdw |  | 2024-12-03 | wthdw | [23 empty] | 5 - DAMS | 1 - DAMS | 219D2 | 736 | Yes | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED |  | Nathaniel Curtis | MIDCOAST SOLAR LLC | Sheepscot Solar LLC | 750 US RT 1, NEWCASTLE, | 2000446431 | 30016250240 | Solar/Battery | 996 | 0.996 | 1552.32 |  | 969 | 44.0222 | -69.5761 | Approx 750 US Route 1 | 750 | US Route 1 | Newcastle | 34 | DAMARISCOTTA MILLS | 219D2 | 219T1 | 12.47 | 9310-L0051-4100-0074-ED00052 |  | TRIGGERING | TRIGGERING | 325000 | Yes | [6 empty] | 2023-05-04 | 2023-05-11 | 2023-05-02 | 2023-05-08 | 2023-05-08 | 2023-05-08 | 2023-05-22 | 2023-05-12 | 2023-05-16 | 2023-05-16 | 2023-05-31 |  |  | 2023-05-23 |  |  | CS | 2023-05-24 | [6 empty] | CS |  |  | 2023-06-05 |  |  | 2024-06-14 | 2024-12-05 | [7 empty] | 2023-06-05 |  |  | 2024-06-20 | [5 empty] | 2023-08-13 |  |  | 2024-06-20 | [5 empty] | 2023-06-13 |  |  | 2024-06-20 | [8 empty] | 2023-08-17 | [6 empty] | 2023-08-17 |  |  | 2024-08-21 | [5 empty] | 2023-08-18 |  |  | 2024-08-21 | [5 empty] | 2023-08-22 | [8 empty] | 2023-08-30 | [7 empty] | 2023-08-30 | [7 empty] | 2023-08-31 |  | 2023-09-06 | 2024-09-20 | 2023-10-04 | 2024-10-21 | [5 empty] | 268124 | 2023-08-30 | 559940 | 2024-08-20 |  | 2021-07-13: 2023-12-11; 2021-07-13: 2023-12-11; 2021-07-13: 2024-10-31; 2021-07-13: 2024-10-31 | [9 empty] | 0 |  |  |  | Q4 2024 |  |  |  | Requested | [11 empty] | FALSE | FALSE |  | 2023-12-11 | 2023-12-11 | 2023 | 2023 | 2023
807 |  | Rigel Paradise | Rick Duperre | 2023-05-03 | 2023-09-21 | L2_Bump | [5 empty] | wthdw | [23 empty] | 3 - BRCM |  | 689D1 | 444 | Yes | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Nick Sampson | BNRG MAINE LLC | BD SOLAR YORK LLC | Major McIntire Rd, York | 2000155271 | 30014994971 | Solar | [5 empty] | 43.1596 | -70.71 | 53 Major McIntire Road | 53 | Major McIntire Road | York | 10 | BRAGDON COMMONS | 689D1 | 689T1 | 12.47 | 9310-L0367-6660-0250-ED00002 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2023-05-10 | 2023-05-17 | 2023-05-05 | 2023-05-08 | 2023-05-08 | 2023-05-12 | 2023-05-22 | 2023-05-12 | 2023-05-18 | 2023-05-18 | 2023-06-02 |  |  | 2023-06-05 |  |  | CS | 2023-06-05 | [6 empty] | CS |  |  | 2023-06-06 |  |  | 2023-09-25 | [11 empty] | 2023-10-06 | [5 empty] | 2023-06-06 |  |  | 2023-10-13 | [5 empty] | 2023-06-22 |  |  | 2023-10-13 | [8 empty] | 2023-08-25 | [6 empty] | 2023-08-25 |  |  | 2023-11-29 | [5 empty] | 2023-08-29 |  |  | 2023-11-29 | [5 empty] | 2023-09-11 |  |  | 2023-11-29 | [5 empty] | 2023-09-11 |  |  | 2023-12-04 |  |  |  |  | 2023-09-11 |  |  | 2023-12-07 |  |  |  |  | 2023-12-28 |  | 2023-12-29 |  | 2024-01-25 | [6 empty] | 364190 |  | 364190 | 2023-11-29 | 2025-08-07 | 2021-07-13: 2024-01-29; 2021-07-13: 2024-01-29 | [9 empty] | 0 |  |  |  | Q4 2025 |  |  |  | REQUESTED | [11 empty] | TRUE | FALSE |  | 2024-01-29 | 2024-01-29 | 2024 | 2024 | 2024
808 |  | Rigel Paradise | Rick Duperre | 2023-05-04 | 2023-10-13 | L2_Bump |  | 2024-05-01 | wthdw | [25 empty] | 689 | 8 - LEBA | 1 - LEBA | 695D2 | 689 | Yes | EXECUTED | EXECUTED |  | Corwin Lavoie | Nexamp, Inc | LEBANON RENEWABLES LLC | NEXAMP SOLAR LLC | 2000470458 | 30016610674 | Solar | 975 | 0.975 | 1333.8 |  |  | 43.396 | -70.9109 | Station Lane |  | Station Lane | Lebanon | 84.1 | LEBANON | 695D2 | 695T1 | 12.47 | 9310-L0473-3190-0003-ED00211 |  | COST SHARE | COST SHARE (255,000) | 50005.03 | Yes | [6 empty] | 2023-05-11 | 2023-05-18 | 2023-05-05 | 2023-05-08 | 2023-05-09 | 2023-05-08 | 2023-05-22 | 2023-05-12 | 2023-05-16 | 2023-05-16 | 2023-05-31 |  |  | 2023-05-25 |  |  | CS | 2023-05-25 | [6 empty] | CS |  |  | 2023-06-07 |  |  | 2024-06-14 | [11 empty] | 2024-07-01 | [5 empty] | 2023-06-23 |  |  | 2024-07-17 | [5 empty] | 2023-06-28 |  |  | 2024-07-17 | [8 empty] | 2023-08-31 | [6 empty] | 2023-08-31 |  |  | 2024-09-04 | [5 empty] | 2023-09-05 |  |  | 2024-09-17 | [5 empty] | 2023-09-22 |  |  | 2024-09-23 | [5 empty] | 2023-09-29 |  |  | 2024-09-27 |  |  |  |  | 2023-09-29 |  |  | 2024-09-27 |  |  |  |  | 2024-10-22 |  | 2024-10-22 |  | 2024-11-21 | 2024-11-21 | [5 empty] | 194491.03 |  | 194491.03 |  |  | 2021-07-13: 2024-11-21; 2021-07-13: 2024-11-22; 2021-07-13: 2025-03-18; 2021-07-13: 2025-03-19 | [9 empty] | -1 |  |  |  | Q4 2024 | [15 empty] | TRUE | FALSE |  | 2024-11-21 | 2024-11-21 | 2024 | 2024 | 2024
809 |  | Rigel Paradise | Rick Duperre | 2023-05-05 |  |  |  | 2025-08-07 | wthdw | [26 empty] | 5 - MAST |  | 634D4 | 783 | Yes | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Michael Brigandi | New Leaf Energy, Inc | Saint Joseph Solar 1, LLC | 120 West St BIDDEFORD | 2000113260 | 30015784579 | Solar/Battery | [5 empty] | 43.4718 | -70.4553 | 120 West Street | 120 | West Street | Biddeford | 55 | MAY STREET | 634D4 | 634T1 | 12.47 | 9310-L0269-0490-0321-ED00210 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2023-05-12 | 2023-05-19 | 2023-05-05 | 2023-05-08 | 2023-08-08 | 2023-08-08 | 2023-08-23 | 2023-08-15 | 2023-08-17 | 2023-08-17 | 2023-08-31 |  |  | 2023-08-29 |  |  | CS | 2023-08-29 | [6 empty] | CS |  |  | 2023-09-06 |  |  | 2025-08-08 | [8 empty] | 2023-09-20 |  |  | 2025-08-27 | [5 empty] | 2023-09-20 |  |  | 2025-08-27 | [5 empty] | 2023-09-20 |  |  | 2025-08-28 | [8 empty] | 2023-11-28 | [6 empty] | 2023-11-28 |  |  | 2025-11-03 | [5 empty] | 2023-11-28 |  |  | 2025-11-03 | [5 empty] | 2024-01-03 | [8 empty] | 2024-01-05 | [7 empty] | 2024-01-05 | [7 empty] | 2024-01-26 |  | 2024-01-30 | 2025-11-07 | 2024-02-28 | 2025-12-11 | [5 empty] | 345986 | 2023-11-28 | 191458 | 2025-11-03 | 2026-05-22 | 2021-07-13: 2024-02-29; 2021-07-13: 2024-02-29; 2021-07-13: 2025-12-11; 2021-07-13: 2025-12-16 | [9 empty] | 0 |  |  |  | Q2 2025 |  |  |  | Requested | [11 empty] | TRUE | FALSE |  | 2024-02-29 | 2024-02-29 | 2024 | 2024 | 2024
810 |  | Rigel Paradise | Rick Duperre | 2023-05-05 | [31 empty] | 6 - MAST |  | 634D4 | 809 |  | WITHDRAWN | WITHDRAWN |  | Michael Brigandi | New Leaf Energy, Inc | 510 PV PROJECT DEVELOPMENT LLC | 525 Elm St BIDDEFORD | 2000113260 | 30014968421 | Solar/Battery | [5 empty] | 43.4733 | -70.4805 | 525 Elm Street | 525 | Elm Street | Biddeford | 113 | MAY STREET | 634D4 | 634T1 | 12.47 | 9310-L0269-0490-0086-ED00041 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2023-05-12 | 2023-05-19 | 2023-05-05 | 2023-05-08 | 2024-02-29 |  | 2024-03-14 | [123 empty] | n/a |  |  |  | 2024-03-13 | [17 empty] | 0 | [19 empty] | TRUE | FALSE |  | 0 | 0 | 1900 | 1900 | 1900
811 |  | Marshall Ripley | Rick Duperre | 2023-05-05 | 2024-03-14 | wthdw | [28 empty] | 798 | 6 - ELM |  | 620D3 | 798 | Yes | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Michael Brigandi | New Leaf Energy, Inc | 510 PV PROJECT DEVELOPMENT LLC | 0 Treatment Plant Rd YARMOUTH | 2000113260 | 30014968090 | Solar/Battery | [5 empty] | 43.789 | -70.168 | 100 Smith St | 100 | Smith St | Yarmouth | 50.5 | ELM STREET | 620D3 | 620T2 | 12.47 | 9310-L0237-6650-0111-ED00062 |  | COST SHARING | COST SHARING (375,000) |  | Yes | [6 empty] | 2023-05-12 | 2023-05-19 | 2023-05-05 | 2023-05-08 | 2023-12-28 | 2024-01-04 | 2024-01-12 | 2024-01-11 | 2024-01-17 | 2024-01-17 | 2023-01-31 |  |  | 2024-01-31 |  |  | CS | [7 empty] | CS |  |  | 2024-11-12 | [11 empty] | 2024-02-07 | [8 empty] | 2024-02-23 |  |  | 2024-11-25 | [5 empty] | 2024-02-23 |  |  | 2024-11-25 | [8 empty] | 2024-04-25 | [9 empty] | 2025-02-11 | [8 empty] | 2025-02-11 | [8 empty] | 2025-02-11 | [8 empty] | 2025-02-19 | [7 empty] | 2025-02-19 |  |  |  |  | 2025-02-25 |  | 2025-03-05 |  | 2025-03-24 | [6 empty] | 457408 | 2025-02-06 |  |  | 2025-10-22 | 2021-07-13: 2025-03-25; 2021-07-13: 2025-03-25 | [9 empty] | 0 |  |  |  | Q4 2024 | [15 empty] | TRUE | FALSE |  | 2025-03-25 | 2025-03-25 | 2025 | 2025 | 2025
812 |  | Marshall Ripley | Rick Duperre | 2023-05-05 | [31 empty] | 1 - RIGB | 1 - RIGB | 650D4 |  |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Michael Brigandi | New Leaf Energy, Inc | South Portland Solar 1, LLC | 0 Dawson Rd SOUTH PORTLAND | 2000113260 | 30015784595 | Solar/Battery | [5 empty] | 43.6339 | -70.3002 | 1461 Broadway St | 1461 | Broadway St | South Portland | 12 | RIGBY | 650D4 | 650T2 | 12.47 | 9310-L0309-5430-0106-ED00004 |  |  |  |  | Yes | [6 empty] | 2023-05-12 | 2023-05-19 | 2023-05-05 | 2023-05-08 | 2023-05-08 | 2023-05-10 | 2023-05-27 | 2023-05-12 | 2023-05-17 | 2023-05-17 | 2023-06-01 |  |  | 2023-05-30 |  |  | CS | 2023-06-08 | [6 empty] | CS |  |  | 2023-06-13 | [7 empty] | 2023-07-12 |  |  |  | 2023-06-21 | [8 empty] | 2023-07-12 | [8 empty] | 2023-07-12 | [11 empty] | 2023-09-14 | [6 empty] | 2023-09-14 | [8 empty] | 2023-09-14 | [8 empty] | 2023-09-19 | [8 empty] | 2023-09-28 | [7 empty] | 2023-09-28 | [7 empty] | 2023-10-20 |  | 2023-10-27 |  | 2023-11-27 | [6 empty] | 451556 | 2023-10-03 |  |  | 2026-02-05 | 2021-07-13: 2023-11-28; 2021-07-13: 2023-11-28 | [9 empty] | 0 |  |  |  | Q3 2026 | [15 empty] | TRUE | FALSE |  | 2023-11-28 | 2023-11-28 | 2023 | 2023 | 2023
813 |  | Lanie Patterson | Brent Brooks | 2023-05-05 | [31 empty] | 3 - SIDN |  | 242D1 | 353 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Paula J Fitzgerald | Novel Energy Solutions LLC | ME Philbrick Middle Road CSG LLC | 2705 MIDDLE RD SIDNEY | 2000357848 | 30015008540 | Solar/Battery |  |  |  |  | 1000 | 44.4379 | -69.7531 | 2705 Middle Road | 2705 | Middle Road | Sidney | 17 | SIDNEY | 242D1 | 242T1 | 12.47 | 9310-L0076-5320-0051-ED00081 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2023-05-12 | 2023-05-19 | 2023-05-10 | 2023-05-18 | 2023-05-18 | 2023-05-24 | 2023-06-02 | 2023-06-06 | 2023-06-07 | 2023-06-07 | 2023-06-22 |  |  | 2023-06-08 |  |  | CS | 2023-06-08 | CS | [5 empty] | CS |  |  | 2023-06-09 | [11 empty] | 2023-08-01 | [8 empty] | 2023-08-04 | [8 empty] | 2023-08-04 | [11 empty] | 2023-10-10 | [6 empty] | 2023-10-09 | [8 empty] | 2023-10-10 | [8 empty] | 2023-10-30 | [8 empty] | 2023-11-15 | [7 empty] | 2023-11-15 | [7 empty] | 2023-11-27 |  | 2023-11-29 |  | 2023-11-29 | [6 empty] | 349064 | 2023-10-09 |  |  | 2026-03-31 | 2021-07-13: 2023-11-30; 2021-07-13: 2023-12-19 | [9 empty] | -19 |  |  |  | Q2 2026 |  |  |  | Requested | [11 empty] | TRUE | FALSE |  | 2023-11-30 | 2023-11-30 | 2023 | 2023 | 2023
814 |  | Eben Snow | Brent Brooks | 2023-05-08 | [31 empty] | 7 - NORW | 1 - NORW | 435D3 | 520 |  | EXECUTED | EXECUTED |  | Nash Sultan | Bridge Energy | PE TUCKER BROOK SOLAR LLC | HATHAWAY RD SOUTH PARIS | 2000357917 | 30015009282 | Solar | 999 | 0.999 | 1399.56 |  |  | 44.2451 | -70.5214 | 27 Hathaway Road | 27 | Hathaway Road | South Paris | 3.2 | NORWAY | 435D3 | 435T2 |  | 9310-L0170-4500-0128-ED00005 |  | COST SHARING | COST SHARING (250,000) | 27908.14 | Yes | [6 empty] | 2023-05-15 | 2023-05-22 | 2023-05-12 | 2023-05-18 | 2023-05-18 | 2023-05-24 | 2023-06-02 | 2023-05-30 | 2023-06-01 | 2023-06-01 | 2023-06-15 |  |  | 2023-06-14 |  |  | CS | [7 empty] | CS |  |  | 2023-06-19 | [20 empty] | 2023-06-14 | [8 empty] | 2023-07-18 | [11 empty] | 2023-09-20 | [6 empty] | 2023-09-20 | [8 empty] | 2023-09-20 | [8 empty] | 2023-10-04 | [8 empty] | 2023-10-05 | [7 empty] | 2023-10-05 | [7 empty] | 2023-10-13 |  | 2023-10-18 |  | 2023-11-14 | [6 empty] | 429364 | 2023-09-20 | 412864 | 2023-10-17 |  | 2021-07-13: 2023-11-20; 2021-07-13: 2023-11-27 | [9 empty] | -7 |  |  |  | Q4 2025 | [15 empty] | TRUE | FALSE |  | 2023-11-20 | 2023-11-20 | 2023 | 2023 | 2023
815 |  | Govinda Neupane |  | 2023-05-09 | [6 empty] | 2023-11-07 | L2_Bump |  | 2023-12-19 | wthdw | [19 empty] | 707 | 8 - RUMF |  | 447D2 | 707 | Yes | WITHDRAWN | WITHDRAWN |  | Paula J Fitzgerald | Novel Energy Solutions LLC | ME RUGG WYMAN HILL CSG LLC | 139 Wyman Hill Rd, Rumford | 2000344321 | 30014836230 | Solar | [5 empty] | 44.5209 | -70.518 | 139 Wyman Hill Rd | 139 | Wyman Hill Rd | Rumford | 40 | RUMFORD | 447D2 | 447T4 | 12.47 | 9310-L0187-5020-0151-ED00051 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2023-05-16 | 2023-05-23 | 2023-05-12 | 2023-05-18 | 2025-08-05 | 2025-08-08 | 2025-08-19 | 2025-08-12 | 2025-08-13 | 2025-08-13 | 2025-08-27 |  |  | 2025-08-27 |  |  | CS | 2025-08-27 | [6 empty] | CS |  |  | 2025-09-02 | [7 empty] | 2025-09-02 |  |  |  | 2025-09-02 | [8 empty] | 2025-09-09 | [8 empty] | 2025-09-09 | [11 empty] | 2025-11-13 | [6 empty] | 2025-11-13 | [8 empty] | 2025-11-13 | [8 empty] | 2025-11-20 | [8 empty] | 2025-11-21 | [7 empty] | 2025-11-21 | [18 empty] | 4492761 | 2025-11-13 |  |  | 2025-12-15 | [17 empty] | 0 |  |  |  | Q4 2026 | [15 empty] | TRUE | FALSE |  | 0 | 0 | 1900 | 1900 | 1900
816 |  | Eben Snow | Brent Brooks | 2023-05-10 | 2023-06-16 | Wthdw | RQP-2 | 2023-06-21 | wthdw | [26 empty] | 6 - BALD |  | 691D1 | 703 | Yes | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Jack Kenworthy | Walden Renewables | WALDEN SOLAR MAINE VI LLC | NS INTERCONNECTIONS | 2000124175 | 30015017178 | Solar | [5 empty] | 43.8078 | -70.7273 | 0 ME-113 | 0 | ME-113 | Baldwin | 236 | BALDWIN | 691D1 | 691T1 | 34.5 | 9310-L0371-0360-0016-ED00180 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2023-05-17 | 2023-05-24 | 2023-05-12 | 2023-05-22 | 2023-05-22 | 2023-05-24 | 2023-06-06 | 2023-05-24 | 2023-05-31 | 2023-06-01 | 2023-06-15 |  |  | 2023-06-22 |  |  | CS | [7 empty] | CS |  |  | 2023-06-22 | [11 empty] | 2023-06-23 | [8 empty] | 2023-06-01 | [8 empty] | 2023-06-30 | [11 empty] | 2023-09-05 | [6 empty] | 2023-09-05 | [8 empty] | 2023-09-06 | [8 empty] | 2023-09-12 | [8 empty] | 2023-09-14 | [7 empty] | 2023-09-14 | [7 empty] | 2023-10-05 |  | 2023-10-10 | 2023-12-12 | 2023-10-13 | [6 empty] | 475351 | 2023-09-05 |  |  | 2025-03-24 | 2021-07-13: 2023-10-16; 2021-07-13: 2023-10-16 | [9 empty] | 0 |  |  |  | Q4 2026 |  |  |  | Requested | [11 empty] | TRUE | FALSE |  | 2023-10-16 | 2023-10-16 | 2023 | 2023 | 2023
817 |  | Lanie Patterson | Brent Brooks | 2023-05-10 | [6 empty] | 2024-04-30 | L2_Bump |  | 2024-08-12 | wthdw |  | 2025-02-10 | studywaived |  | 2025-04-15 | wthdw | [13 empty] | 757 | 15 - MONM | 2 - MONM | 457D2 | 757 | Yes | EXECUTED | EXECUTED |  | Patrick Kay | Paddle Energy LLC | PE THURLOW BROOK SOLAR LLC | BLUE ROCK RD LEEDS. | 2000357889 | 30015009217 | Solar | 999 | 0.999 | 1451.88 |  |  | 44.2369 | -70.0754 | 31 Blue Rock Road | 31 | Blue Rock Road | Leeds | 506 | MONMOUTH | 457D2 | 457T2 | 12.47 | 9310-L0199-3740-0035-ED00020 |  | COST SHARING | COST SHARING (375,000) | 57652 | Yes | [6 empty] | 2023-05-17 | 2023-05-24 | 2023-05-16 | 2023-05-22 | 2024-02-13 | 2024-02-15 | 2024-02-28 | 2024-02-20 | 2024-02-22 | 2024-02-22 | 2024-03-07 |  |  | 2024-03-05 |  |  | CS | [7 empty] | CS |  |  | 2024-03-07 |  |  | 2024-05-01 | 2025-02-13 | 2025-04-15 |  |  | 2024-03-08 |  |  |  | 2024-03-13 |  |  | 2024-05-07 | 2025-03-05 | 2025-04-24 |  |  |  | 2024-03-15 |  |  | 2024-05-07 | 2025-03-05 | 2025-04-24 |  |  |  | 2024-03-15 |  |  | 2024-05-07 | 2025-03-05 | 2025-04-24 | [6 empty] | 2024-05-21 | [6 empty] | N/A |  |  | 2024-07-12 |  | 2025-06-04 | [6 empty] | 2024-07-12 |  | 2025-06-04 | [7 empty] | 2024-07-24 | [8 empty] | 2024-07-30 | [7 empty] | 2024-07-30 |  |  |  | 2025-06-25 |  | 2025-06-26 |  | 2025-06-27 | [6 empty] | 566701 | 2024-07-11 | 691935 | 2025-06-03 |  | 2021-07-13: 2025-06-27; 2021-07-13: 2025-06-30 | [9 empty] | -3 | [19 empty] | FALSE | FALSE |  | 2025-06-27 | 2025-06-27 | 2025 | 2025 | 2025
818 |  | Eben Snow | Brent Brooks | 2023-05-11 | [31 empty] | 3 - TURN | 1 - TURN | 454D1 | 69 |  | EXECUTED | EXECUTED |  | Nash Sultan | Bridge Energy | PE DINGLEY BROOK SOLAR LLC | 107 LORING HILL RD BUCKFIELD | 2000357911 | 30015009233 | Solar | 999 | 0.999 | 1399.56 |  |  | 44.2817 | -70.3614 | 107 Loring Hill Road | 107 | Loring Hill Road | Buckfield | 12 | TURNER | 454D1 | 454T1 | 12.47 | 9310-L0196-0780-0028-ED00005 |  | NOT IMPACTED | NOT IMPACTED |  | Yes | [6 empty] | 2023-05-18 | 2023-05-25 | 2023-05-16 | 2023-05-24 | 2023-05-24 | 2023-05-24 | 2023-06-08 | 2023-05-30 | 2023-06-01 | 2023-06-09 | 2022-06-14 |  |  | 2023-06-14 |  |  | CS | [7 empty] | CS |  |  | 2023-06-19 | [20 empty] | 2023-07-12 | [8 empty] | 2023-07-18 | [11 empty] | 2023-09-20 | [6 empty] | 2023-09-20 | [8 empty] | 2023-09-20 | [8 empty] | 2023-10-04 | [8 empty] | 2023-10-05 | [7 empty] | 2023-10-05 | [7 empty] | 2023-10-13 |  | 2023-10-26 | 2025-04-17 | 2023-11-14 | 2025-04-17 | [5 empty] | 409488 | 2023-09-20 | 197405 | 2023-10-26 |  | 2021-07-13: 2023-11-20; 2021-07-13: 2023-11-27; 2021-07-13: 2025-04-18; 2021-07-13: 2025-04-18 | [9 empty] | -7 |  |  |  | Q4 2025 | [15 empty] | TRUE | FALSE |  | 2023-11-20 | 2023-11-20 | 2023 | 2023 | 2023
819 |  | Lanie Patterson | Brent Brooks | 2023-05-11 | [6 empty] | 2024-04-30 | L2_Bump |  | 2024-08-12 | wthdw |  | 2025-02-10 | studywaived |  | 2025-04-15 | wthdw |  | 2025-10-13 | L2_Bump | [10 empty] | 817 | 16 - MONM |  | 457D2 | 817 | Yes | WITHDRAWN | WITHDRAWN |  | Patrick Kay | Paddle Energy LLC | PE WESTCOTT BROOK SOLAR LLC | 192 Academy Road | 2000357913 | 30015009258 | Solar | [5 empty] | 44.256 | -70.0347 | 192 Academy Road | 192 | Academy Road | Monmouth | 12 | MONMOUTH | 457D2 | 457T2 | 12.47 | 9310-L0199-3740-0001-ED00029 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2023-05-18 | 2023-05-25 | 2023-05-16 | 2023-05-24 | 2025-06-30 | 2025-07-02 | 2025-07-15 | 2025-07-08 | 2025-07-09 | 2025-07-09 | 2025-07-23 |  |  | 2025-07-16 |  |  | CS | 2025-07-16 | [6 empty] | CS |  |  | 2025-07-16 |  |  | 2025-10-13 | [8 empty] | 2025-07-31 |  |  | 2025-11-05 | [5 empty] | 2025-07-31 |  |  | 2025-11-05 | [5 empty] | 2025-07-31 |  |  | 2025-11-05 | [8 empty] | 2025-10-03 | [6 empty] | 2025-10-01 |  |  | 2025-12-16 | [5 empty] | 2025-10-07 |  |  | 2025-12-15 | [41 empty] | 1365326 | 2025-10-01 | 1365326 | 2026-12-16 | 2025-12-17 | [17 empty] | 0 |  |  |  | Q4 2026 | [15 empty] | TRUE | FALSE |  | 0 | 0 | 1900 | 1900 | 1900
820 |  | Govinda Neupane |  | 2023-05-15 | 2023-12-23 | wthdw | [29 empty] | 9 - SKNS | 2 - SKNS | 853D1 | 737 | Yes | EXECUTED | EXECUTED |  | Emma Plocienniik | Nexamp, Inc | Lakewood Renewables, LLC | 651 LAKEWOOD RD / MADISON ME 04950 | 2000433287 | 30016059310 | Solar | 999 | 0.999 | 1249.56 |  |  | 44.8217 | -69.7778 | 651 Lakewood Road | 651 | Lakewood Road | Madison | 123 | SKOWHEGAN NORTH SIDE | 853D1 | 853T1 | 12.47 | 9310-L0430-3510-0027-ED00226 |  | COST SHARING | COST SHARING (325,000) | 54348 | Yes | [6 empty] | 2023-05-22 | 2023-05-30 | 2023-05-22 | 2023-05-25 | 2023-05-25 | 2023-05-26 | 2023-06-09 | 2023-06-07 | 2023-06-08 | 2023-06-08 | 2023-06-23 |  |  | 2023-06-20 |  |  | CS | [7 empty] | CS |  |  | 2023-07-12 |  |  | 2024-07-11 |  |  |  |  | 2023-07-26 | [6 empty] | 2024-07-26 | [5 empty] | 2023-07-26 |  |  | 2024-07-26 | [5 empty] | 2023-07-26 |  |  | 2024-07-26 | [8 empty] | 2023-09-28 | [6 empty] | 2023-09-28 |  |  | 2024-09-30 | [5 empty] | 2023-09-28 |  |  | 2024-09-30 | [5 empty] | 2023-10-09 |  |  | 2024-10-07 | [5 empty] | 2023-10-11 |  |  | 2024-10-15 |  |  |  |  | 2023-10-11 |  |  | 2024-10-15 |  |  |  |  | 2023-10-30 |  | 2023-11-01 | 2024-10-18 | 2023-12-11 | 2024-10-25 | [5 empty] | 151708 | 2023-09-28 | 156334 | 2024-09-30 |  | 2021-07-13: 2023-12-13; 2021-07-13: 2023-12-13; 2021-07-13: 2024-10-31; 2021-07-13: 2024-10-31 | [9 empty] | 0 |  |  |  | Q2 2026 | [15 empty] | TRUE | FALSE |  | 2023-12-13 | 2023-12-13 | 2023 | 2023 | 2023
821 |  | Lanie Patterson | Brent Brooks | 2023-05-15 | [31 empty] | 6 - MCCO | 1 - MCCO | 237D1 | 733 |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED |  | Chris Bitely | REVISION ENERGY INC | Community Solar New England LLC | 1026 Webber Pond Rd Vassalboro | 2000202157 | 30016428127 | Solar | 999 | 0.999 | 1338.48 |  |  | 44.4312 | -69.662 | 1026 Webber Pond Rd | 1026 | Webber Pond Rd | Vassalboro | 8 | MCCOYS | 237D1 | 237T1 | 12.47 | 9310-L0067-6030-0060-ED00131 |  |  |  |  | Yes | [6 empty] | 2023-05-22 | 2023-05-30 | 2023-05-22 | 2023-05-26 | 2023-05-26 | 2023-05-31 | 2023-06-12 | 2023-06-07 | 2023-06-09 | 2023-06-09 | 2023-06-26 |  |  | 2023-07-13 |  |  | CS |  | RS | 2024-01-11 |  |  |  |  | CS |  |  | 2023-07-26 | [7 empty] | 2023-08-07 | 2024-01-02 |  |  | 2023-08-04 | 2024-01-22 | [7 empty] | 2023-07-13 | 2024-01-22 | [7 empty] | 2023-08-07 | 2024-01-22 | [10 empty] | 2023-10-13 | 2024-03-05 | [5 empty] | 2023-10-11 | 2024-03-05 | [7 empty] | 2023-10-11 | 2024-03-05 |  | 2024-03-05 | [5 empty] | 2023-10-23 |  |  | N/A | [5 empty] | 2023-10-26 | N/A |  | N/A |  |  |  |  | 2023-10-26 |  |  | N/A |  |  |  |  | 2024-03-15 |  | 2024-03-26 | 2024-12-11 | 2024-04-08 | 2024-12-12 | [5 empty] | 890018 | 2023-10-11 | 383618 | 2024-03-05 |  | 2021-07-13: 2024-04-09; 2021-07-13: 2024-04-09; 2021-07-13: 2024-12-13; 2021-07-13: 2024-12-13 | [9 empty] | 0 |  |  |  | Q4 2025 |  |  |  | Requested | [11 empty] | TRUE | FALSE |  | 2024-04-09 | 2024-04-09 | 2024 | 2024 | 2024
822 |  | Govinda Neupane |  | 2023-05-19 |  |  |  | 2023-09-08 | L2_Bump |  | 2023-10-03 | L2_bump |  | 2023-10-27 | wthdw |  | 2025-01-22 | L2_With |  | 2025-02-04 | wthdw | [14 empty] | 9 - CARM |  | 808D3 | 790 |  | WITHDRAWN | WITHDRAWN |  | Patrick Kay | Paddle Energy LLC | PE PERKINS BROOK SOLAR LLC | CLEMENES WAY CARMEL | 2000357910 | 30015009225 | Solar | [5 empty] | 44.8202 | -69.0196 | 17 Clements Way | 17 | Clements Way | Carmel | 25H | CARMEL | 808D3 | Carmel Substation Section 35 Tap | 12.47 | 9310-L0389-1020-0028-ED00034 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2023-05-26 | 2023-06-05 | 2023-05-25 | 2023-06-02 | 2025-02-04 | 2025-02-06 | 2025-02-19 | [127 empty] | 2025-02-11 | [17 empty] | 0 | [19 empty] | TRUE | FALSE |  | 0 | 0 | 1900 | 1900 | 1900
823 |  | Govinda Neupane |  | 2023-05-22 | 2023-06-05 | L2_Bump | [28 empty] | 782 | 6 - RUIP | 1 - RUIP | 466D1 | 782 | Yes | EXECUTED | EXECUTED |  | Ryan Peters | SOLAMERICA ENERGY HOLDINGS, INC | Oxford County ME S1, LLC | NS SHELL ACT 478 AUBURN RD PERU ME | 2000209571 | 30015535013 | Solar | 999 | 0.999 | 1311 |  |  | 44.5152 | -70.4186 | 478 Auburn Road | 478 | Auburn Road | Peru | 118 | RUMFORD INDUSTRIAL PARK | 466D1 | 466T1 | 34.5 | 9310-L0205-4610-0005-ED00030 |  | NOT IMPACTED | NOT IMPACTED |  | Yes | [6 empty] | 2023-05-30 | 2023-06-06 | 2023-05-26 | 2023-06-05 | 2023-10-23 | 2023-10-24 | 2023-11-07 | 2023-10-24 | 2023-11-03 | 2023-11-03 | 2023-11-20 |  |  | 2023-11-07 |  |  | CS | [7 empty] | CS |  |  | 2023-11-09 |  |  | 2023-11-09 |  |  |  |  | 2023-12-14 |  |  |  | 2023-12-07 | [8 empty] | 2023-12-14 | [8 empty] | 2023-12-20 | [11 empty] | 2024-02-27 | [6 empty] | 2024-02-27 | [8 empty] | 2024-02-27 | [8 empty] | 2024-03-05 | [8 empty] | 2024-03-08 | [7 empty] | 2024-03-08 | [7 empty] | 2024-05-31 |  | 2024-05-31 |  | 2024-06-28 | [6 empty] | 145351 | 2024-02-26 |  |  |  | 2021-07-13: 2024-07-01; 2021-07-13: 2024-07-01 | [9 empty] | 0 |  |  |  | Q4 2025 |  |  |  | Requested | [11 empty] | TRUE | FALSE |  | 2024-07-01 | 2024-07-01 | 2024 | 2024 | 2024
824 |  | Ben Brooks | Anthony Boucher | 2023-05-24 | [9 empty] | 2023-09-06 | L2_Bump |  | 2024-01-18 | L2_Bump | [17 empty] | 6 - PAST |  | 239D7 | 780 |  | WITHDRAWN | WITHDRAWN |  | Santiago Quijano | Bluewave MA, LLC | BLUEWAVE ORIGINATION LLC | 60 Merrill Dr Rockland | 2000310625 | 30014822107 | Solar/Battery | [5 empty] | 44.0856 | -69.1257 | 60 Merrill Dr | 60 | Merrill Dr | Rockland | 3.1 | PARK STREET | 239D7 | 239T2 | 12.47 | 9310-L0071-4970-0084-ED00013 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2023-06-01 | 2023-06-08 | 2023-05-31 | 2023-06-07 | 2024-06-12 | 2024-06-14 | 2024-06-27 | [127 empty] | 2024-06-20 | [17 empty] | 0 | [19 empty] | TRUE | FALSE |  | 0 | 0 | 1900 | 1900 | 1900
825 |  | Ben Brooks | Anthony Boucher | 2023-06-02 | [9 empty] | 2023-09-06 | L2_Bump |  | 2024-01-18 | L2_Bump |  | 2024-06-20 | wthdw | [14 empty] | 7 - PAST |  | 239D7 | 824 |  | WITHDRAWN | WITHDRAWN |  | Santiago Quijano | Bluewave MA, LLC | BLUEWAVE ORIGINATION LLC | 400 limerock st rockland me | 2000310625 | 30015089458 | Solar/DC BESS | [5 empty] | 44.1058 | -69.1347 | 400 Limerock St | 400 | Limerock St | Rockland | 3H | PARK STREET | 239D7 | 239T2 | 12.47 | 9310-L0071-4970-0045-ED00004 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2023-06-09 | 2023-06-16 | 2023-06-07 | 2023-06-16 | 2024-06-20 | 2024-06-24 | 2024-07-05 | [127 empty] | 2024-06-24 | [17 empty] | 0 | [19 empty] | TRUE | FALSE |  | 0 | 0 | 1900 | 1900 | 1900
826 |  | Govinda Neupane |  | 2023-06-05 | [31 empty] | 15 - ATHN |  | 827D1 | 697 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Corwin Lavoie | Nexamp, Inc | NEXAMP SOLAR LLC | 13 EATON CORNER RD ATHENS | 2000114877 | 30015094003 | Solar | [5 empty] | 44.926 | -69.6792 | 13 Eaton Corner Road | 13 | Eaton Corner Road | Athens | 3.2 | ATHENS | 827D1 | 827T1 | 12.47 | 9310-L0411-0200-0001-ED00020 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2023-06-12 | 2023-06-20 | 2023-06-12 | 2023-06-20 | 2023-06-20 | 2023-06-23 | 2023-07-05 | 2023-06-23 | 2023-06-29 | 2023-06-29 | 2023-07-14 |  |  | 2023-07-10 |  |  | CS | [7 empty] | CS |  |  | 2023-07-10 | [7 empty] | 2023-08-02 |  |  |  | 2023-07-24 | [8 empty] | 2023-06-24 | [8 empty] | 2023-08-02 | [11 empty] | 2023-10-05 | [6 empty] | 2023-10-05 | [8 empty] | 2023-10-05 | [8 empty] | 2023-11-16 | [8 empty] | 2023-10-13 | [7 empty] | 2023-10-13 | [7 empty] | 2023-11-03 |  | 2023-11-16 |  | 2023-12-12 | [6 empty] | 504024 | 2023-10-06 | 487524 | 2023-11-09 | 2024-06-28 | 2021-07-13: 2023-12-28; 2021-07-13: 2023-12-28 | [9 empty] | 0 | [7 empty] | Requested | [11 empty] | TRUE | FALSE |  | 2023-12-28 | 2023-12-28 | 2023 | 2023 | 2023
827 |  | Lanie Patterson | Brent Brooks | 2023-06-12 | [6 empty] | 2024-04-30 | L2_Bump |  | 2024-08-12 | wthdw |  | 2025-02-10 | studywaived |  | 2025-04-15 | wthdw |  | 2025-10-13 | L2_Bump | [10 empty] | 819 | 17 - MONM |  | 457D3 | 819 | Yes | WITHDRAWN | WITHDRAWN |  | Patrick Kay | Paddle Energy LLC | PE QUAKER BROOK SOLAR LLC | 136 ROUTE 126 MONMOUTH | 2000357919 | 30015009290 | Solar | [5 empty] | 44.1859 | -69.9826 | 136 Route 126 | 136 | Route 126 | Monmouth | 516H | MONMOUTH | 457D3 | 457T2 | 12.47 | 9310-L0200-3740-0031-ED00067 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2023-06-20 | 2023-06-27 | 2023-06-20 | 2023-06-27 | 2025-12-17 | 2025-12-18 | 2025-01-02 | 2025-12-22 | 2025-12-29 | 2025-12-29 | 2026-01-13 |  |  | 2026-01-08 |  |  | CS | 2026-01-08 | [6 empty] | CS |  |  | 2026-01-08 | [7 empty] | 2026-01-20 |  |  |  | 2026-01-16 | [8 empty] | 2026-01-21 | [8 empty] | 2026-01-21 | [11 empty] | 2026-03-26 | [6 empty] | 2026-03-20 | [8 empty] | 2026-03-20 | [44 empty] | 241428 | 2026-03-20 |  |  | 2026-04-01 | [17 empty] | 0 |  |  |  | Q4 2026 | [15 empty] | TRUE | FALSE |  | 0 | 0 | 1900 | 1900 | 1900
828 |  |  | Kristofer Coleman | 2023-06-15 | 2024-02-26 | wthdw |  | 2024-06-28 | L2_Bump | [26 empty] | 3 - BRWE |  | 213D3 | 505 |  | WITHDRAWN | WITHDRAWN |  | Emma Plocienniik | Nexamp, Inc | HILL SIDE SOLAR LLC | 135 HILL SIDE RD BRUNSWICK | 2000366065 | 30015119081 | Solar | [5 empty] | 43.9071 | -70.0253 | 133 Hillside Road | 133 | Hillside Road | Brunswick | 23 | BRUNSWICK WEST SIDE | 213D3 | 249T1 | 12.47 | 9310-L0032-0770-0251-ED00021 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2023-06-23 | 2023-06-30 | 2023-06-22 | 2023-06-30 | 2023-06-30 | 2023-07-06 | 2023-07-17 | 2023-07-12 | 2023-07-12 | 2023-07-13 | 2023-07-27 |  |  | 2023-07-19 |  |  | CS | [7 empty] | CS |  |  | 2023-07-20 |  |  |  | 2024-07-05 | 2024-08-09 | [6 empty] | 2023-08-04 |  |  | 2024-04-22 | 2024-08-01 | N/A | [6 empty] | 2024-04-22 | 2024-08-01 | 2024-09-03 |  |  |  | 2023-08-11 |  |  | 2024-04-22 | 2024-08-01 | 2024-09-03 | [6 empty] | 2023-10-19 | [6 empty] | 2023-10-20 |  |  | 2024-06-25 |  | 2024-11-01 |  |  |  | 2024-01-04 |  |  | 2024-06-25 |  | 2024-11-01 |  |  |  | 2023-01-15 |  |  | N/A | [5 empty] | 2024-01-19 |  |  | N/A |  | 2024-11-22 |  |  | 2024-01-19 |  |  | N/A |  | 2024-11-22 |  |  | 2024-02-12 |  | 2024-02-13 | [8 empty] | 977478 | 2023-10-20 | 996957 | 2024-06-24 | 2025-01-16 | [17 empty] | 0 | [19 empty] | TRUE | FALSE |  | 0 | 0 | 1900 | 1900 | 1900
829 |  | Lanie Patterson | Brent Brooks | 2023-06-15 | 2023-10-19 | wthdw | [29 empty] | 6 - RICH | 1 - RICH | 240D1 | 671 | Yes | EXECUTED | EXECUTED |  | Tyler William Perkins | Nexamp, Inc | Richmond Renewables, LLC | 590 Lincoln St, Richmond | 2000114877 | 30016065168 | Solar | 999 | 0.999 | 1375.92 |  |  | 44.1237 | -69.8194 | 590 Lincoln Street | 590 | Lincoln Street | Richmond | 10 | RICHMOND | 240D1 | 240T1 | 12.47 | 9310-L0074-4940-0067-ED00002 |  | COST SHARING | COST SHARING (325,000) | 118107 | Yes | [6 empty] | 2023-06-23 | 2023-06-30 | 2023-06-22 | 2023-06-30 | 2023-06-30 | 2023-07-06 | 2023-07-17 | 2023-07-25 | 2023-07-25 | 2023-07-25 | 2023-08-08 |  |  | 2023-08-03 |  |  | CS | [7 empty] | CS |  |  | 2023-08-03 |  |  | 2023-11-09 |  |  |  |  | 2023-08-22 |  |  |  | 2023-08-16 |  |  | 2023-11-10 | [8 empty] | 2023-11-15 | [5 empty] | 2023-08-23 |  |  | 2023-11-20 | [8 empty] | 2023-10-27 | [6 empty] | 2023-10-25 |  |  | 2023-01-05 | [5 empty] | 2023-10-25 |  |  | 2023-01-11 | [5 empty] | 2023-11-07 |  |  | 2024-01-15 | [8 empty] | 2024-01-19 | [7 empty] | 2024-01-19 |  |  |  |  | 2024-01-30 |  | 2024-02-13 | 2024-07-17 | 2024-02-14 | 2024-07-23 | [5 empty] | 491126 | 2023-10-25 | 491117 | 2024-01-05 |  | 2021-07-13: 2024-02-15; 2021-07-13: 2024-02-27; 2021-07-13: 2024-07-25; 2021-07-13: 2024-07-25 | [9 empty] | -12 |  |  |  | Q1 2026 |  |  |  | Requested | [11 empty] | TRUE | FALSE |  | 2024-02-15 | 2024-02-15 | 2024 | 2024 | 2024
830 |  | Lanie Patterson | Brent Brooks | 2023-06-20 | 2023-10-19 | wthdw | [29 empty] | 7 - RICH |  | 240D1 | 829 |  | WITHDRAWN | WITHDRAWN |  | Tyler William Perkins | Nexamp, Inc | NEXAMP SOLAR LLC | 590 Lincoln Street | 2000114877 | 30015132969 | Solar | [5 empty] | 44.1159 | -69.8337 | 590 Lincoln Street | 590 | Lincoln Street | Richmond | 9 | RICHMOND | 240D1 | 240T1 | 12.47 | 9310-L0074-4940-0067-ED00179 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2023-06-27 | 2023-07-05 | 2023-06-26 | 2023-07-03 | [126 empty] | n/a | n/a | n/a | n/a | 2023-10-23 | [17 empty] | 0 | [19 empty] | TRUE | FALSE |  | 0 | 0 | 1900 | 1900 | 1900
831 |  |  | KRISTOFER COLEMAN | 2023-06-20 | [31 empty] | 7 - LSFA |  | 232D1 | 712 |  | WITHDRAWN | WITHDRAWN |  | Tyler William Perkins | Nexamp, Inc | NEXAMP SOLAR LLC | 280 BOWDOINHAM RD / LISBON | 2000114877 | 30015132951 | Solar | [5 empty] | 44.0408 | -70.0386 | 280 Bowdoinham Road | 280 | Bowdoinham Road | Lisbon | 5 | LISBON FALLS | 232D1 | 232T1 | 12.47 | 9310-L0061-3310-0148-ED00066 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2023-06-27 | 2023-07-05 | 2023-06-27 | 2023-07-03 | 2024-05-28 |  | 2024-06-11 | [127 empty] | 2024-06-10 | [17 empty] | 0 | [19 empty] | TRUE | FALSE |  | 0 | 0 | 1900 | 1900 | 1900
832 |  | Eben Snow | Brent Brooks | 2023-07-05 | [6 empty] | 2025-03-25 | wthdw | [23 empty] | 7 - BALD |  | 691D1 | 816 | Yes | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Andrew Kellar | NHSOLARGARDEN.COM, LLC | SEBAGO ROAD SOLAR LLC | 6 Carl Burnell Rd, Baldwin | 2000193759 | 30012816044 | Solar | [5 empty] | 43.8437 | -70.6622 | 6 Burnell Rd | 6 | Burnell Rd | Baldwin | 115 | BALDWIN | 691D1 | 691T1 | 12.47 | 9310-L0371-0365-0010-ED00005 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2023-07-12 | 2023-07-19 | 2023-07-10 | 2023-07-19 | 2023-10-16 | 2023-10-17 | 2023-10-30 | 2023-10-17 | 2023-10-19 | 2023-10-19 | 2023-11-02 |  |  | 2023-10-19 |  |  | CS | [7 empty] | CS |  |  | 2023-10-23 | [7 empty] | 2023-11-15 |  |  |  | 2023-11-01 | [8 empty] | 2023-11-15 | [8 empty] | 2023-11-15 | [11 empty] | 2024-01-24 | [6 empty] | 2024-01-25 | [8 empty] | 2024-01-25 | [8 empty] | N/A | [8 empty] | N/A | [7 empty] | N/A | [7 empty] | 2024-02-20 |  | 2024-02-20 |  | 2024-04-12 | [6 empty] | 460264 | 2024-01-24 |  |  | 2025-03-26 | 2021-07-13: 2024-04-23; 2021-07-13: 2024-04-23 | [9 empty] | 0 |  |  |  | Q4 2024 | [15 empty] | TRUE | FALSE |  | 2024-04-23 | 2024-04-23 | 2024 | 2024 | 2024
833 |  | Govinda Neupane |  | 2023-07-07 |  |  |  | 2023-09-08 | L2_Bump |  | 2023-10-03 | L2_bump |  | 2023-10-27 | wthdw |  | 2025-01-22 | L2_With |  | 2025-02-04 | wthdw | [14 empty] | 10 - CARM |  | 808D3 | 822 |  | WITHDRAWN | WITHDRAWN |  | Patrick Kay | Paddle Energy LLC | PE EINSTEIN LLC | HORSEBACK RD CARMEL | 2000366278 | 30015122507 | Solar | [5 empty] | 44.8289 | -69.0015 | 41 Hayward Road | 41 | Hayward Road | Carmel | 6 | CARMEL | 808D3 | 808T1 | 12.47 | 9310-L0506-1020-0009-ED00039 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2023-07-14 | 2023-07-21 | 2023-07-12 | 2023-07-21 | [130 empty] | 2025-02-11 | [17 empty] | 0 | [19 empty] | TRUE | FALSE |  | 0 | 0 | 1900 | 1900 | 1900
834 |  | Eben Snow | Brent Brooks | 2023-07-20 | 2024-09-30 | wthdw | [29 empty] | 5 - FRYT | 1 - FRYT | 405D1 | 708 | Yes | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED |  | Tyler William Perkins | Nexamp, Inc | Lovell Road Renewables, LLC | LOVELL RD, FRYEBURG | 2000406536 | 30015658526 | Solar | 999 | 0.999 | 1237.86 |  |  | 44.0729 | -70.945 | Lovell Road |  | Lovell Road | Fryeburg | 503 ½ | FRYEBURG TAP | 405D1 | 405T1 | 12.47/7.2 | 9310-L0116-2130-0050-ED00114 |  | NOT IMPACTED | NOT IMPACTED |  | Yes | [6 empty] | 2023-07-27 | 2023-08-03 | 2023-07-26 | 2023-08-02 | 2023-08-02 | 2023-08-02 | 2023-08-16 | 2023-08-04 | 2023-08-10 | 2023-08-16 | 2023-08-24 |  |  | 2023-08-16 |  |  | CS | 2023-08-16 | [6 empty] | CS |  |  | 2023-08-22 |  |  | 2024-10-02 |  |  |  | 2024-10-16 |  |  |  |  | 2023-08-28 |  |  | 2024-10-17 | [5 empty] | 2023-08-29 |  |  | 2024-10-17 | [5 empty] | 2023-09-05 |  |  | 2024-10-22 | [8 empty] | 2023-11-08 | [6 empty] | 2023-11-08 |  |  | 2024-12-19 | [5 empty] | 2023-11-08 |  |  | 2024-11-19 | [5 empty] | 2023-11-08 |  |  | 2025-01-06 | [5 empty] | 2023-11-14 |  |  | 2024-01-06 |  |  |  |  | 2023-11-14 |  |  | 2024-01-06 |  |  |  |  | 2023-11-28 |  | 2023-12-02 | 2025-01-08 | 2023-12-06 | 2025-01-09 | [5 empty] | 660713 | 2023-11-08 | 393874 | 2024-12-19 |  | 2021-07-13: 2023-12-06; 2021-07-13: 2023-12-19; 2021-07-13: 2025-01-10; 2021-07-13: 2025-01-10 | [9 empty] | -13 |  |  |  | Q4 2025 |  |  |  | Requested | [11 empty] | FALSE | FALSE |  | 2023-12-06 | 2023-12-06 | 2023 | 2023 | 2023
835 |  | Eben Snow | Brent Brooks | 2023-07-20 |  |  |  | 2023-01-05 | L2_Bump |  | 2025-01-06 | wthdw | [22 empty] | 587 | 9 - LEED |  | 471D1 | 587 | Yes | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Will Bliss | VC Renewables LLC | ELP Livermore Solar II, LLC | RT 108 LIVERMORE ME | 2000369087 | 30015157297 | Solar/Battery |  |  |  |  | 4999 | 44.3769 | -70.2578 | 73 Route 108 | 73 | Route 108 | Livermore | 6H | LEEDS | 471D1 | 471T1 | 34.5 | 9310-L0209-3345-0012-ED00133 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2023-07-27 | 2023-08-03 | 2023-07-26 | 2023-08-02 | 2023-08-02 | 2023-08-04 | 2023-08-16 | 2023-08-04 | 2023-08-10 | 2023-08-10 | 2023-08-24 |  |  | 2023-08-22 |  |  | CS | [7 empty] | CS |  |  | 2023-08-23 |  |  | 2025-06-13 | [8 empty] | 2023-09-07 |  |  | 2025-06-25 | [5 empty] | 2023-09-14 |  |  | 2025-06-25 | [5 empty] | 2023-09-15 |  |  | 2025-06-25 | [8 empty] | 2023-11-21 | [6 empty] | 2023-11-20 |  |  | 2025-08-28 | [5 empty] | 2023-11-21 |  |  | 2025-08-28 | [5 empty] | 2023-11-22 |  |  | 2025-09-16 | [5 empty] | 2023-12-06 | [7 empty] | 2023-12-06 | [7 empty] | 2023-12-07 |  | 2023-12-08 | 2025-10-10 | 2024-01-03 | [6 empty] | 378870 | 2023-11-20 | 544480 | 2025-08-28 | 2025-11-25 | 2021-07-13: 2024-01-04; 2021-07-13: 2024-01-04 | [9 empty] | 0 |  |  |  | Q1 2026 |  |  |  | REQUESTED | [11 empty] | TRUE | FALSE |  | 2024-01-04 | 2024-01-04 | 2024 | 2024 | 2024
836 |  | Govinda Neupane |  | 2023-07-20 | [31 empty] | 6 - ANSO |  | 801D1 | 721 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Tyler William Perkins | Nexamp, Inc | NEXAMP SOLAR LLC | 52 LYNES RD STARK | 2000114877 | 30012963903 | Solar | [5 empty] | 44.7486 | -69.906 | Madison Rd |  | Madison Rd | Starks | 014 | ANSON | 801D1 | 801T1 | 12.47 | 9310-L0379-5510-0017-ED00007 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2023-07-27 | 2023-08-03 | 2023-07-26 | 2023-08-02 | 2023-08-02 | 2023-08-04 | 2023-08-16 | 2023-08-04 | 2023-08-10 | 2023-09-12 | 2023-08-24 |  |  | 2023-10-05 |  |  | CS | 2023-10-05 | [6 empty] | CS |  |  | 2023-10-11 | [11 empty] | 2023-10-22 | [17 empty] | 2023-12-12 | [11 empty] | 2024-02-16 | [6 empty] | 2024-02-16 | [8 empty] | 2024-02-19 | [8 empty] | 2024-02-26 | [8 empty] | 2024-03-07 | [7 empty] | 2024-03-07 | [7 empty] | 2024-03-26 |  | 2024-03-27 |  | 2024-04-25 | [6 empty] | 1465565 | 2024-02-16 |  |  | 2024-12-16 | 2021-07-13: 2024-04-29; 2021-07-13: 2024-04-29 | [9 empty] | 0 | [19 empty] | TRUE | FALSE |  | 2024-04-29 | 2024-04-29 | 2024 | 2024 | 2024
837 |  | Govinda Neupane |  | 2023-07-20 | [31 empty] | 7 - ANSO |  | 801D1 | 836 |  | WITHDRAWN | WITHDRAWN |  | Tyler William Perkins | Nexamp, Inc | NEXAMP SOLAR LLC | MADISON RD/STARKS | 2000114877 | 30015211045 | Solar | [5 empty] | 44.7491 | -69.9065 | Madison Rd |  | Madison Rd | Starks | 015 | ANSON | 801D1 | 801T1 | 12.47 | 9310-L0379-5510-0017-ED00008 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2023-07-27 | 2023-08-03 | 2023-07-26 | 2023-08-04 | [126 empty] | n/a | n/a | n/a | n/a | 2023-11-28 | [17 empty] | 0 | [19 empty] | TRUE | FALSE |  | 0 | 0 | 1900 | 1900 | 1900
838 |  | Lanie Patterson | Brent Brooks | 2023-07-24 | 2024-04-11 | L2_Bump |  | 2024-04-22 | wthdw |  | 2024-10-18 | L2_bump |  | 2024-11-06 | wthdw |  | 2024-12-16 | wthdw |  | 2025-08-26 | L2_Bump |  | 2025-12-30 | [11 empty] | 769 | 10 - NOAU |  | 272D2 | 769 | Yes | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Megan Wallis | Borealis Solar LLC | Borealis Solar LLC | 45 COMMERCE DR, AUGUSTA | 2000517702 | 30017288744 | Solar/DC BESS | [5 empty] | 44.3677 | -69.8026 | 45 Commerce Drive | 45 | Commerce Drive | Augusta | 2 | NORTH AUGUSTA | 272D2 | 272T1 | 12.47/7.2 | 9310-L0105-0240-0182-MH00017 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2023-07-31 | 2023-08-07 | 2023-07-28 | 2023-08-04 | 2023-09-06 | 2023-09-18 | 2023-09-20 | 2023-09-17 | 2023-09-21 | 2023-09-21 | 2023-10-03 |  |  | 2023-09-30 |  |  | CS | [7 empty] | CS |  |  | 2024-01-12 |  |  | 2024-09-30 | 2025-05-12 | 2025-09-05 | [6 empty] | 2024-01-16 |  |  |  | 2025-05-14 | 2025-10-28 | 2026-01-29 |  |  | 2024-02-12 |  |  |  | 2025-05-14 | 2025-10-31 | 2026-01-29 |  |  | 2024-02-12 |  |  |  | 2025-05-14 | 2025-10-31 | 2026-01-29 | [5 empty] | 2024-04-17 | [10 empty] | 2025-07-21 | 2025-12-15 | 2026-03-24 | [6 empty] | 2025-08-01 | 2025-12-15 | 2026-03-24 | [6 empty] | 2025-08-04 | [8 empty] | 2025-08-04 | [7 empty] | 2025-08-04 |  |  |  | 2025-12-15 |  | 2025-12-16 | 2026-06-03 | 2025-12-16 | 2026-07-21 | [5 empty] | 320337 | 2025-07-21 | 491094 | 2026-03-24 | 2026-08-10 | 2021-07-13: 2025-12-16; 2021-07-13: 2025-12-16; 2021-07-13: 2026-07-27; 2021-07-13: 2026-07-27 | [9 empty] | 0 |  |  |  | Q4 2024 |  |  |  | 10301245789 | [11 empty] | FALSE | FALSE |  | 2025-12-16 | 2025-12-16 | 2025 | 2025 | 2025
839 |  | Govinda Neupane |  | 2023-07-26 | [12 empty] | 2023-10-05 | L2_Bump | RQP-3 | 2024-10-14 | wthdw |  | 2024-10-15 | wthdw |  | 2024-12-13 | Wthdw |  | 2025-01-22 | L2_with |  |  |  | 9 - STUR | 647 | 17 - STUR |  | 858D1A | 647 | Yes | WITHDRAWN | WITHDRAWN |  | Angela Plummer | SOLAMERICA ENERGY LLC | SOLAMERICA ENERGY LLC | 306 Farmington Rd, Strong | 2000209571 | 30015332031 | Solar | [5 empty] | 44.7814 | -70.2276 | 306 Farmington Rd | 306 | Farmington Rd | Strong | 74 | STURTEVANT | 858D1A | 858T1 | 34.5/19.9 kV | 9310-L0437-5580-0008-ED00222 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2023-08-02 | 2023-08-09 | 2023-08-02 | 2023-08-08 | 2024-10-15 | 2025-10-15 | 2024-10-29 | 2024-10-16 | 2024-10-23 | 2024-10-23 | 2024-11-06 | 2024-11-06 | 2025-05-02 |  |  |  | FS | 2024-11-06 | IS | 2025-05-02 |  |  |  |  | FS | 2025-02-13 | 2025-05-05 | [7 empty] | 2024-11-12 | 2025-05-05 |  |  | 2025-02-26 | 2025-06-10 | [6 empty] | 2025-02-26 | 2025-06-10 | [7 empty] | 2025-02-26 | 2025-06-10 | [10 empty] | 2025-04-02 | 2025-07-24 | [5 empty] | 2025-04-02 | 2025-07-24 | [7 empty] | 2025-04-02 | 2025-07-25 | [7 empty] | 2025-04-03 | N/A | [7 empty] | 2025-04-09 | N/A | [6 empty] | 2025-04-09 | N/A | [8 empty] | 2025-08-05 |  | 2025-08-18 | [8 empty] | 929562 | 2025-07-24 |  |  | 2025-08-21 | [17 empty] | 0 |  |  |  | Q3 2025 | [15 empty] | FALSE | FALSE |  | 0 | 0 | 1900 | 1900 | 1900
840 |  | Marshall Ripley | Rick Duperre | 2023-08-02 | [31 empty] | 8 -GRAY |  | 416D3 | 811 |  | WITHDRAWN | WITHDRAWN |  | Santiago Quijano | BLUEWAVE ORIGINATION LLC | BLUEWAVE ORIGINATION LLC | 116 HUNTINGTON AVE, STE 601 / BOSTON MA 02116-5749 | 2000310625 | 30015227371 | Solar | [5 empty] | 43.7956 | 70.3098 | 44 Gray Rd | 44 | Gray Rd | Gray | 35 | GRAY | 416D3 | 416T1 | 12.47 | 9310-L0235-1280-0026-ED00035 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2023-08-09 | 2023-08-16 | 2023-08-08 | 2023-08-16 | 2024-05-28 | 2024-05-28 | 2024-06-11 | 2024-05-28 | 2024-05-31 | 2024-05-31 | 2024-06-14 |  |  | 2024-06-10 |  |  | CS | 2024-06-10 | [6 empty] | CS |  |  | 2024-06-11 | [7 empty] | 2024-07-08 |  |  |  | 2024-06-26 | [8 empty] | 2024-07-08 | [8 empty] | 2024-07-08 | [11 empty] | 2024-09-10 | [6 empty] | 2024-09-09 | [8 empty] | 2024-09-09 | [8 empty] | 2024-09-18 | [8 empty] | 2024-09-25 | [7 empty] | 2024-09-25 | [18 empty] | 774596 | 2024-09-06 |  |  | 2024-10-21 | [17 empty] | 0 | [19 empty] | TRUE | FALSE |  | 0 | 0 | 1900 | 1900 | 1900
841 |  | Govinda Neupane |  | 2023-08-09 | [31 empty] | 3 - LOMS | 1 - LOMS | 429D1 | 704 |  | EXECUTED | EXECUTED |  | Corwin Lavoie | Nexamp, Inc | Bethel Renewables LLC | 57 Paris Rd, Bethel | 2000432183 | 30016041870 | Solar | 999 | 0.999 | 1264.77 |  |  | 44.408 | -70.708 | 57 Paris Rd | 57 | Paris Rd | Bethel | 7 | LOCKES MILLS | 429D1 | 429T1 | 12.47/7.2 | 9310-L0163-0485-0011-ED00112 |  |  |  |  | Yes | [6 empty] | 2023-08-16 | 2023-08-23 | 2023-08-15 | 2023-08-23 | 2023-08-23 | 2023-08-23 | 2023-09-07 | 2023-08-29 | 2023-09-06 | 2023-09-07 | 2023-09-20 |  |  | 2023-09-20 |  |  | CS | [7 empty] | CS |  |  | 2023-09-21 | [11 empty] | 2023-10-02 | [8 empty] | 2023-10-02 | [8 empty] | 2023-10-06 | [11 empty] | 2023-12-14 | [6 empty] | 2023-12-14 | [8 empty] | 2023-12-14 | [8 empty] | 2024-01-09 | [8 empty] | 2024-01-16 | [7 empty] | 2024-01-16 | [7 empty] | 2024-01-16 |  | 2024-01-23 | 2024-07-02 | 2024-01-26 | 2024-07-07 | [5 empty] | 251248 | 2023-12-14 |  |  |  | 2021-07-13: 2024-02-14; 2021-07-13: 2024-02-14; 2021-07-13: 2024-07-16; 2021-07-13: 2024-07-16 | [9 empty] | 0 |  |  |  | Q1 2026 |  |  |  | Requested | [11 empty] | TRUE | FALSE |  | 2024-02-14 | 2024-02-14 | 2024 | 2024 | 2024
842 |  | Govinda Neupane |  | 2023-08-10 | [31 empty] | 4 - LOMS |  | 429D1 | 841 |  | WITHDRAWN | WITHDRAWN |  | Corwin Lavoie | Nexamp, Inc | NEXAMP SOLAR LLC | 57 Paris Rd Bethel #2 | 2000114877 | 30015276881 | Solar | [5 empty] | 44.408 | 70.708 | 57 Paris Rd | 57 | Paris Rd | Bethel | 8 | LOCKES MILLS | 429D1 | 429T1 | 12.47/7.2 | 9310-L0163-0485-0011-ED00131 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2023-08-17 | 2023-08-24 | 2023-08-15 | 2023-08-23 | [130 empty] | 2023-11-16 | [17 empty] | 0 | [19 empty] | TRUE | FALSE |  | 0 | 0 | 1900 | 1900 | 1900
843 |  | Eben Snow | Brent Brooks | 2023-08-10 | 2023-12-20 | wthdw | [29 empty] | 5 - BRID |  | 406D1 | 802 |  | WITHDRAWN | WITHDRAWN |  | Patrick Kay | Paddle Energy LLC | PE FRANKLIN LLC | 456 PORTLAND RD BRIDGTON | 2000366279 | 30015122515 | Solar | [5 empty] | 44.0266 | -70.6883 | 456 Portland Rd | 456 | Portland Rd | Bridgton | 63 | BRIDGTON | 406D2 | 406T1 | 12.47/7.2 | 9310-L0119-0690-0121-ED00119 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2023-08-17 | 2023-08-24 | 2023-08-15 | 2023-08-24 | 2023-12-20 | 2023-12-26 | 2024-01-05 | 2024-01-03 | 2024-01-11 | 2024-01-11 | 2023-01-26 |  |  | 2024-01-24 |  |  | CS | [7 empty] | CS |  |  | 2024-01-31 | [7 empty] | 2024-02-15 |  |  |  | 2024-02-06 | [8 empty] | 2024-02-15 | [8 empty] | 2024-02-16 | [11 empty] | 2024-04-23 | [6 empty] | 2024-04-25 | [8 empty] | 2024-04-25 | [44 empty] | 245900 | 2024-04-24 |  |  | 2024-05-07 | [17 empty] | #VALUE! | [19 empty] | TRUE | FALSE |  | 0 | 0 | 1900 | #VALUE! | #VALUE!
844 |  | Ben Brooks |  | 2023-08-23 | 2024-04-01 | wthdw | [29 empty] | 2 - BWST |  | 204D6 | 793 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Nathaniel Curtis | MIDCOAST SOLAR LLC | Bath Community Solar LLC | 333 HIGH ST BATH | 2000380490 | 30015840959 | Solar/Battery | [5 empty] | 43.898 | -69.82 | 333-357 High St. | 333-357 | High St. | Bath | 92 | WASHINGTON ST (BATH) | 204D6 | 34kV Bus No. 1 | 34.5 | 9310-L0017-0410-0083-ED00317 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2023-08-30 | 2023-09-07 | 2023-08-29 | 2023-09-06 | 2023-09-06 | 2023-09-18 | 2023-09-20 | 2023-09-19 | 2023-09-21 | 2023-09-21 | 2023-10-05 |  |  | 2023-09-21 |  |  | CS | [7 empty] | CS |  |  | 2023-09-22 |  |  | 2024-04-10 | [8 empty] | 2023-09-25 | [8 empty] | 2023-09-28 | [8 empty] | 2023-10-10 | [11 empty] | 2023-12-15 | [6 empty] | 2023-12-15 | [8 empty] | 2023-12-15 | [8 empty] | 2024-01-23 | [8 empty] | 2024-01-25 | [7 empty] | 2024-01-25 | [7 empty] | 2024-02-22 |  | 2024-02-22 |  | 2024-03-25 | [6 empty] | 388734 | 2023-12-15 |  |  | 2024-05-20 | 2021-07-13: 2024-03-27; 2021-07-13: 2024-03-27 | [9 empty] | 0 | [19 empty] | TRUE | FALSE |  | 2024-03-27 | 2024-03-27 | 2024 | 2024 | 2024
845 |  | Govinda Neupane |  | 2023-08-25 | [30 empty] | 823 | 7 - RUIP | 2 - RUIP | 466D1 | 823 |  | EXECUTED | EXECUTED |  | Corwin Lavoie | Nexamp, Inc | Greenwoods Renewables, LLC | 57 Greenwoods Rd Peru | 2000508111 | 30017141570 | Solar | 999 | 0.999 | 1249.56 |  |  | 44.4869 | -70.3851 | 57 Greenwoods Rd | 57 | Greenwoods Rd | Peru | 9 | RUMFORD INDUSTRIAL PARK | 466D1 | 466T1 | 34.5 | 9310-L0205-4610-0048-ED00038 |  | NOT IMPACTED | NOT IMPACTED |  | Yes | [6 empty] | 2023-09-01 | 2023-09-11 | 2023-08-31 | 2023-09-08 | 2024-07-01 | 2024-07-03 | 2024-07-16 | 2024-07-16 | 2024-07-18 | 2024-07-18 | 2024-08-01 |  |  | 2024-08-01 |  |  | CS | 2024-08-01 | [6 empty] | CS |  |  | 2024-08-07 | [7 empty] | 2024-07-26 |  |  |  | 2024-08-16 | [8 empty] | 2024-08-16 | [8 empty] | 2024-08-16 | [11 empty] | 2024-10-22 | [6 empty] | 2024-10-21 | [8 empty] | 2024-10-21 | [8 empty] | 2024-10-29 | [8 empty] | 2024-11-01 | [7 empty] | 2024-11-01 | [7 empty] | 2024-11-18 |  | 2024-11-18 | 2024-11-19 | 2024-11-19 | [6 empty] | 499108 | 2024-10-17 |  |  |  | 2021-07-13: 2024-11-20; 2021-07-13: 2024-11-20 | [9 empty] | 0 |  |  |  | Q4 2025 | [15 empty] | FALSE | FALSE |  | 2024-11-20 | 2024-11-20 | 2024 | 2024 | 2024
846 |  | Govinda Neupane |  | 2023-08-30 | [12 empty] | 2023-10-05 | L2_Bump |  | 2024-10-14 | wthdw |  | 2024-10-15 | wthdw |  | 2024-12-13 | Wthdw |  | 2025-01-22 | L2_with |  |  |  |  | 839 | 18 - STUR |  | 858D1A | 839 | Yes | WITHDRAWN | WITHDRAWN |  | Katie Kearney | SOLAMERICA ENERGY HOLDINGS, INC | SOLAMERICA ENERGY LLC | 259 Davis rd, Farmington | 2000209571 | 30015329706 | Solar | [5 empty] | 44.6624 | -70.1156 | 259 Davis Road | 259 | Davis Road | Farmington | 12 | STURTEVANT | 858D1A | 858T1 | 34.5 | 9310-L0437-2030-0043-ED00004 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2023-09-07 | 2023-09-14 | 2023-09-05 | 2023-09-12 | [130 empty] | 2025-08-01 | [17 empty] | 0 | [19 empty] | TRUE | FALSE |  | 0 | 0 | 1900 | 1900 | 1900
847 |  | Govinda Neupane |  | 2023-08-30 | 2023-12-23 | wthdw | [29 empty] | 10 - SKNS |  | 853D2 | 820 |  | WITHDRAWN | WITHDRAWN |  | Nicholas Mazuroski | BNRG MAINE LLC | BD SOLAR SKOWHEGAN LLC | transfer station drive skowhegan | 2000132131 | 30011910566 | Solar | [5 empty] | 44.7936 | -69.7165 | 29 Transfer Station Drive | 29 | Transfer Station Drive | Skowhegan | 9.2 | SKOWHEGAN NORTH SIDE | 853D2 | 853T1 | 12.47 | 9310-L0431-5330-0181-ED00087 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2023-09-07 | 2023-09-14 | 2023-09-05 | 2023-09-13 | 2024-10-31 |  | 2024-11-15 | [127 empty] | 2024-11-26 | [17 empty] | 0 | [19 empty] | TRUE | FALSE |  | 0 | 0 | 1900 | 1900 | 1900
848 |  |  | Anthony Boucher | 2023-09-05 | [31 empty] | 2 - MARO | 1 - MARO | 234D1 | 622 |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED |  | Alex Roberts-Pierel | REVISION ENERGY INC | Community Solar New England, LLC | 488 Manktown Rd, Waldoboro | 2000202157 | 30016633973 | Solar | 999 | 0.999 | 1338.48 |  |  | 44.1281 | -69.3079 | 488 Manktown Rd | 488 | Manktown Rd | Waldoboro | 20 | MANKTOWN ROAD | 234D1 | 234T1 | 12.47 | 9310-L0065-6130-0044-ED00022 |  |  |  |  | Yes | [6 empty] | 2023-09-12 | 2023-09-19 | 2023-09-07 | 2023-09-18 | 2023-09-18 |  | 2023-10-02 |  | N/A | N/A |  |  |  | 2023-09-26 |  |  | CS | [7 empty] | CS |  |  | 2023-09-26 | [11 empty] | 2023-10-06 | [8 empty] | 2023-10-11 | [8 empty] | 2023-10-11 | [11 empty] | 2023-12-18 | [6 empty] | 2023-12-15 | [8 empty] | 2023-12-15 | [8 empty] | 2023-12-15 | [8 empty] | 2023-12-15 | [7 empty] | 2023-12-15 | [7 empty] | 2023-12-15 |  | 2023-12-20 | 2025-01-20 | 2023-12-20 | 2025-01-20 | [5 empty] | 251020 | 2023-12-15 |  |  |  | 2021-07-13: 2024-01-16; 2021-07-13: 2024-01-16; 2021-07-13: 2025-01-22; 2021-07-13: 2025-01-22 | [9 empty] | 0 |  |  |  | Q2 2025 | [15 empty] | TRUE | FALSE |  | 2024-01-16 | 2024-01-16 | 2024 | 2024 | 2024
849 |  | Eben Snow | Brent Brooks | 2023-09-26 | [31 empty] | 4 - TURN |  | 454D1 | 818 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Santiago Quijano | Bluewave MA, LLC | Nezinscot River, LLC | 3 RICKER HILL RD GARDINER ME | 2000310625 | 30015785162 | Solar | [5 empty] | 44.2666 | -70.2781 | 3 Ricker Hill Rd | 3 | Ricker Hill Rd | Turner | 13H | TURNER | 454D1 | 454T1 | 12.47 | 9310-L0196-5880-0162-ED00025 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2023-10-03 | 2023-10-11 | 2023-10-02 | 2023-10-06 | 2023-11-27 | 2023-12-06 | 2023-12-11 | 2023-12-07 | 2023-12-14 | 2023-12-14 | 2023-12-28 |  |  | 2023-12-15 |  |  | CS | [7 empty] | CS |  |  | 2023-12-22 | [7 empty] | 2024-01-10 |  |  |  | 2023-12-22 | [8 empty] | 2024-01-10 | [8 empty] | 2024-01-10 | [11 empty] | 2024-03-15 | [6 empty] | 2024-03-15 | [8 empty] | 2024-03-15 | [8 empty] | 2024-03-21 | [8 empty] | 2024-03-27 | [7 empty] | 2024-03-27 | [7 empty] | 2024-03-27 |  | 2024-03-28 |  | 2024-04-01 | [6 empty] | 419486 | 2024-03-14 |  |  | 2025-11-25 | 2021-07-13: 2024-04-15; 2021-07-13: 2024-04-17 | [9 empty] | -2 |  |  |  | Q4 2025 | [15 empty] | TRUE | FALSE |  | 2024-04-15 | 2024-04-15 | 2024 | 2024 | 2024
850 |  |  |  | 2023-09-28 | [31 empty] | 2 - THTP |  | 857D1 | 670 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Dylan Smith | DIRIGO DEVELOPMENT LLC | WHITETAIL SOLAR LLC | Carey Lane Solar Project | 2000387796 | 30015405068 | Solar | [5 empty] | 44.5228 | -69.3181 | 49 Carey Lane | 49 | Carey Lane | Freedom | 020 | THORNDIKE TAP | 857D1 | 857T1 | 34.5 | 9310-L0436-2093-0002-ED00021 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2023-10-05 | 2023-10-13 | 2023-10-02 | 2023-10-12 | 2023-10-12 | 2023-10-13 | 2023-10-26 | 2023-10-16 | 2023-10-18 | 2023-10-18 | 2023-11-01 |  |  | 2023-10-18 |  |  | CS | [7 empty] | CS |  |  | 2023-10-18 | [20 empty] | 2023-10-23 | [8 empty] | 2023-10-25 | [11 empty] | 2024-01-03 | [6 empty] | 2024-01-03 | [8 empty] | 2024-01-04 | [8 empty] | 2024-01-05 | [8 empty] | 2024-01-08 | [7 empty] | 2024-01-08 | [7 empty] | 2024-01-08 |  | 2024-01-10 |  | 2024-02-08 | [6 empty] | 167851 | 2024-02-02 |  |  | 2024-09-10 | 2021-07-13: 2024-02-09; 2021-07-13: 2024-02-12 | [9 empty] | -3 | [7 empty] | Requested | [11 empty] | TRUE | FALSE |  | 2024-02-09 | 2024-02-09 | 2024 | 2024 | 2024
851 |  |  |  | 2023-10-02 | 2023-10-13 | L2_Bump |  | 2023-04-08 | wthdw | [26 empty] | 6 - DAMS |  | 219D1 | 806 |  | WITHDRAWN | WITHDRAWN |  | Annalise Kukor | REVISION ENERGY INC | REVISION ENERGY INC | 342 ROUTE 1 DAMARISCOTTA | 2000038393 | 30015399154 | Solar | [5 empty] | 44.0615 | -69.4935 | 324 Route 1 | 324 | Route 1 | Damariscotta | 93 | DAMARISCOTTA MILLS | 219D1 | 219T1 | 12.47 | 9310-L0050-1520-0003-ED00158 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2023-10-10 | 2023-10-17 | 2023-10-05 | 2023-10-13 | [130 empty] | 2024-10-29 | [17 empty] | 0 | [19 empty] | TRUE | FALSE |  | 0 | 0 | 1900 | 1900 | 1900
852 |  | Eben Snow | Brent Brooks | 2023-10-17 | [6 empty] | 2024-05-10 | wthdw |  | 2024-10-21 | wthdw |  | 2024-10-30 | studywaived |  | 2024-12-18 | wthdw |  | 2025-04-16 | L2_Bump |  | 2025-06-11 | L2_Bump | [8 empty] | 11 - MEFA |  | 431D1 | 791 | Yes | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Jacob Freudenberger | Paddle Energy LLC | PE COPERNICUS LLC |  | 2000366303 | 30015122556 | Solar | [5 empty] | 44.068 | -70.3777 | 206 Poland Corner Road | 206 | Poland Corner Road | Poland | 142 | MECHANIC FALLS | 431D1 | 431T2 | 12.47 | 9310-L0165-4710-0060-ED00062 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2023-10-24 | 2023-10-31 | 2023-10-23 | 2023-10-30 | 2024-12-18 | 2024-12-20 | 2025-01-03 | 2024-12-23 | 2025-01-10 | 2025-01-10 | 2025-01-27 |  |  | 2025-01-27 |  |  | CS | 2025-01-27 | [6 empty] | CS |  |  | 2025-01-27 |  |  | 2025-04-16 | 2025-06-11 |  |  |  | 2025-02-06 |  |  |  | 2025-02-06 |  |  | 2025-04-24 | 2025-06-23 |  |  |  |  | 2025-02-06 |  |  | 2025-04-24 | 2025-06-23 |  |  |  |  | 2025-02-06 |  |  | 2025-04-24 | 2025-06-25 | [7 empty] | 2025-04-11 | [6 empty] | 2025-04-09 |  |  |  | 2025-08-28 |  |  |  |  | 2025-04-09 |  |  |  | 2025-08-28 |  |  |  |  | Waived 4/9/2025 | [8 empty] | N/A | [7 empty] | N/A | [7 empty] | 2025-04-09 |  | 2025-04-09 | 2025-09-15 | 2025-04-09 | 2025-09-16 | [5 empty] | 319892 | 2025-04-07 | 191458 | 2025-08-29 | 2026-04-01 | 2021-07-13: 2025-04-09; 2021-07-13: 2025-04-09; 2021-07-13: 2025-09-17; 2021-07-13: 2025-09-18 | [9 empty] | 0 |  |  |  | Q2 2025 | [15 empty] | TRUE | FALSE |  | 2025-04-09 | 2025-04-09 | 2025 | 2025 | 2025
853 |  | Lanie Patterson | Lanie Patterson | 2023-11-01 | [31 empty] | 6 - SOCH |  | 244D2 | 745 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Nathaniel Curtis | Midcoast Solar LLC | Midcoast Solar LLC | 24 Woodbury Lane, China | 2000380490 | 30015658526 | Solar/Battery | [5 empty] | 44.4067 | -69.5373 | 24 Woodbury Ln | 24 | Woodbury Ln | China | 741.02 | SOUTH CHINA | 244D2 | 244T2 | 12.47 | 9310-L0480-1150-0010-ED00158 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2023-11-08 | 2023-11-16 | 2023-11-07 | 2023-11-10 | 2023-11-13 | 2023-11-29 | 2023-11-29 | 2023-11-29 | 2023-12-07 | 2023-12-07 | 2023-12-21 |  |  | 2023-12-07 |  |  | CS | [7 empty] | CS |  |  | 2023-12-13 | [7 empty] | 2024-01-25 |  |  |  | 2024-01-04 | [8 empty] | 2024-01-25 | [8 empty] | 2024-01-25 | [11 empty] | 2024-03-29 | [6 empty] | 2024-03-29 | [8 empty] | 2024-04-01 | [8 empty] | 2024-04-15 | [8 empty] | 2024-04-15 | [7 empty] | 2024-04-15 | [7 empty] | 2024-05-07 |  | 2024-05-08 |  |  | 2024-06-24 | [5 empty] | 1260974.95 | 2024-03-29 |  |  | 2024-11-25 | 2021-07-13: 2024-06-26; 2021-07-13: 2024-06-28 | [9 empty] | -2 | [7 empty] | Requested | [11 empty] | TRUE | FALSE |  | 2024-06-26 | 2024-06-26 | 2024 | 2024 | 2024
854 |  |  | KRISTOFER COLEMAN | 2023-11-28 | 2025-03-10 | wthdw | [29 empty] | 2 - BANE | 1 - BANE | 206D1 | 662 | Yes | EXECUTED | EXECUTED |  | Alex Roberts-Pierel | REVISION ENERGY INC | CITY OF BATH | 11 DETRITUS DR / BATH ME 04530 | 2800357078 | 30015539163 | Solar | 650 | 0.65 | 807.3 |  |  | 43.94 | -69.822 | 11 Detritus Drive | 11 | Detritus Drive | Bath | 1 | BATH NORTH END | 206D1 | 206T1 | 12.47 | 9310-L0018-0410-0185-ED00001 |  | NOT IMPACTED | NOT IMPACTED |  | Yes | [6 empty] | 2023-12-05 | 2023-12-12 | 2023-12-05 | 2023-12-12 | 2023-12-12 | 2023-12-15 | 2023-12-27 | 2023-12-15 | 2024-01-16 | 2024-01-16 | 2024-01-30 |  |  | 2024-01-17 | 2024-04-26 |  | CS |  | RS | 2024-04-26 |  |  |  |  | CS |  |  | 2024-01-22 | 2024-04-26 |  | 2025-03-11 |  |  |  |  | 2024-01-31 | 2024-04-26 |  | 2025-05-07 | 2024-01-29 |  |  | 2025-03-24 | [5 empty] | 2024-01-31 | 2024-05-07 |  | 2025-03-25 | [5 empty] | 2024-01-31 | 2024-05-07 |  | 2025-03-25 | [8 empty] | 2024-04-04 | 2024-06-20 | [5 empty] | 2024-04-04 | 2024-06-19 |  | 2025-05-27 | [5 empty] | 2024-04-04 | 2024-06-19 |  | 2025-05-28 | [5 empty] | 2024-04-12 | 2024-07-08 | [7 empty] | 2024-04-12 | 2024-07-09 | [6 empty] | 2024-04-12 | 2024-07-09 | [6 empty] | 2024-07-29 |  | 2024-07-30 | 2025-06-10 | 2024-08-19 | 2025-07-10 | [5 empty] | 601592 | 2024-04-04 | 619647 | 2025-05-27 |  | 2021-07-13: 2024-08-20; 2021-07-13: 2024-08-23; 2021-07-13: 2025-07-14; 2021-07-13: 2025-07-14 | [9 empty] | -3 |  |  |  | Q3 2025 | [15 empty] | FALSE | FALSE |  | 2024-08-20 | 2024-08-20 | 2024 | 2024 | 2024
855 |  | Govinda Neupane |  | 2023-12-07 | [31 empty] | 6 - EMDE | 1 - EMDE | 868D1 | 687 |  | EXECUTED | EXECUTED |  | Tyler William Perkins | Nexamp, Inc | Embden Solar, LLC | Embden Solar, LLC | 2000430092 | 30016009836 | Solar | 999 | 0.999 | 1375.92‬ |  |  | 44.9273 | -69.8696 | 610 Kennebec River Rd | 610 | Kennebec River Rd | Embden | 61 | EMBDEN | 868D1 | 868T1 | 12.47 | 9310-L0452-1870-0034-ED00167 |  |  |  |  | Yes | [6 empty] | 2023-12-14 | 2023-12-21 | 2023-12-14 | 2023-12-21 | 2023-12-21 | 2023-12-29 | 2023-01-08 | 2023-01-15 | 2024-01-19 | 2024-01-19 | 2024-02-02 |  |  | 2024-01-19 |  |  | CS | [7 empty] | CS |  |  | 2024-02-05 | [7 empty] | 2024-02-05 |  |  |  | 2024-02-12 | [8 empty] | 2024-02-15 | [8 empty] | 2024-02-16 | [11 empty] | 2024-04-24 | [6 empty] | 2024-04-16 | [8 empty] | 2024-04-16 | [8 empty] | 2024-04-17 | [8 empty] | 2024-04-22 | [7 empty] | 2024-04-22 | [7 empty] | 2024-05-02 |  | 2024-05-02 | 2024-06-21 | 2024-05-09 | [6 empty] | 690456 | 2024-04-12 |  |  |  | 2021-07-13: 2024-05-13; 2021-07-13: 2024-05-22; 2021-07-13: 2024-07-01; 2021-07-13: 2024-07-01 | [9 empty] | -9 |  |  |  | Q1 2027 |  |  |  | Requested | [11 empty] | TRUE | FALSE |  | 2024-05-13 | 2024-05-13 | 2024 | 2024 | 2024
856 |  | Ben Brooks | KRISTOFER COLEMAN | 2023-12-11 |  |  |  | 2025-10-09 | wthdw | [26 empty] | 3 - FREE | 1 - FREE | 225D3 | 601 |  | EXECUTED | EXECUTED |  | Salman Ali | UGE USA INC | PROUT ROAD SOLAR LLC | 11 Prout Rd Freeport ME 04032 | 2000198765 | 30012877582 | Solar | 990 | 0.99 | 1.504 |  |  | 43.8782 | -70.0774 | 11 Prout St | 11 | Prout St | Freeport | 5 | FREEPORT | 225D3 | 225T2 | 12.47 | 9310-L0055-2110-0170-ED00082 |  |  |  |  | Yes | [6 empty] | 2023-12-18 | 2023-12-26 | 2023-12-18 | 2023-12-26 | 2023-06-10 | 2024-06-10 | 2024-06-25 | 2024-06-11 | 2024-06-12 | 2024-06-12 | 2024-06-27 |  |  | 2024-06-13 |  |  | CS | 2024-06-13 | [6 empty] | CS |  |  | 2024-06-17 | 2024-10-29 | [7 empty] | 2024-10-28 |  |  | 2024-07-01 | 2024-11-14 | [7 empty] | 2024-07-01 | 2024-11-14 | [7 empty] | 2024-07-03 | 2024-11-14 | [10 empty] | 2024-09-06 | 2024-12-31 | [5 empty] | 2024-09-05 | 2024-12-20 | [7 empty] | 2024-09-06 | 2024-12-23 | [7 empty] | 2024-09-17 | [8 empty] | 2024-09-19 | [7 empty] | 2024-09-19 | [7 empty] | 2024-01-09 |  | 2025-01-10 |  | 2025-01-22 | [6 empty] | 273298 | 2024-09-06 | 432500 | 2024-12-20 |  | 2021-07-13: 2025-01-23; 2021-07-13: 2025-01-23 | [9 empty] | 0 |  |  |  | Q3 2025 | [15 empty] | TRUE | FALSE |  | 2025-01-23 | 2025-01-23 | 2025 | 2025 | 2025
857 |  | Marshall Ripley | Rick Duperre | 2023-12-11 | 2024-03-14 | wthdw | [29 empty] | 8 - ELM |  | 620D4 | 840 |  | WITHDRAWN | WITHDRAWN |  | Allison Barbour | REVISION ENERGY INC | Yarmouth Water District | YWD SOLAR / 238 SWEETSER RD | 2800725910 | 30015573592 | Solar | [5 empty] | 43.8261 | -70.2262 | 238 Sweetser Road | 238 | 238 Sweetser Road | North Yarmouth | 11 | ELM STREET | 620D4 | 620T2 | 12.47 | 9310-L0238-4200-0034-ED00003 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2023-12-18 | 2023-12-26 | 2023-12-18 | 2023-12-26 | [130 empty] | 2024-04-10 | [17 empty] | 0 | [19 empty] | TRUE | FALSE |  | 0 | 0 | 1900 | 1900 | 1900
858 |  | Govinda Neupane |  | 2023-12-28 | [15 empty] | 2024-11-14 | wthdw | RQP-1 | 2024-12-16 | wthdw |  | 2024-11-19 | studywaived | [7 empty] | 723 | 10 - GUIL | 3 - GUIL | 821D1 | 723 |  | EXECUTED | EXECUTED |  | Kevin Price | KEY SOLAR LLC | 290 PARKMAN SOLAR LLC | 290 State Highway 150 / Parkman | 2000403367 | 30015617241 | Solar | 1500 | 1.5 | 2317 |  |  | 45.1508 | -69.4018 | 290 STATE HIGHWAY 150 | 290 | STATE HIGHWAY 150 | Parkman | 57.01 | GUILFORD | 821D1 | 821T1 | 12.47 | 9310-L0405-4520-0020-ED00130 |  |  |  |  | Yes | [6 empty] | 2024-01-05 | 2024-01-12 | 2024-01-05 | 2024-01-12 | 2025-04-08 | 2025-04-08 | 2025-04-23 | 2025-04-09 | 2025-04-15 | 2025-04-15 | 2025-04-30 |  |  | 2025-04-29 |  |  | CS | 2025-04-29 | [6 empty] | CS |  |  | 2025-04-30 | 2025-08-21 | [6 empty] | 2025-05-08 | 2025-08-21 |  |  | 2025-05-05 | 2025-09-17 | [7 empty] | 2025-05-08 | 2025-09-18 | [7 empty] | 2025-05-08 | 2025-09-18 | [10 empty] | 2025-07-15 | 2025-10-31 | [5 empty] | 2025-07-07 | 2025-10-31 | [7 empty] | 2025-07-10 | 2025-10-31 | [7 empty] | 2025-07-11 | N/A | [7 empty] | 2025-07-11 | N/A | [6 empty] | 2025-07-11 | N/A | [6 empty] | 11/17/205 |  | 2025-11-18 |  | 2025-12-31 | 2025-12-31 | [5 empty] | 10026061 | 2025-07-07 | 542458 | 2025-10-31 |  | 2021-07-13: 2025-12-31; 2021-07-13: 2026-01-02 | [9 empty] | -2 |  |  |  | Q2 2027 | [15 empty] | FALSE | FALSE |  | 2025-12-31 | 2025-12-31 | 2025 | 2026 | 2026
859 |  | Govinda Neupane |  | 2024-01-04 | [31 empty] | 4 - TPCO |  | 453D1 | 504 |  | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED |  | Mike Imoto | BAP POWER CORPORATION dba Cenergy | MEVS COFFIN LLC | 287 BETHEL RD / WEST PARIS | 2000192409 | 30015550616 | Solar | 996 | 0.996 | 1391 |  |  | 44.3336 | -70.5559 | 287 BETHEL ROAD | 287 | BETHEL ROAD | West Paris | 5H | TRAP CORNER | 453D1 | 453T1 | 12.47 | 9310-L0195-6315-0004-ED00111 |  | NOT IMPACTED | NOT IMPACTED |  | Yes | [6 empty] | 2024-01-11 | 2024-01-19 | 2024-01-11 | 2024-01-19 | 2023-01-19 | 2024-01-25 | 2023-02-02 | 2024-01-25 | 2024-01-29 | 2024-01-29 | 2024-02-12 |  |  | 2024-01-30 |  |  | CS | [7 empty] | CS |  |  | 2024-01-30 | [20 empty] | 2024-02-01 | [8 empty] | 2024-02-02 | [11 empty] | 2024-04-08 | [6 empty] | 2024-04-10 | [8 empty] | 2024-04-10 | [8 empty] | N/A | [8 empty] | N/A | [7 empty] | N/A | [7 empty] | 2024-04-11 |  | 2024-04-11 |  | 2024-04-15 | [6 empty] | 682965 | 2024-04-23 | 392967 | 2024-04-30 |  | 2021-07-13: 2024-04-23; 2021-07-13: 2024-04-23 | [9 empty] | 0 |  |  |  | Q2 2025 | [15 empty] | TRUE | FALSE |  | 2024-04-23 | 2024-04-23 | 2024 | 2024 | 2024
860 |  |  | KRISTOFER COLEMAN | 2024-01-29 | 2024-02-08 | L2_Bump |  | 2024-05-15 | wthdw | [26 empty] | 6 - BRIS |  | 210D2 | 771 |  | WITHDRAWN | WITHDRAWN |  | Nathaniel Curtis | MIDCOAST SOLAR LLC | MIDCOAST SOLAR LLC | 83 CHRISTIAN HILL RD BRISTOL | 2000162495 | 30014270331 | Solar/Battery | [5 empty] | 43.9677 | -69.5256 | 83 Christian Hill Road | 83 | Christian Hill Road | Bristol | 11 | BRISTOL | 210D2 | 210T1 | 12.47 | 9310-L0478-0710-0070-ED00013 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2024-02-05 | 2024-02-12 | 2024-02-05 | 2024-02-12 | 2024-08-01 | 2024-08-05 | 2024-08-15 | [127 empty] | 2024-08-06 | [17 empty] | 0 | [19 empty] | TRUE | FALSE |  | 0 | 0 | 1900 | 1900 | 1900
861 |  | Lanie Patterson | Brent Brooks | 2024-01-30 | [31 empty] | 9 - WINS |  | 870D1 | 286 |  | WITHDRAWN | WITHDRAWN |  | Santiago Quijano | Bluewave Project Development, LLC | BWC MESSALONSKEE STREAM LLC | Benton Ave Benton | 2000130138 | 30011881221 | Solar | [5 empty] | 44.5783 | -69.5891 | 0 Benton Ave | 0 | Benton Ave | Benton | 22 | WINSLOW | 870D1 | 870T4 | 12.47 | 9310-L0453-0460-0005-ED00016 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2024-02-06 | 2024-02-13 | 2024-02-07 | 2024-02-13 | 2024-02-13 | 2024-02-15 | 2024-02-28 | 2024-02-15 | 2024-02-21 | 2024-02-21 | 2024-03-06 |  |  | 2024-02-21 |  |  | CS | [7 empty] | CS |  |  | 2024-02-22 | [7 empty] | 2024-03-08 |  |  |  | 2024-03-06 | [8 empty] | 2024-03-08 | [8 empty] | 2024-03-08 | [11 empty] | 2024-05-13 | [6 empty] | 2024-05-10 | [8 empty] | 2024-05-10 | [8 empty] | 2024-05-15 | [8 empty] | 2024-05-16 | [7 empty] | 2024-05-16 | [18 empty] | 3847946 | 2024-05-09 |  |  | 2024-06-10 | [17 empty] | 0 | [19 empty] | TRUE | FALSE |  | 0 | 0 | 1900 | 1900 | 1900
862 |  | Rigel Paradise | Rick Duperre | 2024-02-06 |  |  |  | 2024-05-01 | wthdw | [26 empty] | 9 - LEBA |  | 695D2 | 808 |  | WITHDRAWN | WITHDRAWN |  | Jacob Fraatz | DIMENSION ENERGY LLC | LEBANON CSG LLC | 429 WEST LEBANON RD / LEBANON | 2000408731 | 30015687608 | Solar | [5 empty] | 43.375 | -70.941 | 429 West Lebanon Rd | 429 | West Lebanon Rd | Lebanon | 2 | LEBANON | 695D2 | 695T1 | 12.47 | 9310-L0473-3190-0007-ED00106 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2024-02-13 | 2024-02-21 | 2024-02-13 | 2024-02-21 | 2024-11-22 | 2024-11-26 | 2023-12-10 | [127 empty] | 2024-12-23 | [17 empty] | 0 | [19 empty] | TRUE | FALSE |  | 0 | 0 | 1900 | 1900 | 1900
863 |  |  | KRISTOFER COLEMAN | 2024-02-06 | 2024-10-18 | Wthdw |  | 2024-10-31 | wthdw | [26 empty] | 3 - LISB |  | 231D2 | 562 | Yes | EXECUTED/ENERGIZED | EXECUTED/ENERGIZED |  | Jacob Fraatz | DIMENSION ENERGY LLC | LISBON CSG LLC | 57 UPLAND RD / LISBON ME 04250 | 2000408730 | 30015687392 | Solar | 999 | 0.999 | 1340.88 |  |  | 44.0289 | -70.093 | 57 Upland Road | 57 | Upland Road | Lisbon | 25 | LISBON | 231D2 | 231T1 | 12.47 | 9310-L0060-3310-0126-ED00025 |  |  |  |  | Yes | [6 empty] | 2024-02-13 | 2024-02-21 | 2024-02-13 | 2024-02-21 | 2024-02-21 | 2024-02-29 | 2024-03-06 | 2024-02-29 | 2024-03-06 | 2024-03-06 | 2024-03-20 |  |  | 2024-03-12 |  |  | CS | [7 empty] | CS |  |  | 2024-03-12 |  |  | 2025-03-06 |  |  |  |  | 2024-03-28 |  |  |  | 2024-03-20 |  |  | 2025-03-13 | [5 empty] | 2024-03-28 |  |  | 2025-03-18 | [5 empty] | 2024-03-28 |  |  | 2025-03-18 | [8 empty] | 2024-06-03 | [6 empty] | 2024-06-03 |  |  | 2025-05-19 | [5 empty] | 2024-06-04 |  |  | 2025-05-19 | [5 empty] | 2024-06-04 |  |  | N/A | [5 empty] | 2024-06-14 |  |  | N/A |  |  |  |  | 2024-06-14 |  |  | N/A |  |  |  |  | 2024-06-14 |  | 2024-06-14 | 2025-05-19 | 2024-07-17 | 2025-05-30 | [5 empty] | 147511 | 2024-06-03 | 191458 | 2025-05-16 |  | 2021-07-13: 2024-07-19; 2021-07-13: 2024-07-19; 2021-07-13: 2025-06-03; 2021-07-13: 2025-06-03 | [9 empty] | 0 |  |  |  | Q2 2025 | [15 empty] | FALSE | FALSE |  | 2024-07-19 | 2024-07-19 | 2024 | 2024 | 2024
864 |  | Eben Snow | Brent Brooks | 2024-02-14 |  |  |  | 2024-02-22 | wthdw | [26 empty] | 4 - RA34 | 1 - RA34 | 444D3 | 740 | Yes | EXECUTED | EXECUTED |  | Sachin Patel | MAINELY SOLAR LLC | SEBAGO SOLAR LLC | pipline rd and bittersweet way wind | 2000143907 | 30012094816 | Solar | 996 | 0.996 | 1999.2 |  |  | 43.8805 | -70.4619 | 91 Pipeline Road Cross St: Viola St | 91 | Pipeline Road Cross St: Viola St | Raymond | 5H | RAYMOND 34 KV | 444D3 | 444T1 | 12.47 | 9310-L0183-4900-0101-ED00015 |  |  |  |  | Yes | [6 empty] | 2024-02-22 | 2024-02-29 | 2024-02-22 | 2024-02-29 | 2024-05-23 | 2024-05-23 | 2024-06-07 | 2024-05-28 | 2024-05-29 | 2024-05-29 | 2024-06-12 |  |  | 2024-06-05 |  |  | CS | 2024-06-05 | [6 empty] | CS |  |  | 2024-06-06 | [7 empty] | 2024-06-17 |  |  |  | 2024-06-13 | [8 empty] | 2024-06-17 | [8 empty] | 2024-06-17 | [11 empty] | 2024-08-21 | [6 empty] | 2024-08-21 | [8 empty] | 2024-08-21 | [8 empty] | 2024-09-03 | [8 empty] | 2024-09-04 | [7 empty] | 2024-09-04 | [7 empty] | 2024-09-04 |  | 2024-09-09 |  | 2024-10-02 | [6 empty] | 94486 | 2024-08-21 |  |  |  | 2021-07-13: 2024-10-03; 2021-07-13: 2024-10-03 | [9 empty] | 0 |  |  |  | Q1 2026 | [15 empty] | TRUE | FALSE |  | 2024-10-03 | 2024-10-03 | 2024 | 2024 | 2024
865 |  | Lanie Patterson | KRISTOFER COLEMAN | 2024-02-16 |  |  |  | 2024-07-26 | wthdw |  | 2025-03-24 | wthdw | [23 empty] | 6 - BATH | 1 - BATH | 261D4 | 788 | Yes | EXECUTED | EXECUTED |  | Jack Greene | Norwich Solar Technologies | West Bath Tonal Solar LLC | 13 TONAL LANE | 2000205316 | 30012960842 | Solar | 975 | 0.975 | 1728 |  |  | 43.9125 | -69.8379 | King's Highway |  | King's Highway | West Bath | 4 | BATH 34 | 261D4 | 261T2 | 12.47 | 9310-L0100-0410-0470-ED00004 |  | NOT IMPACTED | NOT IMPACTED |  | Yes | [6 empty] | 2024-02-26 | 2024-03-04 | 2024-02-26 | 2024-03-04 | 2024-03-04 | 2024-03-08 | 2024-03-18 | 2024-03-11 | 2024-03-13 | 2024-03-13 | 2024-03-27 |  |  | 2024-03-21 |  |  | CS | [7 empty] | CS |  |  | 2024-03-28 |  |  | 2024-12-03 | 2025-03-26 |  |  |  | 2024-04-09 |  |  |  | 2024-04-09 |  |  | 2024-12-13 | 2025-04-07 |  |  |  |  | 2024-04-09 |  |  | 2025-01-02 | 2025-04-07 |  |  |  |  | 2024-04-09 |  |  | 2025-01-02 | 2025-04-07 | [7 empty] | 2024-06-13 | [6 empty] | 2024-06-12 |  |  | 2025-03-10 | 2025-06-10 |  |  |  |  | 2024-06-12 |  |  | 2025-03-11 | 2025-06-10 |  |  |  |  | 2024-06-17 |  |  | 2025-03-11 | 2025-06-12 |  |  |  |  | 2024-06-20 |  |  | 2025-03-14 | 2025-06-16 |  |  |  | 2024-06-20 |  |  | 2025-03-14 | 2025-06-16 |  |  |  | 2024-06-28 |  | 2024-07-01 | 2025-03-18 | 2024-07-01 | 2025-03-19 | [5 empty] | 97386 | 2024-06-11 | 325342 | 2025-06-10 |  | 2024-07-05 | 2024-07-08 | 2025-03-24 | 2025-03-24 | 2025-07-08 | 2025-07-08 | [11 empty] | -3 |  |  |  | Q2 2026 | [15 empty] | FALSE | FALSE |  | 2024-07-05 | 2024-07-05 | 2024 | 2024 | 2024
866 |  | Marshall Ripley | Rick Duperre | 2024-02-22 | 2024-03-14 | wthdw |  | 2024-04-10 | wthdw |  | 2025-10-22 | wthdw | [22 empty] | 857 | 9 - ELM | 1 - ELM | 620D2 | 857 | Yes | EXECUTED | EXECUTED |  | David Ikejiani | EDP RENEWABLES | EDPR NA DISTRIBUTED GENERATION LLC | 269 Sligo Rd, Yarmouth 04096 | 2000410757 | 30015718213 | Solar | 975 | 0.975 | 1319.76 |  |  | 43.8126 | -70.2045 | 269 Sligo Road | 269 | Sligo Road | Yarmouth | 21 | ELM STREET | 620D2 | 620T3 | 12.47 | 9310-L0236-6650-0126-ED00026 |  | NOT IMPACTED | NOT IMPACTED |  | Yes | [6 empty] | 2024-02-29 | 2024-03-07 | 2024-02-29 | 2024-03-05 | 2025-03-25 | 2025-03-26 | 2025-04-08 | 2025-04-01 | 2025-04-04 | 2025-04-04 | 2025-04-18 |  |  | 2025-04-16 |  |  | CS | 2025-04-16 | [6 empty] | CS |  |  | 2025-04-17 |  |  | 2025-11-13 |  |  |  |  | 2025-05-05 |  |  |  | 2025-05-01 |  |  | 2025-12-01 | [5 empty] | 2025-05-05 |  |  | 2025-12-01 | [5 empty] | 2025-05-05 |  |  | 2025-12-01 | [8 empty] | 2025-07-10 | [6 empty] | 2025-07-10 |  |  | 2026-02-05 | [5 empty] | 2025-07-10 |  |  | 2026-02-05 | [5 empty] | 2025-07-15 |  |  | 2026-02-19 | [5 empty] | 2025-07-17 |  |  | 2026-02-25 |  |  |  |  | 2025-07-17 |  |  | 2026-02-25 |  |  |  |  | 2025-08-04 |  | 2025-08-06 | 2026-02-25 | 2025-08-12 | [6 empty] | 673530 | 2025-07-10 | 656310 | 2026-05-05 |  | 2021-07-13: 2025-08-13; 2021-07-13: 2025-08-15; 2021-07-13: 2026-02-26; 2021-07-13: 2026-02-26 | [9 empty] | -2 |  |  |  | Q1 2025 |  |  |  | 10301208850 | [11 empty] | FALSE | FALSE |  | 2025-08-13 | 2025-08-13 | 2025 | 2025 | 2025
867 |  | Marshall Ripley | Rick Duperre | 2024-02-23 | 2024-03-14 | wthdw |  | 2024-04-10 | wthdw | [25 empty] | 866 | 10 - ELM |  | 620D2 | 866 | Yes | WITHDRAWN | WITHDRAWN |  | David Ikejiani | EDP RENEWABLES | EDPR NA DISTRIBUTED GENERATION LLC | 269 Sligo Rd, Yarmouth 04096 | 2000410757 | 30015720276 | Solar | [5 empty] | 43.8123 | -70.2055 | 271 Sligo Road | 271 | Sligo Road | Yarmouth | 23 | ELM STREET | 620D2 | 620T3 | 12.47 | 9310-L0236-6650-0126-ED00027 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2024-03-01 | 2024-03-08 | 2024-03-01 | 2024-03-08 | 2025-08-15 | 2025-08-20 | 2025-08-30 | [127 empty] | 2025-09-16 | [17 empty] | 0 |  |  |  | Q1 2025 | [15 empty] | TRUE | FALSE |  | 0 | 0 | 1900 | 1900 | 1900
868 |  | Lanie Patterson | Brent Brooks | 2024-02-28 | 2024-09-30 | L2_Bump | [29 empty] | 4 - SIDN |  | 242D1 | 813 | Yes | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Katie Kearney | SOLAMERICA ENERGY HOLDINGS, INC | Kennebec County ME S2, LLC | 2753 Middle Road Sidney | 2000411712 | 30016135631 | Solar | [5 empty] | 44.4323 | -69.7502 | 2753 Middle Road | 2753 | Middle Road | Sidney | 10 | SIDNEY | 242D1 | 242T1 | 12.47 | 9310-L0076-5320-0051-ED00071 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2024-03-06 | 2024-03-13 | 2024-03-05 | 2024-03-13 | 2024-03-13 | 2024-03-21 | 2024-03-27 | 2024-03-22 | 2024-03-27 | 2024-03-27 | 2024-04-10 |  |  | 2024-04-08 |  |  | CS | 2024-04-08 | [6 empty] | CS |  |  | 2024-04-08 |  |  | 2024-09-30 |  |  |  |  | 2024-04-24 |  |  |  | 2024-04-22 |  |  | 2024-10-25 | [5 empty] | 2024-04-25 |  |  | 2024-10-25 | [5 empty] | 2024-04-25 |  |  | 2024-10-25 | [8 empty] | 2024-07-01 | [6 empty] | 2024-07-01 |  |  | 2025-01-02 | [5 empty] | 2024-07-01 |  |  | 2025-01-03 | [5 empty] | 2024-07-17 |  |  | 2025-01-03 | [5 empty] | 2024-07-17 |  |  | 2025-01-10 |  |  |  |  | 2024-07-17 |  |  | 2025-01-10 |  |  |  |  | 2024-08-06 |  | 2024-08-13 | 2024-09-18 | 2024-09-11 | [6 empty] | 209883 | 2024-07-01 | 811355.88 | 2024-01-02 | 2025-10-07 | 2021-07-13: 2024-09-12; 2021-07-13: 2024-09-17; 2021-07-13: 2025-03-10; 2021-07-13: 2025-03-10 | [9 empty] | -5 |  |  |  | Q2 2025 | [15 empty] | TRUE | FALSE |  | 2024-09-12 | 2024-09-12 | 2024 | 2024 | 2024
869 |  |  | KRISTOFER COLEMAN | 2024-03-05 | [31 empty] | 3 - BANE |  | 206D1 | 854 |  | WITHDRAWN | WITHDRAWN |  | Nathaniel Curtis | MIDCOAST SOLAR LLC | WHITE PINES SOLAR LLC | 1444 High St Bath, ME 04530 | 2000411376 | 30015726067 | Solar/Battery | [5 empty] | 43.9371 | -69.819 | 1526-1434 High St. | 1526-1434 | High St. | Bath | 216 | BATH NORTH END | 206D1 | 206T1 | 12.47 | 9310-L0018-0410-0083-ED00184 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2024-03-12 | 2024-03-19 | 2024-03-12 | 2024-03-19 | 2024-08-23 | 2024-09-11 | 2024-09-09 | 2024-09-17 | 2024-09-20 | 2024-09-20 | 2024-10-04 |  |  | 2024-10-24 |  |  | CS | 2024-10-24 | [6 empty] | CS |  |  | 2024-10-25 | [7 empty] | 2024-11-11 |  |  |  | 2024-11-11 | [8 empty] | 2024-11-11 | [8 empty] | 2024-11-12 | [11 empty] | 2025-01-20 | [6 empty] | 2025-01-21 | [8 empty] | 2025-01-21 | [44 empty] | 687729 | 2025-01-21 | n/a | n/a | 2025-03-04
870 |  | Rigel Paradise | Rick Duperre | 2024-03-12 | [31 empty] | 6 - BUCO | 1 - BUCO | 612D2 | 678 |  | EXECUTED | EXECUTED |  | Colin Derhammer | Bridge Energy | ACTON SOLAR LLC | 82 Sanborn Rd Acton ME 04001 | 2000394146 | 30015492686 | Solar | 600 | 0.6 | 870 |  |  | 43.5334 | -70.9141 | 82 Sanborn Rd | 82 | Sanborn Rd | Acton | 8 | BUTLER'S CORNER | 612D2 | 612T1 | 12.47 | 9310-L0226-0020-0044-ED00130 |  | NOT IMPACTED | NOT IMPACTED |  | Yes | [6 empty] | 2024-03-19 | 2024-03-26 | 2024-03-19 | 2024-03-26 | 2024-03-26 | 2024-03-29 | 2024-04-09 | 2024-04-01 | 2024-04-12 | 2024-04-12 | 2024-04-29 |  |  | 2024-04-15 |  |  | CS | 2024-04-15 | [6 empty] | CS |  |  | 2024-04-16 | [7 empty] | 2023-04-23 |  |  |  | 2024-04-23 | [8 empty] | 2024-04-23 | [8 empty] | 2024-04-23 | [11 empty] | 2023-06-27 | [6 empty] | 2024-06-25 | [8 empty] | 2024-06-05 | [8 empty] | 2024-06-26 | [8 empty] | 2024-07-15 | [7 empty] | 2024-07-15 | [7 empty] | 2024-07-16 |  | 2024-07-19 |  | 2024-08-09 | [6 empty] | 94486 | 2024-06-20 |  |  |  | 2021-07-13: 2024-08-16; 2021-07-13: 2024-08-16 | [13 empty] | Q4 2025
871 |  | Lanie Patterson | Brent Brooks | 2024-03-21 | 2024-09-30 | L2_Bump | [29 empty] | 5 - SIDN |  | 242D1 | 868 | Yes | WITHDRAWN | WITHDRAWN |  | Corwin Lavoie | Nexamp, Inc | NEXAMP SOLAR LLC | Heidi Blvd / Augusta | 2000114877 | 30015731240 | Solar | [5 empty] | 44.4408 | -69.7411 | Heidi Boulevard |  | Heidi Boulevard | Augusta | 9 | SIDNEY | 242D1 | 242T1 | 12.47 | 9310-L0076-5320-0089-ED00012 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2024-03-28 | 2024-04-04 | 2024-03-28 | 2024-04-04 | 2024-09-17 | 2024-09-19 | 2024-10-01 | 2024-09-20 | 2024-09-25 | 2024-09-25 | 2024-10-09 | [123 empty] | 2025-03-24 | [17 empty] | 0 |  |  |  | Q2 2025 | [15 empty] | TRUE | FALSE |  | 0 | 0 | 1900 | 1900 | 1900
872 |  | Ben Brooks | Anthony Boucher | 2024-03-21 | 2024-11-12 | L2_Bump | [29 empty] | 4 - B115 |  | 874D1 | 765 | Yes | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | James Cerkanowicz | VCP REALTY LLC | VCP REALTY LLC | 462 Oak Hill Rd, Swanville ME | 2000262503 | 30015763896 | Solar | [5 empty] | 44.4944 | -69.0399 | 462 Oak Hill Road | 462 | Oak Hill Road | Swanville | 69 | BELFAST 115 | 874D1 | 874T2 | 12.47 | 9310-L0458-5630-0021-ED00078 |  |  |  |  | Yes | [6 empty] | 2024-03-28 | 2024-04-04 | 2024-03-28 | 2024-04-04 | 2024-04-04 | 2024-04-10 | 2024-04-19 | 2024-04-11 | 2024-04-16 | 2024-04-16 | 2024-04-30 |  |  | 2024-04-26 |  |  | CS | 2024-04-26 | [6 empty] | CS |  |  | 2024-04-26 | 2024-09-03 |  | 2024-11-13 |  |  |  |  | 2024-05-17 | 2024-09-03 |  |  | 2024-05-14 | 2024-09-12 |  | 2024-12-02 | [5 empty] | 2024-05-16 | 2024-09-12 |  | 2024-12-02 | [5 empty] | 2024-05-17 | 2024-09-13 |  | 2024-12-02 | [8 empty] | 2024-07-24 | 2024-10-28 | [5 empty] | 2024-07-24 | 2024-10-28 |  | 2025-02-06 | [5 empty] | 2024-07-24 | 2024-10-28 |  | 2024-10-28 | [5 empty] | 2024-07-30 | 2024-11-01 |  | 2025-02-10 | [5 empty] | 2024-08-05 | 2024-11-12 |  | 2025-02-21 |  |  |  |  | 2024-08-05 | 2024-11-12 |  | 2025-02-21 |  |  |  |  | 2025-03-03 |  | 2025-03-04 |  | 2025-03-06 | [6 empty] | 4780723 | 2024-07-22 | 3728802 | 2025-02-05 | 2025-11-07 | 2021-07-13: 2025-03-10; 2021-07-13: 2025-03-10 | [9 empty] | 0 |  |  |  | Q3 2026 | [15 empty] | FALSE | FALSE |  | 2025-03-10 | 2025-03-10 | 2025 | 2025 | 2025
873 |  | Marshall Ripley | Rick Duperre | 2024-03-27 | 2024-09-16 | wthdw | [29 empty] | 5 - BRML |  | 678D1 | 535 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Mike Imoto | BAP Power Corporation DBA Cenergy Power | BAP POWER CORP | 237 HOLLIS RD / HOLLIS | 2000122114 | 30015562298 | Solar | [5 empty] | 43.6011 | -70.5748 | 237 Hollis Rd. | 237 | Hollis Rd. | Hollis | 523 | BAR MILLS | 678D1 | 678T4 | 12.47 | 9310-L0355-2647-0055-ED00064 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2024-04-03 | 2024-04-10 | 2024-04-03 | 2024-04-10 | 2024-04-10 | 2024-04-16 | 2024-04-25 | 2024-04-17 | 2024-04-18 | 2024-04-18 | 2024-05-02 |  |  | 2024-04-19 |  |  | CS | 2024-04-19 | [6 empty] | CS |  |  | 2024-04-19 |  |  | 2024-09-17 | [8 empty] | 2024-05-06 |  |  | 2024-10-03 | [5 empty] | 2024-05-08 |  |  | 2024-10-03 | [5 empty] | 2024-05-08 |  |  | 2024-10-03 | [8 empty] | 2024-07-15 | [6 empty] | 2024-07-17 |  |  | 2024-12-09 | [5 empty] | 2024-07-17 |  |  | 2024-12-09 | [5 empty] | N/A | [8 empty] | N/A | [7 empty] | N/A | [7 empty] | 2024-07-31 |  | 2024-07-31 |  | 2024-08-28 | [6 empty] | 132452 | 2024-07-15 | 473149 |  | 2024-12-24 | 2021-07-13: 2024-08-29; 2021-07-13: 2024-08-29 | [9 empty] | 0 | [19 empty] | TRUE | FALSE |  | 2024-08-29 | 2024-08-29 | 2024 | 2024 | 2024
874 |  | Eben Snow | Brent Brooks | 2024-05-10 | 2025-05-15 | wthdw | [29 empty] | 3 - FRYE |  | 415D2 | 537 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Michael Parker | Loki Solar | Birch Solar LLC | 54 FAIR ST FRYBURG | 2000409138 | 30015693838 | Solar | [5 empty] | 44.0096 | -70.9753 | 54 Fair St. | 54 | Fair St. | Fryeburg | 8 | FRYEBURG | 415D2 | 415T1 | 12.47 | 9310-L0132-2130-0025-ED00021 |  |  |  |  | Yes | [6 empty] | 2024-05-17 | 2024-05-24 | 2024-05-17 | 2024-05-24 | 2024-05-24 | 2024-05-28 | 2024-06-10 | 2024-05-28 | 2024-05-31 | 2024-05-31 | 2024-06-14 |  |  | 2024-05-31 |  |  | CS | 2024-05-31 | [6 empty] | CS |  |  | 2024-05-31 | [7 empty] | 2024-06-25 |  |  |  | 2024-06-26 | [8 empty] | 2024-06-26 | [8 empty] | 2024-06-26 | [11 empty] | 2024-09-29 | [6 empty] | 2024-08-28 | [8 empty] | 2024-08-28 | [8 empty] | 2024-09-11 | [8 empty] | 2024-09-11 | [7 empty] | 2024-09-11 | [7 empty] | 2024-10-01 |  | 2024-10-03 |  | 2024-11-04 | [6 empty] | 94486 | 2024-08-28 |  |  | 2025-06-24 | 2021-07-13: 2024-11-07; 2021-07-13: 2024-11-07 | [9 empty] | 0 |  |  |  | Q3 2025 | [15 empty] | TRUE | FALSE |  | 2024-11-07 | 2024-11-07 | 2024 | 2024 | 2024
875 |  | Govinda Neupane |  | 2024-05-13 | 2025-01-21 | wthdw | [29 empty] | 16 - ATHN |  | 827D2 | 826 | Yes | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Michael Parker | Loki Solar | Red Pine Solar LLC | 19 GILMAN FARM RD ATHENS | 2000422871 | 30016359405 | Solar | [5 empty] | 44.955 | -69.6431 | 19 Gilman Farm Rd | 19 | Gilman Farm Rd | Athens | 108.8 | ATHENS | 827D2 | 827T1 | 12.47 | 9310-L0412-0200-0014-ED00009 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2024-05-20 | 2024-05-28 | 2024-05-20 | 2024-05-28 | 2024-05-28 | 2024-05-31 | 2024-06-11 | 2024-06-03 | 2024-06-06 | 2024-06-06 | 2024-06-21 |  |  | 2024-06-14 |  |  | CS | 2024-06-14 | [6 empty] | CS |  |  | 2024-06-20 |  |  | 2025-01-22 |  |  |  |  | 2024-06-25 |  |  |  | 2024-06-25 |  |  | 2025-02-06 | [5 empty] | 2024-06-26 |  |  | 2025-02-06 | [5 empty] | 2024-06-28 |  |  | 2025-02-06 | [8 empty] | 2024-09-03 | [6 empty] | 2024-08-29 |  |  | 2025-04-10 | [5 empty] | 2024-08-29 |  |  | 2025-04-10 | [5 empty] | 2024-09-13 | [8 empty] | 2024-09-13 | [7 empty] | 2024-09-13 | [7 empty] | 2024-10-03 |  | 2024-10-03 |  | 2024-10-31 | [6 empty] | 455782 |  | 841828 | 2025-04-10 | 2025-05-19 | 2021-07-13: 2024-11-01; 2021-07-13: 2024-11-01 | [9 empty] | 0 |  |  |  | Q3 2025 | [15 empty] | TRUE | FALSE |  | 2024-11-01 | 2024-11-01 | 2024 | 2024 | 2024
876 |  | Lanie Patterson | Brent Brooks | 2024-05-23 | [31 empty] | 6 - SIDN |  | 242D2 | 871 |  | WITHDRAWN | WITHDRAWN |  | Mike Imoto | BAP POWER CORPORATION dba Cenergy | BAP POWER CORP | 3335 West River Rd Sidney ME 04330 | 2000122114 | 30015921304 | Solar | [5 empty] | 44.4605 | -69.6949 | Corner of W RIVER ROAD and Riverside Terrace |  | Corner of W RIVER ROAD and Riverside Terrace | Sidney | 0219 | SIDNEY | 242D2 | 242T1 | 12.47 | 9310-L0435-5325-0032-ED00129 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2024-05-31 | 2024-06-07 | 2024-05-31 | 2024-06-07 | [130 empty] | 2024-09-19 | [17 empty] | 0 | [19 empty] | TRUE | FALSE |  | 0 | 0 | 1900 | 1900 | 1900
877 |  | Lanie Patterson | Brent Brooks | 2024-05-28 | [6 empty] | 2024-10-18 | L2_Bump |  | 2024-11-06 | wthdw |  | 2024-12-16 | wthdw |  | 2025-08-28 | L2_Bump |  | 2025-12-30 | [11 empty] | 838 | 11 - NOAU |  | 272D6 | 838 | Yes | WITHDRAWN | WITHDRAWN |  | Katie Kearney | SolAmerica Energy, LLC | KENNEBEC COUNTY ME S2 LLC | KENNEBEC_CARON 90 POND RD SIDNEY | 2000417923 | 30015923151 | Solar | [5 empty] | 44.4019 | -69.8042 | 90 Pond Road | 90 | Pond Road | Augusta | 13 | NORTH AUGUSTA | 272D6 | 272T2 | 12.47 | 9310-L0470-5320-0028-ED00044 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2024-06-04 | 2024-06-11 | 2024-06-04 | 2024-06-11 | 2025-12-16 | 2025-12-18 | 2025-12-31 | 2025-12-19 | 2025-12-30 | 2025-12-30 | [124 empty] | 2025-01-07 | [17 empty] | 0 |  |  |  | Q3 2025 | [15 empty] | TRUE | FALSE |  | 0 | 0 | 1900 | 1900 | 1900
878 |  | Lanie Patterson | Brent Brooks | 2024-05-28 | [6 empty] | 2024-10-18 | L2_Bump |  | 2024-11-06 | wthdw |  | 2024-12-16 | wthdw |  | 2025-08-28 | L2_Bump |  | 2025-12-30 | [11 empty] | 877 | 12 - NOAU |  | 272D6 | 877 | Yes | WITHDRAWN | WITHDRAWN |  | Katie Kearney | SolAmerica Energy, LLC | SOLAMERICA ENERGY HOLDINGS LLC | KENNEBEC_BRENDLE POND RD SIDNEY | 2000417923 | 30015923169 | Solar | [5 empty] | 44.3963 | -69.7977 | Pond Road |  | Pond Road | Augusta | 5 | NORTH AUGUSTA | 272D6 | 272T2 | 12.47 | 9310-L0470-5320-0028-ED00308 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2024-06-04 | 2024-06-11 | 2024-06-04 | 2024-06-11 | 2026-07-27 | 2026-07-27 | 2026-08-10 | [127 empty] | 2026-07-28 | [17 empty] | 0 |  |  |  | Q3 2025 | [15 empty] | TRUE | FALSE |  | 0 | 0 | 1900 | 1900 | 1900
879 |  | Lanie Patterson | Brent Brooks | 2024-05-28 | 2025-01-08 | wthdw |  | 2025-09-05 | L2_Bump |  | 2025-09-19 | L2_With | [23 empty] | 8 - PDRD | 2 - PDRD | 262D1 | 692 | Yes | EXECUTED | EXECUTED |  | Ryan Coughlin | Perennial Renewables LLC | Perennial Readfield Solar LLC | READFEILD SOLAR | 2000516926 | 30017276418 | Solar | 999 | 0.999 | 1316.52 |  |  | 44.3744 | -69.9256 | 615 Main Street | 615 | Main Street | Readfield | 174 | PUDDLEDOCK ROAD | 262D1 | 34.5kV Bus | 34.5 | 9310-L0101-4910-0057-ED00089 |  | NOT IMPACTED | NOT IMPACTED |  | Yes | [6 empty] | 2024-06-04 | 2024-06-11 | 2024-06-04 | 2024-06-11 | 2024-09-19 | 2024-09-24 | 2024-10-01 | 2024-10-03 | 2024-10-07 | 2024-10-07 | 2024-10-22 |  |  | 2024-10-28 |  |  | CS | 2024-10-28 | [6 empty] | CS |  |  | 2024-10-29 |  |  | 2025-01-08 | 2026-03-25 |  |  |  | 2024-11-12 |  |  |  | 2024-11-26 |  |  | 2024-02-12 | 2026-04-13 |  |  |  |  | 2024-11-26 |  |  | 2025-02-12 | 2026-04-13 |  |  |  |  | 2024-11-26 |  |  | 2025-02-12 | 2026-04-13 | [7 empty] | 2025-02-04 | [9 empty] | 2025-04-04 | 2026-05-27 | [7 empty] | 2025-04-04 | 2026-05-27 | [7 empty] | 2025-04-28 | 2026-06-09 | [7 empty] | 2025-05-13 | 2026-06-10 | [6 empty] | 2025-05-13 | 2026-06-10 |  |  |  | 2025-06-04 |  | 2025-06-05 | 2026-07-09 | 2025-07-21 | 2026-07-16 | [5 empty] | 248890 | 2025-04-04 | 371390 | 2026-05-27 |  | 2021-07-13: 2025-07-21; 2021-07-13: 2025-07-22; 2021-07-13: 2026-07-27; 2021-07-13: 2026-07-26 | [9 empty] | -1 |  |  |  | Q3 2025 | [15 empty] | TRUE | FALSE |  | 2025-07-21 | 2025-07-21 | 2025 | 2025 | 2025
880 |  | Ben Brooks | Anthony Boucher | 2024-05-29 | [6 empty] | 2025-04-04 | wthdw | [23 empty] | 7 - PROS | 1 - PROS | 846D1 | 516 |  | EXECUTED | EXECUTED |  | Jacob Freudenberger | Bridge Energy | PE ALLAGASH LLC | 640 Lebanon Rd Winterport | 2000421471 | 30015869362 | Solar | 900 | 0.9 | 1228.08 |  |  | 44.659 | -68.8893 | 640 Lebanon Road | 640 | Lebanon Road | Winterport | 124 | PROSPECT | 846D1 | 846T1 | 12.47 | 9310-L0426-6440-0015-ED00036 |  | TRIGGERING | TRIGGERING | 290000 | Yes | [6 empty] | 2024-06-05 | 2024-06-12 | 2024-06-05 | 2024-06-12 | 2024-06-12 | 2024-06-14 | 2024-06-27 | 2024-06-17 | 2024-06-19 | 2024-06-19 | 2024-07-05 |  |  | 2024-06-21 |  |  | CS | 2024-06-21 | [6 empty] | CS |  |  | 2024-06-21 | 2024-10-07 |  | 2025-04-07 |  |  |  |  | 2024-06-21 | 2024-10-07 |  |  | 2024-06-28 | 2024-10-16 |  | 2025-04-11 | [5 empty] | 2024-06-28 | 2024-10-16 |  | 2025-04-11 | [5 empty] | 2024-06-28 | 2024-10-21 |  | 2025-04-11 | [8 empty] | 2024-09-03 | 2024-12-05 | [5 empty] | 2024-08-30 | 2024-12-05 |  | 2025-06-13 | [5 empty] | 2024-09-03 | 2024-12-05 |  | 2025-06-13 | [5 empty] | N/A | N/A | [7 empty] | N/A | N/A |  | 2025-06-25 |  |  |  |  | N/A | N/A |  | 2025-06-25 |  |  |  |  | 2024-12-17 |  | 2024-12-17 | 2025-06-26 | 2024-12-18 | 2025-06-27 | [5 empty] | 3368464 | 2024-08-29 | 798675 | 2025-06-13 |  | 2021-07-13: 2024-12-20; 2021-07-13: 2024-12-20; 2021-07-13: 2025-06-27; 2021-07-13: 2025-06-30 | [9 empty] | 0 |  |  |  | Q4 2025 |  |  |  | Requested | [11 empty] | FALSE | FALSE |  | 2024-12-20 | 2024-12-20 | 2024 | 2024 | 2024
881 |  | Eben Snow | Brent Brooks | 2024-05-29 | [9 empty] | 2024-10-21 | wthdw |  | 2024-10-30 | studywaived |  | 2024-12-18 | wthdw |  | 2025-04-16 | L2_Bump |  | 2025-06-11 | L2_Bump | [8 empty] | 12 - MEFA |  | 431D3 | 852 | Yes | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Jacob Freudenberger | Paddle Energy LLC | PE KENNEBEC LLC | 32 Atlantis Dr Mechanic Falls | 2000421472 | 30015869388 | Solar | [5 empty] | 44.0783 | -70.4251 | 32 Atlantis Drive | 32 | Atlantis Drive | Mechanic Falls | 3 | MECHANIC FALLS | 431D3 | 431T2 | 12.47 | 9310-L0167-3610-0021-ED00003 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2024-06-05 | 2024-06-12 | 2024-06-05 | 2024-06-12 | 2025-09-18 | 2025-09-19 | 2025-10-02 | 2025-09-29 | 2025-10-01 | 2025-10-01 | 2025-10-16 |  |  | 2025-10-17 |  |  | CS | 2025-10-17 | [6 empty] | CS |  |  | 2025-10-17 | [11 empty] | 2025-10-24 | [8 empty] | 2025-10-24 | [8 empty] | 2025-10-24 | [11 empty] | 2026-01-02 | [6 empty] | 2025-12-19 | [8 empty] | 2025-12-22 | [17 empty] | N/A | [7 empty] | N/A | [7 empty] | 2025-12-22 |  | 2025-12-22 |  | 2025-12-22 | [6 empty] | 394449 | 2025-12-18 |  |  | 2026-04-01 | 2021-07-13: 2025-12-22; 2021-07-13: 2025-12-23 | [9 empty] | -1 |  |  |  | Q4 2025 | [15 empty] | TRUE | FALSE |  | 2025-12-22 | 2025-12-22 | 2025 | 2025 | 2025
882 |  | Eben Snow | Brent Brooks | 2024-05-29 | [9 empty] | 2024-10-21 | wthdw |  | 2024-10-24 | studywaived |  | 2024-12-18 | wthdw |  | 2025-04-16 | L2_Bump |  | 2025-06-11 | L2_Bump |  | 2026-04-01 | Wthdw | [5 empty] | 13 - MEFA | 1 - MEFA | 431D1 | 881 | Yes | EXECUTED | EXECUTED |  | Jacob Freudenberger | Paddle Energy LLC | PE KATAHDIN LLC | 12 Alexander Ln Poland | 2000421473 | 30015869610 | Solar | 999 | 0.999 | 1124.88 |  |  | 44.0929 | -70.366 | 12 Alexander Lane | 12 | Alexander Lane | Poland | 84 | MECHANIC FALLS | 431D1 | 431T2 | 12.47 | 9310-L0165-4710-0060-ED00114 |  | Cost Sharing | 385558 | 128434 | Yes | [6 empty] | 2024-06-05 | 2024-06-12 | 2024-06-05 | 2024-06-12 | 2025-12-23 | 2025-12-30 | 2025-01-08 | 2025-01-05 | 2026-01-07 | 2026-01-07 | 2026-01-22 |  |  | 2026-01-07 |  |  | CS | 2026-01-07 | [6 empty] | CS |  |  | 2026-01-07 |  |  | 2026-04-06 |  |  |  |  | 2026-01-20 |  |  |  | 2026-01-16 |  |  | 2026-04-28 | [5 empty] | 2026-01-21 |  |  | 2026-04-28 | [5 empty] | 2026-01-21 |  |  | 2026-04-28 | [8 empty] | 2026-03-26 | [6 empty] | 2026-03-24 |  |  | 2026-07-02 | [5 empty] | 2026-03-26 |  |  | 2026-07-02 | [8 empty] | N/A | [5 empty] | N/A | [7 empty] | N/A | [7 empty] | 2026-07-06 |  | 2026-07-09 |  | 2026-08-06 | [6 empty] | 473076 | 2026-03-24 | 267998 | 2026-07-02 |  | 2021-07-13: 2026-08-07; 2021-07-13: 2026-08-07 | [9 empty] | 0 |  |  |  | Q4 2025 |  |  |  | 10301299022 | [11 empty] | TRUE | FALSE |  | 2026-08-07 | 2026-08-07 | 2026 | 2026 | 2026
883 |  | Ben Brooks | Anthony Boucher | 2024-05-29 | [6 empty] | 2025-04-04 | wthdw | [23 empty] | 8 - PROS |  | 846D1 | 880 |  | WITHDRAWN | WITHDRAWN |  | Jacob Freudenberger | Paddle Energy LLC | PE SOLUM LLC | 30 Blueberry Ln Stockton Springs | 2000421474 | 30015869628 | Solar | [5 empty] | 44.5264 | -68.8625 | 30 Blueberry Lane | 30 | Blueberry Lane | Stockton Springs | 47 | PROSPECT | 846D1 | 846T1 | 12.47 | 9310-L0426-5540-0038-ED00024 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2024-06-05 | 2024-06-12 | 2024-06-05 | 2024-06-12 | 2024-12-20 | 2024-12-24 | 2024-01-07 | 2025-01-02 | 2025-01-13 | 2025-01-13 | 2025-01-28 |  |  | 2025-01-27 |  |  | CS | 2025-01-27 | [6 empty] | CS |  |  | 2025-01-27 |  |  | 2025-07-02 |  |  |  |  | 2025-02-06 |  |  |  | 2025-02-06 |  |  | 2025-07-18 | [5 empty] | 2025-02-06 |  |  | 2025-07-18 | [5 empty] | 2025-02-06 |  |  | 2025-07-18 | [8 empty] | 2025-04-11 | [9 empty] | 2025-09-12 | [8 empty] | 2025-09-12 | [41 empty] | 3743279 | 2025-09-11 |  |  | 2025-10-01 | [17 empty] | 0 |  |  |  | Q4 2025 | [15 empty] | TRUE | FALSE |  | 0 | 0 | 1900 | 1900 | 1900
884 |  | Ben Brooks | Anthony Boucher | 2024-05-29 | [6 empty] | 2025-04-04 | wthdw | [23 empty] | 9 - PROS |  | 846D1 | 883 |  | WITHDRAWN | WITHDRAWN |  | Jacob Freudenberger | Paddle Energy LLC | PE MORAINE LLC | Monroe Rd Winterport | 2000421475 | 30015869644 | Solar | [5 empty] | 44.667 | -68.949 | 146 Monroe Road | 146 | Monroe Road | Winterport | 6 | PROSPECT | 846D1 | 846T1 | 12.47 | 9310-L0426-6440-0067-ED00178 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2024-06-05 | 2024-06-12 | 2024-06-05 | 2024-06-12 | 2025-10-01 | 2025-10-13 | 2025-10-16 | [127 empty] | 2025-10-16 | [17 empty] | 0 |  |  |  | Q4 2025 | [15 empty] | TRUE | FALSE |  | 0 | 0 | 1900 | 1900 | 1900
885 |  | Rigel Paradise |  | 2024-06-04 | 2024-10-09 | Wthdw | [29 empty] | 7 - LIME |  | 632D1 | 522 | Yes | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Jacob Fraatz | Dimension Renewable Energy | LIMERICK CSG LLC | 170 BURNHAM RD / LIMERICK | 2000408708 | 30015687368 | Solar | [5 empty] | 43.6826 | -70.7729 | 170 Burnham Rd | 170 | Burnham Rd | Limerick | 513 | LIMERICK | 632D1 | 632T1 | 12.47 | 9310-L0263-3260-0155-ED00076 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2024-06-11 | 2024-06-18 | 2024-06-11 | 2024-06-18 | 2024-06-18 | 2024-06-20 | 2024-07-03 | 2024-06-20 | 2024-06-25 | 2024-06-25 | 2024-07-10 |  |  | 2024-07-03 |  |  | CS | 2024-07-03 | [9 empty] | 2024-07-05 |  |  | 2024-10-10 | 2025-01-06 |  |  |  | 2024-08-07 |  |  |  | 2024-07-23 |  |  | 2024-11-01 | N/A |  |  |  |  | 2024-08-07 |  |  | 2024-11-01 | 2025-01-23 |  |  |  |  | 2024-08-07 |  |  | 2024-11-01 | 2025-01-23 | [7 empty] | 2024-10-10 | [10 empty] | 2025-03-28 | [8 empty] | 2025-03-31 | [8 empty] | 2025-04-01 | [8 empty] | 2025-04-03 | [7 empty] | 2025-04-03 |  |  |  | 2025-04-09 |  | 2025-04-09 |  | 2025-04-10 | [6 empty] | 5838157 | 2025-03-28 | n/a | n/a | 2025-08-04 | 2021-07-13: 2025-04-14; 2021-07-13: 2025-04-25 | [9 empty] | -11 |  |  |  | Q4 2024 | [15 empty] | TRUE | FALSE |  | 2025-04-14 | 2025-04-14 | 2025 | 2025 | 2025
886 |  | Govinda Neupane |  | 2024-06-17 | [31 empty] | 4 - RILE |  | 449D2 | 581 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Chrissi Ramsey | SolAmerica Energy, LLC | SolAmerica Energy LLC | ME Franklin Cerulli / Main Street | 2000209571 | 30016151711 | Solar | [5 empty] | 44.5439 | -70.2369 |  |  | Main St | Jay | 192 | RILEY | 449D2 | 449T1 | 12.47/7.2 | 9310-L0191-2920-0085-ED00264 |  |  |  |  | Yes | [6 empty] | 2024-06-25 | 2024-07-02 | 2024-06-25 | 2024-07-02 | 2024-07-02 | 2024-07-03 | 2024-07-17 | 2024-07-16 | 2024-07-25 | 2024-07-25 | 2024-08-08 | 2024-08-13 |  |  |  |  | FS | 2024-08-13 | IS | 2024-11-06 |  |  |  |  | FS | 2024-08-14 | 2024-11-08 | [7 empty] | 2024-08-30 |  |  |  | 2024-08-27 | 2024-12-02 | [6 empty] | 2024-08-30 | 2024-12-02 | [7 empty] | 2024-09-03 | 2024-12-03 | [10 empty] | 2024-10-08 | 2025-01-16 | [5 empty] | 2024-09-27 | 2025-01-07 | [7 empty] | 2024-09-30 | 2025-01-07 | [16 empty] | 2024-10-18 | [7 empty] | 2024-10-18 | [9 empty] | 2025-01-10 |  | 2025-01-10 |  | 2025-02-24 | [6 empty] | 663419 | 2025-01-06 |  |  | 2025-07-22 | 2021-07-13: 2025-02-26; 2021-07-13: 2025-02-26 | [9 empty] | 0 |  |  |  | Q4 2024 | [15 empty] | TRUE | FALSE |  | 2025-02-26 | 2025-02-26 | 2025 | 2025 | 2025
887 |  | Govinda Neupane |  | 2024-06-18 | [31 empty] | 4 - ANDO |  | 400D1 | 738 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Chrissi Ramsey | SolAmerica Energy, LLC | SolAmerica Energy LLC | ME Oxford Noonan / Farmers Hill | 2000417923 | 30016151729 | Solar | [5 empty] | 44.6162 | -70.715 | Farmers Hill Road |  | Farmers Hill Road | Andover | 8 | ANDOVER | 400D1 | 400T1 | 12.47 | 9310-L0112-0120-0010-ED00086 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2024-06-26 | 2024-07-03 | 2024-06-26 | 2024-07-03 | 2024-07-03 | 2024-07-05 | 2024-07-18 | 2024-07-16 | 2024-07-25 | 2024-07-25 | 2024-08-08 | 2024-08-13 |  |  |  |  | FS | 2024-08-13 | IS | 2024-10-28 |  |  |  |  | FS | 2024-08-14 | 2024-10-28 | [7 empty] | 2024-08-16 |  |  |  | 2024-08-27 | 2024-10-28 | [6 empty] | 2024-08-27 | 2024-11-11 | [7 empty] | 2024-08-27 | 2024-11-11 | [10 empty] | 2024-10-02 | 2024-12-27 | [5 empty] | 2024-10-02 | 2024-12-27 | [7 empty] | 2024-10-02 | 2024-12-27 | [7 empty] | 2024-10-08 | 2024-01-06 | [7 empty] | 2024-10-11 | 2025-01-17 | [6 empty] | 2024-10-11 | 2025-01-17 |  |  |  | 2024-10-11 |  |  |  |  | 2025-02-12 |  | 2025-02-12 |  | 2025-03-13 | [6 empty] | 917783 | 2024-12-27 |  |  | 2025-07-14 | 2021-07-13: 2025-03-14; 2021-07-13: 2025-03-14 | [9 empty] | 0 |  |  |  | Q4 2024 | [15 empty] | TRUE | FALSE |  | 2025-03-14 | 2025-03-14 | 2025 | 2025 | 2025
888 |  | Eben Snow | Brent Brooks | 2024-06-18 | [31 empty] | 6 - BRID |  | 406D2 | 843 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Chrissi Ramsey | SolAmerica Energy, LLC | SOLAMERICA ENERGY LLC | PERLEY RD ME_CUMBERLAND_CHAPLAIN | 2000209571 | 30016151703 | Solar | [5 empty] | 43.9853 | -70.6598 | Perley Road |  | Perley Road | Naples | 23 | BRIDGTON | 406D2 | 406T1 | 12.47 | 9310-L0119-4040-0068-ED00025 |  | NOT IMPACTED | NOT IMPACTED |  | Yes | [6 empty] | 2024-06-26 | 2024-07-03 | 2024-06-26 | 2024-07-03 | 2024-07-03 | 2024-07-05 | 2024-07-18 | 2024-07-11 | 2024-07-12 | 2024-07-12 | 2024-07-26 | 2024-07-26 | 2024-10-07 |  |  |  | FS | 2024-07-29 | IS | 2024-10-07 |  |  |  |  | FS | 2024-07-29 | 2024-10-08 | [7 empty] | 2024-08-06 | 2024-10-08 |  |  | 2024-08-09 | 2024-11-11 | [6 empty] | 2024-08-13 | 2024-11-11 | [7 empty] | 2024-08-13 | 2024-11-11 | [10 empty] | 2024-09-18 | 2024-12-27 | [5 empty] | 2024-09-11 | 2024-12-27 | [7 empty] | 2024-09-17 | 2024-12-27 | [7 empty] | 2024-09-25 | 2024-01-06 | [7 empty] | 2024-10-01 | 2025-01-17 | [6 empty] | 2024-10-01 | 2025-01-17 | [8 empty] | 2025-02-12 |  | 2025-02-18 |  | 2025-03-20 | [6 empty] | 1513049 | 2024-12-27 |  |  | 2025-12-02 | 2021-07-13: 2025-03-24; 2021-07-13: 2025-03-24 | [9 empty] | 0 |  |  |  | Q2 2026 | [15 empty] | TRUE | FALSE |  | 2025-03-24 | 2025-03-24 | 2025 | 2025 | 2025
889 |  | Lanie Patterson | Brent Brooks | 2024-06-26 | [15 empty] | 2024-09-05 | wthdw | [13 empty] | 805 | 9 - MANC |  | 233D1 | 805 | Yes | WITHDRAWN | WITHDRAWN |  | Andre Bonacorsi | Invaleon Technologies Corp | VANGUARD SOLAR ORIGINATION LLC | 29 RANGE WAY / MANCHESTER ME 04351 | 2000428616 | 30015988295 | Solar | [5 empty] | 44.324 | -69.8442 | 29 Range Way | 29 | Range Way | Manchester | 3.01 | MANCHESTER | 233D1 | 233T1 | 12.47 | 9310-L0063-3540-0073-ED00009 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2024-07-03 | 2024-07-11 | 2024-07-03 | 2024-07-11 | 2025-07-29 | 2025-07-29 | 2025-08-12 | 2025-07-30 | 2025-08-01 | 2025-08-01 | 2025-08-15 |  |  | 2025-08-19 |  |  | CS | 2025-08-19 | [6 empty] | CS |  |  | 2025-08-21 | [106 empty] | 2025-09-22 | [17 empty] | 0 |  |  |  | Q2 2024 | [15 empty] | TRUE | FALSE |  | 0 | 0 | 1900 | 1900 | 1900
890 |  | Govinda Neupane |  | 2024-07-02 | [31 empty] | 8 - SKSS | 1 - SKSS | 854D2 | 663 |  | EXECUTED | EXECUTED |  | Andre Bonacorsi | Invaleon Technologies Corp | NEW BALANCE ATHLETICS INC | 17A Walnut St Skowhegan Solar | 2800288229 | 30016039106 | Solar | 600 | 0.6 | 840.4 |  |  | 44.7642 | -69.7079 | 17A Walnut Street | 17 | Walnut Street | Skowhegan | 5 | SKOWHEGAN SOUTH SIDE | 854D2 | 854T1 | 12.47 | 9310-L0433-5330-0124-PM00001 |  |  |  |  | Yes | [6 empty] | 2024-07-10 | 2024-07-17 | 2024-07-08 | 2024-07-12 | 2024-07-12 | 2024-07-15 | 2024-07-26 | 2024-07-16 | 2024-07-18 | 2024-07-18 | 2024-08-01 |  |  | 2024-07-22 |  |  | CS | 2024-07-22 | [6 empty] | CS |  |  | 2024-07-23 | [7 empty] | 2024-08-06 |  |  |  | 2024-08-09 | [8 empty] | 2024-08-09 | [8 empty] | 2024-08-09 | [11 empty] | 2024-10-14 | [6 empty] | 2024-10-08 | [8 empty] | 2024-10-08 | [8 empty] | Waived | [8 empty] | Waived | [7 empty] | Waived | [7 empty] | 2024-10-08 |  | 2024-10-08 |  | 2024-11-06 | [6 empty] | 166113 | 2024-10-07 |  |  |  | 2021-07-13: 2024-11-07; 2021-07-13: 2024-11-07 | [9 empty] | 0 |  |  |  | Q4 2024 | [15 empty] | TRUE | FALSE |  | 2024-11-07 | 2024-11-07 | 2024 | 2024 | 2024
891 |  | Marshall Ripley | Rick Duperre | 2024-07-18 | [31 empty] | 2 -RIGB |  | 650D4 | 812 |  | WITHDRAWN | WITHDRAWN |  | Michael Brigandi | New Leaf Energy, Inc | 510 PV PROJECT DEVELOPMENT LLC | 385 MAIN ST SOUTH PORTLAND | 2000113260 | 30015784546 | Battery | [5 empty] | 43.6279 | -70.2961 | 385 Main St | 385 | Main St | South Portland | 51.01 | RIGBY | 650D4 | 650T2 | 12.47 | 9310-L0309-5430-0225-ED00203 |  | NOT IMPACTED | NOT IMPACTED |  | Yes | [6 empty] | 2024-07-25 | 2024-08-01 | 2024-07-25 | 2024-08-01 | 2024-08-01 | 2024-08-05 | 2024-08-16 | 2024-08-06 | 2024-08-28 | 2024-08-28 | 2023-09-12 |  |  | 2024-08-29 |  |  | CS | 2024-08-29 | [9 empty] | 2024-08-29 | [7 empty] | 2025-06-11 |  |  |  | 2025-06-12 | [8 empty] | 2025-06-13 | [8 empty] | 2025-06-13 | [11 empty] | 2025-08-19 | [6 empty] | 2025-08-19 | [8 empty] | 2025-08-19 | [8 empty] | 2025-08-20 | [8 empty] | 2025-08-26 | [7 empty] | 2025-08-26 | [18 empty] | 7651159 | 2025-08-18 |  |  | 2025-09-17 | [17 empty] | 0 |  |  |  | Q4 2026 | [15 empty] | TRUE | FALSE |  | 0 | 0 | 1900 | 1900 | 1900
892 |  | Marshall Ripley | Rick Duperre | 2024-07-18 | [31 empty] | 4 - PLHL |  | 644D1 | 753 |  | WITHDRAWN | WITHDRAWN |  | Michael Brigandi | New Leaf Energy, Inc | 510 PV PROJECT DEVELOPMENT LLC | 15 RIGBY RD / SCARBOROUGH ME 04074 | 2000113260 | 30016064088 | Battery | [5 empty] | 43.6032 | -70.2997 | 15 Rigby Road | 15 | Rigby Road | Scarborough | 3.2 | PLEASANT HILL | 644D1 | 644T2 | 12.47 | 9310-L0285-5200-0045-ED00006 |  |  |  |  | Yes | [6 empty] | 2024-07-25 | 2024-08-01 | 2024-07-25 | 2024-08-01 | 2024-08-01 | 2024-08-05 | 2024-08-16 | 2024-08-06 | 2024-08-28 | 2024-08-28 | 2023-09-12 |  |  | 2024-08-29 |  |  | CS | 2024-08-29 | [9 empty] | 2024-08-29 | [7 empty] | 2025-06-11 |  |  |  | 2025-06-12 | [8 empty] | 2025-06-13 | [8 empty] | 2025-06-13 | [11 empty] | 2025-08-19 | [6 empty] | 2025-08-19 | [8 empty] | 2025-08-19 | [8 empty] | 2025-08-20 | [8 empty] | 2025-08-26 | [7 empty] | 2025-08-26 | [18 empty] | 7116624 | 2025-08-18 |  |  | 2025-09-17 | [17 empty] | 0 |  |  |  | Q4 2026 | [15 empty] | TRUE | FALSE |  | 0 | 0 | 1900 | 1900 | 1900
893 |  | Marshall Ripley | Rick Duperre | 2024-07-18 | [31 empty] | 1 - BRAV |  | 611D1 |  |  | WITHDRAWN | WITHDRAWN |  | Michael Brigandi | New Leaf Energy, Inc | 510 PV PROJECT DEVELOPMENT LLC | 170 WARREN AVE / WESTBROOK ME 04092 | 2000113260 | 30016064104 | Battery | [5 empty] | 43.6853 | -70.3413 | 170 Warren Avenue | 170 | Warren Avenue | Westbrook | 19 | BRIGHTON AVE | 611D1 | 611T1 | 12.47 | 9310-L0222-6320-0206-ED00019 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2024-07-25 | 2024-08-01 | 2024-07-25 | 2024-08-01 | 2024-08-01 | 2024-08-05 | 2024-08-16 | 2024-08-06 | 2024-08-28 | 2024-08-28 | 2023-09-12 |  |  | 2024-08-29 |  |  | CS | 2024-08-29 | [9 empty] | 2024-08-29 | [106 empty] | 2025-06-17 | [17 empty] | 0 |  |  |  | Q4 2026 | [15 empty] | TRUE | FALSE |  | 0 | 0 | 1900 | 1900 | 1900
894 |  | Marshall Ripley | Rick Duperre | 2024-07-18 | [31 empty] | 5 - SPST |  | 668D1 | 327 |  | WITHDRAWN | WITHDRAWN |  | Michael Brigandi | New Leaf Energy, Inc | 510 PV PROJECT DEVELOPMENT LLC | 26 THOMAS DR / WESTBROOK ME 04092 | 2000113260 | 30016064138 | Battery | [5 empty] | 43.6504 | -70.3509 | 26 Thomas Drive | 26 | Thomas Drive | Westbrook | 16 | SPRING STREET | 668D1 | 668T3 | 12.47 | 9310-L0335-6320-0038-ED00009 |  |  |  |  | Yes | [6 empty] | 2024-07-25 | 2024-08-01 | 2024-07-25 | 2024-08-01 | 2024-08-01 | 2024-08-05 | 2024-08-16 | 2024-08-06 | 2024-08-29 | 2024-08-29 | 2024-09-13 |  |  | 2024-09-13 |  |  | CS | 2024-09-13 | [6 empty] | CS |  |  | 2024-09-17 | [7 empty] | 2025-06-11 |  |  |  | 2025-06-12 | [8 empty] | 2025-06-13 | [8 empty] | 2025-06-13 | [11 empty] | 2025-08-19 | [6 empty] | 2025-08-19 | [8 empty] | 2025-08-19 | [8 empty] | 2025-08-20 | [8 empty] | 2025-08-26 | [7 empty] | 2025-08-26 | [18 empty] | 7779720 | 2025-08-18 |  |  | 2025-09-17 | [17 empty] | 0 |  |  |  | Q4 2026 | [15 empty] | TRUE | FALSE |  | 0 | 0 | 1900 | 1900 | 1900
895 |  | Eben Snow | Brent Brooks | 2024-07-18 | [31 empty] | 8 - NORW |  | 435D1 | 814 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Michael Brigandi | New Leaf Energy, Inc | 510 PV PROJECT DEVELOPMENT LLC | 279 OXFORD ST SOUTH PARIS | 2000113260 | 30015624759 | Solar/Battery | [5 empty] | 44.208 | -70.5145 | 279 Oxford Street | 279 | Oxford Street | South Paris | 37 | NORWAY | 435D1 | 435T2 | 12.47 | 9310-L0168-4500-0117-ED00013 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2024-07-25 | 2024-08-01 | 2024-07-25 | 2024-08-01 | 2024-08-01 | 2024-08-05 | 2024-08-16 | 2024-08-06 | 2024-08-13 | 2024-08-13 | 2024-08-27 |  |  | 2024-08-13 |  |  | CS | 2024-08-13 | [6 empty] | CS |  |  | 2024-08-14 | [11 empty] | 2024-08-29 | [8 empty] | 2024-08-29 | [8 empty] | 2024-08-29 | [11 empty] | 2024-11-04 | [6 empty] | 2024-11-04 | [8 empty] | 2024-11-04 | [8 empty] | 2024-11-13 | [8 empty] | 2024-11-19 | [7 empty] | 2024-11-20 | [7 empty] | 2024-12-10 |  | 2024-12-18 |  | 2024-12-30 | [6 empty] | 254438 | 2024-11-04 |  |  | 2025-11-04 | 2021-07-13: 2025-01-03; 2021-07-13: 2025-01-03 | [9 empty] | 0 |  |  |  | Q4 2026 |  |  |  | Requested | [11 empty] | TRUE | FALSE |  | 2025-01-03 | 2025-01-03 | 2025 | 2025 | 2025
896 |  | Lanie Patterson | Brent Brooks | 2024-07-24 | 2024-09-18 | wthdw | [29 empty] | 2 - PITT |  | 842D1 | 190 | Yes | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Michael Parker | Loki Solar | Spruce Solar LLC | Horseback Rd Pittsfield | 2000459925 | 30016465392 | Solar | [5 empty] | 44.7667 | -69.3549 | Horseback Road |  | Horseback Road | Pittsfield | 58 | PITTSFIELD | 842D1 | 842T1 | 12.47 | 9310-L0425-4650-0081-ED00060 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2024-07-31 | 2024-08-07 | 2024-07-31 | 2024-08-07 | 2024-08-07 | 2024-08-08 | 2024-08-21 | 2024-08-08 | 2024-08-16 | 2024-08-16 | 2024-08-30 |  |  | 2024-08-22 |  |  | CS | 2024-08-22 | [6 empty] | CS |  |  | 2024-08-22 |  |  | 2024-09-18 |  |  |  |  | 2024-09-06 |  |  |  | 2024-09-05 |  |  | N/A | [5 empty] | 2024-09-06 |  |  | 2024-10-04 | [5 empty] | 2024-09-06 |  |  | 2024-10-04 | [8 empty] | 2024-12-12 | [6 empty] | N/A |  |  | 2024-11-18 | [5 empty] | 2024-11-18 |  |  | 2024-10-18 | [5 empty] | 2024-11-12 |  |  | 2024-10-21 | [5 empty] | 2024-12-02 |  |  | 2024-12-02 | [7 empty] | 2024-12-02 |  |  |  |  | 2024-12-20 |  | 2024-12-20 |  | 2025-01-21 | [6 empty] | 503958 | 2024-11-13 |  |  | 2025-09-02 | 2021-07-13: 2025-01-22; 2021-07-13: 2025-01-22 | [9 empty] | 0 |  |  |  | Q3 2025 | [15 empty] | TRUE | FALSE |  | 2025-01-22 | 2025-01-22 | 2025 | 2025 | 2025
897 |  | Ben Brooks | KRISTOFER COLEMAN | 2024-07-25 | [31 empty] | 4 - FREE |  | 225D4 | 856 |  | WITHDRAWN | WITHDRAWN |  | Michael Brigandi | New Leaf Energy, Inc | 510 PV PROJECT DEVELOPMENT LLC | 291 US Route 1 / FREEPORT | 2000113260 | 30016082874 | Battery | [5 empty] | 43.8253 | -70.1365 | 291 US-1 | 291 | US-1 | Freeport | 113.2 | FREEPORT | 225D4 | 225T1 | 12.47 | 9310-L0056-2110-0214-ED00022 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2024-08-01 | 2024-08-08 | 2024-08-01 | 2024-08-08 | 2025-01-23 |  | 2025-02-05 | [123 empty] | n/a |  |  |  | 2025-06-17 | [17 empty] | 0 |  |  |  | Q4 2026 | [15 empty] | TRUE | FALSE |  | 0 | 0 | 1900 | 1900 | 1900
898 |  | Marshall Ripley | Rick Duperre | 2024-08-01 | [31 empty] | 4 - MOSH |  | 635D2 |  |  | WITHDRAWN | WITHDRAWN |  | Michael Brigandi | New Leaf Energy, Inc | 510 PV PROJECT DEVELOPMENT LLC | 37 Bartlett Rd Gorham Me | 2000113260 | 30016096304 | Battery | [5 empty] | 43.6805 | -70.3889 | 37 Bartlett Road | 37 | Bartlett Road | Gorham | 5 | MOSHERS | 635D2 | 635T2 | 12.47 | 9310-L0271-2240-0004-ED00018 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2024-08-08 | 2024-08-15 | 2024-08-08 | 2024-08-15 | 2024-08-15 | 2024-08-15 | 2024-08-29 | 2024-08-23 | 2024-08-28 | 2024-08-28 | 2023-09-12 |  |  | 2024-08-29 |  |  | CS | 2024-08-29 | [9 empty] | 2024-08-29 | [102 empty] | n/a |  |  |  | 2025-06-17 | [17 empty] | 0 |  |  |  | Q4 2026 | [15 empty] | TRUE | FALSE |  | 0 | 0 | 1900 | 1900 | 1900
899 |  | Govinda Neupane |  | 2024-08-26 | [9 empty] | 2024-10-21 | L2 With |  | 2025-08-07 | wthdw | [17 empty] | 6 - DEXT |  | 813D3 | 657 | Yes | WITHDRAWN | WITHDRAWN |  | Paula J Fitzgerald | Novel Energy Solutions LLC | ME DAVIS SKIMMER LANE CSG LLC | 80 Ripley Rd Dexter | 2000348434 | 30016063858 | Solar | [5 empty] | 45.0079 | -69.2999 | 0 Ripley Rd |  | Ripley Rd | Dexter | 1.3 | DEXTER | 813D3 | 813T2 | 12.47 | 9310-L0395-1610-0080-ED00004 |  |  |  |  | Yes | [6 empty] | 2024-09-03 | 2024-09-10 | 2024-09-03 | 2024-09-10 | 2026-03-26 | 2026-04-01 | 2026-04-10 | 2025-04-20 | 2026-04-21 | 2026-04-21 | 2026-05-05 | 2026-05-05 |  |  |  |  | FS | 2026-05-05 | [6 empty] | FS | 2026-05-06 | [108 empty] | 2026-06-11 | [17 empty] | 0 | [19 empty] | TRUE | FALSE |  | 0 | 0 | 1900 | 1900 | 1900
900 |  |  | Anthony Boucher | 2024-09-03 | 2024-10-09 | wthdw | RQP-2 | 2024-10-28 | wthdw | RQP-1 | 2025-02-11 | L2_Bump | [23 empty] | 7 - THCR |  | 246D3 | 628 | Yes | WITHDRAWN | WITHDRAWN |  | Corwin Lavoie | Nexamp, Inc | NEXAMP SOLAR LLC | 291 cushing rd warren me | 2000114877 | 30015665125 | Solar | [5 empty] | 44.0725 | -69.2243 | 291 Cushing Road | 291 | Cushing Road | Warren | 112 | THOMASTON CREEK | 246D3 | 246T1 | 12.47 | 9310-L0083-6160-0036-ED00012 |  |  |  |  | Yes | [6 empty] | 2024-09-10 | 2024-09-17 | 2024-09-10 | 2024-09-17 | 2024-09-17 | 2024-09-19 | 2024-10-01 | 2024-09-23 | 2024-09-27 | 2024-09-27 | 2024-10-11 |  |  | 2024-09-27 |  |  | CS | 2024-09-27 | [6 empty] | CS |  |  | 2024-10-30 |  |  | 2025-02-12 |  |  |  |  | 2024-11-15 |  |  |  | 2024-12-06 |  |  | 2025-02-21 | [5 empty] | 2024-12-06 |  |  | 2025-02-21 | [5 empty] | 2024-11-15 |  |  | 2025-02-21 | [8 empty] | 2025-01-24 | [6 empty] | 2025-01-15 |  |  | 2025-04-23 | [5 empty] | 2025-01-15 |  |  | 2025-04-24 | [5 empty] | 2025-01-20 |  |  | N/A | [5 empty] | 2025-01-23 |  |  | N/A |  |  |  |  | 2025-02-13 |  |  | N/A |  |  |  |  | 2025-02-10 |  | 2025-02-11 | [8 empty] | 204461 | 2025-01-10 | 379815 | 2025-05-06 | 2025-07-07 | [17 empty] | 0 |  |  |  | Q4 2026 | [15 empty] | FALSE | FALSE |  | 0 | 0 | 1900 | 1900 | 1900
901 |  | Lanie Patterson | Brent Brooks | 2024-09-03 | [31 empty] | 3 - CLIN | 1 - CLIN | 810D1 | 684 |  | EXECUTED | EXECUTED |  | Corwin Lavoie | Nexamp, Inc | Clinton Renewables LLC | 65 MUTTON LANE CLINTON | 2000488158 | 30016857010 | Solar | 975 | 0.975 | 1375.92 |  |  | 44.6433 | -69.5058 | 15 Mutton Lane | 15 | Mutton Lane | Clinton | 1 | CLINTON | 810D1 | 810T1 | 12.47 | 9310-L0390-1170-0043-ED00001 |  | COST SHARING | COST SHARING (380,000) | 68295 | Yes | [6 empty] | 2024-09-10 | 2024-09-17 | 2024-09-10 | 2024-09-17 | 2024-09-17 | 2024-09-19 | 2024-10-01 | 2024-09-23 | 2024-09-25 | 2024-09-25 | 2024-10-09 |  |  | 2024-09-25 |  |  | CS | 2024-09-25 | [6 empty] | CS |  |  | 2024-09-25 | [7 empty] | 2024-10-04 |  |  |  | 2024-10-04 | [8 empty] | 2024-10-04 | [8 empty] | 2024-10-04 | [11 empty] | 2024-12-12 | [6 empty] | 2024-12-09 | [8 empty] | 2024-12-09 | [8 empty] | 2024-12-13 | [8 empty] | 2024-09-20 | [7 empty] | 2024-09-20 | [7 empty] | 2024-12-20 |  | 2024-12-23 | 2025-07-03 | 2025-01-04 | 2025-07-11 | [5 empty] | 406804 | 2024-12-09 |  |  |  | 2021-07-13: 2025-01-08; 2021-07-13: 2025-01-08; 2021-07-13: 2025-07-14; 2021-07-13: 2025-07-17 | [9 empty] | 0 |  |  |  | Q4 2026 |  |  |  | Requested | [11 empty] | FALSE | FALSE |  | 2025-01-08 | 2025-01-08 | 2025 | 2025 | 2025
902 |  | Eben Snow | Brent Brooks | 2024-09-05 | [6 empty] | 2025-11-04 | wthdw | [22 empty] | 895 | 9 - NORW | 2 - NORW | 435D1 | 895 | Yes | EXECUTED | EXECUTED |  | Jacob Freudenberger | Paddle Energy LLC | PE BAXTER LLC | KILGORE RD SOUTH PARIS 04281 | 2000441934 | 30016184837 | Solar | 999 | 0.999 | 1256.64 |  |  | 44.2042 | -70.5193 | 1 Kilgore Road | 1 | Kilgore Road | South Paris | 12 | NORWAY | 435D1 | 435T2 | 12.47 | 9310-L0168-4500-0117-ED00001 |  | GFOV TBD During Study Phase | GFOV TBD During Study Phase |  | Yes | [6 empty] | 2024-09-12 | 2024-09-19 | 2024-09-12 | 2024-09-19 | 2025-01-03 | 2024-01-07 | 2024-01-17 | 2025-01-15 | 2025-01-22 | 2025-01-22 | 2025-02-05 |  |  | 2025-01-31 |  |  | CS | 2025-01-31 | [6 empty] | CS |  |  | 2025-01-31 |  |  | 2025-11-05 | [8 empty] | 2025-02-11 |  |  | 2025-11-14 | [5 empty] | 2025-02-12 |  |  | 2025-11-14 | [5 empty] | 2025-02-12 |  |  | 2025-11-14 | [8 empty] | 2025-04-17 | [6 empty] | 2025-04-16 |  |  | 2026-01-21 | [5 empty] | 2025-04-17 |  |  | 2026-01-22 | [5 empty] | N/A | [8 empty] | N/A | [7 empty] | N/A | [7 empty] | 2025-04-22 |  | 2025-04-22 | 2026-01-22 | 2025-04-23 | 2026-02-20 | [5 empty] | 381073 | 2025-04-15 | 216563 | 2026-01-21 |  | 2021-07-13: 2025-04-24; 2021-07-13: 2025-04-24; 2021-07-13: 2026-02-23; 2021-07-13: 2026-02-23 | [9 empty] | 0 |  |  |  | Q4 2025 | [15 empty] | FALSE | FALSE |  | 2025-04-24 | 2025-04-24 | 2025 | 2025 | 2025
903 |  | Marshall Ripley | Rick Duperre | 2024-09-06 | [31 empty] | 9- BONE | 1 - BONE | 610D1 | 679 |  | EXECUTED | EXECUTED |  | Jacob Freudenberger | Paddle Energy LLC | PE BRACKEN LLC | 38 KILLICK POND RD HOLLIS 04042 | 2000441936 | 30016184852 | Solar | 999 | 0.999 | 1256.64 |  |  | 43.6574 | -70.6603 | 38 Killick Pond Road | 38 | Killick Pond Road | Hollis | 113 | BONNY EAGLE | 610D1 | 610T4 | 12.47 | 9310-L0220-2647-0080-ED00025 |  | NOT IMPACTED | NOT IMPACTED |  | Yes | [6 empty] | 2024-09-13 | 2024-09-20 | 2024-09-13 | 2024-09-20 | 2024-09-20 | 2024-09-25 | 2024-10-04 | 2024-10-01 | 2024-10-03 | 2024-10-03 | 2024-10-18 |  |  | 2024-10-04 |  | 2025-02-12 | CS | 2024-10-04 | [6 empty] | CS |  |  | 2024-10-08 |  | 2025-02-20 | [5 empty] | 2024-10-25 |  |  |  | 2024-10-21 | [8 empty] | 2024-10-25 | [8 empty] | 2024-10-25 | [11 empty] | 2025-01-03 | [6 empty] | 2025-01-03 | [8 empty] | 2025-01-06 | [8 empty] | 2025-01-16 | [8 empty] | 2025-01-17 | [7 empty] | 2025-01-17 | [7 empty] | 2025-03-19 |  | 2025-03-20 |  | 2025-03-28 | [6 empty] | 476930 | 2025-01-02 |  |  |  | 2021-07-13: 2025-04-01; 2021-07-13: 2025-04-01 | [9 empty] | 0 |  |  |  | Q4 2025 | [15 empty] | FALSE | FALSE |  | 2025-04-01 | 2025-04-01 | 2025 | 2025 | 2025
904 |  | Lanie Patterson | Brent Brooks | 2024-09-09 | [31 empty] | 8 - RICH |  | 240D1 | 830 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Emma Plocienniik | Nexamp, Inc | NEXAMP SOLAR LLC | 585 Lincoln St / Richmond | 2000430092 | 30016200807 | Solar | [5 empty] | 44.1232 | -69.818 | 585 Lincoln Street | 585 | Lincoln Street | Richmond | 9 | RICHMOND | 240D1 | 240T1 | 12.47 | 9310-L0074-4940-0067-ED00179 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2024-09-16 | 2024-09-23 | 2024-09-16 | 2024-09-23 | 2024-09-23 | 2024-09-25 | 2024-10-07 | 2024-09-27 | 2024-10-02 | 2024-10-02 | 2024-10-17 |  |  | 2024-10-02 |  |  | CS | 2024-10-02 | [6 empty] | CS |  |  | 2024-10-08 | [7 empty] | 2024-10-18 |  |  |  | 2024-10-18 |  |  | 2024-10-18 | [5 empty] | 2024-10-18 | [8 empty] | 2024-10-18 | [11 empty] | 2024-12-26 | [6 empty] | 2024-12-16 | [8 empty] | 2024-12-16 | [8 empty] | 2024-12-17 | [8 empty] | 2024-12-20 | [7 empty] | 2024-12-20 | [7 empty] | 2025-01-13 |  | 2025-01-14 |  | 2024-02-13 | [6 empty] | 2825498 | 2024-12-16 | n/a | n/a | 2025-07-28 | 2021-07-13: 2025-02-13; 2021-07-13: 2025-02-13 | [9 empty] | 0 |  |  |  | Q4 2026 | [15 empty] | TRUE | FALSE |  | 2025-02-13 | 2025-02-13 | 2025 | 2025 | 2025
905 |  | Rigel Paradise | Rick Duperre | 2024-09-10 | [31 empty] | 5 - HITP |  | 692D1 | 596 |  | WITHDRAWN | WITHDRAWN |  | Emma Plocienniik | Nexamp, Inc | NEXAMP SOLAR LLC | 77-133 Cumberland st / Cornish | 2000114877 | 30016220599 | Solar | [5 empty] | 43.8055 | -70.7862 | 77-133 Cumberland St | 77-133 | Cumberland St | Cornish | 9 | HIRAM TAP | 692D1 | 692T1 | 34.5 | 9310-L0372-1240-0027-ED00047 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2024-09-17 | 2024-09-24 | 2024-09-17 | 2024-09-24 | 2025-01-08 | 2025-01-08 | 2025-01-23 | 2025-01-10 | 2025-01-16 | 2025-01-16 | 2025-01-31 | [123 empty] | 2025-02-04 | [17 empty] | 0 |  |  |  | Q4 2026 | [15 empty] | TRUE | FALSE |  | 0 | 0 | 1900 | 1900 | 1900
906 |  | Govinda Neupane |  | 2024-09-11 | 2024-12-20 | wthdw | RQP-1 | 2024-12-20 | L2_with | RQP-1 | 2024-01-06 | studywaived | [23 empty] | 4 - CORI |  | 811D1 | 682 |  | WITHDRAWN | WITHDRAWN |  | Michael Parker | Loki Solar | SOLAR LEASING LLC | Route 11 Corinna ME | 2000422871 | 30016205947 | Solar | [5 empty] | 44.9263 | -69.247 | Exeter Rd |  | Exeter Rd | Corinna | 30 | CORINNA | 811D1 | 811T1 | 12.47 | 9310-L0391-1220-0015-ED00052 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2024-09-18 | 2024-09-25 | 2024-09-18 | 2024-09-25 | 2024-09-25 | 2024-09-26 | 2024-10-09 | 2024-10-07 | 2024-10-10 | 2024-10-10 | 2024-10-25 |  |  | 2024-10-21 |  |  | CS | 2024-10-21 | [6 empty] | CS |  |  | 2024-10-21 |  |  | 2024-12-20 | [8 empty] | 2024-10-24 | [6 empty] | 2024-11-11 |  | 2024-10-24 | [8 empty] | 2024-11-11 | [72 empty] | n/a | n/a | n/a | n/a | 2025-02-06 | [17 empty] | 0 | [19 empty] | TRUE | FALSE |  | 0 | 0 | 1900 | 1900 | 1900
907 |  | Govinda Neupane |  | 2024-09-11 | 2024-12-16 | wthdw | [29 empty] | 8 - ANSO |  | 801D1 | 837 | Yes | WITHDRAWN | WITHDRAWN |  | Emma Plocienniik | Nexamp, Inc | NEXAMP SOLAR LLC | ANSON RD STARKS ME 04911 | 2000444503 | 30016222249 | Solar | [5 empty] | 44.749 | -69.9063 | 843 Industry Rd | 843 | Industry Rd | Starks | 15 | ANSON | 801D1 | 801T1 | 12.47 | 9310-L0379-5510-0017-ED00008 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2024-09-18 | 2024-09-25 | 2024-09-18 | 2024-09-25 | 2024-09-25 | 2024-09-26 | 2024-10-09 | 2024-09-30 | 2024-10-02 | 2024-10-02 | 2024-10-17 |  |  | 2024-10-08 |  |  | CS | 2024-10-08 | [6 empty] | CS |  |  | 2024-10-08 |  |  | 2024-12-16 |  |  |  | 2024-11-08 |  |  |  |  | 2024-11-08 |  |  | 2024-12-20 | [5 empty] | 2024-11-08 | [8 empty] | 2024-11-12 |  |  |  | 2025-01-08 | [7 empty] | 2024-03-10 | [6 empty] | 2024-03-10 |  |  | N/A | [5 empty] | 2025-03-10 | [8 empty] | 2025-03-24 | [8 empty] | 2025-03-25 | [7 empty] | 2025-03-25 | [18 empty] | 3421928 |  |  |  | 2025-04-09 | [17 empty] | 0 |  |  |  | Q4 2026 | [15 empty] | TRUE | FALSE |  | 0 | 0 | 1900 | 1900 | 1900
908 |  | Ben Brooks | Anthony Boucher | 2024-09-12 | [6 empty] | 2025-11-26 | wthdw | [23 empty] | 11 - BUCK |  | 806D2 | 799 | Yes | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Karl Wiedenmann | SolAmerica Energy, LLC | SOLAMERICA ENERGY LLC | 1629 Castine Penobscot | 2000209571 | 30016171974 | Solar | [5 empty] | 44.4836 | -68.7652 | 1629 Castine Road | 1629 | Castine Road | Penobscot | 235 | BUCKSPORT | 806D2 | 806T3 | 34.5 | 9310-L0386-4580-0054-ED00067 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2024-09-19 | 2024-09-26 | 2024-09-19 | 2024-09-26 | 2024-09-26 | 2024-10-08 | 2024-10-10 | 2024-10-09 | 2024-10-10 | 2024-10-10 | 2024-10-25 | 2024-10-28 |  |  |  |  | FS | 2024-10-28 | IS | 2025-01-03 |  |  |  |  | FS | 2024-10-28 | 2025-01-03 |  |  |  | 2025-11-24 | [7 empty] | 2024-11-18 | 2025-01-23 | [6 empty] | 2024-11-18 | 2025-01-23 | [7 empty] | 2024-11-18 | 2025-01-23 | [10 empty] | 2024-12-26 | 2025-03-07 | [5 empty] | 2024-12-26 | 2025-03-06 | [7 empty] | 2024-12-26 | 2025-03-06 | [7 empty] | N/A | 2025-03-07 | [7 empty] | N/A | 2025-03-14 | [6 empty] | N/A | 2025-03-14 | [8 empty] | 2025-04-04 |  | 2025-04-07 |  | 2025-04-07 | [6 empty] | 575049 | 2025-03-06 |  |  | 2025-12-08 | 2021-07-13: 2025-04-09; 2021-07-13: 2025-04-09 | [9 empty] | 0 |  |  |  | Q1 2026 | [15 empty] | TRUE | FALSE |  | 2025-04-09 | 2025-04-09 | 2025 | 2025 | 2025
909 |  | Govinda Neupane |  | 2024-09-12 | [12 empty] | 2025-01-22 | L2_With |  | 2025-02-04 | wthdw | [14 empty] | 11 - CARM |  | 808D2 | 833 |  | WITHDRAWN | WITHDRAWN |  | Karl Wiedenmann | SolAmerica Energy, LLC | SOLAMERICA ENERGY LLC | 365 Main Rd Carmel | 2000209571 | 30016171982 | Solar | [5 empty] | 44.8098 | -69.0051 | 365 Main Road | 365 | Main Road | Carmel | 44 | CARMEL | 808D2 | 808T1 | 12.47 | 9310-L0389-1020-0049-ED00205 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2024-09-19 | 2024-09-26 | 2024-09-19 | 2024-09-26 | [130 empty] | 2025-02-10 | [17 empty] | 0 | [19 empty] | TRUE | FALSE |  | 0 | 0 | 1900 | 1900 | 1900
910 |  | Govinda Neupane |  | 2024-09-12 | [12 empty] | 2025-01-22 | L2_With | RQP-5 | 2025-02-04 | wthdw |  | 2024-02-10 | wthdw |  | 2025-02-11 | Wthdw | [7 empty] | 909 | 12 - CARM |  | 808D3 | 909 | Yes | WITHDRAWN | WITHDRAWN |  | Karl Wiedenmann | SolAmerica Energy, LLC | SOLAMERICA ENERGY LLC | Horseback Rd Levant | 2000209571 | 30016172204 | Solar | [5 empty] | 44.8607 | -69.0149 | Horseback Road |  | Horseback Road | Levant | 53 | CARMEL | 808D3 | 808T2 | 12.47 | 9310-L0506-3220-0007-ED00089 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2024-09-19 | 2024-09-26 | 2024-09-19 | 2024-09-26 | 2025-02-11 | 2025-02-20 | 2025-02-26 | 2025-02-20 | 2025-03-03 | 2025-03-03 | 2025-03-17 | 2025-03-17 |  |  |  |  | FS | 2025-03-17 | [6 empty] | FS | 2025-03-17 | [8 empty] | 2025-03-17 |  |  |  | 2025-03-31 | [7 empty] | 2025-03-31 | [8 empty] | 2025-03-31 | [11 empty] | 2025-05-06 | [6 empty] | 2025-04-28 | [8 empty] | 2025-04-28 | [8 empty] | 2025-05-05 | [8 empty] | 2025-05-07 | [7 empty] | 2025-05-07 | [24 empty] | 2025-06-16 | [17 empty] | 0 |  |  |  | Q1 2026 | [15 empty] | TRUE | FALSE |  | 0 | 0 | 1900 | 1900 | 1900
911 |  | Govinda Neupane |  | 2024-09-12 | [12 empty] | 2025-01-22 | L2_With |  | 2025-02-04 | wthdw |  | 2024-02-10 | wthdw |  | 2025-02-11 | Wthdw |  | 2025-06-16 | Wthdw |  |  |  |  | 910 | 13 - CARM |  | 808D3 | 910 | Yes | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Ryan Coughlin | Perennial Renewables LLC | Perennial Levant Solar LLC | 11 Seldon Seen Ln Levant | 2000516925 | 30017276400 | Solar | [5 empty] | 44.8476 | -69.0112 | 11 Seldom Seen Lane | 11 | Seldom Seen Lane | Levant | 32 | CARMEL | 808D3 | 808T2 | 12.47 | 9310-L0506-3220-0007-ED00004 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2024-09-19 | 2024-09-26 | 2024-09-19 | 2024-09-26 | 2025-06-16 | 2025-06-24 | 2025-07-01 | 2025-06-30 | 2025-07-02 | 2025-07-02 | 2025-07-17 |  |  | 2025-07-17 |  |  | CS | 2025-07-17 | [6 empty] | CS |  |  | 2025-07-17 | [7 empty] | 2025-08-08 |  |  |  | 2025-08-08 | [8 empty] | 2025-08-08 | [8 empty] | 2025-08-08 | [11 empty] | 2025-10-14 | [6 empty] | 2025-10-14 | [8 empty] | 2025-10-14 | [8 empty] | 2025-10-20 | [8 empty] | 2025-10-21 | [7 empty] | 2025-10-21 | [7 empty] | 2025-11-20 |  | 2025-11-20 | 2025-12-05 | 2025-12-04 | 2025-12-05 | [5 empty] | 481458 | 2025-10-14 |  |  | 2026-06-29 | 2021-07-13: 2025-12-08; 2021-07-13: 2025-12-08; 2021-07-13: 2026-03-18; 2021-07-13: 2026-03-19 | [9 empty] | 0 |  |  |  | Q3 2026 |  |  |  | 10301245813 | [11 empty] | TRUE | FALSE |  | 2025-12-08 | 2025-12-08 | 2025 | 2025 | 2025
912 |  | Govinda Neupane |  | 2024-09-12 | [6 empty] | 2024-12-09 | wthdw |  | 2024-12-18 | wthdw |  | 2025-01-06 | wthdw | [17 empty] | 8 - DOVE |  | 815D2 | 545 | Yes | WITHDRAWN | WITHDRAWN |  | Karl Wiedenmann | SolAmerica Energy, LLC | SOLAMERICA ENERGY LLC | 107 Park St. Dover foxcroft | 2000209571 | 30016172220 | Solar | [5 empty] | 45.1968 | -69.2433 | 107 Park Street | 107 | Park Street | Dover-Foxcroft | 18 | DOVER | 815D2 | 815T2 | 12.47 | 9310-L0397-1650-0084-ED00036 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2024-09-19 | 2024-09-26 | 2024-09-19 | 2024-09-26 | 2024-09-26 | 2024-10-08 | 2024-10-10 | 2024-10-09 | 2024-10-11 | 2024-10-11 | 2024-10-28 | 2024-10-30 | 2025-05-02 |  |  |  | FS | 2024-10-30 | IS | 2025-05-02 |  |  |  |  | FS | 2025-01-31 | 2025-05-05 | [7 empty] | 2024-11-06 |  |  |  | 2025-02-18 | [7 empty] | 2024-11-26 | [8 empty] | 2025-02-18 | [11 empty] | 2025-03-25 | [6 empty] | 2025-03-25 | [8 empty] | 2025-03-25 | [8 empty] | 2026-03-26 | [8 empty] | 2025-04-07 | [7 empty] | 2025-04-07 | [20 empty] | n/a completed FS |  |  |  | 2025-06-06 | [17 empty] | 0 |  |  |  | Q4 2025 | [15 empty] | TRUE | FALSE |  | 0 | 0 | 1900 | 1900 | 1900
913 |  | Govinda Neupane |  | 2024-10-08 | [30 empty] | 815 | 9 - RUMF |  | 447D4 | 815 |  | WITHDRAWN | WITHDRAWN |  | Emma Plocienniik | Nexamp, Inc | NEXAMP SOLAR LLC | 220 Highland Terrace Mexico ME 0425 | 2000114877 | 30016294685 | Solar | [5 empty] | 44.5475 | -70.5197 | 220 Highland Terrace | 220 | Highland Terrace | Mexico | 22 | RUMFORD | 447D4 | 447T4 | 12.47 | 9310-L0189-3660-0040-ED00024 |  |  |  |  | Yes | [6 empty] | 2024-10-16 | 2024-10-23 | 2024-10-16 | 2024-10-23 | 2025-12-16 |  | 2025-12-31 | [127 empty] | 2025-01-07 | [17 empty] | 0 |  |  |  | Q4 2026 | [15 empty] | TRUE | FALSE |  | 0 | 0 | 1900 | 1900 | 1900
914 |  | Lanie Patterson | Brent Brooks | 2024-10-08 | [12 empty] | 2025-02-10 | studywaived | RQP-4 | 2025-04-15 | wthdw | RQP-3 | 2025-10-13 | L2_Bump | RQP-2 | [6 empty] | RQP-1 |  |  | 827 | 18 - MONM |  | 457D2 | 827 | Yes | WITHDRAWN | WITHDRAWN |  | Emma Plocienniik | Nexamp, Inc | NEXAMP SOLAR LLC | 65 Berry Rd Monmouth ME 04259 | 2000114877 | 30016294800 | Solar | [5 empty] | 44.2446 | -70.027 | 65 Berry Rd | 65 | Berry Rd | Monmouth | 127 | MONMOUTH | 457D2 | 457T2 | 12.47 | 9310-L0199-3740-0025-ED00039 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2024-10-16 | 2024-10-23 | 2024-10-16 | 2024-10-23 | 2026-04-02 | 2026-04-17 | 2026-04-16 | [127 empty] | 2026-04-24 | [17 empty] | 0 |  |  |  | Q4 2026 | [15 empty] | TRUE | FALSE |  | 0 | 0 | 1900 | 1900 | 1900
915 |  | Govinda Neupane |  | 2024-10-08 |  |  |  | 2024-10-30 | wthdw |  | 2025-01-30 | L2_Bump | [23 empty] | 4 - WILT |  | 885D1 | 482 | Yes | WITHDRAWN | WITHDRAWN |  | Michael Parker | Loki Solar | SOLAR LEASING LLC | 942 WELD RD WILTON ME | 2000422871 | 30016297167 | Solar | [5 empty] | 44.6329 | -70.2956 | 942 Weld Rd | 942 | Weld Rd | Wilton | 117 | WILTON | 885D1 | 885T1 | 12.47 | 9310-L0467-6380-0118-ED00030 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2024-10-16 | 2024-10-23 | 2024-10-16 | 2024-10-23 | 2024-10-23 | 2024-10-23 | 2024-11-06 | 2024-10-23 | 2024-10-29 | 2024-10-29 | 2024-11-13 |  |  | 2024-11-12 |  |  | CS | 2024-11-12 | [6 empty] | CS |  |  | 2024-11-12 | [7 empty] | 2024-11-25 |  |  |  | 2024-11-25 | [8 empty] | 2024-11-25 | [8 empty] | 2024-11-25 | [11 empty] | 2025-02-03 | [64 empty] | 2025-03-12 | [17 empty] | 0 | [19 empty] | TRUE | FALSE |  | 0 | 0 | 1900 | 1900 | 1900
916 |  | Eben Snow | Brent Brooks | 2024-10-16 | [6 empty] | 2025-03-25 | wthdw |  | 2025-03-26 | wthdw | [20 empty] | 8 - BALD |  | 691D1 | 832 | Yes | WITHDRAWN | WITHDRAWN |  | Angela Plummer | SolAmerica Energy, LLC | SOLAMERICA ENERGY DEVELOPEMENT LLC | School Street Baldwin ME 04024 | 2000448613 | 30016284553 | Solar | [5 empty] | 43.803 | -70.6809 | School Street |  | School Street | Baldwin | 160.6 | BALDWIN | 691D1 | 691T1 | 34.5 | 9310-L0371-0360-0016-ED00062 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2024-10-23 | 2024-10-30 | 2024-10-23 | 2024-10-30 | 2024-10-30 | 2024-10-31 | 2024-11-14 | 2024-11-05 | 2024-11-08 | 2024-11-08 | 2024-11-25 | 2024-11-25 | 2025-03-10 |  |  |  | FS | 2024-11-25 | IS | 2025-03-10 |  |  |  |  | FS | 2024-11-25 | 2025-03-10 | [7 empty] | 2024-12-16 | 2025-03-10 |  |  | 2024-12-16 | 2025-03-18 | [6 empty] | 2024-12-16 | 2025-03-18 | [7 empty] | 2024-12-16 | 2025-03-18 | [10 empty] | 2025-01-23 | 2025-04-30 | [5 empty] | 2025-01-22 | [8 empty] | 2025-01-22 | [8 empty] | 2025-02-05 | [8 empty] | 2025-02-13 | [7 empty] | 2025-02-13 | [24 empty] | 2025-04-23 | [17 empty] | 0 |  |  |  | Q4 2025 | [15 empty] | FALSE | FALSE |  | 0 | 0 | 1900 | 1900 | 1900
917 |  | Ben Brooks | Anthony Boucher | 2024-10-16 | [6 empty] | 2025-11-26 | wthdw |  | 2025-12-08 | wthdw | [20 empty] | 12 - BUCK |  | 806D2 | 908 | Yes | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Angela Plummer | SolAmerica Energy Development, LLC | SOLAMERICA ENERGY DEVELOPEMENT LLC | Penobscot Rd Penobscot ME 04406 | 2000448613 | 30016284579 | Solar | [5 empty] | 44.4809 | -68.6891 | N Penobscot Road |  | N Penobscot Road | Penobscot | 60 | BUCKSPORT | 806D2 | 806T1 | 12.47 | 9310-L0386-4580-0033-ED00144 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2024-10-23 | 2024-10-30 | 2024-10-23 | 2024-10-30 | 2025-04-09 | 2025-04-11 | 2025-04-24 | 2025-12-08 | 2025-12-09 | 2025-12-09 | 2025-12-23 | 2025-05-20 | 2025-08-05 |  |  |  | FS | 2025-05-20 | IS | 2025-08-05 |  |  |  |  | FS | 2025-05-21 | 2025-08-08 | [7 empty] | 2025-06-16 | 2025-06-16 |  |  | 2025-06-16 | 2025-08-18 | [6 empty] | 2025-06-16 | 2025-08-19 | [7 empty] | 2025-06-16 | 2025-08-19 | [10 empty] | 7/23/202 | 2025-10-01 | [5 empty] | 2025-07-22 | 2025-09-30 | [7 empty] | 2025-07-23 | 2025-09-30 | [7 empty] | N/A | 2025-10-02 | [7 empty] | N/A | 2025-10-08 | [6 empty] | N/A | 2025-10-08 | [8 empty] | 2025-10-08 |  | 2025-10-10 | 2025-10-31 | 2025-10-17 | 2025-10-31 | [5 empty] | 1827966.5 | 2025-10-01 |  |  | 2025-12-12 | 2021-07-13: 2025-11-11; 2021-07-13: 2025-11-11 | [9 empty] | 0 |  |  |  | Q4 2025 | [15 empty] | TRUE | FALSE |  | 2025-11-11 | 2025-11-11 | 2025 | 2025 | 2025
918 |  | Rigel Paradise | Rick Duperre | 2024-11-06 | [31 empty] | 7 - BUCO |  | 612D1 | 870 |  | WITHDRAWN | WITHDRAWN |  | Annalise Kukor | REVISION ENERGY INC | REVISION ENERGY INC | 21B BLANCHARD RD SPRINGVALE | 2000038393 | 30015745430 | Solar | [5 empty] | 43.4642 | -70.835 | 21B Blanchard Road | 21B | Blanchard Road | Springvale | 3 | BUTLER'S CORNER | 612D1 | 612T1 | 12.47 | 9310-L0225-5170-0254-ED00033 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2024-11-14 | 2024-11-21 | 2024-11-14 | 2024-11-21 | 2024-11-21 | 2024-11-21 | 2024-12-09 | 2024-12-03 | 2024-12-05 | 2024-12-05 | 2024-12-19 |  |  | 2024-12-11 |  |  | CS | 2024-12-11 | [6 empty] | CS |  |  | 2024-12-12 | [7 empty] | 2024-12-24 |  |  |  | 2024-12-23 | [8 empty] | 2024-12-24 | [8 empty] | 2024-12-24 | [11 empty] | 2025-03-03 | [6 empty] | 2025-03-03 | [8 empty] | 2025-03-03 | [8 empty] | 2025-03-04 | [8 empty] | 2025-03-14 | [7 empty] | 2025-03-14 | [18 empty] | 721433 | 2025-02-28 |  |  | 2025-04-04 | [17 empty] | 0 |  |  |  | Q1 2026 | [15 empty] | TRUE | FALSE |  | 0 | 0 | 1900 | 1900 | 1900
919 |  |  | Anthony Boucher | 2024-11-14 | [9 empty] | 2024-11-26 | wthdw | [20 empty] | 8 - SEAR |  | 850D2 | 768 |  | WITHDRAWN | WITHDRAWN |  | Susan Jornov | Genie Solar Energy, LLC | SEARSPORT COMMUNITY SOLAR LLC | 4 back searsport Rd., Searsport | 2000453171 | 30016356419 | Solar | [5 empty] | 44.4647 | -68.9491 | 4 Back Searsport Rd | 4 | Back Searsport Rd | Searsport | 31 | SEARSPORT | 850D2 | 850T1 | 12.47 | 9310-L0428-5220-0051-ED00044 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2024-11-21 | 2024-12-02 | 2024-11-21 | 2024-12-02 | 2025-04-07 | 2025-04-08 | 2025-04-22 | 2025-04-08 | 2025-04-14 | 2025-04-14 | 2025-04-29 | 2025-04-25 |  |  |  |  | FD | 2025-04-25 | [6 empty] | FS | 2025-04-28 | [8 empty] | 2025-04-25 | [99 empty] | 2025-05-09 | [17 empty] | 0 |  |  |  | Q1 2026 | [15 empty] | TRUE | FALSE |  | 0 | 0 | 1900 | 1900 | 1900
920 |  | Rigel Paradise | Rick Duperre | 2024-11-18 | [31 empty] | 8 - BDPP |  | 605D2 | 764 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Corwin Lavoie | Nexamp, Inc | NEXAMP SOLAR LLC | 9A BUZZEL RD BIDDEFORD -SOLAR ARRAY | 2000114877 | 30016377068 | Solar | [5 empty] | 43.51 | -70.5285 | 9 Buzzell Rd | 9 | Buzzell Rd | Biddeford | 5H | BIDDEFORD PUMP | 605D2 | 605T1 | 12.47 | 9310-L0215-0490-0035-ED00014 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2024-11-25 | 2024-12-04 | 2024-11-25 | 2024-12-05 | 2024-12-05 | 2024-12-05 | 2024-12-19 | 2024-12-12 | 2024-12-17 | 2024-12-17 | 2025-01-02 |  |  | 2024-01-02 |  |  | CS | 2024-01-02 | [6 empty] | CS |  |  | 2024-01-02 | [7 empty] | 2024-01-07 |  |  |  | 2024-12-23 | [8 empty] | 2025-01-07 | [8 empty] | 2025-01-07 | [11 empty] | 2025-03-13 | [6 empty] | 2025-03-13 | [8 empty] | 2025-03-13 | [8 empty] | 2025-03-24 | [8 empty] | 2025-03-27 | [7 empty] | 2025-03-27 | [7 empty] | 2025-04-09 |  | 2025-04-09 |  | 2025-04-09 | [6 empty] | 888291 | 2025-03-13 |  |  | 2025-06-13 | 2021-07-13: 2025-04-09; 2021-07-13: 2025-04-09 | [9 empty] | 0 |  |  |  | Q2 2027 | [15 empty] | TRUE | FALSE |  | 2025-04-09 | 2025-04-09 | 2025 | 2025 | 2025
921 |  | Rigel Paradise | Rick Duperre | 2024-12-03 | [31 empty] | 7 - MAST |  | 634D1 | 810 |  | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Corwin Lavoie | Nexamp, Inc | NEXAMP SOLAR LLC | 9 HEAVY HAMMER LN ARUNDEL | 2000114877 | 30016412667 | Solar | [5 empty] | 43.4744 | -70.5331 | 9 Heavy Hammer Ln | 9 | Heavy Hammer ln | Arundel | 181 | MAY STREET | 634D1 | 634T1 | 12.47 | 9310-L0266-4180-0001-ED00203 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2024-12-10 | 2024-12-17 | 2024-12-10 | 2024-12-17 | 2024-12-17 | 2024-12-20 | 2025-01-02 | 2025-01-03 | 2025-01-06 | 2025-01-06 | 2025-01-21 |  |  | 2025-01-07 |  |  | CS | 2025-01-07 | [6 empty] | CS |  |  | 2025-01-07 | [7 empty] | 2025-01-13 |  |  |  | 2025-01-10 | [8 empty] | 2025-01-13 | [8 empty] | 2025-01-13 | [11 empty] | 2025-03-19 | [6 empty] | 2025-03-19 | [8 empty] | 2025-03-19 | [8 empty] | 2025-04-02 | [8 empty] | 2025-03-27 | [7 empty] | 2025-03-27 | [7 empty] | 2024-04-04 |  | 2025-04-04 |  | 2025-04-07 | [6 empty] | 305532 | 2025-03-19 | n/a | n/a | 2025-07-15 | 2021-07-13: 2025-04-07; 2021-07-13: 2025-04-07; 2021-07-13: 2025-04-07 | [9 empty] | 0 |  |  |  | Q4 2026 | [15 empty] | TRUE | FALSE |  | 2025-04-07 | 2025-04-07 | 2025 | 2025 | 2025
922 |  | Eben Snow | Brent Brooks | 2024-12-03 | [30 empty] | 835 | 10 - LEED |  | 471D2 | 835 |  | WITHDRAWN | WITHDRAWN |  | Josh Bardsley | REVISION ENERGY INC | DAYKEN PALLET CO INC | 152 Bogg rd / Leeds | 2800190849 | 30016345289 | Solar | [5 empty] | 44.2603 | -70.079 | 152 Bog Road | 152 | Bog Road | Leeds | 6 | LEEDS | 471D2 | 471T1 | 12.47 | 9310-L0210-3210-0072-ED00020 |  |  |  |  | Yes | [6 empty] | 2024-12-10 | 2024-12-17 | 2024-12-10 | 2024-12-17 | 2025-11-25 |  | 2025-12-11 | [127 empty] | 2025-11-26 | [17 empty] | #REF! |  |  |  | Q3 2026 | [15 empty] | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF!
923 |  | Govinda Neupane |  | 2024-12-06 | 2024-12-16 | wthdw |  | 2025-04-09 | wthdw | [25 empty] | 907 | 9 - ANSO |  | 801D1 | 907 | Yes | WITHDRAWN | WITHDRAWN |  | Corwin Lavoie | Nexamp, Inc | NEXAMP SOLAR LLC | 750 Anson Rd Starks ME 04911 | 2000114877 | 30016434505 | Solar | [5 empty] | 44.7486 | -69.906 | 750 Anson Road | 750 | Anson Road | Starks | 14 | ANSON | 801D1 | 801T1 | 12.47 | 9310-L0379-5510-0017-ED00007 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2024-12-13 | 2024-12-20 | 2024-12-13 | 2024-12-20 | 2025-04-09 | 2025-04-11 | 2025-04-24 | 2025-04-16 | 2025-04-17 | 2025-04-17 | 2025-05-02 |  |  | 2025-05-02 |  |  | CS | 2025-05-02 | [9 empty] | 2025-05-05 | [102 empty] | n/a | n/a | n/a | n/a | 2025-05-20 | [17 empty] | 0 |  |  |  | Q1 2026 | [15 empty] | TRUE | FALSE |  | 0 | 0 | 1900 | 1900 | 1900
924 |  | Govinda Neupane |  | 2024-12-10 | [9 empty] | 2024-12-18 | wthdw |  | 2025-01-06 | wthdw | [17 empty] | 9 - DOVE | 1 - DOVE | 815D1 | 912 | Yes | EXECUTED | EXECUTED |  | David Ikejiani | EDPRNA DG Energy Development, LLC | PISCATAQUIS VALLEY SOLAR LLC | 1123 W MAIN ST PROJ 412 | 2000239310 | 30013422545 | Solar | 975 | 0.975 | 1319.76 |  |  | 45.1814 | -69.2611 | 1123 West Main Street | 1123 | West Main Street | Dover-Foxcroft | 61 | DOVER | 815D1 | 815T1 | 12.47 | 9310-L0396-1650-0049-ED00030 |  | TRIGGERING | TRIGGERING | 290000 | Yes | [6 empty] | 2024-12-17 | 2024-12-24 | 2024-12-17 | 2024-12-24 | 2025-06-06 | 2025-06-13 | 2025-06-23 | 2025-06-19 | 2025-06-20 | 2025-06-20 | 2025-07-07 |  |  | 2025-06-25 |  |  | CS | 2025-06-25 | [6 empty] | CS |  |  | 2025-06-27 | [11 empty] | 2025-07-10 | [17 empty] | 2025-07-11 | [11 empty] | 2025-09-15 | [6 empty] | 2025-09-05 | [8 empty] | 2025-09-08 | [33 empty] | 2025-09-08 |  | 2025-09-08 | 2025-09-15 | 2025-09-12 | 2025-09-22 | [5 empty] | 516070 | 2025-09-05 | n/a | n/a |  | 2021-07-13: 2025-09-25; 2021-07-13: 2025-10-14 | [9 empty] | -19 |  |  |  | Q3 2025 |  |  |  | 10301234602 | [11 empty] | FALSE | FALSE |  | 2025-09-25 | 2025-09-25 | 2025 | 2025 | 2025
925 |  | Eben Snow | Brent Brooks | 2024-12-13 | [30 empty] | 888 | 7 - BRID |  | 406D2 | 888 |  | WITHDRAWN | WITHDRAWN |  | Zeeshan Yasin | Novel Energy Solutions LLC | ME Lopez South High St CSG LLC | ME Lopez South High St CSG LLC | 2000348436 | 30014890674 | Solar | [5 empty] | 44.0274 | -70.7094 | 0 South High St | 0 | South High St | Bridgton | 71 | BRIDGTON | 406D2 | 406T1 | 12.47 | 9310-L0119-0690-0141-ED00088 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2024-12-20 | 2024-12-30 | 2024-12-20 | 2024-12-30 | 2024-03-24 | 2025-03-26 | 2025-04-07 | 2025-03-27 | 2025-04-04 | 2025-04-04 | 2025-04-18 |  |  | 2025-04-09 |  |  | CS | 2025-04-09 | [6 empty] | CS |  |  | 2025-04-09 | [106 empty] | 2025-05-06 | [17 empty] | 0 |  |  |  | Q3 2026 | [15 empty] | TRUE | FALSE |  | 0 | 0 | 1900 | 1900 | 1900
926 |  | Eben Snow | Brent Brooks | 2025-01-15 | 2025-07-14 | L2_Bump | RQP-1 | 2025-09-09 | L2_Bump | RQP-1 | 2025-11-04 | wthdw | RQP-1 | [18 empty] | RQP-1 | 1 - NORW |  | 902 | 10 - NORW | 3 - NORW | 435D1 | 902 | Yes | RESULTS | Developer executed IA due 10/15 |  | Jacob Freudenberger | Paddle Energy LLC | PE PERCIVAL LLC | 1Kilgore Rd south paris | 2000468336 | 30016582725 | Solar/Battery | 4999 | 4.999 | 7066.56 | 4999 |  | 44.205 | -70.5184 | 1 Kilgore Road | 1 | Kilgore Road | South Paris | 12 | NORWAY | 435D1 | 435T2 | 12.47 | 9310-L0168-4500-0117-ED00003 |  | GFOV TBD During Study Phase | GFOV TBD During Study Phase |  | Yes | [6 empty] | 2025-01-23 | 2025-01-30 | 2025-01-23 | 2025-01-30 | 2025-04-24 | 2025-04-25 | 2025-05-08 | 2025-04-29 | 2025-05-01 | 2025-05-01 | 2025-05-15 |  |  | 2025-05-14 |  |  | CS | 2025-05-14 | [6 empty] | CS |  |  | 2025-05-19 |  | 2026-05-26 | 2025-07-14 | 2025-09-24 | 2026-02-24 |  |  |  |  | 2026-06-15 |  | 2025-05-28 |  | 2026-05-26 | N/A | 2025-09-29 | 2026-03-13 |  |  |  | 2025-06-25 |  | 2026-06-15 | 2025-07-14 | 2025-09-29 | 2026-03-13 |  |  |  | 2025-06-25 |  | 2026-06-15 | 2025-07-14 | 2025-09-29 | 2026-03-13 | [6 empty] | 2025-08-28 |  | 2026-08-17 | [6 empty] | 2026-08-17 | 2026-05-06 | [7 empty] | 2026-08-17 | 2026-05-06 | [7 empty] | N/A | 2026-05-15 | [7 empty] | N/A | 2026-05-19 | [12 empty] | 2026-09-03 |  | 2026-09-16 | [8 empty] | 1914800 | 2025-05-06 | [20 empty] | 0 |  |  |  | Q2 2026 | [15 empty] | FALSE | FALSE |  | 0 | 0 | 1900 | 1900 | 1900
927 |  | Marshall Ripley | Rick Duperre | 2025-01-24 | [31 empty] | 5 - SMRD | 1 - SMRD | 660D2 | 586 |  | EXECUTED | EXECUTED |  | Salman Ali | UGE USA INC | ORCHARD ROAD SOLAR LLC | 23 ROSE LN, STANDISH | 2000203988 | 30012942766 | Solar | 990 | 0.99 | 1504.2 |  |  | 43.7339 | -70.5419 | 23 Rose Ln. | 23 | Rose Ln. | Standish | 16 | SHAWS MILL ROAD | 660D2 | 660T1 | 12.47 | 9310-L0493-5500-0050-ED00031 |  | COST SHARE | COST SHARE | 41388 | Yes | [6 empty] | 2025-01-31 | 2025-02-07 | 2025-01-31 | 2025-02-07 | 2025-02-07 | 2025-02-07 | 2025-02-24 | 2025-02-10 | 2025-02-18 | 2025-02-18 | 2025-03-04 |  |  | 2025-02-25 |  |  | CS | 2025-02-25 | [6 empty] | CS |  |  | 2025-02-25 | [11 empty] | 2025-03-12 | [8 empty] | 2025-03-12 | [8 empty] | 2025-03-12 | [11 empty] | 2025-05-15 | [6 empty] | 2025-05-09 | [8 empty] | 2025-05-09 | [8 empty] | 2025-05-22 | [8 empty] | 2025-05-27 | [7 empty] | 2025-05-27 | [7 empty] | 2025-05-28 |  | 2025-05-29 | 2025-06-13 | 2025-06-03 | 2025-06-13 | [5 empty] | 420713 | 2025-05-09 |  |  |  | 2021-07-13: 2025-06-04; 2021-07-13: 2025-06-04; 2021-07-13: 2025-06-16; 2021-07-13: 2025-06-16 | [9 empty] | 0 |  |  |  | Q4 2025 | [15 empty] | FALSE | FALSE |  | 2025-06-04 | 2025-06-04 | 2025 | 2025 | 2025
928 |  | Eben Snow | Brent Brooks | 2025-02-13 | 2025-05-06 | wthdw | [28 empty] | 925 | 8 - BRID |  | 406D2 | 925 | Yes | WITHDRAWN | WITHDRAWN |  | Jacob Freudenberger | Paddle Energy LLC | PE FRANKLIN LLC | 456 PORTLAND RD BRIDGTON | 2000366279 | 30015122515 | Battery | [5 empty] | 44.0262 | -70.6922 | 456 Portland Road | 456 | Portland Road | Bridgton | 63 | BRIDGTON | 406D2 | 406T1 | 12.47 | 9310-L0119-0690-0121-ED00119 |  |  |  |  | Yes | [6 empty] | 2025-02-21 | 2025-02-28 | 2025-02-21 | 2025-02-28 | 2025-05-06 | 2025-05-07 | 2025-05-20 | 2025-05-13 | 2025-05-14 | 2025-05-14 | 2025-05-29 |  |  | 2025-05-19 |  |  | CS | 2025-05-19 | [6 empty] | CS |  |  | 2025-05-20 | [7 empty] | 2025-06-03 |  |  |  | 2025-06-04 | [8 empty] | 2025-06-04 | [8 empty] | 2025-06-04 | [11 empty] | 2025-08-08 | [6 empty] | 2025-08-08 | [8 empty] | 2025-08-08 | [8 empty] | 2025-08-18 | [8 empty] | 2025-08-22 | [7 empty] | 2022-08-22 | [18 empty] | 15056706 | 2025-08-08 |  |  | 2025-09-15 | [17 empty] | 0 |  |  |  | Q3 2026 | [15 empty] | TRUE | FALSE |  | 0 | 0 | 1900 | 1900 | 1900
929 |  |  |  | 2025-02-26 | [31 empty] | 5 - PLHL |  | 644D1 | 892 |  | WITHDRAWN | WITHDRAWN |  | Kelsey Haley | New Leaf Energy, Inc | 510 PV PROJECT DEVELOPMENT LLC | 37 Pond View Dr Scarborough | 2000113260 | 30016567890 | Battery | [5 empty] | 43.6049 | -70.2933 | 1369 Highland Ave | 1369 | Highland Ave | South Portland | 10 | PLEASANT HILL | 644D1 | 644T2 | 12.47 | 9310-L0285-5200-0045-ED00002 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2025-03-05 | 2025-03-12 | 2025-03-05 | 2025-03-12 | [130 empty] | 2025-04-01 | [17 empty] | 0 | [19 empty] | TRUE | FALSE |  | 0 | 0 | 1900 | 1900 | 1900
930 |  |  |  | 2025-02-26 | [31 empty] | 2 - CAEL |  | 613D1 | 637 |  | WITHDRAWN | WITHDRAWN |  | Kelsey Haley | New Leaf Energy, Inc | 510 PV PROJECT DEVELOPMENT LLC | 19 Wells Rd Cape Elizabeth ME | 2000113260 | 30016567882 | Battery | [5 empty] | 43.5959 | -70.2469 | 19 Wells Rd | 19 | Wells Rd | Cape Elizabeth | 78.1 | CAPE ELIZABETH | 613D1 | 613T1 | 12.47 | 9310-L0227-1000-0144-ED00142 |  |  |  |  | Yes | [6 empty] | 2025-03-05 | 2025-03-12 | 2025-03-05 | 2025-03-12 | 2025-03-12 | 2025-03-17 | 2025-03-26 | 2025-04-14 | 2025-04-24 | 2025-04-24 | 2025-05-08 |  |  | 2025-05-28 |  |  | CS | 2025-05-28 | [6 empty] | CS |  |  | 2025-05-28 | [7 empty] | 2025-06-26 |  |  |  | 2025-06-12 | [8 empty] | 2025-06-26 | [8 empty] | 2025-06-26 | [11 empty] | 2025-08-29 | [6 empty] | 2025-08-22 | [8 empty] | 2025-08-22 | [8 empty] | 2025-08-25 | [8 empty] | 2025-08-26 | [7 empty] | 2025-08-26 | [22 empty] | 2025-09-17 | [17 empty] | 0 |  |  |  | Q4 2027 | [15 empty] | TRUE | FALSE |  | 0 | 0 | 1900 | 1900 | 1900
931 |  |  |  | 2025-02-26 | [31 empty] | 1 - HIPO |  | 690D1 |  |  | WITHDRAWN | WITHDRAWN |  | Kelsey Haley | New Leaf Energy, Inc | 510 PV PROJECT DEVELOPMENT LLC | 525 Highland Ave So Portland | 2000113260 | 30016567866 | Battery | [5 empty] | 43.6246 | -70.2656 | 525 Highland Ave | 525 | Highland Ave | South Portland | 46.1 | HINCKLEY POND | 690D1 | 690T1 | 12.47 | 9310-L0368-5430-0180-ED00100 |  |  |  |  | Yes | [6 empty] | 2025-03-05 | 2025-03-12 | 2025-03-05 | 2025-03-12 | 2025-03-12 | 2025-03-17 | 2025-03-26 | 2025-04-14 | 2025-04-24 | 2025-04-24 | 2025-05-08 |  |  | 2025-05-28 |  |  | CS | 2025-05-28 | [6 empty] | CS |  |  | 2025-06-12 | [106 empty] | 2025-06-26 | [17 empty] | 0 |  |  |  | Q4 2027 | [15 empty] | TRUE | FALSE |  | 0 | 0 | 1900 | 1900 | 1900
932 |  | Lanie Patterson | Brent Brooks | 2025-03-07 | [31 empty] | 7 - UNIT |  | 860D1 | 280 |  | WITHDRAWN | WITHDRAWN |  | Angela Plummer | SolAmerica Energy Development, LLC | SOLAMERICA ENERGY LLC | 306 MOOSEHEAD TRAIL DIXMONT ME | 2000209571 | 30016521780 | Solar | [5 empty] | 44.6676 | -69.1703 | 306 MOOSEHEAD TRAIL | 306 | MOOSEHEAD TRAIL | Dixmont | 22 | UNITY | 860D1 | 860T1 | 12.47 | 9310-L0442-1630-0004-ED00024 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2025-03-14 | 2025-03-21 | 2025-03-14 | 2025-03-21 | 2025-03-21 | 2025-03-31 | 2024-04-04 | 2025-05-01 | 2025-05-05 | 2025-05-05 | 2025-05-19 | 2025-05-19 | 2025-08-11 |  |  |  | FS | 2025-05-19 | IS | 2025-08-11 |  |  |  |  | FS | 2025-05-27 | 2025-08-11 | [7 empty] | 2025-06-18 |  |  |  | 2025-06-16 | 2025-08-18 | [6 empty] | 2025-06-18 | 2025-08-18 | [7 empty] | 2025-06-18 | 2025-08-18 | [10 empty] | 2025-07-25 | 2025-09-30 | [5 empty] | 2025-07-24 | 2025-09-30 | [7 empty] | 2025-07-24 | 2025-09-30 | [7 empty] | N/A | 2025-09-30 | [7 empty] | N/A | 2025-10-08 | [6 empty] | N/A | 2025-10-08 | [19 empty] | 4153950 | 2025-09-30 |  |  | 2025-10-31 | [17 empty] | 0 |  |  |  | Q2 2026 | [15 empty] | TRUE | FALSE |  | 0 | 0 | 1900 | 1900 | 1900
933 |  | Govinda Neupane |  | 2025-03-21 | [30 empty] | 924 | 10 - DOVE |  | 815D2 | 924 |  | WITHDRAWN | WITHDRAWN |  | Annalise Reichert | UGE USA INC | ME CDG 001 LLC | 772 ESSEX ST DOVERFOXCROFT ME | 2000191249 | 30012780265 | Solar | [5 empty] | 45.1875 | -69.1924 | 772 Essex St | 772 | Essex St | Dover-Foxcroft | 44.1 | DOVER | 815D2 | 815T2 | 12.47 | 9310-L0397-1650-0029-ED00107 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2025-03-28 | 2025-04-04 | 2025-03-28 | 2025-04-04 | 2025-10-14 | 2025-10-14 | 2025-10-28 | 2025-10-14 | 2025-10-17 | 2025-10-17 | 2025-10-31 |  |  | 2025-10-24 |  |  | CS | 2025-10-24 | [6 empty] | CS |  |  | 2025-10-24 | [7 empty] | 2025-10-24 |  |  |  | 2025-12-01 | [8 empty] | 2025-12-01 | [8 empty] | 2025-12-01 | [11 empty] | 2025-02-05 | [6 empty] | 2026-02-05 | [8 empty] | 2026-02-05 | [44 empty] | 383221 | 2026-02-05 |  |  | 2026-02-12 | [17 empty] | 0 |  |  |  | Q2 2027 | [15 empty] | TRUE | FALSE |  | 0 | 0 | 1900 | 1900 | 1900
934 |  | Rigel Paradise | Rick Duperre | 2025-07-07 | [31 empty] | 5 - NOLI | 2 - NOLI | 638D2 | 341 |  | EXECUTED | EXECUTED |  | Zeeshan Yasin | Novel Energy Solutions LLC | 697 SOKOKIS AVE SOLAR LLC | 700 SOKOKIS AVE, LIMINGTON | 2000458268 | 30016440171 | Solar/Battery | 999 | 0.999 | 1388.4 |  | 1128 | 43.7698 | -70.6598 | 700 Sokokis Ave | 700 | Sokokis Ave | Limington | 60 | NORTH LIMINGTON | 638D2 | 638T1 | 12.47 | 9310-L0498-3270-0039-ED00158 | Non-FERC | COST SHARING | 125000 |  | Yes | [6 empty] | 2025-07-14 | 2025-07-21 | 2025-07-14 | 2025-07-21 | 2025-07-21 | 2025-07-22 | 2025-08-04 | 2025-08-04 | 2025-08-06 | 2025-08-06 | 2025-08-20 |  |  | 2025-08-21 |  |  | CS | 2025-08-21 | [6 empty] | CS |  |  | 2025-08-27 | [7 empty] | 2025-09-08 |  |  |  | 2025-09-02 | [8 empty] | 2025-09-08 | [8 empty] | 2025-09-08 | [11 empty] | 2025-11-12 | [6 empty] | 2025-11-12 | [8 empty] | 2025-11-12 | [8 empty] | 2025-11-17 | [8 empty] | 2025-11-17 | [7 empty] | 2025-11-17 | [7 empty] | 2025-12-03 |  | 2025-12-03 | 2026-03-10 | 2025-12-04 | [6 empty] | 316458 | 2025-11-12 |  |  |  | 2021-07-13: 2025-12-08; 2021-07-13: 2025-12-08 | [9 empty] | 0 |  |  |  | Q2 2026 | [15 empty] | TRUE | FALSE |  | 2025-12-08 | 2025-12-08 | 2025 | 2025 | 2025
935 |  | Eben Snow | Brent Brooks | 2025-07-16 |  |  |  | 2025-12-02 | wthdw | [25 empty] | 928 | 9 - BRID |  | 406D2 | 928 |  | WITHDRAWN | WITHDRAWN |  | Angela Plummer | SolAmerica Energy Development, LLC | SOL AMERICA ENERGY DEVELOPMENT LLC | beechwood ln., bridgton / ME_cumber | 2000467946 | 30016577139 | Solar | [5 empty] | 44.0181 | -70.6658 | N/A Beechwood Ln |  | Beechwood Ln | Bridgton | 75.2 | BRIDGTON | 406D2 | 406T1 | 12.47 | 9310-L0119-0690-0070-ED00173 |  |  |  |  | Yes | [6 empty] | 2025-07-23 | 2025-07-30 | 2025-07-23 | 2025-07-30 | 2025-09-15 | 2025-09-19 | 2025-09-29 | 2025-09-19 | 2025-09-24 | 2025-09-24 | 2025-10-08 |  |  | 2025-10-10 |  |  | CS | 2025-10-10 | [6 empty] | CS |  |  | 2025-10-10 | [7 empty] | 2025-10-22 |  |  |  | 2025-11-03 | [8 empty] | 2025-11-03 | [8 empty] | 2025-11-03 | [11 empty] | 2026-01-12 | [64 empty] | 2025-12-10 | [17 empty] | 0 |  |  |  | Q2 2026 | [15 empty] | TRUE | FALSE |  | 0 | 0 | 1900 | 1900 | 1900
936 |  | Govinda Neupane |  | 2025-07-16 | [30 empty] | 911 | 14 - CARM |  | 808D3 | 911 |  | WITHDRAWN | WITHDRAWN |  | Angela Plummer | SolAmerica Energy Development, LLC | SOLAMERICA ENERGY LLC | irish Rd., Levant - ME_Penobscot_ha | 2000209571 | 30016151927 | Solar | [5 empty] | 44.846 | -69.0256 | N/A Irish Road |  | Irish Road | Levant | 63 | CARMEL | 808D3 | 808T2 | 12.47 | 9310-L0506-3220-0017-ED00003 |  |  |  |  | Yes | [6 empty] | 2025-07-23 | 2025-07-30 | 2025-07-23 | 2025-07-30 | 2025-12-08 | 2025-12-11 | 2025-12-22 | 2025-12-16 | 2025-12-30 | 2025-12-30 | [124 empty] | 2026-01-07 | [17 empty] | 0 |  |  |  | Q2 2026 | [15 empty] | TRUE | FALSE |  | 0 | 0 | 1900 | 1900 | 1900
937 |  | Rigel Paradise | Rick Duperre | 2025-07-16 |  |  |  | 2025-11-21 | wthdw | [26 empty] | 7 - BASS |  | 602D2 | 588 | Yes | EXECUTED-WITHDRAWN | EXECUTED-WITHDRAWN |  | Angela Plummer | SolAmerica Energy Development, LLC | SOL AMERICA ENERGY DEVELOPMENT LLC | 138 Ginney rd., berwick / Me_york_r | 2000467946 | 30016577345 | Solar | [5 empty] | 43.2806 | -70.7905 | 138 GUINEA ROAD | 138 | GUINEA ROAD | BERWICK | 143 | BASSETT | 602D2 | 602T1 | 12.47 | 9310-L0211-0470-0008-ED00060 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2025-07-23 | 2025-07-30 | 2025-07-23 | 2025-07-30 | 2025-07-30 | 2025-08-01 | 2025-08-13 | 2025-08-04 | 2025-08-07 | 2025-08-07 | 2025-08-21 |  |  | 2025-08-07 |  |  | CS | 2025-08-07 | [6 empty] | CS |  |  | 2025-08-11 |  |  | 2025-11-25 |  |  |  |  | 2025-08-22 |  |  |  | 2025-08-18 |  |  | 2025-12-12 | [5 empty] | 2025-08-22 |  |  | 2025-12-12 | [5 empty] | 2025-08-22 |  |  | 2025-12-12 | [8 empty] | 2025-10-28 | [6 empty] | 2025-10-28 |  |  | 2026-02-19 | [5 empty] | 2025-10-28 |  |  | 2026-02-19 | [5 empty] | N/A |  |  | N/A | [5 empty] | N/A |  |  | N/A |  |  |  |  | N/A |  |  | N/A |  |  |  |  | 2025-10-29 |  | 2025-10-30 | 2026-02-26 | 2025-10-31 | 2026-03-03 | [5 empty] | 349614 | 2025-10-28 | 191458 | 2026-02-19 | 2026-05-27 | 2021-07-13: 2025-11-03; 2021-07-13: 2025-11-03; 2021-07-13: 2026-03-04; 2021-07-13: 2026-03-04 | [9 empty] | 0 |  |  |  | Q2 2026 |  |  |  | 10301234554 | [11 empty] | FALSE | FALSE |  | 2025-11-03 | 2025-11-03 | 2025 | 2025 | 2025
938 |  | Govinda Neupane |  | 2025-07-16 | [31 empty] | 4 - FAFA |  | 818D1 | 575 |  | WITHDRAWN | WITHDRAWN |  | Angela Plummer | SolAmerica Energy Development, LLC | SOL AMERICA ENERGY DEVELOPMENT LLC | 161 industry rd,. new sharon | 2000467946 | 30016577162 | Solar | [5 empty] | 44.6506 | -70.0189 | 160 INDUSTRY ROAD | 160 | INDUSTRY ROAD | NEW SHARON | 19 | FARMINGTON FALLS | 818D1 | 818T1 | 12.47 | 9310-L0402-4075-0047-ED00019 |  |  |  |  | Yes | [6 empty] | 2025-07-23 | 2025-07-30 | 2025-07-23 | 2025-07-30 | 2025-07-30 | 2025-08-01 | 2025-08-13 | 2025-08-04 | 2025-08-07 | 2025-08-07 | 2025-08-21 |  |  | 2025-08-07 |  |  | CS | 2025-08-07 | [6 empty] | CS |  |  | 2025-08-11 | [7 empty] | 2025-08-18 |  |  |  | 2025-08-18 | [8 empty] | 2025-08-18 | [8 empty] | 2025-08-18 | [11 empty] | 2025-10-22 | [6 empty] | 2025-10-22 | [8 empty] | 2025-10-22 | [8 empty] | 2025-10-21 | [35 empty] | 780430 | 2025-10-22 |  |  | 2025-10-29 | [17 empty] | 0 |  |  |  | Q2 2026 | [15 empty] | TRUE | FALSE |  | 0 | 0 | 1900 | 1900 | 1900
939 |  | Rigel Paradise | Rick Duperre | 2025-07-16 | [31 empty] | 6 - NOLI |  | 638D1 | 934 |  | WITHDRAWN | WITHDRAWN |  | Angela Plummer | SolAmerica Energy Development, LLC | SOL AMERICA ENERGY DEVELOPMENT LLC | sokokis ave., limington / ME_york_b | 2000467946 | 30016577337 | Solar | [5 empty] | 43.746 | -70.6837 | N/A SOKOKIS AVE |  | SOKOKIS AVE | LIMINGTON | 514.2 | NORTH LIMINGTON | 638D1 | 638T1 | 12.47 | 9310-L0274-3270-0039-ED00097 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2025-07-23 | 2025-07-30 | 2025-07-23 | 2025-07-30 | 2025-12-08 | 2025-12-11 | 2025-12-22 | 2025-12-16 | 2025-12-30 | 2025-12-30 | [124 empty] | 2026-01-12 | [17 empty] | 0 |  |  |  | Q2 2026 | [15 empty] | TRUE | FALSE |  | 0 | 0 | 1900 | 1900 | 1900
940 |  | Ben Brooks | Anthony Boucher | 2025-07-16 | [31 empty] | 13 - BUCK |  | 806D2 | 917 |  | WITHDRAWN | WITHDRAWN |  | Angela Plummer | SolAmerica Energy Development, LLC | SOL AMERICA ENERGY DEVELOPMENT LLC | north penobscot rd., penobscot | 2000467946 | 30016577188 | Solar | [5 empty] | 44.4796 | -68.6981 | N/A N PENOBSCOT ROAD |  | N PENOBSCOT ROAD | PENOBSCOT | 67 | BUCKSPORT | 806D2 | 806T3 | 12.47 | 9310-L0386-4580-0033-ED00155 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2025-07-23 | 2025-07-30 | 2025-07-23 | 2025-07-30 | 2025-11-11 | 2025-11-13 | 2025-11-26 | 2025-11-13 | 2025-11-18 | 2025-11-18 | 2025-12-04 | [123 empty] | 2025-11-25 | [17 empty] | 0 |  |  |  | Q2 2026 | [15 empty] | TRUE | FALSE |  | 0 | 0 | 1900 | 1900 | 1900
941 |  | Govinda Neupane |  | 2025-07-16 | [31 empty] | 5 - RILE | 1 - RILE | 449D2 | 886 |  | EXECUTED | EXECUTED |  | Ryan Coughlin | Perennial Renewables LLC | Perennial Jay Solar LLC | Cessna St SOLAR, Jay | 2000525888 | 30017401479 | Solar | 999 | 0.999 | 1335.36 |  |  | 44.516 | -70.2215 | 14 CESSNA LANE | 14 | CESSNA LANE | JAY | 135 | RILEY | 449D2 | 449T1 | 12.47 | 9310-L0191-2920-0085-ED00098 |  | NOT IMPACTED | NOT IMPACTED |  | Yes | [6 empty] | 2025-07-23 | 2025-07-30 | 2025-07-23 | 2025-07-30 | 2025-07-30 | 2025-08-01 | 2025-08-13 | 2025-08-04 | 2025-08-07 | 2025-08-07 | 2025-08-21 |  |  | 2025-08-07 |  |  | CS | 2025-08-07 | [6 empty] | CS |  |  | 2025-08-11 | [7 empty] | 2025-08-22 |  |  |  | 2025-08-18 | [8 empty] | 2025-08-22 | [8 empty] | 2025-08-22 | [11 empty] | 2025-10-28 | [6 empty] | 2025-10-28 | [8 empty] | 2025-10-28 | [8 empty] | N/A | [8 empty] | N/A | [7 empty] | N/A | [7 empty] | 2025-10-29 |  | 2025-10-30 |  | 2025-10-31 | 2025-03-17 | [5 empty] | 198461 | 2025-10-28 |  |  |  | 2021-07-13: 2025-11-03; 2021-07-13: 2025-11-03; 2021-07-13: 2026-03-18; 2021-07-13: 2026-03-19 | [9 empty] | 0 |  |  |  | Q2 2026 |  |  |  | 10301236962 | [11 empty] | TRUE | FALSE |  | 2025-11-03 | 2025-11-03 | 2025 | 2025 | 2025
942 |  | Eben Snow | Brent Brooks | 2025-07-16 | [31 empty] | 7 - LOVE |  | 430D1 | 749 |  | WITHDRAWN | WITHDRAWN |  | Angela Plummer | SolAmerica Energy Development, LLC | SOL AMERICA ENERGY DEVELOPMENT LLC | lovell rd., fryburg / ME_oxford_ski | 2000467946 | 30016577303 | Solar | [5 empty] | 44.1233 | -70.9227 | N/A LOVELL ROAD |  | LOVELL ROAD | FRYEBURG | 41 | LOVELL | 430D1 | 430T1 | 12.47 | 9310-L0164-2130-0031-ED00026 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2025-07-23 | 2025-07-30 | 2025-07-23 | 2025-07-30 | 2025-07-30 | 2025-08-01 | 2025-08-13 | 2025-08-04 | 2025-08-07 | 2025-08-07 | 2025-08-21 |  |  | 2025-08-07 |  |  | CS | 2025-08-07 | [6 empty] | CS |  |  | 2025-08-11 | [7 empty] | 2025-08-22 |  |  |  | 2025-08-18 | [8 empty] | 2025-08-22 | [8 empty] | 2025-08-22 | [11 empty] | 2025-10-28 | [6 empty] | 2025-10-28 | [8 empty] | 2025-10-28 | [8 empty] | 2025-10-29 | [8 empty] | 2025-10-30 | [26 empty] | 1195107 | 2025-10-28 |  |  | 2025-11-06 | [17 empty] | 0 |  |  |  | Q2 2026 | [15 empty] | TRUE | FALSE |  | 0 | 0 | 1900 | 1900 | 1900
943 |  |  |  | 2025-07-16 |  |  |  | 2025-11-21 | wthdw | [25 empty] | 937 | 8 - BASS |  | 602D2 | 937 | Yes | WITHDRAWN | WITHDRAWN |  | Angela Plummer | SolAmerica Energy Development, LLC | SOL AMERICA ENERGY DEVELOPMENT LLC | 87 cranberry meadow rd., berwick | 2000467946 | 30016577352 | Solar | [5 empty] | 43.2909 | -70.8346 | 87 CRANBERRY MEADOW ROAD | 87 | CRANBERRY MEADOW ROAD | BERWICK | 10 | BASSETT | 602D2 | 602T1 | 12.47 | 9310-L0211-0470-0022-ED00002 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2025-07-23 | 2025-07-30 | 2025-07-23 | 2025-07-30 | 2025-11-03 | 2025-11-10 | 2025-11-18 | 2025-11-10 | 2025-11-13 | 2025-11-13 | 2025-12-01 |  |  | 2025-11-17 |  |  | CS | 2025-11-17 | [6 empty] | CS |  |  | 2025-11-17 |  |  | 2026-04-20 | [103 empty] | 2026-04-23 | [17 empty] | 0 |  |  |  | Q42026 | [15 empty] | TRUE | FALSE |  | 0 | 0 | 1900 | 1900 | 1900
944 |  | Eben Snow | Brent Brooks | 2025-07-25 | [31 empty] | 8 -LOVE |  | 430D1 |  |  | WITHDRAWN | WITHDRAWN |  | Angela Plummer | SolAmerica Energy Development, LLC | SOL AMERICA ENERGY DEVELOPMENT LLC | lovell rd., fryburg /Me_oxford_hast | 2000467946 | 30016577196 | Solar | [5 empty] | 44.1183 | -70.9085 | N/A LOVELL ROAD |  | LOVELL ROAD | FRYEBURG | 30H | LOVELL | 430D1 | 430T1 | 12.47 | 9310-L0164-2130-0031-ED00030 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2025-08-01 | 2025-08-08 | 2025-08-01 | 2025-08-08 | [130 empty] | 2025-11-06 | [17 empty] | 0 | [19 empty] | TRUE | FALSE |  | 0 | 0 | 1900 | 1900 | 1900
945 |  | Govinda Neupane |  | 2025-07-28 | 2025-10-24 | L2_Bump | [29 empty] | 5 - WILT | 1 -WILT | 885D1 |  | Yes | EXECUTED | EXECUTED |  | Michael Parker | Loki Solar | SOLAR LEASING LLC | 942 WELD RD WILTON ME | 2000422871 | 30016297167 | Solar | 999 | 0.999 | 1466.64 |  |  | 44.6328 | -70.2962 | 942 Weld Road | 942 | Weld Road | Wilton | 117H | WILTON | 885D1 | 885T1 | 12.47 | 9310-L0467-6380-0118-ED00223 |  |  |  |  | Yes | [6 empty] | 2025-08-04 | 2025-08-11 | 2025-08-04 | 2025-08-11 | 2025-08-11 | 2025-08-13 | 2025-08-25 | 2025-08-15 | 2025-08-19 | 2025-08-19 | 2025-09-03 |  |  | 2025-09-03 |  |  | CS | 2025-09-03 | [6 empty] | CS |  |  | 2025-09-09 |  |  | 2025-10-28 |  |  |  |  | 2025-09-24 |  |  |  | 2025-10-03 |  |  | 2025-11-20 | [5 empty] | 2025-10-03 |  |  | 2025-11-21 | [5 empty] | 2025-10-03 |  |  | 2025-11-21 | [8 empty] | 2025-12-11 | [9 empty] | 2026-01-28 | [8 empty] | 2026-01-28 | [8 empty] | 2026-02-10 | [8 empty] | 2026-02-19 | [7 empty] | 2026-02-19 |  |  |  |  | 2026-03-17 |  | 2026-03-20 |  | 2025-04-16 | [6 empty] | 383679 | 2026-01-28 |  |  |  | 2021-07-13: 2026-04-16; 2021-07-13: 2026-04-16 | [9 empty] | 0 |  |  |  | Q3 2026 | [15 empty] | TRUE | FALSE |  | 2026-04-16 | 2026-04-16 | 2026 | 2026 | 2026
946 |  | Govinda Neupane |  | 2025-09-12 | [31 empty] | 5 - CORI | 2 - CORI | 811D1 | 906 |  | EXECUTED | EXECUTED |  | Zeeshan Yasin | Novel Energy Solutions LLC | ME HILLACRE NOKOMIS RD CSG LLC | NOKOMIS RD CORINNA ME | 2000502829 | 30017067288 | Solar | 999 | 0.999 | 1322.88 |  |  | 44.9141 | -69.2782 | N/A Nokomis Rd |  | Nokomis Rd | Corinna | 25 | CORINNA | 811D1 | 811T1 | 12.47 | 9310-L0391-1220-0046-ED00026 |  |  |  |  | Yes | [6 empty] | 2025-09-19 | 2025-09-26 | 2025-09-19 | 2025-09-26 | 2025-09-26 | 2025-10-01 | 2025-10-10 | 2025-10-07 | 2025-10-08 | 2025-10-08 | 2025-10-23 |  |  | 2025-10-24 |  |  | CS | 2025-10-24 | [6 empty] | CS |  |  | 2025-10-24 | [7 empty] | 2025-11-20 |  |  |  | 2025-11-21 | [8 empty] | 2025-11-21 | [8 empty] | 2025-11-21 | [11 empty] | 2026-01-30 | [6 empty] | 2026-01-28 | [8 empty] | 2026-01-28 | [8 empty] | 2025-02-03 | [8 empty] | 2026-02-04 | [7 empty] | 2026-02-04 | [7 empty] | 2026-02-17 |  | 2026-02-18 |  | 2026-02-26 | [6 empty] | 1261643 | 2026-01-29 |  |  |  | 2021-07-13: 2026-03-02; 2021-07-13: 2026-03-03 | [9 empty] | -1 |  |  |  | Q32026 |  |  |  | 10301257803 | [11 empty] | TRUE | FALSE |  | 2026-03-02 | 2026-03-02 | 2026 | 2026 | 2026
947 |  |  |  | 2025-09-22 | 2025-01-16 | L2_Bump | [29 empty] | 4 - LULA | 3 - LULA | 461D1 | 795 | Yes | EXECUTED | EXECUTED |  | Venugopal Kancharla | Solar Power New England | PowerQuest SolarLLC | MAIN ST LOT 60 SCARBOROUGH | 2000479419 | 30016734094 | Solar | 4500 | 4.5 | 5999.98 |  |  | 44.5245 | -70.4165 | 540 Main Street | 540 | Main Street | Dixfield | 505 | LUDDEN LANE | 461D1 | 461T3 | 34.5 | 9310-L0500-1620-0011-ED00014 |  | NOT IMPACTED | NOT IMPACTED |  | Yes | [6 empty] | 2025-09-29 | 2025-10-06 | 2025-09-29 | 2025-10-06 | 2025-10-06 | 2025-10-07 | 2025-10-21 | 2025-10-08 | 2025-10-10 | 2025-10-10 | 2025-10-27 |  |  | 2025-10-10 |  |  | CS | 2025-10-10 | [6 empty] | CS |  |  | 2025-10-10 |  |  | 2026-01-16 |  |  |  |  | 2025-10-16 |  |  |  | 2025-10-15 |  |  | 2026-02-02 | [5 empty] | 2025-10-16 |  |  | 2026-02-03 | [5 empty] | 2025-10-16 |  |  | 2026-02-03 | [8 empty] | 2025-12-23 | [6 empty] | 2025-12-12 |  |  | 2026-03-24 | [5 empty] | 2025-12-12 |  |  | 2026-03-24 | [5 empty] | 2025-12-22 |  |  | 2026-03-26 | [5 empty] | 2025-12-23 |  |  | 2026-04-02 |  |  |  |  | 2025-12-23 |  |  | 2026-04-02 |  |  |  |  | 2026-01-13 |  | 2026-01-13 | 2026-04-02 |  | 2026-04-03 | [5 empty] | 382390 | 2025-12-12 | 359890 | 2026-03-24 |  | 2021-07-13: 2026-04-07; 2021-07-13: 2026-04-07 | [9 empty] | 0 |  |  |  | Q4 2026 | [15 empty] | TRUE | FALSE |  | 2026-04-07 | 2026-04-07 | 2026 | 2026 | 2026
948 |  | Govinda Neupane |  | 2025-09-26 | [30 empty] | 933 | 11 - DOVE |  | 815D2 | 933 |  | WITHDRAWN | WITHDRAWN |  | Angela Plummer | SolAmerica Energy Development, LLC | SOL AMERICA ENERGY DEVELOPMENT LLC | essex st., dover- Foxcroft / Me_Pi | 2000467946 | 30016577311 | Solar | [5 empty] | 45.1858 | -69.2076 | N/A Essex Street |  | Essex Street | Dover-Foxcroft | 25 | DOVER | 815D2 | 815T2 | 12.47 | 9310-L0397-1650-0105-ED00003 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2025-10-03 | 2025-10-10 | 2025-10-03 | 2025-10-10 | 2026-02-12 | 2026-02-16 | 2026-02-27 | [127 empty] | 2026-02-17 | [17 empty] | 0 | [19 empty] | TRUE | FALSE |  | 0 | 0 | 1900 | 1900 | 1900
949 |  | Marshall Ripley | Rick Duperre | 2025-10-06 | 2025-12-24 | L2_Bump | [29 empty] | 5 - FOHI |  | 624D1 | 610 |  | WITHDRAWN | WITHDRAWN |  | Ryan Coughlin | Perennial Renewables LLC | PERENNIAL RENEWABLES LLC | 314 fort hill rd gorham me | 2000346231 | 30017099794 | Solar | [5 empty] | 43.7048 | -70.4575 | 314 Fort Hill Rd | 314 | Fort Hill Rd | Gorham | 76 | FORT HILL | 624D1 | 624T1 | 12.47 | 9310-L0250-2240-0039-ED00288 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2025-10-14 | 2025-10-21 | 2025-10-14 | 2025-10-21 | 2025-10-21 |  |  |  | Waived | Waived |  |  |  | 2025-10-16 |  |  | CS | 2025-10-16 | [6 empty] | CS |  |  | 2025-10-21 | [7 empty] | 2025-10-22 |  |  |  | 2025-10-23 | [8 empty] | 2025-10-23 | [8 empty] | 2025-10-23 | [11 empty] | 2025-12-31 | [60 empty] | n/a | n/a | n/a | n/a | 2025-12-29 | [17 empty] | 0 |  |  |  | Q42026 | [15 empty] | TRUE | FALSE |  | 0 | 0 | 1900 | 1900 | 1900
950 |  | Lanie Patterson | Brent Brooks | 2025-10-15 | [31 empty] | 3 - BURN | 1 - BURN | 807D1 | 473 |  | EXECUTED | EXECUTED |  | Ryan Coughlin | Perennial Renewables LLC | Perennial Snakeroot Solar LLC | Lot 16-1A Main st /Pittsfield | 2000516920 | 30017276319 | Solar | 975 | 0.975 | 1446.12 |  |  | 44.7218 | -69.4125 | Burnham Road |  | Burnham Road | Pittsfield | 3H | BURNHAM | 807D1 | 807T1 | 12.47 | 9310-L0387-4650-0006-ED00062 | Non-FERC |  |  |  | Yes | [6 empty] | 2025-10-22 | 2025-10-29 | 2025-10-16 | 2025-10-20 | 2025-10-20 |  |  |  | Waived | Waived |  |  |  | 2025-10-16 |  |  | CS | 2025-10-16 | [6 empty] | CS |  |  | 2025-10-20 | [7 empty] | 2025-10-20 |  |  |  | 2025-10-22 | [8 empty] | 2025-10-22 | [8 empty] | 2025-10-22 | [11 empty] | 2025-12-30 | [6 empty] | 2025-12-08 | [8 empty] | 2025-12-08 | [8 empty] | N/A | [8 empty] | N/A | [7 empty] | N/A | [7 empty] | 2025-12-08 |  | 2025-12-08 |  | 2025-12-16 | [6 empty] | 529815 | 2025-12-05 |  |  |  | 2021-07-13: 2025-12-16; 2021-07-13: 2025-12-16 | [9 empty] | 0 | [19 empty] | TRUE | FALSE |  | 2025-12-16 | 2025-12-16 | 2025 | 2025 | 2025
951 |  | Govinda Neupane |  | 2025-12-10 | [31 empty] | 6 - RILE |  | 449D2 | 941 |  | WITHDRAWN | WITHDRAWN |  | Zeeshan Yasin | Novel Energy Solutions LLC | ME COUTURE MAIN STREET CSG LLC | Main St Jay | 2000515603 | 30017257061 | Solar | [5 empty] | 44.5184 | -70.2241 | N/A Main St |  | Main St | Jay | 137 | RILEY | 449D2 | 449T1 | 12.47 | 9310-L0191-2920-0085-ED00233 |  |  |  |  | Yes | [6 empty] | 2025-12-17 | 2025-12-24 | 2025-12-17 | 2025-12-24 | 2025-12-24 | 2025-12-31 | 2026-01-09 | 2025-01-09 | 2026-01-12 | 2026-01-12 | 2026-01-27 |  |  | 2026-01-22 |  |  | CS | 2026-01-22 | [6 empty] | CS |  |  | 2026-01-23 | [106 empty] | 2026-03-03 | [17 empty] | 0 |  |  |  | Q4 2027 | [15 empty] | TRUE | FALSE |  | 0 | 0 | 1900 | 1900 | 1900
952 |  | Eben Snow | Brent Brooks | 2025-12-10 | [31 empty] | 6 - SABA |  | 450D1 | 786 |  | WITHDRAWN | WITHDRAWN |  | Zeeshan Yasin | Novel Energy Solutions LLC | ME WEBSTER MIDDLE RD CSG LLC | 515 Middle Rd Sabattus | 2000515577 | 30017257012 | Solar | [5 empty] | 44.0874 | -70.0812 | N/A 515 Middle Rd | 515 | Middle Rd | Sabattus | 69 | SABATTUS | 450D1 | 450T1 | 12.47 | 9310-L0192-6230-0084-ED00117 |  |  |  |  | Yes | [6 empty] | 2025-12-17 | 2025-12-24 | 2025-12-17 | 2025-12-24 | 2025-12-24 | 2025-12-31 | 2026-01-09 | 2026-01-08 | 2026-01-09 | 2026-01-09 | 2026-01-26 |  |  | 2026-01-14 |  |  | CS | 2026-01-14 | [6 empty] | CS |  |  | 2026-01-15 | [106 empty] | 2026-02-24 | [17 empty] | 0 | [19 empty] | TRUE | FALSE |  | 0 | 0 | 1900 | 1900 | 1900
953 |  | Lanie Patterson | Anthony Boucher | 2025-12-17 | [31 empty] | 14 - BUCK |  | 806D1 | 940 |  | WITHDRAWN | WITHDRAWN |  | Zeeshan Yasin | Novel Energy Solutions LLC | ME PARKER CROSS POINT RD CSG LLC | 115 CROSS POINT RD | 2000517655 | 30017287878 | Solar | [5 empty] | 44.5662 | -68.7642 | N/A 115 Gross Point Rd | 115 | Gross Point Rd | Orland | 6 | BUCKSPORT | 806D1 | 806T5 | 12.47 | 9310-L0385-4330-0078-ED00041 |  |  |  |  | Yes | [6 empty] | 2025-12-24 | 2026-01-02 | 2025-12-24 | 2025-12-26 | 2025-12-26 | 2026-01-05 | 2026-01-12 | 2026-01-15 | 2026-01-16 | 2026-01-16 | 2026-02-02 |  |  | 2026-02-02 |  |  | CS | 2026-02-02 | [6 empty] | CS |  |  | 2026-02-02 | [106 empty] | 2026-03-11 | [17 empty] | 0 | [19 empty] | TRUE | FALSE |  | 0 | 0 | 1900 | 1900 | 1900
954 |  | Lanie Patterson | Brent Brooks | 2025-12-24 | [18 empty] | 2025-12-30 | wthdw | [10 empty] | 878 | 13 - NOAU |  | 272D6 | 878 | Yes | WITHDRAWN | WITHDRAWN |  | Michael Parker | Loki Solar | SOLAR LEASING LLC | Belgrade Rd, Sidney | 2000422871 | 30016880947 | Solar | [5 empty] | 44.4039 | -69.8109 | N/A Belgrade Road |  | Belgrade Road | Sidney | 16 | NORTH AUGUSTA | 272D6 | 272T2 | 34.5 | 9310-L0470-5320-0006-ED00011 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2026-01-02 | 2026-01-09 | 2026-01-02 | 2026-01-09 | 2026-07-28 | 2025-07-28 | 2026-08-11 | 2026-08-12 | 2026-08-14 | 2026-08-14 | 2026-08-28 |  |  | 2026-08-20 |  |  | CS | 2026-08-20 | [6 empty] | CS |  |  | 2026-08-21 | [106 empty] | 2026-09-17 | [17 empty] | 0 | [19 empty] | TRUE | FALSE |  | 0 | 0 | 1900 | 1900 | 1900
955 |  | Lanie Patterson | Brent Brooks | 2025-12-29 | [31 empty] | 5 - GARD |  | 226D2 | 494 |  | WITHDRAWN | WITHDRAWN |  | Zeeshan Yasin | Novel Energy Solutions LLC | ME ADAMS MARSTON RD CSG LLC | 323 Marston Rd., Gardiner | 2000516196 | 30017266419 | Solar | [5 empty] | 44.1909 | -69.7902 | 323 Marston Rd | 323 | Marston Rd | Gardiner | 41 | GARDINER | 226D2 | 226T1 | 12.47 | 9310-L0057-2190-0072-ED00090 |  | WITHDRAWN | WITHDRAWN |  | Yes | [6 empty] | 2026-01-06 | 2026-01-13 | 2026-01-06 | 2026-01-13 | 2026-01-13 | 2026-01-16 | 2026-01-28 | 2026-01-27 | 2026-01-28 | 2026-01-30 | 2026-02-13 |  |  | 2026-02-12 |  |  | CS | 2026-02-12 | [6 empty] | CS |  |  | 2026-02-13 | [106 empty] | 2026-03-20 | [17 empty] | 0 | [19 empty] | TRUE | FALSE |  | 0 | 0 | 1900 | 1900 | 1900
956 |  | Lanie Patterson | Brent Brooks | 2025-12-29 | [31 empty] | 6 - COMR |  | 230D2 | 564 |  | WITHDRAWN | WITHDRAWN |  | Zeeshan Yasin | Novel Energy Solutions LLC | ME MONSEN COOKSON LN CSG LLC | COOKSON LN Whitefield | 2000518663 | 30017302131 | Solar | [5 empty] | 44.2434 | -69.553 | 0 Cookson Lane | 0 | Cookson Lane | Whitefield | 7 | COOPERS MILLS ROAD | 230D2 | 230T2 | 12.47 | 9310-L0497-6340-0032-ED00025 |  |  |  |  | Yes | [6 empty] | 2026-01-06 | 2026-01-13 | 2026-01-06 | 2026-01-13 | 2026-01-13 | 2026-01-16 | 2026-01-28 | 2026-01-22 | 2026-01-22 | 2026-01-22 | 2026-02-05 |  |  | 2026-02-04 |  |  | CS | 2026-02-04 | [6 empty] | CS |  |  | 2026-02-04 | [106 empty] | 2026-03-12 | [17 empty] | 0 |  |  |  | Q4 2027 | [15 empty] | TRUE | FALSE |  | 0 | 0 | 1900 | 1900 | 1900
957 |  | Lanie Patterson | Brent Brooks | 2025-12-30 | [21 empty] | 2026-09-17 | Wthdw | RQP-1 |  |  |  | RQP-1 | 1 - NOAU |  | 954 | 14 - NOAU | 1 - NOAU | 272D6 | 954 |  | SCOPING | Scoping meeting due 10/1 |  | Zeeshan Yasin | Novel Energy Solutions LLC | ME PATENAUDE MILLS CSG LLC | 0 Mills Rd., Sidney | 2000516197 | 30017266427 | Solar | 999 | 0.999 | 1335.36 |  |  | 44.4161 | -69.8171 | 0 Mills Rd | 0 | Mills Rd | Sidney | 7 | NORTH AUGUSTA | 272D6 | 272T2 | 34.5 | 9310-L0470-5320-0023-ED00028 |  |  |  |  | Yes | [6 empty] | 2026-01-07 | 2026-01-14 | 2026-01-07 | 2026-01-14 | 2026-09-17 | 2026-09-21 | 2026-10-01 | [145 empty] | 0 | [19 empty] | FALSE | FALSE |  | 0 | 0 | 1900 | 1900 | 1900
[38 empty] | 0 | [192 empty] | 0 | [19 empty] | TRUE | TRUE |  | 0 | 0 | 1900 | 1900 | 1900
[38 empty] | 0 | [192 empty] | 0 | [19 empty] | TRUE | TRUE |  | 0 | 0 | 1900 | 1900 | 1900
XXXXX |  | XXXXX | XXXXX | XXXXX | XXXXX |  |  | XXXXX |  |  | XXXXX | XXXXX | XXXXX | [19 empty] | XXXXX |  | XXXXX | XXXXX |  | XXXXX | XXXXX |  | XXXXX |  |  | XXXXX | XXXXX | ` | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX |  | XXXXX | XXXXX |  | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX |  | XXXXX |  |  | XXXXX | XXXXX | XXXXX | XXXXX | #REF! | XXXXX | XXXXX | XXXXX | XXXXX | [11 empty] | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX |  |  |  |  | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX |  |  |  |  | XXXXX | XXXXX | XXXXX |  | XXXXX |  | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX |  | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX |  | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | . | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX |  | XXXXX | XXXXX |  |  |  | XXXXX | . | XXXXX |  | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX |  |  | XXXXX | XXXXX |  |  |  |  | XXXXX | [65 empty] | xxxxxx |  | XXXXX | XXXXX
194491.03
#VALUE!
[53 empty] | #VALUE! | [147 empty] | 44987
[10 empty] | 44690 | 15 | 44728 | [73 empty] | 10 | [39 empty] | 15
44706
28
1
44041
44734
44094
44691
44733
44726
44726
44713
44483
[32 empty] | 44203 | [50 empty] | `
44440
44533
44707
44698
Q_Status_Setting
[210 empty] | PRE_IA |  | PRE_IA
[210 empty] | TRIGGERED |  | TRIGGERED
[210 empty] | RE_QUEUED_FullEx |  | RE_QUEUED_FullEx |  | 2021-07-13: PRE_IA or TRIGGERED or RE_QUEUED_FullEx or RE_QUEUED or EXECUTED-WITHDRAWN or RESULTS or RE_QUEUED_FullEx or QUEUED or SCOPING or STUDY or PRE-STUDY or RESTUDY or EXECUTABLE
[210 empty] | RE_QUEUED |  | RE_QUEUED
[210 empty] | EXECUTED-WITHDRAWN |  | EXECUTED-WITHDRAWN
[210 empty] | RESULTS |  | RESULTS
[210 empty] | RE_QUEUED_FullEx |  | RE_QUEUED_FullEx
[210 empty] | QUEUED |  | QUEUED
[210 empty] | SCOPING |  | SCOPING
[210 empty] | STUDY |  | STUDY
[210 empty] | PRE-STUDY |  | PRE-STUDY
[210 empty] | RESTUDY |  | RESTUDY
[210 empty] | EXECUTABLE |  | EXECUTABLE
Formulas:
AORd = +WORKDAY(LvL4Trk4Accdb6[[#This Row],[AREC]],5, HOLIDAYS)
TEST43 = LvL4Trk4Accdb6[[#This Row],[Fully Executed IA_Agreement]]
TEST44 = LvL4Trk4Accdb6[[#This Row],[Fully Executed IA_Agreement]]
Scoping Due by Date = +WORKDAY(MAX(LvL4Trk4Accdb6[[#This Row],[NOC]],LvL4Trk4Accdb6[[#This Row],[Scoping Availability]]),10,HOLIDAYS)
Decision_dt_II = +LvL4Trk4Accdb6[[#This Row],[01IS_Issue_UnEx Actual]]
NOCd = +WORKDAY(LvL4Trk4Accdb6[[#This Row],[AREC]],10, HOLIDAYS)
NOC = +WORKDAY(LvL4Trk4Accdb6[[#This Row],[AREC]],10, HOLIDAYS)
AOR = +WORKDAY(LvL4Trk4Accdb6[[#This Row],[AREC]],5, HOLIDAYS)
Trigger Three = +WORKDAY([Trigger Three, row below],[ReQued ReStudy Triggered Three Date],HOLIDAYS)
Note on BL1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: =+VLOOKUP([@Circuit],LISTS!A1:H476,3,FALSE)
Note on IL1: Iberdrola S.A.: Means Invoice has been emailed to the customer.
Note on II2: Iberdrola S.A.: By Terry Vogel
Note on AZ3: Iberdrola S.A.: Split between 2 circuits 4.6 MW on each total is 9.2MW
Note on BA3: Iberdrola S.A.: Split between 2 circuits 4.6 MW on each total is 9.2MW
Note on II5: Iberdrola S.A.: Submitted via email by Terry Vogel
Note on II6: Iberdrola S.A.: Submitted via email by Terry Vogel
Note on AZ9: Iberdrola S.A.: Control Limited to 4,999 kW (4.99 MW)
Note on BC9: Iberdrola S.A.: Control Limited to 4,999 kW (4.99 MW)
Note on HF17: JACKSON, JOHN: Withdrew before this date
Note on HF28: JACKSON, JOHN: Withdrew on or before this date
Note on HD35: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: $732,331
Note on HE35: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8/10/2023
Note on HF42: JACKSON, JOHN: Withdrew on or before this date
Note on HF43: JACKSON, JOHN: Withdrawn on or before this date
Note on HF53: JACKSON, JOHN: Withdrew on or before this date
Note on HF84: JACKSON, JOHN: Withdrew on or before this date
Note on GT93: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2/1/2024
Note on HD93: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: $ 168,851
Note on HE93: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1/15/2024
Note on HH102: Iberdrola S.A.: Combined PRJ 101&106 under 1 IA and CMP Acct #
Note on IP102: Iberdrola S.A.: Combined PRJ 101&106 under 1 IA and CMP Acct #
Note on HF105: JACKSON, JOHN: Withdrew on or before this date
Note on HH107: Iberdrola S.A.: Combined PRJ 101&106 under 1 IA and CMP Acct #
Note on IP107: Iberdrola S.A.: Combined PRJ 101&106 under 1 IA and CMP Acct #
Note on HF116: JACKSON, JOHN: Withdrew on or befor this date
Note on AQ118: JACKSON, JOHN: Project was not affected by the last L2 Leapfrogger and retained the latest IA
Note on HF127: JACKSON, JOHN:Withdrew on or before this date
Note on HF146: JACKSON, JOHN: Withdrew on or before this date
Note on HF148: JACKSON, JOHN: Withdrew on or before this date.
Note on HD152: JACKSON, JOHN: 3/18/2024 report was 259,564
Note on HF157: JACKSON, JOHN: Withdrew on or before this date
Note on HF167: JACKSON, JOHN: Withdrew on or before this date
Note on HF172: JACKSON, JOHN: Withdrew on or before this date
Note on HF174: JACKSON, JOHN: Withdrew on or before this date
Note on HF183: JACKSON, JOHN: Withdrew on or before this date
Note on HF195: JACKSON, JOHN: Withdrew on or before this date
Note on HF197: JACKSON, JOHN: Withdrew on or before this date
Note on HF198: JACKSON, JOHN: Withdrew on or before this date
Note on HD201: JACKSON, JOHN: Previous revised cost 3/2/2023 of $329,346
Note on HF217: JACKSON, JOHN: Withdrew on or before this date
Note on HF225: JACKSON, JOHN: Withdrew on or before this date
Note on HF232: JACKSON, JOHN: Withdrew on or before this date
Note on HF233: JACKSON, JOHN: Withdrew on or before this date
Note on DD247: JACKSON, JOHN: First Restudy UnE 12/12/2023
Note on DH247: JACKSON, JOHN: Requested scoping meeting after receiving agreement, conducted 1/29/2024
Note on DY247: JACKSON, JOHN: First RS DEV complete 12/21/2024
Note on EH247: JACKSON, JOHN: First restudy executed 12/22/2023
Note on ET247: JACKSON, JOHN: First Restudy Issue due 2/7/2023
Note on FA247: JACKSON, JOHN: First RS complete 2/7/2024
Note on HD247: JACKSON, JOHN: Previous report 990,811 4/24/2024
Note on HF275: JACKSON, JOHN: Withdrew on or before this date
Note on HF292: JACKSON, JOHN:Withdrew on or before this date. Applied 12/4/2019
Note on HD309: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Previous report $299,466
Note on HE309: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Previous Report 1/27/2025
Note on HF314: JACKSON, JOHN: Withdrew on or before this date
Note on HF316: JACKSON, JOHN: Withdrew on or before this date
Note on HF325: JACKSON, JOHN: Withdrew on or before this date
Note on HN327: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: I.3.9 approved IA
Note on EA342: JACKSON, JOHN: Mod approved after 3 inproper document delays
Note on HD342: JACKSON, JOHN: $1,219,626 report dated 3/13/2023
Note on DD351: JACKSON, JOHN: First Restudy 7/21/2021
Note on EH351: JACKSON, JOHN: First restudy 9/2/2021
Note on ET351: JACKSON, JOHN: First Restudy 10/18/2021
Note on FA351: JACKSON, JOHN: First Restudy 10/19/2021
Note on FJ351: JACKSON, JOHN: First Restudy 10/22/2021
Note on DS360: JACKSON, JOHN: Restudy not required made modification and used paeyment on modified restudy
Note on EJ360: JACKSON, JOHN: Orginal study executed 12/7 study stopped 1/2 and project exercised one-time mod. PRJ went in to cure with withdrawal date of 2/22 due to lack of mod received.
Note on GQ360: JACKSON, JOHN: Requested Revsised IA 5/20/2024
Note on HD360: JACKSON, JOHN: 1,125,571 11/22/2022
Note on DD390: JACKSON, JOHN: Previous restudy 8/16/2021
Note on EH390: JACKSON, JOHN: Previous Restudy 8/21/2021
Note on ET390: JACKSON, JOHN: Previous Restudy due 10/5/2024
Note on FA390: JACKSON, JOHN: previous report completed 10/5/2021
Note on FJ390: JACKSON, JOHN: Previous report issued 10/6/2021
Note on HF406: JACKSON, JOHN: Withdrew on or before this date
Note on HF407: JACKSON, JOHN: Withdrew on or before this date
Note on HD408: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 276,687 previous cost
Note on HE408: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Prviouse cost date 1/16/2024
Note on HF418: JACKSON, JOHN: Withdrew on or before this date
Note on DF419: JACKSON, JOHN: PRJ submitted modification after receiving the study agreement
Note on HD419: JACKSON, JOHN: Previous study $1,634, 685
Note on HE419: JACKSON, JOHN: Prevous date 2/14/2023
Note on HF420: JACKSON, JOHN: Withdrew on or before this date
Note on HF429: JACKSON, JOHN: Withdrew on or before this date
Note on HF440: JACKSON, JOHN: Withdrew on or before this date
Note on FU452: JACKSON, JOHN: Requested IA 5/20/2024
Note on HF456: JACKSON, JOHN: Withdrew on or before this date
Note on HF457: JACKSON, JOHN: Withdrew on or before this date
Note on HF467: JACKSON, JOHN: Withdrew on or before this date
Note on HD482: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Previous study $174,641
Note on HE482: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Previous study 4/26/2024
Note on HF487: JACKSON, JOHN: Withdrew on or before this date
Note on HF495: JACKSON, JOHN: Withdrew on or before this date
Note on CS497: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Cure notification sent for late partial study agreement from developer
Note on DA497: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Cure notification sent for late partial study agreement from developer
Note on HF502: JACKSON, JOHN: Withdrew on or before this date
Note on DN517: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: First Combined Study Deposit. Project was leapfrogged and the study was stopped.
Note on HF518: JACKSON, JOHN: Withdrew on or before this date
Note on AT520: Cornelius R. Stevenson: Needs updated in SAP; requested from developer 10/2020
Note on HF521: JACKSON, JOHN: Withdrew on or before this date
Note on HF533: JACKSON, JOHN: Withdrew on or before this date
Note on HF545: JACKSON, JOHN: Withdrew on or before this date
Note on HI558: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 7/27/2021 this date is before 1st IA
Note on HJ558: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 7/27/2021 this date is before 1st IA
Note on CF578: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Before leapfrogging 6/21/2022
Note on CG578: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Before leapfrogging 8/3/2022
Note on CH578: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Before Leapfrogging 7/7/2022
Note on CQ579: JACKSON, JOHN: Estimate for facility study requested 1/26/2023
Note on HF586: JACKSON,JOHN: Withdrew on or before this date
Note on HD597: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Prev Cost 6,838,174
Note on HE597: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Prev Date 11/15/2022
Note on HF611: JACKSON, JOHN: Withdrew on or before this date
Note on HF616: JACKSON, JOHN: Withdrew on or before this date
Note on BB632: DC/AC ratio (2.69) is outside the typical range of 0.5-2.0.
Note on HD632: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 178,454
Note on HD639: JACKSON, JOHN: Cost form report 1/12/2023 $337,997
Note on DD650: JACKSON, JOHN: Prevous restudy 8/1/2021
Note on DY650: JACKSON, JOHN: Previous study 9/20/2021
Note on EH650: JACKSON, JOHN: Previous study 9/23/2021
Note on ET650: JACKSON, JOHN: Previous Restudy due 11/5/2021
Note on FA650: JACKSON, JOHN: Previous restudy completed 10/22/2021
Note on FJ650: JACKSON, JOHN: previous restudy 10/22/2021
Note on GB650: JACKSON, JOHN: 10/22/2021 First RS Results meeting
Note on GJ650: JACKSON, JOHN: 10/26/2021 First RS results meeting note sent
Note on HD658: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: $ 296,209
Note on HE658: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 11/15/2022 and 6/18/2025
Note on DF670: JACKSON, JOHN: First Agreement sent 9/25 submitted mod second agreement sent 10/11
Note on HD675: JACKSON, JOHN: $358,322 for report 9/15/2022
Note on BK700: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This needs to be confirmed with Distribution Planning prior to adjusting it per the email sent by Robert Fontana at approximately 4:48pm 03/01/2022. The project has stated they selected #65 but we need to be sure that is confirmed with dist planning
Note on FU713: JACKSON, JOHN: Requesed IA 5/24/2024
Note on FR723: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Wavied Meeting, wanted IA. Documented in PRJ Folder.
Note on GA723: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Wavied Meeting, wanted IA. Documented in PRJ Folder.
Note on GI723: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Wavied Meeting, wanted IA. Documented in PRJ Folder.
Note on FR725: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Wavied Meeting, wanted IA. Documented in PRJ Folder.
Note on GA725: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Wavied Meeting, wanted IA. Documented in PRJ Folder.
Note on GI725: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Wavied Meeting, wanted IA. Documented in PRJ Folder.
Note on HD729: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: $ 371,743
Note on HE729: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3/5/2024
Note on HJ729: JACKSON, JOHN: Issued late due to Novel level 2 #81490 having the same POI as 728
Note on HD733: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Prev cost $244,023
Note on HE733: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Prev cost date 7/30/2024
Note on FI751: JACKSON, JOHN: Study not valid due to withdrawal
Note on HD770: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 335827
Note on HE770: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 7/8/2024
Note on HD779: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: $688,051
Note on HE779: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4/19/2024
Note on GT782: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2/4/2024
Note on HD782: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: $ 316,184
Note on HE782: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2/19/2025
Note on GD796: JACKSON, JOHN: Requested IA 5/20/2024
Note on GL796: JACKSON, JOHN: Requested IA 5/22
Note on DC804: JACKSON, JOHN: First executable combined study issued 10/13 prj leapfrogged 10/20
Note on AV809: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Was Stokewood Dr Lebanon ME
Note on DC812: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2/1/2024 Previous combined study
Note on CF816: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1/24/2024 before requeuing
Note on CG816: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2/1/2024 before requeuing
Note on CH816: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2/7/2024 before requeuing
Note on GS822: JACKSON, JOHN: IA Delayed due to a delay of a revised final report with surge arrestors removed
Note on DF839: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: First Agreement 4/20/2024
Note on HD839: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: $ 324,558
Note on HE839: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 12/15/2025
Note on DA840: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Original Unexecuted Date 11/7/2024
Note on DN840: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Original Deposit 12/10/2024
Note on DV840: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Original Dev Complete 12/10/2024
Note on CF841: JACKSON, JOHN: Mod approved switched from Elm St to Gray sub
Note on EE847: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Original Executed Date 12/18/2024
Note on HD853: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 577,016 report revised removed TGFOV
Note on HE853: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8/28/2025 report revised removed TGFOV
Note on HD855: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: $311,593
Note on HE855: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6/18/2024
Note on FR860: JACKSON, JOHN: Waived results meeting 4/11
Note on HD866: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: $ 265,901
Note on HE866: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3/10/2025
Note on CO870: JACKSON, JOHN: Project had been placed in cure
Note on CJ871: JACKSON, JOHN: Meeting moved twice due to storm
Note on EZ874: JACKSON, JOHN: Report was late due to a Level 2 project being included in Cost sharing table
Note on HD881: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: $ 424,989
Note on HE881: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 12/5/2024
Note on CF882: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Before withdrawal 4/9/2025
Note on CG882: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Before withdrawal 4/14/2025
Note on CH882: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Before withdrawal 4/24/2025
Note on CI882: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Before withdrawal 4/15/2025
Note on DC901: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Previous agreement due sent 9/30/2024
Note on HD901: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: $669,815
Note on HE901: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4/17/2025
Note on CJ913: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Second Scoping meeting 1/14/2025
Note on CK913: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Second Scoping meeting 1/14/2025
Note on DA913: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Original Unex agreement send 10/31/2024
Note on DN913: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Original FS deposit 11/26/2024
Note on EE913: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Original Feasibility Study executed 11/26/2024
Note on CI917: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: New Scoping meeting scheduled 3/27/2025
Note on CI918: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Previous Date before withdrawal 4/21/2025
Note on CJ918: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Previous date before withdrawal 5/5/5025
Note on CK918: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Previous date before withdrawal 5/5/2025
Note on CL918: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Previous date before withdrawal 5/19/2025
Note on DG927: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Original Requeued email (9/9)did not contain the study agreement

## LISTS
|  | Sub | [5 empty] | Column1
120D1 | DOVER | BANGOR HYDRO (EMERA) | Not Applicable | 120D1 | 12.47 | BNHE | New Year's Day | 2015-01-01
200D1 | AUGUSTA | AUGUSTA K5 | 200T1 | 200D1 | 12.47 | AGK5 | Martin Luther King Jr. Day | 2015-01-19
200D2 | AUGUSTA | AUGUSTA K5 | 200T1 | 200D2 | 12.47 | AGK6 | President's Day | 2015-02-16
200D3 | AUGUSTA | AUGUSTA K5 | 200T1 | 200D3 | 12.47 | AGK5 | Patriot's Day | 2015-04-20
204D1 | BRUNSWICK | WASHINGTON ST (BATH) | 204T2 | 204D1 | 12.47 | BWST | Memorial Day | 2015-05-25
204D3 | BRUNSWICK | WASHINGTON ST (BATH) | 204T2 | 204D3 | 12.47 | BWST | Independence Day | 2015-07-03
204D6 | BRUNSWICK | WASHINGTON ST (BATH) | 34KV BUS 1 | 204D6 | 34.5 | BWST | Labor Day | 2015-09-07
206D1 | BRUNSWICK | BATH NORTH END | 206T1 | 206D1 | 12.47 | BANE | Columbus Day | 2015-10-12
207D1 | AUGUSTA | BLAIR ROAD | 207T1 | 207D1 | 12.47 | BLRD | Veteran's Day | 2015-11-11
207D2 | AUGUSTA | BLAIR ROAD | 207T1 | 207D2 | 12.47 | BLRD | Thanksgiving Day | 2015-11-26
208D1 | AUGUSTA | BOND BROOK | 208T1 | 208D1 | 12.47 | BOND | Thanksgiving Day After | 2015-11-27
208D2 | AUGUSTA | BOND BROOK | 208T1 | 208D2 | 12.47 | BOND | Christmas Day | 2015-12-25
208D3 | AUGUSTA | BOND BROOK | 208T1 | 208D3 | 12.47 | BOND | New Year's Day | 2016-01-01
209D1 | BRUNSWICK | BOOTHBAY HARBOR | 209T1 | 209D1 | 12.47 | BOOT | Martin Luther King Jr. Day | 2016-01-18
209D2 | BRUNSWICK | BOOTHBAY HARBOR | 209T2 | 209D2 | 12.47 | BOOT | President's Day | 2016-02-15
209D3 | BRUNSWICK | BOOTHBAY HARBOR | 209T1 | 209D3 | 12.47 | BOOT | Patriot's Day | 2016-04-18
210D1 | BRUNSWICK | BRISTOL | 210T1 | 210D1 | 12.47 | BRIS | Memorial Day | 2016-05-30
210D2 | BRUNSWICK | BRISTOL | 210T1 | 210D2 | 12.47 | BRIS | Independence Day | 2016-07-04
211D1 | AUGUSTA | BROWNS CROSSING | 211T1 | 211D1 | 12.47 | BRCR | Labor Day | 2016-09-05
211D2 | AUGUSTA | BROWNS CROSSING | 211T1 | 211D2 | 12.47 | BRWE | Columbus Day | 2016-10-10
213D1 | BRUNSWICK | BRUNSWICK WEST SIDE | 213T1 | 213D1 | 12.47 | BRWE | Veteran's Day | 2016-11-11
213D2 | BRUNSWICK | BRUNSWICK WEST SIDE | 213T2 | 213D2 | 12.47 | BRWE | Thanksgiving Day | 2016-11-24
213D3 | BRUNSWICK | BRUNSWICK WEST SIDE | 213T1 | 213D3 | 12.47 | BRWE | Thanksgiving Day After | 2016-11-25
213D4 | BRUNSWICK | BRUNSWICK WEST SIDE | 213T2 | 213D4 | 12.47 | BRWE | Christmas Day | 2016-12-26
214D1 | ROCKLAND | CAMDEN | 214T2 | 214D1 | 12.47 | CAMD | New Year's Day | 2017-01-02
214D2 | ROCKLAND | CAMDEN | 214T2 | 214D2 | 12.47 | CAMD | Martin Luther King Jr. Day | 2017-01-16
214D3 | ROCKLAND | CAMDEN | 214T1 | 214D3 | 12.47 | CAMD | President's Day | 2017-02-20
214D4 | ROCKLAND | CAMDEN | 214T1 | 214D4 | 12.47 | CAMD | Patriot's Day | 2017-04-17
215D2 | AUGUSTA | CAPITOL STREET | 215T2 | 215D2 | 12.47 | CAST | Memorial Day | 2017-05-29
215D3 | AUGUSTA | CAPITOL STREET | 215T2 | 215D3 | 12.47 | CAST | Independence Day | 2017-07-04
215D5 | AUGUSTA | CAPITOL STREET | 215T1 | 215D5 | 12.47 | CAST | Labor Day | 2017-09-04
215D6 | AUGUSTA | CAPITOL STREET | 215T1 | 215D6 | 12.47 | CAST | Columbus Day | 2017-10-09
215D7 | AUGUSTA | CAPITOL STREET | 215T1 | 215D7 | 12.47 | CAST | Veteran's Day | 2017-11-10
216D1 | AUGUSTA | CONY ROAD | 216T1 | 216D1 | 12.47 | CONY | Thanksgiving Day | 2017-11-23
216D2 | AUGUSTA | CONY ROAD | 216T1 | 216D2 | 12.47 | CONY | Thanksgiving Day After | 2017-11-24
216D3 | AUGUSTA | CONY ROAD | 216T1 | 216D3 | 12.47 | CONY | Christmas Day | 2017-12-25
217D1 | BRUNSWICK | COOKS CORNER | 217T1 | 217D1 | 12.47 | COCO | New Year's Day | 2018-01-01
217D2 | BRUNSWICK | COOKS CORNER | 217T1 | 217D2 | 12.47 | COCO | Martin Luther King Jr. Day | 2018-01-15
217D3 | BRUNSWICK | COOKS CORNER | 34KV BUS 1 | 217D3 | 34.5 | COCO | President's Day | 2018-02-19
218D1 | PORTLAND | WILLIAM F WYMAN OUTSIDE | 218T13 | 218D1 | 12.47 | WFWO | Patriot's Day | 2018-04-16
219D1 | BRUNSWICK | DAMARISCOTTA MILLS | 219T1 | 219D1 | 12.47 | DAMS | Memorial Day | 2018-05-28
219D2 | BRUNSWICK | DAMARISCOTTA MILLS | 219T1 | 219D2 | 12.47 | DAMS | Independence Day | 2018-07-04
223D1 | BRUNSWICK | EDGECOMB | 223T1 | 223D1 | 12.47 | EDGE | Labor Day | 2018-09-03
225D1 | BRUNSWICK | FREEPORT | 225T2 | 225D1 | 12.47 | FREE | Columbus Day | 2018-10-08
225D2 | BRUNSWICK | FREEPORT | 225T1 | 225D2 | 12.47 | FREE | Veteran's Day | 2018-11-12
225D3 | BRUNSWICK | FREEPORT | 225T2 | 225D3 | 12.47 | FREE | Thanksgiving Day | 2018-11-22
225D4 | BRUNSWICK | FREEPORT | 225T1 | 225D4 | 12.47 | FREE | Thanksgiving Day After | 2018-11-23
226D2 | AUGUSTA | GARDINER | 226T1 | 226D2 | 12.47 | GARD | Christmas Day | 2018-12-25
230D1 | AUGUSTA | COOPERS MILLS ROAD | 230T2 | 230D1 | 12.47 | GARD | New Year's Day | 2019-01-01
230D2 | AUGUSTA | COOPERS MILLS ROAD | 230T2 | 230D2 | 12.47 | COMR | Martin Luther King Jr. Day | 2019-01-21
231D1 | BRUNSWICK | LISBON | 231T1 | 231D1 | 12.47 | LISB | President's Day | 2019-02-18
231D2 | BRUNSWICK | LISBON | 231T1 | 231D2 | 12.47 | LISB | Patriot's Day | 2019-04-15
232D1 | BRUNSWICK | LISBON FALLS | 232T1 | 232D1 | 12.47 | LSFA | Memorial Day | 2019-05-27
232D2 | BRUNSWICK | LISBON FALLS | 232T2 | 232D2 | 12.47 | LSFA | Independence Day | 2019-07-04
233D1 | AUGUSTA | MANCHESTER | 233T1 | 233D1 | 12.47 | MANC | Labor Day | 2019-09-02
233D2 | AUGUSTA | MANCHESTER | 233T1 | 233D2 | 12.47 | MANC | Columbus Day | 2019-10-14
234D1 | ROCKLAND | MANKTOWN ROAD | 234T1 | 234D1 | 12.47 | MARO | Veteran's Day | 2019-11-11
237D1 | FAIRFIELD | MCCOYS | 237T1 | 237D1 | 12.47 | MCCO | Thanksgiving Day | 2019-11-28
238D1 | BRUNSWICK | MESSINA | 238T1 | 238D1 | 12.47 | MESS | Thanksgiving Day After | 2019-11-29
239D10 | ROCKLAND | PARK STREET | 239T5 | 239D10 | 12.47 | PAST | Christmas Day | 2019-12-25
239D5 | ROCKLAND | PARK STREET | 239T4 | 239D5 | 12.47 | PAST | New Year's Day | 2020-01-01
239D6 | ROCKLAND | PARK STREET | 239T2 | 239D6 | 12.47 | PAST | Martin Luther King Jr. Day | 2020-01-20
239D7 | ROCKLAND | PARK STREET | 239T2 | 239D7 | 12.47 | PAST | President's Day | 2020-02-17
239D8 | ROCKLAND | PARK STREET | 239T3 | 239D8 | 12.47 | PAST | Patriot's Day | 2020-04-20
239D9 | ROCKLAND | PARK STREET | 239T4 | 239D9 | 12.47 | PAST | Memorial Day | 2020-05-25
240D1 | AUGUSTA | RICHMOND | 240T1 | 240D1 | 12.47 | RICH | Independence Day | 2020-07-03
241D1 | BRUNSWICK | SHEEPSCOT | 241T1 | 241D1 | 12.47 | SHEE | Labor Day | 2020-09-07
242D1 | AUGUSTA | SIDNEY | 242T1 | 242D1 | 12.47 | SIDN | Columbus Day | 2020-10-12
242D2 | AUGUSTA | SIDNEY | 242T1 | 242D2 | 12.47 | SIDN | Veteran's Day | 2020-11-11
244D1 | AUGUSTA | SOUTH CHINA | 244T1 | 244D1 | 12.47 | SOCH | Thanksgiving Day | 2020-11-26
244D2 | AUGUSTA | SOUTH CHINA | 244T1 | 244D2 | 12.47 | SOCH | Thanksgiving Day After | 2020-11-27
245D1 | ROCKLAND | STICKNEYS CORNER | 245T1 | 245D1 | 12.47 | STCO | Christmas Day | 2020-12-25
245D2 | ROCKLAND | STICKNEYS CORNER | 245T1 | 245D2 | 12.47 | STCO | New Year's Day | 2021-01-01
246D1 | ROCKLAND | THOMASTON CREEK | 34kV | 246D1 | 12.47 | THCR | Martin Luther King Jr. Day | 2021-01-18
246D2 | ROCKLAND | THOMASTON CREEK | 246T1 | 246D2 | 12.47 | THCR | President's Day | 2021-02-15
246D3 | ROCKLAND | THOMASTON CREEK | 246T1 | 246D3 | 12.47 | THCR | Patriot's Day | 2021-04-19
249D1 | BRUNSWICK | TOPSHAM OLD | 249T1 | 249D1 | 12.47 | TPOL | Memorial Day | 2021-05-31
249D2 | BRUNSWICK | TOPSHAM OLD | 249T1 | 249D2 | 12.47 | TPOL | Juneteenth National Independence Day (beginning 2021) | 2021-06-18
250D1 | BRUNSWICK | TOPSHAM | 250T2 | 250D1 | 12.47 | TP34 | Independence Day | 2021-07-05
250D2 | BRUNSWICK | TOPSHAM | 250T2 | 250D2 | 12.47 | TP34 | Labor Day | 2021-09-06
250K3 | BRUNSWICK | TOPSHAM | 34KV BUS 1 | 250K3 | 34.5 | TP34 | Columbus Day | 2021-10-11
251D1 | ROCKLAND | UNION | 251T1 | 251D1 | 12.47 | UNIO | Veteran's Day | 2021-11-11
252D1 | ROCKLAND | WALDOBORO | 252T1 | 252D1 | 12.47 | WALD | Thanksgiving Day | 2021-11-25
252D2 | ROCKLAND | WALDOBORO | 252T1 | 252D2 | 12.47 | WALD | Thanksgiving Day After | 2021-11-26
253D1 | ROCKLAND | WARREN | 253T1 | 253D1 | 12.47 | WARR | Christmas Day | 2021-12-24
255D1 | AUGUSTA | WEST STREET | 255T1 | 255D1 | 12.47 | WSST | New Year's Day | 2021-12-31
255D2 | AUGUSTA | WEST STREET | 255T1 | 255D2 | 12.47 | WSST | Martin Luther King Jr. Day | 2022-01-17
256D1 | AUGUSTA | WINTHROP | 256T2 | 256D1 | 12.47 | WINT | President's Day | 2022-02-21
256D2 | AUGUSTA | WINTHROP | 256T1 | 256D2 | 12.47 | WINT | Patriot's Day | 2022-04-18
256D3 | AUGUSTA | WINTHROP | 256T1 | 256D3 | 12.47 | WINT | Memorial Day | 2022-05-30
258D1 | BRUNSWICK | WOOLWICH | 258T1 | 258D1 | 12.47 | WOOL | Juneteenth National Independence Day (beginning 2021) | 2022-06-20
261D3 | BRUNSWICK | BATH | 261T2 | 261D3 | 12.47 | BATH | Independence Day | 2022-07-04
261D4 | BRUNSWICK | BATH | 261T2 | 261D4 | 12.47 | BATH | Labor Day | 2022-09-05
262D1 | AUGUSTA | PUDDLEDOCK ROAD | 34 kV BUS 1 | 262D1 | 34.5 | PDRD | Columbus Day | 2022-10-10
263D1 | AUGUSTA | BOWMAN STREET | 34kV BUS 2 | 263D1 | 34.5 | BOST | Veteran's Day | 2022-11-11
270D1 | ROCKLAND | MEADOW ROAD | 270T2 | 270D1 | 12.47 | MERO | Thanksgiving Day | 2022-11-24
270D2 | ROCKLAND | MEADOW ROAD | 270T2 | 270D2 | 12.47 | MERO | Thanksgiving Day After | 2022-11-25
272D1 | AUGUSTA | NORTH AUGUSTA | 272T1 | 272D1 | 12.47 | NOAU | Christmas Day | 2022-12-26
272D2 | AUGUSTA | NORTH AUGUSTA | 272T1 | 272D2 | 12.47 | NOAU | New Year's Day | 2023-01-02
272D3 | AUGUSTA | NORTH AUGUSTA | 272T1 | 272D3 | 12.47 | NOAU | Martin Luther King Jr. Day | 2023-01-16
272D4 | AUGUSTA | NORTH AUGUSTA | 272T1 | 272D4 | 12.47 | NOAU | President's Day | 2023-02-20
272D5 | AUGUSTA | NORTH AUGUSTA | 272T2 | 272D5 | 34.5 | NOAU | Patriot's Day | 2023-04-17
272D6 | AUGUSTA | NORTH AUGUSTA | 272T2 | 272D6 | 34.5 | NOAU | Memorial Day | 2023-05-29
273D4 | BRUNSWICK | BRUNSWICK HYDRO | 273T2 | 273D4 | 12.47 | BRHY | Juneteenth National Independence Day (beginning 2021) | 2023-06-19
273D5 | BRUNSWICK | BRUNSWICK HYDRO | 273T2 | 273D5 | 12.47 | BRHY | Independence Day | 2023-07-04
274D1 | BRUNSWICK | MAINE YANKEE | 274T2 | 274D1 | 12.47 | MAYA | Labor Day | 2023-09-04
400D1 | FARMINGTON | ANDOVER | 400T1 | 400D1 | 12.47 | ANDO | Columbus Day | 2023-10-09
400D2 | FARMINGTON | ANDOVER | 400T1 | 400D2 | 12.47 | ANDO | Veteran's Day | 2023-11-10
403D1 | FARMINGTON | BETHEL | 403T1 | 403D1 | 12.47 | BETH | Thanksgiving Day | 2023-11-23
403D2 | FARMINGTON | BETHEL | 403T1 | 403D2 | 34.5 | BETH | Thanksgiving Day After | 2023-11-24
405D1 | BRIDGTON | FRYEBURG TAP | 405T1 | 405D1 | 12.47 | FRYT | Christmas Day | 2023-12-25
405D2 | BRIDGTON | FRYEBURG TAP | 405T1 | 405D2 | 12.47 | FRYT | New Year's Day | 2024-01-01
406D1 | BRIDGTON | BRIDGTON | 406T1 | 406D1 | 12.47 | BRID | Martin Luther King Jr. Day | 2024-01-15
406D2 | BRIDGTON | BRIDGTON | 406T1 | 406D2 | 12.47 | BRID | President's Day | 2024-02-19
406D3 | BRIDGTON | BRIDGTON | 406T1 | 406D3 | 12.47 | BRID | Patriot's Day | 2024-04-15
406D4 | BRIDGTON | BRIDGTON | 34kV BUS 1 | 406D4 | 34.5 | BR34 | Memorial Day | 2024-05-27
407D1 | BRIDGTON | BRYANT POND | 407T1 | 407D1 | 12.47 | BRPO | Juneteenth National Independence Day (beginning 2021) | 2024-06-19
409D1 | BRIDGTON | PARIS TAP | 409T1 | 409D1 | 12.47 | PATP | Independence Day | 2024-07-04
411D1 | LEWISTON | CROWLEYS | 411T2 | 411D1 | 12.47 | CROW | Labor Day | 2024-09-02
411D2 | LEWISTON | CROWLEYS | 411T2 | 411D2 | 12.47 | CROW | Columbus Day | 2024-10-14
412D1 | LEWISTON | DEER RIPS | 412T2 | 412D1 | 12.47 | DEER | Veteran's Day | 2024-11-11
412D2 | LEWISTON | DEER RIPS | 412T2 | 412D2 | 12.47 | DEER | Thanksgiving Day | 2024-11-28
412D3 | LEWISTON | DEER RIPS | 412T4 | 412D3 | 12.47 | DEER | Thanksgiving Day After | 2024-11-29
412D4 | LEWISTON | DEER RIPS | 412T4 | 412D4 | 12.47 | DEER | Christmas Day | 2024-12-25
413D1 | BRIDGTON | DENMARK | 413T1 | 413D1 | 12.47 | DENM | New Year's Day | 2025-01-01
413D2 | BRIDGTON | DENMARK | 413T1 | 413D2 | 12.47 | DENM | Martin Luther King Jr. Day | 2025-01-20
415D1 | BRIDGTON | FRYEBURG | 415T2 | 415D1 |  | FRYE | President's Day | 2025-02-17
415D2 | BRIDGTON | FRYEBURG | 415T1 | 415D2 | 12.47 | FRYE | Patriot's Day | 2025-04-21
416D1 | LEWISTON | GRAY | 416T2 | 416D1 | 12.47 | GRAY | Memorial Day | 2025-05-26
416D2 | LEWISTON | GRAY | 416T1 | 416D2 | 12.47 | GRAY | Juneteenth National Independence Day (beginning 2021) | 2025-06-19
416D3 | LEWISTON | GRAY | 416T1 | 416D3 | 12.47 | GRAY | Independence Day | 2025-07-04
419D1 | BRIDGTON | HIRAM HYDRO | 419T3 | 419D1 | 12.47 | HIHY | Labor Day | 2025-09-01
420D1 | LEWISTON | HOTEL ROAD | 420T2 | 420D1 | 12.47 | HORD | Columbus Day | 2025-10-13
420D2 | LEWISTON | HOTEL ROAD | 420T2 | 420D2 | 12.47 | HORD | Veteran's Day | 2025-11-11
420D3 | LEWISTON | HOTEL ROAD | 420T2 | 420D3 | 12.47 | HORD | Thanksgiving Day | 2025-11-27
420D4 | LEWISTON | HOTEL ROAD | 420T1 | 420D4 | 34.5 | HORD | Thanksgiving Day After | 2025-11-28
420D5 | LEWISTON | HOTEL ROAD | 420T2 | 420D5 | 12.47 | HORD | Christmas Day | 2025-12-25
420D6 | LEWISTON | HOTEL ROAD | 420T1 | 420D6 | 34.5 | HORD | New Year's Day | 2026-01-01
420D7 | LEWISTON | HOTEL ROAD | 420T1 | 420D7 | 34.5 | HORD | Martin Luther King Jr. Day | 2026-01-19
421D1 | LEWISTON | CHALLENGER DRIVE | 421T1 | 421D1 | 12.47 | CH12 | President's Day | 2026-02-16
421D2 | LEWISTON | CHALLENGER DRIVE | 421T1 | 421D2 | 12.47 | CH12 | Patriot's Day | 2026-04-20
421D3 | LEWISTON | CHALLENGER DRIVE | 421T1 | 421D3 | 12.47 | CH12 | Memorial Day | 2026-05-25
421D4 | LEWISTON | CHALLENGER DRIVE | 421T2 | 421D4 | 34.5 | CH34 | Juneteenth National Independence Day (beginning 2021) | 2026-06-19
423D1 | BRIDGTON | KIMBALL ROAD | 423T2 | 423D1 | 12.47 | KIRD | Independence Day | 2026-07-03
423D2 | BRIDGTON | KIMBALL ROAD | 423T2 | 423D2 | 12.47 | KIRD | Labor Day | 2026-09-07
424D2 | LEWISTON | LEWISTON LOWER | 424T1 | 424D2 | 12.47 | L115 | Columbus Day | 2026-10-12
424D4 | LEWISTON | LEWISTON LOWER | 424T3 | 424D4 | 12.47 | L115 | Veteran's Day | 2026-11-11
424D5 | LEWISTON | LEWISTON LOWER | 424T3 | 424D5 | 12.47 | L115 | Thanksgiving Day | 2026-11-26
424D6 | LEWISTON | LEWISTON LOWER | 424T1 | 424D6 | 12.47 | L115 | Thanksgiving Day After | 2026-11-27
428D1 | FARMINGTON | LIVERMORE FALLS | 428T1 | 428D1 | 12.47 | LVFA | Christmas Day | 2026-12-25
428D2 | FARMINGTON | LIVERMORE FALLS | 428T1 | 428D2 | 12.47 | LVFA | New Year's Day | 2027-01-01
428D3 | FARMINGTON | LIVERMORE FALLS | 428T1 | 428D3 | 12.47 | LVFA | Martin Luther King Jr. Day | 2027-01-18
429D1 | FARMINGTON | LOCKES MILLS | 429T1 | 429D1 | 12.47 | LOMS | President's Day | 2027-02-15
430D1 | BRIDGTON | LOVELL | 430T1 | 430D1 | 12.47 | LOVE | Patriot's Day | 2027-04-19
431D1 | LEWISTON | MECHANIC FALLS | 431T2 | 431D1 | 12.47 | MEFA | Memorial Day | 2027-05-31
431D2 | LEWISTON | MECHANIC FALLS | 431T1 | 431D2 | 12.47 | MEFA | Juneteenth National Independence Day (beginning 2021) | 2027-06-18
431D3 | LEWISTON | MECHANIC FALLS | 431T2 | 431D3 | 12.47 | MEFA | Independence Day | 2027-07-05
435D1 | BRIDGTON | NORWAY | 435T2 | 435D1 | 12.47 | NORW | Labor Day | 2027-09-06
435D2 | BRIDGTON | NORWAY | 435T2 | 435D2 | 12.47 | NORW | Columbus Day | 2027-10-11
435D3 | BRIDGTON | NORWAY | 435T2 | 435D3 | 12.47 | NORW | Veteran's Day | 2027-11-11
435D4 | BRIDGTON | NORWAY | 435T2 | 435D4 | 12.47 | NORW | Thanksgiving Day | 2027-11-25
436D1 | LEWISTON | GREAT FALLS | 436T2 | 436D1 | 12.47 | GRFA | Thanksgiving Day After | 2027-11-26
436D2 | LEWISTON | GREAT FALLS | 436T2 | 436D2 | 12.47 | GRFA | Christmas Day | 2027-12-24
436D3 | LEWISTON | GREAT FALLS | 436T1 | 436D3 | 12.47 | GRFA | New Year's Day | 2027-12-31
436D4 | LEWISTON | GREAT FALLS | 436T2 | 436D4 | 12.47 | GRFA | Martin Luther King Jr. Day | 2028-01-17
436D6 | LEWISTON | GREAT FALLS | 436T1 | 436D6 | 12.47 | GRFA | President's Day | 2028-02-21
436D7 | LEWISTON | GREAT FALLS | 436T1 | 436D7 | 12.47 | GRFA | Patriot's Day | 2028-04-17
437D1 | BRIDGTON | OXFORD | 437T1 | 437D1 | 12.47 | OXFO | Memorial Day | 2028-05-29
437D2 | BRIDGTON | OXFORD | 437T1 | 437D2 | 12.47 | OXFO | Juneteenth National Independence Day (beginning 2021) | 2028-06-19
438D1 | BRIDGTON | PAPOOSE POND | Tap off of Transmission Line | 438D1 | 34.5 | PAPO | Independence Day | 2028-07-04
441D3 | FARMINGTON | PHILIPS ELMET | 441T3 | 441D3 | 12.47 | PHEN | Labor Day | 2028-09-04
444D1 | BRIDGTON | RAYMOND 34 KV | 444T1 | 444D1 | 12.47 | RA34 | Columbus Day | 2028-10-09
444D2 | BRIDGTON | RAYMOND 34 KV | 444T1 | 444D2 | 12.47 | RA34 | Veteran's Day | 2028-11-10
444D3 | BRIDGTON | RAYMOND 34 KV | 444T1 | 444D3 | 12.47 | RA34 | Thanksgiving Day | 2028-11-23
445D1 | BRIDGTON | RAYMOND 115 KV | 445T1 | 445D1 | 34.5 | R115 | Thanksgiving Day After | 2028-11-24
445D2 | BRIDGTON | RAYMOND 115 KV | 445T2 | 445D2 | 34.5 | R115 | Christmas Day | 2028-12-25
447D1 | FARMINGTON | RUMFORD | 447T3 | 447D1 | 12.47 | RUMF
447D2 | FARMINGTON | RUMFORD | 447T4 | 447D2 | 12.47 | RUMF
447D3 | FARMINGTON | RUMFORD | 447T4 | 447D3 | 12.47 | RUMF
447D4 | FARMINGTON | RUMFORD | 447T3 | 447D4 | 12.47 | RUMF
449D1 | FARMINGTON | RILEY | 449T1 | 449D1 | 12.47 | RILE
449D2 | FARMINGTON | RILEY | 449T1 | 449D2 | 12.47 | RILE
450D1 | LEWISTON | SABATTUS | 450T1 | 450D1 | 12.47 | SABA
450D2 | LEWISTON | SABATTUS | 450T1 | 450D2 | 12.47 | SABA
451D10 | LEWISTON | MIDDLE STREET | 451T2 | 451D10 | 12.47 | MIDD
451D2 | LEWISTON | MIDDLE STREET | 451T2 | 451D2 | 12.47 | MIDD
451D3 | LEWISTON | MIDDLE STREET | 451T3 | 451D3 | 12.47 | MIDD
451D4 | LEWISTON | MIDDLE STREET | 451T2 | 451D4 | 12.47 | MIDD
451D5 | LEWISTON | MIDDLE STREET | 451T3 | 451D5 | 12.47 | MIDD
451D6 | LEWISTON | MIDDLE STREET | 451T2 | 451D6 | 12.47 | MIDD
451D7 | LEWISTON | MIDDLE STREET | 451T3 | 451D7 | 12.47 | MIDD
451D8 | LEWISTON | MIDDLE STREET | 451T2 | 451D8 | 12.47 | MIDD
451D9 | LEWISTON | MIDDLE STREET | 451T3 | 451D9 | 12.47 | MIDD
452K1 | FARMINGTON | WOODSTOCK | 452T1 | 452K1 | 34.5 | WOOD
453D1 | FARMINGTON | TRAP CORNER | 453T1 | 453D1 | 12.47 | TPCO
454D1 | LEWISTON | TURNER | 454T1 | 454D1 | 12.47 | TURN
454D2 | LEWISTON | TURNER | 454T1 | 454D2 | 12.47 | TURN
457D1 | AUGUSTA | MONMOUTH | 457T1 | 457D1 | 34.5 | MONM
457D2 | AUGUSTA | MONMOUTH | 457T2 | 457D2 | 12.47 | MONM
457D3 | AUGUSTA | MONMOUTH | 457T2 | 457D3 | 12.47 | MONM
458D1 | BRIDGTON | WEST BRIDGTON | 458T1 | 458D1 | 12.47 | WEBR
458D2 | BRIDGTON | WEST BRIDGTON | 458T1 | 458D2 | 12.47 | WEBR
460K1 | FARMINGTON | NEWRY | 34KV Tap off of Transmission Line | 460K1 | 34.5 | NEWR
461D1 | FARMINGTON | LUDDEN LANE | 461T1 | 461D1 | 34.5 | LULA
463D1 | BRIDGTON | CASCO TAP | 463T1 | 463D1 | 12.47 | CATP
466D1 | FARMINGTON | RUMFORD INDUSTRIAL PARK | 466T1 | 466D1 | 34.5 | RUIP
467D1 | LEWISTON | TURNER TAP | Tap off of Transmission Line | 467D1 | 34.5 | TUTP
469D1 | BRIDGTON | NAPLES TAP | 469T1 | 469D1 | 12.47 | NATP
470D1 | BRIDGTON | SAND ROAD TAP | 470T1 | 470D1 | 12.47 | SRTP
471D1 | LEWISTON | LEEDS | 471T1 | 471D1 | 34.5 | LEED
471D2 | LEWISTON | LEEDS | 471T1 | 471D2 | 34.5 | LEED
476D1 | BRIDGTON | LAMB MILLS TAP | 476T1 off of tranmssion line | 476D1 | 12.47
602D2 | ALFRED | BASSETT | 602T1 | 602D2 | 12.47 | BASS
602D3 | ALFRED | BASSETT | 602T1 | 602D3 | 12.47 | BASS
603D2 | ALFRED | BERWICK | 603T1 | 603D2 | 12.47 | BERW
603D3 | ALFRED | BERWICK | 603T1 | 603D3 | 12.47 | BERW
605D1 | ALFRED | BIDDEFORD PUMPING STATION | 605T1 | 605D1 | 12.47 | BDPP
607D1 | PORTLAND | BISHOP STREET | 607T1 | 607D1 | 12.47 | BIST
607D2 | PORTLAND | BISHOP STREET | 607T1 | 607D2 | 12.47 | BIST
607D4 | PORTLAND | BISHOP STREET | 607T1 | 607D4 | 12.47 | BIST
607D5 | PORTLAND | BISHOP STREET | 607T2 | 607D5 | 12.47 | BIST
610D1 | PORTLAND | BONNY EAGLE | 610T4 | 610D1 | 12.47 | BONE
610D2 | PORTLAND | BONNY EAGLE | 610T4 | 610D2 | 12.47 | BONE
611D1 | PORTLAND | BRIGHTON AVENUE | 611T1 | 611D1 | 12.47 | BRAV
611D2 | PORTLAND | BRIGHTON AVENUE | 611T1 | 611D2 | 12.47 | BRAV
611D3 | PORTLAND | BRIGHTON AVENUE | 611T1 | 611D3 | 12.47 | BRAV
612D1 | ALFRED | BUTLER'S CORNER | 612T1 | 612D1 | 12.47 | BUCO
612D2 | ALFRED | BUTLER'S CORNER | 612T1 | 612D2 | 12.47 | BUCO
613D1 | PORTLAND | CAPE ELIZABETH | 613T1 | 613D1 | 12.47 | CAEL
613D2 | PORTLAND | CAPE ELIZABETH | 613T1 | 613D2 | 12.47 | CAEL
613D3 | PORTLAND | CAPE ELIZABETH | 613T2 | 613D3 | 12.47 | CAEL
617D1 | PORTLAND | DUNSTAN | 617T1 | 617D1 | 12.47 | DUNS
617D2 | PORTLAND | DUNSTAN | 617T1 | 617D2 | 12.47 | DUNS
617D3 | PORTLAND | DUNSTAN | 617T1 | 617D3 | 12.47 | DUNS
617D4 | PORTLAND | DUNSTAN | 617T1 | 617D4 | 12.47 | DUNS
618D1 | PORTLAND | EAST DEERING | 618T1 | 618D1 | 12.47 | EDER
618D2 | PORTLAND | EAST DEERING | 618T2 | 618D2 | 12.47 | EDER
618D3 | PORTLAND | EAST DEERING | 618T2 | 618D3 | 12.47 | EDER
620D1 | PORTLAND | ELM STREET | 620T2 | 620D1 | 12.47 | ELM
620D2 | PORTLAND | ELM STREET | 620T3 | 620D2 | 12.47 | ELM
620D3 | PORTLAND | ELM STREET | 620T2 | 620D3 | 12.47 | ELM
620D4 | PORTLAND | ELM STREET | 620T2 | 620D4 | 12.47 | ELM
621D1 | ALFRED | FACTORY ISLAND | 621T2 | 621D1 | 12.47 | FAIS
621D2 | ALFRED | FACTORY ISLAND | 621T2 | 621D2 | 12.47 | FAIS
621D3 | ALFRED | FACTORY ISLAND | 621T3 | 621D3 | 12.47 | FAIS
621D4 | ALFRED | FACTORY ISLAND | 621T3 | 621D4 | 12.47 | FAIS
622D1 | PORTLAND | FALMOUTH | 622T1 | 622D1 | 12.47 | FALM
622D2 | PORTLAND | FALMOUTH | 622T1 | 622D2 | 12.47 | FALM
623D1 | PORTLAND | FOREST AVENUE | 623T1 | 623D1 | 12.47 | FOAV
623D2 | PORTLAND | FOREST AVENUE | 623T1 | 623D2 | 12.47 | FOAV
623D4 | PORTLAND | FOREST AVENUE | 623T1 | 623D4 | 12.47 | FOAV
623D5 | PORTLAND | FOREST AVENUE | 623T1 | 623D5 | 12.47 | FOAV
624D1 | PORTLAND | FORT HILL | 624T1 | 624D1 | 12.47 | FOHI
624D2 | PORTLAND | FORT HILL | 624T1 | 624D2 | 12.47 | FOHI
626D1 | ALFRED | HIGH STREET | 626T1 | 626D1 | 12.47 | HIST
626D5 | ALFRED | HIGH STREET | 626T2 | 626D5 | 12.47 | HIST
629D1 | ALFRED | KENNEBUNKPORT | 629T1 | 629D1 | 12.47 | KENN
629D2 | ALFRED | KENNEBUNKPORT | 629T1 | 629D2 | 12.47 | KENN
629D3 | ALFRED | KENNEBUNKPORT | 629T2 | 629D3 | 12.47 | GOOS
630D1 | ALFRED | GOOSEFARE | 630T1 | 630D1 | 12.47 | GOOS
630D2 | ALFRED | GOOSEFARE | 630T1 | 630D2 | 12.47 | GOOS
630D3 | ALFRED | GOOSEFARE | 630T1 | 630D3 | 12.47 | GOOS
630D4 | ALFRED | GOOSEFARE | 630T1 | 630D4 | 12.47 | LAST
631D1 | PORTLAND | LAMBERT STREET | 631T1 | 631D1 | 12.47 | LAST
631D2 | PORTLAND | LAMBERT STREET | 631T1 | 631D2 | 12.47 | LAST
631D3 | PORTLAND | LAMBERT STREET | 631T2 | 631D3 | 12.47 | LAST
632D1 | ALFRED | LIMERICK | 632T1 | 632D1 | 12.47 | LIME
632D2 | ALFRED | LIMERICK | 632T1 | 632D2 | 12.47 | LIME
633D1 | ALFRED | LOUDEN | 633T3 | 633D1 | 12.47 | LOUD
634D1 | ALFRED | MAY STREET | 634T1 | 634D1 | 12.47 | MAST
634D2 | ALFRED | MAY STREET | 634T2 | 634D2 | 12.47 | MAST
634D3 | ALFRED | MAY STREET | 634T2 | 634D3 | 12.47 | MAST
634D4 | ALFRED | MAY STREET | 634T1 | 634D4 | 12.47 | MAST
635D1 | PORTLAND | MOSHERS | 635T2 | 635D1 | 12.47 | MOSH
635D2 | PORTLAND | MOSHERS | 635T2 | 635D2 | 12.47 | MOSH
636D1 | PORTLAND | MUSSEY ROAD | 636T1 | 636D1 | 34.5 | MURD
636D2 | PORTLAND | MUSSEY ROAD | 636T1 | 636D2 | 34.5 | MURD
638D1 | ALFRED | NORTH LIMINGTON | 638T1 | 638D1 | 12.47 | NOLI
638D2 | ALFRED | NORTH LIMINGTON | 638T1 | 638D2 | 12.47 | NOLI
639D1 | PORTLAND | NORTH WINDHAM | 639T1 | 639D1 | 12.47 | NOWI
639D2 | PORTLAND | NORTH WINDHAM | 639T2 | 639D2 | 12.47 | NOWI
639D3 | PORTLAND | NORTH WINDHAM | 639T2 | 639D3 | 12.47 | NOWI
640D1 | ALFRED | OGUNQUIT | 640T2 | 640D1 | 12.47 | OGUN
640D2 | ALFRED | OGUNQUIT | 640T1 | 640D2 | 12.47 | OGUN
640D3 | ALFRED | OGUNQUIT | 640T1 | 640D3 | 12.47 | OGUN
641D1 | ALFRED | OLD ORCHARD BEACH | 641T1 | 641D1 | 12.47 | OOBE
641D2 | ALFRED | OLD ORCHARD BEACH | 641T1 | 641D2 | 12.47 | OOBE
641D3 | ALFRED | OLD ORCHARD BEACH | 641T2 | 641D3 | 12.47 | OOBE
641D4 | ALFRED | OLD ORCHARD BEACH | 641T2 | 641D4 | 12.47 | OOBE
644D1 | PORTLAND | PLEASANT HILL | 644T2 | 644D1 | 12.47 | PLHL
644D2 | PORTLAND | PLEASANT HILL | 644T2 | 644D2 | 12.47 | PLHL
644D3 | PORTLAND | PLEASANT HILL | 644T2 | 644D3 | 12.47 | PLHL
644D4 | PORTLAND | PLEASANT HILL | 644T3 | 644D4 | 12.47 | PLHL
645D1 | PORTLAND | UNION STREET | 645T1 | 645D1 | 12.47 | UNST
645D2 | PORTLAND | UNION STREET | 645T2 | 645D2 | 12.47 | UNST
645D3 | PORTLAND | UNION STREET | 645T2 | 645D3 | 12.47 | UNST
645D4 | PORTLAND | UNION STREET | 645T2 | 645D4 | 12.47 | UNST
645D7 | PORTLAND | UNION STREET | 645T1 | 645D7 | 12.47 | UNST
645D8 | PORTLAND | UNION STREET | 645T1 | 645D8 | 12.47 | UNST
645D9 | PORTLAND | UNION STREET | 645T1 | 645D9 | 12.47 | UNST
645N1 | PORTLAND | UNION STREET | 645T3 | 645N1 | 11.5 | UNST
645N2 | PORTLAND | UNION STREET | 645T4 | 645N2 | 11.5 | UNST
645N3 | PORTLAND | UNION STREET | 645T4 | 645N3 | 11.5 | UNST
645N4 | PORTLAND | UNION STREET | 645T3 | 645N4 | 11.5 | UNST
645N5 | PORTLAND | UNION STREET | 645T4 | 645N5 | 11.5 | UNST
645N6 | PORTLAND | UNION STREET | 645T4 | 645N6 | 11.5 | UNST
647D1 | PORTLAND | PRIDES CORNER | 647T2 | 647D1 | 12.47 | PRCO
647D2 | PORTLAND | PRIDES CORNER | 647T2 | 647D2 | 12.47 | PRCO
647D3 | PORTLAND | PRIDES CORNER | 647T2 | 647D3 | 12.47 | PRCO
650D1 | PORTLAND | RIGBY | 650T1 | 650D1 | 12.47 | RIGB
650D3 | PORTLAND | RIGBY | 650T2 | 650D3 | 12.47 | RIGB
650D4 | PORTLAND | RIGBY | 650T2 | 650D4 | 12.47 | RIGB
653D1 | PORTLAND | FORE RIVER | 653T1 | 653D1 | 12.47 | FORI
653D2 | PORTLAND | FORE RIVER | 653T2 | 653D2 | 12.47 | FORI
653D3 | PORTLAND | FORE RIVER | 653T1 | 653D3 | 12.47 | FORI
653D4 | PORTLAND | FORE RIVER | 653T2 | 653D4 | 12.47 | FORI
653D5 | PORTLAND | FORE RIVER | 653T1 | 653D5 | 12.47 | FORI
653D6 | PORTLAND | FORE RIVER | 653T2 | 653D6 | 12.47 | FORI
656D1 | ALFRED | SANFORD INDUSTRIAL PARK | 656T1 | 656D1 | 12.47 | SAIP
656D2 | ALFRED | SANFORD INDUSTRIAL PARK | 656T1 | 656D2 | 12.47 | SAIP
656D3 | ALFRED | SANFORD INDUSTRIAL PARK | 656T1 | 656D3 | 12.47 | SAIP
657D2 | ALFRED | SANFORD SWITCH | 657T1 | 657D2 | 12.47 | SASW
657D3 | ALFRED | SANFORD SWITCH | 657T1 | 657D3 | 12.47 | SASW
657D4 | ALFRED | SANFORD SWITCH | 657T1 | 657D4 | 12.47 | SASW
659D13 | PORTLAND | SEWALL STREET | 659T1 | 659D13 | 12.47 | SEST
659D4 | PORTLAND | SEWALL STREET | 659T2 | 659D4 | 12.47 | SEST
659D5 | PORTLAND | SEWALL STREET | 659T1 | 659D5 | 12.47 | SEST
659D6 | PORTLAND | SEWALL STREET | 659T2 | 659D6 | 12.47 | SEST
659D8 | PORTLAND | SEWALL STREET | 659T1 | 659D8 | 12.47 | SEST
659D9 | PORTLAND | SEWALL STREET | 659T2 | 659D9 | 12.47 | SEST
660D1 | PORTLAND | SHAWS MILL ROAD | 660T1 | 660D1 | 12.47 | SMRD
660D2 | PORTLAND | SHAWS MILL ROAD | 660T1 | 660D2 | 12.47 | SMRD
660D3 | PORTLAND | SHAWS MILL ROAD | 660T1 | 660D3 | 12.47 | SMRD
661D1 | ALFRED | PRATT & WHITNEY | 661T1 | 661D1 | 12.47 | PRAT
661D2 | ALFRED | PRATT & WHITNEY | 661T1 | 661D2 | 12.47 | PRAT
663D1 | ALFRED | SOUTH BERWICK | 663T1 | 663D1 | 12.47 | SOBE
663D2 | ALFRED | SOUTH BERWICK | 663T1 | 663D2 | 12.47 | SOBE
667D1 | ALFRED | SOUTH SANFORD | 667T2 | 667D1 | 12.47 | SOSA
667D2 | ALFRED | SOUTH SANFORD | 667T2 | 667D2 | 12.47 | SOSA
667D3 | ALFRED | SOUTH SANFORD | 667T1 | 667D3 | 12.47 | SOSA
668D1 | PORTLAND | SPRING STREET | 668T3 | 668D1 | 12.47 | SPST
668D2 | PORTLAND | SPRING STREET | 668T3 | 668D2 | 12.47 | SPST
668D3 | PORTLAND | SPRING STREET | 668T2 | 668D3 | 12.47 | SPST
668D4 | PORTLAND | SPRING STREET | 668T4 | 668D4 | 34.5 | SPST
668D5 | PORTLAND | SPRING STREET | 668T2 | 668D5 | 12.47 | SPST
668D6 | PORTLAND | SPRING STREET | 668T4 | 668D6 | 34.5 | SPST
671D1 | ALFRED | WATERBORO | 671T1 | 671D1 | 12.47 | WATE
671D2 | ALFRED | WATERBORO | 671T1 | 671D2 | 12.47 | WATE
673D1 | ALFRED | BIDDEFORD INDUSTRIAL PARK | 673T2 | 673D1 | 12.47 | BDIP
673D2 | ALFRED | BIDDEFORD INDUSTRIAL PARK | 673T2 | 673D2 | 12.47 | BDIP
673D3 | ALFRED | BIDDEFORD INDUSTRIAL PARK | 673T2 | 673D3 | 12.47 | BDIP
674D1 | PORTLAND | WESTBROOK | 674T1 | 674D1 | 12.47 | WSBR
674D2 | PORTLAND | WESTBROOK | 674T1 | 674D2 | 12.47 | WSBR
675D1 | PORTLAND | WESTERN AVENUE | 675T1 | 675D1 | 12.47 | WEAV
675D2 | PORTLAND | WESTERN AVENUE | 675T1 | 675D2 | 12.47 | WEAV
675D3 | PORTLAND | WESTERN AVENUE | 675T1 | 675D3 | 12.47 | WEAV
676D1 | ALFRED | YORK BEACH | 676T1 | 676D1 | 12.47 | YOBE
676D2 | ALFRED | YORK BEACH | 676T1 | 676D2 | 12.47 | YOBE
677D1 | ALFRED | YORK HARBOR | 677T1 | 677D1 | 12.47 | YOHA
677D2 | ALFRED | YORK HARBOR | 677T1 | 677D2 | 12.47 | YOHA
678D1 | PORTLAND | BAR MILLS | 678T4 | 678D1 | 12.47 | BRML
678D2 | PORTLAND | BAR MILLS | 678T4 | 678D2 | 12.47 | BRML
681D1 | ALFRED | BRANCH BROOK | 681T2 | 681D1 | 12.47 | BRBR
681D2 | ALFRED | BRANCH BROOK | 681T3 | 681D2 | 12.47 | BRBR
681D3 | ALFRED | BRANCH BROOK | 681T3 | 681D3 | 12.47 | BRBR
682D1 | PORTLAND | SWETT ROAD | 682T1 | 682D1 | 12.47 | SWRD
682D2 | PORTLAND | SWETT ROAD | 682T1 | 682D2 | 12.47 | SWRD
685D1 | ALFRED | BOLT HILL | 685T1 | 685D1 | 12.47 | BOLT
685D2 | ALFRED | BOLT HILL | 685T1 | 685D2 | 12.47 | BOLT
687D1 | ALFRED | ELIOT | 687T1 | 687D1 | 12.47 | ELIO
688D1 | ALFRED | KITTERY | 688T1 | 688D1 | 12.47 | KITT
688D2 | ALFRED | KITTERY | 688T1 | 688D2 | 12.47 | KITT
689D1 | ALFRED | BRAGDON COMMONS | 689T1 | 689D1 | 12.47 | BRCM
690D1 | PORTLAND | HINCKLEY POND | 690T1 | 690D1 | 12.47 | HIPO
690D2 | PORTLAND | HINCKLEY POND | 690T1 | 690D2 | 12.47 | HIPO
690D3 | PORTLAND | HINCKLEY POND | 690T1 | 690D3 | 12.47 | HIPO
691D1 | BRIDGTON | BALDWIN | 691T1 | 691D1 | 34.5 | BALD
692D1 | ALFRED | HIRAM TAP | 692T1 | 692D1 | 34.5 | HITP
693D1 | PORTLAND | SCARBOROUGH | 693T1 | 693D1 | 12.47 | SCAR
693D2 | PORTLAND | SCARBOROUGH | 693T1 | 693D2 | 12.47 | SCAR
695D1 | ALFRED | LEBANON | 695T1 | 695D1 | 12.47 | LEBA
695D2 | ALFRED | LEBANON | 695T1 | 695D2 | 12.47 | LEBA
696D1 | PORTLAND | RED BROOK | 696T1 | 696D1 | 34.5 | RED
696D2 | PORTLAND | RED BROOK | 696T1 | 696D2 | 34.5 | RED
696D3 | PORTLAND | RED BROOK | 696T1 | 696D3 | 34.5 | RED
698D1 | ALFRED | PERRIER | 698T1 | 698D1 | 12.47 | PERR
698D2 | ALFRED | PERRIER | 698T2 | 698D2 | 12.47 | PERR
698D3 | ALFRED | PERRIER | 698T2 | 698D3 | 12.47 | PERR
800D1 | ROCKLAND | LINCOLNVILLE | 800T1 | 800D1 | 34.5 | LINC
801D1 | SKOWHEGAN | ANSON | 801T1 | 801D1 | 12.47 | ANSO
803D3 | ROCKLAND | BELFAST WEST SIDE | 803T2 | 803D3 | 12.47 | BEWE
803D4 | ROCKLAND | BELFAST WEST SIDE | 803T1 | 803D4 | 12.47 | BEWE
803D5 | ROCKLAND | BELFAST WEST SIDE | 803T1 | 803D5 | 12.47 | BEWE
803D6 | ROCKLAND | BELFAST WEST SIDE | 34.5 kV Bus | 803D6 | 12.47 | BEWE
805D1 | ROCKLAND | BROOKS | 805T1 | 805D1 | 12.47 | BROO
806D1 | ROCKLAND | BUCKSPORT | 806T5 | 806D1 | 12.47 | BUCK
806D2 | ROCKLAND | BUCKSPORT | 806T3 | 806D2 | 34.5 | BUCK
807D1 | FAIRFIELD | BURNHAM | 807T1 | 807D1 | 12.47 | BURN
808D1 | DOVER | CARMEL | 808T1 | 808D1 | 12.47 | CARM
808D2 | DOVER | CARMEL | 808T1 | 808D2 | 12.47 | CARM
808D3 | DOVER | CARMEL TAP | 808T1 | 808D3 | 12.47 | CART
810D1 | FAIRFIELD | CLINTON | 810T1 | 810D1 | 12.47 | CLIN
811D1 | DOVER | CORINNA | 811T1 | 811D1 | 12.47 | CORI
812D1 | FAIRFIELD | DETROIT | 812T2 | 812D1 | 12.47 | DETR
812D2 | FAIRFIELD | DETROIT | 812T2 | 812D2 | 12.47 | DETR
813D1 | DOVER | DEXTER | 813T1 | 813D1 | 12.47 | DEXT
813D3 | DOVER | DEXTER | 813T2 | 813D3 | 12.47 | DEXT
815D1 | DOVER | DOVER | 815T1 | 815D1 | 12.47 | DOVE
815D2 | DOVER | DOVER | 815T2 | 815D2 | 12.47 | DOVE
816D1 | FARMINGTON | EAST WILTON | 816T1 | 816D1 | 12.47 | DOVE
816D2 | FARMINGTON | EAST WILTON | 816T1 | 816D2 | 12.47 | DOVE
816D3 | FARMINGTON | EAST WILTON | 816T1 | 816D3 | 12.47 | EWIL
817D1 | FAIRFIELD | FAIRFIELD | 817T1 | 817D1 | 12.47 | FAIR
817D2 | FAIRFIELD | FAIRFIELD | 817T2 | 817D2 | 12.47 | FAIR
817D3 | FAIRFIELD | FAIRFIELD | 817T1 | 817D3 | 12.47 | FAIR
818D1 | FARMINGTON | FARMINGTON FALLS | 818T1 | 818D1 | 12.47 | FAFA
818D2 | FARMINGTON | FARMINGTON FALLS | 818T1 | 818D2 | 12.47 | FAFA
820D1 | DOVER | GREENVILLE | 820T1 | 820D1 | 12.47 | GREE
821D1 | DOVER | GUILFORD | 821T1 | 821D1 | 12.47 | GUIL
821D2 | DOVER | GUILFORD | 821T1 | 821D2 | 12.47 | GUIL
821D3 | DOVER | GUILFORD | 821T2 | 821D3 | 34 | GUIL
823D2 | SKOWHEGAN | HARRIS | 823T5 | 823D2 | 12.47 | HARR
824D1 | SKOWHEGAN | HARTLAND | 824T1 | 824D1 | 12.47 | HART
824D2 | SKOWHEGAN | HARTLAND | 824T1 | 824D2 | 12.47 | HART
824D3 | SKOWHEGAN | HARTLAND | 824T1 | 824D3 | 12.47 | HART
825D1 | SKOWHEGAN | JACKMAN | 825T1 | 825D1 | 12.47 | JACK
827D1 | SKOWHEGAN | ATHENS | 827T1 | 827D1 | 12.47 | ATHN
827D2 | SKOWHEGAN | ATHENS | 827T1 | 827D2 | 12.47 | ATHN
827D3 | SKOWHEGAN | ATHENS | 827T1 | 827D3 | 12.47 | ATHN
834D1 | DOVER | MONSON | 834T1 | 834D1 | 12.47 | MONS
834D2 | DOVER | MONSON | 34kV Bus 1 | 834D2 | 34 | MONS
835D1 | FARMINGTON | NEW PORTLAND | 835T1 | 835D1 | 12.47 | NWPO
836D1 | FARMINGTON | NEW VINEYARD | 836T1 | 836D1 | 12.47 | NWVI
837D1 | DOVER | NEWPORT | 837T1 | 837D1 | 12.47 | NEWP
837D2 | DOVER | NEWPORT | 837T2 | 837D2 | 12.47 | NEWP
838D1 | SKOWHEGAN | NORTH ANSON | 838T1 | 838D1 | 4 | NOAN
838D2 | SKOWHEGAN | NORTH ANSON | 838T1 | 838D2 | 4 | NOAN
839D1 | FAIRFIELD | OAKLAND | 839T1 | 839D1 | 12.47 | OAKL |  |  | cn
839D2 | FAIRFIELD | OAKLAND | 839T1 | 839D2 | 12.47 | OAKL
841D1 | FARMINGTON | PHILLIPS/STRONG | 841T1 | 841D1 | 12.47 | PHST
842D1 | FAIRFIELD | PITTSFIELD | 842T1 | 842D1 | 12.47 | PITT
846D1 | ROCKLAND | PROSPECT | 846T1 | 846D1 | 12.47 | PROS
850D1 | ROCKLAND | SEARSPORT | 850T1 | 850D1 | 12.47 | SEAR
850D2 | ROCKLAND | SEARSPORT | 850T1 | 850D2 | 12.47 | SEAR
852D1 | FAIRFIELD | SHAWMUT | 852T3 | 852D1 | 12.47 | SHAW
853D1 | SKOWHEGAN | SKOWHEGAN NORTH SIDE | 853T1 | 853D1 | 12.47 | SKNS
853D2 | SKOWHEGAN | SKOWHEGAN NORTH SIDE | 853T1 | 853D2 | 12.47 | SKNS
854D1 | SKOWHEGAN | SKOWHEGAN SOUTH SIDE | 854T1 | 854D1 | 12.47 | SKSS
854D2 | SKOWHEGAN | SKOWHEGAN SOUTH SIDE | 854T1 | 854D2 | 12.47 | SKSS
855D1 | FAIRFIELD | SOUTH WATERVILLE | 855T1 | 855D1 | 12.47 | SOWA
855D2 | FAIRFIELD | SOUTH WATERVILLE | 855T1 | 855D2 | 12.47 | SOWA
857D1 | ROCKLAND | THORNDIKE TAP | 857T1 | 857D1 | 34.5 | THTP
858D1A | FARMINGTON | STURTEVANT | 858T1 | 858D1A | 34.5 | STUR
858D1B | FARMINGTON | STURTEVANT | 858T2 | 858D1B | 34.5 | STUR
858D2 | FARMINGTON | STURTEVANT | 858T1 | 858D2 | 34.5 | STUR
858D3 | FARMINGTON | STURTEVANT | 858T2 | 858D3 | 12.47 | STUR
858D4 | FARMINGTON | STURTEVANT | 858T2 | 858D4 | 12.47 | STUR
860D1 | FAIRFIELD | UNITY | 860T1 | 860D1 | 12.47 | UNIT
860D2 | FAIRFIELD | UNITY | 860T1 | 860D2 | 12.47 | UNIT
861D8 | FAIRFIELD | VASSALBORO | 861T1 | 861D8 | 12.47 | VASS
861D9 | FAIRFIELD | VASSALBORO | 861T1 | 861D9 | 12.47 | VASS
864D1 | SKOWHEGAN | SKOWHEGAN TAP | 864T1 | 864D1 | 12.47 | SKTP
865D1 | FAIRFIELD | WEST WATERVILLE | 865T1 | 865D1 | 12.47 | WEWA
865D2 | FAIRFIELD | WEST WATERVILLE | 865T2 | 865D2 | 12.47 | WEWA
865D5 | FAIRFIELD | WEST WATERVILLE | 865T2 | 865D5 | 12.47 | WEWA
866D1 | SKOWHEGAN | WESTON HYDRO | 866T2 | 866D1 | 12.47 | WSTN
866D2 | SKOWHEGAN | WESTON HYDRO | 866T2 | 866D2 | 12.47 | WSTN
868D1 | SKOWHEGAN | EMDEN | 868T1 | 868D1 | 12.47 | EMDE
870D1 | FAIRFIELD | WINSLOW | 870T4 | 870D1 | 12.47 | WINS
870D2 | FAIRFIELD | WINSLOW | 870T4 | 870D2 | 12.47 | WINS
872D1 | SKOWHEGAN | WYMAN HYDRO | 872T11 | 872D1 | 12.47 | WYHY
873D1 | FAIRFIELD | COUNTY ROAD | 873T1 | 873D1 | 34.5 | RRPS
873D2 | FAIRFIELD | COUNTY ROAD | 873T2 | 873D2 | 12.47 | RRPS
874D1 | ROCKLAND | BELFAST 115 | 874T2 | 874D1 | 12.47 | RRPS
875D1 | FARMINGTON | RANGELEY | 34KV BUS 1 | 875D1 | 34.5 | B115
875D2 | FARMINGTON | RANGELEY | 875T1 | 875D2 | 12.47 | RANG
875D3 | FARMINGTON | RANGELEY | 875T1 | 875D3 | 12.47 | RANG
876D1 | FARMINGTON | SADDLEBACK | Tap off of Transmission Line | 876D1 | 34.5 | SADD
877D1 | FARMINGTON | STRATTON | 877T1 | 877D1 | 12.47 | STRA
881D1 | FARMINGTON | COPLIN TAP | 881T1 | 881D1 | 7.2 | COTP
882D1 | FARMINGTON | BIGELOW | 882T1 | 882D1 | 34.5 | BIGE
882D2 | FARMINGTON | BIGELOW | 882T1 | 882D2 | 34.5 | BIGE
883D1 | FARMINGTON | DALLAS TAP | 883T1 | 883D1 | 7.2 | DATP
885D1 | FARMINGTON | WILTON | 885T1 | 885D1 | 12.47 | WILT

## Withdrawn Public Queue
PRJ | Type of Gen | kW AC | Withdrawn Date
12 | Battery | 4999 | 2019-12-12
13 | Battery | 14000 | 2023-07-07
15 | Battery | 10000 | 2024-04-25
16 | Solar | 4045 | 2019-11-19
26 | Solar/Battery | 4700 | 2020-08-14
27 | Solar | 4999 | 2019-09-29
28 | Solar | 4999 | 2025-11-04
29 | Solar | 4990 | 2025-11-04
30 | Solar | 4600 | 2025-07-15
35 | Solar/Battery | 5000 | 2020-04-03
36 | Solar/Battery | 5000 | 2020-01-20
38 | Solar/Battery | 4700 | 2020-04-09
39 | Solar/Battery | 4700 | 2020-04-09
41 | Solar/Battery | 4400 | 2019-09-16
42 | Solar/Battery | 4950 | 2019-09-16
47 | Solar | 4990 | 2022-11-07
52 | Solar/Battery | 2750 | 2019-11-17
54 | Solar/Battery | 4995 | 2023-10-24
55 | Solar/Battery | 2000 | 2023-11-29
56 | Solar/Battery | 2000 | 2024-01-02
58 | Solar/Battery | 4990 | 2024-01-09
59 | Solar | 4950 | 2023-07-14
60 | Solar/Battery | 4400 | 2020-04-09
65 | Solar/Battery | 4990 | 2023-03-10
67 | Solar | 2490 | 2024-09-18
69 | Solar/Battery | 4990 | 2022-03-07
71 | Solar | 4950 | 2020-07-01
72 | Solar | 4950 | 2021-08-03
73 | Solar | 2480 | 2020-08-19
74 | Solar | 4990 | 2025-05-14
75 | Solar | 2475 | 2020-05-21
76 | Solar | 4875 | 2024-08-09
78 | Solar/Battery | 2000 | 2020-02-13
83 | Solar | 1990 | 2020-06-09
85 | Solar | 3300 | 2020-07-29
86 | Solar | 4950 | 2023-10-09
88 | Solar/Battery | 4990 | 2025-04-15
90 | Solar | 2250 | 2023-07-25
91 | Solar | 2000 | 2021-07-20
93 | Solar | 4980 | 2021-04-29
96 | Solar | 1350 | 2024-09-30
99/100 | Solar | 3500 | 2024-10-18
103 | Solar | 4990 | 2020-01-10
104 | Solar |  | 2020-01-13
105 | Solar | 4990 | 2019-10-19
109 | Solar | 4990 | 2020-01-09
111 | Solar | 4990 | 2020-04-13
112 | Solar | 4990 | 2020-05-05
113 | Solar | 4990 | 2020-04-06
115 | Solar |  | 2019-10-24
117 | Solar | 14000 | 2024-12-16
120 | Solar | 4980 | 2021-04-27
121 | Solar/Battery | 3800 | 2020-05-20
126 | Solar |  | 2020-04-29
127 | Solar | 4990 | 2020-04-14
128 | Solar | 4990 | 2020-01-09
129 | Solar | 4800 | 2024-02-26
130 | Solar | 4950 | 2023-06-16
131 | Solar | 4950 | 2024-06-14
132 | Solar | 2475 | 2020-12-15
134 | Solar | 4990 | 2020-07-27
136&137 | Solar | 4999 | 2024-08-12
138 | Solar | 2300 | 2024-10-09
139 | Solar | 4990 | 2020-01-12
143 | Solar | 4990 | 2020-02-18
145 | Solar/Battery | 4990 | 2020-05-06
147 | Solar/Battery | 4875 | 2020-01-04
149 | Solar | 4200 | 2023-10-09
154 | Solar | 4999 | 2021-02-26
155 | Solar/Battery | 4990 | 2020-01-13
156 | Solar | 4875 | 2020-12-10
157 | Solar | 5000 | 2020-07-07
158 | Solar | 4990 | 2025-02-04
159 | Solar/Battery | 4999 | 2020-07-28
160 | Solar/Battery | 2822 | 2023-07-17
162 | Solar/Battery | 3190 | 2020-07-29
164 | Solar | 4990 | 2020-04-14
165 | Solar | 4125 | 2021-12-08
166 | Solar | 2000 | 2020-12-10
167 | Solar | 2000 | 2020-09-21
169 | Solar | 4875 | 2023-03-09
171 | Solar | 4950 | 2020-02-10
173 | Solar/Battery |  | 2020-07-09
177 | Solar | 1990 | 2023-10-27
178 | Solar | 3300 | 2020-09-15
179 | Solar | 4950 | 2020-01-12
182 | Solar | 4980 | 2020-02-03
187 | Solar | 3600 | 2020-01-21
188 | Solar | 1990 | 2023-08-24
190 | Solar | 4950 | 2024-09-18
192 | Solar | 3150 | 2020-03-05
193 | Solar/Battery | 4990 | 2020-02-17
194 | Solar | 1500 | 2019-11-19
195 | Solar | 4500 | 2020-05-28
196 | Solar | 2500 | 2020-02-03
197 | Solar |  | 2020-02-03
198 | Solar | 3125 | 2024-10-18
199 | Solar | 4200 | 2020-01-12
202 | Solar/Battery | 4990 | 2025-12-18
204 | Solar | 5000 | 2021-07-09
208 | Solar | 4990 | 2020-01-10
210 | Solar | 4990 | 2020-01-10
211 | Solar | 4990 | 2020-01-10
212 | Solar | 4980 | 2020-02-26
215 | Solar | 4990 | 2020-01-10
216 | Solar | 4990 | 2020-04-14
220 | Solar | 3060 | 2020-02-03
222 | Solar/Battery | 2490 | 2022-04-19
223 | Solar/Battery | 4999 | 2020-11-20
224 | Solar/Battery | 4999 | 2020-04-23
225 | Solar | 4950 | 2024-10-21
226 | Solar | 1962 | 2025-07-15
228 | Solar | 4950 | 2020-01-20
230 | Solar | 3750 | 2021-09-15
231 | Solar | 4990 | 2021-01-19
232 | Solar | 4990 | 2019-11-21
233 | Solar/Battery | 3100 | 2022-10-20
234 | Solar/Battery | 4990 | 2022-10-20
237 | Solar/Battery | 2340 | 2023-03-09
238 | Solar/Battery | 4975 | 2020-01-16
239 | Solar | 4875 | 2020-04-23
240 | Solar/Battery | 4000 | 2023-02-22
241&242 | Solar | 4990 | 2023-12-04
243 | Solar/Battery | 4990 | 2023-12-04
244 | Solar/Battery | 4000 | 2020-01-12
246 | Solar | 1999 | 2025-08-07
248 | Solar | 3375 | 2020-01-29
249 | Solar | 1999 | 2023-12-20
250 | Solar | 4814 | 2020-01-24
251 | Solar | 2000 | 2022-02-11
253 | Solar | 4999 | 2024-05-14
255 | Solar | 1625 | 2023-10-03
257 | Solar/Battery | 2000 | 2021-01-05
259 | Solar | 5000 | 2020-04-14
260 | Solar | 4200 | 2024-07-01
261 | Solar | 2500 | 2020-07-01
262 | Solar | 4200 | 2025-07-15
262 | Solar | 4200 | 2025-07-13
263 | Solar | 3250 | 2022-01-31
266 | Solar/Battery | 4990 | 2021-07-07
267 | Solar | 5000 | 2022-03-10
269 | Solar/Battery | 3900 | 2023-02-18
272 | Solar | 4250 | 2026-05-04
273 | Solar | 4900 | 2020-04-14
274 | Solar | 3700 | 2022-06-01
276 | Solar | 2700 | 2020-01-28
277 | Solar | 4950 | 2020-07-29
278 | Solar | 2475 | 2020-01-12
279 | Solar | 4950 | 2021-06-29
280 | Solar | 4950 | 2020-01-12
283 | Solar | 4950 | 2020-08-24
284 | Solar/Battery | 4975 | 2022-06-06
285 | Solar/Battery | 3500 | 2023-03-09
286 | Solar/Battery | 4990 | 2023-12-04
288 | Solar | 2500 | 2021-11-10
289 | Solar | 1625 | 2022-03-07
291 | Solar | 4950 | 2022-06-01
292 | Solar | 4950 | 2020-10-27
293 | Solar | 4990 | 2020-04-27
294 | Solar/Battery | 4990 | 2020-02-03
295 | Solar/Battery | 3875 | 2023-02-02
296 | Solar | 4999 | 2020-09-04
299 | Solar | 4975 | 2024-02-28
300 | Solar | 4975 | 2020-06-11
302 | Solar | 4999 | 2020-05-27
303 | Solar | 1999 | 2023-08-14
304 | Solar | 999.6 | 2024-12-13
306 | Solar | 2000 | 2024-12-19
307 | Solar | 4000 | 2021-07-30
309 | Solar | 5000 | 2021-09-29
310 | Solar | 2000 | 2024-01-22
312 | Solar | 3500 | 2025-01-15
313 | Solar | 4500 | 2021-02-17
314 | Solar | 4999 | 2020-09-18
315 | Solar/Battery | 3500 | 2021-03-12
317 | Solar | 875 | 2021-08-26
318 | Solar | 999 | 2025-11-11
319 | Solar | 4482 | 2024-02-22
320 | Solar | 4990 | 2020-04-14
322 | Solar | 2750 | 2022-08-25
323 | Solar | 5000 | 2020-12-02
324 | Solar | 2550 | 2020-09-23
325 | Solar | 1992 | 2024-05-13
326 | Solar | 2450 | 2024-09-30
327 | Solar | 4998 | 2020-03-03
329 | Solar | 1990 | 2023-09-26
331 | Solar | 2500 | 2020-09-29
334 | Solar | 4990 | 2023-01-06
335 | Solar/Battery | 3500 | 2022-08-25
336 | Solar | 2500 | 2020-04-14
337 | Solar | 2500 | 2020-06-23
339 | Solar | 2000 | 2024-12-09
340 | Solar | 4999 | 2020-07-28
345 | Solar/Battery | 4990 | 2022-08-11
346 | Solar/Battery | 1990 | 2023-01-18
347 | Solar | 4200 | 2020-05-27
348 | Solar | 4999 | 2020-07-29
351 | Solar | 4950 | 2024-11-06
352 | Solar | 4950 | 2024-08-20
354 | Solar | 1650 | 2020-07-10
356 | Solar | 4950 | 2022-01-06
357 | Solar/Battery | 4999 | 2020-04-28
359 | Solar | 4728 | 2024-12-03
361 | Solar/Battery | 4999 | 2022-08-16
362 | Solar | 4950 | 2021-07-12
363 | Solar | 1992 | 2023-11-28
364 | Solar | 4875 | 2021-09-22
367 | Solar | 4950 | 2020-07-16
369 | Solar | 4999 | 2021-08-26
370 | Solar | 1999 | 2024-05-10
371 | Solar | 4999 | 2023-01-18
373 | Solar | 3000 | 2024-05-10
374 | Solar | 4999 | 2023-10-13
375 | Solar | 2625 | 2024-09-06
378 | Solar | 1740 | 2021-03-12
379 | Solar/Battery | 4975 | 2020-07-10
381 | Solar | 1992 | 2023-10-20
382 | Solar/Battery | 2000 | 2023-08-02
383 | Solar | 4990 | 2020-05-06
384 | Solar | 3652 | 2021-07-16
389 | Solar | 990 | 2025-01-08
393 | Solar | 999 | 2024-04-17
394 | Solar | 1000 | 2022-10-25
395 | Solar | 2000 | 2021-06-29
396 | Solar | 3500 | 2022-12-13
397 | Solar | 2000 | 2023-09-05
398 | Solar | 999 | 2024-08-15
399 | Solar | 2000 | 2023-10-16
402 | Solar | 4990 | 2024-03-06
403 | Solar | 4850 | 2024-07-29
404 | Solar | 996 | 2025-09-22
405 | Solar | 4875 | 2021-01-20
406 | Solar | 4000 | 2022-03-07
407 | Solar | 4999 | 2025-10-24
410 | Solar | 875 | 2023-04-06
412 | Solar | 1950 | 2024-12-18
417 | Solar | 3750 | 2021-02-18
418 | Solar | 4995 | 2025-05-28
419 | Solar | 4975 | 2021-02-26
420 | Solar | 4975 | 2021-02-26
421 | Solar | 4975 | 2021-02-26
422 | Solar | 4975 | 2021-02-26
423 | Solar | 4975 | 2021-02-26
424 | Solar | 4975 | 2021-02-26
425 | Solar | 4975 | 2021-02-26
426 | Solar | 4975 | 2021-02-26
427 | Solar | 4999 | 2022-01-19
428 | Solar | 1800 | 2020-04-27
430 | Solar | 2500 | 2021-07-12
431 | Solar | 4950 | 2021-02-23
432 | Solar | 2000 | 2022-09-28
433 | Solar | 4000 | 2022-01-24
434 | Solar | 2000 | 2024-12-16
435 | Solar | 3000 | 2021-08-19
438 | Solar | 4999 | 2025-02-14
439 | Solar | 2250 | 2021-09-30
440 | Solar | 2400 | 2024-05-08
441 | Solar | 2250 | 2024-04-05
442 | Solar | 2250 | 2024-04-05
443 | Solar | 4998 | 2022-02-01
444 | Solar | 4999 | 2023-06-02
446 | Solar | 4980 | 2020-06-08
447 | Solar | 4950 | 2020-09-27
449 | Solar | 4990 | 2023-10-19
450 | Solar/Battery | 4999 | 2023-02-14
452 | Solar | 4950 | 2021-01-19
455 | Solar | 4990 | 2020-08-24
456 | Solar | 1990 | 2020-12-01
457 | Solar | 4950 | 2023-08-03
458 | Solar | 2375 | 2020-06-29
460 | Solar | 995 | 2025-01-06
461 | Solar | 4999 | 2024-10-30
462 | Solar | 1990 | 2024-04-22
463 | Solar/Battery | 999 | 2024-10-14
464 | Solar | 4990 | 2023-10-19
465 | Solar | 4950 | 2021-05-26
466 | Solar | 4875 | 2020-11-08
467 | Solar | 1998 | 2024-05-14
468 | Solar | 2750 | 2021-05-03
469 | Solar | 4875 | 2023-03-28
470 | Solar | 1992 | 2025-01-21
471 | Solar | 1998 | 2024-10-09
472 | Solar | 1990 | 2024-10-24
473 | Solar | 4980 | 2025-10-08
480 | Solar | 2999 | 2021-01-12
481 | Solar | 999.6 | 2025-10-28
482 | Solar | 2000 | 2023-09-06
483 | Solar | 4980 | 2022-10-07
484 | Solar | 4999 | 2023-12-15
486 | Solar | 1500 | 2020-10-19
488 | Solar | 2125 | 2021-11-01
489 | Solar | 600 | 2021-09-21
490 | Solar | 4975 | 2020-07-08
492 | Solar | 2500 | 2024-10-09
494 | Solar | 3500 | 2020-04-27
495 | Solar | 1999 | 2025-04-04
496 | Solar | 1999 | 2025-04-04
497 | Solar | 4950 | 2024-04-17
498 | Solar | 1999 | 2024-10-04
499 | Solar | 4999 | 2025-02-04
500 | Solar | 4980 | 2022-12-07
501 | Solar | 4980 | 2020-04-10
502 | Solar | 4500 | 2024-04-05
503 | Solar | 4000 | 2024-03-19
504 | Solar | 1000 | 2024-01-30
505 | Solar | 4990 | 2024-02-26
507 | Solar | 4999 | 2020-07-13
508 | Solar | 4990 | 2020-11-18
509 | Solar | 4000 | 2024-07-19
510 | Solar/Battery | 4950 | 2023-05-08
512 | Solar | 1999 | 2024-01-09
513 | Solar | 4950 | 2022-03-23
514 | Solar/Battery | 2000 | 2023-01-13
515 | Solar/Battery | 2000 | 2023-06-26
516 | Solar | 1999 | 2023-06-30
517 | Solar/Battery | 4990 | 2020-08-30
520 | Solar | 4000 | 2021-08-26
521 | Solar/Battery | 4999 | 2021-06-24
522 | Solar | 4998 | 2021-12-21
525 | Battery | 5000 | 2025-01-06
526 | Solar | 2000 | 2024-03-05
527 | Solar | 1999 | 2022-02-14
528 | Solar | 3300 | 2023-10-09
529 | Solar | 4998 | 2024-03-27
530 | Solar | 4998 | 2023-01-24
531 | Solar | 1375 | 2023-03-03
532 | Solar | 2275 | 2020-12-03
533 | Solar | 4950 | 2021-08-03
534 | Solar | 999 | 2023-02-24
535 | Solar | 4500 | 2024-09-16
536 | Solar | 4999 | 2024-01-19
537 | Solar | 3300 | 2021-08-03
538 | Solar | 1620 | 2022-06-30
539 | Solar | 1999 | 2024-08-15
541 | Solar | 4990 | 2022-12-09
542 | Solar | 4000 | 2021-06-30
543 | Solar | 4990 | 2021-05-05
544 | Solar | 4950 | 2020-12-03
545 | Solar | 840 | 2024-03-11
546 | Solar | 4950 | 2023-06-14
547 | Solar | 4950 | 2024-05-13
548 | Solar | 2750 | 2022-07-20
549 | Solar | 988 | 2021-05-05
550 | Solar | 1999 | 2023-01-09
551 | Solar | 1990 | 2024-05-01
552 | Solar | 3500 | 2022-04-05
553 | Solar | 4000 | 2022-06-01
554 | Solar | 4973 | 2025-09-30
556 | Solar | 1990 | 2024-02-02
554 | Solar | 4998 | 2025-09-30
556 | Solar | 1990 | 2024-02-02
557 | Solar | 4750 | 2023-03-09
558 | Solar | 1875 | 2023-04-10
559 | Solar | 4990 | 2020-12-08
560 | Solar | 4990 | 2025-11-25
562 | Solar/Battery | 1999 | 2024-10-31
563 | Solar | 4990 | 2020-12-11
564 | Solar/Battery | 1990 | 2023-12-04
565 | Solar | 1995 | 2024-01-23
567 | Solar | 1995 | 2024-02-13
568 | Solar | 1999 | 2022-10-20
569 | Solar | 4998 | 2020-02-23
570 | Solar | 1999 | 2024-01-09
571 | Solar | 4107 | 2022-01-20
572 | Solar | 990 | 2023-12-06
573 | Solar | 999 | 2024-08-15
574 | Hydro | 425 | 2023-12-12
575 | Solar | 1950 | 2022-02-18
576 | Solar | 3625 | 2021-07-28
577 | Solar/Battery | 4990 | 2025-07-01
578 | Solar | 1990 | 2024-02-02
579 | Solar/Battery | 4990 | 2023-02-02
580 | Solar | 4000 | 2021-07-26
581 | Solar | 4000 | 2021-10-29
582 | Solar | 2000 | 2021-08-12
583 | Solar | 3500 | 2024-01-03
584 | Solar | 4999 | 2021-09-09
585 | Solar | 4000 | 2021-05-17
586 | Solar | 1999 | 2025-01-17
587 | Solar | 4998 | 2025-11-25
588 | Solar | 1999 | 2025-11-21
589 | Solar | 4814 | 2025-11-21
590 | Solar/Battery | 990 | 2023-10-17
591 | Solar | 1995 | 2024-02-27
592 | Solar/DC BESS | 1990 | 2022-06-30
593 | Solar | 4814 | 2020-02-08
594 | Solar | 4000 | 2025-08-07
595 | Solar | 4990 | 2021-01-07
596 | Solar | 975 | 2025-05-14
597 | Solar | 1999 | 2023-11-14
598 | Solar | 4998 | 2023-02-20
600 | Solar | 1250 | 2024-09-04
601 | Solar | 1999 | 2022-08-16
602 | Solar | 1999 | 2022-08-25
604 | Solar | 1500 | 2022-08-12
605 | Solar | 1750 | 2024-02-22
606 | Solar | 1975 | 2023-12-19
607 | Solar | 1975 | 2024-01-22
609 | Solar | 1999 | 2021-12-21
610 | Solar | 2520 | 2021-06-24
611 | Solar | 4990 | 2024-08-28
612 | Solar | 4990 | 2024-10-15
613 | Solar | 1999 | 2023-11-01
614 | Solar/DC BESS | 1990 | 2023-08-03
615 | Solar/DC BESS | 4990 | 2021-01-28
616 | Solar/DC BESS | 4990 | 2021-02-09
617 | Solar | 1998 | 2024-10-09
618 | Solar | 4380 | 2021-11-18
619 | Solar | 1995 | 2024-10-31
621 | Solar | 1950 | 2023-10-10
622 | Solar | 1992 | 2023-09-20
623 | Solar | 3750 | 2022-08-04
624 | Solar | 1960 | 2024-09-04
625 | Solar | 4990 | 2023-09-22
627 | Solar | 2720 | 2025-01-30
628 | Solar | 4980 | 2024-10-29
629 | Solar/Battery | 1990 | 2023-04-20
630 | Solar | 1975 | 2024-07-26
632 | Solar | 4990 | 2023-08-18
633 | Solar | 1995 | 2024-09-04
634 | Solar | 4990 | 2021-02-05
635 | Solar | 999 | 2024-02-22
636 | Solar | 1999 | 2023-09-28
638 | Solar | 999 | 2024-07-31
639 | Solar | 1990 | 2022-08-31
640 | Solar | 1990 | 2025-11-06
641 | Solar | 1999 | 2023-01-10
642 | Solar | 1975 | 2024-04-08
643 | Solar | 975 | 2025-02-19
644 | Solar | 999 | 2025-03-24
645 | Solar | 4990 | 2022-01-19
646 | Solar | 1990 | 2024-02-02
647 | Solar | 5000 | 2024-04-05
648 | Solar | 975 | 2024-09-05
649 | Solar | 1990 | 2024-11-12
650 | Solar | 3450 | 2021-10-15
651 | Solar | 1500 | 2022-03-01
654 | Solar | 4500 | 2022-01-04
655 | Solar/Battery | 1990 | 2023-06-12
656 | Solar | 1990 | 2024-08-24
658 | Solar | 999 | 2025-09-09
659 | Solar/Battery | 4990 | 2021-11-15
660 | Solar | 4950 | 2023-10-10
661 | Solar | 4999 | 2024-11-14
662 | Solar | 2500 | 2025-03-10
663 | Solar | 5000 | 2023-10-19
664 | Solar | 2500 | 2022-08-30
665 | Solar | 4980 | 2023-06-01
666 | Hydro | 3900 | 2021-05-12
667 | Hydro | 4200 | 2021-05-12
668 | Solar | 1922 | 2023-09-13
670 | Solar | 4850 | 2025-03-10
671 | Solar | 1950 | 2023-07-18
672 | Solar | 2500 | 2024-08-05
675 | Solar | 1750 | 2022-06-28
676 | Solar | 999 | 2025-04-25
677 | Solar | 999 | 2023-03-22
678 | Solar | 1875 | 2023-12-11
679 | Solar | 1999 | 2022-11-14
680 | Solar | 2625 | 2022-09-13
681 | Solar | 3375 | 2022-03-09
682 | Solar | 1990 | 2022-01-12
683 | Solar | 4990 | 2021-12-03
684 | Solar | 1950 | 2024-07-19
685 | Solar | 1950 | 2024-03-14
686 | Solar | 4000 | 2023-09-19
687 | Solar | 1950 | 2023-12-28
688 | Solar | 990 | 2023-07-20
689 | Solar | 1999 | 2024-06-11
690 | Solar | 1999 | 2023-03-28
691 | Solar | 975 | 2023-10-03
692 | Solar | 1975 | 2024-09-05
693 | Solar | 1200 | 2022-11-15
694 | Solar/DC BESS | 1990 | 2024-11-06
695 | Solar | 1440 | 2023-05-12
696 | Solar | 3500 | 2022-09-07
697 | Solar | 1950 | 2023-06-29
699 | Solar | 1999 | 2026-01-02
700 | Solar | 1999 | 2023-11-14
701 | Solar | 4900 | 2025-07-15
702 | Solar | 4980 | 2025-11-26
703 | Solar | 600 | 2023-06-21
704 | Solar | 1950 | 2023-10-09
705 | Solar | 1999 | 2022-06-14
707 | Solar | 999 | 2026-06-03
708 | Solar | 1650 | 2023-08-14
709 | Solar | 1950 | 2022-09-19
710 | Solar/Battery | 996 | 2023-01-06
711 | Solar | 1950 | 2024-09-10
713 | Solar | 975 | 2022-05-17
714 | Solar | 975 | 2022-06-07
716 | Solar | 1750 | 2024-11-26
717 | Solar | 990 | 2023-10-26
719 | Solar | 500 | 2022-11-15
720 | Solar | 1990 | 2024-06-03
721 | Solar | 1990 | 2022-08-26
722 | Solar | 999 | 2022-11-28
723 | Solar | 4950 | 2025-04-08
726 | Solar | 1990 | 2024-01-09
727 | Solar | 1999 | 2022-10-18
729 | Solar | 1990 | 2022-12-20
730 | Solar | 499 | 2025-05-15
734 | Battery | 9690 | 2023-03-30
735 | Solar | 990 | 2023-06-14
736 | Solar/Battery | 1992 | 2023-05-23
738 | Solar | 992 | 2023-07-20
739 | Solar/Battery | 2100 | 2024-03-14
740 | Solar/Battery | 996 | 2024-05-23
742 | Solar | 999 | 2024-04-02
743 | Solar | 2000 | 2025-04-16
744 | Solar | 990 | 2023-06-06
747 | Solar | 600 | 2024-05-20
748 | Solar | 600 | 2023-10-24
749 | Solar | 600 | 2024-05-20
750 | Solar | 990 | 2024-11-27
751 | Solar | 500 | 2026-03-31
752 | Fuel Cell | 975 | 2023-08-24
753 | Fuel Cell | 975 | 2023-08-24
754 | Fuel Cell | 975 | 2023-08-24
755 | Fuel Cell | 975 | 2023-08-24
756 | Fuel Cell | 975 | 2023-08-24
757 | Solar | 990 | 2025-04-15
759 | Fuel Cell | 975 | 2023-03-23
760 | Fuel Cell | 975 | 2023-03-23
761 | Fuel Cell | 975 | 2023-08-24
762 | Fuel Cell | 975 | 2023-08-24
763 | Solar | 975 | 2024-02-02
764 | Solar | 990 | 2024-11-25
766 | Battery | 20000 | 2022-11-23
767 | Fuel Cell | 975 | 2023-03-23
768 | Solar | 999 | 2026-07-13
769 | Solar | 1875 | 2025-12-30
770 | Solar/Battery | 12400 | 2025-12-18
771 | Solar | 960 | 2024-05-15
772 | Solar | 975 | 2025-07-15
773 | Fuel Cell | 975 | 2023-03-23
774 | Solar | 960 | 2023-09-11
775 | Fuel Cell | 975 | 2023-03-23
776 | Fuel Cell | 975 | 2023-03-23
777 | Solar | 990 | 2023-07-20
778 | Solar | 990 | 2025-09-22
779 | Solar | 875 | 2024-08-16
780 | Solar | 960 | 2023-08-24
782 | Solar | 960 | 2023-10-23
783 | Fuel Cell | 975 | 2023-03-23
784 | Fuel Cell | 975 | 2023-03-23
785 | Fuel Cell | 975 | 2023-03-23
786 | Fuel Cell | 975 | 2023-03-23
787 | Fuel Cell | 975 | 2023-03-23
788 | Solar | 960 | 2024-02-15
789 | Fuel Cell | 975 | 2023-03-23
790 | Solar | 996 | 2025-02-04
791 | Solar | 1999 | 2024-12-18
792 | Solar | 999 | 2023-10-19
793 | Solar | 999 | 2024-04-01
794 | Solar | 100 | 2023-06-05
797 | Solar | 999 | 2024-05-23
799 | Solar | 999 | 2024-05-28
800 | Battery | 9690 | 2025-12-02
802 | Solar | 990 | 2023-12-20
804 | Solar | 240 | 2023-06-26
805 | Solar/Battery | 996 | 2026-03-03
807 | Solar | 990 | 2025-08-07
809 | Solar/Battery | 999 | 2026-05-22
810 | Solar/Battery | 999 | 2024-03-13
811 | Solar/Battery | 999 | 2025-10-22
812 | Solar/Battery | 999 | 2026-02-05
813 | Solar/Battery | 996 | 2026-03-31
815 | Solar | 2000 | 2025-12-15
816 | Solar | 999 | 2025-03-24
819 | Solar | 999 | 2025-12-17
822 | Solar | 999 | 2025-02-11
824 | Solar/Battery | 990 | 2024-06-20
825 | Solar/DC BESS | 996 | 2024-06-24
826 | Solar | 990 | 2024-06-28
827 | Solar | 999 | 2026-04-01
828 | Solar | 900 | 2025-01-16
830 | Solar | 999 | 2023-10-23
831 | Solar | 999 | 2024-06-10
832 | Solar | 900 | 2025-03-26
833 | Solar | 900 | 2025-02-11
835 | Solar/Battery | 4999 | 2025-11-25
836 | Solar | 999 | 2024-12-16
837 | Solar | 999 | 2023-11-28
838 | Solar/Battery | 999 | 2026-08-10
839 | Solar | 999 | 2025-08-21
840 | Solar | 994 | 2024-10-21
842 | Solar | 999 | 2023-11-16
843 | Solar | 999 | 2024-05-07
844 | Solar/Battery | 996 | 2024-05-20
846 | Solar | 999 | 2025-08-01
847 | Solar | 999 | 2024-11-26
849 | Solar | 994 | 2025-11-25
850 | Solar | 600 | 2024-09-10
851 | Solar | 999 | 2024-10-29
852 | Solar | 999 | 2026-04-01
853 | Solar/Battery | 996 | 2024-11-25
857 | Solar | 233.3 | 2024-04-10
860 | Solar/Battery | 996 | 2024-08-06
861 | Solar | 700 | 2024-06-10
862 | Solar | 999 | 2024-12-23
867 | Solar | 975 | 2025-09-16
868 | Solar | 999 | 2025-10-07
869 | Solar/Battery | 750 | 2025-03-04
871 | Solar | 999 | 2025-03-24
872 | Solar | 2000 | 2025-11-07
873 | Solar | 996 | 2024-12-24
874 | Solar | 999 | 2025-06-24
875 | Solar | 999 | 2025-05-19
876 | Solar | 996 | 2024-09-19
877 | Solar | 950 | 2025-01-07
878 | Solar | 999 | 2026-07-28
881 | Solar | 999 | 2026-04-01
883 | Solar | 999 | 2025-10-01
884 | Solar | 999 | 2025-10-16
885 | Solar | 999 | 2025-08-04
886 | Solar | 999 | 2025-07-22
887 | Solar | 999 | 2025-07-14
888 | Solar | 999 | 2025-12-02
889 | Solar | 360 | 2025-09-22
891 | Battery | 4999 | 2025-09-17
892 | Battery | 4999 | 2025-09-17
893 | Battery | 4999 | 2025-06-17
894 | Battery | 4999 | 2025-09-17
895 | Solar/Battery | 1990 | 2025-11-04
896 | Solar | 999 | 2025-09-02
897 | Battery | 4990 | 2025-06-17
898 | Battery | 4999 | 2025-06-17
899 | Solar | 999 | 2026-06-11
900 | Solar | 999 | 2025-07-07
904 | Solar | 4999 | 2025-07-28
905 | Solar | 4999 | 2025-02-04
906 | Solar | 999 | 2025-02-06
907 | Solar | 4999 | 2025-04-09
908 | Solar | 4999 | 2025-12-08
909 | Solar | 999 | 2025-02-10
910 | Solar | 999 | 2025-06-16
911 | Solar | 999 | 2026-06-29
912 | Solar | 999 | 2025-06-06
913 | Solar | 4999 | 2025-01-07
914 | Solar | 4999 | 2026-04-24
915 | Solar | 999 | 2025-03-12
916 | Solar | 999 | 2025-04-23
917 | Solar | 999 | 2025-12-12
918 | Solar | 780 | 2025-04-04
919 | Solar | 999 | 2025-05-09
920 | Solar | 975 | 2025-06-13
921 | Solar | 975 | 2025-07-15
922 | Solar | 450 | 2025-11-26
923 | Solar | 999 | 2025-05-20
925 | Solar | 250 | 2025-05-06
928 | Battery | 4999 | 2025-09-15
929 | Battery | 4999 | 2025-04-01
930 | Battery | 4999 | 2025-09-17
931 | Battery | 4999 | 2025-06-26
932 | Solar | 999 | 2025-10-31
933 | Solar | 999 | 2026-02-12
935 | Solar | 999 | 2025-12-10
936 | Solar | 999 | 2026-01-07
937 | Solar | 999 | 2026-05-27
938 | Solar | 999 | 2025-10-29
939 | Solar | 999 | 2026-01-12
940 | Solar | 999 | 2025-11-25
942 | Solar | 999 | 2025-11-06
943 | Solar | 999 | 2026-04-23
944 | Solar | 999 | 2025-11-06
948 | Solar | 999 | 2026-02-17
949 | Solar | 975 | 2025-12-29
951 | Solar | 999 | 2026-03-03
952 | Solar | 999 | 2026-02-24
953 | Solar | 999 | 2026-03-11
954 | Solar | 999 | 2026-09-17
955 | Solar | 999 | 2026-03-20
956 | Solar | 999 | 2026-03-12

## Limited Transmission Tracker (hidden)
PRJ | Developer | Project Name | Type of Generation | Total Size (kW) | Battery Size (kW) | Fully Executed Interconnection Agreement | Estimated Commercial Operation Date | Executable Issue Date | Executable due date | Dev Executable received | Payment Received | Fully Executed Issued
200 | Syncarpha Solar LLC | LIVERMORE SOLAR 1 LLC | Solar | 999 | 0 | 2022-03-21 | Q3 2026 | 2025-06-20 | 2025-06-27 | 2025-06-23 | 2025-06-24
481 | Syncarpha Solar LLC | OAKLAND SOLAR I LLC | Solar | 999.6 | 0 | 2022-06-21 |  | 2025-06-20 | 2025-06-27 | 2025-06-23 | 2025-06-24
669 | Nexamp, Inc | NEXAMP SOLAR LLC | Solar | 975 | 0 | 2025-01-08 | Q4 2024 | 2025-06-20 | 2025-06-27 | 2025-06-27 | 2025-06-27
698 | Novel Energy SPV 4 LLC | OAKLAND FIRST PARK SOLAR LLC | Solar | 999 | 0 | 2023-05-03 | Q2 2026 | 2025-06-20 | 2025-06-27 | 2025-06-27 | Rec'd conf 6/27
712 | Nexamp, Inc | Lisbon Falls Solar, LLC | Solar | 999 | 0 | 2024-05-28 | Q3 2026 | 2025-06-20 | 2025-06-27 | 2025-06-26 | 2025-06-27
731 | Novel Energy Solutions LLC | ME Vassalboro Cain CS LLC | Solar | 975 | 0 | 2024-03-27 | Q2 2026 | 2025-06-20 | 2025-06-27 | 2025-06-27 | Rec'd conf 6/27
772 | Novel Energy Solutions LLC | ME Fairfield Kissinger CSG LLC | Solar | 975 | 0 | 2024-01-30 | Q2 2026 | 2025-06-20 | 2025-06-27 | Declined study | Declined study
781 | SUSTAINABLE STRATEGIES 2050 INC | SUSTAINABLE STRATEGIES 2050 INC | Solar | 950 | 0 | 2024-12-03 | Q3 2026 | 2025-06-20 | 2025-06-27 | 2025-06-27 | Pending
795 | BNRG MAINE LLC | BD SOLAR DIXFIELD LLC | Solar | 990 | 0 | 2024-05-29 | Q1 2026 | 2025-06-20 | 2025-06-27 | 2025-06-27 | Pending
811 | New Leaf Energy, Inc | 510 PV PROJECT DEVELOPMENT LLC | Solar/Battery | 999 |  | 2025-03-25 |  | 2025-06-20 | 2025-06-27 | Declined study | Declined study
813 | Novel Energy Solutions LLC | ME Philbrick Middle Road CSG LLC | Solar/Battery | 996 | 0 | 2023-11-30 | Q2 2026 | 2025-06-20 | 2025-06-27 | 2025-06-27 | Rec'd conf 6/27
820 | Nexamp, Inc | Lakewood Renewables, LLC | Solar | 999 | 0 | 2023-12-13 | Q2 2026 | 2025-06-20 | 2025-06-27 | 2025-06-27 | 2025-06-27
829 | Nexamp, Inc | Richmond Renewables, LLC | Solar | 999 | 0 | 2024-02-15 | Q1 2026 | 2025-06-20 | 2025-06-27 | 2025-06-26 | 2025-06-27
841 | Nexamp, Inc | Bethel Renewables LLC | Solar | 999 | 0 | 2024-02-14 | Q1 2026 | 2025-06-20 | 2025-06-27 | 2025-06-27 | 2025-06-27
852 | Paddle Energy LLC | PE Copernicus LLC | Solar | 999 | 0 | 2025-04-09 |  | 2025-06-20 | 2025-06-27 | 2025-06-23 | 2025-06-26
864 | MAINELY SOLAR LLC | SEBAGO SOLAR LLC | Solar | 996 | 0 | 2024-10-03 | Q1 2026 | 2025-06-20 | 2025-06-27 | 2025-06-21 | 2025-06-27
886 | SolAmerica Energy, LLC | SolAmerica Energy LLC | Solar | 999 | 0 | 2025-02-26 | Q3 2026 | 2025-06-20 | 2025-06-27 | 2025-06-25 | 2025-07-07
890 | Invaleon Technologies Corp | NEW BALANCE ATHLETICS INC | Solar | 600 | 0 | 2024-11-07 | Q4 2024 | 2025-06-20 | 2025-06-27 | Declined study | Declined study
901 | Nexamp, Inc | NEXAMP SOLAR LLC | Solar | 975 | 0 | 2025-01-08 | Q4 2026 | 2025-06-20 | 2025-06-27 | 2025-06-26 | 2025-06-26
903 | Paddle Energy LLC | PE BRACKEN LLC | Solar | 999 |  | 2024-04-01 | Q4 2025 | 2025-06-20 | 2025-06-27 | 2025-06-23 | 2025-06-23
908 | SolAmerica Energy, LLC | SOLAMERICA ENERGY LLC | Solar | 999 |  | 2025-04-09 | Q1 2026 | 2025-06-20 | 2025-06-27 | 2025-06-25 | 2025-07-07

## Website
PROTECT
(D) - Application progress dependent on project indicated
Updated: 9/25/2026
***Project details included in this Interconnections table reflect Level 4 applications under the MPUC Chapter 324 Rule as of August 2018 only. Generation requests and generators interconnected to the CMP network prior to 2018 (whether under MPUC Chapter 324 or previous interconnection procedures) are not captured in this table.*** | [11 empty] | Feasibility Study |  | Impact Study |  | Combined Study |  | ReStudy |  | Facility Study |  | IA | ReQueued Restudy
PRJ | ISO_QP | Queue Position | (D) PRJ | r'Qd | Date App Rec'd | Town | Substation | Circuit | Type of Generation | Total Size (kW) | Battery Size (kW) | Start | Completion | Start | Completion | Start | Completion | Start | Completion | Start | Completion | Fully Executed Interconnection Agreement | R`Qd One Start | R`Qd One Stop | R`Qd Two Start | R`Qd Two Stop | R`Qd Three Start | R`Qd Three Stop | R`Qd Four Start | R`Qd Four Stop | Estimated Commercial Operation Date | Application Status | Energized Status | 25% Payment | Cluster Area | 115 kV SS | T. Level 0=Screen NC=Non-Comp 3=Full | 1.3.9 Approval | i39: RC Approval | PROJECT STATUS
1 | 0 | 0 | 0 |  | 2018-08-06 | Fairfield | FAIRFIELD | 817D3 | Solar | 4320 | 0 |  |  |  |  | 2018-08-20 | 2018-10-04 |  |  |  |  | 2019-06-07 | [8 empty] | Q1 2021 | Fully Executed Interconnection Agreement | Yes | 2020-09-03 | Cluster 02 - Winslow-County Rd-Lakewood -1 | Winslow-County Rd | 0 | 2018-10-11 |  | EXECUTED/ENERGIZED
2 | 0 | 0 | 0 |  | 2018-08-29 | Oxford | OXFORD | 437D1 | Solar | 4600 | 0 |  |  |  |  | 2018-10-11 | 2018-12-17 |  |  |  |  | 2019-05-30 | [8 empty] | Q4 2020 | Fully Executed Interconnection Agreement | Yes | 2019-08-22 | Cluster 05 - Lewiston Loop - 1 | Norway | Individual | 2019-08-26 |  | EXECUTED/ENERGIZED
3 | 0 | 0 | 0 |  | 2018-08-29 | Oxford | OXFORD | 437D2 | Solar | 4600 | 0 |  |  |  |  | 2018-10-11 | 2018-12-17 |  |  |  |  | 2019-05-30 | [8 empty] | Q4 2020 | Fully Executed Interconnection Agreement | Yes | 2019-08-22 | Cluster 05 - Lewiston Loop - 1 | Norway | Individual | 2019-08-26 |  | EXECUTED/ENERGIZED
4 | 0 | 0 | 0 |  | 2018-10-15 | Augusta | BLAIR ROAD | 207D2 | Solar | 7200 | 0 |  |  |  |  | 2018-10-24 | 2019-01-04 |  |  |  |  | 2019-05-30 | [8 empty] | Q4 2020 | Fully Executed Interconnection Agreement | Yes | 2020-07-10 | Cluster 11 - Augusta E-Puddledock-Bowman St - 2 | Augusta E/Puddledock/Bowman St | Individual | 2019-08-26 |  | EXECUTED/ENERGIZED
5 | 0 | 0 | 0 |  | 2018-10-29 | Fairfield | SHAWMUT | 852D1 | Solar | 4990 | 0 |  |  |  |  | 2018-12-11 | 2019-02-13 |  |  |  |  | 2019-05-30 | [8 empty] | Q4 2020 | Fully Executed Interconnection Agreement | Yes | 2020-07-15 | Cluster 02 - Winslow-County Rd-Lakewood -1 | Lakewood | 0 | 2019-05-01 |  | EXECUTED/ENERGIZED
6 | 0 | 0 | 0 |  | 2018-11-19 | Winslow | WINSLOW | 870D2 | Solar | 6999 | 0 |  |  |  |  | 2019-02-08 | 2019-04-11 |  |  |  |  | 2019-06-07 | [8 empty] | Q4 2020 | Fully Executed Interconnection Agreement | Yes | 2020-09-01 | Cluster 02 - Winslow-County Rd-Lakewood -1 | Winslow-County Rd | Individual | 2020-07-27 |  | EXECUTED/ENERGIZED
7 | 0 | 0 | 0 |  | 2019-01-24 | Waterville | SOUTH WATERVILLE | 855D2 | Solar | 4920 | 0 |  |  |  |  | 2019-03-15 | 2019-05-16 |  |  |  |  | 2019-06-07 | [8 empty] | Q1 2021 | Fully Executed Interconnection Agreement | Yes | 2020-09-03 | Cluster 02 - Winslow-County Rd-Lakewood -1 | Winslow-County Rd | 0 | 2019-12-13 |  | EXECUTED/ENERGIZED
8 | 0 | 0 | 0 |  | 2019-02-04 | Rumford | RUMFORD INDUSTRIAL PARK | 466D1 | Battery | 4999 | 4999 |  |  |  |  | 2019-04-29 | 2019-07-02 |  |  |  |  | 2019-08-05 | [8 empty] | Q1 2021 | Fully Executed Interconnection Agreement | Yes | 2020-08-19 | Cluster 10 - Roxbury-Rumford-Woodstock - 1 | Rumford IP | 0 | 2020-04-10 |  | EXECUTED/ENERGIZED
9 | 0 | 0 | 0 |  | 2019-03-05 | Sanford | HIGH STREET | 626D1 | Solar | 4950 | 0 |  |  |  |  | 2019-07-11 | 2019-09-09 |  |  |  |  | 2020-02-19 | [8 empty] | Q4 2020 | Fully Executed Interconnection Agreement | Yes | 2020-08-12 | Cluster 04 - Sanford-Quaker Hill - 1 | Sanford | 0 | 2019-12-30 |  | EXECUTED/ENERGIZED
10 | 0 | 0 | 0 |  | 2019-03-11 | Fairfield | SHAWMUT | 852D1 | Solar | 650 | 0 |  |  |  |  | 2019-05-02 | 2019-07-01 |  |  |  |  | 2019-12-05 | [8 empty] | Q4 2019 | Fully Executed Interconnection Agreement | Yes | 2019-10-12 | Cluster 12 - Winslow-County Rd-Lakewood - 2 | Lakewood | 0 |  | Not Required | EXECUTED/ENERGIZED
11 | 0 | 0 | 0 |  | 2019-04-02 | Sanford | SANFORD INDUSTRIAL PARK | 656D3 | Battery | 4999 | 4999 |  |  |  |  | 2019-06-20 | 2019-08-23 |  |  |  |  | 2020-05-11 | [8 empty] | Q4 2020 | Fully Executed Interconnection Agreement | No | 2021-02-02 | Cluster 04 - Sanford-Quaker Hill - 1 | Sanford | NC | 2020-07-14 |  | EXECUTED
12 | 0 | 0 | 0 |  | 2019-04-25 | Dover | DOVER | 815D1 | Battery | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Guilford |  |  |  | WITHDRAWN
13 | 0 | 0 | 0 |  | 2019-05-02 | Manchester | PUDDLEDOCK ROAD | 262D1 | Battery | 0 | 0 | [10 empty] | 2020-05-15 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 01 - Augusta/ E_Puddledock/ BowmanSt - 1 | Augusta E/Puddledock/Bowman St | Individual |  | 2022-10-21 | EXECUTED-WITHDRAWN
14 | 0 | 0 | 0 |  | 2019-05-03 | Hartland | HARTLAND | 824D2 | Solar | 4000 | 0 |  |  |  |  | 2019-06-17 | 2019-08-20 |  |  |  |  | 2019-08-29 | [8 empty] | Q1 2021 | Fully Executed Interconnection Agreement | Yes | 2020-09-03 | Cluster 16 - Wyman Area - 1 | Hartland | 0 | 2019-12-13 |  | EXECUTED/ENERGIZED
15 | 0 | 0 | 0 |  | 2019-05-15 | South Portland | MUSSEY ROAD | 636D2 | Battery | 0 | 0 | [10 empty] | 2019-11-06 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 15 - Greater Portland - 1 | Mussey Road | Individual | 2023-05-31 |  | 0
16 | 0 | 0 | 0 |  | 2019-05-15 | Hartland | HARTLAND | 824D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Hartland |  |  |  | WITHDRAWN
17 | 0 | 0 | 0 |  | 2019-05-16 | Wells | PRATT & WHITNEY | 661D2 | Solar | 4800 | 0 |  |  |  |  | 2019-07-12 | 2019-09-16 |  |  |  |  | 2020-02-13 | [8 empty] | Q4 2020 | Fully Executed Interconnection Agreement | Yes | 2020-09-10 | Cluster 04 - Sanford-Quaker Hill - 1 | Pratt & Whitney | 0 | 2020-04-28 |  | EXECUTED/ENERGIZED
18 | 0 | 0 | 0 |  | 2019-05-21 | Sanford | SOUTH SANFORD | 667D1 | Solar | 4950 | 0 |  |  |  |  | 2019-07-12 | 2019-09-16 |  |  |  |  | 2020-02-18 | [8 empty] | Q4 2020 | Fully Executed Interconnection Agreement | Yes | 2020-09-22 | Cluster 04 - Sanford-Quaker Hill - 1 | Sanford | NC | 2020-04-28 |  | EXECUTED
19 | 0 | 0 | 0 |  | 2019-05-23 | Wells | PRATT & WHITNEY | 661D2 | Solar | 4950 | 0 |  |  |  |  | 2020-01-27 | 2020-03-30 |  |  |  |  | 2020-05-01 | [8 empty] | Q4 2020 | Fully Executed Interconnection Agreement | Yes | 2020-11-25 | Cluster 04 - Sanford-Quaker Hill - 1 | Pratt & Whitney | NC | 2020-07-30 |  | EXECUTED/ENERGIZED
20 | 0 | 0 | 0 |  | 2019-06-07 | Pittsfield | DETROIT | 812D1 | Solar | 4875 | 0 |  |  |  |  | 2019-07-16 | 2019-09-17 |  |  |  |  | 2019-10-02 | [8 empty] | Q4 2020 | Fully Executed Interconnection Agreement | Yes | 2020-09-01 | Cluster 06 - Detroit-Guilford-Belfast - 1 | Detroit | 0 | 2020-02-26 |  | EXECUTED/ENERGIZED
21 | 0 | 0 | 0 |  | 2019-06-13 | Unity | UNITY | 860D1 | Solar | 4980 | 0 |  |  |  |  | 2019-08-05 | 2019-10-07 |  |  |  |  | 2019-11-14 | [8 empty] | Q4 2020 | Fully Executed Interconnection Agreement | Yes | 2020-09-03 | Cluster 06 - Detroit-Guilford-Belfast - 1 | Belfast | 0 | 2019-12-13 |  | EXECUTED/ENERGIZED
22 | 0 | 0 | 0 |  | 2019-06-14 | Palmyra | NEWPORT | 837D1 | Solar | 4990 | 0 |  |  |  |  | 2019-07-24 | 2019-09-25 |  |  |  |  | 2020-02-13 | [8 empty] | Q2 2021 | Fully Executed Interconnection Agreement | Yes | 2020-09-15 | Cluster 06 - Detroit-Guilford-Belfast - 1 | Detroit | 0 | 2020-02-26 |  | EXECUTED/ENERGIZED
23 | 0 | 0 | 0 |  | 2019-06-17 | Poland | HOTEL ROAD | 420D4 | Solar | 4875 | 0 |  |  |  |  | 2019-08-14 | 2019-10-16 |  |  |  |  | 2019-12-05 | [8 empty] | Q3 2020 | Fully Executed Interconnection Agreement | Yes | 2020-05-21 | Cluster 05 - Lewiston Loop - 1 | Hotel Rd/Gulf/Middle St/Crowleys/Norway | 0 | 2020-02-26 |  | EXECUTED/ENERGIZED
24 | 0 | 0 | 0 |  | 2019-07-12 | Lewiston | DEER RIPS | 412D4 | Solar | 4900 | 0 |  |  |  |  | 2019-08-14 | 2019-10-16 |  |  |  |  | 2019-12-05 | [8 empty] | Q3 2020 | Fully Executed Interconnection Agreement | Yes | 2020-11-10 | Cluster 05 - Lewiston Loop - 1 | Hotel Rd/Gulf/Middle St/Crowleys/Norway | 0 | 2020-02-28 |  | EXECUTED/ENERGIZED
25 | 0 | 0 | 0 |  | 2019-07-18 | Madison | SKOWHEGAN NORTH SIDE | 853D1 | Solar | 4999 | 0 |  |  |  |  | 2019-10-01 | 2019-12-03 |  |  |  |  | 2020-02-06 | [8 empty] | Q4 2020 | Fully Executed Interconnection Agreement | Yes | 2020-05-21 | Cluster 02 - Winslow-County Rd-Lakewood -1 | Lakewood | NC | 2020-04-28 |  | EXECUTED/ENERGIZED
26 | 0 | 0 | 0 |  | 2019-07-31 | Madison | SKOWHEGAN NORTH SIDE | 853D1 | Solar/Battery | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 02 - Winslow-County Rd-Lakewood -1 | Lakewood | 3 |  |  | WITHDRAWN
27 | 0 | 0 | 0 |  | 2019-07-31 | Saco | DUNSTAN | 617D2 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Vallee Lane |  |  |  | WITHDRAWN
28 | 0 | 0 | 0 |  | 2019-08-06 | Auburn | HOTEL ROAD | 420D4 | Solar | 0 | 0 | [10 empty] | 2020-04-08 | [8 empty] | Q2 2021 | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 05 - Lewiston Loop - 1 | Hotel Rd/Gulf/Middle St/Crowleys/Norway | 3 | 2022-07-19 |  | RE_QUEUED_FullEx
29 | 0 | 0 | 28 |  | 2019-08-06 | Auburn | HOTEL ROAD | 420D4 | Solar | 0 | 0 | [10 empty] | 2020-08-26 | [8 empty] | Q2 2021 | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 05 - Lewiston Loop - 1 | Hotel Rd/Gulf/Middle St/Crowleys/Norway | 3 | 2022-07-19 |  | RE_QUEUED_FullEx
30 | 0 | 0 | 0 |  | 2019-08-06 | Lewiston | DEER RIPS | 412D4 | Solar | 0 | 0 | [10 empty] | 2020-06-17 | [8 empty] | Q3 2020 | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 05 - Lewiston Loop - 1 | Hotel Rd/Gulf/Middle St/Crowleys/Norway | 3 | 2022-07-19 |  | RE_QUEUED_FullEx
31 | 0 | 0 | 0 |  | 2019-08-07 | Rumford | RUMFORD | 447D2 | Solar | 4990 | 0 |  |  |  |  | 2019-11-20 | 2020-01-29 |  |  |  |  | 2020-04-13 | [8 empty] | Q4 2020 | Fully Executed Interconnection Agreement | Yes | 2020-08-11 | Cluster 10 - Roxbury-Rumford-Woodstock - 1 | Rumford | 0 | 2020-06-25 |  | EXECUTED/ENERGIZED
32 | 0 | 0 | 0 |  | 2019-08-07 | Gorham | FORT HILL | 624D1 | Solar/Battery | 4990 | 3000 |  |  |  |  | 2019-11-20 | 2020-01-29 |  |  |  |  | 2020-04-15 | [8 empty] | Q4 2020 | Fully Executed Interconnection Agreement | Yes | 2020-08-27 | Cluster 07 - Raymond - 1 | Raymond | NC | 2020-07-14 |  | EXECUTED/ENERGIZED
33 | 0 | 0 | 0 |  | 2019-08-07 | Auburn | GREAT FALLS | 436D6 | Solar | 4990 | 0 |  |  |  |  | 2019-12-05 | 2020-02-04 |  |  |  |  | 2020-04-20 | [8 empty] | Q4 2020 | Fully Executed Interconnection Agreement | Yes | 2020-08-23 | Cluster 05 - Lewiston Loop - 1 | Hotel Rd/Gulf/Middle St/Crowleys/Norway | NC | 2020-07-14 |  | EXECUTED/ENERGIZED
34 | 0 |  | 0 |  | 2019-08-07 | Auburn | GREAT FALLS | 436D6 | Solar | 999 | 0 |  |  |  |  | 2020-07-13 | 2020-09-15 |  |  |  |  | 2020-11-08 | 2023-06-19 | 2023-08-09 | 2024-12-06 | 2025-02-13 |  |  |  |  | Q3 2028 | Fully Executed Interconnection Agreement | No | 2024-04-04 | Cluster 05 - Lewiston Loop - 1 | Hotel Rd/Gulf/Middle St/Crowleys/Norway | 3 | 2022-07-19 | Not Required | RE_QUEUED_FullEx
35 | 0 | 0 | 0 |  | 2019-08-07 | Woodstock | TRAP CORNER | 453D1 | Solar/Battery | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Woodstock |  |  |  | WITHDRAWN
36 | 0 | 0 | 0 |  | 2019-08-07 | South Thomaston | THOMASTON CREEK | 246D1 | Solar/Battery | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Highland/Park St |  |  |  | WITHDRAWN
37 | 0 | 0 | 0 |  | 2019-08-09 | Dayton | BIDDEFORD PUMP | 605D2 | Solar | 4990 | 0 | 2019-10-21 | 2019-11-20 | 2020-01-10 | 2020-02-11 | [6 empty] | 2020-04-02 | [8 empty] | Q4 2020 | Fully Executed Interconnection Agreement | Yes | 2020-06-26 | Cluster 14 - Louden-Biddeford IP - 1 | Louden | 0 | 2020-04-28 |  | EXECUTED
38 | 0 | 0 | 0 |  | 2019-08-09 | Dayton | BIDDEFORD PUMP | 605D1 | Solar/Battery | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Louden |  |  |  | WITHDRAWN
39 | 0 | 0 | 0 |  | 2019-08-09 | Dayton | BIDDEFORD PUMP | 605D1 | Solar/Battery | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Louden |  |  |  | WITHDRAWN
40 | 0 | 0 | 0 |  | 2019-08-09 | Scarborough | SCARBOROUGH | 693D1 | Solar | 4980 | 0 |  |  |  |  | 2019-12-05 | 2020-02-04 |  |  |  |  | 2020-04-10 | [8 empty] | Q4 2020 | Fully Executed Interconnection Agreement | Yes | 2020-06-26 | Cluster 15 - Greater Portland - 1 | Spring St | 0 | 2020-07-14 |  | EXECUTED/ENERGIZED
41 | 0 | 0 | 0 |  | 2019-08-09 | Buxton | BONNY EAGLE | 610D2 | Solar/Battery | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Kimball Road/Lovell |  |  |  | WITHDRAWN
42 | 0 | 0 | 0 |  | 2019-08-09 | Buxton | BONNY EAGLE | 610D2 | Solar/Battery | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Kimball Road/Lovell |  |  |  | WITHDRAWN
43 | 0 | 0 | 0 |  | 2019-08-12 | Harrison | KIMBALL ROAD | 423D1 | Solar/Battery | 4990 | 4990 |  |  |  |  | 2019-10-31 | 2020-01-10 |  |  |  |  | 2020-01-28 | [8 empty] | Q4 2020 | Fully Executed Interconnection Agreement | Yes | 2020-08-24 | Cluster 03 - Kimball Rd-Lovell - 1 | Kimball Road/Lovell | 0 | 2020-02-28 |  | EXECUTED/ENERGIZED
44 | 0 | 0 | 0 |  | 2019-08-12 | Saco | LOUDEN | 633D1 | Solar | 4800 | 0 | 2019-10-23 | 2019-11-27 | 2020-01-13 | 2020-02-11 |  |  | 2020-03-18 |  |  |  | 2020-04-03 | [8 empty] | Q4 2020 | Fully Executed Interconnection Agreement | Yes | 2020-06-15 | Cluster 14 - Louden-Biddeford IP - 1 | Louden | NC | 2020-04-28 |  | EXECUTED
45 | 0 | 0 | 0 |  | 2019-08-13 | Lewiston | CROWLEYS | 411D1 | Solar | 2000 | 0 |  |  |  |  | 2019-10-08 | 2019-12-11 |  |  |  |  | 2020-01-06 | [8 empty] | Q3 2020 | Fully Executed Interconnection Agreement | Yes | 2020-05-28 | Cluster 05 - Lewiston Loop - 1 | Hotel Rd/Gulf/Middle St/Crowleys/Norway | 0 | 2020-02-28 |  | EXECUTED/ENERGIZED
46 | 0 | 0 | 0 |  | 2019-08-15 | Winslow | WINSLOW | 870D2 | Solar | 4600 | 0 |  |  |  |  | 2019-10-08 | 2019-12-11 |  |  |  |  | 2020-07-01 | [8 empty] | Q4 2020 | Fully Executed Interconnection Agreement | Yes | 2022-03-24 | Cluster 02 - Winslow-County Rd-Lakewood -1 | Winslow-County Rd | NC | 2020-08-31 |  | EXECUTED
47 | 0 | 0 | 0 |  | 2019-08-15 | Biddeford | BIDDEFORD PUMP | 605D1 | Solar | 0 | 0 | [10 empty] | 2020-08-05 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 14 - Louden-Biddeford IP - 1 | Louden | NC | 2021-03-30 |  | EXECUTED-WITHDRAWN
48 | 0 | 0 | 0 |  | 2019-08-15 | Waterville | OAKLAND | 839D1 | Solar | 4600 | 0 |  |  |  |  | 2019-10-08 | 2019-12-11 |  |  |  |  | 2020-06-11 | [8 empty] | Q4 2020 | Fully Executed Interconnection Agreement | Yes | 2020-11-12 | Cluster 02 - Winslow-County Rd-Lakewood -1 | Winslow-County Rd | NC | 2020-07-14 |  | EXECUTED/ENERGIZED
49 | 0 | 0 | 0 |  | 2019-08-19 | Fryeburg | FRYEBURG TAP | 405D2 | Solar | 4900 | 0 |  |  |  |  | 2019-11-04 | 2020-01-14 |  |  |  |  | 2020-03-02 | [8 empty] | Q4 2020 | Fully Executed Interconnection Agreement | Yes | 2020-09-10 | Cluster 03 - Kimball Rd-Lovell - 1 | Kimball Road/Lovell | 0 | 2020-04-28 |  | EXECUTED/ENERGIZED
50 | 0 | 0 | 0 |  | 2019-08-21 | Naples | RAYMOND 115 KV | 445D2 | Solar | 2000 | 0 |  |  |  |  | 2019-11-05 | 2020-01-15 |  |  |  |  | 2020-04-20 | [8 empty] | Q1 2020 | Fully Executed Interconnection Agreement | Yes | 2020-08-11 | Cluster 07 - Raymond - 1 | Raymond | NC | 2020-07-14 |  | EXECUTED/ENERGIZED
51 | 0 | 0 | 0 |  | 2019-08-29 | Skowhegan | WESTON HYDRO | 866D1 | Solar | 2625 | 0 |  |  |  |  | 2019-10-07 | 2019-12-10 |  |  |  |  | 2020-01-15 | [8 empty] | Q4 2021 | Fully Executed Interconnection Agreement | Yes | 2020-06-06 | Cluster 02 - Winslow-County Rd-Lakewood -1 | Lakewood | NC | 2020-04-28 |  | EXECUTED/ENERGIZED
52 | 0 | 0 | 0 |  | 2019-08-29 | Lebanon | LEBANON | 695D2 | Solar/Battery | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Sanford |  |  |  | WITHDRAWN
53 | 0 | 0 | 0 |  | 2019-08-29 | Standish | SHAWS MILL ROAD | 660D1 | Solar | 4990 | 0 |  |  |  |  | 2019-10-01 | 2019-12-03 |  |  |  |  | 2020-02-06 | [8 empty] | Q4 2021 | Fully Executed Interconnection Agreement | Yes | 2020-09-10 | Cluster 07 - Raymond - 1 | Raymond | 0 | 2020-04-28 |  | EXECUTED/ENERGIZED
54 | 0 | 0 | 0 |  | 2019-08-29 | Auburn | HOTEL ROAD | 420D2 | Solar/Battery | 0 | 0 | [10 empty] | 2021-02-19 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 05 - Lewiston Loop - 1 | Hotel Rd/Gulf/Middle St/Crowleys/Norway | 3 | 2022-07-19 |  | EXECUTED-WITHDRAWN
55 | 0 | 0 | 0 |  | 2019-08-29 | Auburn | HOTEL ROAD | 420D2 | Solar/Battery | 0 | 0 |  |  |  |  | 2021-07-13 | 2021-09-13 | 2021-12-11 | 2022-01-18 | [12 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 18 - Lewiston Loop - 2 | Hotel Rd/Gulf/Middle St/Crowleys/Norway | 3 |  |  | WITHDRAWN
56 | 0 | 0 | 0 |  | 2019-08-29 | Auburn | HOTEL ROAD | 420D2 | Solar/Battery | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 18 - Lewiston Loop - 2 | Hotel Rd/Gulf/Middle St/Crowleys/Norway | 3 |  |  | Kelsey Haley
57 | 0 | 0 | 0 |  | 2019-08-29 | Bethel | BETHEL | 403D1 | Solar | 4800 | 0 |  |  |  |  | 2019-10-31 | 2020-01-10 |  |  |  |  | 2020-02-18 | [8 empty] | Q4 2020 | Fully Executed Interconnection Agreement | Yes | 2020-07-23 | Cluster 10 - Roxbury-Rumford-Woodstock - 1 | Woodstock | 0 | 2020-04-28 |  | EXECUTED/ENERGIZED
58 | 0 | 0 | 0 |  | 2019-08-30 | Auburn | HOTEL ROAD | 420D2 | Solar/Battery | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 18 - Lewiston Loop - 2 | Hotel Rd/Gulf/Middle St/Crowleys/Norway | 3 |  |  | WITHDRAWN
59 | 0 | 0 | 0 |  | 2019-08-30 | Buxton | BONNY EAGLE | 610D2 | Solar | 0 | 0 | [10 empty] | 2020-04-03 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 03 - Kimball Rd-Lovell - 1 | Kimball Road/Lovell | 3 | 2023-04-27 |  | EXECUTED-WITHDRAWN
60 | 0 | 0 | 0 |  | 2019-08-30 | Buxton | BONNY EAGLE | 610D2 | Solar/Battery | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Kimball Road/Lovell |  |  |  | WITHDRAWN
61 | 0 | 0 | 0 |  | 2019-09-03 | Winthrop | WINTHROP | 256D1 | Solar/Battery | 4990 | 5000 |  |  |  |  | 2019-10-31 | 2020-01-10 |  |  |  |  | 2020-04-02 | [8 empty] | Q2 2021 | Fully Executed Interconnection Agreement | Yes | 2020-10-08 | Cluster 11 - Augusta E-Puddledock-Bowman St - 2 | Augusta E/Puddledock/Bowman St | 0 | 2020-04-28 |  | EXECUTED/ENERGIZED
62 | 0 | 0 | 0 |  | 2019-09-03 | Rumford | RUMFORD INDUSTRIAL PARK | 466D1 | Solar | 4988 | 0 |  |  |  |  | 2019-10-03 | 2019-12-09 |  |  |  |  | 2020-01-16 | [8 empty] | Q4 2020 | Fully Executed Interconnection Agreement | Yes | 2020-08-12 | Cluster 10 - Roxbury-Rumford-Woodstock - 1 | Rumford IP | NC | 2020-07-14 |  | EXECUTED/ENERGIZED
63 | 0 | 0 | 0 |  | 2019-09-04 | Otisfield | CASCO TAP | 463D1 | Solar/Battery | 3880 | 4000 |  |  |  |  | 2019-10-07 | 2019-12-10 |  |  |  |  | 2020-06-19 | [8 empty] | Q4 2020 | Fully Executed Interconnection Agreement | Yes | 2020-10-19 | Cluster 07 - Raymond - 1 | Raymond | NC | 2020-07-14 |  | EXECUTED/ENERGIZED
64 | 0 | 0 | 0 |  | 2019-09-04 | Gray | GRAY | 416D2 | Solar | 4990 | 0 |  |  |  |  | 2019-10-03 | 2019-12-09 |  |  |  |  | 2020-03-26 | [8 empty] | Q4 2020 | Fully Executed Interconnection Agreement | Yes | 2020-09-13 | Cluster 15 - Greater Portland - 1 | Elm St | 0 | 2020-04-28 |  | EXECUTED/ENERGIZED
65 | 0 | 0 | 0 |  | 2019-09-05 | Turner | TURNER | 454D1 | Solar/Battery | 0 | 0 | [10 empty] | 2020-04-03 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 05 - Lewiston Loop - 1 | Hotel Rd/Gulf/Middle St/Crowleys/Norway | 3 | 2022-07-19 |  | EXECUTED-WITHDRAWN
66 | 0 | 0 | 0 |  | 2019-09-05 | Farmington | STURTEVANT | 858D3 | Solar | 4875 | 0 |  |  |  |  | 2019-10-02 | 2019-11-12 |  |  |  |  | 2019-11-20 | [8 empty] | Q4 2020 | Fully Executed Interconnection Agreement | Yes | 2020-09-03 | Cluster 08 - Sturtevant-Leeds-Livermore-Ludden-Riley - 1 | Sturtevant | 0 | 2019-12-30 |  | EXECUTED/ENERGIZED
67 | 0 | 0 | 0 |  | 2019-09-05 | Standish | BONNY EAGLE | 610D2 | Solar | 0 | 0 | [10 empty] | 2020-11-14 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 03 - Kimball Rd-Lovell - 1 | Kimball Road/Lovell | 3 | 2023-04-27 |  | RE_QUEUED_FullEx
68 | 0 | 0 | 0 |  | 2019-09-05 | Leeds | LEEDS | 471D2 | Solar | 20000 | 0 | 2019-12-04 | 2020-01-03 | 2020-01-28 | 2020-02-27 | [6 empty] | 2020-06-11 | [8 empty] | Q2 2021 | Fully Executed Interconnection Agreement | Yes | 2020-09-22 | Cluster 08 - Sturtevant-Leeds-Livermore-Ludden-Riley - 1 | Leeds | Individual | 2021-12-17 |  | EXECUTED
69 | 0 | 0 | 0 |  | 2019-09-06 | Turner | TURNER | 454D1 | Solar/Battery | 0 | 0 | [10 empty] | 2020-09-11 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 05 - Lewiston Loop - 1 | Hotel Rd/Gulf/Middle St/Crowleys/Norway | 3 |  | 2022-07-22 | EXECUTED-WITHDRAWN
70 | 0 | 0 | 0 |  | 2019-09-09 | Readfield | PUDDLEDOCK ROAD | 262D1 | Solar | 4950 | 0 |  |  |  |  | 2020-04-02 | 2020-06-08 |  |  |  |  | 2020-06-17 | 2023-07-14 |  |  | 2023-07-25 |  |  |  |  | Q4 2020 | Fully Executed Interconnection Agreement | Yes | 2021-08-19 | Cluster 01 - Augusta - 1 | Augusta E/Puddledock/Bowman St | 3 | 2021-01-04 |  | RE_QUEUED_FullEx/ENERGIZED
71 | 0 | 0 | 0 |  | 2019-09-09 | Readfield | PUDDLEDOCK ROAD | 262D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Augusta E/Puddledock/Bowman St |  |  |  | WITHDRAWN
72 | 0 | 0 | 0 |  | 2019-09-09 | Leeds | LEEDS | 471D2 | Solar | 0 | 0 | [10 empty] | 2020-08-07 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 08 - Sturtevant-Leeds-Livermore-Ludden-Riley - 1 | Leeds | 3 |  | 2023-12-15 | EXECUTED-WITHDRAWN
73 | 0 | 0 | 0 |  | 2019-09-09 | Leeds | LEEDS | 471D2 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Leeds |  |  |  | WITHDRAWN
74 | 0 | 0 | 0 |  | 2019-09-09 | Fryeburg | FRYEBURG | 415D2 | Solar | 0 | 0 |  |  |  |  | 2020-03-31 | 2020-06-05 |  |  |  |  | 2020-05-18 | [8 empty] | Q4 2021 | WITHDRAWN | WITHDRAWN |  | Cluster 03 - Kimball Rd-Lovell - 1 | Kimball Road/Lovell | 3 | 2023-04-27 |  | EXECUTED
75 | 0 | 0 | 0 |  | 2019-09-09 | Waterville | OAKLAND | 839D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 02 - Winslow-County Rd-Lakewood -1 | Winslow-County Rd | 3 |  |  | WITHDRAWN
76 | 0 | 0 | 0 |  | 2019-09-09 | Gorham | FORT HILL | 624D2 | Solar | 0 | 0 |  |  |  |  | 2020-06-24 | 2020-08-27 |  |  |  |  | 2020-09-23 | 2023-03-23 | 2023-05-05 | [7 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 07 - Raymond - 1 | Raymond | 3 | 2023-12-21 |  | EXECUTED-WITHDRAWN
77 | 0 | 0 | 0 |  | 2019-09-09 | Baldwin | BALDWIN | 691D1 | Solar | 4950 | 0 |  |  |  |  | 2019-10-18 | 2019-12-19 |  |  |  |  | 2020-04-29 | [8 empty] | Q4 2021 | Fully Executed Interconnection Agreement | Yes | 2020-09-16 | Cluster 03 - Kimball Rd-Lovell - 1 | Kimball Road/Lovell | NC | 2020-07-14 |  | EXECUTED/ENERGIZED
78 | 0 | 0 | 0 |  | 2019-09-10 | Saco | DUNSTAN | 617D2 | Solar/Battery | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Vallee Lane |  |  |  | WITHDRAWN
79 | 0 | 0 | 0 |  | 2019-09-10 | Parkman | GUILFORD | 821D1 | Solar | 4875 | 0 |  |  |  |  | 2019-10-11 | 2019-12-16 |  |  |  |  | 2020-01-15 | 2022-10-12 | 2022-11-23 | 2022-12-20 |  | 2023-10-12 | 2023-11-28 |  |  | Q1 2022 | Fully Executed Interconnection Agreement | Yes | 2020-07-02 | Cluster 06 - Detroit-Guilford-Belfast - 1 | Guilford | 0 | 2020-04-10 |  | RE_QUEUED_FullEx
80 | 0 | 0 | 0 |  | 2019-09-10 | Pittsfield | DETROIT | 812D1 | Solar | 4980 | 0 |  |  |  |  | 2019-10-09 | 2019-12-12 |  |  |  |  | 2020-05-11 | [8 empty] | Q4 2021 | Fully Executed Interconnection Agreement | Yes | 2020-05-18 | Cluster 06 - Detroit-Guilford-Belfast - 1 | Detroit | NC | 2020-06-25 |  | EXECUTED/ENERGIZED
81 | 0 | 0 | 0 |  | 2019-09-10 | Washington | STICKNEYS CORNER | 245D2 | Solar | 2000 | 0 |  |  |  |  | 2019-10-29 | 2019-12-24 |  |  |  |  | 2020-02-25 | [8 empty] | Q1 2021 | Fully Executed Interconnection Agreement | Yes | 2020-08-19 | Cluster 09 - Midcoast - 1 | Coopers Mills | 0 | 2020-04-28 |  | EXECUTED/ENERGIZED
82 | 0 | 0 | 0 |  | 2019-09-10 | Oakland | COUNTY RD (RICE RIPS) | 873D1 | Solar | 4990 | 0 |  |  |  |  | 2019-12-05 | 2020-02-04 |  |  |  |  | 2020-05-05 | [8 empty] | Q4 2021 | Fully Executed Interconnection Agreement | Yes | 2020-11-05 | Cluster 02 - Winslow-County Rd-Lakewood -1 | Winslow-County Rd | NC | 2020-06-25 |  | EXECUTED/ENERGIZED
83 | 0 | 0 | 0 |  | 2019-09-10 | Wilton | WILTON | 885D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Sturtevant |  |  |  | WITHDRAWN
84 | 0 | 0 | 0 |  | 2019-09-10 | North Bridgton | BRIDGTON | 406D1 | Solar | 4990 | 0 |  |  |  |  | 2019-12-05 | 2020-02-04 |  |  |  |  | 2020-03-26 | [8 empty] | Q4 2021 | Fully Executed Interconnection Agreement | Yes | 2020-09-10 | Cluster 03 - Kimball Rd-Lovell - 1 | Kimball Road/Lovell | NC | 2020-07-14 |  | EXECUTED/ENERGIZED
85 | 0 | 0 | 0 |  | 2019-09-10 | Baldwin | BALDWIN | 691D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 13 - Kimball Rd-Lovell - 2 | Kimball Road/Lovell | 3 |  |  | WITHDRAWN
86 | 0 | 0 | 0 |  | 2019-09-10 | Naples | BRIDGTON 34 KV | 406D4 | Solar | 0 | 0 | [10 empty] | 2020-07-24 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 03 - Kimball Rd-Lovell - 1 | Kimball Road/Lovell | 3 | 2023-04-27 |  | EXECUTED-WITHDRAWN
87 | 0 | 0 | 0 |  | 2019-09-11 | Hermon | BANGOR HYDRO (Versant) | 120D1 | Solar | 4990 | 0 |  |  |  |  | 2020-03-10 | 2020-05-13 | 2021-08-23 | 2021-09-16 |  |  | 2021-11-30 | [8 empty] | Q4 2021 | Fully Executed Interconnection Agreement | Yes | 2023-07-20 | N/A | Emera Transmission |  | 2022-08-17 |  | EXECUTED
88 | 0 | 0 | 0 |  | 2019-09-13 | Turner | TURNER TAP | 467D1 | Solar/Battery | 0 | 0 | [10 empty] | 2020-03-26 | [8 empty] | Q2 2021 | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 05 - Lewiston Loop - 1 | Hotel Rd/Gulf/Middle St/Crowleys/Norway | 3 | 2022-07-19 |  | EXECUTED
89 | 0 | 0 | 0 |  | 2019-09-13 | Monmouth | MONMOUTH | 457D1 | Solar | 4950 | 0 |  |  |  |  | 2019-10-29 | 2020-01-02 |  |  |  |  | 2020-03-23 | [9 empty] | Fully Executed Interconnection Agreement | Yes | 2020-09-28 | N/A | Monmouth | 0 | 2020-06-25 |  | EXECUTED/ENERGIZED
90 | 0 | 0 | 0 |  | 2019-09-16 | Harrison | KIMBALL ROAD | 423D1 | Solar | 0 | 0 | [10 empty] | 2020-04-14 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 03 - Kimball Rd-Lovell - 1 | Kimball Road/Lovell | 3 | 2023-04-27 |  | EXECUTED-WITHDRAWN
91 | 0 | 0 | 0 |  | 2019-09-16 | Standish | BONNY EAGLE | 610D2 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 03 - Kimball Rd-Lovell - 1 | Kimball Road/Lovell | 3 |  | 2023-04-22 | WITHDRAWN
92 | 0 |  | 0 |  | 2019-09-16 | Manchester | PUDDLEDOCK ROAD | 262D1 | Solar | 998 | 0 |  |  |  |  | 2020-09-17 | 2020-11-23 | 2023-11-30 | 2024-01-15 |  |  | 2021-01-12 | 2023-09-11 | 2023-10-24 | 2025-10-30 | 2026-01-07 |  |  |  |  | Q3 2026 | Fully Executed Interconnection Agreement | No | 2024-09-18 | Cluster 11 - Augusta E-Puddledock-Bowman St - 2 | Augusta E/Puddledock/Bowman St | 3 | 2024-05-28 |  | RE_QUEUED_FullEx
93 | 0 | 0 | 0 |  | 2019-09-17 | Wiscasset | MAINE YANKEE | 274D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Maine Yankee | 0 |  |  | WITHDRAWN
94 | 0 | 0 | 0 |  | 2019-09-17 | Augusta | AUGUSTA K5 | 200D2 | Solar | 4988 | 0 |  |  |  |  | 2019-10-11 | 2019-12-16 |  |  |  |  | 2020-01-28 | [8 empty] | Q4 2020 | Fully Executed Interconnection Agreement | Yes | 2020-08-17 | Cluster 11 - Augusta E-Puddledock-Bowman St - 2 | Augusta E/Puddledock/Bowman St | 0 | 2020-04-28 |  | EXECUTED/ENERGIZED
95 | 0 | 0 | 0 |  | 2019-09-17 | Manchester | MANCHESTER | 233D1 | Solar | 4500 | 0 |  |  |  |  | 2020-01-30 | 2020-04-06 |  |  |  |  | 2020-04-14 | [8 empty] | Q4 2021 | Fully Executed Interconnection Agreement | Yes | 2021-05-26 | Cluster 01 - Augusta - 1 | Augusta E/Puddledock/Bowman St | 3 | 2021-01-04 |  | EXECUTED/ENERGIZED
96 | 0 | 0 | 0 |  | 2019-09-18 | Fryeburg | FRYEBURG TAP | 405D1 | Solar | 0 | 0 | [10 empty] | 2020-10-19 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 03 - Kimball Rd-Lovell - 1 | Kimball Road/Lovell | 3 | 2023-04-27 |  | EXECUTED
97 | 0 | 0 | 0 |  | 2019-09-18 | Lebanon | LEBANON | 695D2 | Solar | 2000 | 0 |  |  |  |  | 2020-04-08 | 2020-06-11 |  |  |  |  | 2020-07-01 | [8 empty] | Q2 2022 | Fully Executed Interconnection Agreement (combo PRJ 98) | Yes | 2020-08-11 | Cluster 04 - Sanford-Quaker Hill - 1 | Sanford | 3 | 2022-06-27 |  | EXECUTED
98 | 0 | 0 | 0 |  | 2019-09-18 | Lebanon | LEBANON | 695D2 | Solar | 1750 | 0 |  |  |  |  | 2020-04-08 | 2020-06-11 |  |  |  |  | 2020-07-01 | [8 empty] | Q2 2022 | Fully Executed Interconnection Agreement (combo PRJ 97) | Yes | 2020-08-11 | Cluster 04 - Sanford-Quaker Hill - 1 | Sanford | 3 | 2022-06-27 |  | EXECUTED
99 | 0 | 0 | 0 |  | 2019-09-19 | Turner | TURNER TAP | 467D1 | Solar | 0 | 0 | [10 empty] | 2020-08-07 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 05 - Lewiston Loop - 1 | Hotel Rd/Gulf/Middle St/Crowleys/Norway | 3 | 2022-07-19 |  | EXECUTED
100 | 0 | 0 | 0 |  | 2019-09-19 | Turner | TURNER TAP | 467D1 | Solar | 0 | 0 | [10 empty] | 2020-08-07 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 05 - Lewiston Loop - 1 | Hotel Rd/Gulf/Middle St/Crowleys/Norway | 3 | 2022-07-19 |  | EXECUTED
101 | 0 | 0 | 0 |  | 2019-09-19 | Limerick | LIMERICK | 632D1 | Solar | 2000 | 0 |  |  |  |  | 2020-02-10 | 2020-04-15 |  |  |  |  | 2020-05-06 | [8 empty] | Q1 2028 | Fully Executed Interconnection Agreement (combo PRJ 106) | Yes | 2020-08-12 | Cluster 03 - Kimball Rd-Lovell - 1 | Kimball Road/Lovell | 3 | 2023-04-27 |  | EXECUTED
102 | 0 | 0 | 0 |  | 2019-09-19 | Washington | STICKNEYS CORNER | 245D1 | Solar | 4000 | 0 |  |  |  |  | 2020-04-16 | 2020-06-18 |  |  |  |  | 2020-07-02 | [9 empty] | Fully Executed Interconnection Agreement | Yes | 2020-07-20 | Cluster 09 - Midcoast - 1 | Coopers Mills | NC | 2020-10-05 |  | EXECUTED/ENERGIZED
103 | 0 | 0 | 0 |  | 2019-09-19 | Saco | LOUDEN | 633D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Louden |  |  |  | WITHDRAWN
104 | 0 | 0 | 0 |  | 2019-09-19 | Old Orchard Beach | CROWLEYS | 411D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A |  |  |  |  | WITHDRAWN
105 | 0 | 0 | 0 |  | 2019-09-19 | Newport | NEWPORT | 837D2 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Detroit |  |  |  | WITHDRAWN
106 | 0 | 0 | 0 |  | 2019-09-19 | Limerick | LIMERICK | 632D1 | Solar | 2000 | 0 |  |  |  |  | 2020-02-10 | 2020-04-15 |  |  |  |  | 2020-05-06 | [8 empty] | Q1 2028 | Fully Executed Interconnection Agreement (combo PRJ 101) | Yes | 2020-08-12 | Cluster 03 - Kimball Rd-Lovell - 1 | Kimball Road/Lovell | 3 | 2023-04-27 |  | EXECUTED
107 | 0 | 0 | 0 |  | 2019-09-19 | Jay | LIVERMORE FALLS | 428D3 | Solar | 2000 | 0 |  |  |  |  | 2020-02-07 | 2020-04-14 |  |  |  |  | 2020-04-28 | [8 empty] | Q4 2021 | Fully Executed Interconnection Agreement (combo PRJ 108) | Yes | 2020-08-11 | Cluster 08 - Sturtevant-Leeds-Livermore-Ludden-Riley - 1 | Livermore Falls | 0 | 2020-06-25 |  | EXECUTED/ENERGIZED
108 | 0 | 0 | 0 |  | 2019-09-19 | Jay | LIVERMORE FALLS | 428D3 | Solar | 1250 | 0 |  |  |  |  | 2020-02-07 | 2020-04-14 |  |  |  |  | 2020-04-28 | [8 empty] | Q4 2021 | Fully Executed Interconnection Agreement (combo PRJ 107) | Yes | 2020-08-11 | Cluster 08 - Sturtevant-Leeds-Livermore-Ludden-Riley - 1 | Livermore Falls | 0 | 2020-06-25 |  | EXECUTED/ENERGIZED
109 | 0 | 0 | 0 |  | 2019-09-20 | Auburn | HOTEL ROAD | 420D6 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Hotel Rd/Gulf/Middle St/Crowleys |  |  |  | WITHDRAWN
110 | 0 | 0 | 0 |  | 2019-10-31 | North Berwick | BASSETT | 602D3 | Solar | 4950 | 0 |  |  |  |  | 2020-01-30 | 2020-04-06 |  |  |  |  | 2020-04-13 | [9 empty] | Fully Executed Interconnection Agreement | Yes | 2020-07-20 | Cluster 04 - Sanford-Quaker Hill - 1 | Quaker Hill | NC | 2020-07-14 |  | EXECUTED/ENERGIZED
111 | 0 | 0 | 0 |  | 2019-09-20 | Brunswick | BRUNSWICK WEST SIDE | 213D3 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Topsham |  |  |  | WITHDRAWN
112 | 0 | 0 | 0 |  | 2019-09-20 | Berwick | PRATT & WHITNEY | 661D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Pratt & Whitney |  |  |  | WITHDRAWN
113 | 0 | 0 | 0 |  | 2019-09-20 | Newport | NEWPORT | 837D2 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Detroit |  |  |  | WITHDRAWN
114 | 0 | 0 | 0 |  | 2019-09-20 | Sabattus | CROWLEYS | 411D1 | Solar | 2000 | 0 |  |  |  |  | 2020-02-18 | 2020-04-22 |  |  |  |  | 2020-04-14 | [8 empty] | Q2 2021 | Fully Executed Interconnection Agreement | Yes | 2020-08-19 | Cluster 05 - Lewiston Loop - 1 | Hotel Rd/Gulf/Middle St/Crowleys/Norway | 3 | 2022-07-19 |  | EXECUTED/ENERGIZED
115 | 0 | 0 | 0 |  | 2019-09-20 | Sabattus | FACTORY ISLAND | 621D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A |  |  |  |  | WITHDRAWN
116 | 0 | 0 | 0 |  | 2019-09-23 | Winthrop | WINTHROP | 256D3 | Solar | 2500 | 0 |  |  |  |  | 2020-04-29 | 2020-07-02 |  |  |  |  | 2020-09-29 | [8 empty] | Q3 2021 | Fully Executed Interconnection Agreement | Yes | 2021-02-17 | Cluster 01 - Augusta - 1 | Augusta E/Puddledock/Bowman St | 3 | 2021-01-04 |  | EXECUTED/ENERGIZED
117 | 0 | 0 | 0 |  | 2019-09-23 | Parkman | GUILFORD | 821D3 | Solar | 0 | 0 | [10 empty] | 2020-07-13 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 06 - Detroit-Guilford-Belfast - 1 | Guilford | 3 | 2023-08-31 |  | RE_QUEUED_FullEx
118 | 0 | 0 | 0 |  | 2019-09-23 | Bingham | WYMAN HYDRO | 872D1 | Solar | 4950 | 0 |  |  |  |  | 2019-11-18 | 2020-01-27 |  |  |  |  | 2020-03-26 | [8 empty] | Q3 2021 | Fully Executed Interconnection Agreement | Yes | 2021-01-22 | Cluster 16 - Wyman Area - 1 | Wyman Hydro | 0 | 2020-06-25 |  | EXECUTED/ENERGIZED
119 | 0 | 0 | 0 |  | 2019-09-23 | Orland | BUCKSPORT | 806D2 | Solar/Battery | 4990 | 4990 |  |  |  |  | 2019-11-18 | 2020-01-27 |  |  |  |  | 2020-03-02 | [8 empty] | Q2 2021 | Fully Executed Interconnection Agreement | Yes | 2020-09-13 | Cluster 06 - Detroit-Guilford-Belfast - 1 | Bucksport | 0 | 2020-04-28 |  | EXECUTED/ENERGIZED
120 | 0 | 0 | 0 |  | 2019-09-23 | Pittsfield | BURNHAM | 807D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Detroit | NC |  |  | WITHDRAWN
121 | 0 | 0 | 0 |  | 2019-09-24 | Harrison | KIMBALL ROAD | 423D1 | Solar/Battery | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 13 - Kimball Rd-Lovell - 2 | Kimball Road/Lovell | 3 |  |  | WITHDRAWN
122 | 0 | 0 | 0 |  | 2019-09-24 | Waldoboro | WALDOBORO | 252D2 | Solar | 2500 | 0 | 2019-11-12 | 2019-12-16 | 2020-02-27 |  |  |  | 2020-03-12 | 2020-04-27 |  |  | 2020-04-29 | [8 empty] | Q4 2020 | Fully Executed Interconnection Agreement | Yes | 2020-08-18 | Cluster 09 - Midcoast - 1 | Highland/Park St | 0 | 2020-06-25 |  | EXECUTED/ENERGIZED
123 | 0 | 0 | 0 |  | 2019-09-24 | Augusta | BLAIR ROAD | 207D2 | Solar/Battery | 3750 | 2000 | 2019-11-12 | 2019-12-16 | 2019-12-27 | 2020-01-28 |  |  | 2020-03-30 | 2020-05-12 |  |  | 2020-04-28 | [8 empty] | Q4 2020 | Fully Executed Interconnection Agreement | Yes | 2021-05-11 | Cluster 01 - Augusta - 1 | Augusta E/Puddledock/Bowman St | 3 | 2021-01-04 |  | EXECUTED/ENERGIZED
124 | 0 | 0 | 0 |  | 2019-09-24 | China | SOUTH CHINA | 244D1 | Solar | 4875 | 0 |  |  |  |  | 2019-11-12 | 2019-01-21 | 2020-03-30 | 2020-04-16 |  |  | 2020-04-23 | [8 empty] | Q4 2020 | Fully Executed Interconnection Agreement | Yes | 2020-08-18 | Cluster 11 - Augusta E-Puddledock-Bowman St - 2 | Augusta E/Puddledock/Bowman St | NC | 2020-06-25 |  | EXECUTED/ENERGIZED
125 | 0 | 0 | 0 |  | 2019-09-25 | Augusta | NORTH AUGUSTA | 272D6 | Solar | 2475 | 0 |  |  |  |  | 2019-10-31 | 2019-01-10 | 2020-04-09 | 2020-05-19 |  |  | 2020-06-04 | [8 empty] | Q2 2021 | Fully Executed Interconnection Agreement | Yes | 2020-08-31 | Cluster 11 - Augusta E-Puddledock-Bowman St - 2 | North Augusta | 0 | 2020-07-30 |  | EXECUTED/ENERGIZED
126 | 0 | 0 | 0 |  | 2019-09-26 | Warren | THOMASTON CREEK | 246D3 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A |  |  |  |  | WITHDRAWN
127 | 0 | 0 | 0 |  | 2019-09-26 | Windham | SWETT ROAD | 682D1/D2 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Raymond |  |  |  | WITHDRAWN
128 | 0 | 0 | 0 |  | 2019-09-26 | Richmond | RICHMOND | 240D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Augusta E/Puddledock/Bowman St |  |  |  | WITHDRAWN
129 | 0 | 0 | 0 |  | 2019-09-26 | Newport | NEWPORT | 837D2 | Solar | 0 | 0 | [10 empty] | 2020-07-16 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 06 - Detroit-Guilford-Belfast - 1 | Detroit | 3 | 2023-08-31 |  | EXECUTED-WITHDRAWN
130 | 0 | 0 | 0 |  | 2019-09-26 | Baldwin | BALDWIN | 691D1 | Solar | 0 | 0 | [10 empty] | 2021-05-24 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 03 - Kimball Rd-Lovell - 1 | Kimball Road/Lovell | 3 | 2023-04-27 |  | EXECUTED-WITHDRAWN
131 | 0 | 0 | 0 |  | 2019-09-26 | Belgrade | COUNTY RD (RICE RIPS) | 873D1 | Solar | 0 | 0 | [10 empty] | 2020-07-01 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 02 - Winslow-County Rd-Lakewood -1 | Winslow-County Rd | 3 | 2021-12-17 |  | EXECUTED-WITHDRAWN
132 | 0 | 0 | 0 |  | 2019-09-26 | Belgrade | COUNTY RD (RICE RIPS) | 873D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 02 - Winslow-County Rd-Lakewood -1 | Winslow-County Rd | 3 |  | 2021-12-21 | WITHDRAWN
133 | 0 | 0 | 0 |  | 2019-09-26 | Livermore Falls | LIVERMORE FALLS | 428D3 | Solar | 3892 | 0 |  |  |  |  | 2020-06-02 | 2020-08-04 |  |  |  |  | 2020-08-24 | [8 empty] | Q4 2020 | Fully Executed Interconnection Agreement | Yes | 2020-09-21 | Cluster 08 - Sturtevant-Leeds-Livermore-Ludden-Riley - 1 | Livermore Falls | NC | 2020-11-20 |  | EXECUTED/ENERGIZED
134 | 0 | 0 | 0 |  | 2019-09-26 | Wales | MONMOUTH | 457D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Monmouth |  |  |  | WITHDRAWN
135 | 0 | 0 | 0 |  | 2019-09-26 | Wales | MONMOUTH | 457D1 | Solar | 4500 | 0 |  |  |  |  | 2020-09-09 | 2020-11-12 |  |  |  |  | 2021-06-04 | [9 empty] | Fully Executed Interconnection Agreement | Yes | 2021-10-21 | N/A | Monmouth | NC | 2021-02-25 |  | EXECUTED
136 | 0 | 0 | 0 |  | 2019-09-26 | Wales | MONMOUTH | 457D1 | Solar | 0 | 0 | [10 empty] | 2021-11-05 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | N/A | Monmouth | NC | 2021-11-23 |  | RE_QUEUED_FullEx
137 | 0 | 0 | 0 |  | 2019-09-26 | Wales | MONMOUTH | 457D1 | Solar | 0 | 0 | [10 empty] | 2021-11-05 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | N/A | Monmouth | NC | 2021-11-23 | Not Required | EXECUTED-WITHDRAWN
138 | 0 | 0 | 0 |  | 2019-09-26 | Naples | BRIDGTON 34 KV | 406D4 | Solar | 0 | 0 | [10 empty] | 2020-11-10 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 03 - Kimball Rd-Lovell - 1 | Kimball Road/Lovell | 3 | 2023-04-27 |  | RE_QUEUED_FullEx
139 | 0 | 0 | 0 |  | 2019-09-27 | Limerick | LIMERICK | 632D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Kimball Road/Lovell |  |  |  | WITHDRAWN
140 | 0 |  | 0 |  | 2019-09-27 | Guilford | GUILFORD | 821D1 | Solar | 999 | 0 |  |  |  |  | 2020-08-05 | 2020-10-08 | 2021-01-04 | 2021-02-03 |  |  | 2021-07-09 | 2023-08-23 | 2024-07-29 | 2024-03-21 |  | 2024-05-22 |  |  |  | Q3 2025 | Fully Executed Interconnection Agreement | Yes | 2024-06-03 | Cluster 06 - Detroit-Guilford-Belfast - 1 | Guilford | 3 | 2023-08-31 | Not Required | RE_QUEUED_FullEx
141 | 0 | 0 | 0 |  | 2019-09-27 | China | SOUTH CHINA | 244D2 | Solar/Battery | 4478 | 2250 |  |  |  |  | 2020-05-01 | 2020-07-06 |  |  |  |  | 2020-07-24 | [8 empty] | Q4 2020 | Fully Executed Interconnection Agreement | Yes | 2021-05-24 | Cluster 01 - Augusta - 1 | Augusta E/Puddledock/Bowman St | 3 | 2021-01-04 |  | EXECUTED/ENERGIZED
142 | 0 | 0 | 0 |  | 2019-09-27 | Union | UNION | 251D1 | Solar | 4875 | 0 |  |  |  |  | 2019-11-05 | 2020-01-15 |  |  |  |  | 2020-05-11 | [8 empty] | Q4 2020 | Fully Executed Interconnection Agreement | Yes | 2020-10-08 | Cluster 09 - Midcoast - 1 | Coopers Mills | NC | 2020-07-14 |  | EXECUTED/ENERGIZED
143 | 0 | 0 | 0 |  | 2019-09-27 | Poland | HOTEL ROAD | 420D4 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Hotel Rd/Gulf/Middle St/Crowleys |  |  |  | WITHDRAWN
144 | 0 | 0 | 0 |  | 2019-10-01 | Union | UNION | 251D1 | Solar | 2000 | 0 |  |  |  |  | 2020-06-10 | 2020-08-13 |  |  |  |  | 2020-09-23 | 2022-11-10 | [7 empty] | Q4 2020 | Fully Executed Interconnection Agreement | Yes | 2022-09-16 | Cluster 09 - Midcoast - 1 | Coopers Mills | NC | 2021-03-30 |  | EXECUTED
145 | 0 | 0 | 0 |  | 2019-10-01 | Woodstock | BRYANT POND | 407D1 | Solar/Battery | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Woodstock |  |  |  | WITHDRAWN
146 | 0 | 0 | 0 |  | 2019-10-01 | Oxford | OXFORD | 437D1 | Solar/Battery | 4290 | 0 |  |  |  |  | 2019-11-14 | 2020-01-23 |  |  |  |  | 2020-02-13 | [8 empty] | Q4 2020 | Fully Executed Interconnection Agreement | Yes | 2020-09-10 | Cluster 05 - Lewiston Loop - 1 | Norway | 0 | 2020-07-14 |  | EXECUTED/ENERGIZED
147 | 0 | 0 | 0 |  | 2019-10-01 | Limington | NORTH LIMINGTON | 638D1 | Solar/Battery | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Kimball Road/Lovell |  |  |  | WITHDRAWN
148 | 0 | 0 | 0 |  | 2019-10-01 | Rockport | MEADOW ROAD | 270D1 | Solar | 2125 | 0 |  |  |  |  | 2019-12-05 | 2020-02-04 |  |  |  |  | 2020-02-18 | [8 empty] | Q3 2020 | Fully Executed Interconnection Agreement | Yes | 2020-09-13 | Cluster 09 - Midcoast - 1 | Meadow Road | 0 | 2020-04-28 |  | EXECUTED/ENERGIZED
149 | 0 | 0 | 0 |  | 2019-10-01 | Limington | NORTH LIMINGTON | 638D1 | Solar | 0 | 0 | [10 empty] | 2020-08-21 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 03 - Kimball Rd-Lovell - 1 | Kimball Road/Lovell | 3 | 2023-04-27 |  | EXECUTED-WITHDRAWN
150 | 0 | 0 | 0 |  | 2019-10-01 | Baldwin | HIRAM TAP | 692D1 | Solar | 4875 | 0 | 2019-11-14 | 2019-12-16 | 2019-12-27 | 2020-01-28 |  |  | 2020-03-31 | 2020-05-14 |  |  | 2020-05-05 | [8 empty] | Q4 2020 | Fully Executed Interconnection Agreement | Yes | 2020-08-10 | Cluster 03 - Kimball Rd-Lovell - 1 | Kimball Road/Lovell | NC | 2020-07-14 |  | EXECUTED/ENERGIZED
151 | 0 |  | 0 |  | 2019-10-01 | Harrison | KIMBALL ROAD | 423D2 | Solar | 999 | 0 |  |  |  |  | 2020-06-24 | 2020-08-27 | 2024-04-17 | 2024-05-30 |  |  | 2020-09-09 | 2023-08-28 | 2023-10-10 | 2024-01-12 | 2024-03-18 |  |  |  |  | Q4 2025 | Fully Executed Interconnection Agreement | Yes | 2023-12-11 | Cluster 03 - Kimball Rd-Lovell - 1 | Kimball Road/Lovell | 3 | Not Required | Not Required | RE_QUEUED_FullEx
152 | 0 | 0 | 0 |  | 2019-10-02 | Leeds | LEEDS | 471D2 | Solar | 4999 | 0 |  |  |  |  | 2020-09-29 | 2020-12-04 | 2021-10-01 | 2021-11-12 | 2021-08-10 |  | 2021-11-20 | [9 empty] | Fully Executed Interconnection Agreement | Yes | 2023-10-05 | Cluster 08 - Sturtevant-Leeds-Livermore-Ludden-Riley - 1 | Leeds | 3 | 2023-12-21 |  | EXECUTED
153 | 0 | 0 | 0 |  | 2019-10-02 | Norridgewock | SKOWHEGAN TAP | 864D1 | Solar | 4999 | 0 |  |  |  |  | 2019-12-10 | 2020-02-14 |  |  |  |  | 2020-03-26 | [8 empty] | Q1 2021 | Fully Executed Interconnection Agreement | Yes | 2020-07-22 | Cluster 02 - Winslow-County Rd-Lakewood -1 | Lakewood | NC | 2020-06-25 |  | EXECUTED/ENERGIZED
154 | 0 | 0 | 0 |  | 2019-10-02 | Norridgewock | SKOWHEGAN SOUTH SIDE | 854D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Lakewood |  |  |  | WITHDRAWN
155 | 0 | 0 | 0 |  | 2019-10-03 | Windham | GRAY | 416D3 | Solar/Battery | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Elm St |  |  |  | WITHDRAWN
156 | 0 | 0 | 0 |  | 2019-10-04 | Standish | SHAWS MILL ROAD | 660D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Raymond | NC |  |  | WITHDRAWN
157 | 0 | 0 | 0 |  | 2019-10-04 | Farmington | STURTEVANT | 858D1A | Solar | 0 | 0 |  |  |  |  | 2020-01-20 | [15 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Sturtevant |  |  |  | WITHDRAWN
158 | 0 | 0 | 0 |  | 2019-10-04 | Farmington | STURTEVANT | 858D1A | Solar | 0 | 0 | [10 empty] | 2021-05-17 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 08 - Sturtevant-Leeds-Livermore-Ludden-Riley - 1 | Sturtevant | 3 | 2023-12-21 |  | RE_QUEUED_FullEx/ENERGIZED
159 | 0 | 0 | 0 |  | 2019-10-04 | Plymouth | NEWPORT | 837D2 | Solar/Battery | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Detroit |  |  |  | WITHDRAWN
160 | 0 | 0 | 0 |  | 2019-10-04 | Plymouth | NEWPORT | 837D2 | Solar/Battery | 0 | 0 | [10 empty] | 2021-05-28 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 06 - Detroit-Guilford-Belfast - 1 | Detroit | 3 |  | 2023-08-23 | EXECUTED-WITHDRAWN
161 | 0 | 0 | 0 |  | 2019-10-07 | Biddeford | BIDDEFORD INDUSTRIAL PARK | 673D1 | Solar | 700 | 0 |  |  |  |  | 2020-04-02 | 2020-06-08 |  |  |  |  | 2020-06-16 | [8 empty] | Q4 2020 | Fully Executed Interconnection Agreement | Yes | 2020-08-17 | Cluster 14 - Louden-Biddeford IP - 1 | Biddeford IP | 0 |  | Not Required | EXECUTED/ENERGIZED
162 | 0 | 0 | 0 |  | 2019-10-07 | Washington | STICKNEYS CORNER | 245D2 | Solar/Battery | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Coopers Mills |  |  |  | WITHDRAWN
163 | 0 | 0 | 0 |  | 2019-10-07 | Windsor | COOPERS MILLS ROAD | 230D1 | Solar | 2000 | 0 |  |  |  |  | 2019-12-23 | 2020-02-27 |  |  |  |  | 2020-04-06 | [8 empty] | Q2 2021 | Fully Executed Interconnection Agreement | Yes | 2020-08-19 | Cluster 09 - Midcoast - 1 | Coopers Mills | NC | 2020-07-14 |  | EXECUTED/ENERGIZED
164 | 0 | 0 | 0 |  | 2019-10-08 | Ripley | DEXTER | 813D3 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Guilford |  |  |  | WITHDRAWN
165 | 0 | 0 | 0 |  | 2019-10-08 | Monmouth | MONMOUTH | 457D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Monmouth |  |  |  | WITHDRAWN
166 | 0 | 0 | 0 |  | 2019-10-08 | Standish | SHAWS MILL ROAD | 660D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Detroit |  |  |  | WITHDRAWN
167 | 0 | 0 | 0 |  | 2019-10-08 | Etna | CARMEL | 808D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Detroit | NC |  |  | WITHDRAWN
168 | 0 | 0 | 0 |  | 2019-10-08 | Topsham | TOPSHAM 34 KV | 250D2 | Solar/Battery | 4990 | 4990 |  |  |  |  | 2019-12-05 | 2020-02-04 |  |  |  |  | 2020-03-02 | [8 empty] | Q2 2021 | Fully Executed Interconnection Agreement | Yes | 2020-08-24 | Cluster 09 - Midcoast - 1 | Topsham | 0 | 2020-04-28 |  | EXECUTED/ENERGIZED
169 | 0 | 0 | 0 |  | 2019-10-09 | Etna | CARMEL | 808D1 | Solar | 0 | 0 | [10 empty] | 2021-05-07 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 06 - Detroit-Guilford-Belfast - 1 | Detroit | 3 |  | 2023-08-23 | EXECUTED-WITHDRAWN
170 | 0 | 0 | 0 |  | 2019-10-09 | South Paris | NORWAY | 435D3 | Solar | 4950 | 0 |  |  |  |  | 2019-11-14 | 2020-01-23 |  |  |  |  | 2020-04-07 | 2022-08-09 | 2022-09-20 | [6 empty] | Q4 2021 | Fully Executed Interconnection Agreement | Yes | 2022-11-28 | Cluster 05 - Lewiston Loop - 1 | Hotel Rd/Gulf/Middle St/Crowleys/Norway | 3 | 2022-07-19 |  | #REF!
171 | 0 | 0 | 0 |  | 2019-10-09 | Naples | BRIDGTON | 406D2 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Kimball Road/Lovell |  |  |  | WITHDRAWN
172 | 0 | 0 | 0 |  | 2019-10-15 | Acton | BUTLER'S CORNER | 612D2 | Solar | 3450 | 0 |  |  |  |  | 2019-12-18 | 2020-05-18 | 2020-04-09 |  |  |  | 2020-06-02 | [8 empty] | Q1 2021 | Fully Executed Interconnection Agreement | Yes | 2020-07-09 | Cluster 04 - Sanford-Quaker Hill - 1 | Sanford | NC | 2020-07-14 |  | #REF!
173 | 0 | 0 | 0 |  | 2019-10-15 | Benton | WINSLOW | 870D1 | Solar/Battery | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A |  |  |  |  | WITHDRAWN
174 | 0 | 0 | 0 |  | 2019-10-15 | Belfast | BELFAST WEST SIDE | 803D5 | Solar | 4750 | 3000 | 2019-11-25 | 2019-12-24 | 2020-01-09 | 2020-02-07 |  |  | 2020-03-31 | 2020-05-14 |  |  | 2020-04-30 | [8 empty] | Q4 2020 | Fully Executed Interconnection Agreement | Yes | 2020-07-23 | Cluster 06 - Detroit-Guilford-Belfast - 1 | Belfast | NC | 2020-06-25 |  | EXECUTED/ENERGIZED
175 | 0 | 0 | 0 |  | 2019-10-15 | Bowdoin | TOPSHAM 34 KV | 250D1 | Solar/Battery | 3638 | 2000 |  |  |  |  | 2020-03-24 | 2020-05-28 |  |  |  |  | 2020-06-19 | [8 empty] | Q4 2020 | Fully Executed Interconnection Agreement | Yes | 2020-10-08 | Cluster 09 - Midcoast - 1 | Topsham | NC | 2020-07-30 |  | EXECUTED/ENERGIZED
176 | 0 | 0 | 0 |  | 2019-10-15 | Gorham | SPRING STREET | 668D5 | Solar | 4875 | 0 |  |  |  |  | 2019-12-11 | 2020-02-17 |  |  |  |  | 2020-05-12 | [8 empty] | Q3 2020 | Fully Executed Interconnection Agreement | Yes | 2020-10-08 | Cluster 15 - Greater Portland - 1 | Spring St | NC | 2020-07-30 |  | EXECUTED/ENERGIZED
177 | 0 | 0 | 0 |  | 2019-10-15 | Carmel | CARMEL | 808D3 | Solar | 0 | 0 | [10 empty] | 2022-05-23 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 17 - Detroit Guilford Belfast - 2 | Detroit | 3 |  |  | EXECUTED-WITHDRAWN
178 | 0 | 0 | 0 |  | 2019-10-15 | Paris | NORWAY | 435D3 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 05 - Lewiston Loop - 1 | Hotel Rd/Gulf/Middle St/Crowleys/Norway | 3 |  | 2022-07-22 | WITHDRAWN
179 | 0 | 0 | 0 |  | 2019-10-15 | Leeds | MONMOUTH | 457D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Monmouth |  |  |  | WITHDRAWN
180 | 0 | 0 | 0 |  | 2019-10-15 | Buxton | BAR MILLS | 678D2 | Solar | 2400 | 0 |  |  |  |  | 2019-12-23 | 2020-02-27 |  |  |  |  | 2020-03-19 | [8 empty] | Q3 2020 | Fully Executed Interconnection Agreement | Yes | 2020-08-10 | Cluster 14 - Louden-Biddeford IP - 1 | West Buxton | 0 | 2020-04-28 |  | EXECUTED/ENERGIZED
181 | 0 | 0 | 0 |  | 2019-10-15 | Knox | UNITY | 860D2 | Solar | 1500 | 0 |  |  |  |  | 2020-02-20 | 2020-04-24 |  |  |  |  | 2020-06-17 | [8 empty] | Q4 2020 | Fully Executed Interconnection Agreement | Yes | 2020-07-06 | Cluster 06 - Detroit-Guilford-Belfast - 1 | Belfast | NC | 2020-07-30 |  | EXECUTED/ENERGIZED
182 | 0 | 0 | 0 |  | 2019-10-15 | Skowhegan | WESTON HYDRO | 866D2 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Lakewood |  |  |  | WITHDRAWN
183 | 0 | 0 | 0 |  | 2019-10-15 | Fairfield | FAIRFIELD | 817D1 | Solar | 4980 | 0 |  |  |  |  | 2019-12-11 | 2020-02-17 |  |  |  |  | 2020-04-16 | [8 empty] | Q3 2021 | Fully Executed Interconnection Agreement | Yes | 2022-01-05 | Cluster 02 - Winslow-County Rd-Lakewood -1 | Winslow-County Rd | 3 | 2021-12-17 |  | EXECUTED/ENERGIZED
184 | 0 | 0 | 0 |  | 2019-10-15 | Skowhegan | SKOWHEGAN TAP | 864D1 | Solar | 1453 | 0 |  |  |  |  | 2020-05-01 | 2020-07-07 | 2020-10-21 | 2020-12-18 | 2020-08-28 | 2020-09-02 | 2021-12-02 | [8 empty] | Q4 2021 | Fully Executed Interconnection Agreement | Yes | 2022-09-16 | Cluster 02 - Winslow-County Rd-Lakewood -1 | Lakewood | 3 | 2021-12-17 |  | EXECUTED
185 | 0 | 0 | 0 |  | 2019-10-15 | Skowhegan | SKOWHEGAN TAP | 864D1 | Solar | 996 | 0 |  |  |  |  | 2022-01-24 | 2022-03-28 |  |  |  |  | 2022-07-29 | [8 empty] | Q3 2025 | Fully Executed Interconnection Agreement | Yes | 2023-06-16 | Cluster XX - Winslow/ County Rd/ Lakewood - TBD | Lakewood | 3 |  | Not Required | EXECUTED
186 | 0 | 0 | 0 |  | 2019-10-15 | Wiscasset | MAINE YANKEE | 274D1 | Solar | 4950 | 0 |  |  |  |  | 2020-05-01 | 2020-07-06 | 2021-06-24 | 2021-07-12 |  |  | 2020-08-18 | [8 empty] | Q3 2020 | Fully Executed Interconnection Agreement | Yes | 2021-10-26 | Cluster 09 - Midcoast - 1 | Maine Yankee | NC | 2020-10-05 |  | EXECUTED/ENERGIZED
187 | 0 | 0 | 0 |  | 2019-10-15 | Farmington | STURTEVANT | 858D1A | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Sturtevant |  |  |  | WITHDRAWN
188 | 0 | 0 | 0 |  | 2019-10-17 | Naples | BRIDGTON 34 KV | 406D4 | Solar | 0 | 0 | [10 empty] | 2021-12-30 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 03 - Kimball Rd-Lovell - 1 | Kimball Road/Lovell | 3 | 2023-04-27 |  | EXECUTED-WITHDRAWN
189 | 0 | 0 | 0 |  | 2019-10-17 | Wiscasset | MESSINA | 238D1 | Solar | 4950 | 0 |  |  |  |  | 2020-04-02 | 2020-06-08 |  |  |  |  | 2020-07-23 | [8 empty] | Q4 2020 | Fully Executed Interconnection Agreement | Yes | 2021-08-19 | Cluster 09 - Midcoast - 1 | Mason | 0 | 2020-08-31 |  | EXECUTED/ENERGIZED
190 | 0 | 0 | 0 |  | 2019-10-17 | Pittsfield | PITTSFIELD | 842D1 | Solar | 0 | 0 | [10 empty] | 2020-07-23 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 06 - Detroit-Guilford-Belfast - 1 | Detroit | 3 | 2023-08-31 |  | EXECUTED
191 | 0 | 0 | 0 |  | 2019-10-17 | Waldoboro | WALDOBORO | 252D2 | Solar | 4950 | 0 |  |  |  |  | 2020-06-04 | 2020-08-07 |  |  |  |  | 2020-10-27 | [8 empty] | Q4 2020 | Fully Executed Interconnection Agreement | Yes | 2021-08-17 | Cluster 09 - Midcoast - 1 | Highland/Park St | NC | 2021-03-30 |  | EXECUTED/ENERGIZED
192 | 0 | 0 | 0 |  | 2019-10-17 | Dover-Foxcroft | DOVER | 815D2 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Guilford |  |  |  | WITHDRAWN
193 | 0 | 0 | 0 |  | 2019-10-17 | Monmouth | MONMOUTH | 457D2 | Solar/Battery | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Monmouth |  |  |  | WITHDRAWN
194 | 0 | 0 | 0 |  | 2019-10-18 | Starks | ANSON | 801D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Winslow/ County Rd/ Lakewood - TBD | Lakewood |  |  |  | WITHDRAWN
195 | 0 | 0 | 0 |  | 2019-10-18 | Augusta | BLAIR ROAD | 207D2 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Augusta E/Puddledock/Bowman St |  |  |  | WITHDRAWN
196 | 0 | 0 | 0 |  | 2019-10-18 | Skowhegan | WESTON HYDRO | 866D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Lakewood |  |  |  | WITHDRAWN
197 | 0 | 0 | 0 |  | 2019-10-18 | Skowhegan | WESTON HYDRO | 866D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Lakewood |  |  |  | WITHDRAWN
198 | 0 | 0 | 0 |  | 2019-10-21 | Lisbon | LISBON | 231D2 | Solar | 0 | 0 | [10 empty] | 2020-05-18 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 05 - Lewiston Loop - 1 | Hotel Rd/Gulf/Middle St/Crowleys/Norway | 3 | 2022-07-19 |  | EXECUTED
199 | 0 | 0 | 0 |  | 2019-10-21 | Oxford | OXFORD | 437D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Norway |  |  |  | WITHDRAWN
200 | 0 | 0 | 0 |  | 2019-10-21 | Livermore | LEEDS | 471D1 | Solar | 999 | 0 |  |  |  |  | 2022-01-04 | 2022-03-02 |  |  |  |  | 2022-03-21 |  |  | 2024-03-12 | 2024-05-16 |  |  |  |  | Q4 2023 | Fully Executed Interconnection Agreement | No | 2025-03-24 | Cluster XX - Sturtevant/ Leeds/ Livermore/ Ludden/ Riley_TBD | Leeds | 3 |  | Not Required | RE_QUEUED_FullEx
201 | 0 | 0 | 0 |  | 2019-10-21 | Troy | UNITY | 860D1 | Solar | 995 | 0 |  |  |  |  | 2020-08-07 | 2020-10-13 | 2023-04-18 | 2023-06-01 | 2022-11-11 | 2023-02-09 | 2020-11-08 | 2022-07-19 | 2022-08-30 | 2023-04-19 | 2023-06-01 |  |  |  |  | Q2 2025 | Fully Executed Interconnection Agreement | Yes | 2023-06-20 | Cluster 06 - Detroit-Guilford-Belfast - 1 | Belfast | 3 |  | Not Required | RE_QUEUED_FullEx
202 | 0 | 0 | 0 |  | 2019-10-21 | Windham | SWETT ROAD | 682D2 | Solar/Battery | 0 | [11 empty] | 2020-07-24 | [8 empty] | Q3 2021 | EXECUTED-WITHDRAWN | WITHDRAWN | 2021-05-04 | Cluster 07 - Raymond - 1 | Raymond | 3 | 2023-12-21 |  | EXECUTED
203 | 0 | 0 | 0 |  | 2019-10-21 | Searsport | SEARSPORT | 850D1 | Solar/Battery | 4990 | 4990 |  |  |  |  | 2019-11-20 | 2020-01-29 |  |  |  |  | 2020-03-02 | [8 empty] | Q2 2021 | Fully Executed Interconnection Agreement | Yes | 2020-10-08 | Cluster 06 - Detroit-Guilford-Belfast - 1 | Belfast | NC | 2020-04-28 |  | EXECUTED/ENERGIZED
204 | 0 | 0 | 0 |  | 2019-10-22 | Farmington | STURTEVANT | 858D1A | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Sturtevant |  |  |  | WITHDRAWN
205 | 0 | 0 | 201 |  | 2019-10-22 | Thorndike | UNITY | 860D2 | Solar | 996 | [5 empty] | 2020-12-02 | 2021-02-08 |  |  |  |  | 2021-06-21 | 2023-06-21 |  | 2023-08-22 | [5 empty] | Q4 2021 | Fully Executed Interconnection Agreement | Yes | 2023-03-13 | Cluster 06 - Detroit-Guilford-Belfast - 1 | Belfast | 3 |  | Not Required | RE_QUEUED_FullEx
206 | 0 | 0 | 0 |  | 2019-10-22 | North Berwick | PRATT & WHITNEY | 661D1 | Solar | 4999 | 0 |  |  |  |  | 2020-05-18 | 2020-07-22 |  |  |  |  | 2020-08-04 | [8 empty] | Q3 2021 | Fully Executed Interconnection Agreement | Yes | 2021-03-15 | Cluster 04 - Sanford-Quaker Hill - 1 | Pratt & Whitney | NC | 2020-10-05 |  | EXECUTED/ENERGIZED
207 | 0 | 0 | 0 |  | 2019-10-23 | Athens | ATHENS | 827D2 | Solar | 4400 | 0 |  |  |  |  | 2020-02-03 | 2020-04-08 |  |  |  |  | 2020-04-13 | [8 empty] | Q4 2021 | Fully Executed Interconnection Agreement | Yes | 2020-07-22 | Cluster 16 - Wyman Area - 1 | Athens | 0 | 2020-06-25 |  | EXECUTED/ENERGIZED
208 | 0 | 0 | 0 |  | 2019-10-23 | Augusta | CONY ROAD | 216D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Augusta E/Puddledock/Bowman St |  |  |  | WITHDRAWN
209 | 0 | 0 | 0 |  | 2019-10-23 | Farmingdale | BROWNS CROSSING | 211D2 | Solar | 4850 | 0 |  |  |  |  | 2020-03-05 | 2020-05-08 |  |  |  |  | 2020-05-15 | [8 empty] | Q3 2020 | Fully Executed Interconnection Agreement | Yes | 2020-07-22 | Cluster 11 - Augusta E-Puddledock-Bowman St - 2 | Browns Crossing | 0 | 2020-07-14 |  | EXECUTED/ENERGIZED
210 | 0 | 0 | 0 |  | 2019-10-23 | Palmyra | DETROIT | 812D2 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Detroit |  |  |  | WITHDRAWN
211 | 0 | 0 | 0 |  | 2019-10-23 | Palmyra | NEWPORT | 837D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Detroit |  |  |  | WITHDRAWN
212 | 0 | 0 | 0 |  | 2019-10-23 | Augusta | BOND BROOK | 208D3 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Augusta E/Puddledock/Bowman St |  |  |  | WITHDRAWN
213 | 0 | 0 | 0 |  | 2019-10-23 | Randolph | BOWMAN STREET | 263D1 | Solar | 4990 | [5 empty] | 2019-12-05 | 2020-02-04 |  |  |  |  | 2020-02-13 | [9 empty] | Fully Executed Interconnection Agreement | Yes | 2021-05-05 | Cluster 01 - Augusta - 1 | Augusta E/Puddledock/Bowman St | 3 | 2021-01-04 |  | EXECUTED/ENERGIZED
214 | 0 | 0 | 0 |  | 2019-10-23 | Gardiner | GARDINER | 226D2 | Solar | 875 | 0 |  |  |  |  | 2019-11-25 | 2020-01-31 |  |  |  |  | 2020-03-02 | [8 empty] | Q4 2020 | Fully Executed Interconnection Agreement | Yes | 2020-09-17 | Cluster 11 - Augusta E-Puddledock-Bowman St - 2 | Augusta E/Puddledock/Bowman St | 0 |  | Not Required | EXECUTED/ENERGIZED
215 | 0 | 0 | 0 |  | 2019-10-25 | Durham | LISBON FALLS | 232D2 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Hotel Rd/Gulf/Middle St/Crowleys |  |  |  | WITHDRAWN
216 | 0 | 0 | 0 |  | 2019-10-25 | Vassalboro | MCCOYS | 237D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Augusta E/Puddledock/Bowman St |  |  |  | WITHDRAWN
217 | 0 | 0 | 0 |  | 2019-10-25 | Westbrook | SPRING STREET | 668D5 | Solar | 4990 | 0 |  |  |  |  | 2020-06-02 | 2020-08-04 |  |  |  |  | 2020-08-18 | [8 empty] | Q4 2021 | Fully Executed Interconnection Agreement | Yes | 2021-07-14 | Cluster 15 - Greater Portland - 1 | Spring St | NC | 2020-12-14 |  | EXECUTED
218 | 0 | 0 | 0 |  | 2019-10-25 | Jay | RILEY | 449D2 | Solar | 4950 | 0 |  |  |  |  | 2019-12-05 | 2020-02-04 |  |  |  |  | 2020-06-16 | [8 empty] | Q4 2020 | Fully Executed Interconnection Agreement | Yes | 2020-07-20 | Cluster 08 - Sturtevant-Leeds-Livermore-Ludden-Riley - 1 | Riley | 0 | 2020-07-14 |  | EXECUTED/ENERGIZED
219 | 0 | 0 | 0 |  | 2019-10-25 | Benton | CLINTON | 810D1 | Solar | 4450 | 0 |  |  |  |  | 2019-12-16 | 2020-02-20 |  |  |  |  | 2020-04-03 | [8 empty] | Q2 2021 | Fully Executed Interconnection Agreement | Yes | 2022-01-20 | Cluster 02 - Winslow-County Rd-Lakewood -1 | Winslow-County Rd | 3 | 2021-12-17 |  | EXECUTED/ENERGIZED
220 | 0 | 0 | 0 |  | 2019-10-25 | Warren | WARREN | 253D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Highland/Park St |  |  |  | WITHDRAWN
221 | 0 | 0 | 0 |  | 2019-10-28 | Gardiner | GARDINER | 226D2 | Solar | 3250 | 0 |  |  |  |  | 2020-02-12 | 2020-04-14 |  |  |  |  | 2020-04-27 | [8 empty] | Q4 2020 | Fully Executed Interconnection Agreement | Yes | 2021-05-26 | Cluster 01 - Augusta - 1 | Augusta E/Puddledock/Bowman St | 3 | 2021-01-04 |  | EXECUTED/ENERGIZED
222 | 0 | 0 | 0 |  | 2019-10-28 | Topsham | TOPSHAM 34 KV | 250D1 | Solar/Battery | 0 | 0 | [10 empty] | 2021-01-12 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 09 - Midcoast - 1 | Topsham | NC | 2021-03-30 |  | EXECUTED-WITHDRAWN
223 | 0 | 0 | 0 |  | 2019-10-28 | South Paris | PARIS TAP | 409D1 | Solar/Battery | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Woodstock |  |  |  | WITHDRAWN
224 | 0 | 0 | 0 |  | 2019-10-28 | West Paris | PARIS TAP | 409D1 | Solar/Battery | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Woodstock |  |  |  | WITHDRAWN
225 | 0 | 0 | 0 |  | 2019-10-28 | Mechanic Falls | MECHANIC FALLS | 431D3 | Solar | 0 | 0 | [10 empty] | 2020-04-08 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 05 - Lewiston Loop - 1 | Hotel Rd/Gulf/Middle St/Crowleys/Norway | 3 | 2022-07-19 |  | RE_QUEUED_FullEx
226 | 0 | 0 | 0 |  | 2019-10-28 | Minot | MECHANIC FALLS | 431D2 | Solar | 0 | 0 | [10 empty] | 2020-08-05 | [8 empty] | Q4 2020 | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 05 - Lewiston Loop - 1 | Hotel Rd/Gulf/Middle St/Crowleys/Norway | 3 | 2022-07-19 |  | RE_QUEUED_FullEx
227 | 0 | 0 | 0 |  | 2019-10-29 | Skowhegan | WESTON HYDRO | 866D1 | Solar | 4950 | 0 |  |  |  |  | 2020-03-20 | 2020-05-27 |  |  |  |  | 2020-06-19 | [8 empty] | Q4 2021 | Fully Executed Interconnection Agreement | Yes | 2020-07-17 | Cluster 02 - Winslow-County Rd-Lakewood -1 | Lakewood | 3 | 2021-12-17 |  | EXECUTED/ENERGIZED
228 | 0 | 0 | 0 |  | 2019-10-29 | Paris | PARIS TAP | 409D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Woodstock |  |  |  | WITHDRAWN
229 | 0 | 0 | 0 |  | 2019-10-29 | Madison | SKOWHEGAN NORTH SIDE | 853D1 | Solar | 4000 | 0 |  |  |  |  | 2020-08-14 | 2020-10-20 |  |  |  |  | 2020-10-29 | [9 empty] | Fully Executed Interconnection Agreement | Yes | 2022-01-19 | Cluster 02 - Winslow-County Rd-Lakewood -1 | Lakewood | 3 | 2021-12-17 |  | EXECUTED/ENERGIZED
230 | 0 | 0 | 0 |  | 2019-10-29 | Parkman | GUILFORD | 821D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 17 - Detroit Guilford Belfast - 2 | Guilford | 3 |  |  | WITHDRAWN
231 | 0 | 0 | 0 |  | 2019-10-31 | North Berwick | PRATT & WHITNEY | 661D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Pratt & Whitney |  |  |  | WITHDRAWN
232 | 0 | 0 | 0 |  | 2019-09-20 | Berwick | BASSETT | 602D3 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Quaker Hill |  |  |  | WITHDRAWN
233 | 0 | 0 | 0 |  | 2019-11-01 | Sweden | LOVELL | 430D1 | Solar/Battery | 0 | 0 | [10 empty] | 2020-11-03 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 03 - Kimball Rd-Lovell - 1 | Kimball Road/Lovell | 3 |  | 2023-04-22 | EXECUTED-WITHDRAWN
234 | 0 | 0 | 0 |  | 2019-11-01 | Sweden | LOVELL | 430D1 | Solar/Battery | 0 | 0 | [10 empty] | 2021-07-08 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 03 - Kimball Rd-Lovell - 1 | Kimball Road/Lovell | 3 |  | 2023-04-22 | EXECUTED-WITHDRAWN
235 | 0 | 0 | 0 |  | 2019-11-04 | West Paris | TRAP CORNER | 453D1 | Solar | 2500 | 0 |  |  |  |  | 2020-05-01 | 2020-07-06 |  |  |  |  | 2020-07-13 | [8 empty] | Q4 2021 | Fully Executed Interconnection Agreement | Yes | 2020-08-17 | Cluster 10 - Roxbury-Rumford-Woodstock - 1 | Woodstock | NC | 2020-10-05 |  | EXECUTED/ENERGIZED
236 | 0 | 0 | 0 |  | 2019-11-06 | Benton | WINSLOW | 870D1 | Solar/Battery | 873 | [5 empty] | 2020-07-28 | 2020-09-30 | 2020-11-17 | 2020-01-06 |  |  | 2021-01-19 | [8 empty] | Q4 2020 | Fully Executed Interconnection Agreement | Yes | 2021-06-09 | Cluster 02 - Winslow-County Rd-Lakewood -1 | Winslow-County Rd | 3 |  | Not Required | EXECUTED/ENERGIZED
237 | 0 | 0 | 0 |  | 2019-11-07 | Denmark | DENMARK | 413D1 | Solar/Battery | 0 | 0 | [10 empty] | 2020-05-27 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 03 - Kimball Rd-Lovell - 1 | Kimball Road/Lovell | 3 |  | 2023-04-22 | 0
238 | 0 | 0 | 0 |  | 2019-11-07 | Manchester | MANCHESTER | 233D1 | Solar/Battery | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Augusta E/Puddledock/Bowman St |  |  |  | WITHDRAWN
239 | 0 | 0 | 0 |  | 2019-11-07 | Cornish | HIRAM TAP | 692D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Kimball Road/Lovell |  |  |  | WITHDRAWN
240 | 0 | 0 | 0 |  | 2019-11-07 | Searsport | SEARSPORT | 850D2 | Solar/Battery | 0 | 0 | [10 empty] | 2020-06-16 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 06 - Detroit-Guilford-Belfast - 1 | Belfast | 3 |  | 2023-08-23 | EXECUTED-WITHDRAWN
241 | 0 | 0 | 0 |  | 2019-11-07 | Benton | WINSLOW | 870D1 | Solar | 0 | 0 | [10 empty] | 2021-07-13 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 12 - Winslow-County Rd-Lakewood - 2 | Winslow-County Rd | 3 | 2024-05-28 |  | EXECUTED-WITHDRAWN
242 | 0 | 0 | 0 |  | 2019-11-07 | Benton | WINSLOW | 870D1 | Solar | 0 | 0 | [10 empty] | 2021-07-13 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 12 - Winslow-County Rd-Lakewood - 2 | Winslow-County Rd | 3 | 2023-12-04 | Not Required | EXECUTED-WITHDRAWN
243 | 0 | 0 | 0 |  | 2019-11-07 | Benton | WINSLOW | 870D1 | Solar/Battery | 0 | 0 | [10 empty] | 2021-12-08 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster XX - Winslow/ County Rd/ Lakewood - TBD | Winslow-County Rd | 3 | 2023-12-04 |  | EXECUTED-WITHDRAWN
244 | 0 | 0 | 0 |  | 2019-11-07 | Searsport | SEARSPORT | 850D2 | Solar/Battery | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Belfast |  |  |  | WITHDRAWN
245 | 0 | 0 | 0 |  | 2019-11-07 | Starks | ANSON | 801D1 | Solar | 1800 | 0 |  |  |  |  | 2020-01-30 | 2020-04-01 | 2020-04-24 | 2020-06-04 |  |  | 2020-07-06 | [8 empty] | Q4 2021 | Fully Executed Interconnection Agreement | Yes | 2020-09-07 | Cluster 02 - Winslow-County Rd-Lakewood -1 | Lakewood | 3 | 2021-12-17 |  | EXECUTED/ENERGIZED
246 | 0 | 0 | 0 |  | 2019-11-07 | Dexter | DEXTER | 813D1 | Solar | 0 | 0 | [10 empty] | 2020-08-18 | [8 empty] | Q4 2021 | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 06 - Detroit-Guilford-Belfast - 1 | Guilford | 3 | 2023-08-31 |  | RE_QUEUED_STUDY
247 | 0 | 0 | 0 |  | 2019-11-07 | North Anson | NORTH ANSON | 838D1 | Solar | 2000 | 0 |  |  |  |  | 2020-02-03 | 2020-04-08 |  |  |  |  | 2020-06-04 | [8 empty] | Q4 2021 | Fully Executed Interconnection Agreement | Yes | 2022-05-10 | Cluster 02 - Winslow-County Rd-Lakewood -1 | Lakewood | 3 | 2021-12-17 |  | EXECUTED
248 | 0 | 0 | 0 |  | 2019-11-07 | Westbrook | SPRING STREET | 668D5 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Spring St |  |  |  | WITHDRAWN
249 | 0 | 0 | 0 |  | 2019-11-07 | Skowhegan | SKOWHEGAN NORTH SIDE | 853D2 | Solar | 0 | 0 | [10 empty] | 2021-09-16 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 12 - Winslow-County Rd-Lakewood - 2 | Lakewood | 3 | 2024-05-28 |  | EXECUTED-WITHDRAWN
250 | 0 | 0 | 0 |  | 2019-11-12 | Augusta | BOND BROOK | 208D3 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Augusta E/Puddledock/Bowman St |  |  |  | WITHDRAWN
251 | 0 | 0 | 0 |  | 2019-11-12 | Farmington | FARMINGTON FALLS | 818D2 | Solar | 0 | 0 | [10 empty] | 2020-03-20 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 08 - Sturtevant-Leeds-Livermore-Ludden-Riley - 1 | Sturtevant | NC | 2020-06-25 |  | EXECUTED-WITHDRAWN
252 | 0 | 0 | 0 |  | 2019-11-13 | Berwick | BERWICK | 603D2 | Solar | 3562 | 0 |  |  |  |  | 2019-12-05 | 2020-02-04 |  |  |  |  | 2020-03-24 | [8 empty] | Q4 2020 | Fully Executed Interconnection Agreement | Yes | 2020-08-12 | Cluster 04 - Sanford-Quaker Hill - 1 | Quaker Hill | 0 | 2020-06-25 |  | EXECUTED/ENERGIZED
253 | 0 | 0 | 0 |  | 2019-11-13 | Naples | RAYMOND 115 KV | 445D2 | Solar | 0 | 0 | [10 empty] | 2020-08-04 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 07 - Raymond - 1 | Raymond | 3 | 2023-12-21 |  | EXECUTED-WITHDRAWN
254 | 0 | 0 | 0 |  | 2019-11-13 | Sidney | SOUTH WATERVILLE | 855D2 | Solar | 1950 | 0 |  |  |  |  | 2020-01-27 | 2020-04-01 |  |  |  |  | 2020-05-20 | [8 empty] | Q4 2021 | Fully Executed Interconnection Agreement | Yes | 2020-06-30 | Cluster 02 - Winslow-County Rd-Lakewood -1 | Winslow-County Rd | 3 | 2021-12-17 |  | EXECUTED/ENERGIZED
255 | 0 | 0 | 0 |  | 2019-11-13 | Gorham | FORT HILL | 624D2 | Solar | 0 | 0 | [10 empty] | 2021-06-24 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 07 - Raymond - 1 | Raymond | 3 |  | 2023-12-15 | EXECUTED-WITHDRAWN
256 | 0 | 0 | 0 |  | 2019-11-13 | Rockport | MEADOW ROAD | 270D2 | Solar | 3550 | 0 |  |  |  |  | 2020-04-08 | 2020-06-11 |  |  |  |  | 2020-06-12 | [8 empty] | Q4 2020 | Fully Executed Interconnection Agreement | Yes | 2020-07-23 | Cluster 09 - Midcoast - 1 | Meadow Road | NC | 2020-08-31 |  | EXECUTED/ENERGIZED
257 | 0 | 0 | 0 |  | 2019-11-13 | Hallowell | MANCHESTER | 233D2 | Solar/Battery | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 01 - Augusta - 1 | Augusta E/Puddledock/Bowman St | 3 |  | December | WITHDRAWN
258 | 0 | 0 | 0 |  | 2019-11-13 | Sabattus | CROWLEYS | 411D1 | Solar | 4900 | 0 |  |  |  |  | 2020-03-26 | 2020-06-02 |  |  |  |  | 2020-06-19 | [9 empty] | Fully Executed Interconnection Agreement | Yes | 2020-07-22 | Cluster 05 - Lewiston Loop - 1 | Hotel Rd/Gulf/Middle St/Crowleys/Norway | 3 | 2022-07-19 |  | EXECUTED/ENERGIZED
259 | 0 | 0 | 0 |  | 2019-11-13 | St Albans | HARTLAND | 824D2 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Hartland | NC |  |  | WITHDRAWN
260 | 0 | 0 | 0 |  | 2019-11-14 | Parsonfield | HIRAM TAP | 692D1 | Solar | 0 | 0 | [10 empty] | 2020-09-11 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 03 - Kimball Rd-Lovell - 1 | Kimball Road/Lovell | 3 | 2023-04-27 |  | EXECUTED-WITHDRAWN
261 | 0 | 0 | 0 |  | 2019-11-14 | Eustis | STRATTON | 877D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Bigelow |  |  |  | WITHDRAWN
262 | 0 | 0 | 0 |  | 2019-11-18 | Jay | LIVERMORE FALLS | 428D1 | Solar | 0 | 0 | [10 empty] | 2021-03-10 | [8 empty] | Q3 2020 | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 08 - Sturtevant-Leeds-Livermore-Ludden-Riley - 1 | Livermore Falls | NC | 2021-07-15 |  | EXECUTED
263 | 0 | 0 | 0 |  | 2019-11-18 | Monmouth | MONMOUTH | 457D3 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Monmouth |  |  |  | WITHDRAWN
264 | 0 | 0 | 0 |  | 2019-11-18 | Strong | PHILLIPS/STRONG | 841D1 | Solar | 4990 | 0 |  |  |  |  | 2020-02-25 | 2020-04-29 |  |  |  |  | 2020-05-06 | [8 empty] | Q3 2021 | Fully Executed Interconnection Agreement | Yes | 2020-09-13 | Cluster 08 - Sturtevant-Leeds-Livermore-Ludden-Riley - 1 | Sturtevant | NC | 2020-08-31 |  | EXECUTED/ENERGIZED
265 | 0 | 0 | 0 |  | 2019-11-19 | Oakland | OAKLAND | 839D1 | Solar | 2375 | 0 |  |  |  |  | 2020-09-08 | 2020-11-11 |  |  |  |  | 2021-05-28 | 2022-10-13 | 2022-10-10 | [6 empty] | Q4 2020 | Fully Executed Interconnection Agreement | Yes | 2023-05-24 | Cluster 02 - Winslow-County Rd-Lakewood -1 | Winslow-County Rd | 3 | 2021-12-17 |  | EXECUTED
266 | 0 | 0 | 0 |  | 2019-11-19 | Newcastle | DAMARISCOTTA MILLS | 219D2 | Solar/Battery | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Newcastle |  |  |  | WITHDRAWN
267 | 0 | 0 | 0 |  | 2019-11-19 | Wales | MONMOUTH | 457D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Monmouth |  |  |  | WITHDRAWN
268 | 0 |  | 0 |  | 2019-11-19 | Corinna | CORINNA | 811D1 | Solar | 4950 | 0 |  |  |  |  | 2020-04-02 | 2020-06-08 |  |  |  | 2023-04-26 | 2020-07-23 | 2022-09-06 | 2022-10-18 | [6 empty] | Q4 2020 | Fully Executed Interconnection Agreement | No | 2024-10-24 | Cluster 06 - Detroit-Guilford-Belfast - 1 | Detroit | 3 | 2023-08-31 |  | RE_QUEUED_FullEx
269 | 0 | 0 | 0 |  | 2019-11-20 | Paris | NORWAY | 435D3 | Solar/Battery | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Norway |  |  |  | WITHDRAWN
270 | 0 | 0 | 0 |  | 2019-11-20 | Vassalboro | VASSALBORO | 861D8 | Solar | 3300 | 0 |  |  |  |  | 2020-01-27 | 2020-03-30 |  | 2022-07-19 |  |  | 2020-04-17 | 2022-07-11 | 2022-07-20 | 2022-10-18 | 2022-11-04 | 2023-05-01 | 2023-06-13 |  |  | Q1 2022 | Fully Executed Interconnection Agreement | Yes | 2020-09-28 | Cluster 02 - Winslow-County Rd-Lakewood -1 | Winslow-County Rd | 3 | 2021-12-17 |  | RE_QUEUED_FullEx/ENERGIZED
271 | 0 | 0 | 0 |  | 2019-11-21 | Sabattus | SABATTUS | 450D1 | Solar | 900 | 0 |  |  |  |  | 2020-01-07 | 2020-03-10 | 2020-05-01 | 2020-06-01 |  |  | 2020-06-16 | [9 empty] | Fully Executed Interconnection Agreement | Yes | 2020-08-04 | Cluster 05 - Lewiston Loop - 1 | Hotel Rd/Gulf/Middle St/Crowleys/Norway | 0 |  | Not Required | EXECUTED
272 | 0 | 0 | 0 |  | 2019-11-22 | Greenville | MONSON | 834D2 | Solar | 0 | 0 | [10 empty] | 2020-05-18 | [8 empty] | Q4 2021 | EXECUTED-WITHDRAWN | No | 2020-08-17 | Cluster 06 - Detroit-Guilford-Belfast - 1 | Guilford | 3 | 2023-08-31 |  | EXECUTED
273 | 0 | 0 | 0 |  | 2019-11-22 | Bethel | BETHEL | 403D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Woodstock |  |  |  | WITHDRAWN
274 | 0 | 0 | 0 |  | 2019-11-22 | Carmel | CARMEL | 808D2 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Detroit |  |  |  | WITHDRAWN
275 | 0 | 0 | 0 |  | 2019-11-25 | Sidney | SIDNEY | 242D1 | Solar | 2000 | 0 |  |  |  |  | 2020-02-21 | 2020-04-27 |  |  |  |  | 2020-06-18 | [8 empty] | Q4 2021 | Fully Executed Interconnection Agreement | Yes | 2020-06-06 | Cluster 01 - Augusta - 1 | Augusta E/Puddledock/Bowman St | 3 | 2021-01-04 |  | EXECUTED/ENERGIZED
276 | 0 | 0 | 0 |  | 2019-11-25 | Gorham | MOSHERS | 635D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Moshers |  |  |  | WITHDRAWN
277 | 0 | 0 | 0 |  | 2019-11-26 | China | SOUTH CHINA | 244D2 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Augusta E-Puddledock-Bowman St - TBD | Augusta E/Puddledock/Bowman St | 3 |  |  | WITHDRAWN
278 | 0 | 0 | 0 |  | 2019-11-26 | New Gloucester | HOTEL ROAD | 420D7 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Hotel Rd/Gulf/Middle St/Crowleys |  |  |  | WITHDRAWN
279 | 0 | 0 | 0 |  | 2019-11-26 | Unity | UNITY | 860D2 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Belfast |  |  |  | WITHDRAWN
280 | 0 | 0 | 0 |  | 2019-11-26 | Unity | UNITY | 860D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Belfast |  |  |  | WITHDRAWN
281 | 0 | 0 | 270 |  | 2019-11-26 | Winslow | VASSALBORO | 861D9 | Solar | 4125 | 0 |  |  |  |  | 2020-06-04 | 2020-08-07 | 2020-09-24 | 2020-11-10 |  |  | 2021-06-16 | 2022-08-10 | 2022-09-12 | 2022-11-15 | 2022-12-22 | 2023-08-04 | 2023-09-19 |  |  |  | Fully Executed Interconnection Agreement | Yes | 2022-08-17 | Cluster 02 - Winslow-County Rd-Lakewood -1 | Winslow-County Rd | 3 | 2021-12-17 |  | RE_QUEUED_FullEx
282 | 0 | 0 | 0 |  | 2019-11-26 | Harmony | ATHENS | 827D2 | Solar | 4910 | 0 |  |  |  |  | 2020-05-15 | 2020-07-15 |  |  |  |  | 2020-09-04 | [9 empty] | Fully Executed Interconnection Agreement | Yes | 2020-08-27 | Cluster 16 - Wyman Area - 1 | Athens | NC | 2020-10-05 |  | EXECUTED/ENERGIZED
283 | 0 | 0 | 0 |  | 2019-11-26 | Denmark | DENMARK | 413D2 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Kimball Road/Lovell |  |  |  | WITHDRAWN
284 | 0 | 0 | 0 |  | 2019-11-26 | Auburn | HOTEL ROAD | 420D4 | Solar/Battery | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 18 - Lewiston Loop - 2 | Hotel Rd/Gulf/Middle St/Crowleys/Norway | 3 |  |  | WITHDRAWN
285 | 0 | 0 | 0 |  | 2019-11-26 | Sanford | SOUTH SANFORD | 667D2 | Solar/Battery | 0 | 0 | [10 empty] | 2020-08-04 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 04 - Sanford-Quaker Hill - 1 | Sanford | 3 | 2022-10-19 |  | EXECUTED-WITHDRAWN
286 | 0 | 0 | 0 |  | 2019-12-02 | Winslow | WINSLOW | 870D1 | Solar/Battery | 0 | 0 | [10 empty] | 2022-03-25 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster XX - Winslow/ County Rd/ Lakewood - TBD | Winslow-County Rd | 3 |  |  | EXECUTED-WITHDRAWN
287 | 0 | 0 | 0 |  | 2019-12-02 | Oxford | NORWAY | 435D1 | Solar | 3000 | 0 |  |  |  |  | 2020-10-05 | 2020-12-10 |  |  |  |  | 2021-06-17 | 2023-01-10 | 2023-02-20 | [6 empty] | Q4 2021 | Fully Executed Interconnection Agreement | Yes | 2023-02-15 | Cluster 05 - Lewiston Loop - 1 | Hotel Rd/Gulf/Middle St/Crowleys/Norway | 3 | 2022-07-19 |  | RE_QUEUED_FullEx/ENERGIZED
288 | 0 | 0 | 0 |  | 2019-12-03 | Skowhegan | SKOWHEGAN NORTH SIDE | 853D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Winslow/ County Rd/ Lakewood - TBD | Lakewood | 3 |  |  | WITHDRAWN
289 | 0 | 0 | 0 |  | 2019-12-03 | Skowhegan | SKOWHEGAN NORTH SIDE | 853D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Winslow/ County Rd/ Lakewood - TBD | Lakewood | 3 |  |  | WITHDRAWN
290 | 0 | 0 | 0 |  | 2019-12-03 | Woolwich | WOOLWICH | 258D1 | Solar | 4999 | 0 |  |  |  |  | 2020-01-13 | 2020-03-16 |  |  |  |  | 2020-05-27 | [8 empty] | Q4 2020 | Fully Executed Interconnection Agreement | Yes | 2020-09-15 | Cluster 09 - Midcoast - 1 | Bath | 0 | 2020-07-14 |  | EXECUTED/ENERGIZED
291 | 0 | 0 | 0 |  | 2019-12-04 | Bridgton | BRIDGTON 34 KV | 406D4 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Kimball Road/Lovell |  |  |  | WITHDRAWN
292 | 0 | 0 | 0 |  | 2019-12-04 | Wells | PRATT & WHITNEY | 661D2 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Pratt & Whitney |  |  |  | WITHDRAWN
293 | 0 | 0 | 0 |  | 2019-12-12 | Berwick | BASSETT | 602D2 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Quaker Hill |  |  |  | WITHDRAWN
294 | 0 | 0 | 0 |  | 2019-12-12 | Leeds | LEEDS | 471D2 | Solar/Battery | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Leeds |  |  |  | WITHDRAWN
295 | 0 | 0 | 0 |  | 2019-12-20 | Waterford | PAPOOSE POND | 438D1 | Solar/Battery | 0 | 0 | [10 empty] | 2020-05-14 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 03 - Kimball Rd-Lovell - 1 | Kimball Road/Lovell | 3 |  | 2023-04-22 | EXECUTED-WITHDRAWN
296 | 0 | 0 | 0 |  | 2019-12-20 | Mechanic Falls | MECHANIC FALLS | 431D2 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Hotel Rd/Gulf/Middle St/Crowleys/Norway |  |  |  | WITHDRAWN
297 | 0 | 0 | 0 |  | 2019-12-20 | Waterboro | WATERBORO | 671D1 | Solar | 4875 | 0 |  |  |  |  | 2020-01-10 | 2020-03-17 |  |  |  |  | 2020-04-22 | [8 empty] | Q4 2021 | Fully Executed Interconnection Agreement | Yes | 2020-07-14 | Cluster 04 - Sanford-Quaker Hill - 1 | Waterboro | 0 | 2020-06-25 |  | EXECUTED/ENERGIZED
298 | 0 | 0 | 0 |  | 2019-12-20 | Norridgewock | SKOWHEGAN SOUTH SIDE | 854D1 | Solar | 4999 | 0 |  |  |  |  | 2020-03-02 | 2020-04-02 |  |  |  |  | 2020-05-14 | [8 empty] | Q4 2021 | Fully Executed Interconnection Agreement | Yes | 2021-10-21 | Cluster 02 - Winslow-County Rd-Lakewood -1 | Lakewood | 3 | 2021-12-17 |  | EXECUTED
299 | 0 | 0 | 0 |  | 2020-01-07 | Auburn | HOTEL ROAD | 420D4 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 18 - Lewiston Loop - 2 | Hotel Rd/Gulf/Middle St/Crowleys/Norway | 3 |  |  | WITHDRAWN
300 | 0 | 0 | 0 |  | 2020-01-07 | Palmyra | DETROIT | 812D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Detroit |  |  |  | WITHDRAWN
301 | 0 | 0 | 0 |  | 2020-01-07 | Chelsea | CONY ROAD | 216D2 | Solar | 4999 | 0 |  |  |  |  | 2020-03-02 | 2020-05-05 |  |  |  |  | 2020-05-12 | [8 empty] | Q3 2021 | Fully Executed Interconnection Agreement | Yes | 2020-09-13 | Cluster 01 - Augusta - 1 | Augusta E/Puddledock/Bowman St | 3 | 2021-01-04 |  | EXECUTED/ENERGIZED
302 | 0 | 0 | 0 |  | 2020-01-07 | Poland | MECHANIC FALLS | 431D3 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Norway |  |  |  | WITHDRAWN
303 | 0 | 0 | 0 |  | 2020-01-09 | Kingfield | STURTEVANT | 858D2 | Solar | 0 | 0 | [10 empty] | 2021-12-23 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster XX - Sturtevant/ Leeds/ Livermore/ Ludden/ Riley_TBD | Sturtevant | 3 |  |  | EXECUTED-WITHDRAWN
304 | 0 | 0 | 0 |  | 2020-01-09 | New Portland | STURTEVANT | 858D2 | Solar | 0 | 0 | [10 empty] | 2022-06-28 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster XX - Sturtevant/ Leeds/ Livermore/ Ludden/ Riley_TBD | Sturtevant | 3 |  | Not Required | RE_QUEUED_FullEx
305 | 0 | 0 | 0 |  | 2020-01-09 | Rangeley | RANGELEY | 875D2 | Solar | 3000 | 0 |  |  |  |  | 2020-04-09 | 2020-06-10 | 2021-03-05 |  |  |  | 2020-08-04 | [8 empty] | Q4 2021 | Fully Executed Interconnection Agreement | Yes | 2022-04-14 | Cluster 10 - Roxbury-Rumford-Woodstock - 1 | Roxbury | 0 | 2020-08-31 |  | EXECUTED
306 | 0 | 0 | 0 |  | 2020-01-09 | Corinna | CORINNA | 811D1 | Solar | 0 | 0 | [10 empty] | 2021-07-14 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 06 - Detroit-Guilford-Belfast - 1 | Detroit | 3 | 2023-08-31 |  | RE_QUEUED_FullEx
307 | 0 | 0 | 0 |  | 2020-01-10 | Livermore Falls | LIVERMORE FALLS | 428D2 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 08 - Sturtevant-Leeds-Livermore-Ludden-Riley - 1 | Livermore Falls | 3 |  | 2023-12-15 | WITHDRAWN
308 | 0 | 0 | 0 |  | 2020-01-15 | Dexter | DEXTER | 813D1 | Solar | 995 | 0 | 2020-09-09 | 2020-11-11 | 2020-12-08 | 2021-01-22 | [6 empty] | 2021-08-30 |  |  | 2024-11-22 | 2025-01-29 | 2025-08-20 | 2025-10-24 |  |  | Q1 2025 | Fully Executed Interconnection Agreement | No | 2024-06-04 | Cluster 06 - Detroit-Guilford-Belfast - 1 | Guilford | 3 | 2023-08-31 |  | RE_QUEUED_FullEx
309 | 0 | 0 | 0 |  | 2020-01-15 | Dexter | DEXTER | 813D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 17 - Detroit Guilford Belfast - 2 | Guilford | 3 |  |  | WITHDRAWN
310 | 0 | 0 | 0 |  | 2020-01-17 | Winthrop | WINTHROP | 256D3 | Solar | 0 | 0 | [10 empty] | 2021-06-15 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 11 - Augusta E-Puddledock-Bowman St - 2 | Augusta E/Puddledock/Bowman St | 3 | 2024-05-28 |  | EXECUTED-WITHDRAWN
311 | 0 | 0 | 0 |  | 2020-01-17 | Whitefield | COOPERS MILLS ROAD | 230D2 | Solar | 990 | 0 |  |  |  |  | 2020-05-15 | 2020-07-20 | 2020-08-28 | 2020-10-09 |  |  | 2020-12-01 | [9 empty] | Fully Executed Interconnection Agreement | Yes | 2021-02-16 | Cluster 09 - Midcoast - 1 | Coopers Mills | NC |  | Not Required | EXECUTED/ENERGIZED
312 | 0 | 0 | 0 |  | 2020-01-17 | Naples | NAPLES TAP | 469D1 | Solar | 0 | 0 | [10 empty] | 2020-08-26 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 07 - Raymond - 1 | Raymond | 3 | 2023-12-21 |  | EXECUTED
313 | 0 | 0 | 0 |  | 2020-01-17 | Starks | ANSON | 801D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Winslow/ County Rd/ Lakewood - TBD | Lakewood |  |  |  | WITHDRAWN
314 | 0 | 0 | 0 |  | 2020-01-21 | Augusta | BLAIR ROAD | 207D2 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 01 - Augusta - 1 | Augusta E/Puddledock/Bowman St | 3 |  | 2022-03-21 | WITHDRAWN
315 | 0 | 0 | 0 |  | 2020-01-21 | Poland | MECHANIC FALLS | 431D3 | Solar/Battery | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 05 - Lewiston Loop - 1 | Hotel Rd/Gulf/Middle St/Crowleys/Norway | 3 |  | 2022-07-22 | WITHDRAWN
316 | 0 | 0 | 0 |  | 2020-01-21 | Augusta | NORTH AUGUSTA | 272D4 | Solar | 999 | 0 |  |  |  |  | 2020-07-27 | 2020-09-29 |  |  |  |  | 2020-11-03 | [9 empty] | Fully Executed Interconnection Agreement | Yes | 2021-07-01 | Cluster 11 - Augusta E-Puddledock-Bowman St - 2 | North Augusta | NC |  | Not Required | EXECUTED/ENERGIZED
317 | 0 | 0 | 0 |  | 2020-01-24 | Norway | NORWAY | 435D3 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Norway | 0 |  |  | WITHDRAWN
318 | 0 | 0 | 0 |  | 2020-01-24 | Monson | MONSON | 834D1 | Solar | 0 | 0 | [10 empty] | 2020-10-05 | [8 empty] | Q3 2025 | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 06 - Detroit-Guilford-Belfast - 1 | Guilford | 3 |  | Not Required | RE_QUEUED_FullEx
319 | 0 | 0 | 0 |  | 2020-01-24 | Windham | RAYMOND 34 KV | 444D3 | Solar | 0 | 0 | [10 empty] | 2020-10-27 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 07 - Raymond - 1 | Raymond | 3 | 2023-12-21 |  | EXECUTED-WITHDRAWN
320 | 0 | 0 | 0 |  | 2020-01-24 | Kittery | BRAGDON COMMONS | 689D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Quaker Hill |  |  |  | WITHDRAWN
321 | 0 | 0 | 0 |  | 2020-01-24 | Waterboro | WATERBORO | 671D2 | Solar | 4998 | 0 |  |  |  |  | 2020-05-22 | 2020-07-28 |  |  |  |  | 2020-09-04 | [9 empty] | Fully Executed Interconnection Agreement | Yes | 2021-01-20 | Cluster 04 - Sanford-Quaker Hill - 1 | Waterboro | NC | 2020-10-05 |  | EXECUTED/ENERGIZED
322 | 0 | 0 | 0 |  | 2020-01-24 | Mercer | SKOWHEGAN TAP | 864D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Winslow/ County Rd/ Lakewood - TBD | Lakewood | 3 |  |  | WITHDRAWN
323 | 0 | 0 | 0 |  | 2020-01-24 | Hartland | HARTLAND | 824D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Hartland | NC |  |  | WITHDRAWN
324 | 0 | 0 | 0 |  | 2020-01-24 | Union | UNION | 251D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Coopers Mills |  |  |  | WITHDRAWN
325 | 0 | 0 | 0 |  | 2020-01-27 | Lewiston | DEER RIPS | 412D4 | Solar | 0 | 0 | [10 empty] | 2021-02-16 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 05 - Lewiston Loop - 1 | Hotel Rd/Gulf/Middle St/Crowleys/Norway | 3 | 2022-07-19 |  | EXECUTED-WITHDRAWN
326 | 0 | 0 | 0 |  | 2020-01-27 | Limington | NORTH LIMINGTON | 638D1 | Solar | 0 | 0 | [10 empty] | 2020-11-05 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 03 - Kimball Rd-Lovell - 1 | Kimball Road/Lovell | 3 | 2023-04-27 |  | Decision due 9/4
327 | 0 | 0 | 0 |  | 2020-01-27 | Gorham | SPRING STREET | 668D5 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Spring St |  |  |  | WITHDRAWN
328 | 0 | 0 | 0 |  | 2020-01-27 | Sanford | SANFORD INDUSTRIAL PARK | 656D3 | Solar | 4998 | 0 |  |  |  |  | 2020-06-23 | 2020-08-25 |  |  |  |  | 2020-09-29 | [9 empty] | Fully Executed Interconnection Agreement | Yes | 2021-07-16 | Cluster 04 - Sanford-Quaker Hill - 1 | Sanford | 3 | 2022-06-27 |  | EXECUTED/ENERGIZED
329 | 0 | 0 | 0 |  | 2020-01-27 | Auburn | DEER RIPS | 412D1 | Solar | 0 | 0 | [10 empty] | 2021-08-17 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 18 - Lewiston Loop - 2 | Hotel Rd/Gulf/Middle St/Crowleys/Norway | 3 |  |  | EXECUTED-WITHDRAWN
330 | 0 | 0 | 0 |  | 2020-01-27 | South Berwick | BASSETT | 602D3 | Solar | 4000 | 0 |  |  |  |  | 2020-06-09 | 2020-08-12 |  |  |  |  | 2020-09-11 | [9 empty] | Fully Executed Interconnection Agreement | Yes | 2020-10-21 | Cluster 04 - Sanford-Quaker Hill - 1 | Quaker Hill | NC | 2021-03-30 |  | EXECUTED/ENERGIZED
331 | 0 | 0 | 0 |  | 2020-01-28 | Skowhegan | WESTON HYDRO | 866D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Lakewood | NA |  |  | WITHDRAWN
332 | 0 | 0 | 0 |  | 2020-01-28 | Anson | NORTH ANSON | 838D1 | Solar | 4000 | 0 |  |  |  |  | 2020-07-06 | 2020-09-08 |  |  |  |  | 2020-10-19 | [8 empty] | Q2 2021 | Fully Executed Interconnection Agreement | Yes | 2022-03-09 | Cluster 02 - Winslow-County Rd-Lakewood -1 | Lakewood | 3 | 2021-12-17 |  | EXECUTED
333 | 0 | 0 | 0 |  | 2020-01-28 | Old Orchard Beach | GOOSEFARE | 630D4 | Solar | 4700 | 0 |  |  |  |  | 2020-05-05 | 2020-07-09 |  |  |  |  | 2020-07-16 | [8 empty] | Q3 2021 | Fully Executed Interconnection Agreement | Yes | 2020-08-04 | Cluster 14 - Louden-Biddeford IP - 1 | Louden | NC | 2021-03-30 |  | EXECUTED/ENERGIZED
334 | 0 | 0 | 0 |  | 2020-01-28 | Winslow | VASSALBORO | 861D9 | Solar | 0 | 0 | [10 empty] | 2021-10-26 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 12 - Winslow-County Rd-Lakewood - 2 | Winslow-County Rd | 3 | 2024-05-28 |  | EXECUTED-WITHDRAWN
335 | 0 | 0 | 0 |  | 2020-01-30 | Mercer | SKOWHEGAN TAP | 864D1 | Solar/Battery | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Winslow/ County Rd/ Lakewood - TBD | Lakewood | 3 |  |  | WITHDRAWN
336 | 0 | 0 | 0 |  | 2020-01-30 | Vassalboro | MCCOYS | 237D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Augusta E/Puddledock/Bowman St |  |  |  | WITHDRAWN
337 | 0 | 0 | 0 |  | 2020-01-30 | Vassalboro | MCCOYS | 237D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Augusta E/Puddledock/Bowman St |  |  |  | WITHDRAWN
338 | 0 | 0 | 0 |  | 2020-01-31 | Sandy River Plantation | SADDLEBACK | 876D1 | Solar | 4890 | 0 |  |  |  |  | 2020-04-23 | 2020-06-25 |  |  |  |  | 2020-09-16 | [8 empty] | Q4 2020 | Fully Executed Interconnection Agreement | Yes | 2020-09-25 | Cluster 10 - Roxbury-Rumford-Woodstock - 1 | Roxbury | NC | 2020-08-31 |  | EXECUTED/ENERGIZED
339 | 0 | 0 | 0 |  | 2020-02-03 | Dover-Foxcroft | DOVER | 815D2 | Solar | 0 | 0 | [10 empty] | 2020-09-02 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 06 - Detroit-Guilford-Belfast - 1 | Guilford | 3 | 2023-08-31 |  | EXECUTED
340 | 0 | 0 | 0 |  | 2020-02-03 | Farmington | STURTEVANT | 858D4 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Sturtevant/ Leeds/ Livermore/ Ludden/ Riley_TBD | Sturtevant | 3 |  |  | WITHDRAWN
341 | 0 | 0 | 0 |  | 2020-02-03 | Limington | NORTH LIMINGTON | 638D2 | Solar | 996 | 0 |  |  |  |  | 2020-12-14 | 2021-02-19 |  |  |  |  | 2021-05-26 | 2024-05-21 | 2024-07-26 | 2024-11-01 | 2025-01-29 |  |  |  |  | Q2 2025 | Fully Executed Interconnection Agreement | No | 2023-08-31 | Cluster 03 - Kimball Rd-Lovell - 1 | Kimball Road/Lovell | 3 | 2023-04-27 |  | RE_QUEUED_STUDY
342 | 0 | 0 | 0 |  | 2020-02-03 | Waterboro | WATERBORO | 671D2 | Solar | 4998 | 0 |  |  |  |  | 2020-10-23 | 2020-12-30 |  |  |  |  | 2021-06-14 | [9 empty] | Fully Executed Interconnection Agreement | Yes | 2022-04-07 | Cluster 04 - Sanford-Quaker Hill - 1 | Waterboro | 3 | 2022-06-27 |  | EXECUTED
343 | 0 | 0 | 0 |  | 2020-02-05 | Bristol | BRISTOL | 210D2 | Solar | 4899 | 0 |  |  |  |  | 2020-03-06 | 2020-05-11 |  |  |  |  | 2020-05-21 | [8 empty] | Q4 2021 | Fully Executed Interconnection Agreement | Yes | 2020-10-05 | Cluster 09 - Midcoast - 1 | Newcastle | NC | 2020-07-30 |  | EXECUTED/ENERGIZED
344 | 0 | 0 | 0 |  | 2020-02-05 | Embden | EMBDEN | 868D1 | Solar | 4999 | 0 |  |  |  |  | 2020-03-25 | 2020-05-29 |  |  |  |  | 2020-06-01 | [8 empty] | Q4 2021 | Fully Executed Interconnection Agreement | Yes | 2020-10-16 | Cluster 16 - Wyman Area - 1 | Embden | 0 | 2020-07-30 |  | EXECUTED/ENERGIZED
345 | 0 | 0 | 0 |  | 2020-02-05 | Orland | BUCKSPORT | 806D2 | Solar/Battery | 0 | 0 | [10 empty] | 2020-07-24 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 06 - Detroit-Guilford-Belfast - 1 | Bucksport | NC | 2020-10-05 |  | EXECUTED-WITHDRAWN
346 | 0 | 0 | 0 |  | 2020-02-06 | Winslow | VASSALBORO | 861D9 | Solar/Battery | 0 | 0 | [10 empty] | 2021-12-21 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster XX - Winslow/ County Rd/ Lakewood - TBD | Winslow-County Rd | 3 |  |  | EXECUTED-WITHDRAWN
347 | 0 | 0 | 0 |  | 2020-02-07 | Oxford | OXFORD | 437D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Norway |  |  |  | WITHDRAWN
348 | 0 | 0 | 0 |  | 2020-02-07 | Winthrop | WINTHROP | 256D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Augusta E-Puddledock-Bowman St - TBD | Augusta E/Puddledock/Bowman St |  |  |  | WITHDRAWN
349 | 0 | 0 | 0 |  | 2020-02-07 | Limerick | LIMERICK | 632D1 | Solar | 4998 | 0 |  |  |  |  | 2020-06-09 | 2020-08-11 |  |  |  |  | 2020-09-04 | [8 empty] | Q2 2021 | Fully Executed Interconnection Agreement | No | 2022-04-25 | Cluster 03 - Kimball Rd-Lovell - 1 | Kimball Road/Lovell | 3 | 2023-04-27 |  | EXECUTED
350 | 0 | 0 | 0 |  | 2020-02-12 | Winthrop | MANCHESTER | 233D2 | Solar | 995 | 0 |  |  |  |  | 2020-12-18 | 2021-06-11 | 2024-06-06 | 2024-07-24 |  | 2024-07-19 | 2021-11-24 | 2023-01-26 |  | 2023-06-14 | 2023-07-20 | 2023-10-27 | 2023-12-13 | 2024-02-14 | 2024-04-19 | Q4 2025 | Fully Executed Interconnection Agreement | No | 2024-11-18 | Cluster 11 - Augusta E-Puddledock-Bowman St - 2 | Augusta E/Puddledock/Bowman St | 3 | 2024-05-28 | Not Required | RE_QUEUED_RESULTS
351 | 0 | 0 | 0 |  | 2020-02-14 | Augusta | NORTH AUGUSTA | 272D4 | Solar | 0 | 0 | [10 empty] | 2021-07-01 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 11 - Augusta E-Puddledock-Bowman St - 2 | North Augusta | 3 | 2024-05-28 |  | EXECUTED
352 | 0 | 0 | 0 |  | 2020-02-14 | Windsor | COOPERS MILLS ROAD | 230D1 | Solar | 0 | 0 | [10 empty] | 2021-07-01 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 09 - Midcoast - 1 | Coopers Mills | 3 | 2023-12-21 |  | EXECUTED-WITHDRAWN
353 | 0 | 0 | 0 |  | 2020-02-14 | Sidney | SIDNEY | 242D1 | Solar | 1500 | 0 |  |  |  |  | 2020-07-06 | 2020-09-08 |  |  |  |  | 2020-12-08 | [8 empty] | Q1 2021 | Fully Executed Interconnection Agreement | Yes | 2022-04-01 | Cluster 01 - Augusta - 1 | Augusta E/Puddledock/Bowman St | 3 | 2021-01-04 |  | EXECUTED/ENERGIZED
354 | 0 | 0 | 0 |  | 2020-02-19 | Casco | RAYMOND 115 KV | 445D2 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Raymond |  |  |  | WITHDRAWN
355 | 0 | 0 | 0 |  | 2020-02-19 | Belfast | BELFAST 115 | 874D1 | Solar | 4999 | 0 |  |  |  |  | 2020-04-17 | 2020-06-19 |  |  |  |  | 2020-07-15 | 2022-08-23 | 2022-10-05 | [6 empty] | Q4 2021 | Fully Executed Interconnection Agreement | Yes | 2022-12-09 | Cluster 06 - Detroit-Guilford-Belfast - 1 | Belfast | 3 | 2023-05-31 |  | RE_QUEUED_FullEx
356 | 0 | 0 | 0 |  | 2020-02-19 | Farmington | STURTEVANT | 858D4 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Sturtevant/ Leeds/ Livermore/ Ludden/ Riley_TBD | Sturtevant | 3 |  |  | WITHDRAWN
357 | 0 | 0 | 0 |  | 2020-02-20 | Cumberland | ELM STREET | 620D1 | Solar/Battery | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Elm St |  |  |  | WITHDRAWN
358 | 0 | 0 | 0 |  | 2020-02-21 | Belfast | BELFAST WEST SIDE | 803D3 | Solar | 3500 | 0 |  |  |  |  | 2020-06-09 | 2020-08-12 | 2020-09-24 | 2020-11-09 |  |  | 2020-11-14 | [8 empty] | Q4 2020 | Fully Executed Interconnection Agreement | Yes | 2022-12-07 | Cluster 06 - Detroit-Guilford-Belfast - 1 | Belfast | 3 | 2023-05-31 |  | EXECUTED
359 | 0 | 0 | 0 |  | 2020-02-21 | Damariscotta | DAMARISCOTTA MILLS | 219D1 | Solar | 0 | 0 | [10 empty] | 2020-11-12 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 09 - Midcoast - 1 | Newcastle | 3 | 2023-12-21 |  | RE_QUEUED_FullEx
360 | 0 | 0 | 0 |  | 2020-02-24 | Waterville | SOUTH WATERVILLE | 855D2 | Solar | 3500 | [5 empty] | 2020-07-24 | 2020-09-28 |  |  |  |  | 2020-10-20 | [9 empty] | Fully Executed Interconnection Agreement | Yes | 2022-06-10 | Cluster 02 - Winslow-County Rd-Lakewood -1 | Winslow-County Rd | 3 | 2021-12-17 |  | EXECUTED/ENERGIZED
361 | 0 | 0 | 0 |  | 2020-02-24 | South Berwick | BASSETT | 602D3 | Solar/Battery | 0 | 0 | [10 empty] | 2021-02-18 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 04 - Sanford-Quaker Hill - 1 | Quaker Hill | 3 | 2022-06-27 |  | EXECUTED-WITHDRAWN
362 | 0 | 0 | 0 |  | 2020-02-25 | Waterboro | WATERBORO | 671D2 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Waterboro |  |  |  | WITHDRAWN
363 | 0 | 0 | 0 |  | 2020-02-25 | Windsor | COOPERS MILLS ROAD | 230D1 | Solar | 0 | 0 | [10 empty] | 2021-12-13 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster XX - Midcoast - TBD | Coopers Mills | 3 |  |  | EXECUTED-WITHDRAWN
364 | 0 | 0 | 0 |  | 2020-02-25 | Buxton | BONNY EAGLE | 610D2 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Kimball Rd/ Lovell - TBD | Kimball Road/Lovell | 3 |  |  | WITHDRAWN
365 | 0 | 0 | 0 |  | 2020-02-25 | Bethel | LOCKES MILLS | 429D1 | Solar | 2997 | 0 |  |  |  |  | 2020-04-15 | 2020-06-19 |  |  |  |  | 2020-07-01 | [8 empty] | Q4 2021 | Fully Executed Interconnection Agreement | Yes | 2020-08-25 | Cluster 10 - Roxbury-Rumford-Woodstock - 1 | Woodstock | NC | 2020-08-31 |  | EXECUTED/ENERGIZED
366 | 0 | 0 | 0 |  | 2020-02-28 | Edgecomb | EDGECOMB | 223D1 | Solar | 4950 | 0 |  |  |  |  | 2020-04-14 | 2020-06-18 |  |  |  |  | 2020-07-21 | [9 empty] | Fully Executed Interconnection Agreement | Yes | 2020-10-19 | Cluster 09 - Midcoast - 1 | Newcastle | NC | 2020-08-31 |  | EXECUTED/ENERGIZED
367 | 0 | 0 | 0 |  | 2020-02-28 | Belfast | BELFAST 115 | 874D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Belfast |  |  |  | WITHDRAWN
368 | 0 | 0 | 0 |  | 2020-02-28 | Belfast | BELFAST WEST SIDE | 803D6 | Solar | 2475 | 0 |  |  |  |  | 2021-01-15 | 2021-06-28 |  |  |  |  | 2021-07-07 | [8 empty] | Q3 2022 | Fully Executed Interconnection Agreement | Yes | 2022-11-29 | Cluster 06 - Detroit-Guilford-Belfast - 1 | Belfast | 3 | 2023-05-31 |  | EXECUTED
369 | 0 | 0 | 0 |  | 2020-02-28 | Belfast | BELFAST WEST SIDE | 803D6 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 17 - Detroit Guilford Belfast - 2 | Belfast | 3 |  |  | WITHDRAWN
370 | 0 | 0 | 0 |  | 2020-02-28 | Mechanic Falls | MECHANIC FALLS | 431D2 | Solar | 0 | 0 | [10 empty] | 2021-10-12 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 18 - Lewiston Loop - 2 | Hotel Rd/Gulf/Middle St/Crowleys/Norway | 3 |  |  | EXECUTED-WITHDRAWN
371 | 0 | 0 | 0 |  | 2020-02-28 | Vassalboro | VASSALBORO | 861D9 | Solar | 0 | 0 |  |  |  |  | 2022-02-14 | 2022-04-22 | 2022-05-31 | [13 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Winslow/ County Rd/ Lakewood - TBD | Winslow-County Rd | 3 |  |  | WITHDRAWN
372 | 0 | 0 | 0 |  | 2020-02-28 | Berwick | BERWICK | 603D2 | Solar | 1750 | 0 |  |  |  |  | 2020-04-13 | 2020-06-16 |  |  |  |  | 2020-07-16 | [8 empty] | Q4 2020 | Fully Executed Interconnection Agreement | Yes | 2020-11-30 | Cluster 04 - Sanford-Quaker Hill - 1 | Quaker Hill | NC | 2020-08-31 |  | EXECUTED/ENERGIZED
373 | 0 | 0 | 0 |  | 2020-02-28 | Livermore Falls | LIVERMORE FALLS | 428D3 | Solar | 0 | 0 | [10 empty] | 2021-12-27 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster XX - Sturtevant/ Leeds/ Livermore/ Ludden/ Riley_TBD | Livermore Falls | 3 |  |  | WITHDRAWN
374 | 0 | 0 | 0 |  | 2020-03-04 | Springvale | BUTLER'S CORNER | 612D1 | Solar | 0 | 0 | [10 empty] | 2020-10-06 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 04 - Sanford-Quaker Hill - 1 | Sanford | 3 | 2022-06-27 |  | EXECUTED-WITHDRAWN
375 | 0 | 0 | 0 |  | 2020-03-04 | Hampden | BANGOR HYDRO (Versant) | 120D1 | Solar | 0 | 0 | [10 empty] | 2023-01-03 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | N/A | Emera Transmission |  | 2024-03-21 |  | EXECUTED
376 | 0 | 0 | 0 |  | 2020-03-04 | Brunswick | BRUNSWICK WEST SIDE | 213D1 | Solar | 4999 | 0 |  |  |  |  | 2020-05-15 | 2020-07-21 |  |  |  |  | 2020-08-20 | [9 empty] | Fully Executed Interconnection Agreement | Yes | 2020-09-01 | Cluster 09 - Midcoast - 1 | Topsham | NC | 2020-10-05 |  | EXECUTED/ENERGIZED
377 | 0 | 0 | 0 |  | 2020-03-06 | Pittston | BOWMAN STREET | 263D1 | Solar | 4950 | 0 |  |  |  |  | 2020-04-23 | 2020-06-25 |  |  |  |  | 2020-09-29 | [8 empty] | Q3 2021 | Fully Executed Interconnection Agreement | Yes | 2021-03-31 | Cluster 01 - Augusta - 1 | Augusta E/Puddledock/Bowman St | 3 | 2021-01-04 |  | RE_QUEUED_FullEx/ENERGIZED
378 | 0 | 0 | 0 |  | 2020-03-06 | Biddeford | BIDDEFORD INDUSTRIAL PARK | 673D2 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Biddeford IP | NC |  |  | WITHDRAWN
379 | 0 | 0 | 0 |  | 2020-03-06 | Arundel | MAY STREET | 634D1 | Solar/Battery | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Biddeford IP |  |  |  | WITHDRAWN
380 | 0 | 0 | 0 |  | 2020-03-06 | Lewiston | CROWLEYS | 411D2 | Solar | 4999 | 0 |  |  |  |  | 2020-07-24 | 2020-09-28 |  |  |  |  | 2020-10-19 | [8 empty] | Q4 2021 | Fully Executed Interconnection Agreement | Yes | 2022-08-01 | Cluster 05 - Lewiston Loop - 1 | Hotel Rd/Gulf/Middle St/Crowleys/Norway | 3 | 2022-07-19 |  | EXECUTED
381 | 0 | 0 | 0 |  | 2020-03-10 | Belfast | BELFAST WEST SIDE | 803D6 | Solar | 0 | 0 | [10 empty] | 2022-05-10 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 17 - Detroit Guilford Belfast - 2 | Belfast | 3 |  |  | EXECUTED-WITHDRAWN
382 | 0 | 0 | 0 |  | 2020-03-10 | Gray | GRAY | 416D3 | Solar/Battery | 0 | 0 | [10 empty] | 2020-10-16 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 15 - Greater Portland - 1 | Elm St | NC | 2020-11-20 |  | EXECUTED-WITHDRAWN
383 | 0 | 0 | 0 |  | 2020-03-10 | Woodstock | BRYANT POND | 407D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Woodstock |  |  |  | WITHDRAWN
384 | 0 | 0 | 0 |  | 2020-03-10 | Acton | BUTLER'S CORNER | 612D2 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 04 - Sanford-Quaker Hill - 1 | Sanford | 3 |  | 2022-06-22 | WITHDRAWN
385 | 0 | 0 | 0 |  | 2020-03-10 | Gray | GRAY | 416D1 | Solar | 4999 | 0 |  |  |  |  | 2020-10-19 | 2020-12-23 |  |  |  |  | 2021-04-29 | [8 empty] | Q3 2021 | Fully Executed Interconnection Agreement | Yes | 2021-10-18 | Cluster 15 - Greater Portland - 1 | Elm St | NC | 2021-04-16 |  | RE_QUEUED_FullEx
386 | 0 | 0 | 0 |  | 2020-03-13 | Skowhegan | SKOWHEGAN SOUTH SIDE | 854D1 | Solar | 3199 | 0 |  |  |  |  | 2020-06-16 | 2020-08-18 |  |  |  |  | 2020-09-11 | [8 empty] | Q2 2022 | Fully Executed Interconnection Agreement | Yes | 2020-10-22 | Cluster 02 - Winslow-County Rd-Lakewood -1 | Lakewood | 3 | 2021-12-17 |  | EXECUTED/ENERGIZED
387 | 0 | 0 | 0 |  | 2020-03-13 | Augusta | NORTH AUGUSTA | 272D3 | Solar | 996 | 0 |  |  |  |  | 2021-09-15 | 2021-11-12 | 2021-12-10 | 2022-01-20 |  |  | 2022-01-28 | [8 empty] | Q3 2021 | Fully Executed Interconnection Agreement | Yes | 2022-09-09 | Cluster XX - Augusta E-Puddledock-Bowman St - TBD | North Augusta | 3 |  | Not Required | EXECUTED/ENERGIZED
388 | 0 | 0 | 0 |  | 2020-03-13 | Augusta | BOND BROOK | 208D1 | Solar | 4875 | 0 |  |  |  |  | 2020-04-15 | 2020-06-16 |  |  |  |  | 2020-08-24 | 2024-01-09 | 2024-03-05 | [7 empty] | Fully Executed Interconnection Agreement | Yes | 2022-11-04 | Cluster 01 - Augusta - 1 | Augusta E/Puddledock/Bowman St | 3 | 2021-01-04 |  | RE_QUEUED_FullEx
389 | 0 | 0 | 0 |  | 2020-03-20 | Manchester | PUDDLEDOCK ROAD | 262D1 | Solar | 0 | 0 |  |  |  |  | 2021-04-02 | 2021-07-06 | 2024-07-26 | 2024-09-09 |  |  | 2021-10-13 | 2024-04-15 | 2024-06-07 | [7 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 11 - Augusta E-Puddledock-Bowman St - 2 | Augusta E/Puddledock/Bowman St | 3 | 2024-05-28 |  | RE_QUEUED_RESTUDY
390 | 0 | 0 | 345 |  | 2020-03-20 | Bucksport | BUCKSPORT | 806D2 | Solar | 4980 | 0 |  |  |  |  | 2020-09-11 | 2020-11-17 |  |  |  |  | 2020-12-03 | 2022-08-30 | 2022-10-12 | 2022-12-07 | 2023-01-18 | [5 empty] | Fully Executed Interconnection Agreement | Yes | 2022-11-07 | Cluster 06 - Detroit-Guilford-Belfast - 1 | Bucksport | 3 | 2023-05-31 |  | RE_QUEUED_FullEx/ENERGIZED
391 | 0 | 0 | 0 |  | 2020-03-20 | Augusta | CAPITOL STREET | 215D2 | Solar | 500 | 0 |  |  |  |  | 2020-04-17 | 2020-06-16 |  |  |  |  | 2020-08-24 | [9 empty] | Fully Executed Interconnection Agreement | Yes | 2022-03-07 | Cluster 11 - Augusta E-Puddledock-Bowman St - 2 | Augusta E/Puddledock/Bowman St | 0 |  | Not Required | EXECUTED/ENERGIZED
392 | 0 | 0 | 0 |  | 2020-03-20 | Augusta | CAPITOL STREET | 215D3 | Solar | 1703 | 0 |  |  |  |  | 2020-04-17 | 2020-06-16 |  |  |  |  | 2020-08-24 | [9 empty] | Fully Executed Interconnection Agreement | Yes | 2022-03-07 | Cluster 01 - Augusta - 1 | Augusta E/Puddledock/Bowman St | 3 | 2021-01-04 |  | EXECUTED/ENERGIZED
393 | 0 | 0 | 0 |  | 2020-03-20 | Belmont | BELFAST WEST SIDE | 803D6 | Solar | 0 | 0 | [10 empty] | 2023-04-04 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 17 - Detroit Guilford Belfast - 2 | Belfast | 3 |  | Not Required | EXECUTED-WITHDRAWN
394 | 0 | 0 | 0 |  | 2020-03-20 | Lewiston | CROWLEYS | 411D1 | Solar | 0 | 0 | [10 empty] | 2021-02-18 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 05 - Lewiston Loop - 1 | Hotel Rd/Gulf/Middle St/Crowleys/Norway | 3 |  | Not Required | EXECUTED-WITHDRAWN
395 | 0 | 0 | 0 |  | 2020-03-20 | Prospect | PROSPECT | 846D1 | Solar | 0 | 0 | [10 empty] | 2020-08-04 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 06 - Detroit-Guilford-Belfast - 1 | Belfast | 3 |  | 2023-08-23 | EXECUTED-WITHDRAWN
396 | 0 | 0 | 0 |  | 2020-03-20 | Searsmont | BELFAST WEST SIDE | 803D6 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 17 - Detroit Guilford Belfast - 2 | Belfast | 3 |  |  | WITHDRAWN
397 | 0 | 0 | 0 |  | 2020-03-20 | Searsmont | BELFAST WEST SIDE | 803D6 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 17 - Detroit Guilford Belfast - 2 | Belfast | 3 |  |  | WITHDRAWN
398 | 0 | 0 | 0 |  | 2020-03-20 | Searsmont | BELFAST WEST SIDE | 803D6 | Solar | 0 | 0 | [10 empty] | 2023-08-21 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 17 - Detroit Guilford Belfast - 2 | Belfast | 3 |  | Not Required | EXECUTED-WITHDRAWN
399 | 0 | 0 | 0 |  | 2020-03-20 | Stockton Springs | SEARSPORT | 850D1 | Solar | 0 | 0 | [10 empty] | 2020-09-23 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 06 - Detroit-Guilford-Belfast - 1 | Belfast | 3 | 2023-08-31 |  | EXECUTED-WITHDRAWN
400 | 0 | 0 | 0 |  | 2020-03-20 | Prospect | PROSPECT | 846D1 | Solar | 4999 | 0 |  |  |  |  | 2020-04-24 | 2020-06-26 | 2021-07-20 | 2021-08-30 |  |  | 2020-08-04 | [9 empty] | Fully Executed Interconnection Agreement | Yes | 2020-12-09 | Cluster 06 - Detroit-Guilford-Belfast - 1 | Belfast | 3 | 2023-05-31 |  | EXECUTED
401 | 0 | 0 | 0 |  | 2020-03-20 | Carrabassett Valley | BIGELOW | 882D1 | Solar | 4995 | 0 |  |  |  |  | 2020-05-05 | 2020-07-09 |  |  |  |  | 2020-08-20 | [9 empty] | Fully Executed Interconnection Agreement | Yes | 2020-09-11 | Cluster 16 - Wyman Area - 1 | Bigelow | NC | 2020-10-05 |  | EXECUTED/ENERGIZED
402 | 0 | 0 | 0 |  | 2020-03-24 | Auburn | HOTEL ROAD | 420D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 18 - Lewiston Loop - 2 | Hotel Rd/Gulf/Middle St/Crowleys/Norway | 3 |  |  | WITHDRAWN
403 | 0 | 0 | 0 |  | 2020-03-23 | Casco | SAND ROAD TAP | 470D1 | Solar | 0 | 0 | [10 empty] | 2020-08-04 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 07 - Raymond - 1 | Raymond | 3 | 2023-12-21 |  | RE_QUEUED_FullEx
404 | 0 | 0 | 329 |  | 2020-03-26 | Auburn | DEER RIPS | 412D3 | Solar | 0 | 0 | [10 empty] | 2022-06-14 | [8 empty] | Q4 2025 | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 18 - Lewiston Loop - 2 | Hotel Rd/Gulf/Middle St/Crowleys/Norway | 3 |  | Not Required | RE_QUEUED_RESULTS
405 | 0 | 0 | 0 |  | 2020-03-27 | Winterport | PROSPECT | 846D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 06 - Detroit-Guilford-Belfast - 1 | Belfast | 3 |  | 2023-08-23 | WITHDRAWN
406 | 0 | 0 | 0 |  | 2020-03-27 | Corinth | SKOWHEGAN NORTH SIDE | 853T1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A |  |  |  |  | WITHDRAWN
407 | 0 | 0 | 131 |  | 2020-03-27 | Waterville | COUNTY RD (RICE RIPS) | 873D2 | Solar | 0 | 0 | [10 empty] | 2021-07-07 | [8 empty] | Q4 2021 | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 12 - Winslow-County Rd-Lakewood - 2 | Winslow-County Rd | 3 | 2024-05-28 |  | RE_QUEUED_STUDY
408 | 0 | 0 | 0 | RQP-5 | 2020-03-27 | South Paris | PARIS TAP | 409D1 | Solar | 3000 | 0 |  |  |  |  | 2020-05-06 | 2020-07-10 |  |  |  |  | 2020-07-27 | [8 empty] | Q3 2021 | Fully Executed Interconnection Agreement | Yes | 2022-01-21 | Cluster 10 - Roxbury-Rumford-Woodstock - 1 | Woodstock | NC | 2020-10-05 |  | EXECUTED
409 | 0 | 0 | 0 |  | 2020-03-27 | Athens | ATHENS | 827D1 | Solar | 2864 | 0 |  |  |  |  | 2020-09-08 | 2020-11-12 |  |  |  |  | 2020-12-08 | [9 empty] | Fully Executed Interconnection Agreement | Yes | 2021-08-10 | Cluster 16 - Wyman Area - 1 | Athens | NC | 2021-02-25 |  | EXECUTED/ENERGIZED
410 | 0 | 0 | 0 |  | 2020-03-30 | Lovell | LOVELL | 430D1 | Solar | 0 | 0 | [10 empty] | 2022-01-07 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 13 - Kimball Rd-Lovell - 2 | Kimball Road/Lovell | 3 |  | Not Required | EXECUTED-WITHDRAWN
411 | 0 | 0 | 0 |  | 2020-03-30 | South Thomaston | THOMASTON CREEK | 246D1 | Solar | 4000 | 0 |  |  |  |  | 2020-06-04 | 2020-08-07 | 2020-09-29 | 2020-11-16 |  |  | 2020-12-01 | [9 empty] | Fully Executed Interconnection Agreement | Yes | 2021-07-09 | Cluster 09 - Midcoast - 1 | Highland/Park St | NC | 2021-03-30 |  | EXECUTED/ENERGIZED
412 | 0 | 0 | 0 |  | 2020-03-30 | Dover-Foxcroft | DOVER | 815D1 | Solar | 0 | 0 | [10 empty] | 2021-07-27 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 06 - Detroit-Guilford-Belfast - 1 | Guilford | 3 | 2023-08-31 |  | RE_QUEUED_FullEx
413 | 0 | 0 | 0 |  | 2020-04-01 | Richmond | RICHMOND | 240D1 | Solar | 1750 | 0 |  |  |  |  | 2020-05-15 | 2020-07-15 |  |  |  |  | 2020-08-18 | [9 empty] | Fully Executed Interconnection Agreement | Yes | 2020-09-13 | Cluster 01 - Augusta - 1 | Augusta E/Puddledock/Bowman St | 3 | 2021-01-04 |  | EXECUTED/ENERGIZED
414 | 0 | 0 | 0 |  | 2020-04-01 | Lebanon | LEBANON | 695D2 | Solar | 1998 | 0 |  |  |  |  | 2020-08-14 | 2020-10-20 |  |  |  |  | 2020-11-12 | 2023-12-07 | 2024-03-01 | [7 empty] | Fully Executed Interconnection Agreement | Yes | 2023-07-13 | Cluster 04 - Sanford-Quaker Hill - 1 | Sanford | 3 | 2022-06-27 |  | RE_QUEUED_FullEx
415 | 0 | 0 | 0 |  | 2020-04-01 | Brooks | BROOKS | 805D1 | Solar | 4000 | 0 |  |  |  |  | 2020-05-15 | 2020-07-20 |  |  |  |  | 2020-08-18 | [9 empty] | Fully Executed Interconnection Agreement | Yes | 2020-10-23 | Cluster 06 - Detroit-Guilford-Belfast - 1 | Belfast | 3 | 2023-05-31 |  | EXECUTED
416 | 0 | 0 | 0 |  | 2020-04-01 | Lincolnville | LINCOLNVILLE | 800D1 | Solar | 4000 | 0 |  |  |  |  | 2020-04-24 | 2020-06-29 |  |  |  |  | 2020-07-13 | [9 empty] | Fully Executed Interconnection Agreement | Yes | 2020-07-24 | Cluster 09 - Midcoast - 1 | Lincolnville | 0 | 2020-08-31 |  | EXECUTED/ENERGIZED
417 | 0 | 0 | 0 |  | 2020-04-02 | Lewiston | CROWLEYS | 411D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 18 - Lewiston Loop - 2 | Hotel Rd/Gulf/Middle St/Crowleys/Norway | 3 |  |  | WITHDRAWN
418 | 0 |  | 0 |  | 2020-04-06 | Augusta | BOND BROOK | 208D2 | Solar | 0 | 0 | [10 empty] | 2021-06-16 | [8 empty] | Q4 2021 | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 11 - Augusta E-Puddledock-Bowman St - 2 | Augusta E/Puddledock/Bowman St | 3 | 2024-05-28 |  | RE_QUEUED_RESULTS
419 | 0 | 0 | 0 |  | 2020-04-06 | Athens | ATHENS | 827D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Athens |  |  |  | WITHDRAWN
420 | 0 | 0 | 0 |  | 2020-04-06 | Athens | ATHENS | 827D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Athens |  |  |  | WITHDRAWN
421 | 0 | 0 | 0 |  | 2020-04-06 | Athens | ATHENS | 827D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Athens |  |  |  | WITHDRAWN
422 | 0 | 0 | 0 |  | 2020-04-06 | Athens | ATHENS | 827D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Athens |  |  |  | WITHDRAWN
423 | 0 | 0 | 0 |  | 2020-04-06 | Athens | ATHENS | 827D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Athens |  |  |  | WITHDRAWN
424 | 0 | 0 | 0 |  | 2020-04-06 | Athens | ATHENS | 827D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Athens |  |  |  | WITHDRAWN
425 | 0 | 0 | 0 |  | 2020-04-06 | Athens | ATHENS | 827D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Athens |  |  |  | WITHDRAWN
426 | 0 | 0 | 0 |  | 2020-04-06 | Athens | ATHENS | 827D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Athens |  |  |  | WITHDRAWN
427 | 0 | 0 | 0 |  | 2020-04-13 | Stockton Springs | PROSPECT | 846D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Belfast |  |  |  | WITHDRAWN
428 | 0 | 0 | 0 |  | 2020-04-13 | Gardiner | GARDINER | 226D2 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 01 - Augusta - 1 | Augusta E/Puddledock/Bowman St | 3 |  | 2022-03-21 | WITHDRAWN
429 | 0 | 0 | 0 |  | 2020-04-13 | Gardiner | WEST STREET | 255D1 | Solar | 4000 | 0 |  |  |  |  | 2020-08-07 | 2020-10-13 |  |  |  |  | 2020-09-23 | [9 empty] | Fully Executed Interconnection Agreement | Yes | 2021-03-24 | Cluster 01 - Augusta - 1 | Augusta E/Puddledock/Bowman St | 3 | 2021-01-04 |  | EXECUTED/ENERGIZED
430 | 0 | 0 | 0 |  | 2020-04-13 | Brooks | BROOKS | 805D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 06 - Detroit-Guilford-Belfast - 1 | Belfast | 3 |  | 2023-08-23 | WITHDRAWN
431 | 0 | 0 | 0 |  | 2020-04-13 | Athens | ATHENS | 827D2 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Athens |  |  |  | WITHDRAWN
432 | 0 | 0 | 0 |  | 2020-04-17 | Farmington | STURTEVANT | 858D3 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Sturtevant/ Leeds/ Livermore/ Ludden/ Riley_TBD | Sturtevant | 3 |  |  | WITHDRAWN
433 | 0 | 0 | 0 |  | 2020-04-21 | Monroe | BROOKS | 805D1 | Solar | 0 | 0 |  |  |  |  | 2021-08-31 | [15 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 17 - Detroit Guilford Belfast - 2 | Belfast | 3 |  |  | WITHDRAWN
434 | 0 | 0 | 0 |  | 2020-04-21 | Belgrade | NORTH AUGUSTA | 272D6 | Solar | 0 | 0 | [10 empty] | 2022-07-28 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster XX - Augusta E-Puddledock-Bowman St - TBD | North Augusta | 3 |  |  | EXECUTED
435 | 0 | 0 | 0 |  | 2020-04-21 | Waterville | WEST WATERVILLE | 865D5 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 12 - Winslow-County Rd-Lakewood - 2 | Winslow-County Rd | 3 | 2024-05-28 |  | WITHDRAWN
436 | 0 | 0 | 0 |  | 2020-04-23 | Rumford | RUMFORD | 447D2 | Solar | 3984 | 0 |  |  |  |  | 2020-05-15 | 2020-07-21 |  |  |  |  | 2020-08-26 | [9 empty] | Fully Executed Interconnection Agreement | Yes | 2021-01-12 | Cluster 10 - Roxbury-Rumford-Woodstock - 1 | Rumford | NC | 2020-11-20 |  | EXECUTED/ENERGIZED
437 | 0 | 0 | 0 |  | 2020-04-23 | Gorham | WESTBROOK | 674D2 | Solar/Battery | 4990 | 0 |  |  |  |  | 2020-05-21 | 2020-07-27 |  |  |  |  | 2020-08-26 | [9 empty] | Fully Executed Interconnection Agreement | Yes | 2020-11-25 | Cluster 15 - Greater Portland - 1 | Moshers/Prides Corner | 0 | 2020-10-05 |  | EXECUTED/ENERGIZED
438 | 0 | 0 | 0 |  | 2020-04-23 | Thomaston | PARK STREET | 239D10 | Solar | 0 | 0 | [10 empty] | 2020-08-10 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 09 - Midcoast - 1 | Highland/Park St | NC | 2020-10-05 |  | EXECUTED
439 | 0 | 0 | 0 |  | 2020-04-23 | Turner | WATERBORO | 671T1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A |  |  |  |  | WITHDRAWN
440 | 0 | 0 | 0 |  | 2020-04-23 | Naples | NAPLES TAP | 469D1 | Solar | 0 | 0 | [10 empty] | 2021-06-10 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 07 - Raymond - 1 | Raymond | 3 | 2023-12-21 |  | EXECUTED-WITHDRAWN
441 | 0 | 0 | 0 |  | 2020-04-24 | Turner | DEER RIPS | 412D3 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 18 - Lewiston Loop - 2 | Hotel Rd/Gulf/Middle St/Crowleys/Norway | 3 |  |  | WITHDRAWN
442 | 0 | 0 | 0 |  | 2020-04-24 | Turner | DEER RIPS | 412D3 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 18 - Lewiston Loop - 2 | Hotel Rd/Gulf/Middle St/Crowleys/Norway | 3 |  |  | WITHDRAWN
443 | 0 | 0 | 0 |  | 2020-04-24 | Pownal | GRAY | 416D1 | Solar | 0 | 0 |  |  |  |  | 2021-06-03 | 2021-08-13 | 2021-10-12 | 2021-11-12 | [12 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 15 - Greater Portland - 1 | Elm St | 3 |  | 2024-03-19 | WITHDRAWN
444 | 0 | 0 | 0 |  | 2020-04-24 | York | BRAGDON COMMONS | 689D1 | Solar | 0 | 0 | [10 empty] | 2020-08-26 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 04 - Sanford-Quaker Hill - 1 | Quaker Hill | 3 | 2022-06-27 |  | EXECUTED-WITHDRAWN
445 | 0 | 0 | 0 |  | 2020-04-27 | Oxford | OXFORD | 437D1 | Solar | 1625 | 0 |  |  |  |  | 2020-07-09 | 2020-09-11 | 2020-11-10 | 2020-12-28 |  |  | 2021-06-03 | [9 empty] | Fully Executed Interconnection Agreement | Yes | 2022-12-02 | Cluster 05 - Lewiston Loop - 1 | Hotel Rd/Gulf/Middle St/Crowleys/Norway | 3 | 2022-07-19 |  | EXECUTED
446 | 0 | 0 | 0 |  | 2020-04-27 | Shapleigh | BUTLER'S CORNER | 612D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Sanford |  |  |  | WITHDRAWN
447 | 0 | 0 | 0 |  | 2020-04-29 | Chelsea | BOWMAN STREET | 263D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 11 - Augusta E-Puddledock-Bowman St - 2 | Augusta E/Puddledock/Bowman St | 3 | 2024-05-28 |  | WITHDRAWN
448 | 0 | 0 | 0 |  | 2020-04-30 | Berwick | BERWICK | 603D2 | Solar | 3450 | 0 |  |  |  |  | 2020-07-27 | 2020-09-29 |  |  |  |  | 2020-11-14 | [9 empty] | Fully Executed Interconnection Agreement | Yes | 2023-10-25 | Cluster 04 - Sanford-Quaker Hill - 1 | Quaker Hill | 3 | 2022-06-27 |  | EXECUTED
449 | 0 | 0 | 0 |  | 2020-04-30 | Richmond | RICHMOND | 240D1 | Solar | 0 | 0 | [10 empty] | 2020-11-12 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 11 - Augusta E-Puddledock-Bowman St - 2 | Augusta E/Puddledock/Bowman St | 3 | 2024-05-28 |  | EXECUTED-WITHDRAWN
450 | 0 | 0 | 0 |  | 2020-05-04 | Waterford | PAPOOSE POND | 438D1 | Solar/Battery | 0 | 0 | [10 empty] | 2020-08-20 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 03 - Kimball Rd-Lovell - 1 | Kimball Road/Lovell | 3 |  | 2023-04-22 | EXECUTED-WITHDRAWN
451 | 0 | 0 | 414 |  | 2020-05-04 | Lebanon | LEBANON | 695D1 | Solar | 1999 | 0 |  |  |  |  | 2020-12-08 | 2021-02-12 |  |  |  |  | 2021-06-21 | 2024-04-22 | 2024-05-17 | [6 empty] | Q4 2021 | Fully Executed Interconnection Agreement | Yes | 2023-10-17 | Cluster 04 - Sanford-Quaker Hill - 1 | Sanford | 3 | 2022-06-27 |  | RE_QUEUED_FullEx
452 | 0 | 0 | 0 |  | 2020-05-04 | Bowdoin | TOPSHAM 34 KV | 250D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Topsham |  |  |  | WITHDRAWN
453 | 0 | 0 | 0 |  | 2020-05-04 | South Portland | PLEASANT HILL | 644D2 | Solar | 2500 | 0 |  |  |  |  | 2020-07-02 | 2020-09-03 |  |  |  |  | 2020-10-15 | [9 empty] | Fully Executed Interconnection Agreement | Yes | 2021-03-04 | Cluster 15 - Greater Portland - 1 | Pleasant Hill | 0 | 2020-10-05 |  | EXECUTED/ENERGIZED
454 | 0 | 0 | 0 |  | 2020-05-05 | Kittery | PNSY | PNSY | CTG/Battery | 6800 | 1000 |  |  |  |  | 2021-12-17 | 2021-12-17 |  |  |  |  | 2021-12-17 | [9 empty] | Fully Executed Interconnection Agreement | Yes |  | N/A | N/A |  | N/A | N/A | EXECUTED
455 | 0 | 0 | 0 |  | 2020-05-07 | Augusta | CAPITOL STREET | 215D2 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 11 - Augusta E-Puddledock-Bowman St - 2 | Augusta E/Puddledock/Bowman St | 3 | 2024-05-28 |  | WITHDRAWN
456 | 0 | 0 | 0 |  | 2020-05-07 | Thomaston | THOMASTON CREEK | 246D3 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Highland/Park St |  |  |  | WITHDRAWN
457 | 0 | 0 | 0 |  | 2020-05-08 | York | SOUTH BERWICK | 663D2 | Solar | 0 | 0 | [10 empty] | 2020-10-28 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 04 - Sanford-Quaker Hill - 1 | Quaker Hill | 3 | 2022-06-27 |  | EXECUTED-WITHDRAWN
458 | 0 | 0 | 0 |  | 2020-05-08 | Norridgewock | SKOWHEGAN SOUTH SIDE | 854D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Lakewood |  |  |  | WITHDRAWN
459 | 0 | 0 | 0 |  | 2020-05-08 | Wilton | EAST WILTON | 816D1 | Solar | 3000 | 0 |  |  |  |  | 2020-06-17 | 2020-08-20 |  |  |  |  | 2020-09-16 | [9 empty] | Fully Executed Interconnection Agreement | Yes | 2020-10-23 | Cluster 08 - Sturtevant-Leeds-Livermore-Ludden-Riley - 1 | Sturtevant | NC | 2021-06-01 |  | EXECUTED/ENERGIZED
460 | 0 | 0 | 0 |  | 2020-05-11 | Dover-Foxcroft | DOVER | 815D2 | Solar | 0 | 0 |  |  |  |  | 2021-09-30 | [5 empty] | 2021-12-13 | 2023-04-05 | 2023-05-18 | [7 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 17 - Detroit Guilford Belfast - 2 | Guilford | 3 |  | Not Required | RE_QUEUED_FullEx
461 | 0 | 0 | 0 |  | 2020-05-11 | Wilton | WILTON | 885D1 | Solar | 0 | 0 | [10 empty] | 2021-08-30 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 08 - Sturtevant-Leeds-Livermore-Ludden-Riley - 1 | Sturtevant | 3 | 2023-12-21 |  | RE_QUEUED_FullEx
462 | 0 | 0 | 0 |  | 2020-05-11 | Augusta | NORTH AUGUSTA | 272D2 | Solar | 0 | 0 |  |  |  |  | 2022-09-29 | 2022-12-06 |  |  |  |  | 2023-01-13 | [9 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Augusta E-Puddledock-Bowman St - TBD | North Augusta | 3 |  |  | EXECUTED-WITHDRAWN
463 | 0 | 0 | 0 |  | 2020-05-13 | Farmington | STURTEVANT | 858D4 | Solar/Battery | 0 | 0 |  |  |  |  | 2024-06-10 | 2024-08-07 | [14 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Sturtevant/ Leeds/ Livermore/ Ludden/ Riley_TBD | Sturtevant | 3 |  | Not Required | RE_QUEUED_RESULTS
464 | 0 | 0 | 0 |  | 2020-05-13 | Windham | SWETT ROAD | 682D1 | Solar | 0 | 0 | [10 empty] | 2020-11-14 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 07 - Raymond - 1 | Raymond | 3 |  | 2023-12-15 | EXECUTED-WITHDRAWN
465 | 0 | 0 | 0 |  | 2020-05-13 | Waterford | PAPOOSE POND | 438D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 03 - Kimball Rd-Lovell - 1 | Kimball Road/Lovell | 3 |  | 2023-04-22 | WITHDRAWN
466 | 0 | 0 | 0 |  | 2020-05-13 | Sanford | HIGH STREET | 626D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A |  |  |  |  | WITHDRAWN
467 | 0 | 0 | 0 |  | 2020-05-14 | West Gardiner | WEST STREET | 255D2 | Solar | 0 | 0 | [10 empty] | 2022-01-18 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 11 - Augusta E-Puddledock-Bowman St - 2 | Augusta E/Puddledock/Bowman St | 3 | 2024-05-28 |  | EXECUTED-WITHDRAWN
468 | 0 | 0 | 0 |  | 2020-05-14 | Jay | RILEY | 449D2 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Riley | NC |  |  | WITHDRAWN
469 | 0 | 0 | 0 |  | 2020-05-18 | Sanford | SANFORD SWITCH | 657D4 | Solar | 0 | 0 | [10 empty] | 2020-09-09 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 04 - Sanford-Quaker Hill - 1 | Sanford | 3 | 2022-06-27 |  | EXECUTED-WITHDRAWN
470 | 0 | 0 | 0 |  | 2020-05-20 | Harmony | ATHENS | 827D2 | Solar | 0 | 0 | [10 empty] | 2021-10-26 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 16 - Wyman Area - 1 | Athens | 3 | 2023-04-27 |  | EXECUTED
471 | 0 | 0 | 0 |  | 2020-05-22 | South Thomaston | THOMASTON CREEK | 246D1 | Solar | 0 | 0 | [10 empty] | 2022-01-18 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 09 - Midcoast - 1 | Highland/Park St | 3 | 2023-12-21 |  | EXECUTED
472 | 0 | 0 | 0 |  | 2020-05-26 | Oakland | COUNTY RD (RICE RIPS) | 873D1 | Solar | 0 | 0 | [10 empty] | 2022-01-11 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 12 - Winslow-County Rd-Lakewood - 2 | Winslow-County Rd | 3 | 2024-05-28 |  | RE_QUEUED_FullEx
473 | 0 | 0 | 0 |  | 2020-05-26 | Pittsfield | BURNHAM | 807D1 | Solar | 0 | 0 | [10 empty] | 2020-09-18 | [8 empty] | Q4 2025 | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 06 - Detroit-Guilford-Belfast - 1 | Detroit | 3 | 2023-08-31 |  | EXECUTED
474 | 0 | 0 | 0 |  | 2020-05-26 | New Sharon | FARMINGTON FALLS | 818D1 | Solar | 3750 | 0 |  |  |  |  | 2020-07-24 | 2020-09-28 | 2022-03-21 | 2022-04-29 |  |  | 2020-11-14 | [9 empty] | Fully Executed Interconnection Agreement | Yes | 2021-10-20 | Cluster 08 - Sturtevant-Leeds-Livermore-Ludden-Riley - 1 | Sturtevant | NC | 2021-06-01 |  | RE_QUEUED_FullEx/ENERGIZED
475 | 0 | 0 | 0 |  | 2020-05-26 | Fairfield | SHAWMUT | 852D1 | Solar | 1000 | 0 |  |  |  |  | 2020-07-17 | 2020-09-15 | 2021-09-16 | 2021-10-14 |  |  | 2020-09-23 | [9 empty] | Fully Executed Interconnection Agreement | Yes | 2022-02-02 | Cluster 02 - Winslow-County Rd-Lakewood -1 | Lakewood | 3 | 2021-12-17 |  | EXECUTED/ENERGIZED
476 | 0 | 0 | 0 |  | 2020-05-26 | Waterville | WEST WATERVILLE | 865D5 | Solar | 4950 | 0 |  |  |  |  | 2020-08-03 | 2020-10-06 |  |  |  |  | 2020-10-19 | [9 empty] | Fully Executed Interconnection Agreement | Yes | 2022-02-02 | Cluster 02 - Winslow-County Rd-Lakewood -1 | Winslow-County Rd | 3 | 2021-12-17 |  | EXECUTED/ENERGIZED
477 | 0 | 0 | 0 |  | 2020-05-27 | Andover | ANDOVER | 400D1 | Solar | 999 | 0 |  |  |  |  | 2020-07-24 | 2020-09-28 |  |  |  |  | 2020-11-10 | 2023-08-25 | 2023-10-09 | [6 empty] | Q4 2025 | Fully Executed Interconnection Agreement | Yes | 2023-11-20 | Cluster 10 - Roxbury-Rumford-Woodstock - 1 | Roxbury | 3 |  | Not Required | RE_QUEUED_FullEx
478 | 0 | 0 | 0 |  | 2020-05-28 | Augusta | AUGUSTA K5 | 200D3 | Solar | 2000 | 0 |  |  |  |  | 2020-07-27 | 2020-09-29 |  |  |  |  | 2020-10-26 | [9 empty] | Fully Executed Interconnection Agreement | Yes | 2021-05-04 | Cluster 01 - Augusta - 1 | Augusta E/Puddledock/Bowman St | 3 | 2021-01-04 |  | EXECUTED/ENERGIZED
479 | 0 | 0 | 0 |  | 2020-05-28 | Chelsea | CONY ROAD | 216D1 | Solar | 4999 | 0 | 2020-08-03 | 2020-09-08 | 2020-09-29 | 2020-11-12 | [6 empty] | 2020-11-24 | [9 empty] | Fully Executed Interconnection Agreement | Yes | 2021-12-31 | Cluster 01 - Augusta - 1 | Augusta E/Puddledock/Bowman St | 3 | 2021-01-04 |  | EXECUTED
480 | 0 | 0 | 0 |  | 2020-06-04 | Edgecomb | EDGECOMB | 223D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 09 - Midcoast - 1 | Newcastle | 3 |  | 2023-12-15 | WITHDRAWN
481 | 0 | 0 | 472 |  | 2020-06-04 | Oakland | COUNTY RD (RICE RIPS) | 873D1 | Solar | 0 | 0 | [10 empty] | 2022-06-21 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster XX - Winslow/ County Rd/ Lakewood - TBD | Winslow-County Rd | 3 |  | Not Required | RE_QUEUED_FullEx
482 | 0 | 0 | 0 |  | 2020-06-05 | Wilton | WILTON | 885D1 | Solar | 0 | 0 | [10 empty] | 2021-12-10 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster XX - Sturtevant/ Leeds/ Livermore/ Ludden/ Riley_TBD | Sturtevant | 3 |  |  | EXECUTED-WITHDRAWN
483 | 0 | 0 | 0 |  | 2020-06-08 | Shapleigh | SANFORD SWITCH | 657D3 | Solar | 0 | 0 | [10 empty] | 2021-01-26 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 04 - Sanford-Quaker Hill - 1 | Sanford | 3 | 2022-06-27 |  | EXECUTED-WITHDRAWN
484 | 0 | 0 | 0 |  | 2020-06-16 | Skowhegan | WESTON HYDRO | 866D2 | Solar | 0 | 0 | [10 empty] | 2021-03-01 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 12 - Winslow-County Rd-Lakewood - 2 | Lakewood | 3 | 2024-05-28 |  | EXECUTED-WITHDRAWN
485 | 0 | 0 | 0 |  | 2020-06-15 | Hollis | BAR MILLS | 678D1 | Solar | 4950 | 0 |  |  |  |  | 2020-08-03 | 2020-10-06 |  |  |  |  | 2020-10-19 | [9 empty] | Fully Executed Interconnection Agreement | Yes | 2021-09-23 | Cluster 14 - Louden-Biddeford IP - 1 | West Buxton | NC | 2021-09-03 |  | EXECUTED/ENERGIZED
486 | 0 | 0 | 0 |  | 2020-06-15 | North Anson | NORTH ANSON | 838D2 | Solar | 0 | 0 |  |  |  |  | 2020-11-12 | [15 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Lakewood |  |  |  | WITHDRAWN
487 | 0 | 0 | 0 |  | 2020-06-15 | Norridgewock | SKOWHEGAN SOUTH SIDE | 854D1 | Solar | 2318 | 0 |  |  |  |  | 2020-07-24 | 2020-09-28 | 2020-11-10 | 2020-12-28 |  |  | 2021-05-13 | [9 empty] | Fully Executed Interconnection Agreement | Yes | 2022-12-07 | Cluster 02 - Winslow-County Rd-Lakewood -1 | Lakewood | 3 | 2021-12-17 |  | EXECUTED
488 | 0 | 0 | 0 |  | 2020-06-15 | Owls Head | PARK STREET | 239D5 | Solar | 0 | 0 | [10 empty] | 2021-06-11 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 09 - Midcoast - 1 | Highland/Park St | 3 |  | 2023-12-15 | EXECUTED-WITHDRAWN
489 | 0 | 0 | 0 |  | 2020-06-15 | Fairfield | SHAWMUT | 852D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 12 - Winslow-County Rd-Lakewood - 2 | Lakewood | 3 | 2024-05-28 |  | WITHDRAWN
490 | 0 | 0 | 0 |  | 2020-06-16 | Palmyra | DETROIT | 812D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Detroit |  |  |  | WITHDRAWN
491 | 0 | 0 | 0 |  | 2020-06-16 | Bristol | BRISTOL | 210D2 | Solar | 3500 | 0 |  |  |  |  | 2020-08-05 | 2020-10-06 |  |  |  |  | 2020-11-04 | [9 empty] | Fully Executed Interconnection Agreement | Yes | 2023-03-02 | Cluster 09 - Midcoast - 1 | Newcastle | 3 | 2023-12-21 |  | EXECUTED
492 | 0 | 0 | 0 |  | 2020-06-22 | Limerick | LIMERICK | 632D2 | Solar | 0 | 0 |  |  |  |  | 2020-10-05 | 2020-12-15 | 2021-01-15 | 2021-06-11 |  |  | 2021-06-21 | [9 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 03 - Kimball Rd-Lovell - 1 | Kimball Road/Lovell | 3 | 2023-04-27 |  | EXECUTED
493 | 0 | 0 | 0 |  | 2020-06-23 | Gardiner | BROWNS CROSSING | 211D2 | Solar | 3875 | 0 |  |  |  |  | 2020-08-13 | 2020-10-19 | 2020-12-07 | 2021-01-19 |  |  | 2020-12-09 | [9 empty] | Fully Executed Interconnection Agreement | Yes | 2021-08-11 | Cluster 11 - Augusta E-Puddledock-Bowman St - 2 | Browns Crossing | NC | 2021-02-25 |  | EXECUTED/ENERGIZED
494 | 0 | 0 | 0 |  | 2020-06-23 | Gardiner | GARDINER | 226D2 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Augusta E/Puddledock/Bowman St |  |  |  | WITHDRAWN
495 | 0 | 0 | 0 |  | 2020-06-24 | Prospect | PROSPECT | 846D1 | Solar | 0 | 0 |  |  |  |  | 2021-03-10 | 2021-07-08 | 2021-11-04 | 2021-12-20 |  |  | 2022-09-15 | 2023-01-17 | 2023-02-21 | [7 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 17 - Detroit Guilford Belfast - 2 | Belfast | 3 |  |  | RE_QUEUED_FullEx
496 | 0 | 0 | 0 |  | 2020-06-24 | Monroe | BROOKS | 805D1 | Solar | 0 | 0 | 2022-03-30 | 2022-05-05 | 2022-09-08 | 2022-10-19 | [6 empty] | 2023-01-23 | [9 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 17 - Detroit Guilford Belfast - 2 | Belfast | 3 |  |  | EXECUTED
497 | 0 | 0 | 0 |  | 2020-06-24 | Casco | RAYMOND 115 KV | 445D2 | Solar | 0 | 0 | [10 empty] | 2021-01-19 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 07 - Raymond - 1 | Raymond | 3 | 2023-12-21 |  | EXECUTED-WITHDRAWN
498 | 0 | 0 | 0 |  | 2020-06-26 | Parkman | GUILFORD | 821D1 | Solar | 0 | 0 | [10 empty] | 2022-08-04 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 17 - Detroit Guilford Belfast - 2 | Guilford | 3 |  |  | RE_QUEUED_FullEx
499 | 0 | 0 | 0 |  | 2020-07-01 | Scarborough | SCARBOROUGH | 693D1 | Solar | 0 | 0 | [10 empty] | 2020-11-05 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 15 - Greater Portland - 1 | Spring St | 3 | 2024-02-22 |  | RE_QUEUED_FullEx
500 | 0 | 0 | 0 |  | 2020-07-01 | Farmington | STURTEVANT | 858D3 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Sturtevant/ Leeds/ Livermore/ Ludden/ Riley_TBD | Sturtevant | 3 |  |  | WITHDRAWN
501 | 0 | 0 | 0 |  | 2020-07-01 | Scarborough | SCARBOROUGH | 693D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Spring St |  |  |  | WITHDRAWN
502 | 0 | 0 | 0 |  | 2020-07-02 | Farmington | STURTEVANT | 858D1A | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Sturtevant/ Leeds/ Livermore/ Ludden/ Riley_TBD | Sturtevant | 3 |  |  | WITHDRAWN
503 | 0 | 0 | 0 |  | 2020-07-02 | Auburn | HOTEL ROAD | 420D4 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 18 - Lewiston Loop - 2 | Hotel Rd/Gulf/Middle St/Crowleys | 3 |  |  | WITHDRAWN
504 | 0 | 0 | 0 |  | 2020-07-08 | West Paris | TRAP CORNER | 453D1 | Solar | 0 | 0 | [10 empty] | 2021-05-06 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 10 - Roxbury-Rumford-Woodstock - 1 | Woodstock | 3 |  | Not Required | EXECUTED-WITHDRAWN
505 | 0 | 0 | 0 |  | 2020-07-09 | Brunswick | TOPHAM OLD | 249D1 | Solar | 0 | 0 | [10 empty] | 2020-12-01 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 09 - Midcoast - 1 | Topsham | 3 | 2023-12-21 |  | EXECUTED-WITHDRAWN
506 | 0 | 0 | 0 |  | 2020-07-09 | Canton | RUMFORD INDUSTRIAL PARK | 466D1 | Solar | 3000 | 0 |  |  |  |  | 2020-08-20 | 2020-10-26 |  |  |  |  | 2020-12-08 | [9 empty] | Fully Executed Interconnection Agreement | Yes | 2021-11-12 | Cluster 10 - Roxbury-Rumford-Woodstock - 1 | Rumford IP | NC | 2021-02-25 |  | EXECUTED/ENERGIZED
507 | 0 | 0 | 0 |  | 2020-07-13 | Scarborough | SCARBOROUGH | 693D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Spring St |  |  |  | WITHDRAWN
508 | 0 | 0 | 0 |  | 2020-07-13 | Arundel | BIDDEFORD INDUSTRIAL PARK | 673D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Biddeford IP |  |  |  | WITHDRAWN
509 | 0 | 0 | 0 |  | 2020-07-13 | Paris | PARIS TAP | 409D1 | Solar | 0 | 0 | [10 empty] | 2021-05-19 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 10 - Roxbury-Rumford-Woodstock - 1 | Woodstock | 3 | 2023-12-21 |  | EXECUTED-WITHDRAWN
510 | 0 | 0 | 0 |  | 2020-07-14 | New Portland | STURTEVANT | 858D2 | Solar/Battery | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Sturtevant/ Leeds/ Livermore/ Ludden/ Riley_TBD | Sturtevant | 3 |  |  | WITHDRAWN
511 | 0 | 0 | 0 |  | 2020-07-20 | Bristol | BRISTOL | 210D1 | Solar | 1999 | 0 |  |  |  |  | 2020-11-17 | 2021-01-26 | 2021-09-16 | 2021-10-27 |  |  | 2021-11-24 | [8 empty] | Q3 2026 | Fully Executed Interconnection Agreement | No | 2023-03-16 | Cluster 09 - Midcoast - 1 | Newcastle | 3 | 2023-12-21 |  | EXECUTED
512 | 0 | 0 | 0 |  | 2020-07-22 | Dover-Foxcroft | DOVER | 815D2 | Solar | 0 | 0 | 2022-03-02 | [10 empty] | 2023-08-28 | [8 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 17 - Detroit Guilford Belfast - 2 | Guilford | 3 |  |  | WITHDRAWN
513 | 0 | 0 | 0 |  | 2020-07-22 | Hollis | BAR MILLS | 678D1 | Solar | 0 | 0 | [10 empty] | 2021-07-06 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 14 - Louden-Biddeford IP - 1 | West Buxton | 3 |  | 2024-03-19 | EXECUTED-WITHDRAWN
514 | 0 | 0 | 0 |  | 2020-07-22 | Hermon | BANGOR HYDRO (Versant) | 120D1 | Solar/Battery | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Emera Transmission |  |  |  | WITHDRAWN
515 | 0 | 0 | 0 |  | 2020-07-22 | Rumford | RUMFORD | 447D2 | Solar/Battery | 0 | 0 | [10 empty] | 2021-02-02 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 10 - Roxbury-Rumford-Woodstock - 1 | Rumford | 3 |  | 2023-12-15 | EXECUTED-WITHDRAWN
516 | 0 | 0 | 0 |  | 2020-07-24 | Prospect | PROSPECT | 846D1 | Solar | 0 | 0 |  |  |  |  | 2023-04-26 | 2023-06-08 | [14 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 17 - Detroit Guilford Belfast - 2 | Belfast | 3 |  | Not Required | WITHDRAWN
517 | 0 | 0 | 0 |  | 2020-07-24 | Saco | LOUDEN | 633D1 | Solar/Battery | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Louden |  |  |  | WITHDRAWN
518 | 0 | 0 | 0 |  | 2020-07-24 | Fryeburg | FRYEBURG TAP | 405D1 | Hydro | 600 | 0 |  |  |  |  | 2020-11-13 | 2021-05-12 | 2021-07-19 | 2021-08-30 |  |  | 2021-10-06 | [9 empty] | Fully Executed Interconnection Agreement | Yes | 2022-04-11 | Cluster 03 - Kimball Rd-Lovell - 1 | Kimball Road/Lovell | 3 |  | Not Required | EXECUTED/ENERGIZED
519 | 0 | 0 | 0 |  | 2020-07-28 | Sabattus | SABATTUS | 450D1 | Solar | 4950 | 0 |  |  |  |  | 2020-08-20 | 2020-10-26 | 2023-11-22 | 2024-01-09 |  |  | 2020-11-10 | 2023-08-31 | 2023-10-16 | [7 empty] | Fully Executed Interconnection Agreement | Yes | 2022-09-26 | Cluster 05 - Lewiston Loop - 1 | Hotel Rd/Gulf/Middle St/Crowleys | 3 | 2022-07-19 |  | RE_QUEUED_FullEx
520 | 0 | 0 | 0 |  | 2020-07-28 | South Paris | NORWAY | 435D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Louden-Biddeford IP - TBD | Norway | 3 |  |  | WITHDRAWN
521 | 0 | 0 | 0 |  | 2020-07-29 | Plymouth | NEWPORT | 837D2 | Solar/Battery | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Detroit |  |  |  | WITHDRAWN
522 | 0 | 0 | 0 |  | 2020-07-30 | Newfield | LIMERICK | 632D2 | Solar | 0 | 0 |  |  |  |  | 2021-07-12 | [15 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 13 - Kimball Rd-Lovell - 2 | Kimball Road/Lovell | 3 |  |  | WITHDRAWN
523 | 0 | 0 | 0 |  | 2020-07-31 | Embden | EMBDEN | 868D1 | Solar | 1000 | 0 |  |  |  |  | 2020-08-28 | 2020-11-03 | 2021-08-31 |  |  |  | 2020-11-17 | [9 empty] | Fully Executed Interconnection Agreement | Yes | 2022-05-17 | Cluster 16 - Wyman Area - 1 | Embden | 3 | N/A |  | EXECUTED/ENERGIZED
524 | 0 | 0 | 0 |  | 2020-08-07 | Biddeford | BIDDEFORD PUMP | 605D1 | Solar | 840 | 0 |  |  |  |  | 2020-09-14 | 2020-11-17 | 2022-12-02 | 2021-09-14 |  |  | 2021-11-24 | 2022-12-02 | 2023-01-18 | [6 empty] | Q4 2025 | Fully Executed Interconnection Agreement | No | 2022-12-27 | Cluster 14 - Louden-Biddeford IP - 1 | Louden | 3 |  | Not Required | RE_QUEUED_FullEx
525 | 0 | 0 | 0 |  | 2020-08-07 | Leeds | LEEDS | 471D2 | Solar/Battery | 0 | 0 |  |  |  |  | 2022-04-06 | 2022-06-03 |  |  |  |  | 2022-10-31 | 2024-09-13 | 2024-11-19 | [7 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Sturtevant/ Leeds/ Livermore/ Ludden/ Riley_TBD | Leeds | 3 |  |  | RE_QUEUED_RESULTS
526 | 0 | 0 | 0 |  | 2020-08-10 | Greenville | MONSON | 834D2 | Solar | 0 | 0 | [10 empty] | 2021-07-21 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 06 - Detroit-Guilford-Belfast - 1 | Guilford | 3 | 2023-08-31 |  | EXECUTED-WITHDRAWN
527 | 0 | 0 | 0 |  | 2020-08-10 | Fairfield | SHAWMUT | 852D1 | Solar | 0 | 0 | 2022-01-05 | 2022-02-03 | [18 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Winslow/ County Rd/ Lakewood - TBD | Lakewood | 3 |  |  | WITHDRAWN
528 | 0 | 0 | 0 |  | 2020-08-10 | Denmark | DENMARK | 413D2 | Solar | 0 | 0 | [10 empty] | 2020-11-22 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 03 - Kimball Rd-Lovell - 1 | Kimball Road/Lovell | 3 | 2023-04-27 |  | EXECUTED-WITHDRAWN
529 | 0 | 0 | 0 |  | 2020-08-11 | New Gloucester | HOTEL ROAD | 420D7 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 18 - Lewiston Loop - 2 | Hotel Rd/Gulf/Middle St/Crowleys | 3 |  |  | WITHDRAWN
530 | 0 | 0 | 0 |  | 2020-08-11 | Sidney | NORTH AUGUSTA | 272D6 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Augusta E-Puddledock-Bowman St - TBD | North Augusta | 3 |  |  | WITHDRAWN
531 | 0 | 0 | 0 |  | 2020-08-12 | Bryant Pond | BRYANT POND | 407D1 | Solar | 0 | 0 | [10 empty] | 2021-05-05 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 10 - Roxbury-Rumford-Woodstock - 1 | Woodstock | 3 |  | 2023-12-15 | EXECUTED-WITHDRAWN
532 | 0 | 0 | 0 |  | 2020-08-13 | Detroit | DETROIT | 812D2 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Detroit |  |  |  | WITHDRAWN
533 | 0 | 0 | 0 |  | 2020-08-17 | Arundel | BIDDEFORD INDUSTRIAL PARK | 673D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 14 - Louden-Biddeford IP - 1 | Biddeford IP | 3 |  | 2024-03-19 | WITHDRAWN
534 | 0 | 0 | 0 |  | 2020-08-19 | Bingham | WYMAN HYDRO | 872D1 | Solar | 0 | 0 | [10 empty] | 2022-01-19 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 16 - Wyman Area - 1 | Wyman Hydro | 3 |  | Not Required | EXECUTED-WITHDRAWN
535 | 0 | 0 | 0 |  | 2020-08-19 | Buxton | BAR MILLS | 678D2 | Solar | 0 | 0 | [10 empty] | 2022-09-02 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 14 - Louden-Biddeford IP - 1 | West Buxton | 3 | 2024-02-22 |  | EXECUTED
536 | 0 | 0 | 0 |  | 2020-08-19 | Newport | NEWPORT | 837D2 | Solar | 0 | 0 | [10 empty] | 2022-06-14 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 17 - Detroit Guilford Belfast - 2 | Detroit | 3 |  |  | EXECUTED-WITHDRAWN
537 | 0 | 0 | 0 |  | 2020-08-21 | Fryeburg | FRYEBURG | 415D2 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 03 - Kimball Rd-Lovell - 1 | Kimball Road/Lovell | 3 |  | 2023-04-22 | WITHDRAWN
538 | 0 | 0 | 0 |  | 2020-08-21 | Auburn | GREAT FALLS | 436D6 | Solar | 0 | 0 |  |  |  |  | 2020-12-04 | 2021-02-10 | 2022-03-02 | 2022-04-15 |  | 2021-04-02 | [10 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 05 - Lewiston Loop - 1 | Hotel Rd/Gulf/Middle St/Crowleys | 3 |  | 2022-07-22 | WITHDRAWN
539 | 0 | 0 | 0 |  | 2020-08-31 | Monson | MONSON | 834D2 | Solar | 0 | 0 | [10 empty] | 2022-06-16 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 17 - Detroit Guilford Belfast - 2 | Guilford | 3 |  |  | EXECUTED-WITHDRAWN
540 | 0 | 0 | 0 |  | 2020-09-04 | Dixfield | LUDDEN LANE | 461D1 | Solar | 975 | 0 |  |  |  |  | 2021-01-08 | 2021-06-22 | 2021-08-19 | 2021-09-29 |  |  | 2021-11-08 | 2023-09-01 | 2023-10-17 | 2023-12-22 | 2024-02-26 |  |  |  |  | Q4 2025 | Fully Executed Interconnection Agreement | No | 2024-07-18 | Cluster 08 - Sturtevant-Leeds-Livermore-Ludden-Riley - 1 | Ludden Lane | 3 | 2023-12-21 | Not Required | RE_QUEUED_FullEx
541 | 0 | 0 | 0 |  | 2020-09-08 | Sanford | SANFORD INDUSTRIAL PARK | 656D2 | Solar | 0 | 0 | [10 empty] | 2021-07-01 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 04 - Sanford-Quaker Hill - 1 | Sanford | 3 | 2022-06-27 |  | EXECUTED-WITHDRAWN
542 | 0 | 0 | 0 |  | 2020-09-10 | Solon | EMBDEN | 868D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 16 - Wyman Area - 1 | Embden | 3 |  | 2023-05-15 07:38 | WITHDRAWN
543 | 0 | 0 | 0 |  | 2020-09-11 | York | YORK BEACH | 676D2 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Bolt Hill | 0 |  |  | WITHDRAWN
544 | 0 | 0 | 0 |  | 2020-09-11 | Pittsfield | DETROIT | 812D2 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Detroit |  |  |  | WITHDRAWN
545 | 0 | 0 | 0 |  | 2020-09-11 | Dover-Foxcroft | DOVER | 815D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 17 - Detroit Guilford Belfast - 2 | Guilford | 3 |  | Not Required | WITHDRAWN
546 | 0 | 0 | 0 |  | 2020-09-15 | Lincolnville | CAMDEN | 214D4 | Solar | 0 | 0 | [10 empty] | 2021-05-17 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 09 - Midcoast - 1 | Meadow Road | 3 |  | 2023-12-15 | EXECUTED-WITHDRAWN
547 | 0 | 0 | 0 |  | 2020-09-17 | Topsham | TOPHAM OLD | 249D1 | Solar | 0 | 0 |  |  |  |  | 2020-10-22 | 2020-12-29 |  |  |  |  | 2021-07-09 |  | 2022-12-08 | [7 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 09 - Midcoast - 1 | Topsham | 3 | 2023-12-21 |  | EXECUTED-WITHDRAWN
548 | 0 | 0 | 0 |  | 2020-09-24 | Vassalboro | MCCOYS | 237D1 | Solar | 0 | 0 | [10 empty] | 2021-09-01 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 11 - Augusta E-Puddledock-Bowman St - 2 | Augusta E/Puddledock/Bowman St | 3 | 2024-05-28 |  | EXECUTED-WITHDRAWN
549 | 0 | 0 | 0 |  | 2020-09-24 | Waterville | SOUTH WATERVILLE | 855D2 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 12 - Winslow-County Rd-Lakewood - 2 | Winslow-County Rd | 3 | 2024-05-28 |  | WITHDRAWN
550 | 0 | 0 | 0 |  | 2020-09-28 | Sanford | SANFORD INDUSTRIAL PARK | 656D2 | Solar | 0 | 0 | [10 empty] | 2021-12-08 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 19 - Sanford-Quaker Hill - 2 | Sanford | 3 |  |  | EXECUTED-WITHDRAWN
551 | 0 | 0 | 0 |  | 2020-09-28 | Lebanon | LEBANON | 695D2 | Solar | 0 | 0 | [10 empty] | 2021-12-21 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 19 - Sanford-Quaker Hill - 2 | Sanford | 3 |  |  | EXECUTED-WITHDRAWN
552 | 0 | 0 | 0 |  | 2020-09-29 | Warren | WARREN | 253D1 | Solar | 0 | 0 | [10 empty] | 2021-06-30 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 09 - Midcoast - 1 | Highland/Park St | 3 |  | 2023-12-15 | EXECUTED-WITHDRAWN
553 | 0 | 0 | 0 |  | 2020-09-29 | Carmel | CARMEL | 808D2 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 17 - Detroit Guilford Belfast - 2 | Detroit | 3 |  |  | WITHDRAWN
554 | 0 | 0 | 0 |  | 2020-09-30 | Freeport | FREEPORT | 225D4 | Solar | 0 | 0 | [10 empty] | 2021-05-05 | [8 empty] | Q2 2021 | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 15 - Greater Portland - 1 | Elm St | 3 | 2024-02-22 |  | RE_QUEUED_FullEx
555 | 0 | 0 | 0 |  | 2020-09-30 | Thomaston | PARK STREET | 239D7 | Solar | 999 | 0 |  |  |  |  | 2021-07-15 | 2021-09-21 |  |  |  |  | 2021-10-26 | 2023-01-06 | 2023-02-15 | 2023-05-30 | 2023-07-10 | 2023-11-01 | 2023-12-22 | 2024-02-08 | 2024-04-16 | Q1 2026 | Fully Executed Interconnection Agreement | No | 2024-07-12 | Cluster XX - Midcoast - TBD | Highland/Park St | 3 |  | Not Required | RE_QUEUED_FullEx
556 | 0 | 0 | 0 |  | 2020-10-01 | Skowhegan | WESTON HYDRO | 866D2 | Solar | 0 | 0 | [10 empty] | 2021-11-24 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 12 - Winslow-County Rd-Lakewood - 2 | Lakewood | 3 | 2024-05-28 |  | EXECUTED-WITHDRAWN
557 | 0 | 0 | 0 |  | 2020-10-01 | Rockport | MEADOW ROAD | 270D2 | Solar | 0 | 0 | [10 empty] | 2021-08-02 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 09 - Midcoast - 1 | Meadow Road | 3 |  | 2023-12-15 | EXECUTED-WITHDRAWN
558 | 0 | 0 | 0 |  | 2020-10-05 | Lisbon | LISBON FALLS | 232D1 | Solar | 0 | 0 | [10 empty] | 2021-06-29 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 05 - Lewiston Loop - 1 | Hotel Rd/Gulf/Middle St/Crowleys | 3 | 2022-07-19 |  | EXECUTED-WITHDRAWN
559 | 0 | 0 | 0 |  | 2020-10-06 | Chelsea | CONY ROAD | 216D2 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Augusta E/Puddledock/Bowman St |  |  |  | WITHDRAWN
560 | 0 | 0 | 0 |  | 2020-10-06 | Raymond | RAYMOND 115 KV | 445D1 | Solar | 0 | 0 | [10 empty] | 2021-07-01 | [8 empty] | Q4 2025 | EXECUTED-WITHDRAWN | WITHDRAWN | 2022-11-15 | Cluster 07 - Raymond - 1 | Raymond | 3 | 2023-12-21 |  | RE_QUEUED_FullEx
561 | 0 | 0 | 478 |  | 2020-10-13 | Augusta | AUGUSTA K5 | 200D2 | Solar | 1900 | 0 |  |  |  |  | 2020-12-14 | 2021-02-19 |  |  |  |  | 2021-07-13 | 2023-08-14 | 2023-09-28 | [6 empty] | Q2 2025 | Fully Executed Interconnection Agreement | Yes | 2023-04-11 | Cluster 11 - Augusta E-Puddledock-Bowman St - 2 | Augusta E/Puddledock/Bowman St | 3 | 2024-05-28 |  | RE_QUEUED_FullEx
562 | 0 | 0 | 0 |  | 2020-10-15 | Lisbon | LISBON | 231D1 | Solar/Battery | 0 | 0 | [10 empty] | 2021-10-14 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 05 - Lewiston Loop - 1 | Hotel Rd/Gulf/Middle St/Crowleys | 3 | 2022-07-19 |  | EXECUTED
563 | 0 | 0 | 0 |  | 2020-10-15 | Hartland | HARTLAND | 824D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Hartland |  |  |  | WITHDRAWN
564 | 0 | 0 | 0 |  | 2020-10-15 | Windsor | COOPERS MILLS ROAD | 230D2 | Solar/Battery | 0 | 0 | [10 empty] | 2022-05-23 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster XX - Midcoast - TBD | Coopers Mills | 3 |  |  | EXECUTED-WITHDRAWN
565 | 0 | 0 | 0 |  | 2020-10-15 | Windham | SWETT ROAD | 682D1 | Solar | 0 | 0 | [10 empty] | 2021-11-11 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 07 - Raymond - 1 | Raymond | 3 | 2023-12-21 |  | EXECUTED-WITHDRAWN
566 | 0 | 0 | 0 |  | 2020-10-15 | Dixfield | LUDDEN LANE | 461D1 | Solar/Battery | 2500 | 0 |  |  |  |  | 2020-11-23 | 2020-02-01 |  |  |  |  | 2021-03-01 | [8 empty] | Q4 2021 | Fully Executed Interconnection Agreement | Yes | 2021-11-04 | Cluster 08 - Sturtevant-Leeds-Livermore-Ludden-Riley - 1 | Ludden Lane | NC | 2021-07-15 |  | #REF!
567 | 0 | 0 | 0 |  | 2020-10-19 | Sanford | HIGH STREET | 626D5 | Solar | 0 | 0 | [10 empty] | 2021-09-23 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 04 - Sanford-Quaker Hill - 1 | Sanford | 3 | 2022-06-27 |  | EXECUTED-WITHDRAWN
568 | 0 | 0 | 0 |  | 2020-10-19 | South Berwick | SOUTH BERWICK | 663D2 | Solar | 0 | 0 | [10 empty] | 2021-10-22 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 04 - Sanford-Quaker Hill - 1 | Quaker Hill | 3 | 2022-06-27 |  | EXECUTED-WITHDRAWN
569 | 0 | 0 | 0 |  | 2020-10-19 | Pownal | GRAY | 416D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Elm St |  |  |  | WITHDRAWN
570 | 0 | 0 | 0 |  | 2020-10-21 | Strong | PHILLIPS/STRONG | 841D1 | Solar | 0 | 0 | [10 empty] | 2021-11-24 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 08 - Sturtevant-Leeds-Livermore-Ludden-Riley - 1 | Sturtevant | 3 | 2023-12-21 |  | EXECUTED-WITHDRAWN
571 | 0 | 0 | 0 |  | 2020-10-21 | Strong | PHILLIPS/STRONG | 841D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Sturtevant/ Leeds/ Livermore/ Ludden/ Riley_TBD | Sturtevant | 3 |  |  | WITHDRAWN
572 | 0 | 0 | 0 |  | 2020-10-29 | Monson | MONSON | 834D1 | Solar | 0 | 0 | [10 empty] | 2023-03-29 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 17 - Detroit Guilford Belfast - 2 | Guilford | 3 |  | Not Required | EXECUTED-WITHDRAWN
573 | 0 | 0 | 0 |  | 2020-10-30 | Searsmont | BELFAST WEST SIDE | 803D6 | Solar | 0 | 0 | [10 empty] | 2022-12-12 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 17 - Detroit Guilford Belfast - 2 | Belfast | 3 |  | Not Required | EXECUTED-WITHDRAWN
574 | 0 | 0 | 0 |  | 2020-11-03 | Pittsfield | DETROIT | 812D1 | Hydro | 0 | 0 | [10 empty] | 2021-08-26 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 06 - Detroit-Guilford-Belfast - 1 | Detroit | 3 |  | Not Required | EXECUTED-WITHDRAWN
575 | 0 | 0 | 0 |  | 2020-11-03 | New Sharon | FARMINGTON FALLS | 818D1 | Solar | 0 | 0 | [10 empty] | 2021-10-05 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 08 - Sturtevant-Leeds-Livermore-Ludden-Riley - 1 | Sturtevant | 3 |  | 2023-12-15 | EXECUTED-WITHDRAWN
576 | 0 | 0 | 0 |  | 2020-11-06 | Rumford | RUMFORD | 447D2 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 10 - Roxbury-Rumford-Woodstock - 1 | Rumford | 3 |  | 2023-12-15 | WITHDRAWN
577 | 0 | 0 | 481 |  | 2020-11-12 | Oakland | COUNTY RD (RICE RIPS) | 873D1 | Solar/Battery | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Winslow/ County Rd/ Lakewood - TBD | Winslow-County Rd | 3 |  |  | RE_QUEUED
578 | 0 | 0 | 0 |  | 2020-11-12 | Windham | SWETT ROAD | 682D1 | Solar | 0 | 0 | [10 empty] | 2023-07-05 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster XX - Raymond - TBD | Raymond | 3 |  |  | EXECUTED-WITHDRAWN
579 | 0 | 0 | 0 |  | 2020-11-12 | Bridgton | WEST BRIDGTON | 458D1 | Solar/Battery | 0 | 0 | [10 empty] | 2021-07-20 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 03 - Kimball Rd-Lovell - 1 | Kimball Road/Lovell | 3 |  | 2023-04-22 | EXECUTED-WITHDRAWN
580 | 0 | 0 | 0 |  | 2020-11-12 | Solon | EMBDEN | 868D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Embden |  |  |  | WITHDRAWN
581 | 0 | 0 | 0 |  | 2020-11-12 | Jay | RILEY | 449D2 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 08 - Sturtevant-Leeds-Livermore-Ludden-Riley - 1 | Riley | 3 |  | 2023-12-15 | WITHDRAWN
582 | 0 | 0 | 0 |  | 2020-11-12 | South Portland | PLEASANT HILL | 644D2 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 15 - Greater Portland - 1 | Pleasant Hill | 3 |  | 2024-03-19 | WITHDRAWN
583 | 0 | 0 | 0 |  | 2020-11-12 | Eliot | ELIOT | 687D1 | Solar | 0 | 0 | [10 empty] | 2021-09-09 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 19 - Sanford-Quaker Hill - 2 | Bolt Hill | NC | 2021-07-15 |  | EXECUTED-WITHDRAWN
584 | 0 | 0 | 0 |  | 2020-11-12 | Sebago | BALDWIN | 691D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 13 - Kimball Rd-Lovell - 2 | Kimball Road/Lovell | 3 |  |  | WITHDRAWN
585 | 0 | 0 | 0 |  | 2020-11-13 | Rockport | CAMDEN | 214D3 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Meadow Road |  |  |  | WITHDRAWN
586 | 0 | 0 | 0 |  | 2020-11-13 | Standish | SHAWS MILL ROAD | 660D2 | Solar | 0 | 0 | [10 empty] | 2021-10-22 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 07 - Raymond - 1 | Raymond | 3 | 2023-12-21 |  | EXECUTED
587 | 0 | 0 | 525 |  | 2020-11-13 | Livermore | LEEDS | 471D1 | Solar | 0 | 0 | [10 empty] | 2023-03-30 | [8 empty] | Q3 2021 | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster XX - Sturtevant/ Leeds/ Livermore/ Ludden/ Riley_TBD | Leeds | 3 |  |  | RE_QUEUED_FullEx
588 | 0 | 0 | 0 |  | 2020-11-19 | Berwick | BASSETT | 602D2 | Solar | 0 | 0 | [10 empty] | 2021-09-22 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 19 - Sanford-Quaker Hill - 2 | Quaker Hill | 3 |  |  | RE_QUEUED_FullEx
589 | 0 | 0 | 0 |  | 2020-11-19 | Parkman | GUILFORD | 821D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 17 - Detroit Guilford Belfast - 2 | Guilford | 3 |  |  | RE_QUEUED
590 | 0 | 0 | 0 |  | 2020-11-24 | Carmel | CARMEL | 808D1 | Solar/Battery | 0 | 0 | [10 empty] | 2023-01-05 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 17 - Detroit Guilford Belfast - 2 | Detroit | 3 |  | Not Required | EXECUTED-WITHDRAWN
591 | 0 | 0 | 0 |  | 2020-11-24 | Eliot | ELIOT | 687D1 | Solar | 0 | 0 | [10 empty] | 2021-12-08 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 19 - Sanford-Quaker Hill - 2 | Bolt Hill | 3 |  |  | EXECUTED-WITHDRAWN
592 | 0 | 0 | 0 |  | 2020-11-30 | Fairfield | FAIRFIELD | 817D3 | Solar/DC BESS | 0 | 0 | [10 empty] | 2021-10-14 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 12 - Winslow-County Rd-Lakewood - 2 | Winslow-County Rd | 3 | 2024-05-28 |  | EXECUTED-WITHDRAWN
593 | 0 | 0 | 0 |  | 2020-12-08 | Parkman | GUILFORD | 821D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 17 - Detroit Guilford Belfast - 2 | Guilford | 3 |  |  | WITHDRAWN
594 | 0 | 0 | 0 |  | 2020-12-08 | Biddeford | MAY STREET | 634D1 | Solar | 0 | 0 | [10 empty] | 2021-06-07 | [8 empty] | Q3 2025 | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 14 - Louden-Biddeford IP - 1 | Biddeford IP | 3 | 2024-02-22 |  | RE_QUEUED_FullEx
595 | 0 | 0 | 0 |  | 2020-12-08 | Chelsea | BOWMAN STREET | 263D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Augusta E-Puddledock-Bowman St - TBD | Augusta E/Puddledock/Bowman St | 3 |  |  | WITHDRAWN
596 | 0 | 0 | 0 |  | 2020-12-08 | Cornish | HIRAM TAP | 692D1 | Solar | 0 | 0 | [10 empty] | 2021-08-18 | [8 empty] | Q2 2022 | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 13 - Kimball Rd-Lovell - 2 | Kimball Road/Lovell | 3 |  |  | RE_QUEUED_STUDY
597 | 0 | 0 | 0 |  | 2020-12-09 | Livermore Falls | LIVERMORE FALLS | 428D2 | Solar | 0 | 0 | [10 empty] | 2022-07-14 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster XX - Sturtevant/ Leeds/ Livermore/ Ludden/ Riley_TBD | Livermore Falls | 3 |  |  | WITHDRAWN
598 | 0 | 0 | 0 |  | 2020-12-09 | Belgrade | NORTH AUGUSTA | 272D6 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Augusta E-Puddledock-Bowman St - TBD | North Augusta | 3 |  |  | WITHDRAWN
599 | 0 | 0 | 0 |  | 2020-12-09 | Lewiston | CHALLENGER 12 KV | 421D2 | Solar | 1975 | 0 |  |  |  |  | 2021-01-12 | 2021-06-09 |  |  |  |  | 2021-07-07 | 2024-01-22 | 2024-03-22 | [6 empty] | Q1 2022 | Fully Executed Interconnection Agreement | Yes | 2023-11-09 | Cluster 05 - Lewiston Loop - 1 | Challenger Dr | 3 | 2022-07-19 |  | RE_QUEUED_FullEx
600 | 0 | 0 | 0 |  | 2020-12-09 | Westbrook | PRIDES CORNER | 647D1 | Solar | 0 | 0 | [10 empty] | 2021-07-08 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 15 - Greater Portland - 1 | Moshers/Prides Corner | 3 | 2024-02-22 |  | EXECUTED
601 | 0 | 0 | 0 |  | 2020-12-09 | Freeport | FREEPORT | 225D3 | Solar | 0 | 0 | [10 empty] | 2021-10-20 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 15 - Greater Portland - 1 | Elm St | 3 |  | 2024-03-19 | EXECUTED-WITHDRAWN
602 | 0 | 0 | 0 |  | 2020-12-14 | Andover | ANDOVER | 400D1 | Solar | 0 | 0 | [10 empty] | 2021-09-16 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 10 - Roxbury-Rumford-Woodstock - 1 | Roxbury | 3 |  | 2023-12-15 | EXECUTED-WITHDRAWN
603 | 0 | 0 | 0 |  | 2020-12-14 | Alna | SHEEPSCOT | 241D1 | Solar | 2875 | 0 |  |  |  |  | 2021-02-04 | 2021-05-12 |  |  |  |  | 2021-07-28 | [9 empty] | Fully Executed Interconnection Agreement | Yes | 2023-10-04 | Cluster 09 - Midcoast - 1 | Mason | 3 | 2023-12-21 |  | EXECUTED
604 | 0 | 0 | 0 |  | 2020-12-14 | Mechanic Falls | MECHANIC FALLS | 431D1 | Solar | 0 | 0 | [10 empty] | 2021-01-18 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 18 - Lewiston Loop - 2 | Norway | 3 |  |  | EXECUTED-WITHDRAWN
605 | 0 | 0 | 0 |  | 2020-12-15 | Wilton | EAST WILTON | 816D1 | Solar | 0 | 0 | [10 empty] | 2021-08-02 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 08 - Sturtevant-Leeds-Livermore-Ludden-Riley - 1 | Sturtevant | 3 | 2023-12-21 |  | EXECUTED-WITHDRAWN
606 | 0 | 0 | 0 |  | 2020-12-15 | Rumford | RUMFORD | 447D1 | Solar | 0 | 0 | [10 empty] | 2021-11-26 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster XX - Woodstock/ Roxbury/ Rumford - TBD | Rumford | 3 |  |  | EXECUTED-WITHDRAWN
607 | 0 | 0 | 0 |  | 2020-12-15 | Winthrop | WINTHROP | 256D2 | Solar | 0 | 0 |  |  |  |  | 2021-07-28 | 2021-09-22 |  |  |  |  | 2021-11-24 | [9 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Augusta E-Puddledock-Bowman St - TBD | Augusta E/Puddledock/Bowman St | 3 |  |  | EXECUTED-WITHDRAWN
608 | 0 | 0 | 0 |  | 2020-12-15 | Wiscasset | MESSINA | 238D1 | Solar | 975 | 0 |  |  |  |  | 2021-01-21 | 2021-06-17 | 2023-12-27 | 2024-02-08 |  | 2023-09-11 | 2021-08-02 | 2023-04-26 | 2023-06-07 | [6 empty] | Q4 2025 | Fully Executed Interconnection Agreement | Yes | 2024-09-09 | Cluster 09 - Midcoast - 1 | Mason | 3 | 2023-12-21 | Not Required | RE_QUEUED_FullEx
609 | 0 | 0 | 0 |  | 2020-12-15 | Waldoboro | WALDOBORO | 252D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 09 - Midcoast - 1 | Highland/Park St | 3 |  | 2023-12-15 | WITHDRAWN
610 | 0 | 0 | 0 |  | 2020-12-17 | Gorham | FORT HILL | 624D2 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Raymond - TBD | Raymond | 3 |  |  | WITHDRAWN
611 | 0 | 0 | 0 |  | 2020-12-17 | Turner | DEER RIPS | 412D3 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 18 - Lewiston Loop - 2 | Hotel Rd/Gulf/Middle St/Crowleys | 3 |  |  | WITHDRAWN
612 | 0 | 0 | 0 |  | 2020-12-17 | Farmington | STURTEVANT | 858D4 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Sturtevant/ Leeds/ Livermore/ Ludden/ Riley_TBD | Sturtevant | 3 |  |  | RE_QUEUED
613 | 0 | 0 | 0 |  | 2020-12-17 | North Berwick | PRATT & WHITNEY | 661D1 | Solar | 0 | 0 | [10 empty] | 2021-10-12 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 04 - Sanford-Quaker Hill - 1 | Pratt & Whitney | 3 | 2022-06-27 |  | EXECUTED-WITHDRAWN
614 | 0 | 0 | 0 |  | 2020-12-21 | Rockland | PARK STREET | 239D6 | Solar/DC BESS | 0 | 0 |  |  |  |  | 2021-12-13 | 2022-02-17 | [14 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Midcoast - TBD | Highland/Park St | 3 |  |  | WITHDRAWN
615 | 0 | 0 | 0 |  | 2020-12-21 | Hartland | HARTLAND | 824D1 | Solar/DC BESS | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Hartland |  |  |  | WITHDRAWN
616 | 0 | 0 | 0 |  | 2020-12-21 | Penobscot | BUCKSPORT | 806D2 | Solar/DC BESS | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Bucksport |  |  |  | WITHDRAWN
617 | 0 | 0 | 0 |  | 2020-12-21 | Lincolnville | LINCOLNVILLE | 800D1 | Solar | 0 | 0 | [10 empty] | 2021-01-18 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 09 - Midcoast - 1 | Lincolnville | 3 | 2023-12-21 |  | EXECUTED
618 | 0 | 0 | 0 |  | 2020-12-21 | Pittsfield | DETROIT | 812D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 17 - Detroit Guilford Belfast - 2 | Detroit | 3 |  | Not Required | WITHDRAWN
619 | 0 | 0 | 0 |  | 2020-12-21 | Westbrook | WESTBROOK | 674D2 | Solar | 0 | 0 | [10 empty] | 2022-05-26 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 15 - Greater Portland - 1 | Moshers/Prides Corner | 3 | 2024-02-22 |  | EXECUTED
620 | 0 |  | 600 |  | 2020-12-21 | Westbrook | PRIDES CORNER | 647D3 | Solar | 999 | 0 |  |  |  |  | 2022-09-23 | 2022-12-01 | 2023-02-09 | 2023-03-21 |  |  | 2023-05-01 | 2024-09-20 | 2024-11-26 | [6 empty] | Q4 2025 | Fully Executed Interconnection Agreement | Yes | 2023-10-13 | Cluster XX - Greater Portland - TBD | Moshers/Prides Corner | 3 |  | Not Required | RE_QUEUED_Fullex
621 | 0 | 0 | 0 |  | 2020-12-21 | New Vineyard | NEW VINEYARD | 836D1 | Solar | 0 | 0 | [10 empty] | 2021-10-12 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 08 - Sturtevant-Leeds-Livermore-Ludden-Riley - 1 | Sturtevant | 3 |  | 2023-12-15 | EXECUTED-WITHDRAWN
622 | 0 | 0 | 0 |  | 2020-12-23 | Waldoboro | MANKTOWN ROAD | 234D1 | Solar | 0 | 0 | [10 empty] | 2021-10-28 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 09 - Midcoast - 1 | Highland/Park St | 3 |  | 2023-12-15 | EXECUTED-WITHDRAWN
623 | 0 | 0 | 0 |  | 2020-12-29 | Livermore | LIVERMORE FALLS | 428D2 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Sturtevant/ Leeds/ Livermore/ Ludden/ Riley_TBD | Livermore Falls | 3 |  |  | WITHDRAWN
624 | 0 | 0 | 0 |  | 2020-12-29 | West Baldwin | HIRAM HYDRO | 419D1 | Solar | 0 | 0 | [10 empty] | 2021-12-09 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 13 - Kimball Rd-Lovell - 2 | Kimball Road/Lovell | 3 |  |  | EXECUTED
625 | 0 | 0 | 0 |  | 2021-01-05 | Belfast | BELFAST WEST SIDE | 803D6 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 17 - Detroit Guilford Belfast - 2 | Belfast | 3 |  |  | WITHDRAWN
626 | 0 | 0 | 0 |  | 2021-01-07 | Scarborough | DUNSTAN | 617D3 | Solar | 1950 | 0 |  |  |  |  | 2021-02-17 | 2021-06-29 |  |  |  |  | 2021-07-07 | 2023-08-10 | 2023-11-02 | [7 empty] | Fully Executed Interconnection Agreement | Yes | 2023-06-06 | Cluster 14 - Louden-Biddeford IP - 1 | Vallee Lane | NC | 2021-11-08 |  | RE_QUEUED_FullEx
627 | 0 | 0 | 0 |  | 2021-01-07 | Chelsea | CONY ROAD | 216D2 | Solar | 0 | 0 | [10 empty] | 2021-10-26 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 11 - Augusta E-Puddledock-Bowman St - 2 | Augusta E/Puddledock/Bowman St | 3 | 2024-05-28 |  | EXECUTED
628 | 0 | 0 | 0 |  | 2021-01-13 | Warren | THOMASTON CREEK | 246D3 | Solar | 0 | 0 | [10 empty] | 2022-07-14 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster XX - Midcoast - TBD | Highland/Park St | 3 |  |  | EXECUTED
629 | 0 | 0 | 0 |  | 2021-01-13 | Bridgton | BRIDGTON | 406D1 | Solar | 0 | 0 | [10 empty] | 2021-10-12 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 13 - Kimball Rd-Lovell - 2 | Kimball Road/Lovell | 3 |  |  | EXECUTED-WITHDRAWN
630 | 0 | 0 | 0 |  | 2021-01-25 | West Bath | BATH 34 | 261D3 | Solar | 0 | 0 | [10 empty] | 2021-10-28 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 09 - Midcoast - 1 | Bath | 3 | 2023-12-21 |  | EXECUTED-WITHDRAWN
631 | 0 |  | 0 |  | 2021-01-25 | Scarborough | DUNSTAN | 617D2 | Solar | 999 | 0 |  |  |  |  | 2021-08-20 | 2021-10-26 |  |  |  |  | 2021-11-11 | 2024-09-10 | 2024-11-11 | [6 empty] | Q3 2026 | Fully Executed Interconnection Agreement | Yes | 2022-11-08 | Cluster 14 - Louden-Biddeford IP - 1 | Vallee Lane | 3 | 2024-02-22
632 | 0 | 0 | 0 |  | 2021-01-26 | Starks | ANSON | 801D1 | Solar | 0 | 0 | [10 empty] | 2021-09-01 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 12 - Winslow-County Rd-Lakewood - 2 | Lakewood | 3 | 2024-05-28 |  | RE_QUEUED_FullEx
633 | 0 | 0 | 0 |  | 2021-01-27 | Sanford | SANFORD SWITCH | 657D3 | Solar | 0 | 0 | [10 empty] | 2021-07-20 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 19 - Sanford-Quaker Hill - 2 | Sanford | 3 |  |  | EXECUTED-WITHDRAWN
634 | 0 | 0 | 0 |  | 2021-01-27 | Richmond | RICHMOND | 240D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Augusta E/Puddledock/Bowman St |  |  |  | WITHDRAWN
635 | 0 | 0 | 0 |  | 2021-01-29 | Avon | PHILLIPS/STRONG | 841D1 | Solar | 0 | 0 |  |  |  |  | 2022-03-07 | 2022-05-02 | 2022-07-15 |  |  |  |  | 2023-01-13 | [8 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Sturtevant/ Leeds/ Livermore/ Ludden/ Riley_TBD | Sturtevant | 3 |  | Not Required | WITHDRAWN
636 | 0 | 0 | 0 |  | 2021-02-02 | Windham | PRIDES CORNER | 647D2 | Solar | 0 | 0 |  |  |  |  | 2023-06-15 | 2023-08-23 | [14 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Greater Portland - TBD | Moshers/Prides Corner | 3 |  |  | WITHDRAWN
637 | 0 | 0 | 0 |  | 2021-02-02 | Cape Elizabeth | CAPE ELIZABETH | 613D1 | Solar | 900 | 0 |  |  |  |  | 2021-03-09 | 2021-06-29 |  |  |  |  | 2021-07-29 | [8 empty] | Q4 2025 | Fully Executed Interconnection Agreement | No | 2023-01-18 | Cluster 15 - Greater Portland - 1 | Pleasant Hill | 3 |  | Not Required | EXECUTED
638 | 0 | 0 | 0 |  | 2021-02-03 | Newport | NEWPORT | 837D1 | Solar | 0 | 0 |  |  |  |  | 2022-08-11 | 2022-10-13 | 2022-11-30 | 2023-01-12 |  |  |  | 2024-03-21 | 2024-05-17 | [7 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 17 - Detroit Guilford Belfast - 2 | Detroit | 3 |  |  | WITHDRAWN
639 | 0 | 0 | 0 |  | 2021-02-11 | Windham | NORTH WINDHAM | 639D2 | Solar | 0 | 0 | [10 empty] | 2021-10-20 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster XX - Raymond - TBD | Raymond | 3 |  |  | EXECUTED-WITHDRAWN
640 | 0 | 0 | 0 |  | 2021-02-02 | Durham | LISBON FALLS | 232D2 | Solar | 0 | 0 | [10 empty] | 2022-01-13 | [8 empty] | Q4 2022 | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 18 - Lewiston Loop - 2 | Hotel Rd/Gulf/Middle St/Crowleys | 3 |  |  | RE_QUEUED_FullEx
641 | 0 | 0 | 0 |  | 2021-02-15 | Searsport | SEARSPORT | 850D2 | Solar | 0 | 0 | [10 empty] | 2021-12-21 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 17 - Detroit Guilford Belfast - 2 | Belfast | 3 |  |  | EXECUTED-WITHDRAWN
642 | 0 | 0 | 0 |  | 2021-02-15 | Newcastle | DAMARISCOTTA MILLS | 219D2 | Solar | 0 | 0 | [10 empty] | 2021-11-29 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 09 - Midcoast - 1 | Newcastle | 3 | 2023-12-21 |  | EXECUTED-WITHDRAWN
643 | 0 | 0 | 0 |  | 2021-02-15 | Topsham | LISBON FALLS | 232D2 | Solar | 0 | 0 |  |  |  |  | 2022-02-02 | 2022-04-14 |  |  |  | 2022-10-07 | 2022-11-17 | 2023-08-11 | 2023-09-26 | [7 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 18 - Lewiston Loop - 2 | Hotel Rd/Gulf/Middle St/Crowleys | 3 |  | Not Required | RE_QUEUED_FullEx
644 | 0 | 0 | 0 |  | 2021-02-16 | West Bath | BATH 34 | 261D3 | Solar | 0 | 0 |  |  |  |  | 2022-02-02 | 2022-04-14 | 2022-05-31 | 2022-07-11 |  |  | 2022-07-29 | 2023-10-24 | 2023-12-12 | 2024-08-08 | 2024-09-27 |  |  |  |  | Q4 2026 | WITHDRAWN | WITHDRAWN |  | Cluster XX - Midcoast - TBD | Bath | 3 |  | Not Required | RE_QUEUED_FullEx
645 | 0 | 0 | 0 |  | 2021-02-18 | Naples | NAPLES TAP | 469D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Raymond |  |  |  | WITHDRAWN
646 | 0 | 0 | 0 |  | 2021-02-18 | Skowhegan | SKOWHEGAN SOUTH SIDE | 854D2 | Solar | 0 | 0 | [10 empty] | 2022-08-10 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 12 - Winslow-County Rd-Lakewood - 2 | Lakewood | 3 | 2024-05-28 |  | EXECUTED-WITHDRAWN
647 | 0 | 0 | 0 |  | 2021-02-18 | Farmington | STURTEVANT | 858D3 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Sturtevant/ Leeds/ Livermore/ Ludden/ Riley_TBD | Sturtevant | 3 |  |  | RE_QUEUED
648 | 0 | 0 | 0 |  | 2021-02-24 | Winthrop | MANCHESTER | 233D2 | Solar | 0 | 0 | [10 empty] | 2022-07-06 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 11 - Augusta E-Puddledock-Bowman St - 2 | Augusta E/Puddledock/Bowman St | 3 |  | Not Required | RE_QUEUED_FullEx
649 | 0 | 0 | 0 |  | 2021-03-02 | Lewiston | SABATTUS | 450D2 | Solar | 0 | 0 | [10 empty] | 2022-01-31 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 18 - Lewiston Loop - 2 | Hotel Rd/Gulf/Middle St/Crowleys | 3 |  |  | RE_QUEUED_FullEx
650 | 0 | 0 | 0 |  | 2021-03-10 | Waterford | PAPOOSE POND | 438D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 13 - Kimball Rd-Lovell - 2 | Kimball Road/Lovell | 3 |  |  | WITHDRAWN
651 | 0 | 0 | 0 |  | 2021-03-15 | Kittery | KITTERY | 688D1 | Solar | 0 | 0 | [10 empty] | 2021-08-16 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 19 - Sanford-Quaker Hill - 2 | Bolt Hill | NC | 2021-11-23 |  | EXECUTED-WITHDRAWN
652 | 0 | 0 | 390 |  | 2021-03-24 | Bucksport | BUCKSPORT | 806D1 | Solar/Battery | 1990 | 0 |  |  |  |  | 2021-05-04 | 2021-07-12 | 2021-08-19 | 2021-10-01 |  |  | 2021-12-07 | 2023-03-02 | 2023-04-12 | [7 empty] | Fully Executed Interconnection Agreement | Yes | 2023-05-25 | Cluster 06 - Detroit-Guilford-Belfast - 1 | Bucksport | 3 | 2023-05-31 |  | RE_QUEUED_FullEx
653 | 0 | 0 | 0 |  | 2021-03-26 | Winthrop | WINTHROP | 256D2 | Solar | 975 | 0 |  |  |  |  | 2022-01-21 | 2022-03-04 |  |  |  | 2022-10-03 | 2022-11-21 | 2024-02-28 | 2024-04-29 | [6 empty] | Q3 2025 | Fully Executed Interconnection Agreement | Yes | 2024-10-04 | Cluster XX - Augusta E-Puddledock-Bowman St - TBD | Augusta E/Puddledock/Bowman St | 3 |  | Not Required | RE_QUEUED_FullEx
654 | 0 | 0 | 0 |  | 2021-03-26 | Roxbury | RUMFORD | 447D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Woodstock/ Roxbury/ Rumford - TBD | Rumford | 3 |  |  | WITHDRAWN
655 | 0 | 0 | 0 |  | 2021-03-29 | Orland | BUCKSPORT | 806D1 | Solar/Battery | 0 | 0 |  |  |  |  | 2022-02-04 | 2022-04-14 | [14 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 17 - Detroit Guilford Belfast - 2 | Bucksport | 3 |  |  | WITHDRAWN
656 | 0 | 0 | 0 |  | 2021-03-30 | Naples | RAYMOND 115 KV | 445D2 | Solar | 0 | 0 | [10 empty] | 2021-11-05 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster XX - Raymond - TBD | Raymond | 3 |  |  | EXECUTED-WITHDRAWN
657 | 0 | 0 | 0 |  | 2021-04-02 | Dexter | DEXTER | 813D3 | Solar/Battery | 996 | 0 |  |  |  |  | 2021-11-23 | 2022-01-28 | 2022-03-30 | 2022-05-11 |  |  | 2022-07-06 | 2025-04-16 | 2025-06-18 | 2026-02-09 | 2026-03-20 | [5 empty] | Fully Executed Interconnection Agreement | No |  | Cluster 17 - Detroit Guilford Belfast - 2 | Guilford | 3 |  |  | RE_QUEUED_FullEx
658 | 0 | 0 | 0 |  | 2021-04-02 | South Berwick | SOUTH BERWICK | 663D2 | Solar | 0 | 0 |  |  |  |  | 2022-01-04 | 2022-03-11 | 2022-05-25 | 2022-07-15 |  |  | 2022-07-25 | 2023-04-20 | 2023-06-05 | 2023-07-21 | 2023-09-01 | 2023-12-22 | 2024-02-29 |  |  | Q3 2025 | WITHDRAWN | WITHDRAWN |  | Cluster 19 - Sanford-Quaker Hill - 2 | Quaker Hill | 3 |  | Not Required | RE_QUEUED_FullEx
659 | 0 | 0 | 0 |  | 2021-04-12 | Monmouth | MONMOUTH | 457D2 | Solar/Battery | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Monmouth |  |  |  | WITHDRAWN
660 | 0 | 0 | 0 |  | 2021-04-15 | Brunswick | COOKS CORNER | 217D3 | Solar | 0 | 0 | [10 empty] | 2021-08-10 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster XX - Midcoast - TBD | Topsham | 3 |  |  | EXECUTED-WITHDRAWN
661 | 0 | 0 | 0 |  | 2021-04-22 | Sangerville | GUILFORD | 821D3 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 17 - Detroit Guilford Belfast - 2 | Guilford | 3 |  |  | RE_QUEUED
662 | 0 | 0 | 0 |  | 2021-04-22 | Bath | BATH NORTH END | 206D1 | Solar | 0 | 0 |  |  |  |  | 2021-06-16 | 2021-08-16 |  |  |  | 2022-01-06 | 2022-06-03 | [9 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Midcoast - TBD | Bath | 3 |  |  | EXECUTED
663 | 0 | 0 | 0 |  | 2021-04-22 | Skowhegan | SKOWHEGAN SOUTH SIDE | 854D2 | Solar | 0 | 0 |  |  |  |  | 2022-09-09 | 2022-11-08 |  |  |  | 2023-05-26 | [10 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Winslow/ County Rd/ Lakewood - TBD | Lakewood | 3 |  |  | WITHDRAWN
664 | 0 | 0 | 0 |  | 2021-04-30 | Bath | BATH 34 | 261D3 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Midcoast - TBD | Bath | 3 |  |  | WITHDRAWN
665 | 0 | 0 | 0 |  | 2021-04-30 | Raymond | RAYMOND 34 KV | 444D1 | Solar | 0 | 0 | [10 empty] | 2021-09-01 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster XX - Raymond - TBD | Raymond | 3 |  |  | EXECUTED-WITHDRAWN
666 | 0 | 0 | 0 |  | 2021-04-30 | Gorham | MOSHERS | 635D2 | Hydro | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Moshers/Prides Corner |  |  |  | WITHDRAWN
667 | 0 | 0 | 0 |  | 2021-04-30 | Standish | NORTH WINDHAM | 639D2 | Hydro | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | N/A | Raymond |  |  |  | WITHDRAWN
668 | 0 | 0 | 0 |  | 2021-04-30 | Casco | SAND ROAD TAP | 470D1 | Solar | 0 | 0 | [10 empty] | 2021-12-10 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster XX - Raymond - TBD | Raymond | 3 |  |  | EXECUTED-WITHDRAWN
669 | 0 | 0 | 648 |  | 2021-05-25 | Manchester | MANCHESTER | 233D1 | Solar | 975 | 0 |  |  |  |  | 2022-09-15 | 2022-11-21 |  |  |  |  | 2025-01-08 | 2024-10-18 | 2024-12-16 | [6 empty] | Q4 2023 | Fully Executed Interconnection Agreement | No | 2025-05-29 | Cluster XX - Augusta E-Puddledock-Bowman St - TBD | Augusta E/Puddledock/Bowman St | 3 |  | Not Required | RE_QUEUED
670 | 0 | 0 | 0 |  | 2021-05-28 | Thorndike | THORNDIKE TAP | 857D1 | Solar | 0 | 0 |  |  |  |  | 2021-07-28 | 2021-10-12 | 2021-12-02 | 2022-01-18 |  | 2022-04-22 | 2022-07-08 | [9 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 17 - Detroit Guilford Belfast - 2 | Belfast | 3 |  |  | EXECUTED
671 | 0 | 0 | 0 |  | 2021-05-28 | Richmond | RICHMOND | 240D1 | Solar | 0 | 0 | [10 empty] | 2022-02-04 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster XX - Augusta E-Puddledock-Bowman St - TBD | Augusta E/Puddledock/Bowman St | 3 |  |  | EXECUTED-WITHDRAWN
672 | 0 | 0 | 0 |  | 2021-06-21 | Newport | NEWPORT | 837D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 17 - Detroit Guilford Belfast - 2 | Detroit | 3 |  |  | WITHDRAWN
673 | 0 | 0 | 0 |  | 2021-06-21 | Gorham | MOSHERS | 635D2 | Hydro | 3990 | 0 |  |  |  |  | 2021-08-13 | 2021-10-19 |  |  |  |  | 2021-12-08 | [9 empty] | Fully Executed Interconnection Agreement | Yes | 2024-08-02 | Cluster 15 - Greater Portland - 1 | Moshers/Prides Corner | 3 | 2024-02-22 |  | EXECUTED
674 | 0 |  | 0 |  | 2021-06-21 | Standish | NORTH WINDHAM | 639D3 | Hydro | 4200 | 0 |  |  |  |  | 2021-12-21 | 2022-02-28 |  |  |  |  | 2022-03-25 | 2023-06-30 |  | 2024-04-25 | 2024-07-01 |  |  |  |  | Q4 2025 | Fully Executed Interconnection Agreement | Yes | 2024-08-20 | Cluster XX - Raymond - TBD | Raymond | 3 |  | Not Required | RE_QUEUED_FullEx
675 | 0 | 0 | 0 |  | 2021-07-02 | Boothbay | BOOTHBAY HARBOR | 209D3 | Solar | 0 | 0 | [10 empty] | 2021-10-26 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster XX - Midcoast - TBD | Mason | 3 |  |  | EXECUTED-WITHDRAWN
676 | 0 | 0 | 0 |  | 2021-07-02 | Lincolnville | LINCOLNVILLE | 800D1 | Solar | 0 | 0 |  |  |  |  | 2022-04-22 | 2022-05-23 | 2022-08-12 | 2022-09-22 |  |  | 2022-10-14 | 2024-10-31 | 2025-01-10 | [6 empty] | Q4 2025 | WITHDRAWN | WITHDRAWN |  | Cluster XX - Midcoast - TBD | Lincolnville | 3 |  |  | EXECUTED
677 | 0 | 0 | 0 |  | 2021-07-07 | Wales | MONMOUTH | 457D1 | Solar | 0 | 0 |  |  |  |  | 2022-04-06 | 2022-06-03 | 2022-07-27 |  |  |  |  | 2023-01-13 | 2023-02-27 | [7 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Augusta E-Puddledock-Bowman St - TBD | Monmouth | 3 |  | Not Required | WITHDRAWN
678 | 0 | 0 | 0 |  | 2021-07-16 | Acton | BUTLER'S CORNER | 612D2 | Solar | 0 | 0 | [10 empty] | 2021-12-08 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 19 - Sanford-Quaker Hill - 2 | Sanford | 3 |  |  | EXECUTED-WITHDRAWN
679 | 0 | 0 | 0 |  | 2021-07-20 | Buxton | BONNY EAGLE | 610D2 | Solar | 0 | 0 |  |  |  |  | 2022-06-06 | 2022-07-26 | [14 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 13 - Kimball Rd-Lovell - 2 | Kimball Road/Lovell | 3 |  |  | WITHDRAWN
680 | 0 | 0 | 0 |  | 2021-07-20 | Livermore Falls | LIVERMORE FALLS | 428D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Sturtevant/ Leeds/ Livermore/ Ludden/ Riley_TBD | Livermore Falls | 3 |  |  | WITHDRAWN
681 | 0 | 0 | 0 |  | 2021-07-22 | Arundel | KENNEBUNKPORT | 629D3 | Solar | 0 | 0 | 2021-11-24 | 2021-12-28 | [18 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 14 - Louden-Biddeford IP - 1 | Biddeford IP | 3 |  | 2024-03-19 | WITHDRAWN
682 | 0 | 0 | 0 |  | 2021-08-11 | Corinna | CORINNA | 811D1 | Solar | 0 | 0 |  |  |  |  | 2021-12-23 | [15 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 17 - Detroit Guilford Belfast - 2 | Detroit | 3 |  | Not Required | WITHDRAWN
683 | 0 | 0 | 0 |  | 2021-08-16 | Boothbay Harbor | BOOTHBAY HARBOR | 209D2 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Midcoast - TBD | Mason | 3 |  |  | WITHDRAWN
684 | 0 | 0 | 0 |  | 2021-08-16 | Clinton | CLINTON | 810D1 | Solar | 0 | 0 |  |  |  |  | 2021-10-15 | 2021-11-30 |  |  |  |  | 2022-01-03 | [9 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Winslow/ County Rd/ Lakewood - TBD | Winslow-County Rd | 3 |  |  | EXECUTED-WITHDRAWN
685 | 0 | 0 | 0 |  | 2021-08-24 | Yarmouth | ELM STREET | 620D2 | Solar | 0 | 0 |  |  |  |  | 2021-12-15 | 2022-02-22 |  |  |  |  | 2022-05-26 | 2023-04-19 | [8 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Greater Portland - TBD | Elm St | 3 |  |  | EXECUTED-WITHDRAWN
686 | 0 | 0 | 0 |  | 2021-09-14 | Windham | PRIDES CORNER | 647D3 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Greater Portland - TBD | Moshers/Prides Corner | 3 |  |  | WITHDRAWN
687 | 0 | 0 | 0 |  | 2021-10-19 | Embden | EMBDEN | 868D1 | Solar | 0 | 0 | [10 empty] | 2022-11-02 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster XX - Wyman Area - TBD | Embden | 3 |  |  | EXECUTED-WITHDRAWN
688 | 0 | 0 | 0 |  | 2021-10-25 | Windham | NORTH WINDHAM | 639D2 | Solar | 0 | 0 | [10 empty] | 2022-11-29 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster XX - Raymond - TBD | Raymond | 3 |  | Not Required | EXECUTED-WITHDRAWN
689 | 0 | 0 | 0 |  | 2021-11-30 | Lebanon | LEBANON | 695D2 | Solar | 0 | 0 | [10 empty] | 2022-08-12 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 19 - Sanford-Quaker Hill - 2 | Sanford | 3 |  |  | EXECUTED-WITHDRAWN
690 | 0 | 0 | 0 |  | 2021-11-30 | North Yarmouth | ELM STREET | 620D4 | Solar | 0 | 0 | [10 empty] | 2022-11-17 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster XX - Greater Portland - TBD | Elm St | 3 |  |  | EXECUTED-WITHDRAWN
691 | 0 | 0 | 0 |  | 2021-12-01 | Lewiston | SABATTUS | 450D1 | Solar | 0 | 0 | [10 empty] | 2022-06-14 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 18 - Lewiston Loop - 2 | Hotel Rd/Gulf/Middle St/Crowleys | 3 |  | Not Required | EXECUTED-WITHDRAWN
692 | 0 | 0 | 0 |  | 2021-12-13 | Readfield | PUDDLEDOCK ROAD | 262D1 | Solar | 0 | 0 |  |  |  |  | 2022-02-02 | 2022-03-29 |  |  |  | 2022-08-31 | 2022-11-17 | [9 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Augusta E-Puddledock-Bowman St - TBD | Augusta E/Puddledock/Bowman St | 3 |  |  | EXECUTED-WITHDRAWN
693 | 0 | 0 | 0 |  | 2021-12-21 | Waldoboro | WALDOBORO | 252D1 | Solar | 0 | 0 |  |  |  |  | 2022-02-16 | 2022-04-25 | [14 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 09 - Midcoast - 1 | Highland/Park St | 3 |  | 2023-12-15 | WITHDRAWN
694 | 0 | 0 | 0 |  | 2021-12-22 | Eustis | STRATTON | 877D1 | Solar/DC BESS | 0 | 0 | [10 empty] | 2022-08-08 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster XX - Wyman Area - TBD | Bigelow | 3 |  |  | EXECUTED
695 | 0 | 0 | 0 |  | 2022-01-07 | Skowhegan | WESTON HYDRO | 866D2 | Solar | 0 | 0 |  |  |  |  | 2022-02-14 | 2022-04-20 | 2022-06-28 |  |  |  |  | 2023-04-17 | [8 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Winslow/ County Rd/ Lakewood - TBD | Lakewood | 3 |  |  | WITHDRAWN
696 | 0 | 0 | 0 |  | 2022-01-12 | Eliot | ELIOT | 687D1 | Solar | 0 | 0 | 2022-03-21 | 2022-04-26 | 2022-06-28 | [17 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 19 - Sanford-Quaker Hill - 2 | Bolt Hill | 3 |  |  | WITHDRAWN
697 | 0 | 0 | 0 |  | 2022-01-24 | Athens | ATHENS | 827D1 | Solar | 0 | 0 | [10 empty] | 2022-06-14 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster XX - Wyman Area - TBD | Athens | 3 |  |  | EXECUTED-WITHDRAWN
698 | 0 | 0 | 265 |  | 2022-01-24 | Oakland | OAKLAND | 839D2 | Solar | 999 | 0 |  |  |  |  | 2023-02-06 | 2023-04-11 |  |  |  |  | 2023-05-03 | [8 empty] | Q2 2026 | Fully Executed Interconnection Agreement | No | 2023-11-22 | Cluster XX - Winslow/ County Rd/ Lakewood - TBD | Winslow-County Rd | 3 |  | Not Required | RE_QUEUED_FullEx
699 | 0 | 0 | 0 |  | 2022-01-24 | Oxford | OXFORD | 437D1 | Solar | 0 | 0 |  |  |  |  | 2022-03-16 | 2022-05-18 |  |  |  |  | 2022-07-14 | [8 empty] | Q1 2026 | Fully Executed Interconnection Agreement | No | 2022-08-16 | Cluster 18 - Lewiston Loop - 2 | Norway | 3 |  |  | EXECUTED
700 | 0 | 0 | 0 |  | 2022-01-25 | Skowhegan | WESTON HYDRO | 866D1 | Solar | 0 | 0 |  |  |  |  | 2023-07-28 | 2023-10-04 | [14 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Winslow/ County Rd/ Lakewood - TBD | Lakewood | 3 |  |  | WITHDRAWN
701 | 0 | 0 | 611 |  | 2022-02-01 | Lewiston | DEER RIPS | 412D4 | Solar | 0 | 0 |  |  |  |  | 2024-09-23 | 2024-11-27 |  |  |  |  | 2025-02-05 | [8 empty] | Q4 2025 | WITHDRAWN | WITHDRAWN |  | Cluster 18 - Lewiston Loop - 2 | Hotel Rd/Gulf/Middle St/Crowleys/Norway | 3 |  |  | RE_QUEUED_SCOPING
702 | 0 | 0 | 655 |  | 2022-02-04 | Bucksport | BUCKSPORT | 806D2 | Solar | 0 | [11 empty] | 2024-01-29 | [8 empty] | Q4 2024 | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 17 - Detroit Guilford Belfast - 2 | Bucksport | 3 |  |  | RE_QUEUED_FullEx
703 | 0 | 0 | 0 |  | 2022-02-09 | Baldwin | BALDWIN | 691D1 | Solar | 0 | 0 | [10 empty] | 2022-05-18 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 13 - Kimball Rd-Lovell - 2 | Kimball Road/Lovell | 3 |  | Not Required | EXECUTED-WITHDRAWN
704 | 0 | 0 | 0 |  | 2022-02-16 | Bethel | LOCKES MILLS | 429D1 | Solar | 0 | 0 | [10 empty] | 2022-10-18 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster XX - Woodstock/ Roxbury/ Rumford - TBD | Woodstock | 3 |  |  | EXECUTED-WITHDRAWN
705 | 0 | 0 | 0 |  | 2022-02-17 | Peru | RUMFORD INDUSTRIAL PARK | 466D1 | Solar | 0 | 0 |  |  |  |  | 2022-03-30 | 2022-05-25 | [14 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Woodstock/ Roxbury/ Rumford - TBD | Rumford IP | 3 |  |  | WITHDRAWN
706 | 1151 | 0 | 0 |  | 2022-03-10 | Woodstock | BRYANT POND | 407D1 | Solar | 1968 | 0 |  |  |  |  | 2022-03-10 | 2022-05-11 |  |  |  |  | 2023-06-12 | [9 empty] | Fully Executed Interconnection Agreement | Yes | 2023-07-21 | N/A | Woodstock | 3 | N/A |  | EXECUTED
707 | 1169 | 0 | 606 |  | 2022-03-10 | Roxbury | RUMFORD | 447D1 | Solar | 0 | 0 | [10 empty] | 2023-09-26 | [8 empty] | Q3 2024 | EXECUTED-WITHDRAWN | No | 2023-11-13 | Cluster XX - Woodstock/ Roxbury/ Rumford - TBD | Rumford | 3 |  | Not Required | RE_QUEUED_RESULTS
708 | 0 | 0 | 0 |  | 2022-03-17 | Fryeburg | FRYEBURG TAP | 405D1 | Solar | 0 | 0 | [10 empty] | 2022-08-04 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 13 - Kimball Rd-Lovell - 2 | Kimball Road/Lovell | 3 |  |  | EXECUTED-WITHDRAWN
709 | 0 | 0 | 0 |  | 2022-03-18 | Woolwich | WOOLWICH | 258D1 | Solar | 0 | 0 | [10 empty] | 2022-08-04 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster XX - Midcoast - TBD | Bath | 3 |  |  | EXECUTED-WITHDRAWN
710 | 0 | 0 | 0 |  | 2022-03-31 | Topsham | TOPSHAM 34 KV | 250D1 | Solar | 0 | 0 | [10 empty] | 2022-09-08 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster XX - Midcoast - TBD | Topsham | 3 |  | Not Required | EXECUTED-WITHDRAWN
711 | 0 | 0 | 0 |  | 2022-04-07 | Casco | RAYMOND 115 KV | 445D1 | Solar | 0 | 0 | [10 empty] | 2022-09-09 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster XX - Raymond - TBD | Raymond | 3 |  |  | RE_QUEUED_FullEx
712 | 0 |  | 643 |  | 2022-04-07 | Lisbon | LISBON FALLS | 232D1 | Solar | 999 | 0 |  |  |  |  | 2023-01-13 | 2023-03-20 |  |  |  |  | 2024-05-28 | 2024-03-19 | 2024-05-23 | [6 empty] | Q3 2026 | Fully Executed Interconnection Agreement | No | 2024-09-26 | Cluster 18 - Lewiston Loop - 2 | Hotel Rd/Gulf/Middle St/Crowleys | 3 |  | Not Required | RE_QUEUED_FullEx
713 | 0 | 0 | 0 |  | 2022-04-20 | Auburn | GREAT FALLS | 436D6 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 18 - Lewiston Loop - 2 | Hotel Rd/Gulf/Middle St/Crowleys | 3 |  |  | WITHDRAWN
714 | 0 | 0 | 0 |  | 2022-04-28 | Skowhegan | SKOWHEGAN TAP | 864D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Winslow/ County Rd/ Lakewood - TBD | Lakewood | 3 |  |  | WITHDRAWN
715 | 0 | 0 | 0 |  | 2022-05-06 | Hartland | HARTLAND | 824D1 | Solar | 860 | 0 |  |  |  |  | 2022-06-17 | 2022-07-14 |  |  |  |  | 2022-09-08 | [9 empty] | Fully Executed Interconnection Agreement | Yes | 2023-01-19 | Cluster XX - Wyman Area - TBD | Hartland | 3 |  | Not Required | EXECUTED
716 | 0 | 0 | 0 |  | 2022-05-11 | Searsport | SEARSPORT | 850D1 | Solar | 0 | 0 | [10 empty] | 2022-11-01 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 17 - Detroit Guilford Belfast - 2 | Belfast | 3 |  |  | RE_QUEUED_FullEx
717 | 0 | 0 | 0 |  | 2022-05-13 | Biddeford | BIDDEFORD PUMP | 605D2 | Solar | 0 | 0 | [10 empty] | 2023-06-06 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster XX - Louden-Biddeford IP - TBD | Louden | 3 |  | TBD | EXECUTED-WITHDRAWN
718 | 0 |  | 0 |  | 2022-05-16 | Monmouth | MONMOUTH | 457D2 | Solar | 999 | 0 |  |  |  |  | 2023-05-04 | 2023-07-06 |  |  |  |  | 2023-08-22 |  | 2024-10-30 | [6 empty] | Q4 2025 | Fully Executed Interconnection Agreement | No | 2024-01-11 | Cluster XX - Augusta E-Puddledock-Bowman St - TBD | Monmouth | 3 |  | Not Required | RE_QUEUED_FullEx
719 | 0 | 0 | 0 |  | 2022-05-23 | Auburn | GREAT FALLS | 436D6 | Solar | 0 | 0 |  |  |  |  | 2022-08-04 | 2022-10-06 | [14 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 18 - Lewiston Loop - 2 | Hotel Rd/Gulf/Middle St/Crowleys | 3 |  | Not Required | WITHDRAWN
720 | 0 | 0 | 0 |  | 2022-05-31 | Winthrop | WINTHROP | 256D1 | Solar | 0 | 0 |  |  |  |  | 2023-01-12 | 2023-03-20 | [14 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Augusta E-Puddledock-Bowman St - TBD | Augusta E/Puddledock/Bowman St | 3 |  |  | WITHDRAWN
721 | 0 | 0 | 0 |  | 2022-05-31 | Starks | ANSON | 801D1 | Solar | 0 | 0 |  |  |  |  | 2022-08-25 | [15 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Winslow/ County Rd/ Lakewood - TBD | Lakewood | 3 |  |  | WITHDRAWN
722 | 0 | 0 | 0 |  | 2022-06-03 | Boothbay | BOOTHBAY HARBOR | 209D3 | Solar | 0 | 0 | [10 empty] | 2022-09-27 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster XX - Midcoast - TBD | Mason | 3 |  | Not Required | EXECUTED-WITHDRAWN
723 | 0 | 0 | 661 |  | 2022-06-08 | Parkman | GUILFORD | 821D1 | Solar | 0 | 0 |  |  |  |  | 2025-01-30 | 2024-04-04 | [13 empty] | Q4 2026 | WITHDRAWN | WITHDRAWN |  | Cluster 17 - Detroit Guilford Belfast - 2 | Guilford | 3 |  |  | RE_QUEUED
724 | 0 | 0 | 0 |  | 2022-06-08 | Fairfield | FAIRFIELD | 817D3 | Solar | 996 | 0 |  |  |  |  | 2022-07-25 | 2022-09-22 |  |  |  |  | 2022-09-27 | [8 empty] | Q3 2025 | Fully Executed Interconnection Agreement | Yes | 2022-10-14 | Cluster XX - Winslow/ County Rd/ Lakewood - TBD | Winslow-County Rd | 3 |  | Not Required | EXECUTED
725 | 0 | 0 | 0 |  | 2022-06-09 | South China | SOUTH CHINA | 244D2 | Solar | 975 | 0 | 2022-08-08 | 2022-09-14 | 2022-10-12 | 2022-11-09 | [6 empty] | 2023-01-09 | [8 empty] | Q4 2025 | Fully Executed Interconnection Agreement | No | 2023-10-03 | Cluster XX - Augusta E-Puddledock-Bowman St - TBD | Augusta E/Puddledock/Bowman St | 3 |  | Not Required | EXECUTED
726 | 0 | 0 | 0 |  | 2022-06-09 | Manchester | MANCHESTER | 233D2 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Augusta E-Puddledock-Bowman St - TBD | Augusta E/Puddledock/Bowman St | 3 |  |  | WITHDRAWN
727 | 0 | 0 | 0 |  | 2022-06-13 | Vassalboro | BLAIR ROAD | 207D1 | Solar | 0 | 0 |  |  |  |  | 2022-07-21 | 2022-09-21 | [14 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Augusta E-Puddledock-Bowman St - TBD | Augusta E/Puddledock/Bowman St | 3 |  |  | WITHDRAWN
728 | 0 |  | 0 |  | 2022-06-13 | Pittston | BOWMAN STREET | 263D1 | Solar | 975 | 0 |  |  |  |  | 2022-07-21 | 2022-09-22 |  |  |  |  | 2023-03-14 | 2023-01-21 | 2023-03-06 | 2023-12-07 | 2024-03-05 | 2026-02-23 | 2026-04-22 |  |  | Q1 2027 | Fully Executed Interconnection Agreement | No | 2023-10-25 | Cluster XX - Augusta E-Puddledock-Bowman St - TBD | Augusta E/Puddledock/Bowman St | 3 |  | Not Required | RE_QUEUED_FullEx
729 | 0 | 0 | 0 |  | 2022-06-20 | Readfield | PUDDLEDOCK ROAD | 262D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Augusta E-Puddledock-Bowman St - TBD | Augusta E/Puddledock/Bowman St | 3 |  |  | WITHDRAWN
730 | 0 | 0 | 0 |  | 2022-06-29 | Bristol | BRISTOL | 210D2 | Solar | 0 | 0 |  |  |  |  | 2022-08-08 | 2022-10-12 |  |  |  |  | 2022-11-14 | 2024-03-20 | 2024-05-22 | [6 empty] | Q4 2026 | WITHDRAWN | WITHDRAWN |  | Cluster XX - Midcoast - TBD | Newcastle | 3 |  | Not Required | RE_QUEUED_FullEx
731 | 0 | 0 | 371 |  | 2022-07-11 | Vassalboro | VASSALBORO | 861D8 | Solar | 975 | 0 |  |  |  |  | 2024-01-08 | 2024-03-05 |  |  |  |  | 2024-03-27 | 2024-01-08 | 2024-03-05 | 2025-08-06 | 2025-10-07 |  |  |  |  | Q2 2026 | Fully Executed Interconnection Agreement | No | 2024-11-08 | Cluster XX - Winslow/ County Rd/ Lakewood - TBD | Winslow-County Rd | 3 |  | Not Required | RE_QUEUED_FullEx
732 | 0 |  | 680 |  | 2022-07-18 | Jay | LIVERMORE FALLS | 428D3 | Solar | 999 | 0 |  |  |  |  | 2022-11-15 | 2023-01-17 | 2023-03-06 | 2023-04-10 |  |  | 2023-04-19 | 2023-12-27 | 2024-03-04 | 2024-05-31 | 2024-08-02 | 2025-08-06 | 2025-10-08 |  |  | Q4 2025 | Fully Executed Interconnection Agreement | No | 2023-11-06 | Cluster XX - Sturtevant/ Leeds/ Livermore/ Ludden/ Riley_TBD | Livermore Falls | 3 |  |  | #REF!
733 | 0 | 0 | 0 |  | 2022-07-21 | Vassalboro | MCCOYS | 237D1 | Solar | 1000 | 0 |  |  |  |  | 2022-10-04 | 2022-12-12 |  |  |  |  | 2022-12-28 | [9 empty] | Fully Executed Interconnection Agreement | Yes | 2023-02-03 | Cluster XX - Augusta E-Puddledock-Bowman St - TBD | Augusta E/Puddledock/Bowman St | 3 |  |  | EXECUTED
734 | 0 | 0 | 0 |  | 2022-07-22 | Lewiston | MIDDLE STREET | 451D8 | Battery | 0 | 0 | [20 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 18 - Lewiston Loop - 2 | Middle Street | 3 |  |  | WITHDRAWN
735 | 0 | 0 | 0 |  | 2022-07-25 | Mechanic Falls | MECHANIC FALLS | 431D1 | Solar | 0 | 0 | [10 empty] | 2022-11-29 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 18 - Lewiston Loop - 2 | Norway | 3 |  | Not Required | EXECUTED-WITHDRAWN
736 | 0 | 0 | 0 |  | 2022-07-26 | Newcastle | DAMARISCOTTA MILLS | 219D2 | Solar/Battery | 0 | 0 |  |  |  |  | 2022-09-12 | 2022-11-09 |  |  |  |  | 2022-11-30 | [9 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Midcoast - TBD | Newcastle | 3 |  |  | EXECUTED-WITHDRAWN
737 | 0 | 0 | 0 |  | 2022-07-29 | Madison | SKOWHEGAN NORTH SIDE | 853D1 | Solar | 975 | 0 |  |  |  |  | 2022-08-24 | 2022-10-31 |  |  |  |  | 2023-01-09 | 2024-02-07 | 2024-04-11 | [6 empty] | Q3 2025 | Fully Executed Interconnection Agreement | No | 2023-10-03 | Cluster XX - Winslow/ County Rd/ Lakewood - TBD | Lakewood | 3 |  | Not Required | RE_QUEUED_FullEx
738 | 0 | 0 | 0 |  | 2022-08-09 | Andover | ANDOVER | 400D1 | Solar | 0 | 0 | [10 empty] | 2022-12-12 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster XX - Woodstock/ Roxbury/ Rumford - TBD | Roxbury | 3 |  | Not Required | EXECUTED-WITHDRAWN
739 | 0 | 0 | 0 |  | 2022-08-11 | Wiscasset | MESSINA | 238D1 | Solar/Battery | 0 | 0 |  |  |  |  | 2022-09-23 | 2022-12-01 | 2023-01-24 | 2023-03-07 | [12 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Midcoast - TBD | Mason | 3 |  | Not Required | WITHDRAWN
740 | 0 | 0 | 0 |  | 2022-08-18 | Raymond | RAYMOND 34 KV | 444D1 | Solar/Battery | 0 | 0 | [10 empty] | 2023-11-22 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster XX - Raymond - TBD | Raymond | 3 |  | Not Required | EXECUTED-WITHDRAWN
741 | 0 | 0 | 0 |  | 2022-08-18 | Mercer | SKOWHEGAN TAP | 864D1 | Solar | 999 | 0 |  |  |  |  | 2022-10-26 | 2023-01-05 | 2023-04-18 | 2023-05-30 |  |  | 2023-07-31 | [8 empty] | Q4 2025 | Fully Executed Interconnection Agreement | Yes | 2023-12-19 | Cluster XX - Winslow/ County Rd/ Lakewood - TBD | Lakewood | 3 |  |  | EXECUTED
742 | 0 | 0 | 0 |  | 2022-08-18 | Mercer | SKOWHEGAN TAP | 864D1 | Solar | 0 | 0 |  |  |  |  | 2023-12-12 | 2024-02-16 | [14 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Winslow/ County Rd/ Lakewood - TBD | Lakewood | 3 |  |  | WITHDRAWN
743 | 0 | 0 | 676 |  | 2022-08-26 | Northport | LINCOLNVILLE | 800D1 | Solar | 0 | 0 |  |  |  |  | 2022-11-11 | 2023-01-11 |  |  |  |  | 2023-02-24 | [8 empty] | Q4 2024 | WITHDRAWN | WITHDRAWN |  | Cluster XX - Midcoast - TBD | Lincolnville | 3 |  |  | EXECUTED
744 | 0 | 0 | 0 |  | 2022-08-30 | Windham | NORTH WINDHAM | 639D2 | Solar | 0 | 0 |  |  |  |  | 2023-01-09 | 2023-03-16 | [14 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Raymond - TBD | Raymond | 3 |  | Not Required | WITHDRAWN
745 | 0 | 0 | 725 |  | 2022-09-08 | South China | SOUTH CHINA | 244D1 | Solar | 975 | 0 |  |  |  |  | 2023-05-01 | 2023-07-07 |  |  |  |  | 2023-08-24 | [8 empty] | Q2 2025 | Fully Executed Interconnection Agreement | Yes | 2024-01-10 | Cluster XX - Augusta E-Puddledock-Bowman St - TBD | Augusta E/Puddledock/Bowman St | 3 |  | Not Required | EXECUTED
746 | 0 |  | 0 |  | 2022-09-08 | Fairfield | SHAWMUT | 852D1 | Solar | 500 | 0 |  |  |  |  | 2022-11-02 | 2023-01-10 |  |  |  |  | 2023-02-13 | 2024-03-25 | 2024-05-29 | [6 empty] | Q4 2025 | Fully Executed Interconnection Agreement | No | 2023-10-25 | Cluster XX - Winslow/ County Rd/ Lakewood - TBD | Lakewood | 3 |  | Not Required | RE_QUEUED_FullEx
747 | 0 | 0 | 0 |  | 2022-10-07 | Sweden | LOVELL | 430D1 | Solar | 0 | 0 | [10 empty] | 2023-09-15 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 13 - Kimball Rd-Lovell - 2 | Kimball Road/Lovell | 3 |  | Not Required | EXECUTED-WITHDRAWN
748 | 0 | 0 | 0 |  | 2022-10-07 | Sweden | LOVELL | 430D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 13 - Kimball Rd-Lovell - 2 | Kimball Road/Lovell | 3 |  | Not Required | WITHDRAWN
749 | 0 | 0 | 0 |  | 2022-10-07 | Sweden | LOVELL | 430D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 13 - Kimball Rd-Lovell - 2 | Kimball Road/Lovell | 3 |  | Not Required | WITHDRAWN
750 | 0 | 0 | 0 |  | 2022-10-12 | Levant | CARMEL | 808D3 | Solar | 0 | 0 | [10 empty] | 2024-04-11 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 17 - Detroit Guilford Belfast - 2 | Detroit | 3 |  | Not Required | RE_QUEUED_FullEx
751 | 0 | 0 | 700 |  | 2022-10-17 | Skowhegan | WESTON HYDRO | 866D2 | Solar | 0 | 0 | [10 empty] | 2024-08-12 | [8 empty] | Q2 2025 | EXECUTED-WITHDRAWN | WITHDRAWN | 2025-05-19 | Cluster XX - Winslow/ County Rd/ Lakewood - TBD | Lakewood | 3 |  | Not Required | RE_QUEUED_FullEx
752 | 0 | 0 | 0 |  | 2022-10-19 | Lewiston | DEER RIPS | 412D2 | Fuel Cell | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 18 - Lewiston Loop - 2 | Hotel Rd/Gulf/Middle St/Crowleys/Norway | 3 |  | Not Required | WITHDRAWN
753 | 0 | 0 | 0 |  | 2022-10-19 | Scarborough | PLEASANT HILL | 644D4 | Fuel Cell | 0 | 0 | [10 empty] | 2023-04-26 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster XX - Greater Portland - TBD | Pleasant Hill | 3 |  | Not Required | EXECUTED-WITHDRAWN
754 | 0 | 0 | 0 |  | 2022-10-19 | Biddeford | BIDDEFORD INDUSTRIAL PARK | 673D1 | Fuel Cell | 0 | 0 | [10 empty] | 2023-04-28 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster XX - Louden-Biddeford IP - TBD | Biddeford IP | 3 |  | Not Required | EXECUTED-WITHDRAWN
755 | 0 | 0 | 0 |  | 2022-10-19 | Sanford | SANFORD SWITCH | 657D4 | Fuel Cell | 0 | 0 |  |  |  |  | 2022-12-23 | 2023-02-27 | [14 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 19 - Sanford-Quaker Hill - 2 | Sanford | 3 |  | Not Required | WITHDRAWN
756 | 0 | 0 | 0 |  | 2022-10-19 | Augusta | CAPITOL STREET | 215D3 | Fuel Cell | 0 | 0 | [10 empty] | 2023-04-17 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster XX - Augusta E-Puddledock-Bowman St - TBD | Augusta E/Puddledock/Bowman St | 3 |  | Not Required | EXECUTED-WITHDRAWN
757 | 0 | 0 | 718 |  | 2022-12-12 | Monmouth | MONMOUTH | 457D2 | Solar | 0 | 0 | [10 empty] | 2024-02-12 | [8 empty] | Q3 2025 | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster XX - Augusta E-Puddledock-Bowman St - TBD | Monmouth | 3 |  | Not Required | RE_QUEUED_FullEx
758 | 0 | 0 | 0 |  | 2022-11-04 | Sanford | SANFORD INDUSTRIAL PARK | 656D2 | Solar | 990 | 0 |  |  |  |  | 2023-04-12 | 2023-06-16 |  |  |  |  | 2023-08-02 | [8 empty] | Q4 2025 | Fully Executed Interconnection Agreement | Yes | 2023-08-16 | Cluster 19 - Sanford-Quaker Hill - 2 | Sanford | 3 |  | Not Required | RE_QUEUED_FullEx
759 | 0 | 0 | 0 |  | 2022-11-04 | Portland | LAMBERT STREET | 631D1 | Fuel Cell | 0 | 0 |  |  |  |  | 2022-12-14 | 2023-02-21 | [14 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Greater Portland - TBD | Moshers/Prides Corner | 3 |  | Not Required | WITHDRAWN
760 | 0 | 0 | 0 |  | 2022-11-07 | Scarborough | MUSSEY ROAD | 636D2 | Fuel Cell | 0 | 0 |  |  |  |  | 2022-12-14 | [15 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Greater Portland - TBD | Mussey Road | 3 |  | Not Required | WITHDRAWN
761 | 0 | 0 | 0 |  | 2022-11-07 | Fairfield | FAIRFIELD | 817D2 | Fuel Cell | 0 | 0 | [10 empty] | 2023-06-06 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster XX - Winslow/ County Rd/ Lakewood - TBD | Winslow-County Rd | 3 |  | Not Required | EXECUTED-WITHDRAWN
762 | 0 | 0 | 0 |  | 2022-11-07 | Bucksport | BUCKSPORT | 806D1 | Fuel Cell | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 17 - Detroit Guilford Belfast - 2 | Bucksport | 3 |  | Not Required | WITHDRAWN
763 | 0 | 0 | 0 |  | 2022-11-17 | West Gardiner | WEST STREET | 255D2 | Solar | 0 | 0 | [10 empty] | 2023-08-24 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster XX - Augusta E-Puddledock-Bowman St - TBD | Augusta E/Puddledock/Bowman St | 3 |  | Not Required | EXECUTED-WITHDRAWN
764 | 0 | 0 | 0 |  | 2022-11-18 | Biddeford | BIDDEFORD PUMP | 605D2 | Solar | 0 | 0 | [10 empty] | 2024-04-09 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster XX - Louden-Biddeford IP - TBD | Louden | 3 |  | Not Required | RE_QUEUED_FullEx
765 | 0 | 0 | 0 |  | 2022-11-21 | Belfast | BELFAST 115 | 874D1 | Solar/Battery | 800 | 0 |  |  |  |  | 2023-01-24 | 2023-03-28 |  |  |  |  | 2023-03-30 | [8 empty] | Q4 2025 | Fully Executed Interconnection Agreement | No | 2024-06-07 | Cluster 17 - Detroit Guilford Belfast - 2 | Belfast | 3 |  | Not Required | RE_QUEUED_FullEx
766 | 0 | 0 | 0 |  | 2022-11-23 | Chelsea | CONY ROAD | 216D1 | Battery | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Withdrawn | Withdrawn | 3 |  | Not Required | WITHDRAWN
767 | 0 | 0 | 0 |  | 2022-11-29 | Saco | GOOSEFARE | 630D2 | Fuel Cell | 0 | 0 |  |  |  |  | 2023-02-03 | 2023-04-10 | [14 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Louden-Biddeford IP - TBD | Louden | 3 |  | Not Required | WITHDRAWN
768 | 0 |  | 0 |  | 2022-12-05 | Searsport | SEARSPORT | 850D1 | Solar | 0 | 0 | [10 empty] | 2024-08-19 | [8 empty] | Q3 2026 | EXECUTED-WITHDRAWN | WITHDRAWN | 2025-02-12 | Cluster 17 - Detroit Guilford Belfast - 2 | Belfast | 3 |  | Not Required | RE_QUEUED_FullEx
769 | 0 | 0 | 0 | 0 | 2022-12-20 | Augusta | NORTH AUGUSTA | 272D4 | Solar | 0 | 0 |  |  |  |  | 2023-05-09 | 2023-07-10 |  |  |  |  | 2023-09-26 | 2024-05-10 | 2024-07-12 | 2024-12-27 | 2025-03-04 |  |  |  |  | Q2 2025 | Fully Executed Interconnection Agreement | No |  | Cluster XX - Augusta E-Puddledock-Bowman St - TBD | North Augusta | 3 |  |  | RE_QUEUED_RESULTS
770 | 0 | 0 | 0 |  | 2022-12-29 | Carrabassett Valley | BIGELOW | 882D2 | Solar/Battery | 0 | 0 | [10 empty] | 2023-08-24 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster XX - Wyman Area - TBD | Bigelow | 3 |  |  | EXECUTED
771 | 0 | 0 | 0 |  | 2023-01-04 | Bristol | BRISTOL | 210D1 | Solar | 0 | 0 | [10 empty] | 2023-04-25 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster XX - Midcoast - TBD | Newcastle | 3 |  | Not Required | EXECUTED-WITHDRAWN
772 | 0 | 0 | 761 |  | 2023-01-05 | Fairfield | FAIRFIELD | 817D3 | Solar | 0 | 0 |  |  |  |  | 2023-10-30 | 2024-01-08 |  |  |  |  | 2024-01-30 | [8 empty] | Q2 2026 | WITHDRAWN | WITHDRAWN |  | Cluster XX - Winslow/ County Rd/ Lakewood - TBD | Winslow-County Rd | 3 |  | Not Required | EXECUTED
773 | 0 | 0 | 0 |  | 2023-01-09 | Biddeford | MAY STREET | 634D1 | Fuel Cell | 0 | 0 |  |  |  |  | 2023-02-13 | 2023-04-19 | [14 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Louden-Biddeford IP - TBD | Biddeford IP | 3 |  | Not Required | WITHDRAWN
774 | 0 | 0 | 0 |  | 2023-01-11 | Boothbay | BOOTHBAY HARBOR | 209D3 | Solar | 0 | 0 | [10 empty] | 2023-05-04 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster XX - Midcoast - TBD | Mason | 3 |  | Not Required | EXECUTED-WITHDRAWN
775 | 0 | 0 | 0 |  | 2023-01-12 | Bath | BATH 34 | 261D4 | Fuel Cell | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Midcoast - TBD | Bath | 3 |  | Not Required | WITHDRAWN
776 | 0 | 0 | 0 |  | 2023-01-23 | Lewiston | CHALLENGER 12 KV | 421D2 | Fuel Cell | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 18 - Lewiston Loop - 2 | Challenger Dr | 3 |  | Not Required | WITHDRAWN
777 | 0 | 0 | 0 |  | 2023-01-24 | Mechanic Falls | MECHANIC FALLS | 431D1 | Solar | 0 | 0 |  |  |  |  | 2023-03-02 | 2023-05-02 |  |  |  |  | 2023-06-29 | [9 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 18 - Lewiston Loop - 2 | Norway | 3 |  | Not Required | EXECUTED-WITHDRAWN
778 | 0 | 0 | 0 |  | 2023-01-27 | Auburn | GREAT FALLS | 436D6 | Solar | 0 | 0 | [10 empty] | 2024-05-08 | [8 empty] | Q4 2025 | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 18 - Lewiston Loop - 2 | Hotel Rd/Gulf/Middle St/Crowleys | 3 |  | Not Required | RE_QUEUED_FullEx
779 | 0 | 0 | 0 |  | 2023-01-31 | Monson | MONSON | 834D1 | Solar | 0 | 0 |  |  |  |  | 2023-04-27 | 2023-07-03 | [14 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 17 - Detroit Guilford Belfast - 2 | Guilford | 3 |  | Not Required | WITHDRAWN
780 | 0 | 0 | 0 |  | 2023-02-02 | Rockland | PARK STREET | 239D6 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Midcoast - TBD | Highland/Park St | 3 |  | Not Required | WITHDRAWN
781 | 0 |  | 732 |  | 2023-02-02 | Livermore Falls | LIVERMORE FALLS | 428D2 | Solar | 950 | 0 |  |  |  |  | 2023-05-05 | N/A |  |  |  |  | 2024-12-03 | 2024-09-16 | 2024-11-15 | 2024-12-16 | 2025-02-19 | 2025-12-01 | 2025-02-04 |  |  | #REF! | Fully Executed Interconnection Agreement | No | 2025-03-24 | Cluster XX - Sturtevant/ Leeds/ Livermore/ Ludden/ Riley_TBD | Livermore Falls | 3 |  | Not Required | RE_QUEUED
782 | 0 | 0 | 0 |  | 2023-02-07 | Peru | RUMFORD INDUSTRIAL PARK | 466D1 | Solar | 0 | 0 | [10 empty] | 2023-07-18 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster XX - Woodstock/ Roxbury/ Rumford - TBD | Rumford IP | 3 |  | Not Required | EXECUTED-WITHDRAWN
783 | 0 | 0 | 0 |  | 2023-02-09 | Biddeford | MAY STREET | 634D3 | Fuel Cell | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Louden-Biddeford IP - TBD | Biddeford IP | 3 |  | Not Required | WITHDRAWN
784 | 0 | 0 | 0 |  | 2023-02-10 | Lewiston | LEWISTON LOWER 115 | 424D5 | Fuel Cell | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 18 - Lewiston Loop - 2 | LEWISTON LOWER 115 KV | 3 |  | Not Required | WITHDRAWN
785 | 0 | 0 | 0 |  | 2023-02-10 | Kittery | BOLT HILL | 685D2 | Fuel Cell | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 19 - Sanford-Quaker Hill - 2 | Bolt Hill | 3 |  | Not Required | WITHDRAWN
786 | 0 | 0 | 0 |  | 2023-02-10 | Lewiston | SABATTUS | 450D2 | Fuel Cell | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 18 - Lewiston Loop - 2 | Hotel Rd/Gulf/Middle St/Crowleys | 3 |  | Not Required | WITHDRAWN
787 | 0 | 0 | 0 |  | 2023-02-10 | Lewiston | CHALLENGER 12 KV | 421D2 | Fuel Cell | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 18 - Lewiston Loop - 2 | Challenger Dr | 3 |  | Not Required | WITHDRAWN
788 | 0 | 0 | 0 |  | 2023-02-22 | West Bath | BATH 34 | 261D3 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Midcoast - TBD | Bath | 3 |  | Not Required | WITHDRAWN
789 | 0 | 0 | 0 |  | 2023-03-03 | Lisbon | LISBON FALLS | 232D1 | Fuel Cell | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 18 - Lewiston Loop - 2 | Hotel Rd/Gulf/Middle St/Crowleys | 3 |  | Not Required | WITHDRAWN
790 | 0 | 0 | 0 |  | 2023-03-03 | Carmel | CARMEL | 808D2 | Solar | 0 | 0 |  |  |  |  | 2024-05-31 | 2024-08-01 | 2024-11-20 |  |  |  |  | 2024-12-09 | [8 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 17 - Detroit Guilford Belfast - 2 | Detroit | 3 |  |  | RE_QUEUED_RESULTS
791 | 0 | 0 | 0 |  | 2023-03-03 | Minot | MECHANIC FALLS | 431D2 | Solar | 0 | 0 |  |  |  |  | 2024-06-18 | 2024-08-16 | [14 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 18 - Lewiston Loop - 2 | Norway | 3 |  |  | RE_QUEUED_RESULTS
792 | 0 | 0 | 0 |  | 2023-03-14 | Gray | GRAY | 416D3 | Solar | 0 | 0 | [10 empty] | 2023-07-31 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster XX - Greater Portland - TBD | Elm St | 3 |  | Not Required | EXECUTED-WITHDRAWN
793 | 0 | 0 | 0 |  | 2023-03-23 | Phippsburg | WASHINGTON ST (BATH) | 204D6 | Solar | 0 | 0 | [10 empty] | 2023-08-01 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster XX - Midcoast - TBD | Bath | 3 |  | Not Required | EXECUTED-WITHDRAWN
794 | 0 | 0 | 0 |  | 2023-03-27 | Topsham | TOPSHAM 34 KV | 250K3 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Midcoast - TBD | Topsham | 3 |  | Not Required | WITHDRAWN
795 | 0 | 0 | 0 |  | 2023-03-28 | Dixfield | LUDDEN LANE | 461D1 | Solar | 990 | 0 |  |  |  |  | 2023-05-19 | 2023-07-21 |  |  |  |  | 2024-05-29 | 2024-03-22 | 2024-05-17 | [6 empty] | Q1 2026 | Fully Executed Interconnection Agreement | No | 2024-09-30 | Cluster XX - Sturtevant/ Leeds/ Livermore/ Ludden/ Riley_TBD | Ludden Lane | 3 |  | Not Required | RE_QUEUED_FullEx
796 | 0 | 0 | 685 |  | 2023-03-28 | North Yarmouth | ELM STREET | 620D4 | Solar | 999 | 0 |  |  |  |  | 2023-05-22 | 2023-07-19 |  |  |  |  | 2023-09-15 | 2024-03-28 | 2024-06-03 | [6 empty] | Q2 2025 | Fully Executed Interconnection Agreement | Yes | 2024-04-11 | Cluster XX - Greater Portland - TBD | Elm St | 3 |  | Not Required | RE_QUEUED_FullEx
797 | 0 | 0 | 0 |  | 2023-03-29 | Bucksport | BUCKSPORT | 806D2 | Solar | 0 | 0 |  |  |  |  | 2024-03-07 | 2024-05-10 | [14 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 17 - Detroit Guilford Belfast - 2 | Bucksport | 3 |  | TBD | WITHDRAWN
798 | 0 | 0 | 796 |  | 2023-03-29 | North Yarmouth | ELM STREET | 620D4 | Solar | 999 | 0 |  |  |  |  | 2023-10-05 | 2023-12-13 |  |  |  |  | 2023-12-19 | 2024-07-10 | 2024-09-11 | [6 empty] | Q3 2025 | Fully Executed Interconnection Agreement | Yes | 2024-04-11 | Cluster XX - Greater Portland - TBD | Elm St | 3 |  | Not Required | RE_QUEUED_STUDY
799 | 0 | 0 | 0 |  | 2023-03-29 | Bucksport | BUCKSPORT | 806D2 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 17 - Detroit Guilford Belfast - 2 | Bucksport | 3 |  | TBD | WITHDRAWN
800 | 0 | 0 | 0 |  | 2023-04-12 | Lewiston | MIDDLE STREET | 451D8 | Battery | 0 | 0 | [10 empty] | 2024-01-10 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 18 - Lewiston Loop - 2 | Middle Street | 3 |  |  | EXECUTED
801 | 0 | 0 | 0 |  | 2023-04-19 | South Sanford | PRATT & WHITNEY | 661D1 | Solar | 999 | 0 |  |  |  |  | 2023-06-12 | 2023-08-15 | 2023-10-10 |  |  |  | 2024-04-29 | 2023-12-14 | 2024-02-21 | [6 empty] | Q4 2026 | Fully Executed Interconnection Agreement | No | 2024-10-02 | Cluster 19 - Sanford-Quaker Hill - 2 | Pratt & Whitney | 3 |  | Not Required | RE_QUEUED_FullEx
802 | 0 | 0 | 0 |  | 2023-04-20 | Bridgton | BRIDGTON | 406D1 | Solar | 0 | 0 |  |  |  |  | 2023-07-12 | 2023-09-18 | [6 empty] | 2023-09-18 | [7 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 13 - Kimball Rd-Lovell - 2 | Kimball Road/Lovell | 3 |  | Not Required | WITHDRAWN
803 | 0 |  | 625 |  | 2023-04-21 | Belfast | BELFAST WEST SIDE | 803D4 | Solar | 999 | 0 |  |  |  |  | 2024-05-14 | 2024-07-17 |  |  |  |  | 2024-09-19 | 2024-09-03 | [7 empty] | Q4 2025 | Fully Executed Interconnection Agreement | No | 2025-01-23 | Cluster 17 - Detroit Guilford Belfast - 2 | Belfast | 3 |  | Not Required | RE_QUEUED_STUDY
804 | 0 | 0 | 0 |  | 2023-04-24 | Saco | GOOSEFARE | 630D4 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Louden-Biddeford IP - TBD | Louden | 3 |  | Not Required | WITHDRAWN
805 | 0 | 0 | 726 |  | 2023-04-25 | Manchester | MANCHESTER | 233D2 | Solar/Battery | 0 | 0 | [10 empty] | 2025-07-25 | [8 empty] | Q2 2026 | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster XX - Augusta E-Puddledock-Bowman St - TBD | Augusta E/Puddledock/Bowman St | 3 |  | Not Required | RE_QUEUED
806 | 0 |  | 0 |  | 2023-04-27 | Newcastle | DAMARISCOTTA MILLS | 219D2 | Solar/Battery | 996 | 0 |  |  |  |  | 2023-06-13 | 2023-08-17 |  |  |  |  | 2023-12-11 | 2024-06-20 | 2024-08-21 | [6 empty] | Q4 2024 | Fully Executed Interconnection Agreement | Yes | 2025-03-17 | Cluster XX - Midcoast - TBD | Newcastle | 3 |  | Not Required | RE_QUEUED_STUDY
807 | 0 | 0 | 0 |  | 2023-05-03 | York | BRAGDON COMMONS | 689D1 | Solar | 0 | 0 | [10 empty] | 2024-01-29 | [8 empty] | Q4 2025 | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 19 - Sanford-Quaker Hill - 2 | Quaker Hill | 3 |  | Not Required | RE_QUEUED_FullEx
808 | 0 | 0 | 689 |  | 2023-05-04 | Lebanon | LEBANON | 695D2 | Solar | 975 | 0 |  |  |  |  | 2023-06-28 | 2023-08-31 |  |  |  |  | 2024-11-21 | 2024-07-17 | 2024-09-04 | [6 empty] | Q4 2024 | Fully Executed Interconnection Agreement | No | 2025-04-11 | Cluster 19 - Sanford-Quaker Hill - 2 | Sanford | 3 |  |  | RE_QUEUED_RESULTS
809 | 0 | 0 | 0 |  | 2023-05-05 | Biddeford | MAY STREET | 634D4 | Solar/Battery | 0 | 0 | [10 empty] | 2024-02-29 | [8 empty] | Q2 2025 | EXECUTED-WITHDRAWN | No | 2024-10-17 | Cluster XX - Louden-Biddeford IP - TBD | Biddeford IP | 3 |  | Not Required | EXECUTED
810 | 0 | 0 | 0 |  | 2023-05-05 | Biddeford | MAY STREET | 634D4 | Solar/Battery | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Louden-Biddeford IP - TBD | Biddeford IP | 3 |  | Not Required | WITHDRAWN
811 | 0 | 0 | 798 |  | 2023-05-05 | Yarmouth | ELM STREET | 620D3 | Solar/Battery | 0 | 0 | [10 empty] | 2025-03-25 | [8 empty] | Q4 2024 | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster XX - Greater Portland - TBD | Elm St | 3 |  | Not Required | RE_QUEUED
812 | 0 | 0 | 0 |  | 2023-05-05 | South Portland | RIGBY | 650D4 | Solar/Battery | 0 | 0 | [10 empty] | 2023-11-28 | [8 empty] | Q3 2026 | EXECUTED-WITHDRAWN | WITHDRAWN | 2024-04-03 | Cluster XX - Greater Portland - TBD | Pleasant Hill | 3 |  | Not Required | EXECUTED
813 | 0 | 0 | 0 |  | 2023-05-05 | Sidney | SIDNEY | 242D1 | Solar/Battery | 0 | 0 | [10 empty] | 2023-11-30 | [8 empty] | Q2 2026 | EXECUTED-WITHDRAWN | WITHDRAWN | 2024-07-23 | Cluster XX - Augusta E-Puddledock-Bowman St - TBD | Augusta E/Puddledock/Bowman St | 3 |  | Not Required | EXECUTED
814 | 0 | 0 | 0 |  | 2023-05-08 | South Paris | NORWAY | 435D3 | Solar | 999 | 0 |  |  |  |  | 2023-07-18 | 2023-09-20 |  |  |  |  | 2023-11-20 | [8 empty] | Q4 2025 | Fully Executed Interconnection Agreement | No | 2024-03-07 | Cluster XX - Louden-Biddeford IP - TBD | Norway | 3 |  | Not Required | EXECUTED
815 | 0 | 0 | 707 |  | 2023-05-09 | Rumford | RUMFORD | 447D2 | Solar | 0 | 0 |  |  |  |  | 2025-09-09 | 2025-11-13 | [13 empty] | Q4 2026 | WITHDRAWN | WITHDRAWN |  | Cluster XX - Woodstock/ Roxbury/ Rumford - TBD | Rumford | 3 |  |  | RE_QUEUED
816 | 0 | 0 | 0 |  | 2023-05-10 | Baldwin | BALDWIN | 691D1 | Solar | 0 | 0 |  |  |  |  | 2023-06-30 | 2023-09-05 |  |  |  |  | 2023-10-16 | [8 empty] | Q4 2026 | WITHDRAWN | WITHDRAWN |  | Cluster 13 - Kimball Rd-Lovell - 2 | Kimball Road/Lovell | 3 |  | Not Required | RE_QUEUED_FullEx
817 | 0 |  | 757 |  | 2023-05-10 | Leeds | MONMOUTH | 457D2 | Solar | 999 | 0 |  |  |  |  | 2024-03-15 | N/A |  |  |  |  | 2025-06-27 | 2024-05-07 | 2024-07-12 | 2025-03-05 |  | 2025-04-24 | 2025-06-04 |  |  |  | Fully Executed Interconnection Agreement | No | 2025-10-30 | Cluster XX - Augusta E-Puddledock-Bowman St - TBD | Monmouth | 3 |  | Not Required | RE_QUEUED
818 | 0 | 0 | 0 |  | 2023-05-11 | Buckfield | TURNER | 454D1 | Solar | 999 | 0 |  |  |  |  | 2023-07-18 | 2023-09-20 |  |  |  |  | 2023-11-20 | [8 empty] | Q4 2025 | Fully Executed Interconnection Agreement | No | 2023-12-15 | Cluster 18 - Lewiston Loop - 2 | Hotel Rd/Gulf/Middle St/Crowleys/Norway | 3 |  | Not Required | EXECUTED
819 | 0 | 0 | 817 |  | 2023-05-11 | Monmouth | MONMOUTH | 457D2 | Solar | 0 | 0 |  |  |  |  | 2025-07-31 | 2025-10-01 | [5 empty] | 2025-11-05 | 2025-12-16 | [6 empty] | Q4 2026 | Active | No |  | Cluster XX - Augusta E-Puddledock-Bowman St - TBD | Monmouth | 3 |  | Not Required | RE_QUEUED
820 | 0 | 0 | 0 |  | 2023-05-15 | Madison | SKOWHEGAN NORTH SIDE | 853D1 | Solar | 999 | 0 |  |  |  |  | 2023-07-26 | 2023-09-28 |  |  |  |  | 2023-12-13 | 2024-07-26 | 2024-09-30 | [6 empty] | Q2 2026 | Fully Executed Interconnection Agreement | No | 2024-04-25 | Cluster XX - Winslow/ County Rd/ Lakewood - TBD | Lakewood | 3 |  | Not Required | RE_QUEUED_STUDY
821 | 0 | 0 | 0 |  | 2023-05-15 | Vassalboro | MCCOYS | 237D1 | Solar | 999 | 0 |  |  |  |  | 2023-08-07 | 2023-10-11 | 2024-01-22 | 2024-03-05 |  |  | 2024-04-09 | [8 empty] | Q4 2025 | Fully Executed Interconnection Agreement | Yes | 2024-08-21 | Cluster XX - Augusta E-Puddledock-Bowman St - TBD | Augusta E/Puddledock/Bowman St | 3 |  | Not Required | EXECUTED
822 | 0 | 0 | 0 |  | 2023-05-19 | Carmel | CARMEL | 808D3 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 17 - Detroit Guilford Belfast - 2 | Detroit | 3 |  | Not Required | RE_QUEUED
823 | 0 | 0 | 782 |  | 2023-05-22 | Peru | RUMFORD INDUSTRIAL PARK | 466D1 | Solar | 999 | 0 |  |  |  |  | 2023-12-20 | 2024-02-27 |  |  |  |  | 2024-07-01 | [8 empty] | Q4 2025 | Fully Executed Interconnection Agreement | No | 2024-10-31 | Cluster XX - Woodstock/ Roxbury/ Rumford - TBD | Rumford IP | 3 |  | Not Required | #REF!
824 | 0 | 0 | 0 |  | 2023-05-24 | Rockland | PARK STREET | 239D7 | Solar/Battery | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Midcoast - TBD | Highland/Park St | 3 |  | Not Required | WITHDRAWN
825 | 0 | 0 | 0 |  | 2023-06-02 | Rockland | PARK STREET | 239D7 | Solar/DC BESS | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Midcoast - TBD | Highland/Park St | 3 |  | Not Required | WITHDRAWN
826 | 0 | 0 | 0 |  | 2023-06-05 | Athens | ATHENS | 827D1 | Solar | 0 | 0 | [10 empty] | 2023-12-28 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster XX - Wyman Area - TBD | Athens | 3 |  | Not Required | EXECUTED-WITHDRAWN
827 | 0 | 0 | 819 |  | 2023-06-12 | Monmouth | MONMOUTH | 457D3 | Solar | 0 | 0 |  |  |  |  | 2026-01-21 | 2026-03-20 | [13 empty] | Q4 2026 | Active | No |  | Cluster XX - Augusta E-Puddledock-Bowman St - TBD | Monmouth | 3 |  | Not Required | RE_QUEUED
828 | 0 | 0 | 0 |  | 2023-06-15 | Brunswick | BRUNSWICK WEST SIDE | 213D3 | Solar | 0 | 0 |  |  |  |  | 2023-08-11 | 2023-10-20 | [5 empty] | 2024-04-22 | 2024-06-25 | 2024-08-01 |  | 2024-09-03 | 2024-11-01 |  |  |  | WITHDRAWN | WITHDRAWN |  | Cluster XX - Midcoast - TBD | Topsham | 3 |  | Not Required | RE_QUEUED_STUDY
829 | 0 | 0 | 0 |  | 2023-06-15 | Richmond | RICHMOND | 240D1 | Solar | 999 | 0 |  |  |  |  | 2023-08-23 | 2023-10-25 |  |  |  |  | 2024-02-15 | 2023-11-20 | 2023-01-05 | [6 empty] | Q1 2026 | Fully Executed Interconnection Agreement | No | 2024-09-26 | Cluster XX - Augusta E-Puddledock-Bowman St - TBD | Augusta E/Puddledock/Bowman St | 3 |  |  | RE_QUEUED_FullEx
830 | 0 | 0 | 0 |  | 2023-06-20 | Richmond | RICHMOND | 240D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Augusta E-Puddledock-Bowman St - TBD | Augusta E/Puddledock/Bowman St | 3 |  |  | WITHDRAWN
831 | 0 | 0 | 0 |  | 2023-06-20 | Lisbon | LISBON FALLS | 232D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 18 - Lewiston Loop - 2 | Hotel Rd/Gulf/Middle St/Crowleys | 3 |  |  | WITHDRAWN
832 | 0 | 0 | 0 |  | 2023-07-05 | Baldwin | BALDWIN | 691D1 | Solar | 0 | 0 |  |  |  |  | 2023-11-15 | 2024-01-25 |  |  |  |  | 2024-04-23 | [8 empty] | Q4 2024 | WITHDRAWN | WITHDRAWN |  | Cluster 13 - Kimball Rd-Lovell - 2 | Kimball Road/Lovell | 3 |  | Not Required | EXECUTED
833 | 0 | 0 | 0 |  | 2023-07-07 | Carmel | CARMEL | 808D3 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 17 - Detroit Guilford Belfast - 2 | Detroit | 3 |  | Not Required | RE_QUEUED
834 | 0 |  | 0 |  | 2023-07-20 | Fryeburg | FRYEBURG TAP | 405D1 | Solar | 999 | 0 |  |  |  |  | 2023-09-05 | 2023-11-08 |  |  |  |  | 2023-12-06 | 2024-10-22 | 2024-12-19 | [6 empty] | Q4 2025 | Fully Executed Interconnection Agreement | Yes | 2024-04-18 | Cluster 13 - Kimball Rd-Lovell - 2 | Kimball Road/Lovell | 3 |  | Not Required | EXECUTED
835 | 0 | 0 | 587 |  | 2023-07-20 | Livermore | LEEDS | 471D1 | Solar/Battery | 0 | 0 | [10 empty] | 2024-01-04 | [8 empty] | Q1 2026 | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster XX - Sturtevant/ Leeds/ Livermore/ Ludden/ Riley_TBD | Leeds | 3 |  |  | RE_QUEUED_FullEx
836 | 0 | 0 | 0 |  | 2023-07-20 | Starks | ANSON | 801D1 | Solar | 0 | 0 | [10 empty] | 2024-04-29 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster XX - Winslow/ County Rd/ Lakewood - TBD | Lakewood | 3 |  | Not Required | EXECUTED
837 | 0 | 0 | 0 |  | 2023-07-20 | Starks | ANSON | 801D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Winslow/ County Rd/ Lakewood - TBD | Lakewood | 3 |  | Not Required | WITHDRAWN
838 | 0 |  | 769 | 0 | 2023-07-24 | Augusta | NORTH AUGUSTA | 272D2 | Solar/DC BESS | 0 | 0 | [10 empty] | 2025-12-16 | [8 empty] | Q4 2024 | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster XX - Augusta E-Puddledock-Bowman St - TBD | North Augusta | 3 |  | Not Required | RE_QUEUED
839 | 0 |  | 647 |  | 2023-07-26 | Strong | STURTEVANT | 858D1A | Solar | 0 | 0 | 2025-02-26 | 2025-04-02 | 2025-06-10 | 2025-07-24 | [15 empty] | Q3 2025 | WITHDRAWN | WITHDRAWN |  | Cluster XX - Sturtevant/ Leeds/ Livermore/ Ludden/ Riley_TBD | Sturtevant | 3 |  | Not Required | #REF!
840 | 0 | 0 | 0 |  | 2023-08-02 | Gray | GRAY | 416D3 | Solar | 0 | 0 |  |  |  |  | 2024-07-08 | 2024-09-09 | [14 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Greater Portland - TBD | Elm St | 3 |  | Not Required | STUDY
841 | 0 | 0 | 0 |  | 2023-08-09 | Bethel | LOCKES MILLS | 429D1 | Solar | 999 | 0 |  |  |  |  | 2023-10-06 | 2023-12-14 |  |  |  |  | 2024-02-14 | [8 empty] | Q1 2026 | Fully Executed Interconnection Agreement | No | 2024-06-27 | Cluster XX - Woodstock/ Roxbury/ Rumford - TBD | Woodstock | 3 |  | Not Required | EXECUTED
842 | 0 | 0 | 0 |  | 2023-08-10 | Bethel | LOCKES MILLS | 429D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Woodstock/ Roxbury/ Rumford - TBD | Woodstock | 3 |  | TBD | WITHDRAWN
843 | 0 | 0 | 0 |  | 2023-08-10 | Bridgton | BRIDGTON | 406D2 | Solar | 0 | 0 |  |  |  |  | 2024-02-16 | 2024-04-25 | [14 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 13 - Kimball Rd-Lovell - 2 | Kimball Road/Lovell | 3 |  | Not Required | WITHDRAWN
844 | 0 | 0 | 0 |  | 2023-08-23 | Bath | WASHINGTON ST (BATH) | 204D6 | Solar/Battery | 0 | 0 | [10 empty] | 2024-03-27 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster XX - Midcoast - TBD | Bath | 3 |  | Not Required | EXECUTED-WITHDRAWN
845 | 0 |  | 823 |  | 2023-08-25 | Peru | RUMFORD INDUSTRIAL PARK | 466D1 | Solar | 999 | 0 |  |  |  |  | 2024-08-16 | 2024-10-21 |  |  |  |  | 2024-11-20 | [8 empty] | Q4 2025 | Fully Executed Interconnection Agreement | No | 2025-03-24 | Cluster XX - Woodstock/ Roxbury/ Rumford - TBD | Rumford IP | 3 |  | Not Required | STUDY
846 | 0 | 0 | 839 |  | 2023-08-30 | Farmington | STURTEVANT | 858D1A | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Sturtevant/ Leeds/ Livermore/ Ludden/ Riley_TBD | Sturtevant | 3 |  | Not Required | RE_QUEUED
847 | 0 | 0 | 0 |  | 2023-08-30 | Skowhegan | SKOWHEGAN NORTH SIDE | 853D2 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Winslow/ County Rd/ Lakewood - TBD | Lakewood | 3 |  | Not Required | RE_QUEUED
848 | 0 | 0 | 0 |  | 2023-09-05 | Waldoboro | MANKTOWN ROAD | 234D1 | Solar | 999 | 0 |  |  |  |  | 2023-10-11 | 2023-12-15 |  |  |  |  | 2024-01-16 | [8 empty] | Q2 2025 | Fully Executed Interconnection Agreement | Yes | 2024-02-16 | Cluster XX - Midcoast - TBD | Highland/Park St | 3 |  | Not Required | EXECUTED
849 | 0 | 0 | 0 |  | 2023-09-26 | Turner | TURNER | 454D1 | Solar | 0 | 0 | [10 empty] | 2024-04-15 | [8 empty] | Q4 2025 | EXECUTED-WITHDRAWN | WITHDRAWN | 2024-08-08 | Cluster 18 - Lewiston Loop - 2 | Hotel Rd/Gulf/Middle St/Crowleys/Norway | 3 |  | Not Required | EXECUTED
850 | 0 | 0 | 0 |  | 2023-09-28 | Freedom | THORNDIKE TAP | 857D1 | Solar | 0 | 0 |  |  |  |  | 2023-10-25 | 2024-01-03 |  |  |  |  | 2024-02-09 | [9 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 17 - Detroit Guilford Belfast - 2 | Belfast | 3 |  | Not Required | #REF!
851 | 0 | 0 | 0 |  | 2023-10-02 | Damariscotta | DAMARISCOTTA MILLS | 219D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Midcoast - TBD | Newcastle | 3 |  | Not Required | RE_QUEUED
852 | 0 | 0 | 0 | 0 | 2023-10-17 | Poland | MECHANIC FALLS | 431D1 | Solar | 0 | 0 | [10 empty] | 2025-04-09 | [8 empty] | Q2 2025 | EXECUTED-WITHDRAWN | WITHDRAWN | 2025-08-12 | Cluster 18 - Lewiston Loop - 2 | Norway | 3 |  | Not Required | QUEUED
853 | 0 | 0 | 0 |  | 2023-11-01 | China | SOUTH CHINA | 244D2 | Solar/Battery | 0 | 0 | [10 empty] | 2024-06-26 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster XX - Augusta E-Puddledock-Bowman St - TBD | Augusta E/Puddledock/Bowman St | 3 |  | Not Required | EXECUTED
854 | 0 |  | 0 |  | 2023-11-28 | Bath | BATH NORTH END | 206D1 | Solar | 650 | 0 |  |  |  |  | 2024-01-31 | 2024-04-04 | 2024-05-07 | 2024-06-19 |  |  | 2024-08-20 | 2025-03-25 | 2025-05-27 | [6 empty] | Q3 2025 | Fully Executed Interconnection Agreement | No |  | Cluster XX - Midcoast - TBD | Bath | 3 |  | Not Required | EXECUTED
855 | 0 | 0 | 0 |  | 2023-12-07 | Embden | EMBDEN | 868D1 | Solar | 999 | 0 |  |  |  |  | 2024-02-16 | 2024-04-16 |  |  |  |  | 2024-05-13 | [8 empty] | Q1 2027 | Fully Executed Interconnection Agreement | No | 2024-11-14 | Cluster XX - Wyman Area - TBD | Embden | 3 |  | Not Required
856 | 0 | 0 | 0 |  | 2023-12-11 | Freeport | FREEPORT | 225D3 | Solar | 990 | 0 |  |  |  |  | 2024-07-03 | 2024-09-05 | 2024-11-14 | 2024-12-20 |  |  | 2025-01-23 | [8 empty] | Q3 2025 | Fully Executed Interconnection Agreement | No | 2025-05-28 | Cluster XX - Greater Portland - TBD | Elm St | 3
857 | 0 | 0 | 0 |  | 2023-12-11 | North Yarmouth | ELM STREET | 620D4 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Greater Portland - TBD | Elm St | 3 |  | Not Required
858 | 0 |  | 723 |  | 2023-12-28 | Parkman | GUILFORD | 821D1 | Solar | 1500 | 0 |  |  |  |  | 2025-05-08 | 2025-07-07 | 2025-09-18 | 2025-10-31 |  |  | 2025-12-31 | [8 empty] | Q2 2027 | Active | No |  | Cluster 17 - Detroit Guilford Belfast - 2 | Guilford | 3
859 | 0 | 0 | 0 |  | 2024-01-04 | West Paris | TRAP CORNER | 453D1 | Solar | 996 | 0 |  |  |  |  | 2024-02-02 | 2024-04-10 |  |  |  |  | 2024-04-23 | [8 empty] | Q2 2025 | Fully Executed Interconnection Agreement | Yes | 2024-05-10 | Cluster XX - Roxbury-Rumford-Woodstock - TBD | Woodstock | 3 |  | Not Required
860 | 0 | 0 | 0 |  | 2024-01-29 | Bristol | BRISTOL | 210D2 | Solar/Battery | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Midcoast - TBD | Newcastle | 3 |  | Not Required
861 | 0 | 0 | 0 |  | 2024-01-30 | Benton | WINSLOW | 870D1 | Solar | 0 | 0 |  |  |  |  | 2024-03-08 | 2024-05-10 | [14 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Winslow/ County Rd/ Lakewood - TBD | Winslow-County Rd | 3 |  | Not Required
862 | 0 | 0 | 0 |  | 2024-02-06 | Lebanon | LEBANON | 695D2 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 19 - Sanford-Quaker Hill - 2 | Sanford | 3 |  | Not Required
863 | 0 |  | 0 |  | 2024-02-06 | Lisbon | LISBON | 231D2 | Solar | 999 | 0 |  |  |  |  | 2024-03-28 | 2024-06-03 |  |  |  |  | 2024-07-19 | 2025-03-18 | 2025-05-19 | [6 empty] | Q2 2025 | Fully Executed Interconnection Agreement | Yes | 2025-01-23 | Cluster XX - Lewiston Loop - TBD | Hotel Rd/Gulf/Middle St/Crowleys | 3 |  | Not Required
864 | 0 | 0 | 0 |  | 2024-02-14 | Raymond | RAYMOND 34 KV | 444D3 | Solar | 996 | 0 |  |  |  |  | 2024-06-17 | 2024-08-21 |  |  |  |  | 2024-10-03 | [8 empty] | Q1 2026 | Fully Executed Interconnection Agreement | No | 2025-02-10 | Cluster XX - Raymond - TBD | Raymond | 3 |  | Not Required
865 | 0 |  | 0 |  | 2024-02-16 | West Bath | BATH 34 | 261D4 | Solar | 975 | 0 |  |  |  |  | 2024-04-09 | 2024-06-12 |  |  |  |  | 2024-07-05 | 2025-01-02 | 2025-03-10 | 2025-04-07 | 2025-06-10 |  |  |  |  | Q2 2026 | Fully Executed Interconnection Agreement | No | 2025-01-22 | Cluster XX - Midcoast - TBD | Bath | 3 |  | Not Required
866 | 0 |  | 857 |  | 2024-02-22 | Yarmouth | ELM STREET | 620D2 | Solar | 975 | 0 |  |  |  |  | 2025-05-05 | 2025-07-10 |  |  |  |  | 2025-08-13 | 2025-12-01 | 2026-02-05 | [6 empty] | Q1 2025 | Fully Executed Interconnection Agreement | No |  | Cluster XX - Greater Portland - TBD | Elm St | 3 |  | Not Required
867 | 0 | 0 | 866 |  | 2024-02-23 | Yarmouth | ELM STREET | 620D2 | Solar | 0 | 0 | [19 empty] | Q1 2025 | WITHDRAWN | WITHDRAWN |  | Cluster XX - Greater Portland - TBD | Elm St | 3 |  | Not Required
868 | 0 | 0 | 0 |  | 2024-02-28 | Sidney | SIDNEY | 242D1 | Solar | 0 | 0 | [10 empty] | 2024-09-12 | [8 empty] | Q2 2025 | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster XX - Augusta E-Puddledock-Bowman St - TBD | Augusta E/Puddledock/Bowman St | 3 |  | Not Required
869 | 0 | 0 | 0 |  | 2024-03-05 | Bath | BATH NORTH END | 206D1 | Solar/Battery | 0 | 0 |  |  |  |  | 2024-11-12 | 2025-01-21 | [14 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 19 - Sanford-Quaker Hill - 2 | Sanford | 3 |  | Not Required
870 | 0 |  | 0 |  | 2024-03-12 | Acton | BUTLER'S CORNER | 612D2 | Solar | 600 | 0 |  |  |  |  | 2024-04-23 | 2024-06-25 |  |  |  |  | 2024-08-16 | [8 empty] | Q4 2025 | Fully Executed Interconnection Agreement | No | 2024-12-23 | Cluster 19 - Sanford-Quaker Hill - 2 | Sanford | 3 |  | Not Required
871 | 0 | 0 | 0 |  | 2024-03-21 | Augusta | SIDNEY | 242D1 | Solar | 0 | 0 | [19 empty] | Q2 2025 | WITHDRAWN | WITHDRAWN |  | Cluster XX - Augusta E-Puddledock-Bowman St - TBD | Augusta E/Puddledock/Bowman St | 3 |  | Not Required
872 | 0 |  | 0 |  | 2024-03-21 | Swanville | BELFAST 115 | 874D1 | Solar | 0 | 0 |  |  |  |  | 2024-05-17 | 2024-07-24 | 2024-09-13 | 2024-10-28 |  |  | 2025-03-10 | 2024-12-02 | 2025-02-06 | [6 empty] | Q3 2026 | Fully Executed Interconnection Agreement | No |  | Cluster 17 - Detroit Guilford Belfast - 2 | Belfast | 3
873 | 0 | 0 | 0 |  | 2024-03-27 | Hollis | BAR MILLS | 678D1 | Solar | 0 | 0 | [10 empty] | 2024-08-29 | [9 empty] | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster xx - Louden-Biddeford IP - TBD | West Buxton | 3 |  | Not Required
874 | 0 | 0 | 0 |  | 2024-05-10 | Fryeburg | FRYEBURG | 415D2 | Solar | 0 | 0 |  |  |  |  | 2024-06-26 | 2024-08-28 |  |  |  |  | 2024-11-07 | [8 empty] | Q3 2025 | WITHDRAWN | WITHDRAWN |  | Cluster XX - Kimball Rd-Lovell - TBD | Kimball Road/Lovell | 3 |  | Not Required
875 | 0 | 0 | 0 |  | 2024-05-13 | Athens | ATHENS | 827D2 | Solar | 0 | 0 | [10 empty] | 2024-11-01 | [8 empty] | Q3 2025 | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster XX - Wyman Area - TBD | Athens | 3 |  | Not Required
876 | 0 | 0 | 0 |  | 2024-05-23 | Sidney | SIDNEY | 242D2 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Augusta E-Puddledock-Bowman St - TBD | Augusta E/Puddledock/Bowman St | 3 |  | Not Required
877 | 0 | 0 | 838 | 0 | 2024-05-28 | Augusta | NORTH AUGUSTA | 272D6 | Solar | 0 | 0 | [19 empty] | Q3 2025 | WITHDRAWN | WITHDRAWN |  | Cluster XX - Augusta E-Puddledock-Bowman St - TBD | North Augusta | 3 |  | Not Required
878 | 0 | 0 | 877 | 0 | 2024-05-28 | Augusta | NORTH AUGUSTA | 272D6 | Solar | 0 | 0 | [19 empty] | Q3 2025 | WITHDRAWN | WITHDRAWN |  | Cluster XX - Augusta E-Puddledock-Bowman St - TBD | North Augusta | 3 |  | Not Required
879 | 0 | 0 | 0 |  | 2024-05-28 | Readfield | PUDDLEDOCK ROAD | 262D1 | Solar | 999 | 0 |  |  |  |  | 2024-11-26 | [5 empty] | 2025-07-21 | 2025-02-12 | 2025-04-04 | 2026-04-13 | 2026-05-27 |  |  |  |  | Q3 2025 | Fully Executed Interconnection Agreement | No |  | Cluster XX - Augusta E-Puddledock-Bowman St - TBD | Augusta E/Puddledock/Bowman St | 3 |  | Not Required
880 | 0 |  | 0 |  | 2024-05-29 | Winterport | PROSPECT | 846D1 | Solar | 900 | 0 |  |  |  |  | 2024-06-28 | 2024-08-30 | 2024-10-21 | 2024-12-05 |  |  | 2024-12-20 | 2025-04-11 | 2025-06-13 | [6 empty] | Q4 2025 | Fully Executed Interconnection Agreement | No | 2025-11-25 | Cluster 17 - Detroit Guilford Belfast - 2 | Belfast | 3 |  | Not Required
881 | 0 | 0 | 0 |  | 2024-05-29 | Mechanic Falls | MECHANIC FALLS | 431D3 | Solar | 0 | 0 | [10 empty] | 2025-12-22 | [8 empty] | Q4 2025 | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 18 - Lewiston Loop - 2 | Norway | 3 |  | Not Required
882 | 0 | 0 | 0 | 0 | 2024-05-29 | Poland | MECHANIC FALLS | 431D1 | Solar | 999 | 0 |  |  |  |  | 2026-01-21 | 2026-03-24 |  |  |  |  | 2026-08-07 | 2026-04-28 | 2026-07-02 | [6 empty] | Q4 2025 | Active | No |  | Cluster 18 - Lewiston Loop - 2 | Norway | 3 |  | Not Required
883 | 0 | 0 | 0 |  | 2024-05-29 | Stockton Springs | PROSPECT | 846D1 | Solar | 0 | 0 |  |  |  |  | 2025-02-06 | [6 empty] | 2025-07-18 | 2025-09-12 | [6 empty] | Q4 2025 | WITHDRAWN | WITHDRAWN |  | Cluster 17 - Detroit Guilford Belfast - 2 | Belfast | 3 |  | Not Required
884 | 0 | 0 | 0 |  | 2024-05-29 | Winterport | PROSPECT | 846D1 | Solar | 0 | 0 | [19 empty] | Q4 2025 | WITHDRAWN | WITHDRAWN |  | Cluster 17 - Detroit Guilford Belfast - 2 | Belfast | 3 |  | Not Required
885 | 0 | 0 | 0 |  | 2024-06-04 | Limerick | LIMERICK | 632D1 | Solar | 0 | 0 | [10 empty] | 2025-04-14 | [8 empty] | Q4 2024 | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 13 - Kimball Rd-Lovell - 2 | Kimball Road/Lovell | 3 |  | Not Required
886 | 0 | 0 | 0 |  | 2024-06-17 | Jay | RILEY | 449D2 | Solar | 0 | 0 | [10 empty] | 2025-02-26 | [8 empty] | Q4 2024 | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster XX - Sturtevant-Leeds-Livermore-Ludden-Riley - TBD | Riley | 3 |  | Not Required
887 | 0 | 0 | 0 |  | 2024-06-18 | Andover | ANDOVER | 400D1 | Solar | 0 | 0 | [10 empty] | 2025-03-14 | [8 empty] | Q4 2024 | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster XX - Woodstock/ Roxbury/ Rumford - TBD | Roxbury | 3 |  | Not Required
888 | 0 | 0 | 0 |  | 2024-06-18 | Naples | BRIDGTON | 406D2 | Solar | 0 | 0 | [10 empty] | 2025-03-24 | [8 empty] | Q2 2026 | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 13 - Kimball Rd-Lovell - 2 | Kimball Road/Lovell | 3 |  | Not Required
889 | 0 | 0 | 805 |  | 2024-06-26 | Manchester | MANCHESTER | 233D1 | Solar | 0 | 0 | [19 empty] | Q2 2024 | WITHDRAWN | WITHDRAWN |  | Cluster XX - Augusta E-Puddledock-Bowman St - TBD | Augusta E/Puddledock/Bowman St | 3 |  | Not Required
890 | 0 | 0 | 0 |  | 2024-07-02 | Skowhegan | SKOWHEGAN SOUTH SIDE | 854D2 | Solar | 600 | 0 |  |  |  |  | 2024-08-09 | 2024-10-08 |  |  |  |  | 2024-11-07 | [8 empty] | Q4 2024 | Fully Executed Interconnection Agreement | No | 2025-04-08 | Cluster XX - Augusta E-Puddledock-Bowman St - TBD | Augusta E/Puddledock/Bowman St | 3 |  | Not Required
891 | 0 | 0 | 0 |  | 2024-07-18 | South Portland | RIGBY | 650D4 | Battery | 0 | 0 |  |  |  |  | 2025-06-13 | 2025-08-19 | [13 empty] | Q4 2026 | WITHDRAWN | WITHDRAWN |  | Cluster XX - Winslow/ County Rd/ Lakewood - TBD | Lakewood | 3
892 | 0 | 0 | 0 |  | 2024-07-18 | Scarborough | PLEASANT HILL | 644D1 | Battery | 0 | 0 |  |  |  |  | 2025-06-13 | 2025-08-19 | [13 empty] | Q4 2026 | WITHDRAWN | WITHDRAWN |  | Cluster XX - Greater Portland - TBD | Pleasant Hill | 3
893 | 0 | 0 | 0 |  | 2024-07-18 | Westbrook | BRIGHTON AVE | 611D1 | Battery | 0 | 0 | [19 empty] | Q4 2026 | WITHDRAWN | WITHDRAWN |  | Cluster XX - Greater Portland - TBD | Pleasant Hill | 3
894 | 0 | 0 | 0 |  | 2024-07-18 | Westbrook | SPRING STREET | 668D1 | Battery | 0 | 0 |  |  |  |  | 2025-06-13 | 2025-08-19 | [13 empty] | Q4 2026 | WITHDRAWN | WITHDRAWN |  | Cluster XX - Greater Portland - TBD | Sewall St. | 3
895 | 0 | 0 | 0 |  | 2024-07-18 | South Paris | NORWAY | 435D1 | Solar/Battery | 0 | 0 | [10 empty] | 2025-01-03 | [8 empty] | Q4 2026 | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster XX - Greater Portland - TBD | Spring St | 3
896 | 0 | 0 | 0 |  | 2024-07-24 | Pittsfield | PITTSFIELD | 842D1 | Solar | 0 | 0 | [10 empty] | 2025-01-22 | [8 empty] | Q3 2025 | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster XX - Louden-Biddeford IP - TBD | Norway | 3
897 | 0 | 0 | 0 |  | 2024-07-25 | Freeport | FREEPORT | 225D4 | Battery | 0 | 0 | [19 empty] | Q4 2026 | WITHDRAWN | WITHDRAWN |  | Cluster XX - Detroit-Guilford-Belfast - TBD | Detroit | 3
898 | 0 | 0 | 0 |  | 2024-08-01 | Gorham | MOSHERS | 635D2 | Battery | 0 | 0 | [19 empty] | Q4 2026 | WITHDRAWN | WITHDRAWN |  | Cluster XX - Greater Portland - TBD | Elm St | 3
899 | 0 | 0 | 0 |  | 2024-08-26 | Dexter | DEXTER | 813D3 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | No |  | Cluster XX - Greater Portland - TBD | Elm St | 3
900 | 0 |  | 0 |  | 2024-09-03 | Warren | THOMASTON CREEK | 246D3 | Solar | 0 | 0 |  |  |  |  | 2024-11-15 | 2025-01-15 | [5 empty] | 2025-02-21 | 2025-04-23 | [6 empty] | Q4 2026 | WITHDRAWN | WITHDRAWN |  | Cluster XX - Midcoast - TBD | Highland/Park St | 3
901 | 0 |  | 0 |  | 2024-09-03 | Clinton | CLINTON | 810D1 | Solar | 975 | 0 |  |  |  |  | 2024-10-04 | 2024-12-09 |  |  |  |  | 2025-01-08 | [8 empty] | Q4 2026 | Fully Executed Interconnection Agreement | No | 2025-05-15 | Cluster XX - Midcoast - TBD | Park St. | 3 |  | Not Required
902 | 0 |  | 895 |  | 2024-09-05 | South Paris | NORWAY | 435D1 | Solar | 999 | 0 |  |  |  |  | 2025-02-12 | 2025-04-16 |  |  |  |  | 2025-04-24 | 2025-11-14 | 2026-01-21 | [6 empty] | Q4 2025 | Active | No | 2025-08-26 | Cluster XX - Winslow/ County Rd/ Lakewood - TBD | Detroit | 3 |  | Not Required
903 | 0 |  | 0 |  | 2024-09-06 | Hollis | BONNY EAGLE | 610D1 | Solar | 999 | 0 |  |  |  |  | 2024-10-25 | 2025-01-03 |  |  |  |  | 2025-04-01 | [8 empty] | Q4 2025 | Fully Executed Interconnection Agreement | No | 2025-07-22 | Cluster 18 - Lewiston Loop - 2 | Norway | 3 |  | Not Required
904 | 0 | 0 | 0 |  | 2024-09-09 | Richmond | RICHMOND | 240D1 | Solar | 0 | 0 |  |  |  |  | 2024-10-18 | 2024-12-16 |  |  |  |  | 2025-02-13 | [8 empty] | Q4 2026 | WITHDRAWN | WITHDRAWN |  | Cluster XX - Augusta E-Puddledock-Bowman St - TBD | Augusta E/Puddledock/Bowman St | 3
905 | 0 | 0 | 0 |  | 2024-09-10 | Cornish | HIRAM TAP | 692D1 | Solar | 0 | 0 | [19 empty] | Q4 2026 | WITHDRAWN | WITHDRAWN |  | Cluster 13 - Kimball Rd-Lovell - 2 | Kimball Road/Lovell | 3
906 | 0 | 0 | 0 |  | 2024-09-11 | Corinna | CORINNA | 811D1 | Solar | 0 | 0 | 2024-11-11 |  |  |  | 2024-11-11 | [15 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 17 - Detroit Guilford Belfast - 2 | Detroit | 3
907 | 0 | 0 |  |  | 2024-09-11 | Starks | ANSON | 801D1 | Solar | 0 | 0 |  |  |  |  | 2024-11-12 | 2024-03-10 | [6 empty] | N/A | 2025-01-08 | [5 empty] | Q4 2026 | WITHDRAWN | WITHDRAWN |  | Cluster XX - Winslow/ County Rd/ Lakewood - TBD | Lakewood | 3
908 | 0 | 0 | 0 |  | 2024-09-12 | Penobscot | BUCKSPORT | 806D2 | Solar | 0 | 0 | [10 empty] | 2025-04-09 | [8 empty] | Q1 2026 | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 17 - Detroit Guilford Belfast - 2 | Bucksport | 3 |  | Not Required
909 | 0 | 0 | 0 |  | 2024-09-12 | Carmel | CARMEL | 808D2 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster 17 - Detroit Guilford Belfast - 2 | Detroit | 3
910 | 0 | 0 | 909 |  | 2024-09-12 | Levant | CARMEL | 808D3 | Solar | 0 | 0 | 2025-03-31 | 2025-04-28 | [17 empty] | Q1 2026 | WITHDRAWN | WITHDRAWN |  | Cluster 17 - Detroit Guilford Belfast - 2 | Detroit | 3
911 | 0 | 0 | 910 |  | 2024-09-12 | Levant | CARMEL | 808D3 | Solar | 0 | 0 | [10 empty] | 2025-12-08 | [8 empty] | Q3 2026 | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 17 - Detroit Guilford Belfast - 2 | Detroit | 3
912 | 0 | 0 | 0 |  | 2024-09-12 | Dover-Foxcroft | DOVER | 815D2 | Solar | 0 | 0 | 2025-02-18 | 2025-03-25 | [17 empty] | Q4 2025 | WITHDRAWN | WITHDRAWN |  | Cluster 17 - Detroit Guilford Belfast - 2 | Guilford | 3
913 | 0 | 0 | 815 |  | 2024-10-08 | Mexico | RUMFORD | 447D4 | Solar | 0 | 0 | [19 empty] | Q4 2026 | WITHDRAWN | WITHDRAWN |  | Cluster XX - Woodstock/ Roxbury/ Rumford - TBD | Rumford | 3
914 | 0 | 0 | 827 | RQP-1 | 2024-10-08 | Monmouth | MONMOUTH | 457D2 | Solar | 0 | 0 | [19 empty] | Q4 2026 | WITHDRAWN | WITHDRAWN |  | Cluster XX - Augusta E-Puddledock-Bowman St - TBD | Monmouth | 3
915 | 0 | 0 | 0 |  | 2024-10-08 | Wilton | WILTON | 885D1 | Solar | 0 | 0 |  |  |  |  | 2024-11-25 | [15 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Sturtevant/ Leeds/ Livermore/ Ludden/ Riley_TBD | Sturtevant | 3
916 | 0 |  | 0 |  | 2024-10-16 | Baldwin | BALDWIN | 691D1 | Solar | 0 | 0 | 2024-12-16 | 2025-01-22 | 2025-03-18 | [16 empty] | Q4 2025 | WITHDRAWN | WITHDRAWN |  | Cluster 13 - Kimball Rd-Lovell - 2 | Kimball Road/Lovell | 3
917 | 0 | 0 | 0 |  | 2024-10-16 | Penobscot | BUCKSPORT | 806D2 | Solar | 0 | 0 | [10 empty] | 2025-11-11 | [8 empty] | Q4 2025 | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster 17 - Detroit Guilford Belfast - 2 | Bucksport | 3
918 | 0 | 0 | 0 |  | 2024-11-06 | Springvale | BUTLER'S CORNER | 612D1 | Solar | 0 | 0 |  |  |  |  | 2024-12-24 | 2025-03-03 | [13 empty] | Q1 2026 | WITHDRAWN | WITHDRAWN |  | Cluster 19 - Sanford-Quaker Hill - 2 | Sanford | 3
919 | 0 | 0 | 0 |  | 2024-11-14 | Searsport | SEARSPORT | 850D2 | Solar | 0 | 0 | [19 empty] | Q1 2026 | WITHDRAWN | WITHDRAWN |  | Cluster 17 - Detroit Guilford Belfast - 2 | Belfast | 3
920 | 0 | 0 | 0 |  | 2024-11-18 | Biddeford | BIDDEFORD PUMP | 605D2 | Solar | 0 | 0 | [10 empty] | 2025-04-09 | [8 empty] | Q2 2027 | EXECUTED-WITHDRAWN | WITHDRAWN |  | Cluster XX - Louden-Biddeford IP - TBD | Louden | 3
921 | 0 | 0 | 0 |  | 2024-12-03 | Arundel | MAY STREET | 634D1 | Solar | 0 | 0 |  |  |  |  | 2025-01-13 | 2025-03-19 |  |  |  |  | 2025-04-07 | [8 empty] | Q4 2026 | WITHDRAWN | WITHDRAWN |  | Cluster XX - Louden-Biddeford IP - TBD | Louden | 3
922 | 0 | 0 | 835 |  | 2024-12-03 | Leeds | LEEDS | 471D2 | Solar | 0 | 0 | [19 empty] | Q3 2026 | WITHDRAWN | WITHDRAWN |  | Cluster XX - Sturtevant-Leeds-Livermore-Ludden-Riley - TBD | Leeds | 3
923 | 0 | 0 | 907 |  | 2024-12-06 | Starks | ANSON | 801D1 | Solar | 0 | 0 | [19 empty] | Q1 2026 | WITHDRAWN | WITHDRAWN |  | Cluster XX - Winslow-County Rd-Lakewood - TBD | Lakewood | 3
924 | 0 |  | 0 |  | 2024-12-10 | Dover-Foxcroft | DOVER | 815D1 | Solar | 975 | 0 |  |  |  |  | 2025-07-11 | 2025-09-05 |  |  |  |  | 2025-09-25 | [8 empty] | Q3 2025 | Fully Executed Interconnection Agreement | No |  | Cluster 17 - Detroit Guilford Belfast - 2 | Guilford | 3
925 | 0 | 0 | 888 |  | 2024-12-13 | Bridgton | BRIDGTON | 406D2 | Solar | 0 | 0 | [19 empty] | Q3 2026 | WITHDRAWN | WITHDRAWN |  | Cluster XX - Kimball Rd-Lovell - TBD | Kimball Road/Lovell | 3
926 | 0 | 1 - NORW | 902 | RQP-1 | 2025-01-15 | South Paris | NORWAY | 435D1 | Solar/Battery | 4999 | 4999 |  |  |  |  | 2025-06-25 |  |  |  |  | 2026-08-17 |  | 2025-07-14 | 2026-05-06 | 2025-09-29 |  | 2026-03-13 |  |  |  | Q2 2026 | Active | No |  | Cluster 18 - Lewiston Loop - 2 | Norway | 3
927 | 0 |  | 0 |  | 2025-01-24 | Standish | SHAWS MILL ROAD | 660D2 | Solar | 990 | 0 |  |  |  |  | 2025-03-12 | 2025-05-09 |  |  |  |  | 2025-06-04 | [8 empty] | Q4 2025 | Fully Executed Interconnection Agreement | No | 2025-10-07 | Cluster XX - Raymond - TBD | Raymond | 3 |  | Not Required
928 | 0 | 0 | 925 |  | 2025-02-13 | Bridgton | BRIDGTON | 406D2 | Battery | 0 | 0 |  |  |  |  | 2025-06-04 | 2025-08-08 | [13 empty] | Q3 2026 | WITHDRAWN | WITHDRAWN |  | Cluster XX - Kimball Rd-Lovell - TBD | Kimball Road/Lovell | 3
929 | 0 | 0 | 0 |  | 2025-02-26 | South Portland | PLEASANT HILL | 644D1 | Battery | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN |  | Cluster XX - Greater Portland - TBD | Pleasant Hill | 3
930 | 0 | 0 | 0 |  | 2025-02-26 | Cape Elizabeth | CAPE ELIZABETH | 613D1 | Battery | 0 | 0 |  |  |  |  | 2025-06-26 | 2025-08-22 | [13 empty] | Q4 2027 | WITHDRAWN | WITHDRAWN |  | Cluster XX - Greater Portland - TBD | Pleasant Hill | 3
931 | 0 | 0 | 0 |  | 2025-02-26 | South Portland | HINCKLEY POND | 690D1 | Battery | 0 | 0 | [19 empty] | Q4 2027 | WITHDRAWN | WITHDRAWN |  | Cluster XX - Greater Portland - TBD | Pleasant Hill | 3
932 | 0 | 0 | 0 |  | 2025-03-07 | Dixmont | UNITY | 860D1 | Solar | 0 | 0 | 2025-06-18 | 2025-07-24 | 2025-08-18 | 2025-09-30 | [15 empty] | Q2 2026 | WITHDRAWN | WITHDRAWN
933 | 0 | 0 | 924 |  | 2025-03-21 | Dover-Foxcroft | DOVER | 815D2 | Solar | 0 | 0 |  |  |  |  | 2025-12-01 | 2026-02-05 | [13 empty] | Q2 2027 | WITHDRAWN | WITHDRAWN
934 | 0 | 0 | 0 |  | 2025-07-07 | Limington | NORTH LIMINGTON | 638D2 | Solar/Battery | 999 | 0 |  |  |  |  | 2025-09-08 | 2025-11-12 |  |  |  |  | 2025-12-08 | [8 empty] | Q2 2026 | Fully Executed Interconnection Agreement | No
935 | 0 | 0 | 928 |  | 2025-07-16 | Bridgton | BRIDGTON | 406D2 | Solar | 0 | 0 |  |  |  |  | 2025-11-03 | [14 empty] | Q2 2026 | Active | No
936 | 0 | 0 | 911 |  | 2025-07-16 | Levant | CARMEL | 808D3 | Solar | 0 | 0 | [19 empty] | Q2 2026 | WITHDRAWN | WITHDRAWN
937 | 0 | 0 | 0 |  | 2025-07-16 | BERWICK | BASSETT | 602D2 | Solar | 0 | 0 | [10 empty] | 2025-11-03 | [8 empty] | Q2 2026 | EXECUTED-WITHDRAWN | No
938 | 0 | 0 | 0 |  | 2025-07-16 | NEW SHARON | FARMINGTON FALLS | 818D1 | Solar | 0 | 0 |  |  |  |  | 2025-08-18 | 2025-10-22 | [13 empty] | Q2 2026 | WITHDRAWN | WITHDRAWN
939 | 0 | 0 | 0 |  | 2025-07-16 | LIMINGTON | NORTH LIMINGTON | 638D1 | Solar | 0 | 0 | [19 empty] | Q2 2026 | Active | No
940 | 0 | 0 | 0 |  | 2025-07-16 | PENOBSCOT | BUCKSPORT | 806D2 | Solar | 0 | 0 | [19 empty] | Q2 2026 | WITHDRAWN | WITHDRAWN
941 | 0 | 0 | 0 |  | 2025-07-16 | JAY | RILEY | 449D2 | Solar | 999 | 0 |  |  |  |  | 2025-08-22 | 2025-10-28 |  |  |  |  | 2025-11-03 | [8 empty] | Q2 2026 | Fully Executed Interconnection Agreement | No
942 | 0 | 0 | 0 |  | 2025-07-16 | FRYEBURG | LOVELL | 430D1 | Solar | 0 | 0 |  |  |  |  | 2025-08-22 | 2025-10-28 | [13 empty] | Q2 2026 | WITHDRAWN | WITHDRAWN
943 | 0 | 0 | 937 |  | 2025-07-16 | BERWICK | BASSETT | 602D2 | Solar | 0 | 0 | [19 empty] | Q42026 | WITHDRAWN | No
944 | 0 | 0 | 0 |  | 2025-07-25 | FRYEBURG | LOVELL | 430D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN
945 | 0 | 0 | 0 |  | 2025-07-28 | Wilton | WILTON | 885D1 | Solar | 999 | 0 |  |  |  |  | 2025-10-03 | [5 empty] | 2026-04-16 | 2025-11-21 | 2026-01-28 | [6 empty] | Q3 2026 | Fully Executed Interconnection Agreement | No
946 | 0 | 0 | 0 |  | 2025-09-12 | Corinna | CORINNA | 811D1 | Solar | 999 | 0 |  |  |  |  | 2025-11-21 | 2026-01-28 |  |  |  |  | 2026-03-02 | [8 empty] | Q32026 | Fully Executed Interconnection Agreement | No
947 | 0 | 0 | 0 |  | 2025-09-22 | Dixfield | LUDDEN LANE | 461D1 | Solar | 4500 | 0 |  |  |  |  | 2025-10-16 | 2025-12-12 |  |  |  |  | 2026-04-07 | 2026-02-03 | 2026-03-24 | [6 empty] | Q4 2026 | Fully Executed Interconnection Agreement
948 | 0 | 0 | 933 |  | 2025-09-26 | Dover-Foxcroft | DOVER | 815D2 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN
949 | 0 | 0 | 0 |  | 2025-10-06 | Gorham | FORT HILL | 624D1 | Solar | 0 | 0 |  |  |  |  | 2025-10-23 | [14 empty] | Q42026 | WITHDRAWN | WITHDRAWN
950 | 0 | 0 | 0 |  | 2025-10-15 | Pittsfield | BURNHAM | 807D1 | Solar | 975 | 0 |  |  |  |  | 2025-10-22 | 2025-12-08 |  |  |  |  | 2025-12-16 | [9 empty] | Fully Executed Interconnection Agreement
951 | 0 | 0 | 0 |  | 2025-12-10 | Jay | RILEY | 449D2 | Solar | 0 | 0 | [19 empty] | Q4 2027 | WITHDRAWN | WITHDRAWN
952 | 0 | 0 | 0 |  | 2025-12-10 | Sabattus | SABATTUS | 450D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN
953 | 0 | 0 | 0 |  | 2025-12-17 | Orland | BUCKSPORT | 806D1 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN
954 | 0 | 0 | 878 | 0 | 2025-12-24 | Sidney | NORTH AUGUSTA | 272D6 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN
955 | 0 | 0 | 0 |  | 2025-12-29 | Gardiner | GARDINER | 226D2 | Solar | 0 | 0 | [20 empty] | WITHDRAWN | WITHDRAWN
956 | 0 | 0 | 0 |  | 2025-12-29 | Whitefield | COOPERS MILLS ROAD | 230D2 | Solar | 0 | 0 | [19 empty] | Q4 2027 | Active
957 | 0 | 1 - NOAU | 954 | RQP-1 | 2025-12-30 | Sidney | NORTH AUGUSTA | 272D6 | Solar | 999 | 0 | [20 empty] | Active
Formulas:
Combined Study = IF(OR([Application Status]="EXECUTED-WITHDRAWN"),"",IF('Level 4 Applications'!EG2=0,"",'Level 4 Applications'!EG2))
Completion = IF(OR([Application Status]="EXECUTED-WITHDRAWN"),"",IF('Level 4 Applications'!EZ2=0,"",'Level 4 Applications'!EZ2))
Completion = IF(OR([Application Status]="EXECUTED-WITHDRAWN"),"",IF('Level 4 Applications'!EX38=0,"",'Level 4 Applications'!EX38))
ReQueued Restudy = IF(OR([Application Status]="EXECUTED-WITHDRAWN"),"",IF('Level 4 Applications'!EJ35=0,"",'Level 4 Applications'!EJ35))
R`Qd One Stop = IF(OR([Application Status]="EXECUTED-WITHDRAWN"),"",IF('Level 4 Applications'!FC35=0,"",'Level 4 Applications'!FC35))
R`Qd Two Start = IF(OR([Application Status]="EXECUTED-WITHDRAWN"),"",IF('Level 4 Applications'!EK35=0,"",'Level 4 Applications'!EK35))
R`Qd Two Stop = IF(OR([Application Status]="EXECUTED-WITHDRAWN"),"",IF('Level 4 Applications'!FD35=0,"",'Level 4 Applications'!FD35))
Feasibility Study = IF(OR([Application Status]="EXECUTED-WITHDRAWN"),"",IF('Level 4 Applications'!EE38=0,"",'Level 4 Applications'!EE38))
Feasibility Study = IF(OR([Application Status]="EXECUTED-WITHDRAWN"),"",IF('Level 4 Applications'!EG907=0,"",'Level 4 Applications'!EG907))
Impact Study = IF(OR([Application Status]="EXECUTED-WITHDRAWN"),"",IF('Level 4 Applications'!EF38=0,"",'Level 4 Applications'!EF38))
ReStudy = IF(OR([Application Status]="EXECUTED-WITHDRAWN"),"",IF('Level 4 Applications'!EH45=0,"",'Level 4 Applications'!EH45))
R`Qd Three Start = IF(OR([Application Status]="EXECUTED-WITHDRAWN"),"",IF('Level 4 Applications'!EL80=0,"",'Level 4 Applications'!EL80))
R`Qd Three Stop = IF(OR([Application Status]="EXECUTED-WITHDRAWN"),"",IF('Level 4 Applications'!FE80=0,"",'Level 4 Applications'!FE80))
Facility Study = IF(OR([Application Status]="EXECUTED-WITHDRAWN"),"",IF('Level 4 Applications'!EI153=0,"",'Level 4 Applications'!EI153))
R`Qd Four Start = IF(OR([Application Status]="EXECUTED-WITHDRAWN"),"",IF('Level 4 Applications'!EM351=0,"",'Level 4 Applications'!EM351))
R`Qd Four Stop = IF(OR([Application Status]="EXECUTED-WITHDRAWN"),"",IF('Level 4 Applications'!FF351=0,"",'Level 4 Applications'!FF351))

## Energized Dates
PRJ # | Energized Date
1 | 2022-12-19
2 | 2021-06-10
3 | 2021-06-10
4 | 2021-06-23
5 | 2021-06-14
6 | 2022-06-01
7 | 2023-03-17
8 | 2021-05-28
9 | 2024-02-08
10 | 2020-10-01
14 | 2021-12-15
17 | 2022-07-14
18 | 2024-11-06
19 | 2022-06-23
20 | 2023-08-24
21 | 2021-12-20
22 | 2022-06-01
23 | 2022-03-25
24 | 2022-03-16
25 | 2022-07-28
31 | 2022-08-24
32 | 2023-02-10
33 | 2024-04-16
37 | 2024-11-05
40 | 2023-05-17
43 | 2022-11-03
44 | 2024-12-03
45 | 2022-04-13
46 | 2024-08-27
48 | 2022-09-01
49 | 2023-01-19
50 | 2021-12-01
51 | 2020-12-31
53 | 2023-10-31
57 | 2021-09-24
61 | 2023-06-06
62 | 2021-05-26
63 | 2023-07-28
64 | 2022-07-13
66 | 2024-03-13
68 | 2024-12-17
70 | 2023-11-13
77 | 2022-03-31
79 | 2024-12-19
80 | 2022-01-18
81 | 2023-03-16
82 | 2022-09-28
84 | 2022-11-17
87 | 2024-10-31
89 | 2022-03-30
94 | 2022-06-16
95 | 2023-08-31
102 | 2022-06-29
110 | 2022-09-29
114 | 2023-10-23
116 | 2023-08-17
118 | 2023-10-20
119 | 2023-11-27
122 | 2021-06-17
123 | 2022-05-03
124 | 2021-12-17
125 | 2022-03-23
133 | 2021-10-25
135 | 2024-11-04
140 | 2026-03-05
141 | 2022-12-13
142 | 2024-07-17
144 | 2024-10-29
146 | 2022-11-09
148 | 2023-06-22
150 | 2021-06-08
152 | 2024-11-22
153 | 2022-03-22
161 | 2022-04-20
163 | 2022-10-12
168 | 2023-01-25
170 | 2024-02-22
172 | 2021-12-01
174 | 2021-06-16
175 | 2022-02-24
176 | 2023-04-27
180 | 2020-12-30
181 | 2021-11-17
183 | 2023-04-26
184 | 2025-06-30
185 | 2025-07-07
186 | 2023-07-18
189 | 2024-01-02
191 | 2023-10-25
201 | 2025-04-15
203 | 2023-05-02
205 | 2024-12-02
206 | 2022-12-14
207 | 2022-06-29
209 | 2022-06-28
213 | 2022-12-30
214 | 2021-04-28
217 | 2024-10-17
218 | 2023-05-24
219 | 2023-12-28
221 | 2022-06-28
227 | 2023-08-04
229 | 2023-06-27
235 | 2023-01-27
236 | 2023-05-25
245 | 2023-08-10
247 | 2024-11-05
252 | 2021-05-06
254 | 2024-07-16
256 | 2021-12-29
258 | 2023-10-05
264 | 2023-10-03
265 | 2024-12-18
270 | 2024-02-27
271 | 2024-09-06
275 | 2022-03-25
281 | 2024-09-18
282 | 2022-08-26
287 | 2024-06-27
290 | 2023-09-08
297 | 2024-07-03
298 | 2024-11-18
301 | 2022-12-13
305 | 2024-10-09
311 | 2023-06-29
316 | 2023-11-16
321 | 2021-11-11
328 | 2024-07-08
330 | 2023-06-08
332 | 2024-10-16
333 | 2022-09-21
338 | 2023-11-15
342 | 2024-12-12
343 | 2023-12-08
344 | 2023-12-30
353 | 2023-05-19
355 | 2024-09-16
358 | 2024-10-16
360 | 2024-07-11
365 | 2022-12-05
366 | 2023-11-06
368 | 2024-11-25
372 | 2023-04-19
376 | 2022-07-28
377 | 2023-12-12
380 | 2024-10-21
385 | 2024-12-02
386 | 2023-05-31
387 | 2023-08-24
388 | 2024-12-27
390 | 2024-04-02
391 | 2023-07-26
392 | 2023-07-26
400 | 2024-10-18
401 | 2023-12-04
408 | 2024-12-16
409 | 2024-03-12
411 | 2023-10-03
413 | 2023-12-01
414 | 2024-11-19
415 | 2024-12-20
416 | 2022-04-05
429 | 2023-07-25
436 | 2022-12-29
437 | 2023-11-09
445 | 2024-12-17
448 | 2024-12-12
451 | 2024-12-12
453 | 2022-08-02
459 | 2023-12-20
474 | 2024-06-28
475 | 2023-10-06
476 | 2023-06-30
477 | 2025-12-23
478 | 2024-05-22
479 | 2024-12-10
485 | 2023-08-10
487 | 2024-11-20
491 | 2024-12-18
493 | 2023-04-07
506 | 2024-04-10
518 | 2023-02-14
519 | 2024-12-31
523 | 2023-12-18
561 | 2025-12-11
566 | 2023-12-07
599 | 2024-12-09
603 | 2024-12-07
608 | 2025-12-30
620 | 2025-12-22
626 | 2024-12-23
652 | 2024-11-18
653 | 2026-04-27
673 | 2024-12-19
674 | 2026-01-06
706 | 2024-12-03
715 | 2024-11-07
724 | 2026-04-02
733 | 2024-12-10
741 | 2025-12-22
745 | 2025-08-13
758 | 2025-12-31
796 | 2025-06-28
798 | 2025-10-31
806 | 2026-04-21
821 | 2025-12-11
834 | 2025-12-17
848 | 2025-08-07
859 | 2025-05-07
863 | 2025-10-28
101-106 | 2026-07-29
107/108 | 2022-05-10
97/98 | 2024-12-03

## Non enegized queue (hidden)
PRJ | NonEnergized QP | Substation | Circuit | Developer
1 | 0 | FAIRFIELD | 817D3 | Madison Energy Holdings
2 | 0 | OXFORD | 437D1 | CRSEF Acadia Aggregator, LLC
3 | 0 | OXFORD | 437D2 | CRSEF Acadia Aggregator, LLC
4 | 0 | BLAIR ROAD | 207D2 | CRSEF Acadia Aggregator, LLC
5 | 0 | SHAWMUT | 852D1 | CRSEF Acadia Aggregator, LLC
6 | 0 | WINSLOW | 870D2 | CRSEF Acadia Aggregator, LLC
7 | 0 | SOUTH WATERVILLE | 855D2 | Madison Energy Holdings
8 | 0 | RUMFORD INDUSTRIAL PARK | 466D1 | Agilitas Energy, Inc.
9 | 0 | HIGH STREET | 626D1 | Nautilus Solar
10 | 0 | SHAWMUT | 852D1 | Aligned Solar Partners
11 | 1 - SAIP | SANFORD INDUSTRIAL PARK | 656D3 | NEW ENGLAND BATTERY STORAGE
12 | 0 | DOVER | 815D1 | NEW ENGLAND BATTERY STORAGE
13 | 0 | PUDDLEDOCK ROAD | 262D1 | Agilitas Energy, Inc.
14 | 0 | HARTLAND | 824D2 | Madison Energy Holdings
15 | 0 | MUSSEY ROAD | 636D2 | NEW ENGLAND BATTERY STORAGE
16 | 0 | HARTLAND | 824D1 | Walden Renewables
17 | 0 | PRATT & WHITNEY | 661D2 | Nautilus Solar
18 | 0 | SOUTH SANFORD | 667D1 | Nautilus Solar
19 | 0 | PRATT & WHITNEY | 661D2 | Walden Renewables
20 | 0 | DETROIT | 812D1 | LongRoad Development Company LLC
21 | 0 | UNITY | 860D1 | Madison Energy Holdings
22 | 0 | NEWPORT | 837D1 | CRSEF Acadia Aggregator, LLC
23 | 0 | HOTEL ROAD | 420D4 | Renewable Properties
24 | 0 | DEER RIPS | 412D4 | Renewable Properties
25 | 0 | SKOWHEGAN NORTH SIDE | 853D1 | MN8 Energy LLC
26 | 0 | SKOWHEGAN NORTH SIDE | 853D1 | Dynamic Energy
27 | 0 | DUNSTAN | 617D2 | BORREGO SOLAR SYSTEMS INC
28 | 0 | HOTEL ROAD | 420D4 | CRSEF Acadia Aggregator, LLC
29 | 0 | HOTEL ROAD | 420D4 | CRSEF Acadia Aggregator, LLC
30 | 0 | DEER RIPS | 412D4 | NEXTGRID INC
31 | 0 | RUMFORD | 447D2 | Nexamp, Inc
32 | 0 | FORT HILL | 624D1 | Nexamp, Inc
33 | 0 | GREAT FALLS | 436D6 | Nexamp, Inc
34 | 1 - GRFA | GREAT FALLS | 436D6 | Nexamp, Inc
35 | 0 | TRAP CORNER | 453D1 | Nexamp, Inc
36 | 0 | THOMASTON CREEK | 246D1 | Nexamp, Inc
37 | 0 | BIDDEFORD PUMP | 605D2 | Bluewave MA, LLC
38 | 0 | BIDDEFORD PUMP | 605D1 | Bluewave MA, LLC
39 | 0 | BIDDEFORD PUMP | 605D1 | Bluewave MA, LLC
40 | 0 | SCARBOROUGH | 693D1 | Navisun LLC
41 | 0 | BONNY EAGLE | 610D2 | Bluewave MA, LLC
42 | 0 | BONNY EAGLE | 610D2 | Bluewave MA, LLC
43 | 0 | KIMBALL ROAD | 423D1 | Nexamp, Inc
44 | 0 | LOUDEN | 633D1 | Bluewave MA, LLC
45 | 0 | CROWLEYS | 411D1 | Renewable Properties
46 | 0 | WINSLOW | 870D2 | NEXTGRID INC
47 | 0 | BIDDEFORD PUMP | 605D1 | NEXTGRID INC
48 | 0 | OAKLAND | 839D1 | Renewable Properties
49 | 0 | FRYEBURG TAP | 405D2 | Nautilus Solar
50 | 0 | RAYMOND 115 KV | 445D2 | Harrison Street
51 | 0 | WESTON HYDRO | 866D1 | Aligned Solar Partners
52 | 0 | LEBANON | 695D2 | NEXTGRID INC
53 | 0 | SHAWS MILL ROAD | 660D1 | Nautilus US Power Holdco, LLC
54 | 0 | HOTEL ROAD | 420D2 | New Leaf Energy, Inc
55 | 0 | HOTEL ROAD | 420D2 | New Leaf Energy, Inc
56 | 0 | HOTEL ROAD | 420D2 | New Leaf Energy, Inc
57 | 0 | BETHEL | 403D1 | ECA Solar
58 | 0 | HOTEL ROAD | 420D2 | New Leaf Energy, Inc
59 | 0 | BONNY EAGLE | 610D2 | Bluewave ME, LLC
60 | 0 | BONNY EAGLE | 610D2 | Bluewave MA, LLC
61 | 0 | WINTHROP | 256D1 | Nexamp, Inc
62 | 0 | RUMFORD INDUSTRIAL PARK | 466D1 | Energy Management, Inc.
63 | 0 | CASCO TAP | 463D1 | REA Investments
64 | 0 | GRAY | 416D2 | Nautilus US Power Holdco, LLC
65 | 0 | TURNER | 454D1 | New Leaf Energy, Inc
66 | 0 | STURTEVANT | 858D3 | Madison Energy Holdings
67 | 0 | BONNY EAGLE | 610D2 | Soltage LLC
68 | 0 | LEEDS | 471D2 | Walden Renewables
69 | 0 | TURNER | 454D1 | BORREGO SOLAR SYSTEMS INC
70 | 0 | PUDDLEDOCK ROAD | 262D1 | Syncarpha Solar LLC
71 | 0 | PUDDLEDOCK ROAD | 262D1 | Syncarpha Solar LLC
72 | 0 | LEEDS | 471D2 | LongRoad Development Company LLC
73 | 0 | LEEDS | 471D2 | LongRoad Development Company LLC
74 | 0 | FRYEBURG | 415D2 | Dirigo/BNRG
75 | 0 | OAKLAND | 839D1 | HEP
76 | 0 | FORT HILL | 624D2 | HEP
77 | 0 | BALDWIN | 691D1 | LongRoad Development Company LLC
78 | 0 | DUNSTAN | 617D2 | BORREGO SOLAR SYSTEMS INC
79 | 0 | GUILFORD | 821D1 | C2 ENERGY DEVELOPMENT LLC
80 | 0 | DETROIT | 812D1 | Summit Ridge Energy
81 | 0 | STICKNEYS CORNER | 245D2 | Summit Ridge Energy
82 | 0 | COUNTY RD (RICE RIPS) | 873D1 | Nautilus US Power Holdco, LLC
83 | 0 | WILTON | 885D1 | Dirigo/BNRG
84 | 0 | BRIDGTON | 406D1 | Nautilus US Power Holdco, LLC
85 | 0 | BALDWIN | 691D1 | LongRoad Development Company LLC
86 | 0 | BRIDGTON 34 KV | 406D4 | Summit Ridge Energy
87 | 0 | BANGOR HYDRO (Versant) | 120D1 | Atlus Power LLC
88 |  | TURNER TAP | 467D1 | Greenbacker Capital
89 | 0 | MONMOUTH | 457D1 | LongRoad Development Company LLC
90 | 0 | KIMBALL ROAD | 423D1 | Pine Gate Renewables LLC
91 | 0 | BONNY EAGLE | 610D2 | Pine Gate Renewables LLC
92 | 1 - PDRD | PUDDLEDOCK ROAD | 262D1 | New Leaf Energy, Inc
93 | 0 | MAINE YANKEE | 274D1 | MEVS LLC AKA CENERGY
94 | 0 | AUGUSTA K5 | 200D2 | Syncarpha Capital, LLC
95 | 0 | MANCHESTER | 233D1 | AES Clean Energy
96 | 0 | FRYEBURG TAP | 405D1 | ECA Solar
97 | 0 | LEBANON | 695D2 | Dimension Renewable Energy
98 | 0 | LEBANON | 695D2 | Dimension Renewable Energy
99 | 0 | TURNER TAP | 467D1 | Dimension Renewable Energy
100 | 0 | TURNER TAP | 467D1 | Dimension Renewable Energy
101 | 1 - LIME | LIMERICK | 632D1 | Dimension Renewable Energy
102 | 0 | STICKNEYS CORNER | 245D1 | Nautilus US Power Holdco, LLC
103 | 0 | LOUDEN | 633D1 | Turning Point Energy
104 | 0 | CROWLEYS | 411D1 | Turning Point Energy
105 | 0 | NEWPORT | 837D2 | Turning Point Energy
106 | 2 - LIME | LIMERICK | 632D1 | Dimension Renewable Energy
107 | 0 | LIVERMORE FALLS | 428D3 | Nexamp, Inc
108 | 0 | LIVERMORE FALLS | 428D3 | Nexamp, Inc
109 | 0 | HOTEL ROAD | 420D6 | Turning Point Energy
110 | 0 | BASSETT | 602D3 | Nexamp, Inc
111 | 0 | BRUNSWICK WEST SIDE | 213D3 | Turning Point Energy
112 | 0 | PRATT & WHITNEY | 661D1 | Turning Point Energy
113 | 0 | NEWPORT | 837D2 | Turning Point Energy
114 | 0 | CROWLEYS | 411D1 | Summit Ridge Energy
115 | 0 | FACTORY ISLAND | 621D1 | Turning Point Energy
116 | 0 | WINTHROP | 256D3 | Nexamp, Inc
117 | 0 | GUILFORD | 821D3 | C2 ENERGY DEVELOPMENT LLC
118 | 0 | WYMAN HYDRO | 872D1 | MEVS LLC AKA CENERGY
119 | 0 | BUCKSPORT | 806D2 | Nexamp, Inc
120 | 0 | BURNHAM | 807D1 | CIANBRO CORP
121 | 0 | KIMBALL ROAD | 423D1 | BORREGO SOLAR SYSTEMS INC
122 | 0 | WALDOBORO | 252D2 | SunRaise Investments LLC
123 | 0 | BLAIR ROAD | 207D2 | SunRaise Investments LLC
124 | 0 | SOUTH CHINA | 244D1 | SunRaise Investments LLC
125 | 0 | NORTH AUGUSTA | 272D6 | LongRoad Development Company LLC
126 | 0 | THOMASTON CREEK | 246D3 | Turning Point Energy
127 | 0 | SWETT ROAD | 682D1/D2 | Turning Point Energy
128 | 0 | RICHMOND | 240D1 | Turning Point Energy
129 | 0 | NEWPORT | 837D2 | Turning Point Energy
130 | 0 | BALDWIN | 691D1 | Walden Renewables
131 | 0 | COUNTY RD (RICE RIPS) | 873D1 | Summit Ridge Energy
132 | 0 | COUNTY RD (RICE RIPS) | 873D1 | LongRoad Development Company LLC
133 | 0 | LIVERMORE FALLS | 428D3 | REVISION ENERGY INC
134 | 0 | MONMOUTH | 457D1 | Dynamic Energy
135 | 0 | MONMOUTH | 457D1 | Atlus Power LLC
136 | 0 | MONMOUTH | 457D1 | MN8 Energy LLC
137 | 0 | MONMOUTH | 457D1 | MN8 Energy LLC
138 | 0 | BRIDGTON 34 KV | 406D4 | Soltage LLC
139 | 0 | LIMERICK | 632D1 | Dynamic Energy
140 | 1 - GUIL | GUILFORD | 821D1 | REC Solar Commercial Corporation
141 | 0 | SOUTH CHINA | 244D2 | SunRaise Investments LLC
142 | 0 | UNION | 251D1 | Standard Solar
143 | 0 | HOTEL ROAD | 420D4 | BORREGO SOLAR SYSTEMS INC
144 | 0 | UNION | 251D1 | Aligned Solar Partners 6, LP
145 | 0 | BRYANT POND | 407D1 | BORREGO SOLAR SYSTEMS INC
146 | 0 | OXFORD | 437D1 | Nexamp, Inc
147 | 0 | NORTH LIMINGTON | 638D1 | CEC Development LLC
148 | 0 | MEADOW ROAD | 270D1 | Nexamp, Inc
149 | 0 | NORTH LIMINGTON | 638D1 | Soltage LLC
150 | 0 | HIRAM TAP | 692D1 | SunRaise Investments LLC
151 | 1 - KIRD | KIMBALL ROAD | 423D2 | DIMENSION ENERGY LLC
152 | 0 | LEEDS | 471D2 | Dynamic Energy
153 | 0 | SKOWHEGAN TAP | 864D1 | Harrison Street
154 | 0 | SKOWHEGAN SOUTH SIDE | 854D1 | Dynamic Energy
155 | 0 | GRAY | 416D3 | BORREGO SOLAR SYSTEMS INC
156 | 0 | SHAWS MILL ROAD | 660D1 | CEC Development LLC
157 | 0 | STURTEVANT | 858D1A | Environomics
158 | 0 | STURTEVANT | 858D1A | EDF Renewables
159 | 0 | NEWPORT | 837D2 | SunRaise Investments LLC
160 | 0 | NEWPORT | 837D2 | SunRaise Investments LLC
161 | 0 | BIDDEFORD INDUSTRIAL PARK | 673D1 | Madison Energy Holdings
162 | 0 | STICKNEYS CORNER | 245D2 | SunRaise Investments LLC
163 | 0 | COOPERS MILLS ROAD | 230D1 | Summit Ridge Energy
164 | 0 | DEXTER | 813D3 | Turning Point Energy
165 | 0 | MONMOUTH | 457D1 | LongRoad Development Company LLC
166 | 0 | SHAWS MILL ROAD | 660D1 | CEC Development LLC
167 | 0 | CARMEL | 808D1 | CEC Development LLC
168 | 0 | TOPSHAM 34 KV | 250D2 | Nexamp, Inc
169 | 0 | CARMEL | 808D1 | CEC Development LLC
170 | 0 | NORWAY | 435D3 | Summit Ridge Energy
171 | 0 | BRIDGTON | 406D2 | LongRoad Development Company LLC
172 | 0 | BUTLER'S CORNER | 612D2 | Harrison Street
173 | 0 | WINSLOW | 870D1 | SunRaise Investments LLC
174 | 0 | BELFAST WEST SIDE | 803D5 | SunRaise Investments LLC
175 | 0 | TOPSHAM 34 KV | 250D1 | SunRaise Investments LLC
176 | 0 | SPRING STREET | 668D5 | Summit Ridge Energy
177 | 0 | CARMEL | 808D3 | Syncarpha Solar LLC
178 | 0 | NORWAY | 435D3 | LongRoad Development Company LLC
179 | 0 | MONMOUTH | 457D1 | LongRoad Development Company LLC
180 | 0 | BAR MILLS | 678D2 | REVISION ENERGY INC
181 | 0 | UNITY | 860D2 | REVISION ENERGY INC
182 | 0 | WESTON HYDRO | 866D2 | MEVS LLC AKA CENERGY
183 | 0 | FAIRFIELD | 817D1 | Nexamp, Inc
184 |  | SKOWHEGAN TAP | 864D1 | MEVS LLC AKA CENERGY
185 | 0 | SKOWHEGAN TAP | 864D1 | MEVS LLC AKA CENERGY
186 | 0 | MAINE YANKEE | 274D1 | Luminace
187 | 0 | STURTEVANT | 858D1A | Dynamic Energy
188 | 0 | BRIDGTON 34 KV | 406D4 | Syncarpha Solar LLC
189 | 0 | MESSINA | 238D1 | Syncarpha Solar LLC
190 | 0 | PITTSFIELD | 842D1 | Syncarpha Solar LLC
191 | 0 | WALDOBORO | 252D2 | Syncarpha Solar LLC
192 | 0 | DOVER | 815D2 | REVISION ENERGY INC
193 | 0 | MONMOUTH | 457D2 | BORREGO SOLAR SYSTEMS INC
194 | 0 | ANSON | 801D1 | REVISION ENERGY INC
195 | 0 | BLAIR ROAD | 207D2 | REVISION ENERGY INC
196 | 0 | WESTON HYDRO | 866D1 | REVISION ENERGY INC
197 | 0 | WESTON HYDRO | 866D1 | REVISION ENERGY INC
198 | 0 | LISBON | 231D2 | Dimension Renewable Energy
199 | 0 | OXFORD | 437D1 | REVISION ENERGY INC
200 | 1 - LEED | LEEDS | 471D1 | Syncarpha Solar LLC
201 |  | UNITY | 860D1 | Syncarpha Solar LLC
202 | 0 | SWETT ROAD | 682D2 | New Leaf Energy, Inc
203 | 0 | SEARSPORT | 850D1 | Nexamp, Inc
204 | 0 | STURTEVANT | 858D1A | Environomics
205 | 0 | UNITY | 860D2 | Aligned Solar Partners
206 | 0 | PRATT & WHITNEY | 661D1 | Nautilus US Power Holdco, LLC
207 | 0 | ATHENS | 827D2 | Nautilus Solar
208 | 0 | CONY ROAD | 216D1 | Turning Point Energy
209 | 0 | BROWNS CROSSING | 211D2 | Nautilus Solar
210 | 0 | DETROIT | 812D2 | Turning Point Energy
211 | 0 | NEWPORT | 837D1 | Turning Point Energy
212 | 0 | BOND BROOK | 208D3 | MEVS LLC AKA CENERGY
213 | 0 | BOWMAN STREET | 263D1 | AES Clean Energy
214 | 0 | GARDINER | 226D2 | SunRaise Investments LLC
215 | 0 | LISBON FALLS | 232D2 | Turning Point Energy
216 | 0 | MCCOYS | 237D1 | Turning Point Energy
217 | 0 | SPRING STREET | 668D5 | Nautilus Solar
218 | 0 | RILEY | 449D2 | Nexamp, Inc
219 | 0 | CLINTON | 810D1 | Navisun LLC
220 | 0 | WARREN | 253D1 | Bluewave MA, LLC
221 | 0 | GARDINER | 226D2 | SunRaise Investments LLC
222 | 0 | TOPSHAM 34 KV | 250D1 | SunRaise Investments LLC
223 | 0 | PARIS TAP | 409D1 | SunRaise Investments LLC
224 | 0 | PARIS TAP | 409D1 | SunRaise Investments LLC
225 | 0 | MECHANIC FALLS | 431D3 | NEXTGRID INC
226 |  | MECHANIC FALLS | 431D2 | NEXTGRID INC
227 | 0 | WESTON HYDRO | 866D1 | REC Energy Solar Holdings, LLC
228 | 0 | PARIS TAP | 409D1 | Sustainable Strategies 2050 Inc
229 | 0 | SKOWHEGAN NORTH SIDE | 853D1 | Nexamp, Inc
230 | 0 | GUILFORD | 821D1 | Dimension Renewable Energy
231 | 0 | PRATT & WHITNEY | 661D1 | Turning Point Energy
232 | 0 | BASSETT | 602D3 | Turning Point Energy
233 | 0 | LOVELL | 430D1 | Nexamp, Inc
234 | 0 | LOVELL | 430D1 | Nexamp, Inc
235 | 0 | TRAP CORNER | 453D1 | Nexamp, Inc
236 | 0 | WINSLOW | 870D1 | SunRaise Investments LLC
237 | 0 | DENMARK | 413D1 | Con Edison Clean Energy
238 | 0 | MANCHESTER | 233D1 | Con Edison Clean Energy
239 | 0 | HIRAM TAP | 692D1 | CEC Development LLC
240 | 0 | SEARSPORT | 850D2 | SunRaise Investments LLC
241 | 0 | WINSLOW | 870D1 | Bluewave MA, LLC
242 | 0 | WINSLOW | 870D1 | Bluewave MA, LLC
243 | 0 | WINSLOW | 870D1 | Bluewave MA, LLC
244 | 0 | SEARSPORT | 850D2 | SunRaise Investments LLC
245 | 0 | ANSON | 801D1 | REVISION ENERGY INC
246 |  | DEXTER | 813D1 | Dirigo/BNRG
247 | 0 | NORTH ANSON | 838D1 | Nautilus US Power Holdco, LLC
248 | 0 | SPRING STREET | 668D5 | Dirigo/BNRG
249 | 0 | SKOWHEGAN NORTH SIDE | 853D2 | Dirigo/BNRG
250 | 0 | BOND BROOK | 208D3 | MEVS LLC AKA CENERGY
251 | 0 | FARMINGTON FALLS | 818D2 | Summit Ridge Energy
252 | 0 | BERWICK | 603D2 | Energy Management, Inc.
253 | 0 | RAYMOND 115 KV | 445D2 | ISM Solar Development LLC
254 | 0 | SOUTH WATERVILLE | 855D2 | REVISION ENERGY INC
255 | 0 | FORT HILL | 624D2 | REVISION ENERGY INC
256 | 0 | MEADOW ROAD | 270D2 | Navisun LLC
257 | 0 | MANCHESTER | 233D2 | Con Edison Clean Energy
258 | 0 | CROWLEYS | 411D1 | Nautilus US Power Holdco, LLC
259 | 0 | HARTLAND | 824D2 | Standard Solar
260 | 0 | HIRAM TAP | 692D1 | Soltage LLC
261 | 0 | STRATTON | 877D1 | EDF Renewables
262 |  | LIVERMORE FALLS | 428D1 | NEXTGRID INC
263 | 0 | MONMOUTH | 457D3 | Dimension Renewable Energy
264 | 0 | PHILLIPS/STRONG | 841D1 | Nexamp, Inc
265 | 0 | OAKLAND | 839D1 | Greenbacker Capital
266 | 0 | DAMARISCOTTA MILLS | 219D2 | Nexamp, Inc
267 | 0 | MONMOUTH | 457D1 | Encore Redevelopment, LLC
268 | 1 - CORI | CORINNA | 811D1 | Nexamp, Inc
269 | 0 | NORWAY | 435D3 | BORREGO SOLAR SYSTEMS INC
270 | 0 | VASSALBORO | 861D8 | Summit Ridge Energy
271 | 0 | SABATTUS | 450D1 | Dynamic Energy
272 | 0 | MONSON | 834D2 | Nexamp, Inc
273 | 0 | BETHEL | 403D1 | Dimension Renewable Energy
274 | 0 | CARMEL | 808D2 | Dimension Renewable Energy
275 | 0 | SIDNEY | 242D1 | Summit Ridge Energy
276 | 0 | MOSHERS | 635D1 | REVISION ENERGY INC
277 | 0 | SOUTH CHINA | 244D2 | LongRoad Development Company LLC
278 | 0 | HOTEL ROAD | 420D7 | LongRoad Development Company LLC
279 | 0 | UNITY | 860D2 | LongRoad Development Company LLC
280 | 0 | UNITY | 860D1 | LongRoad Development Company LLC
281 | 0 | VASSALBORO | 861D9 | Summit Ridge Energy
282 | 0 | ATHENS | 827D2 | LongRoad Development Company LLC
283 | 0 | DENMARK | 413D2 | LongRoad Development Company LLC
284 | 0 | HOTEL ROAD | 420D4 | Con Edison Clean Energy
285 | 0 | SOUTH SANFORD | 667D2 | Con Edison Clean Energy
286 | 0 | WINSLOW | 870D1 | Bluewave MA, LLC
287 | 0 | NORWAY | 435D1 | Nautilus Solar Energy, LLC
288 | 0 | SKOWHEGAN NORTH SIDE | 853D1 | EDF Renewables
289 | 0 | SKOWHEGAN NORTH SIDE | 853D1 | EDF Renewables
290 | 0 | WOOLWICH | 258D1 | Luminace
291 | 0 | BRIDGTON 34 KV | 406D4 | LongRoad Development Company LLC
292 | 0 | PRATT & WHITNEY | 661D2 | LongRoad Development Company LLC
293 | 0 | BASSETT | 602D2 | EDF Renewables
294 | 0 | LEEDS | 471D2 | Bluewave MA, LLC
295 | 0 | PAPOOSE POND | 438D1 | SunRaise Investments LLC
296 | 0 | MECHANIC FALLS | 431D2 | Synergen Solar
297 | 0 | WATERBORO | 671D1 | Madison Energy Holdings
298 | 0 | SKOWHEGAN SOUTH SIDE | 854D1 | Dynamic Energy
299 | 0 | HOTEL ROAD | 420D4 | Standard Solar
300 | 0 | DETROIT | 812D1 | Standard Solar
301 | 0 | CONY ROAD | 216D2 | Nautilus Solar Energy
302 | 0 | MECHANIC FALLS | 431D3 | ISM Solar Development LLC
303 | 0 | STURTEVANT | 858D2 | Syncarpha Solar LLC
304 | 0 | STURTEVANT | 858D2 | Syncarpha Solar LLC
305 | 0 | RANGELEY | 875D2 | Nautilus US Power Holdco, LLC
306 | 0 | CORINNA | 811D1 | Dirigo/BNRG
307 | 0 | LIVERMORE FALLS | 428D2 | OYA Diamond
308 | 1 - DEXT | DEXTER | 813D1 | US Solar Development, LLC
309 | 0 | DEXTER | 813D1 | US Solar Development, LLC
310 | 0 | WINTHROP | 256D3 | Summit Ridge Energy
311 | 0 | COOPERS MILLS ROAD | 230D2 | REVISION ENERGY INC
312 | 0 | NAPLES TAP | 469D1 | Bluewave MA, LLC
313 | 0 | ANSON | 801D1 | Encore Redevelopment, LLC
314 | 0 | BLAIR ROAD | 207D2 | AES DISTRIBUTED ENERGY, INC.
315 | 0 | MECHANIC FALLS | 431D3 | Bluewave MA, LLC
316 | 0 | NORTH AUGUSTA | 272D4 | SOL ALLIANCE DEVELOPMENT LLC
317 | 0 | NORWAY | 435D3 | UGE USA Inc
318 | 0 | MONSON | 834D1 | UGE USA Inc
319 | 0 | RAYMOND 34 KV | 444D3 | LastMile Energy
320 | 0 | BRAGDON COMMONS | 689D1 | Turning Point Energy
321 | 0 | WATERBORO | 671D2 | Solar Managment International
322 | 0 | SKOWHEGAN TAP | 864D1 | Nexamp, Inc
323 | 0 | HARTLAND | 824D1 | Nexamp, Inc
324 | 0 | UNION | 251D1 | REVISION ENERGY INC
325 | 0 | DEER RIPS | 412D4 | Ameresco, Inc
326 | 0 | NORTH LIMINGTON | 638D1 | Novel Energy Solutions LLC
327 | 0 | SPRING STREET | 668D5 | NBD SOLAR MAINE LLC
328 | 0 | SANFORD INDUSTRIAL PARK | 656D3 | Novel Energy Solutions LLC
329 | 0 | DEER RIPS | 412D1 | Hexagon Energy LLC
330 | 0 | BASSETT | 602D3 | Summit Ridge Energy
331 | 0 | WESTON HYDRO | 866D1 | REVISION ENERGY INC
332 | 0 | NORTH ANSON | 838D1 | Greenbacker Capital
333 | 0 | GOOSEFARE | 630D4 | Nexamp, Inc
334 | 0 | VASSALBORO | 861D9 | Turning Point Energy
335 | 0 | SKOWHEGAN TAP | 864D1 | Nexamp, Inc
336 | 0 | MCCOYS | 237D1 | NextEra Energy Resources
337 | 0 | MCCOYS | 237D1 | NextEra Energy Resources
338 | 0 | SADDLEBACK | 876D1 | Nexamp, Inc
339 | 0 | DOVER | 815D2 | UGE USA INC
340 | 0 | STURTEVANT | 858D4 | US Solar Development, LLC
341 | 1 - NOLI | NORTH LIMINGTON | 638D2 | Novel Energy Solutions LLC
342 | 0 | WATERBORO | 671D2 | Novel Energy Solutions LLC
343 | 0 | BRISTOL | 210D2 | Luminace
344 | 0 | EMBDEN | 868D1 | Luminace
345 | 0 | BUCKSPORT | 806D2 | BORREGO SOLAR SYSTEMS INC
346 | 0 | VASSALBORO | 861D9 | SunRaise Investments LLC
347 | 0 | OXFORD | 437D1 | ISM Solar Development LLC
348 | 0 | WINTHROP | 256D1 | ISM Solar Development LLC
349 | 3 - LIME | LIMERICK | 632D1 | Novel Energy Solutions LLC
350 | 1 - MANC | MANCHESTER | 233D2 | Encore Redevelopment, LLC
351 | 0 | NORTH AUGUSTA | 272D4 | Syncarpha Solar LLC
352 | 0 | COOPERS MILLS ROAD | 230D1 | Syncarpha Solar LLC
353 | 0 | SIDNEY | 242D1 | Nautilus US Power Holdco, LLC
354 | 0 | RAYMOND 115 KV | 445D2 | LongRoad Development Company LLC
355 | 0 | BELFAST 115 | 874D1 | Luminace
356 | 0 | STURTEVANT | 858D4 | REVISION ENERGY INC
357 | 0 | ELM STREET | 620D1 | Renewable Energy International LLC
358 | 0 | BELFAST WEST SIDE | 803D3 | Syncarpha Solar LLC
359 | 0 | DAMARISCOTTA MILLS | 219D1 | Syncarpha Solar LLC
360 | 0 | SOUTH WATERVILLE | 855D2 | CleanTap Energy,LLC
361 | 0 | BASSETT | 602D3 | CleanTap Energy,LLC
362 | 0 | WATERBORO | 671D2 | REVISION ENERGY INC
363 | 0 | COOPERS MILLS ROAD | 230D1 | REVISION ENERGY INC
364 | 0 | BONNY EAGLE | 610D2 | SWEB Development
365 | 0 | LOCKES MILLS | 429D1 | National Renewable Solutions LLC (Summit Ridge Energy)
366 | 0 | EDGECOMB | 223D1 | Syncarpha Solar LLC
367 | 0 | BELFAST 115 | 874D1 | LongRoad Development Company LLC
368 | 0 | BELFAST WEST SIDE | 803D6 | Summit Ridge Energy
369 | 0 | BELFAST WEST SIDE | 803D6 | ISM Solar Development LLC
370 | 0 | MECHANIC FALLS | 431D2 | ASPEN POWER PARTNERS
371 | 0 | VASSALBORO | 861D9 | NEW ENGLAND SOLAR GARDEN CORP
372 | 0 | BERWICK | 603D2 | ASPEN POWER PARTNERS LLC
373 | 0 | LIVERMORE FALLS | 428D3 | ASPEN POWER PARTNERS
374 | 0 | BUTLER'S CORNER | 612D1 | EDF Renewables
375 | 0 | BANGOR HYDRO (Versant) | 120D1 | Dirigo/BNRG
376 | 0 | BRUNSWICK WEST SIDE | 213D1 | SOL ALLIANCE DEVELOPMENT LLC
377 | 0 | BOWMAN STREET | 263D1 | REVISION ENERGY INC
378 | 0 | BIDDEFORD INDUSTRIAL PARK | 673D2 | Dimension Renewable Energy
379 | 0 | MAY STREET | 634D1 | Con Edison Clean Energy
380 | 0 | CROWLEYS | 411D2 | Luminace
381 | 0 | BELFAST WEST SIDE | 803D6 | REVISION ENERGY INC
382 | 0 | GRAY | 416D3 | CleanTap Energy,LLC
383 | 0 | BRYANT POND | 407D1 | Nexamp, Inc
384 | 0 | BUTLER'S CORNER | 612D2 | MELINK SOLAR DEVELOPMENT
385 | 0 | GRAY | 416D1 | Atlus Power LLC
386 | 0 | SKOWHEGAN SOUTH SIDE | 854D1 | Luminace
387 | 0 | NORTH AUGUSTA | 272D3 | EcoPower
388 | 0 | BOND BROOK | 208D1 | BAP POWER CORPORATION dba Cenergy
389 | 0 | PUDDLEDOCK ROAD | 262D1 | Renewable Energy International LLC
390 | 0 | BUCKSPORT | 806D2 | Ameresco, Inc
391 | 0 | CAPITOL STREET | 215D2 | EcoPower
392 | 0 | CAPITOL STREET | 215D3 | EcoPower
393 | 0 | BELFAST WEST SIDE | 803D6 | ASPEN POWER PARTNERS
394 | 0 | CROWLEYS | 411D1 | NEW ENGLAND SOLAR GARDEN CORP
395 | 0 | PROSPECT | 846D1 | NEW ENGLAND SOLAR GARDEN CORP
396 | 0 | BELFAST WEST SIDE | 803D6 | ASPEN POWER PARTNERS
397 | 0 | BELFAST WEST SIDE | 803D6 | ASPEN POWER PARTNERS
398 | 0 | BELFAST WEST SIDE | 803D6 | Aspen Power Partners
399 | 0 | SEARSPORT | 850D1 | ASPEN POWER PARTNERS
400 | 0 | PROSPECT | 846D1 | ASPEN POWER PARTNERS LLC
401 | 0 | BIGELOW | 882D1 | Luminace
402 | 0 | HOTEL ROAD | 420D1 | Turning Point Energy
403 | 0 | SAND ROAD TAP | 470D1 | The Gray Pen Group, LLC
404 | 0 | DEER RIPS | 412D3 | Bluewave MA, LLC
405 | 0 | PROSPECT | 846D1 | SunRaise Investments LLC
406 | 0 | SKOWHEGAN NORTH SIDE | 853T1 | SunRaise Investments LLC
407 |  | COUNTY RD (RICE RIPS) | 873D2 | Dirigo/BNRG
408 | 0 | PARIS TAP | 409D1 | ISM Solar Development LLC
409 | 0 | ATHENS | 827D1 | Greenbacker Capital
410 | 0 | LOVELL | 430D1 | MELINK SOLAR DEVELOPMENT
411 | 0 | THOMASTON CREEK | 246D1 | Nexamp, Inc
412 | 0 | DOVER | 815D1 | CleanTap Energy,LLC
413 | 0 | RICHMOND | 240D1 | RENESOLA POWER HOLDINGS
414 | 0 | LEBANON | 695D2 | Atlus Power LLC
415 | 0 | BROOKS | 805D1 | Encore Redevelopment, LLC
416 | 0 | LINCOLNVILLE | 800D1 | SunRaise Investments LLC
417 | 0 | CROWLEYS | 411D1 | Sustainable Strategies 2050 Inc
418 | 0 | BOND BROOK | 208D2 | NEXTERA ENERGY RESOURCES
419 | 0 | ATHENS | 827D1 | Con Edison Clean Energy
420 | 0 | ATHENS | 827D1 | Con Edison Clean Energy
421 | 0 | ATHENS | 827D1 | Con Edison Clean Energy
422 | 0 | ATHENS | 827D1 | Con Edison Clean Energy
423 | 0 | ATHENS | 827D1 | Con Edison Clean Energy
424 | 0 | ATHENS | 827D1 | Con Edison Clean Energy
425 | 0 | ATHENS | 827D1 | Con Edison Clean Energy
426 | 0 | ATHENS | 827D1 | Con Edison Clean Energy
427 | 0 | PROSPECT | 846D1 | Dirigo/BNRG
428 | 0 | GARDINER | 226D2 | Dimension Renewable Energy
429 | 0 | WEST STREET | 255D1 | Summit Ridge Energy
430 | 0 | BROOKS | 805D1 | Renergetica USA
431 | 0 | ATHENS | 827D2 | REVISION ENERGY INC
432 | 0 | STURTEVANT | 858D3 | US Solar Development, LLC
433 | 0 | BROOKS | 805D1 | NEXTGRID INC
434 | 0 | NORTH AUGUSTA | 272D6 | Solar Fields
435 | 0 | WEST WATERVILLE | 865D5 | REVISION ENERGY INC
436 | 0 | RUMFORD | 447D2 | DSD Renewables
437 | 0 | WESTBROOK | 674D2 | CleanCapital Holdings LLC
438 | 0 | PARK STREET | 239D10 | ISM Solar Development LLC
439 | 0 | WATERBORO | 671T1 | NEXTERA ENERGY RESOURCES
440 | 0 | NAPLES TAP | 469D1 | Soltage LLC
441 | 0 | DEER RIPS | 412D3 | NEXTERA ENERGY RESOURCES
442 | 0 | DEER RIPS | 412D3 | NEXTERA ENERGY RESOURCES
443 | 0 | GRAY | 416D1 | Fogler LLC
444 | 0 | BRAGDON COMMONS | 689D1 | Dirigo/BNRG
445 | 0 | OXFORD | 437D1 | Summit Ridge Energy
446 | 0 | BUTLER'S CORNER | 612D1 | MEVS LLC AKA CENERGY
447 | 0 | BOWMAN STREET | 263D1 | LongRoad Development Company LLC
448 | 0 | BERWICK | 603D2 | Soltage LLC
449 | 0 | RICHMOND | 240D1 | Turning Point Energy
450 | 0 | PAPOOSE POND | 438D1 | BORREGO SOLAR SYSTEMS INC
451 | 0 | LEBANON | 695D1 | Soltage LLC
452 | 0 | TOPSHAM 34 KV | 250D1 | LongRoad Development Company LLC
453 | 0 | PLEASANT HILL | 644D2 | REVISION ENERGY INC
454 | 1 - PNSY | PNSY | PNSY | Ameresco, Inc
455 | 0 | CAPITOL STREET | 215D2 | ISM Solar Development LLC
456 | 0 | THOMASTON CREEK | 246D3 | Bluewave MA, LLC
457 | 0 | SOUTH BERWICK | 663D2 | Norwich Solar Technologies
458 | 0 | SKOWHEGAN SOUTH SIDE | 854D1 | Dirigo/BNRG
459 | 0 | EAST WILTON | 816D1 | Greenbacker Capital
460 | 0 | DOVER | 815D2 | REVISION ENERGY INC
461 | 0 | WILTON | 885D1 | US Solar Development, LLC
462 | 0 | NORTH AUGUSTA | 272D2 | SunRaise Investments LLC
463 | 0 | STURTEVANT | 858D4 | CleanTap Energy,LLC
464 | 0 | SWETT ROAD | 682D1 | Turning Point Energy
465 | 0 | PAPOOSE POND | 438D1 | REVISION ENERGY INC
466 | 0 | HIGH STREET | 626D1 | MEVS LLC AKA CENERGY
467 | 0 | WEST STREET | 255D2 | Summit Ridge Energy
468 | 0 | RILEY | 449D2 | Energy Management, Inc.
469 | 0 | SANFORD SWITCH | 657D4 | MEVS LLC AKA CENERGY
470 | 0 | ATHENS | 827D2 | Emeren
471 | 0 | THOMASTON CREEK | 246D1 | Summit Ridge Energy
472 | 0 | COUNTY RD (RICE RIPS) | 873D1 | Syncarpha Solar LLC
473 | 0 | BURNHAM | 807D1 | Summit Ridge Energy
474 | 0 | FARMINGTON FALLS | 818D1 | Catalyze Holdings, LLC
475 | 0 | SHAWMUT | 852D1 | Luminace
476 | 0 | WEST WATERVILLE | 865D5 | Luminace
477 | 0 | ANDOVER | 400D1 | REVISION ENERGY INC
478 | 0 | AUGUSTA K5 | 200D3 | REVISION ENERGY INC
479 | 0 | CONY ROAD | 216D1 | Novel ME SPV 2 LLC
480 | 0 | EDGECOMB | 223D1 | EDF Renewables
481 | 0 | COUNTY RD (RICE RIPS) | 873D1 | Syncarpha Solar LLC
482 | 0 | WILTON | 885D1 | US Solar Development, LLC
483 | 0 | SANFORD SWITCH | 657D3 | MEVS LLC AKA CENERGY
484 | 0 | WESTON HYDRO | 866D2 | Sunrise Energy Ventures, LLC
485 | 0 | BAR MILLS | 678D1 | Nexamp, Inc
486 | 0 | NORTH ANSON | 838D2 | Dirigo/BNRG
487 | 0 | SKOWHEGAN SOUTH SIDE | 854D1 | Nautilus US Power Holdco, LLC
488 | 0 | PARK STREET | 239D5 | REVISION ENERGY INC
489 | 0 | SHAWMUT | 852D1 | LastMile Energy
490 | 0 | DETROIT | 812D1 | Standard Solar
491 | 0 | BRISTOL | 210D2 | EDPR
492 | 0 | LIMERICK | 632D2 | Soltage LLC
493 | 0 | BROWNS CROSSING | 211D2 | Summit Ridge Energy
494 | 0 | GARDINER | 226D2 | REVISION ENERGY INC
495 | 0 | PROSPECT | 846D1 | FFP ORIGINATION LLC
496 | 0 | BROOKS | 805D1 | FFP ORIGINATION LLC
497 | 0 | RAYMOND 115 KV | 445D2 | Summit Ridge Energy
498 | 0 | GUILFORD | 821D1 | FFP ORIGINATION LLC
499 | 0 | SCARBOROUGH | 693D1 | EDF Renewables
500 | 0 | STURTEVANT | 858D3 | MEVS LLC AKA CENERGY
501 | 0 | SCARBOROUGH | 693D1 | MEVS LLC AKA CENERGY
502 | 0 | STURTEVANT | 858D1A | NEXTERA ENERGY RESOURCES
503 | 0 | HOTEL ROAD | 420D4 | NEXTGRID INC
504 | 0 | TRAP CORNER | 453D1 | MEVS LLC AKA CENERGY
505 | 0 | TOPHAM OLD | 249D1 | Turning Point Energy
506 | 0 | RUMFORD INDUSTRIAL PARK | 466D1 | REA Investments
507 | 0 | SCARBOROUGH | 693D1 | EDF Renewables
508 | 0 | BIDDEFORD INDUSTRIAL PARK | 673D1 | Bluewave MA, LLC
509 | 0 | PARIS TAP | 409D1 | Encore Redevelopment, LLC
510 | 0 | STURTEVANT | 858D2 | Con Edison Clean Energy
511 | 1 - BRIS | BRISTOL | 210D1 | MIDCOAST SOLAR LLC
512 | 0 | DOVER | 815D2 | FFP ORIGINATION LLC
513 | 0 | BAR MILLS | 678D1 | MEVS LLC AKA CENERGY
514 | 0 | BANGOR HYDRO (Versant) | 120D1 | Summit Ridge Energy
515 | 0 | RUMFORD | 447D2 | Summit Ridge Energy
516 | 0 | PROSPECT | 846D1 | Aspen Power Partners
517 | 0 | LOUDEN | 633D1 | BORREGO SOLAR SYSTEMS INC
518 | 0 | FRYEBURG TAP | 405D1 | Bold Coast Energy
519 | 0 | SABATTUS | 450D1 | MEVS LLC AKA CENERGY
520 | 0 | NORWAY | 435D1 | REVISION ENERGY INC
521 | 0 | NEWPORT | 837D2 | SunRaise Investments LLC
522 | 0 | LIMERICK | 632D2 | Fogler LLC
523 | 0 | EMBDEN | 868D1 | Luminace
524 | 1 - BDPP | BIDDEFORD PUMP | 605D1 | THE MAINE WATER COMPANY
525 | 0 | LEEDS | 471D2 | Walden Renewables
526 | 0 | MONSON | 834D2 | FFP ORIGINATION LLC
527 | 0 | SHAWMUT | 852D1 | FFP ORIGINATION LLC
528 | 0 | DENMARK | 413D2 | Summit Ridge Energy
529 | 0 | HOTEL ROAD | 420D7 | US Solar Development, LLC
530 | 0 | NORTH AUGUSTA | 272D6 | US Solar Development, LLC
531 | 0 | BRYANT POND | 407D1 | MEVS LLC AKA CENERGY
532 | 0 | DETROIT | 812D2 | RENESOLA POWER HOLDINGS
533 | 0 | BIDDEFORD INDUSTRIAL PARK | 673D1 | LongRoad Development Company LLC
534 | 0 | WYMAN HYDRO | 872D1 | Encore Redevelopment, LLC
535 | 0 | BAR MILLS | 678D2 | NEXTERA ENERGY RESOURCES
536 | 0 | NEWPORT | 837D2 | UGE USA INC
537 | 0 | FRYEBURG | 415D2 | LongRoad Development Company LLC
538 | 0 | GREAT FALLS | 436D6 | Nexamp, Inc
539 | 0 | MONSON | 834D2 | FFP ORIGINATION LLC
540 | 1 - LULA | LUDDEN LANE | 461D1 | Citizens Energy Corporation
541 | 0 | SANFORD INDUSTRIAL PARK | 656D2 | Bluewave MA, LLC
542 | 0 | EMBDEN | 868D1 | Hexagon Energy LLC
543 | 0 | YORK BEACH | 676D2 | Turning Point Energy
544 | 0 | DETROIT | 812D2 | Sustainable Strategies 2050 Inc
545 | 0 | DOVER | 815D1 | UGE USA INC
546 | 0 | CAMDEN | 214D4 | Norwich Solar Technologies
547 | 0 | TOPHAM OLD | 249D1 | Summit Ridge Energy
548 | 0 | MCCOYS | 237D1 | Sunvest Solar Inc.
549 | 0 | SOUTH WATERVILLE | 855D2 | LastMile Energy
550 | 0 | SANFORD INDUSTRIAL PARK | 656D2 | ME WHITE PINE SOLAR LLC
551 | 0 | LEBANON | 695D2 | EDF Renewables
552 | 0 | WARREN | 253D1 | REVISION ENERGY INC
553 | 0 | CARMEL | 808D2 | Dimension Renewable Energy
554 | 0 | FREEPORT | 225D4 | Novel Energy Solutions LLC
555 | 1 - PAST | PARK STREET | 239D7 | Novel Energy Solutions LLC
556 | 0 | WESTON HYDRO | 866D2 | Engie
557 | 0 | MEADOW ROAD | 270D2 | HODSON INC
558 | 0 | LISBON FALLS | 232D1 | SOLAR PROVIDER GROUP LLC
559 | 0 | CONY ROAD | 216D2 | Bluewave MA, LLC
560 |  | RAYMOND 115 KV | 445D1 | Bluewave MA, LLC
561 | 0 | AUGUSTA K5 | 200D2 | Green Sun LLC
562 | 0 | LISBON | 231D1 | New Leaf Energy, Inc
563 | 0 | HARTLAND | 824D1 | BORREGO SOLAR SYSTEMS INC
564 | 0 | COOPERS MILLS ROAD | 230D2 | New Leaf Energy, Inc
565 | 0 | SWETT ROAD | 682D1 | SOLAR PROVIDER GROUP LLC
566 | 0 | LUDDEN LANE | 461D1 | Nexamp, Inc
567 | 0 | HIGH STREET | 626D5 | RENESOLA POWER HOLDINGS
568 | 0 | SOUTH BERWICK | 663D2 | NEW ENGLAND SOLAR GARDEN CORP
569 | 0 | GRAY | 416D1 | Fogler LLC
570 | 0 | PHILLIPS/STRONG | 841D1 | NEXTGRID INC
571 | 0 | PHILLIPS/STRONG | 841D1 | NEXTGRID INC
572 | 0 | MONSON | 834D1 | Dirigo/BNRG
573 | 0 | BELFAST WEST SIDE | 803D6 | Aspen Power Partners
574 | 0 | DETROIT | 812D1 | CHRISTOPHER ANTHONY
575 | 0 | FARMINGTON FALLS | 818D1 | Summit Ridge Energy
576 | 0 | RUMFORD | 447D2 | Energy Management, Inc.
577 | 0 | COUNTY RD (RICE RIPS) | 873D1 | Galehead Development
578 | 0 | SWETT ROAD | 682D1 | Engie
579 | 0 | WEST BRIDGTON | 458D1 | New Leaf Energy, Inc
580 | 0 | EMBDEN | 868D1 | Hexagon Energy LLC
581 | 0 | RILEY | 449D2 | Hexagon Energy LLC
582 | 0 | PLEASANT HILL | 644D2 | Hexagon Energy LLC
583 | 0 | ELIOT | 687D1 | New Hampshire Solar Garden
584 | 0 | BALDWIN | 691D1 | New Hampshire Solar Garden
585 | 0 | CAMDEN | 214D3 | BORREGO SOLAR SYSTEMS INC
586 | 0 | SHAWS MILL ROAD | 660D2 | Greenbacker Capital
587 | 0 | LEEDS | 471D1 | VC Renewables LLC
588 | 0 | BASSETT | 602D2 | Greenbacker Capital
589 | 0 | GUILFORD | 821D1 | FFP ORIGINATION LLC
590 | 0 | CARMEL | 808D1 | Bluewave MA, LLC
591 | 0 | ELIOT | 687D1 | SOLAR PROVIDER GROUP LLC
592 | 0 | FAIRFIELD | 817D3 | REWILD RENEWABLES LLC
593 | 0 | GUILFORD | 821D1 | FFP ORIGINATION LLC
594 |  | MAY STREET | 634D1 | Dirigo/BNRG
595 | 0 | BOWMAN STREET | 263D1 | Bluewave MA, LLC
596 | 0 | HIRAM TAP | 692D1 | Nexamp, Inc
597 | 0 | LIVERMORE FALLS | 428D2 | FFP ORIGINATION LLC
598 | 0 | NORTH AUGUSTA | 272D6 | Louth Callan Renewables
599 | 0 | CHALLENGER 12 KV | 421D2 | Greenday Finance LLC
600 | 0 | PRIDES CORNER | 647D1 | SOLAR PROVIDER GROUP LLC
601 | 0 | FREEPORT | 225D3 | NEW HAMPSHIRE SOLAR GARDEN
602 | 0 | ANDOVER | 400D1 | GREEN LANTERN DEVELOPMENT LLC
603 | 0 | SHEEPSCOT | 241D1 | SunRay Power, LLC
604 | 0 | MECHANIC FALLS | 431D1 | GREEN LANTERN DEVELOPMENT LLC
605 | 0 | EAST WILTON | 816D1 | Norwich Solar Technologies
606 | 0 | RUMFORD | 447D1 | Norwich Solar Technologies
607 | 0 | WINTHROP | 256D2 | Norwich Solar Technologies
608 |  | MESSINA | 238D1 | Norwich Solar Technologies
609 | 0 | WALDOBORO | 252D1 | CITIZENS ENERGY CORPORATION
610 | 0 | FORT HILL | 624D2 | CITIZENS ENERGY CORPORATION
611 | 0 | DEER RIPS | 412D3 | CITIZENS ENERGY CORPORATION
612 | 0 | STURTEVANT | 858D4 | CITIZENS ENERGY CORPORATION
613 | 0 | PRATT & WHITNEY | 661D1 | ASPEN POWER PARTNERS
614 | 0 | PARK STREET | 239D6 | New Leaf Energy, Inc
615 | 0 | HARTLAND | 824D1 | BORREGO SOLAR SYSTEMS INC
616 | 0 | BUCKSPORT | 806D2 | Galehead Development
617 | 0 | LINCOLNVILLE | 800D1 | Summit Ridge Energy
618 | 0 | DETROIT | 812D1 | UGE USA INC
619 | 0 | WESTBROOK | 674D2 | C2 ENERGY DEVELOPMENT LLC
620 | 1 - PRCO | PRIDES CORNER | 647D3 | EDP RENEWABLES
621 | 0 | NEW VINEYARD | 836D1 | C2 ENERGY DEVELOPMENT LLC
622 | 0 | MANKTOWN ROAD | 234D1 | REVISION ENERGY INC
623 | 0 | LIVERMORE FALLS | 428D2 | SOLAR PROVIDER GROUP LLC
624 | 0 | HIRAM HYDRO | 419D1 | SOLAR PROVIDER GROUP LLC
625 | 0 | BELFAST WEST SIDE | 803D6 | Galehead Development
626 | 0 | DUNSTAN | 617D3 | MEVS LLC AKA CENERGY
627 | 0 | CONY ROAD | 216D2 | Bluewave MA, LLC
628 | 0 | THOMASTON CREEK | 246D3 | Maine Department of Corrections
629 | 0 | BRIDGTON | 406D1 | BORREGO SOLAR SYSTEMS INC
630 | 0 | BATH 34 | 261D3 | Norwich Solar Technologies
631 | 1 - DUNS | DUNSTAN | 617D2 | Bridge Energy
632 | 0 | ANSON | 801D1 | Nexamp, Inc
633 | 0 | SANFORD SWITCH | 657D3 | SOLAR PROVIDER GROUP LLC
634 | 0 | RICHMOND | 240D1 | Nexamp, Inc
635 | 0 | PHILLIPS/STRONG | 841D1 | NBD SOLAR MAINE LLC
636 | 0 | PRIDES CORNER | 647D2 | Walker Capital LLC
637 | 1 - CAEL | CAPE ELIZABETH | 613D1 | Encore Redevelopment, LLC
638 | 0 | NEWPORT | 837D1 | GL Investment LLC
639 | 0 | NORTH WINDHAM | 639D2 | GREEN LANTERN DEVELOPMENT LLC
640 |  | LISBON FALLS | 232D2 | Norwich Solar Technologies
641 | 0 | SEARSPORT | 850D2 | SolAmerica Energy
642 | 0 | DAMARISCOTTA MILLS | 219D2 | Norwich Solar Technologies
643 | 0 | LISBON FALLS | 232D2 | Norwich Solar Technologies
644 | 0 | BATH 34 | 261D3 | Walden Renewables
645 | 0 | NAPLES TAP | 469D1 | Bluewave MA, LLC
646 | 0 | SKOWHEGAN SOUTH SIDE | 854D2 | Galehead Development
647 | 0 | STURTEVANT | 858D3 | NEXTERA ENERGY RESOURCES
648 | 0 | MANCHESTER | 233D2 | Norwich Solar Technologies
649 | 0 | SABATTUS | 450D2 | Syncarpha Solar LLC
650 | 0 | PAPOOSE POND | 438D1 | REVISION ENERGY INC
651 | 0 | KITTERY | 688D1 | Louth Callan Renewables
652 | 0 | BUCKSPORT | 806D1 | Aligned Solar Partners 6 LP c/o Aligned Climate Capital LLC
653 | 1 - WINT | WINTHROP | 256D2 | Norwich Solar Technologies
654 | 0 | RUMFORD | 447D1 | Synergen Solar
655 | 0 | BUCKSPORT | 806D1 | Galehead Development
656 | 0 | RAYMOND 115 KV | 445D2 | Bluewave MA, LLC
657 | 2 - DEXT | DEXTER | 813D3 | Boston Environmental
658 | 0 | SOUTH BERWICK | 663D2 | Novel Energy SPV 4 LLC
659 | 0 | MONMOUTH | 457D2 | BORREGO SOLAR SYSTEMS INC
660 | 0 | COOKS CORNER | 217D3 | C2 ENERGY DEVELOPMENT LLC
661 | 0 | GUILFORD | 821D3 | UGE USA INC
662 | 0 | BATH NORTH END | 206D1 | NEXTERA ENERGY RESOURCES
663 | 0 | SKOWHEGAN SOUTH SIDE | 854D2 | NEXTERA ENERGY RESOURCES
664 | 0 | BATH 34 | 261D3 | NEXTERA ENERGY RESOURCES
665 | 0 | RAYMOND 34 KV | 444D1 | Mainely Solar LLC
666 | 0 | MOSHERS | 635D2 | Dichotomy Power
667 | 0 | NORTH WINDHAM | 639D2 | Dichotomy Power
668 | 0 | SAND ROAD TAP | 470D1 | Mainely Solar LLC
669 | 2 - MANC | MANCHESTER | 233D1 | Nexamp, Inc
670 | 0 | THORNDIKE TAP | 857D1 | NEXTERA ENERGY RESOURCES
671 | 0 | RICHMOND | 240D1 | Nexamp, Inc
672 | 0 | NEWPORT | 837D1 | Nexamp, Inc
673 | 0 | MOSHERS | 635D2 | Elevate Power
674 |  | NORTH WINDHAM | 639D3 | Elevate Power
675 | 0 | BOOTHBAY HARBOR | 209D3 | ReWild Renewables LLC
676 |  | LINCOLNVILLE | 800D1 | REVISION ENERGY INC
677 | 0 | MONMOUTH | 457D1 | NBD SOLAR MAINE LLC
678 | 0 | BUTLER'S CORNER | 612D2 | MELINK SOLAR DEVELOPMENT
679 | 0 | BONNY EAGLE | 610D2 | Louth Callan Renewables
680 | 0 | LIVERMORE FALLS | 428D1 | Louth Callan Renewables
681 | 0 | KENNEBUNKPORT | 629D3 | Louth Callan Renewables
682 | 0 | CORINNA | 811D1 | Dirigo/BNRG
683 | 0 | BOOTHBAY HARBOR | 209D2 | MIDCOAST SOLAR LLC
684 | 0 | CLINTON | 810D1 | Nexamp, Inc
685 | 0 | ELM STREET | 620D2 | C2 ENERGY DEVELOPMENT LLC
686 | 0 | PRIDES CORNER | 647D3 | Louth Callan Renewables
687 | 0 | EMBDEN | 868D1 | Nexamp, Inc
688 | 0 | NORTH WINDHAM | 639D2 | GREEN LANTERN DEVELOPMENT LLC
689 | 0 | LEBANON | 695D2 | Novel Energy Solutions LLC
690 | 0 | ELM STREET | 620D4 | Branch Renewable Energy
691 | 0 | SABATTUS | 450D1 | Novel Energy Solutions LLC
692 | 0 | PUDDLEDOCK ROAD | 262D1 | Norwich Solar Technologies
693 | 0 | WALDOBORO | 252D1 | CITIZENS ENERGY CORPORATION
694 | 0 | STRATTON | 877D1 | New Leaf Energy, Inc
695 | 0 | WESTON HYDRO | 866D2 | YSG Solar
696 | 0 | ELIOT | 687D1 | AGGREGATE RECYCLING
697 | 0 | ATHENS | 827D1 | Nexamp, Inc
698 | 4 - OAKL | OAKLAND | 839D2 | Novel Energy SPV 4 LLC
699 | 0 | OXFORD | 437D1 | Louth Callan Renewables
700 | 0 | WESTON HYDRO | 866D1 | WILDCAT RENEWABLES LLC
701 | 0 | DEER RIPS | 412D4 | Nexamp, Inc
702 | 0 | BUCKSPORT | 806D2 | Ameresco, Inc
703 | 0 | BALDWIN | 691D1 | NEW HAMPSHIRE SOLAR GARDEN
704 | 0 | LOCKES MILLS | 429D1 | Nexamp, Inc
705 | 0 | RUMFORD INDUSTRIAL PARK | 466D1 | Green Lantern DEVELOPMENT LLC
706 | 0 | BRYANT POND | 407D1 | Nexamp, Inc
707 | 0 | RUMFORD | 447D1 | VC Renewables LLC
708 | 0 | FRYEBURG TAP | 405D1 | Nexamp, Inc
709 | 0 | WOOLWICH | 258D1 | Nexamp, Inc
710 | 0 | TOPSHAM 34 KV | 250D1 | SunRaise Investments LLC
711 | 0 | RAYMOND 115 KV | 445D1 | LastMile Energy
712 | 1 - LSFA | LISBON FALLS | 232D1 | Nexamp, Inc
713 | 0 | GREAT FALLS | 436D6 | Novel Energy Solutions LLC
714 | 0 | SKOWHEGAN TAP | 864D1 | Novel Energy Solutions LLC
715 | 0 | HARTLAND | 824D1 | Nexamp, Inc
716 | 0 | SEARSPORT | 850D1 | VCP REALTY LLC
717 | 0 | BIDDEFORD PUMP | 605D2 | Nexamp, Inc
718 | 1 - MONM | MONMOUTH | 457D2 | SOLAMERICA ENERGY LLC
719 | 0 | GREAT FALLS | 436D6 | Novel Energy Solutions LLC
720 | 0 | WINTHROP | 256D1 | Hexagon Energy LLC
721 | 0 | ANSON | 801D1 | Hexagon Energy LLC
722 | 0 | BOOTHBAY HARBOR | 209D3 | ReWild Renewables LLC
723 |  | GUILFORD | 821D1 | Nexamp, Inc
724 | 1 - FAIR | FAIRFIELD | 817D3 | Sunwealth
725 | 1 - SOCH | SOUTH CHINA | 244D2 | Novel Energy Solutions LLC
726 | 0 | MANCHESTER | 233D2 | ACADIA ENERGY LLC
727 | 0 | BLAIR ROAD | 207D1 | SOLAMERICA ENERGY LLC
728 | 1 - BOST | BOWMAN STREET | 263D1 | Novel Energy Solutions LLC
729 | 0 | PUDDLEDOCK ROAD | 262D1 | Hexagon Energy LLC
730 | 0 | BRISTOL | 210D2 | MIDCOAST SOLAR LLC
731 | 1 - VASS | VASSALBORO | 861D8 | Novel Energy Solutions LLC
732 | 1 - LVFA | LIVERMORE FALLS | 428D3 | Novel Energy Solutions LLC
733 | 0 | MCCOYS | 237D1 | Sunvest Solar Inc.
734 | 0 | MIDDLE STREET | 451D8 | NUPOWER BATTERY STORAGE LLC
735 | 0 | MECHANIC FALLS | 431D1 | MECHANIC FALLS GLC SOLAR LLC
736 | 0 | DAMARISCOTTA MILLS | 219D2 | MIDCOAST SOLAR LLC
737 | 1 - SKNS | SKOWHEGAN NORTH SIDE | 853D1 | Novel Energy Solutions LLC
738 | 0 | ANDOVER | 400D1 | GREEN LANTERN DEVELOPMENT LLC
739 | 0 | MESSINA | 238D1 | Bluewave MA, LLC
740 | 0 | RAYMOND 34 KV | 444D1 | Mainely Solar LLC
741 | 0 | SKOWHEGAN TAP | 864D1 | Nexamp, Inc
742 | 0 | SKOWHEGAN TAP | 864D1 | Nexamp, Inc
743 | 0 | LINCOLNVILLE | 800D1 | VCP REALTY LLC
744 | 0 | NORTH WINDHAM | 639D2 | GREEN LANTERN DEVELOPMENT LLC
745 | 0 | SOUTH CHINA | 244D1 | Madison Energy Holdings
746 | 1 - SHAW | SHAWMUT | 852D1 | Novel Energy Solutions LLC
747 | 0 | LOVELL | 430D1 | Nexamp, Inc
748 | 0 | LOVELL | 430D1 | Nexamp, Inc
749 | 0 | LOVELL | 430D1 | Nexamp, Inc
750 | 0 | CARMEL | 808D3 | SOLAMERICA ENERGY LLC
751 | 0 | WESTON HYDRO | 866D2 | Novel Energy Solutions LLC
752 | 0 | DEER RIPS | 412D2 | Bloom Energy Corporation
753 | 0 | PLEASANT HILL | 644D4 | Bloom Energy Corporation
754 | 0 | BIDDEFORD INDUSTRIAL PARK | 673D1 | Bloom Energy Corporation
755 | 0 | SANFORD SWITCH | 657D4 | Bloom Energy Corporation
756 | 0 | CAPITOL STREET | 215D3 | Bloom Energy Corporation
757 |  | MONMOUTH | 457D2 | GREEN LANTERN DEVELOPMENT LLC
758 | 0 | SANFORD INDUSTRIAL PARK | 656D2 | Bluewave MA, LLC
759 | 0 | LAMBERT STREET | 631D1 | BOLD COAST ENERGY, LLC
760 | 0 | MUSSEY ROAD | 636D2 | BOLD COAST ENERGY, LLC
761 | 0 | FAIRFIELD | 817D2 | Bloom Energy Corporation
762 | 0 | BUCKSPORT | 806D1 | Bloom Energy Corporation
763 | 0 | WEST STREET | 255D2 | SHANACHIE PARTNERS LLC
764 | 0 | BIDDEFORD PUMP | 605D2 | Nexamp, Inc
765 | 1 - B115 | BELFAST 115 | 874D1 | Novel Energy Solutions LLC
766 | 0 | CONY ROAD | 216D1 | EAST POINT ENERGY, LLC
767 | 0 | GOOSEFARE | 630D2 | BOLD COAST ENERGY, LLC
768 | 0 | SEARSPORT | 850D1 | SOLAMERICA ENERGY LLC
769 | 0 | NORTH AUGUSTA | 272D4 | RENEWABLE PROPERTIES LLC
770 | 0 | BIGELOW | 882D2 | BNRG MAINE LLC
771 | 0 | BRISTOL | 210D1 | EDPR NA Distributed Generation LLC
772 | 0 | FAIRFIELD | 817D3 | Novel Energy Solutions LLC
773 | 0 | MAY STREET | 634D1 | BOLD COAST ENERGY, LLC
774 | 0 | BOOTHBAY HARBOR | 209D3 | SUSTAINABLE STRATEGIES 2050 INC
775 | 0 | BATH 34 | 261D4 | BOLD COAST ENERGY, LLC
776 | 0 | CHALLENGER 12 KV | 421D2 | BOLD COAST ENERGY, LLC
777 | 0 | MECHANIC FALLS | 431D1 | GREEN LANTERN DEVELOPMENT LLC
778 | 0 | GREAT FALLS | 436D6 | Bluewave MA, LLC
779 | 0 | MONSON | 834D1 | SUSTAINABLE STRATEGIES 2050 INC
780 | 0 | PARK STREET | 239D6 | SUSTAINABLE STRATEGIES 2050 INC
781 | 2 - LVFA | LIVERMORE FALLS | 428D2 | EDPRNA DG Energy Development, LLC
782 | 0 | RUMFORD INDUSTRIAL PARK | 466D1 | SUSTAINABLE STRATEGIES 2050 INC
783 | 0 | MAY STREET | 634D3 | MAINE COMMUNITY ENERGY, LLC
784 | 0 | LEWISTON LOWER 115 | 424D5 | MAINE COMMUNITY ENERGY, LLC
785 | 0 | BOLT HILL | 685D2 | MAINE COMMUNITY ENERGY, LLC
786 | 0 | SABATTUS | 450D2 | MAINE COMMUNITY ENERGY, LLC
787 | 0 | CHALLENGER 12 KV | 421D2 | MAINE COMMUNITY ENERGY, LLC
788 | 0 | BATH 34 | 261D3 | SUSTAINABLE STRATEGIES 2050 INC
789 | 0 | LISBON FALLS | 232D1 | MAINE COMMUNITY ENERGY, LLC
790 | 0 | CARMEL | 808D2 | Novel Energy Solutions LLC
791 | 0 | MECHANIC FALLS | 431D2 | Correlate Inc.
792 | 0 | GRAY | 416D3 | BWC HOLDINGS, INC
793 | 0 | WASHINGTON ST (BATH) | 204D6 | BOLD COAST ENERGY, LLC
794 | 0 | TOPSHAM 34 KV | 250K3 | Freedom Solar Holdings LLC
795 | 2 - LULA | LUDDEN LANE | 461D1 | BNRG MAINE LLC
796 |  | ELM STREET | 620D4 | Dimension ME 1, LLC
797 | 0 | BUCKSPORT | 806D2 | Nexamp, Inc
798 | 0 | ELM STREET | 620D4 | Dimension ME 1, LLC
799 | 0 | BUCKSPORT | 806D2 | Nexamp, Inc
800 | 0 | MIDDLE STREET | 451D8 | NUPOWER BATTERY STORAGE LLC
801 | 1 - PRAT | PRATT & WHITNEY | 661D1 | Nexamp, Inc
802 | 0 | BRIDGTON | 406D1 | New Leaf Energy, Inc
803 | 1 - BEWE | BELFAST WEST SIDE | 803D4 | Bridge Energy
804 | 0 | GOOSEFARE | 630D4 | Freedom Solar Holdings LLC
805 | 0 | MANCHESTER | 233D2 | MIDCOAST SOLAR LLC
806 | 1 - DAMS | DAMARISCOTTA MILLS | 219D2 | MIDCOAST SOLAR LLC
807 | 0 | BRAGDON COMMONS | 689D1 | BNRG MAINE LLC
808 | 1 - LEBA | LEBANON | 695D2 | Nexamp, Inc
809 | 0 | MAY STREET | 634D4 | New Leaf Energy, Inc
810 | 0 | MAY STREET | 634D4 | New Leaf Energy, Inc
811 | 0 | ELM STREET | 620D3 | New Leaf Energy, Inc
812 | 1 - RIGB | RIGBY | 650D4 | New Leaf Energy, Inc
813 | 0 | SIDNEY | 242D1 | Novel Energy Solutions LLC
814 | 1 - NORW | NORWAY | 435D3 | Bridge Energy
815 | 0 | RUMFORD | 447D2 | Novel Energy Solutions LLC
816 | 0 | BALDWIN | 691D1 | Walden Renewables
817 | 2 - MONM | MONMOUTH | 457D2 | Paddle Energy LLC
818 | 1 - TURN | TURNER | 454D1 | Bridge Energy
819 | 0 | MONMOUTH | 457D2 | Paddle Energy LLC
820 | 2 - SKNS | SKOWHEGAN NORTH SIDE | 853D1 | Nexamp, Inc
821 | 1 - MCCO | MCCOYS | 237D1 | REVISION ENERGY INC
822 | 0 | CARMEL | 808D3 | Paddle Energy LLC
823 | 1 - RUIP | RUMFORD INDUSTRIAL PARK | 466D1 | SOLAMERICA ENERGY HOLDINGS, INC
824 | 0 | PARK STREET | 239D7 | Bluewave MA, LLC
825 | 0 | PARK STREET | 239D7 | Bluewave MA, LLC
826 | 0 | ATHENS | 827D1 | Nexamp, Inc
827 | 0 | MONMOUTH | 457D3 | Paddle Energy LLC
828 | 0 | BRUNSWICK WEST SIDE | 213D3 | Nexamp, Inc
829 | 1 - RICH | RICHMOND | 240D1 | Nexamp, Inc
830 | 0 | RICHMOND | 240D1 | Nexamp, Inc
831 | 0 | LISBON FALLS | 232D1 | Nexamp, Inc
832 | 0 | BALDWIN | 691D1 | NHSOLARGARDEN.COM, LLC
833 | 0 | CARMEL | 808D3 | Paddle Energy LLC
834 | 1 - FRYT | FRYEBURG TAP | 405D1 | Nexamp, Inc
835 | 0 | LEEDS | 471D1 | VC Renewables LLC
836 | 0 | ANSON | 801D1 | Nexamp, Inc
837 | 0 | ANSON | 801D1 | Nexamp, Inc
838 | 0 | NORTH AUGUSTA | 272D2 | Borealis Solar LLC
839 | 0 | STURTEVANT | 858D1A | SOLAMERICA ENERGY LLC
840 | 0 | GRAY | 416D3 | BLUEWAVE ORIGINATION LLC
841 | 1 - LOMS | LOCKES MILLS | 429D1 | Nexamp, Inc
842 | 0 | LOCKES MILLS | 429D1 | Nexamp, Inc
843 | 0 | BRIDGTON | 406D2 | Paddle Energy LLC
844 | 0 | WASHINGTON ST (BATH) | 204D6 | MIDCOAST SOLAR LLC
845 | 2 - RUIP | RUMFORD INDUSTRIAL PARK | 466D1 | Nexamp, Inc
846 | 0 | STURTEVANT | 858D1A | SOLAMERICA ENERGY HOLDINGS, INC
847 | 0 | SKOWHEGAN NORTH SIDE | 853D2 | BNRG MAINE LLC
848 | 1 - MARO | MANKTOWN ROAD | 234D1 | REVISION ENERGY INC
849 | 0 | TURNER | 454D1 | Bluewave MA, LLC
850 | 0 | THORNDIKE TAP | 857D1 | DIRIGO DEVELOPMENT LLC
851 | 0 | DAMARISCOTTA MILLS | 219D1 | REVISION ENERGY INC
852 | 0 | MECHANIC FALLS | 431D1 | Paddle Energy LLC
853 | 0 | SOUTH CHINA | 244D2 | Midcoast Solar LLC
854 | 1 - BANE | BATH NORTH END | 206D1 | REVISION ENERGY INC
855 | 1 - EMDE | EMBDEN | 868D1 | Nexamp, Inc
856 | 1 - FREE | FREEPORT | 225D3 | UGE USA INC
857 | 0 | ELM STREET | 620D4 | REVISION ENERGY INC
858 | 3 - GUIL | GUILFORD | 821D1 | KEY SOLAR LLC
859 |  | TRAP CORNER | 453D1 | BAP POWER CORPORATION dba Cenergy
860 | 0 | BRISTOL | 210D2 | MIDCOAST SOLAR LLC
861 | 0 | WINSLOW | 870D1 | Bluewave Project Development, LLC
862 | 0 | LEBANON | 695D2 | DIMENSION ENERGY LLC
863 | 0 | LISBON | 231D2 | DIMENSION ENERGY LLC
864 | 1 - RA34 | RAYMOND 34 KV | 444D3 | MAINELY SOLAR LLC
865 | 1 - BATH | BATH 34 | 261D4 | Norwich Solar Technologies
866 | 1 - ELM | ELM STREET | 620D2 | EDP RENEWABLES
867 | 0 | ELM STREET | 620D2 | EDP RENEWABLES
868 | 0 | SIDNEY | 242D1 | SOLAMERICA ENERGY HOLDINGS, INC
869 | 0 | BATH NORTH END | 206D1 | MIDCOAST SOLAR LLC
870 | 1 - BUCO | BUTLER'S CORNER | 612D2 | Bridge Energy
871 | 0 | SIDNEY | 242D1 | Nexamp, Inc
872 | 0 | BELFAST 115 | 874D1 | VCP REALTY LLC
873 | 0 | BAR MILLS | 678D1 | BAP Power Corporation DBA Cenergy Power
874 | 0 | FRYEBURG | 415D2 | Loki Solar
875 | 0 | ATHENS | 827D2 | Loki Solar
876 | 0 | SIDNEY | 242D2 | BAP POWER CORPORATION dba Cenergy
877 | 0 | NORTH AUGUSTA | 272D6 | SolAmerica Energy, LLC
878 | 0 | NORTH AUGUSTA | 272D6 | SolAmerica Energy, LLC
879 | 2 - PDRD | PUDDLEDOCK ROAD | 262D1 | Perennial Renewables LLC
880 | 1 - PROS | PROSPECT | 846D1 | Bridge Energy
881 | 0 | MECHANIC FALLS | 431D3 | Paddle Energy LLC
882 | 1 - MEFA | MECHANIC FALLS | 431D1 | Paddle Energy LLC
883 | 0 | PROSPECT | 846D1 | Paddle Energy LLC
884 | 0 | PROSPECT | 846D1 | Paddle Energy LLC
885 | 0 | LIMERICK | 632D1 | Dimension Renewable Energy
886 | 0 | RILEY | 449D2 | SolAmerica Energy, LLC
887 |  | ANDOVER | 400D1 | SolAmerica Energy, LLC
888 | 0 | BRIDGTON | 406D2 | SolAmerica Energy, LLC
889 | 0 | MANCHESTER | 233D1 | Invaleon Technologies Corp
890 | 1 - SKSS | SKOWHEGAN SOUTH SIDE | 854D2 | Invaleon Technologies Corp
891 | 0 | RIGBY | 650D4 | New Leaf Energy, Inc
892 | 0 | PLEASANT HILL | 644D1 | New Leaf Energy, Inc
893 | 0 | BRIGHTON AVE | 611D1 | New Leaf Energy, Inc
894 | 0 | SPRING STREET | 668D1 | New Leaf Energy, Inc
895 |  | NORWAY | 435D1 | New Leaf Energy, Inc
896 | 0 | PITTSFIELD | 842D1 | Loki Solar
897 | 0 | FREEPORT | 225D4 | New Leaf Energy, Inc
898 | 0 | MOSHERS | 635D2 | New Leaf Energy, Inc
899 | 0 | DEXTER | 813D3 | Novel Energy Solutions LLC
900 |  | THOMASTON CREEK | 246D3 | Nexamp, Inc
901 | 1 - CLIN | CLINTON | 810D1 | Nexamp, Inc
902 | 2 - NORW | NORWAY | 435D1 | Paddle Energy LLC
903 | 1 - BONE | BONNY EAGLE | 610D1 | Paddle Energy LLC
904 |  | RICHMOND | 240D1 | Nexamp, Inc
905 | 0 | HIRAM TAP | 692D1 | Nexamp, Inc
906 | 0 | CORINNA | 811D1 | Loki Solar
907 | 0 | ANSON | 801D1 | Nexamp, Inc
908 | 0 | BUCKSPORT | 806D2 | SolAmerica Energy, LLC
909 | 0 | CARMEL | 808D2 | SolAmerica Energy, LLC
910 |  | CARMEL | 808D3 | SolAmerica Energy, LLC
911 | 0 | CARMEL | 808D3 | Perennial Renewables LLC
912 |  | DOVER | 815D2 | SolAmerica Energy, LLC
913 |  | RUMFORD | 447D4 | Nexamp, Inc
914 | 0 | MONMOUTH | 457D2 | Nexamp, Inc
915 | 0 | WILTON | 885D1 | Loki Solar
916 |  | BALDWIN | 691D1 | SolAmerica Energy, LLC
917 | 0 | BUCKSPORT | 806D2 | SolAmerica Energy Development, LLC
918 | 0 | BUTLER'S CORNER | 612D1 | REVISION ENERGY INC
919 | 0 | SEARSPORT | 850D2 | Genie Solar Energy, LLC
920 | 0 | BIDDEFORD PUMP | 605D2 | Nexamp, Inc
921 | 0 | MAY STREET | 634D1 | Nexamp, Inc
922 | 0 | LEEDS | 471D2 | REVISION ENERGY INC
923 | 0 | ANSON | 801D1 | Nexamp, Inc
924 | 1 - DOVE | DOVER | 815D1 | EDPRNA DG Energy Development, LLC
925 | 0 | BRIDGTON | 406D2 | Novel Energy Solutions LLC
926 | 3 - NORW | NORWAY | 435D1 | Paddle Energy LLC
927 | 1 - SMRD | SHAWS MILL ROAD | 660D2 | UGE USA INC
928 | 0 | BRIDGTON | 406D2 | Paddle Energy LLC
929 | 0 | PLEASANT HILL | 644D1 | New Leaf Energy, Inc
930 | 0 | CAPE ELIZABETH | 613D1 | New Leaf Energy, Inc
931 | 0 | HINCKLEY POND | 690D1 | New Leaf Energy, Inc
932 | 0 | UNITY | 860D1 | SolAmerica Energy Development, LLC
933 | 0 | DOVER | 815D2 | UGE USA INC
934 | 2 - NOLI | NORTH LIMINGTON | 638D2 | Novel Energy Solutions LLC
935 | 0 | BRIDGTON | 406D2 | SolAmerica Energy Development, LLC
936 | 0 | CARMEL | 808D3 | SolAmerica Energy Development, LLC
937 | 0 | BASSETT | 602D2 | SolAmerica Energy Development, LLC
938 | 0 | FARMINGTON FALLS | 818D1 | SolAmerica Energy Development, LLC
939 | 0 | NORTH LIMINGTON | 638D1 | SolAmerica Energy Development, LLC
940 | 0 | BUCKSPORT | 806D2 | SolAmerica Energy Development, LLC
941 | 1 - RILE | RILEY | 449D2 | Perennial Renewables LLC
942 | 0 | LOVELL | 430D1 | SolAmerica Energy Development, LLC
943 | 0 | BASSETT | 602D2 | SolAmerica Energy Development, LLC
944 | 0 | LOVELL | 430D1 | SolAmerica Energy Development, LLC
945 | 1 -WILT | WILTON | 885D1 | Loki Solar
946 | 2 - CORI | CORINNA | 811D1 | Novel Energy Solutions LLC
947 | 3 - LULA | LUDDEN LANE | 461D1 | Solar Power New England
948 |  | DOVER | 815D2 | SolAmerica Energy Development, LLC
0 | 0 | 0 | 0 | 0
XXXXX | 0 | XXXXX | XXXXX | XXXXX
0 | 0 | 0 | 0 | 0
XXXXX | 0 | XXXXX | XXXXX | XXXXX
0 | 0 | 0 | 0 | #REF!
0 | 0 | 0 | 0 | 0

## Cluster Study 2025-2026 (hidden)
PRJ | Developer | Project Name | Type of Generation | Total Size (kW) | Battery Size (kW) | Fully Executed Interconnection Agreement | Estimated Commercial Operation Date | Executable Issue Date | Executable due date | Dev Executable received | Payment Received | Fully Executed Issued
587 | VC Renewables LLC | ELP LIVERMORE SOLAR LLC | Solar | 4998 |  | 2022-03-21 | Q3 2026 | 2025-11-07 | 2025-11-21
588 | New Hampshire Solar Garden | 259 SCHOOL STREET SOLAR LLC | Solar | 1999 |  | 2022-06-21 |  | 2025-11-07 | 2025-11-21
699 | Louth Callan Renewables | 119 Main Street Solar LLC | Solar | 1999 |  | 2024-05-28 | Q3 2026 | 2025-11-07 | 2025-11-21
702 | Ameresco, Inc | Penobscot Narrows Solar II LLC | Solar | 4980 |  | 2024-03-27 | Q2 2026 | 2025-11-07 | 2025-11-21
769 | RENEWABLE PROPERTIES LLC | RPME Solar 1, LLC | Solar | 1875 |  | 2024-01-30 | Q2 2026 | 2025-11-07 | 2025-11-21 | 2025-11-21 | 2025-11-24
770 | BNRG MAINE LLC | BD SOLAR CV LLC | Solar/Battery | 12400 | 12400 | 2024-12-03 | Q3 2026 | 2025-11-07 | 2025-11-21
800 | NUPOWER BATTERY STORAGE LLC | NUPOWER BATTERY STORAGE LLC | Battery | 9690 | 9690 | 2024-05-29 | Q1 2026 | 2025-11-07 | 2025-11-21
835 | VC Renewables LLC | ELP Livermore Solar II, LLC | Solar/Battery | 4999 | 4999 | 2025-03-25 |  | 2025-11-07 | 2025-11-21

## Cost Addendum Tracker (hidden)
PRJ | Original Cost Estimate | Updated Cost Estimate Date | Updated Cost Addendum Email Sent | Cost Addendum Meeting | Response for Revised IA | Move Forward with Revised IA | Revised Executable IA Date | Fully Executed Revised IA Issued | Adjusted 22% Overhead | Sent to Nate | Nate update email
13 | 2021-06-17 | 2022-06-08 | 2022-06-08 | 2022-06-21
15 | 2021-06-21 | 2022-06-07 | 2022-06-08 | 2022-06-21
54 | 2021-05-17 | 2022-06-20 | 2022-06-27 |  | No Response |  |  |  | No
55 | 2021-09-16 | 2022-09-01 | 2022-09-01 | N/A | No Response |  |  |  | Yes | Yes | Yes
59 | 2021-06-03 | 2022-09-27 | 2022-09-27 |  | No Response |  |  |  | Yes | Yes | Yes
74 | 2021-06-08 | 2022-09-27 | 2022-09-27 |  | No Response |  |  |  | Yes | Yes | Yes
76 | 2021-05-25 | 2022-07-07 | 2022-07-08 | 2022-07-19 | 2022-07-19 | Yes | 2022-07-19 | 2022-07-22 | No
86 | 2020-07-14 | 2022-09-12 | 2022-09-12 |  | No Response |  |  |  | Yes | Yes | Yes
90 | 2020-03-19 | 2022-09-12 | 2022-09-13 |  |  | Yes | 2022-06-03 | 2022-06-09 | Yes | Yes | Yes
92 | 2020-11-24 | 2022-08-10 | 2022-08-13 | [5 empty] | Yes
130 | 2020-10-23 | 2022-09-27 | 2022-09-27 |  | No Response |  |  |  | Yes | Yes | Yes
140 | 2021-05-20 | 2022-06-23 | 2022-06-28 |  | LVL 2 Leap frogged |  |  |  | N/A
149 | 2020-03-19 | 2022-09-12 | 2022-09-12 |  | No Response |  |  |  | Yes | Yes | Yes
151 |  | 2022-09-27 | 2022-09-27 |  | No Response |  |  |  | Yes | Yes | Yes
152 |  | 2022-08-02 | 2022-08-02 |  | 2022-08-17 |  |  |  | Yes
158 |  | 2022-08-02 | 2022-08-02 |  | No Response |  |  |  | No
160 | 2021-05-21 | 2022-06-28 | 2022-06-30 |  | No Response |  |  |  | No
170 | 2020-01-16 | 2022-06-20 | 2022-06-27 |  | LVL 2 Leap frogged |  |  |  | N/A
185 |  | 2022-09-12 | 2022-09-12 | N/A | 2022-05-25 | Yes | 2022-07-22 | 2022-07-22 | Yes | Yes | Yes
190 | 2021-05-20 | 2022-06-27 | 2022-06-28 |  | No Response |  |  |  | no
200
225 | 2021-06-03 | 2022-06-21 | 2022-06-28 | N/A | 2022-06-28 | Yes | 2022-06-28 | 2022-07-11 | No
240 | 2021-05-18 | 2022-06-30 | 2022-06-30 |  | No Response |  |  |  | No
243 |  | 2022-09-14 | 2022-09-14 | [5 empty] | Yes
249 |  | 2022-08-15 | 2022-08-30 | [5 empty] | Yes
253 | 2021-07-12 | 2022-07-07 | 2022-07-08 |  | No Response |  |  |  | No
255 |  | 2022-09-20 | 2022-09-22 |  | No Response |  |  |  | Yes |  | Yes
268 | 2022-06-07 | 2022-06-27 | 2022-06-29 |  | No Response
285
287 | 2021-06-03 | 2022-06-21 | 2022-06-28 |  | LVL 2 Leap frogged
306 | 2021-06-09 | 2022-07-01 | 2022-07-01 | 2022-07-18 | 2022-07-19 | Yes | 2022-07-19 | 2022-07-28 | no
308 | 2021-05-24 | 2022-07-05 | 2022-07-05 |  | No Response
310 |  | 2022-08-09 | 2022-08-13 | [5 empty] | Yes
312 | 2020-05-11 | 2022-07-26 | 2022-07-28 |  | No Response |  |  |  | Yes | no | yes
318 | 2021-07-28 | 2022-07-05 | 2022-07-05 | 2022-07-14 | 2022-07-14 | Yes | 2022-07-14 | 2022-08-31 | Yes
325 | 2021-08-23 | 2022-06-21 | 2022-06-28 |  | Mod request
350 |  | 2022-08-09 | 2022-08-15 | [5 empty] | Yes
351 |  | 2022-08-09 | 2022-08-15 | [5 empty] | Yes
352 |  | 2022-08-31 | 2022-09-01 | [5 empty] | Yes
355 | 2021-05-20 | 2022-07-05 | 2022-07-06 |  | LVL 2 Leap frogged
358 | 2022-07-16 | 2022-06-28 | 2022-06-29 |  | No Response
359 |  | 2022-08-22 | 2022-08-30 | [5 empty] | Yes
363 |  | 2022-04-25 | 2022-09-20 |  | No Response |  |  |  | Yes
368 | 2021-06-24 | 2022-07-06 | 2022-07-06 | N/A | 2022-07-06 | Yes | 2022-07-06 | 2022-07-11 | No
370 |  | 2022-09-08 | 2022-09-08 | [5 empty] | Yes
373 |  | 2022-09-14 | 2022-09-14 | [5 empty] | Yes
375
380 | 2021-05-31 | 2022-06-22 | 2022-06-28 |  | Assigned/No Response
381 | 2021-11-24 | 2022-09-20 | 2022-09-20 |  | 2022-05-01 | Yes | 2022-05-10 | 2022-06-03 | Yes | Yes | Yes
389 |  | 2022-08-10 | 2022-08-15 | [5 empty] | Yes
395
400
407 |  | 2022-08-15 | 2022-08-30 | [5 empty] | Yes
410 |  | 2022-09-02 | 2022-09-02 | [5 empty] | Yes
418 | 2020-08-07 | 2022-08-11 | 2022-08-16 | Yes | 2022-08-30 | Yes | 2022-08-30 |  | Yes
444 |  | 2022-07-15 | 2022-06-16 |  | Yes | Yes |  | 2022-07-27 | No
445 | 2021-05-19 | 2022-06-22 | 2022-06-28 |  | No Response
448 | 2021-07-01 | 2022-06-14 | 2022-06-16 | Yes | No Response
449 |  | 2022-08-30 | 2022-08-30 | 2022-08-30 | 2022-08-31 | Yes | 2022-08-31 |  | Yes
451 | 2021-06-10 | 2022-06-16 | 2022-06-17 |  | Yes |  |  | 2022-07-22
457 | 2021-06-03 | 2022-06-16 | 2022-06-17 | Yes | 2022-08-31 | Yes
460 |  | 2022-09-27 | 2022-09-27 |  | No Response |  |  |  | Yes | Yes | Yes
461 |  | 2022-08-02 | 2022-08-02 |  | No Response |  |  |  | No
464 |  | 2022-07-27 | 2022-07-28 | Yes | Not requested
467 |  | 2022-08-02 | 2022-08-16 | [5 empty] | Yes
470 |  | 2022-09-02 | 2022-09-09 | [5 empty] | Yes
471 |  | 2022-08-22 | 2022-08-31 | [5 empty] | Yes
472 |  | 2022-08-16 | 2022-08-30 | [5 empty] | Yes
477 |  | 2022-09-20 | 2022-09-20 |  | No Response |  |  |  | Yes | Yes | Yes
487 | 2021-05-03 | 2022-09-19 | 2022-09-20 | 2022-06-29 |  | Yes | 2022-07-27 | 2022-08-04 | Yes |  | Yes
488
491 |  | 2022-08-23 | 2022-08-31 | Yes |  |  |  |  | Yes
495
497 |  | 2022-07-27 | 2022-07-29 | N/A | 2022-08-02 | Yes | 2022-08-02 | 2022-08-09
499 |  | 2022-09-06 | 2022-09-07 | [5 empty] | Yes
504 | 2020-10-12 | 2022-08-10 | 2022-08-11 | N/A | 2022-08-15 | Yes | 2022-08-16 | 2022-08-23 | Yes
509 |  | 2022-08-10 | 2022-08-11 | [5 empty] | Yes
511 |  | 2022-08-25 | 2022-08-31 | Yes |  |  |  |  | Yes
515 |  | 2022-08-10 | 2022-08-11 |  | Responded ? Regarding O/M | No |  |  | No
516
519 | 2021-06-09 | 2022-06-22 | 2022-07-05 | N/A | 2022-07-12 | Yes | 2022-07-12 | 2022-07-27 | No
524 |  | 2022-09-20 | 2022-09-21 |  | No Response |  |  |  | Yes
526 | 2021-05-10 | 2022-07-06 | 2022-07-06 | N/A | 2022-07-07 | Yes |  |  | Yes |  | Yes
528
531 |  | 2022-08-10 | 2022-08-12 | [5 empty] | Yes
534 | 2021-10-25 | 2022-07-06 | 2022-07-06 | 2022-07-13 | TBD | TBD
536
540 |  | 2022-08-02 | 2022-08-02 | 2022-08-16 | 2022-08-16 | Yes | 2022-08-17 | 2022-08-24 | Yes
551
552
554 |  | 2022-09-07 | 2022-09-07 | [5 empty] | Yes
557 |  | 2022-08-25 | 2022-08-31 | [5 empty] | Yes
558 | 2021-06-07 | 2022-06-22 | 2022-06-28 | N/A | 2022-06-30 | Yes
560 | 2021-06-29 | 2022-07-28 | 2022-07-29 |  | No Response | [5 empty] | yes
561 |  | 2022-08-12 | 2022-08-16 | [5 empty] | Yes
562 | 2021-09-22 | 2022-06-23 | 2022-06-28 |  | 2022-08-16 | Yes
565 |  | 2022-07-28 | 2022-07-29 | N/A | 2022-07-29 | Yes | 2022-07-29
568 | 2021-09-28 | 2022-06-17 | 2022-06-24 |  |  | Yes | 2022-07-14 | 2022-08-08 | No
574
579
586 | 2021-09-19 | 2022-07-29 | 2022-07-29 | N/A | 2022-08-15 | Yes
591
594 |  | 2022-09-02 | 2022-09-06 | [5 empty] | Yes
596 |  | 2022-08-31 | 2022-09-01 | [5 empty] | Yes
600 |  | 2022-09-09 | 2022-09-09 | [5 empty] | Yes | Yes | Yes
605
606 |  | 2022-09-16 | 2022-09-19 | [5 empty] | Yes
607 |  | 2022-09-16 | 2022-09-19 | [5 empty] | Yes
608 |  | 2022-08-26 | 2022-08-31 | [5 empty] | Yes
613 | 2021-05-28 | 2022-06-17 | 2022-06-17 |  | 2022-07-12 | Yes | 2022-07-12
614
617 |  | 2022-08-26 | 2022-08-31 | [5 empty] | Yes
621 |  | 2022-08-02 | 2022-08-02 |  | No Response |  |  |  | No
622 |  | 2022-09-20 | 2022-09-20 |  | No Response |  |  |  | Yes | Yes | Yes
627 |  | 2022-08-12 | 2022-08-16 | [5 empty] | Yes
630 |  | 2022-08-29 | 2022-08-31 | [5 empty] | Yes
631 |  | 2022-09-06 | 2022-09-06 | [5 empty] | Yes
632 |  | 2022-08-17 | 2022-08-30 | [5 empty] | Yes
633
637 |  | 2022-08-17 | 2022-08-17 | [5 empty] | Yes
640 |  | 2022-09-08 | 2022-09-08 | [5 empty] | Yes
641 |  | 2022-09-20 | 2022-09-21 | [5 empty] | Yes |  | Yes
642 |  | 2022-08-29 | 2022-08-31 | [5 empty] | Yes
648 |  | 2022-09-01 | 2022-09-02 |  | 2022-06-30 | Yes | 2022-08-30 | 2022-07-06 | Yes | Yes | Yes
649 |  | 2022-09-08 | 2022-09-08 | [5 empty] | Yes
660 |  | 2022-09-15 | 2022-09-15 | [5 empty] | Yes
662 |  |  | 2022-05-11 |  |  |  | 2022-05-11 | 2022-06-03 | Facilities Study based IA | Yes
671 |  | 2022-09-16 | 2022-09-19 | [5 empty] | Yes
673 |  | 2022-09-07 | 2022-09-07 | [5 empty] | Yes
674 |  | 2022-09-15 | 2022-09-19 | [5 empty] | Yes
684
692 | 2022-03-01 | 2022-04-21 | 2022-04-28 |  | Proceeded w/FAC Study |  |  |  | N/A
693 | 2022-06-01 | 2022-09-13 | 2022-09-14 | [5 empty] | Yes
241/242 |  | 2022-08-12 | 2022-08-30 | [5 empty] | Yes