## Level 2 Online Report
Project # | App Received | Customer Notified Application Complete | Facility Type | AC kW | Circuit | Substation | Substation Transformer | Tech Screen Completed | Tech Screen Results | ESA Results | ESA Completed | Withdrawn
109833 | 2025-12-29 |  | Solar | 999
109822 | 2025-12-26 |  | Solar | 750
109808 | 2025-12-23 |  | Solar | 999
109788 | 2025-12-19 |  | Solar | 450
109782 | 2025-12-18 | 2025-12-31 | Solar | 152.16 | 225D3 | FREEPORT | 225T2
109728 | 2025-12-12 | 2025-12-17 | Solar | 220 | 674D2 | WESTBROOK | 674T1 |  |  | Pending
109730 | 2025-12-12 |  | Solar | 300 | 674D1 | WESTBROOK | 674T1 |  | Pending
109731 | 2025-12-12 | 2025-12-17 | Solar | 240 | 674D1 | WESTBROOK | 674T1 |  | Pending
109689 | 2025-12-10 | 2025-12-30 | Solar | 999 | 837D2 | NEWPORT | 837T2 |  | Pending
109670 | 2025-12-09 |  | Solar | 750 | 842D1 | PITTSFIELD | 842T1
109671 | 2025-12-09 |  | Solar | 249 | 842D1 | PITTSFIELD | 842T1
109651 | 2025-12-07 | 2025-12-10 | Solar | 999 | 824D1 | HARTLAND | 824T1 |  | Pending
109649 | 2025-12-05 | 2025-12-09 | Solar | 152.16 | 232D2 | LISBON FALLS | 232T2 | 2025-12-29 | Fail
109624 | 2025-12-02 | 2025-12-05 | Solar | 975 | 624D2 | FORT HILL | 624T1 |  | Pending
109626 | 2025-12-02 | 2025-12-09 | Solar | 999 | 272D6 | NORTH AUGUSTA | 272T2 | 2025-12-30 | Fail
109500 | 2025-11-20 | 2025-11-25 | Solar | 600 | 219D1 | DAMARISCOTTA MILLS | 219T1 | 2025-12-11 | Fail | Pending
109467 | 2025-11-18 | 2025-11-19 | Solar | 995 | 691D1 | BALDWIN | 691T1 | 2025-12-03 | Fail | Pass | 2025-12-31
109422 | 2025-11-13 | 2025-11-18 | Solar | 100 | 650D1 | RIGBY | 650T1 | 2025-12-09 | Fail | Pending
109427 | 2025-11-13 | 2025-11-18 | Solar | 200 | 239D7 | PARK STREET | 239T2 | 2025-12-03 | Fail | Pending
109429 | 2025-11-13 | 2025-12-03 | Solar | 400 | 420D4 | HOTEL ROAD | 420T1 | 2025-12-26 | Fail
109286 | 2025-11-05 | 2025-11-10 | Solar | 160 | 214D2 | CAMDEN | 214T2 | 2025-12-01 | Fail | Pending
109255 | 2025-11-03 | 2025-11-13 | Solar | 167 | 692D1 | HIRAM TAP | 692T1 | 2025-12-05 | Fail | Pending
109257 | 2025-11-03 | 2025-11-13 | Solar | 167 | 692D1 | HIRAM TAP | 692T1 | 2025-12-05 | Fail | Pending
109155 | 2025-10-27 | 2025-11-04 | Solar | 250 | 620D1 | ELM STREET | 620T2 | 2025-11-24 | Fail | Pending
109160 | 2025-10-27 | 2025-10-30 | Solar | 995 | 824D2 | HARTLAND | 824T1 | 2025-11-05 | Fail | Fail | 2025-12-18 | Yes
109086 | 2025-10-22 | 2025-10-23 | Solar | 167 | 885D1 | WILTON | 885T1 | 2025-11-11 | Fail | Pending
109107 | 2025-10-22 | 2025-10-24 | Solar | 167 | 240D1 | RICHMOND | 240T1 | 2025-11-05 | Fail | Pass | 2025-12-23
109110 | 2025-10-22 | 2025-10-24 | Solar | 167 | 240D1 | RICHMOND | 240T1 | 2025-11-05 | Fail | Pass | 2025-12-23
108994 | 2025-10-15 | 2025-10-17 | Solar | 167 | 803D6 | BELFAST WEST SIDE | 34.5 kV Bus | 2025-11-04 | Fail | Fail | 2025-12-23 | Yes
108995 | 2025-10-15 | 2025-10-17 | Solar | 167 | 803D6 | BELFAST WEST SIDE | 34.5 kV Bus | 2025-11-04 | Fail | Fail | 2025-12-23 | Yes
108963 | 2025-10-14 | 2025-10-22 | Solar | 975 | 807D1 | BURNHAM | 807T1 | 2025-11-05 | Fail | Fail | 2025-12-23 | Yes
108978 | 2025-10-14 | 2025-10-15 | Solar | 975 | 808D3 | CARMEL TAP | 808T1 | 2025-11-05 | Fail | Fail | 2025-12-15 | Yes
108982 | 2025-10-14 | 2025-10-22 | Solar | 975 | 457D2 | MONMOUTH | 457T2 | 2025-11-05 | Fail | Fail | 2025-12-17 | Yes
108984 | 2025-10-14 | 2025-10-22 | Solar | 975 | 252D2 | WALDOBORO | 252T1 | 2025-11-04 | Fail | Pass | 2025-12-22
108908 | 2025-10-13 | 2025-10-20 | Solar | 167 | 435D3 | NORWAY | 435T2 | 2025-11-10 | Fail | Pass | 2025-12-29
108947 | 2025-10-13 | 2025-10-15 | Solar | 996 | 813D3 | DEXTER | 813T2 | 2025-11-05 | Fail | Pending
108898 | 2025-10-10 | 2025-10-13 | Solar | 167 | 244D2 | SOUTH CHINA | 244T1 | 2025-11-04 | Fail | Pass | 2025-12-18
108900 | 2025-10-10 | 2025-10-13 | Solar | 167 | 244D2 | SOUTH CHINA | 244T1 | 2025-11-04 | Fail | Fail | 2025-12-18 | Yes
108903 | 2025-10-10 | 2025-10-14 | Solar | 167 | 803D6 | BELFAST WEST SIDE | 34.5 kV Bus | 2025-11-04 | Fail | Fail | 2025-12-16 | Yes
108904 | 2025-10-10 | 2025-10-14 | Solar | 167 | 803D6 | BELFAST WEST SIDE | 34.5 kV Bus | 2025-11-04 | Fail | Fail | 2025-12-16 | Yes
108907 | 2025-10-10 | 2025-10-14 | Solar | 167 | 435D3 | NORWAY | 435T2 | 2025-11-04 | Fail | Pass | 2025-12-23
108910 | 2025-10-10 | 2025-10-22 | Solar | 999 | 687D1 | ELIOT | 687T1 | 2025-11-13 | Fail | Pending
108892 | 2025-10-09 | 2025-10-15 | Solar | 975 | 262D1 | PUDDLEDOCK ROAD | 34 kV BUS 1 | 2025-11-05 | Fail | Pass | 2025-12-24
108857 | 2025-10-07 | 2025-10-08 | Solar | 975 | 219D2 | DAMARISCOTTA MILLS | 219T1 | 2025-10-30 | Fail | Pass | 2025-12-16
108804 | 2025-10-06 | 2025-10-09 | Solar | 999 | 824D2 | HARTLAND | 824T1 | 2025-10-31 | Fail | Fail | 2025-12-17
108789 | 2025-10-03 | 2025-10-07 | Solar | 175 | 435D3 | NORWAY | 435T2 | 2025-10-29 | Fail
108790 | 2025-10-03 | 2025-10-08 | Solar | 999 | 208D2 | BOND BROOK | 208T1 | 2025-10-30 | Fail | Pass | 2025-12-30
108792 | 2025-10-03 | 2025-10-09 | Solar | 999 | 873D1 | COUNTY RD (RICE RIPS) | 873T1 | 2025-10-31 | Fail | Pass | 2025-12-17
108794 | 2025-10-03 | 2025-10-09 | Solar | 999 | 252D1 | WALDOBORO | 252T1 | 2025-10-31 | Fail | Fail | 2025-12-24 | Yes
108795 | 2025-10-03 | 2025-10-08 | Solar | 999 | 818D1 | FARMINGTON FALLS | 818T1 | 2025-10-30 | Fail | Fail | 2025-12-17
108719 | 2025-09-29 | 2025-10-03 | Solar | 975 | 438D1 | PAPOOSE POND | Tap off of Transmission Line | 2025-10-27 | Fail | Pass | 2025-12-16
108721 | 2025-09-29 | 2025-10-01 | Solar | 975 | 824D1 | HARTLAND | 824T1 | 2025-10-20 | Fail | Fail | 2025-12-02
108723 | 2025-09-29 | 2025-10-01 | Solar | 975 | 824D2 | HARTLAND | 824T1 | 2025-10-20 | Fail | Fail | 2025-12-02
108725 | 2025-09-29 | 2025-10-01 | Solar | 999 | 818D1 | FARMINGTON FALLS | 818T1 | 2025-10-23 | Fail |  |  | Yes
108726 | 2025-09-29 | 2025-10-03 | Solar | 999 | 210D1 | BRISTOL | 210T1 | 2025-10-27 | Fail | Pass | 2025-12-17
108691 | 2025-09-26 | 2025-09-30 | Solar | 375 | 810D1 | CLINTON | 810T1 | 2025-10-20 | Fail |  |  | Yes
108639 | 2025-09-25 | 2025-09-29 | Solar | 995 | 815D2 | DOVER | 815T2 | 2025-10-21 | Fail | Fail | 2025-12-12 | Yes
108641 | 2025-09-25 | 2025-09-29 | Solar | 375 | 210D2 | BRISTOL | 210T1 | 2025-10-20 | Fail |  |  | Yes
108651 | 2025-09-25 | 2025-09-30 | Solar | 975 | 624D1 | FORT HILL | 624T1 | 2025-10-20 | Fail | Pass | 2025-12-09
108655 | 2025-09-25 | 2025-09-29 | Solar | 500 | 632D2 | LIMERICK | 632T1 | 2025-10-21 | Fail | Fail | 2025-12-17 | Yes
108610 | 2025-09-23 | 2025-09-29 | Solar | 975 | 428D2 | LIVERMORE FALLS | 428T1 | 2025-10-21 | Fail | Fail | 2025-12-08
108582 | 2025-09-22 | 2025-10-03 | Solar | 167 | 244D2 | SOUTH CHINA | 244T1 | 2025-10-20 | Fail | Pass | 2025-12-08
108583 | 2025-09-22 | 2025-10-03 | Solar | 167 | 244D2 | SOUTH CHINA | 244T1 | 2025-10-20 | Fail | Fail | 2025-12-08 | Yes
108584 | 2025-09-22 | 2025-10-03 | Solar | 167 | 244D2 | SOUTH CHINA | 244T1 | 2025-10-20 | Fail |  |  | Yes
108587 | 2025-09-22 | 2025-09-25 | Solar | 995 | 671D1 | WATERBORO | 671T1 | 2025-10-17 | Fail | Fail | 2025-12-08
108600 | 2025-09-22 | 2025-09-29 | Solar | 975 | 866D2 | WESTON | 866T2 | 2025-10-20 | Fail | Pass | 2025-12-02
108564 | 2025-09-18 | 2025-09-25 | Solar | 152.16 | 225D3 | FREEPORT | 225T2 | 2025-10-21 | Fail |  |  | Yes
108422 | 2025-09-09 | 2025-09-19 | Solar | 220 | 412D1 | DEER RIPS | 412T2 | 2025-10-01 | Fail | Pass | 2025-12-16 | No
108396 | 2025-09-08 | 2025-09-11 | Solar | 975 | 837D2 | NEWPORT | 837T2 | 2025-10-01 | Fail | Pass | 2025-11-13
108355 | 2025-09-05 | 2025-09-10 | Solar | 999 | 885D1 | WILTON | 885T1 | 2025-09-23 | Fail | Pass | 2025-10-15
108345 | 2025-09-04 | 2025-09-08 | Solar | 995 | 457D3 | MONMOUTH | 457T2 | 2025-09-16 | Fail | Pass | 2025-10-09
108348 | 2025-09-04 | 2025-09-11 | Solar | 150 | 250D1 | TOPSHAM | 250T2 | 2025-10-01 | Fail | Pass | 2025-12-11 | No
108318 | 2025-09-03 |  | Solar | 167 | 810D1 | CLINTON | 810T1 | 2025-10-28 | Fail | Pending
108297 | 2025-09-02 | 2025-10-03 | Solar | 167 | 400D1 | ANDOVER | 400T1 | 2025-10-27 | Fail | Pass | 2025-12-16
108305 | 2025-09-02 | 2025-10-03 | Solar | 167 | 400D1 | ANDOVER | 400T1 | 2025-10-27 | Fail | Pass | 2025-12-16
108240 | 2025-08-28 | 2025-09-08 | Solar | 995 | 827D2 | ATHENS | 827T1 | 2025-09-16 | Fail | Fail | 2025-10-29 | Yes
108275 | 2025-08-28 | 2025-09-10 | Solar | 996 | 461D1 | LUDDEN LANE | 461T1 | 2025-09-23 | Fail | Pending
108223 | 2025-08-27 | 2025-09-26 | Solar | 167 | 250D2 | TOPSHAM | 250T2 | 2025-10-20 | Fail | Fail | 2025-12-16 | No
108150 | 2025-08-21 | 2025-09-05 | Solar | 995.004 | 813D3 | DEXTER | 813T2 | 2025-09-19 | Fail | Pass | 2025-11-26
108039 | 2025-08-15 | 2025-09-05 | Solar | 996 | 419D1 | HIRAM HYDRO | 419T3 | 2025-09-22 | Fail
107972 | 2025-08-11 | 2025-08-29 | Solar | 150 | 438D1 | PAPOOSE POND | Tap off of Transmission Line | 2025-09-22 | Fail | Pass | 2025-10-30
107976 | 2025-08-11 | 2025-09-04 | Solar | 150 | 438D1 | PAPOOSE POND | Tap off of Transmission Line | 2025-09-23 | Fail | Pass | 2025-11-13
107945 | 2025-08-08 | 2025-09-09 | Solar | 975 | 617D2 | DUNSTAN | 617T1 | 2025-09-24 | Fail | Pass | 2025-11-18
107656 | 2025-07-25 | 2025-08-14 | Solar | 999 | 626D5 | HIGH STREET | 626T2 | 2025-09-03 | Fail | Pass | 2025-10-22
107549 | 2025-07-20 | 2025-07-25 | Solar | 995 | 691D1 | BALDWIN | 691T1 | 2025-08-15 | Fail | Fail | 2025-10-03 | Yes
107430 | 2025-07-15 | 2025-07-23 | Solar | 150 | 437D2 | OXFORD | 437T1 | 2025-08-12 | Fail | Fail | 2025-09-26 | Yes
107434 | 2025-07-15 | 2025-07-22 | Solar | 150 | 435D3 | NORWAY | 435T2 | 2025-08-12 | Fail | Pass | 2025-09-04
107347 | 2025-07-10 | 2025-07-16 | Solar | 975 | 262D1 | PUDDLEDOCK ROAD | 34 kV BUS 1 | 2025-07-30 | Fail | Pass | 2025-09-02
107361 | 2025-07-10 | 2025-08-06 | Solar | 998.9 | 256D1 | WINTHROP | 256T2 | 2025-08-25 | Fail | Fail | 2025-10-22 | Yes
107304 | 2025-07-08 | 2025-07-15 | Solar | 233 | 225D4 | FREEPORT | 225T1 | 2025-07-23 | Fail | Pass | 2025-11-12
107262 | 2025-07-04 | 2025-08-28 | Solar | 999 | 272D6 | NORTH AUGUSTA | 272T2 | 2025-09-18 | Fail | Fail | 2025-11-17
107163 | 2025-06-26 | 2025-07-01 | Solar | 300 | 424D2 | LEWISTON LOWER | 424T1 | 2025-07-23 | Pass
107146 | 2025-06-24 | 2025-07-17 | Solar | 900 | 461D1 | LUDDEN LANE | 461T1 | 2025-08-05 | Fail |  |  | Yes
107059 | 2025-06-18 | 2025-06-19 | Solar | 150 | 855D1 | SOUTH WATERVILLE | 855T1 | 2025-07-01 | Fail | Fail | 2025-09-12 | Yes
107068 | 2025-06-18 | 2025-06-30 | Solar | 150 | 400D1 | ANDOVER | 400T1 | 2025-07-21 | Fail | Fail | 2025-08-28 | Yes
107032 | 2025-06-17 | 2025-08-26 | Solar | 125.4 | 421D2 | CHALLENGER | 421T1 | 2025-09-16 | Fail | Pass
106959 | 2025-06-11 | 2025-06-17 | Solar | 150 | 400D1 | ANDOVER | 400T1 | 2025-06-25 | Fail | Fail | 2025-08-06 | Yes
106867 | 2025-06-04 | 2025-06-09 | Solar | 999 | 885D1 | WILTON | 885T1 | 2025-06-20 | Fail | Fail | 2025-07-14 | Yes
106789 | 2025-05-29 | 2025-06-03 | Solar | 999 | 632D2 | LIMERICK | 632T1 | 2025-06-24 | Fail | Fail | 2025-08-28 | Yes
106772 | 2025-05-27 | 2025-06-05 | Solar | 996 | 272D2 | NORTH AUGUSTA | 272T1 | 2025-06-20 | Fail | Pass | 2025-08-07
106698 | 2025-05-22 | 2025-05-30 | Solar | 975 | 435D3 | NORWAY | 435T2 | 2025-06-09 | Fail | Pass | 2025-07-11
106654 | 2025-05-20 | 2025-06-03 | Solar | 999 | 415D2 | FRYEBURG | 415T1 | 2025-06-09 | Fail | Pass | 2025-07-25
106484 | 2025-05-07 | 2025-05-21 | Solar | 975 | 857D1 | THORNDIKE TAP | 857T1 | 2025-06-04 | Fail | Pass | 2025-08-05
106392 | 2025-04-30 | 2025-05-09 | Solar | 300 | 800D1 | LINCOLNVILLE | 800T1 | 2025-06-02 | Fail | Pass | 2025-08-27
106395 | 2025-04-30 | 2025-05-09 | Solar | 840 | 817D3 | FAIRFIELD | 817T1 | 2025-05-28 | Fail |  |  | Yes
106396 | 2025-04-30 | 2025-05-09 | Solar | 440 | 416D3 | GRAY | 416T1 | 2025-06-02 | Fail | Pass | 2025-08-26
106397 | 2025-04-30 | 2025-05-09 | Solar | 320 | 431D3 | MECHANIC FALLS | 431T2 | 2025-06-02 | Pass
106391 | 2025-04-29 | 2025-05-09 | Solar | 360 | 803D6 | BELFAST WEST SIDE | 34.5 kV Bus | 2025-06-02 | Fail | Pass | 2025-08-26
106272 | 2025-04-22 | 2025-05-01 | Solar | 152 | 423D2 | KIMBALL ROAD | 423T2 | 2025-05-20 | Fail | Pending |  | Yes
106220 | 2025-04-18 | 2025-04-24 | Solar | 440 | 246D3 | THOMASTON CREEK | 246T1 | 2025-05-13 | Fail | Fail | 2025-08-26 | Yes
106226 | 2025-04-18 | 2025-04-24 | Solar | 160 | 803D6 | BELFAST WEST SIDE | 34.5 kV Bus | 2025-05-13 | Fail | Pass | 2025-08-14
106231 | 2025-04-18 | 2025-04-24 | Solar | 320 | 678D2 | BAR MILLS | 678T4 | 2025-05-14 | Fail | Pending |  | Yes
106234 | 2025-04-18 | 2025-04-24 | Solar | 160 | 873D1 | COUNTY RD (RICE RIPS) | 873T1 | 2025-05-13 | Fail |  |  | Yes
106242 | 2025-04-18 | 2025-04-23 | Solar | 995 | 692D1 | HIRAM TAP | 692T1 | 2025-05-06 | Fail | Pass | 2025-07-07
106244 | 2025-04-18 | 2025-04-24 | Solar | 995 | 857D1 | THORNDIKE TAP | 857T1 | 2025-05-13 | Fail | Pass | 2025-07-07
106179 | 2025-04-16 | 2025-04-21 | Solar | 152 | 409D1 | PARIS TAP | 409T1 | 2025-05-05 | Fail | Pass | 2025-06-27
106128 | 2025-04-14 | 2025-04-17 | Solar | 875 | 428D3 | LIVERMORE FALLS | 428T1 | 2025-05-05 | Fail | Fail | 2025-07-02 | Yes
106048 | 2025-04-08 | 2025-04-15 | Solar | 153.6 | 208D2 | BOND BROOK | 208T1 | 2025-04-21 | Fail | Pass | 2025-06-04
105982 | 2025-04-03 | 2025-05-02 | Solar | 999 | 610D2 | BONNY EAGLE | 610T4 | 2025-05-16 | Fail | Pass | 2025-07-02
105997 | 2025-04-03 | 2025-04-17 | Solar | 136.8 | 219D2 | DAMARISCOTTA MILLS | 219T1 | 2025-05-05 | Fail | Pass | 2025-06-26
105865 | 2025-03-26 | 2025-03-31 | Solar | 999 | 885D1 | WILTON | 885T1 | 2025-04-04 | Fail | Fail | 2025-05-13 | Yes
105830 | 2025-03-24 | 2025-03-27 | Solar | 999 | 449D2 | RILEY | 449T1 | 2025-03-28 | Fail | Pass | 2025-06-20
105827 | 2025-03-21 | 2025-03-28 | Solar | 150 | 435D4 | NORWAY | 435T2 | 2025-04-04 | Fail | Pass | 2025-05-13
105796 | 2025-03-19 | 2025-03-27 | Solar | 999 | 238D1 | MESSINA | 238T1 | 2025-03-28 | Fail |  |  | Yes
105773 | 2025-03-17 | 2025-03-19 | Solar | 999 | 860D1 | UNITY | 860T1 | 2025-03-25 | Fail |  |  | Yes
105711 | 2025-03-12 | 2025-03-19 | Solar | 999 | 853D1 | SKOWHEGAN NORTH SIDE | 853T1 | 2025-03-25 | Fail |  |  | Yes
105681 | 2025-03-11 | 2025-03-19 | Solar | 999 | 467D1 | TURNER TAP | Tap off of Transmission Line | 2025-03-25 | Fail | Pass | 2025-04-23
105660 | 2025-03-07 | 2025-03-17 | Solar | 995 | 806D1 | BUCKSPORT | 806T5 | 2025-03-18 | Fail | Pass | 2025-04-04
105641 | 2025-03-06 | 2025-03-17 | Solar | 995 | 837D2 | NEWPORT | 837T2 | 2025-03-18 | Fail | Pass | 2025-04-03
105649 | 2025-03-06 |  | Solar | 990 | [7 empty] | Yes
105547 | 2025-02-25 | 2025-03-11 | Solar | 999 | 815D2 | DOVER | 815T2 |  | Fail |  |  | Yes
105548 | 2025-02-25 | 2025-03-12 | Solar | 999 | 638D1 | NORTH LIMINGTON | 638T1 | 2025-03-12 | Fail |  |  | Yes
105549 | 2025-02-25 | 2025-03-12 | Solar | 999 | 602D2 | BASSETT | 602T1 | 2025-03-12 | Fail |  |  | Yes
105550 | 2025-02-25 | 2025-03-11 | Solar | 999 | 602D2 | BASSETT | 602T1 | 2025-03-11 | Fail |  |  | Yes
105551 | 2025-02-25 | 2025-03-11 | Solar | 999 | 818D1 | FARMINGTON FALLS | 818T1 | 2025-03-11 | Fail |  |  | Yes
105521 | 2025-02-21 | 2025-03-07 | Solar | 999 | 842D1 | PITTSFIELD | 842T1 | 2025-03-11 | Fail | Pass | 2025-04-24
105523 | 2025-02-21 | 2025-03-07 | Solar | 999 | 885D1 | WILTON | 885T1 | 2025-03-11 | Fail | Fail | 2025-05-28 | Yes
105500 | 2025-02-19 | 2025-02-24 | Solar | 975 | 431D1 | MECHANIC FALLS | 431T2 | 2025-02-28 | Fail | Pass | 2025-04-18 | Yes
105454 | 2025-02-14 | 2025-02-18 | Solar | 969.4 | 813D1 | DEXTER | 813T1 | 2025-02-21 | Fail | Fail | 2025-03-20 | Yes
105424 | 2025-02-13 | 2025-02-17 | Solar | 200 | 810D1 | CLINTON | 810T1 | 2025-02-21 | Fail | Fail | 2025-03-13 | Yes
105405 | 2025-02-11 | 2025-02-12 | Solar | 995 | 431D1 | MECHANIC FALLS | 431T2 | 2025-02-14 | Fail | Pass | 2025-04-16
105215 | 2025-01-24 | 2025-01-28 | Solar | 152 | 423D2 | KIMBALL ROAD | 423T2 | 2025-01-31 | Fail | Fail | 2025-02-27 | Yes
105216 | 2025-01-24 | 2025-02-04 | Solar | 999 | 860D1 | UNITY | 860T1 | 2025-02-06 | Fail |  |  | Yes
105198 | 2025-01-23 | 2025-02-11 | Solar | 999 | 808D3 | CARMEL TAP | 808T1 | 2025-02-18 | Fail |  |  | Yes
105204 | 2025-01-23 | 2025-01-27 | Solar | 996 | 813D1 | DEXTER | 813T1 | 2025-01-31 | Fail | Fail | 2025-02-20 | Yes
105158 | 2025-01-16 | 2025-01-20 | Solar | 995 | 850D1 | SEARSPORT | 850T1 | 2025-01-24 | Fail | Pass | 2025-02-14
105134 | 2025-01-15 | 2025-01-23 | Solar | 200 | 675D2 | WESTERN AVENUE | 675T1 | 2025-01-24 | Pass |  |  | Yes
105120 | 2025-01-14 | 2025-01-20 | Solar | 141.84 | 253D1 | WARREN | 253T1 | 2025-01-24 | Fail | Fail | 2025-03-17 | Yes
105126 | 2025-01-14 | 2025-02-03 | Solar | 975 | 272D4 | NORTH AUGUSTA | 272T1 | 2025-02-06 | Fail | Pass | 2025-03-20
105055 | 2025-01-08 | 2025-01-27 | Solar | 975 | 873D1 | COUNTY RD (RICE RIPS) | 873T1 | 2025-02-03 | Fail |  |  | Yes
104989 | 2025-01-02 | 2025-01-03 | Solar | 152 | 409D1 | PARIS TAP | 409T1 | 2025-01-03 | Fail | Fail | 2025-01-24 | Yes
104942 | 2024-12-20 |  | Solar | 152 | [7 empty] | Yes
104944 | 2024-12-20 | 2024-12-23 | Solar | 152 | 423D2 | KIMBALL ROAD | 423T2 | 2024-12-30 | Fail | Pass | 2025-01-22
104916 | 2024-12-18 | 2024-12-31 | Solar | 220 | 239D7 | PARK STREET | 239T2 | 2025-01-03 | Fail | Pass | 2025-01-30
104902 | 2024-12-17 | 2024-12-31 | Solar | 200 | 246D3 | THOMASTON CREEK | 246T1 | 2025-01-03 | Fail | Pass | 2025-02-11
104903 | 2024-12-17 | 2024-12-24 | Solar | 240 | 239D6 | PARK STREET | 239T2 | 2025-01-03 | Fail | Pass | 2025-02-19 | Yes
104904 | 2024-12-17 | 2024-12-31 | Solar | 100 | 239D5 | PARK STREET | 239T4 | 2025-01-03 | Fail | Pass | 2025-01-29
104822 | 2024-12-10 | 2024-12-12 | Solar | 995 | 467D1 | TURNER TAP | Tap off of Transmission Line | 2024-12-18 | Fail | Pass | 2025-01-14
104658 | 2024-11-22 | 2024-12-13 | Solar | 680 | 674D1 | WESTBROOK | 674T1 | 2024-12-16 | Fail | Fail | 2025-02-06
104659 | 2024-11-22 | 2024-12-13 | Solar | 400 | 674D1 | WESTBROOK | 674T1 | 2024-12-16 | Fail | Pass | 2025-05-29
104661 | 2024-11-22 | 2024-12-17 | Solar | 600 | 232D2 | LISBON FALLS | 232T2 | 2024-12-18 | Fail | Pass | 2025-01-06
104636 | 2024-11-21 | 2024-12-13 | Solar | 150 | 647D2 | PRIDES CORNER | 647T2 | 2024-12-16 | Pass
104638 | 2024-11-21 | 2024-12-13 | Solar | 240 | 674D2 | WESTBROOK | 674T1 | 2024-12-16 | Fail | Pass | 2025-02-06
104609 | 2024-11-20 | 2024-11-25 | Solar | 995 | 813D1 | DEXTER | 813T1 | 2024-11-26 | Fail |  |  | Yes
104613 | 2024-11-20 | 2024-11-25 | Solar | 999 | 431D1 | MECHANIC FALLS | 431T2 | 2024-11-26 | Fail | Fail | 2025-01-02 | Yes
104553 | 2024-11-15 | 2024-12-03 | Solar | 990 | 603D2 | BERWICK | 603T1 | 2024-12-03 | Fail | Pass | 2025-04-08
104517 | 2024-11-13 | 2024-11-21 | Solar | 999 | 428D2 | LIVERMORE FALLS | 428T1 | 2024-11-21 | Fail | Pass | 2024-12-09
104498 | 2024-11-12 |  | Solar | 265.05 | [7 empty] | Yes
104424 | 2024-11-05 | 2024-11-13 | Solar | 995 | 885D1 | WILTON | 885T1 | 2024-11-13 | Fail | Pass | 2025-01-23
104271 | 2024-10-23 | 2024-10-24 | Solar | 984.85 | 874D1 | BELFAST 115 | 874T2 | 2024-10-25 | Fail | Pass | 2024-11-12
104273 | 2024-10-23 | 2024-10-24 | Solar | 995 | 858D3 | STURTEVANT | 858T2 | 2024-10-25 | Fail | Pass | 2024-11-12
104262 | 2024-10-22 | 2024-11-05 | Solar | 999 | 850D2 | SEARSPORT | 850T1 | 2024-11-06 | Fail |  |  | Yes
104264 | 2024-10-22 | 2024-11-26 | Solar | 999 | 815D2 | DOVER | 815T2 | 2024-11-26 | Fail |  |  | Yes
104167 | 2024-10-15 | 2024-10-21 | Solar | 990 | 208D1 | BOND BROOK | 208T1 | 2024-10-22 | Fail | Pass | 2024-11-04
103912 | 2024-09-25 | 2024-09-25 | Solar | 153.6 | 219D2 | DAMARISCOTTA MILLS | 219T1 | 2024-09-26 | Fail | Pass | 2024-10-28
103885 | 2024-09-23 | 2024-10-01 | Solar | 975 | 624D2 | FORT HILL | 624T1 | 2024-10-02 | Fail |  |  | Yes
103844 | 2024-09-19 | 2024-09-24 | Solar | 975 | 272D4 | NORTH AUGUSTA | 272T1 | 2024-09-24 | Fail | Pass | 2024-10-17 | Yes
103677 | 2024-09-05 | 2024-09-05 | Solar | 100 | 803D6 | BELFAST WEST SIDE | 34.5 kV Bus | 2024-09-10 | Fail | Pass | 2024-10-15
103608 | 2024-08-30 |  | Solar | 4999 | [7 empty] | Yes
103599 | 2024-08-29 | 2024-09-16 | Solar | 999.6 | 842D1 | PITTSFIELD | 842T1 | 2024-09-16 | Fail | Pass | 2024-10-11
103367 | 2024-08-14 | 2024-08-15 | Solar | 995 | 242D1 | SIDNEY | 242T1 | 2024-08-16 | Fail | Pass | 2024-09-25
103285 | 2024-08-06 | 2024-08-13 | Solar | 540 | 647D1 | PRIDES CORNER | 647T2 | 2024-08-13 | Fail | Pass | 2024-09-12
103291 | 2024-08-06 | 2024-08-16 | Solar | 125 | 647D1 | PRIDES CORNER | 647T2 | 2024-08-22 | Fail | Pass | 2024-09-16
103293 | 2024-08-06 | 2024-08-16 | Solar | 150 | 647D1 | PRIDES CORNER | 647T2 | 2024-08-22 | Fail | Pass | 2024-09-16
103125 | 2024-07-30 | 2024-08-06 | Solar | 994 | 454D1 | TURNER | 454T1 | 2024-08-07 | Fail | Pass | 2024-09-16
103042 | 2024-07-24 | 2024-08-12 | Solar | 975 | 207D2 | BLAIR ROAD | 207T1 | 2024-08-13 | Fail | Fail | 2024-09-30 | Yes
103022 | 2024-07-23 |  | Solar | 480 | [7 empty] | Yes
103024 | 2024-07-23 | 2024-07-26 | Solar | 480 | 437D1 | OXFORD | 437T1 | 2024-07-29 | Fail | Fail | 2024-08-12 | Yes
103027 | 2024-07-23 |  | Solar | 150 | 437D1 | OXFORD | 437T1 |  |  |  |  | Yes
103030 | 2024-07-23 | 2024-07-26 | Solar | 420 | 216D2 | CONY ROAD | 216T1 | 2024-07-29 | Fail | Fail | 2024-08-23 | Yes
102896 | 2024-07-12 | 2024-07-30 | Solar | 975 | 634D1 | MAY STREET | 634T1 | 2024-08-16 | Fail | Fail | 2024-10-02 | Yes
102852 | 2024-07-11 | 2024-07-18 | Solar | 390 | 605D1 | BIDDEFORD PUMPING STATION | 605T1 | 2024-07-26 | Fail | Pass | 2024-08-28
102789 | 2024-07-08 | 2024-07-08 | Solar | 145.152 | 685D1 | BOLT HILL | 685T1 | 2024-07-10 | Pass
102756 | 2024-07-02 | 2024-07-10 | Solar | 995 | 874D1 | BELFAST 115 | 874T2 | 2024-07-12 | Fail | Fail | 2024-09-03 | Yes
102732 | 2024-07-01 | 2024-07-02 | Solar | 150 | 239D6 | PARK STREET | 239T2 | 2024-07-09 | Fail | Pass | 2024-08-05
102742 | 2024-07-01 | 2024-07-02 | Solar | 200 | 630D2 | GOOSEFARE | 630T1 | 2024-07-03 | Fail | Pass | 2024-08-06
102659 | 2024-06-25 | 2024-06-26 | Solar | 975 | 810D1 | CLINTON | 810T1 | 2024-06-27 | Fail | Fail | 2024-08-12 | Yes
102613 | 2024-06-24 | 2024-06-26 | Solar | 720 | 656D1 | SANFORD INDUSTRIAL PARK | 656T1 | 2024-07-12 | Fail | Pass | 2024-08-28
102614 | 2024-06-24 | 2024-06-26 | Solar | 360 | 644D1 | PLEASANT HILL | 644T2 | 2024-06-28 | Pass
102616 | 2024-06-24 | 2024-06-28 | Solar | 660 | 635D2 | MOSHERS | 635T2 | 2024-07-02 | Fail | Pass | 2024-08-01
102617 | 2024-06-24 | 2024-06-28 | Solar | 100 | 693D2 | SCARBOROUGH | 693T1 | 2024-07-02 | Pass
102619 | 2024-06-24 | 2024-06-28 | Solar | 200 | 693D2 | SCARBOROUGH | 693T1 | 2024-07-02 | Pass
102622 | 2024-06-24 | 2024-06-28 | Solar | 150 | 630D1 | GOOSEFARE | 630T1 | 2024-07-02 | Pass
102492 | 2024-06-13 |  | Solar | 996 | [7 empty] | Yes
102439 | 2024-06-10 | 2024-06-13 | Solar | 280 | 213D3 | BRUNSWICK WEST SIDE | 213T1 | 2024-06-24 | Pass
102340 | 2024-06-04 | 2024-07-10 | Solar | 160 | 213D3 | BRUNSWICK WEST SIDE | 213T1 | 2024-07-12 | Fail | Pass | 2024-08-09
102272 | 2024-05-30 | 2024-06-12 | Solar | 975 | 450D1 | SABATTUS | 450T1 | 2024-06-13 | Pass | Pass | 2024-07-15 | Yes
102178 | 2024-05-23 | 2024-05-29 | Solar/Battery | 996 | 444D3 | RAYMOND 34 KV | 444T1 | 2024-06-03 | Fail |  |  | Yes
102153 | 2024-05-22 | 2024-06-04 | Solar | 600 | 854D2 | SKOWHEGAN SOUTH SIDE | 854T1 | 2024-06-07 | Fail |  |  | Yes
102149 | 2024-05-21 | 2024-05-21 | Solar | 152 | 435D4 | NORWAY | 435T2 | 2024-05-22 | Fail | Pass | 2024-07-10
102000 | 2024-05-10 | 2024-05-22 | Wind | 225 | 806D2 | BUCKSPORT | 806T3 | 2024-05-31 | Fail | Pass | 2024-07-09
102005 | 2024-05-10 | 2024-05-23 | Solar | 999 | 263D1 | BOWMAN STREET | 34kV BUS 2 | 2024-05-29 | Fail |  |  | Yes
101765 | 2024-04-23 | 2024-05-15 | Solar | 999 | 821D3 | GUILFORD | 821T2 | 2024-05-28 | Fail | Pass | 2024-07-10
101713 | 2024-04-18 | 2024-05-07 | Solar | 975 | 674D2 | WESTBROOK | 674T1 | 2024-05-17 | Fail |  |  | Yes
101717 | 2024-04-18 | 2024-04-19 | Solar | 975 | 226D2 | GARDINER | 226T1 | 2024-04-22 | Fail | Pass | 2024-05-20
101658 | 2024-04-12 | 2024-04-18 | Solar | 153.6 | 219D2 | DAMARISCOTTA MILLS | 219T1 | 2024-05-08 | Fail |  |  | Yes
101603 | 2024-04-08 | 2024-04-17 | Solar | 250 | 412D4 | DEER RIPS | 412T4 | 2024-04-25 | Fail | Pass | 2024-06-24
101569 | 2024-04-04 | 2024-04-23 | Solar | 999 | 602D3 | BASSETT | 602T1 | 2024-05-09 | Fail | Pass | 2024-06-28
101528 | 2024-04-01 | 2024-04-12 | Solar | 999 | 431D1 | MECHANIC FALLS | 431T2 | 2024-04-22 | Fail | Fail | 2024-06-19 | Yes
101504 | 2024-03-28 | 2024-04-02 | Solar | 999 | 252D1 | WALDOBORO | 252T1 | 2024-04-05 | Fail | Fail | 2024-05-21 | Yes
101353 | 2024-03-18 | 2024-03-25 | Solar | 120 | 630D1 | GOOSEFARE | 630T1 | 2024-04-12 | Pass
101333 | 2024-03-14 |  | Solar | 150 | 403D1 | BETHEL | 403T1 |  |  |  |  | Yes
101334 | 2024-03-14 |  | Solar | 200 | 858D2 | STURTEVANT | 858T1 |  |  |  |  | Yes
101262 | 2024-03-08 | 2024-03-14 | Solar | 152 | 423D2 | KIMBALL ROAD | 423T2 | 2024-03-18 | Fail | Pass | 2024-04-30
101251 | 2024-03-07 | 2024-03-08 | Solar | 780 | 612D1 | BUTLER'S CORNER | 612T1 | 2024-03-27 | Fail | Fail | 2024-05-21 | Yes
101145 | 2024-02-27 | 2024-02-28 | Solar | 999 | 457D2 | MONMOUTH | 457T2 | 2024-03-01 | Fail | Pass | 2024-04-23
101131 | 2024-02-26 | 2024-02-29 | Solar | 999 | 447D4 | RUMFORD | 447T3 | 2024-03-01 | Fail | Fail | 2024-05-01 | Yes
101137 | 2024-02-26 | 2024-03-08 | Solar | 975 | 230D2 | COOPERS MILLS ROAD | 230T2 | 2024-03-08 | Fail | Pass | 2024-05-01
101067 | 2024-02-21 | 2024-02-23 | Solar | 125 | 865D1 | WEST WATERVILLE | 865T1 | 2024-02-26 | Pass |  |  | Yes
101037 | 2024-02-19 |  | Solar | 100 | 415D2 | FRYEBURG | 415T1 |  |  |  |  | Yes
100989 | 2024-02-13 |  | Solar | 996 | [7 empty] | Yes
100963 | 2024-02-09 | 2024-02-12 | Solar | 115.2 | 216D3 | CONY ROAD | 216T1 | 2024-02-13 | Pass
100873 | 2024-02-01 | 2024-02-13 | Solar | 995 | 667D2 | SOUTH SANFORD | 667T2 | 2024-03-07 | Fail | Fail | 2024-05-06 | Yes
100862 | 2024-01-31 | 2024-02-08 | Solar | 150 | 233D1 | MANCHESTER | 233T1 | 2024-02-09 | Fail | Pass | 2024-03-25
100863 | 2024-01-31 | 2024-02-09 | Solar | 600 | 415D2 | FRYEBURG | 415T1 | 2024-02-16 | Fail | Fail | 2024-04-12 | Yes
100846 | 2024-01-30 | 2024-02-19 | Solar | 999 | 272D2 | NORTH AUGUSTA | 272T1 | 2024-02-20 | Fail | Pass | 2024-04-11
100821 | 2024-01-26 | 2024-03-04 | Solar | 999 | 632D1 | LIMERICK | 632T1 | 2024-03-07 | Fail | Fail | 2024-05-12 | Yes
100803 | 2024-01-25 | 2024-02-02 | Solar | 999 | 246D3 | THOMASTON CREEK | 246T1 | 2024-02-21 | Fail | Fail | 2024-05-07 | Yes
100814 | 2024-01-25 | 2024-02-07 | Solar | 233.3 | 620D4 | ELM STREET | 620T2 | 2024-02-09 | Fail | Pass | 2024-04-02
100792 | 2024-01-24 | 2024-02-23 | Solar | 999 | 467D1 | TURNER TAP | Tap off of Transmission Line | 2024-02-26 | Fail | Pass | 2024-04-24
100687 | 2024-01-12 | 2024-01-18 | Solar | 500 | 256D2 | WINTHROP | 256T1 | 2024-01-19 | Fail |  |  | Yes
100680 | 2024-01-11 | 2024-01-22 | Solar | 380 | 668D3 | SPRING STREET | 668T2 | 2024-02-05 | Pass |  |  | Yes
100681 | 2024-01-11 | 2024-01-22 | Solar | 999 | 685D2 | BOLT HILL | 685T1 | 2024-02-13 | Fail | Pass | 2024-04-12
100682 | 2024-01-11 | 2024-01-22 | Solar | 999 | 603D3 | BERWICK | 603T1 | 2024-02-22 | Fail | Fail | 2024-04-26 | Yes
100620 | 2024-01-05 | 2024-01-05 | Solar | 400 | 412D1 | DEER RIPS | 412T2 | 2024-01-09 | Fail | Pass | 2024-03-18
100623 | 2024-01-05 | 2024-01-08 | Solar | 720 | 412D1 | DEER RIPS | 412T2 | 2024-01-09 | Fail | Pass | 2024-03-11
100571 | 2023-12-29 | 2024-01-16 | Solar | 750 | 200D3 | AUGUSTA K5 | 200T1 | 2024-01-16 | Fail | Pass | 2024-03-20
100520 | 2023-12-22 | 2024-01-09 | Solar | 500 | 660D2 | SHAWS MILL ROAD | 660T1 | 2024-01-13 | Fail | Pass | 2024-02-15
100461 | 2023-12-15 | 2024-01-10 | Solar | 999 | 818D2 | FARMINGTON FALLS | 818T1 | 2024-01-17 | Fail | Pass | 2024-04-11 | Yes
100388 | 2023-12-11 | 2023-12-15 | Solar | 350 | 421D2 | CHALLENGER | 421T1 | 2024-01-03 | Fail | Pass | 2024-02-21
100360 | 2023-12-08 |  | Solar | 999 | [7 empty] | Yes
100368 | 2023-12-08 | 2023-12-14 | Solar | 330 | 841D1 | PHILLIPS/STRONG | 841T1 | 2024-01-03 | Fail |  |  | Yes
100376 | 2023-12-08 | 2023-12-15 | Solar | 999 | 855D2 | SOUTH WATERVILLE | 855T1 | 2023-12-18 | Fail | Fail | 2024-02-08 | Yes
100379 | 2023-12-08 |  | Solar | 1000 | [7 empty] | Yes
100340 | 2023-12-07 | 2023-12-11 | Solar | 360 | 215D2 | CAPITOL STREET | 215T2 | 2023-12-11 | Fail | Pass | 2024-02-09
100354 | 2023-12-07 | 2024-01-08 | Solar | 999 | 632D1 | LIMERICK | 632T1 | 2024-02-01 | Fail | Fail | 2024-04-09 | Yes
100324 | 2023-12-06 | 2023-12-12 | Solar | 360 | 273D5 | BRUNSWICK HYDRO | 273T2 | 2024-01-02 | Pass
100307 | 2023-12-05 | 2023-12-06 | Solar | 540 | 249D2 | TOPSHAM OLD | 249T1 | 2023-12-27 | Fail | Pass | 2024-03-11
100263 | 2023-12-01 | 2024-01-10 | Solar | 900 | 818D1 | FARMINGTON FALLS | 818T1 | 2024-01-17 | Fail | Pass | 2024-03-18 | Yes
100265 | 2023-12-01 | 2023-12-06 | Solar | 240 | 865D1 | WEST WATERVILLE | 865T1 | 2023-12-06 | Fail | Pass | 2024-01-29
100266 | 2023-12-01 | 2023-12-06 | Solar | 400 | 639D2 | NORTH WINDHAM | 639T2 | 2023-12-11 | Fail | Pass | 2024-03-08
100267 | 2023-12-01 | 2023-12-06 | Solar | 240 | 681D3 | BRANCH BROOK | 681T3 | 2023-12-27 | Pass
100268 | 2023-12-01 | 2023-12-06 | Solar | 500 | 681D3 | BRANCH BROOK | 681T3 | 2023-12-26 | Pass
100245 | 2023-11-30 | 2023-12-07 | Solar | 120 | 249D1 | TOPSHAM OLD | 249T1 | 2023-12-29 | Fail | Pass | 2024-02-22
100251 | 2023-11-30 | 2023-12-07 | Solar | 100 | 249D1 | TOPSHAM OLD | 249T1 | 2024-01-02 | Fail | Pass | 2024-02-19
100252 | 2023-11-30 | 2024-01-17 | Solar | 1020 | 471D1 | LEEDS | 471T1 | 2024-01-23 | Fail | Fail | 2024-04-29 | Yes
100255 | 2023-11-30 | 2023-12-15 | Solar | 1020 | 873D1 | COUNTY RD (RICE RIPS) | 873T1 | 2023-12-18 | Fail |  |  | Yes
100222 | 2023-11-29 | 2023-11-30 | Solar | 996 | 678D1 | BAR MILLS | 678T4 | 2023-12-26 | Fail | Fail | 2024-03-21 | Yes
100227 | 2023-11-29 | 2023-12-12 | Solar | 1020 | 450D2 | SABATTUS | 450T1 | 2023-12-26 | Fail | Fail | 2024-03-11 | Yes
100140 | 2023-11-27 | 2023-12-07 | Solar | 360 | 668D3 | SPRING STREET | 668T2 | 2023-12-11 | Pass
100119 | 2023-11-22 | 2023-11-29 | Solar | 996 | 453D1 | TRAP CORNER | 453T1 | 2023-12-05 | Fail |  |  | Yes
100126 | 2023-11-22 | 2023-12-06 | Solar | 360 | 233D1 | MANCHESTER | 233T1 | 2023-12-06 | Fail | Fail | 2024-02-20 | Yes
100128 | 2023-11-22 | 2023-12-07 | Solar | 420 | 213D4 | BRUNSWICK WEST SIDE | 213T2 | 2023-12-29 | Pass |  |  | Yes
100129 | 2023-11-22 | 2023-12-06 | Solar | 480 | 668D3 | SPRING STREET | 668T2 | 2023-12-11 | Fail |  |  | Yes
100091 | 2023-11-17 | 2023-11-27 | Solar | 975 | 461D1 | LUDDEN LANE | 461T1 | 2023-12-11 | Fail | Pass | 2024-02-12
100056 | 2023-11-16 | 2023-11-27 | Solar | 120 | 208D1 | BOND BROOK | 208T1 | 2023-11-27 | Fail |  |  | Yes
100057 | 2023-11-16 | 2023-11-27 | Solar | 120 | 453D1 | TRAP CORNER | 453T1 | 2023-11-28 | Fail |  |  | Yes
100000 | 2023-11-15 | 2023-11-27 | Solar | 994 | 210D1 | BRISTOL | 210T1 | 2023-12-18 | Fail | Pass | 2024-01-25 | Yes
100001 | 2023-11-15 | 2023-11-27 | Solar | 700 | 870D1 | WINSLOW | 870T4 | 2023-11-28 | Fail | Fail | 2024-01-02 | Yes
100002 | 2023-11-15 | 2023-11-22 | Solar | 994 | 454D1 | TURNER | 454T1 | 2023-11-28 | Fail | Fail | 2024-01-25 | Yes
100049 | 2023-11-15 | 2024-01-04 | Solar | 1020 | 858D2 | STURTEVANT | 858T1 | 2024-01-05 | Fail |  |  | Yes
85879 | 2023-11-13 | 2023-11-20 | Solar | 999 | 695D2 | LEBANON | 695T1 | 2023-12-13 | Fail | Fail | 2024-02-14 | Yes
85877 | 2023-11-10 | 2023-11-13 | Solar | 995 | 842D1 | PITTSFIELD | 842T1 | 2023-11-14 | Fail | Pass | 2023-12-08
85876 | 2023-11-09 | 2023-12-06 | Solar | 100 | 803D5 | BELFAST WEST SIDE | 803T1 | 2023-12-29 | Fail | Pass | 2024-02-21
85862 | 2023-11-08 | 2023-11-15 | Solar | 150 | 233D1 | MANCHESTER | 233T1 | 2023-11-15 | Fail | Pass | 2024-01-02
85875 | 2023-11-08 | 2023-12-11 | Solar | 999 | 837D2 | NEWPORT | 837T2 | 2023-12-11 | Fail | Pass | 2024-01-17 | Yes
85805 | 2023-11-03 | 2023-11-09 | Solar | 999 | 813D1 | DEXTER | 813T1 | 2023-11-17 | Fail | Pass | 2024-01-02
85807 | 2023-11-03 | 2023-11-09 | Solar | 999 | 256D2 | WINTHROP | 256T1 | 2023-11-10 | Fail | Pass | 2023-12-06
85736 | 2023-11-02 | 2023-11-02 | Solar | 999 | 471D2 | LEEDS | 471T1 | 2023-11-08 | Fail | Pass | 2024-01-02
85743 | 2023-11-02 | 2023-11-14 | Solar | 560 | 412D1 | DEER RIPS | 412T2 | 2023-11-17 | Fail | Pass | 2024-01-11 | Yes
85721 | 2023-11-01 | 2023-11-13 | Solar | 970 | 239D6 | PARK STREET | 239T2 | 2023-11-14 | Fail | Pass | 2024-01-17
85727 | 2023-11-01 | 2023-11-13 | Solar | 625 | 230D1 | COOPERS MILLS ROAD | 230T2 | 2023-11-13 | Fail | Pass | 2024-01-25
85695 | 2023-10-31 | 2023-11-13 | Solar | 300 | 865D5 | WEST WATERVILLE | 865T2 | 2023-11-14 | Fail | Pass | 2024-01-29
85703 | 2023-10-31 | 2023-11-03 | Solar | 975 | 421D2 | CHALLENGER | 421T1 | 2023-11-09 | Fail | Pass | 2023-12-06 | Yes
85663 | 2023-10-27 | 2023-11-03 | Solar | 600 | 612D2 | BUTLER'S CORNER | 612T1 | 2023-11-28 | Fail | Fail | 2024-02-14 | Yes
85622 | 2023-10-24 | 2023-11-13 | Solar | 152 | 423D2 | KIMBALL ROAD | 423T2 | 2023-11-14 | Fail | Pass | 2024-01-11
85588 | 2023-10-18 | 2023-10-24 | Solar | 600 | 865D1 | WEST WATERVILLE | 865T1 | 2023-10-25 | Pass
85484 | 2023-10-13 | 2023-10-18 | Solar | 975 | 447D1 | RUMFORD | 447T3 | 2023-10-30 | Pass
85488 | 2023-10-13 | 2023-10-19 | Solar | 500 | 208D1 | BOND BROOK | 208T1 | 2023-10-19 | Fail | Pass | 2023-11-27
85228 | 2023-09-28 | 2023-10-04 | Solar | 975 | 261D4 | BATH 34 | 261T2 | 2023-10-26 | Fail | Fail | 2023-11-10 | Yes
85186 | 2023-09-26 | 2023-10-17 | Solar | 900 | 667D3 | SOUTH SANFORD | 667T1 | 2023-11-14 | Fail | Pass | 2024-01-24
85197 | 2023-09-26 | 2023-10-02 | Solar | 480 | 423D1 | KIMBALL ROAD | 423T2 | 2023-10-05 | Fail | Pass | 2023-11-10
85173 | 2023-09-25 | 2023-09-28 | Solar | 250 | 673D1 | BIDDEFORD INDUSTRIAL PARK | 673T2 | 2023-10-23 | Pass
85069 | 2023-09-15 | 2023-10-04 | Solar | 975 | 466D1 | RUMFORD INDUSTRIAL PARK | 466T1 | 2023-10-06 | Fail | Fail | 2023-11-10 | Yes
85041 | 2023-09-13 | 2023-09-27 | Solar | 994 | 263D1 | BOWMAN STREET | 34kV BUS 2 | 2023-09-28 | Fail | Pass | 2023-10-25 | Yes
85031 | 2023-09-12 | 2023-10-12 | Solar | 1999 | 225D3 | FREEPORT | 225T2 | 2023-10-26 | Fail |  |  | Yes
85012 | 2023-09-11 | 2023-09-18 | Solar | 1050 | 207D1 | BLAIR ROAD | 207T1 | 2023-09-19 | Fail | Fail | 2023-10-25 | Yes
84974 | 2023-09-08 | 2023-09-13 | Solar | 975 | 233D1 | MANCHESTER | 233T1 | 2023-09-13 | Fail | Pass | 2023-09-29
84979 | 2023-09-08 | 2023-09-13 | Solar | 975 | 219D2 | DAMARISCOTTA MILLS | 219T1 | 2023-09-19 | Fail | Pass | 2023-10-12
84902 | 2023-09-05 | 2023-09-12 | Other | 100 | 855D1 | SOUTH WATERVILLE | 855T1 | 2023-09-06 | Fail | Pass | 2023-10-12
84904 | 2023-09-05 | 2023-09-11 | Solar | 150 | 252D2 | WALDOBORO | 252T1 | 2023-09-15 | Fail | Pass | 2023-10-12
84764 | 2023-08-23 | 2023-09-19 | Solar | 500 | 210D2 | BRISTOL | 210T1 | 2023-10-11 | Fail | Fail | 2023-12-08 | Yes
84691 | 2023-08-17 | 2023-08-25 | Solar | 144.48 | 667D1 | SOUTH SANFORD | 667T2 | 2023-08-31 | Fail | Pass | 2023-10-12
84683 | 2023-08-14 |  | Solar | 799.98 | 874D1 | BELFAST 115 | 874T2 |  |  |  |  | Yes
84684 | 2023-08-14 | 2023-08-28 | Solar | 100 | 239D7 | PARK STREET | 239T2 | 2023-08-31 | Pass
84618 | 2023-08-09 | 2023-08-10 | Solar | 999 | 412D1 | DEER RIPS | 412T2 | 2023-08-11 | Fail | Pass | 2023-09-28
84619 | 2023-08-09 | 2023-08-10 | Solar | 996 | 870D1 | WINSLOW | 870T4 | 2023-08-11 | Fail | Fail | 2023-09-14 | Yes
84757 | 2023-08-09 | 2023-09-08 | Solar | 999.6 | 808D3 | CARMEL TAP | 808T1 | 2023-09-26 | Pass
84609 | 2023-08-08 | 2023-08-21 | Solar | 999 | 821D1 | GUILFORD | 821T1 | 2023-08-22 | Fail | Pass | 2023-12-01
84547 | 2023-08-01 | 2023-08-04 | Solar | 999 | 412D4 | DEER RIPS | 412T4 | 2023-08-07 | Fail | Fail | 2023-10-25 | Yes
84553 | 2023-08-01 | 2023-08-04 | Solar | 999 | 412D4 | DEER RIPS | 412T4 | 2023-08-07 | Fail | Fail | 2023-10-25 | Yes
84450 | 2023-07-25 | 2023-07-27 | Solar | 996 | 695D2 | LEBANON | 695T1 | 2023-08-24 | Fail | Pass | 2023-10-12
84451 | 2023-07-25 | 2023-07-27 | Solar | 996 | 663D2 | SOUTH BERWICK | 663T1 | 2023-08-24 | Fail | Fail | 2023-10-12 | Yes
84452 | 2023-07-25 | 2023-07-27 | Solar | 996 | 225D4 | FREEPORT | 225T1 | 2023-08-17 | Fail | Fail | 2023-10-03 | Yes
84411 | 2023-07-20 | 2023-08-07 | Solar | 999 | 632D2 | LIMERICK | 632T1 | 2023-08-31 | Fail |  |  | Yes
84416 | 2023-07-20 | 2023-08-07 | Solar | 999 | 632D2 | LIMERICK | 632T1 | 2023-08-31 | Fail |  |  | Yes
84392 | 2023-07-18 | 2023-08-21 | Solar | 200 | 607D1 | BISHOP STREET | 607T1 | 2023-09-08 | Pass |  |  | Yes
84389 | 2023-07-17 | 2023-07-26 | Solar | 975 | 232D2 | LISBON FALLS | 232T2 | 2023-08-11 | Fail | Fail | 2023-09-20 | Yes
84338 | 2023-07-13 | 2023-07-19 | Solar | 975 | 244D1 | SOUTH CHINA | 244T1 | 2023-07-19 | Fail | Fail | 2023-08-16 | Yes
84350 | 2023-07-13 | 2023-07-19 | Solar | 975 | 255D2 | WEST STREET | 255T1 | 2023-07-19 | Fail | Pass | 2023-08-23
84304 | 2023-07-10 | 2023-07-10 | Solar | 750 | 858D2 | STURTEVANT | 858T1 | 2023-07-13 | Pass
84290 | 2023-07-06 | 2023-07-10 | Solar | 975 | 808D1 | CARMEL | 808T1 | 2023-07-14 | Fail | Pass | 2023-08-31 | Yes
84276 | 2023-07-05 | 2023-07-21 | Solar | 999 | 837D1 | NEWPORT | 837T1 | 2023-07-24 | Fail | Pass | 2023-08-11
84277 | 2023-07-05 | 2023-07-21 | Solar | 999 | 837D1 | NEWPORT | 837T1 | 2023-07-24 | Fail | Pass | 2023-09-06 | Yes
84278 | 2023-07-05 | 2023-07-21 | Solar | 999 | 837D1 | NEWPORT | 837T1 | 2023-07-24 | Fail | Pass | 2023-09-06 | Yes
84279 | 2023-07-05 | 2023-07-21 | Solar | 999 | 837D1 | NEWPORT | 837T1 | 2023-07-24 | Fail | Fail | 2023-09-06 | Yes
84280 | 2023-07-05 | 2023-07-21 | Solar | 999 | 837D1 | NEWPORT | 837T1 | 2023-07-24 | Fail | Fail | 2023-09-06 | Yes
84272 | 2023-06-30 | 2023-07-05 | Solar | 825 | 253D1 | WARREN | 253T1 | 2023-07-06 | Fail | Pass | 2023-08-01
84231 | 2023-06-29 | 2023-07-10 | Solar | 996 | 461D1 | LUDDEN LANE | 461T1 | 2023-07-13 | Fail | Pass | 2023-08-11
84228 | 2023-06-28 | 2023-06-30 | Solar | 999 | 860D1 | UNITY | 860T1 | 2023-07-10 | Fail | Fail | 2023-08-30 | Yes
84222 | 2023-06-27 | 2023-07-05 | Solar | 120 | 678D1 | BAR MILLS | 678T4 | 2023-07-26 | Fail | Pass | 2023-09-11
84188 | 2023-06-23 | 2023-06-28 | Solar | 975 | 238D1 | MESSINA | 238T1 | 2023-07-20 | Fail | Fail | 2023-08-16 | Yes
84211 | 2023-06-23 | 2023-07-07 | Solar | 160 | 689D1 | BRAGDON COMMONS | 689T1 | 2023-07-26 | Fail | Pass | 2023-09-20
84117 | 2023-06-16 | 2023-06-21 | Solar | 975 | 858D1B | STURTEVANT | 858T2 | 2023-07-06 | Fail | Pass | 2023-09-25
84104 | 2023-06-14 | 2023-07-05 | Solar | 1000 | 815D2 | DOVER | 815T2 | 2023-07-06 | Fail |  |  | Yes
84107 | 2023-06-14 | 2023-06-15 | Solar | 999 | 636D1 | MUSSEY ROAD | 636T1 | 2023-06-30 | Fail | Pass | 2023-08-08 | Yes
84070 | 2023-06-12 | 2023-06-15 | Solar | 975 | 860D2 | UNITY | 860T1 | 2023-06-29 | Fail | Pass | 2023-07-27
84071 | 2023-06-12 | 2023-06-14 | Solar | 975 | 858D1A | STURTEVANT | 858T1 | 2023-06-15 | Fail | Pass | 2023-07-18 | Yes
84066 | 2023-06-09 | 2023-06-12 | Solar | 995 | 471D1 | LEEDS | 471T1 | 2023-06-15 | Fail | Fail | 2023-07-10 | Yes
84068 | 2023-06-09 | 2023-06-13 | Solar | 875 | 253D1 | WARREN | 253T1 | 2023-06-28 | Fail |  |  | Yes
84024 | 2023-06-07 | 2023-06-13 | Solar | 975 | 431D1 | MECHANIC FALLS | 431T2 | 2023-06-15 | Fail | Pass | 2023-07-18
83991 | 2023-06-02 | 2023-06-08 | Solar | 160 | 852D1 | SHAWMUT | 852T3 | 2023-06-09 | Fail | Pass | 2023-07-25
84004 | 2023-06-02 | 2023-06-21 | Solar | 999 | 256D1 | WINTHROP | 256T2 | 2023-06-27 | Fail | Pass | 2023-08-16
83944 | 2023-05-26 | 2023-06-01 | Solar | 975 | 639D2 | NORTH WINDHAM | 639T2 | 2023-06-07 | Fail | Pass | 2023-07-12 | Yes
83909 | 2023-05-24 | 2023-06-05 | Solar | 999 | 813D1 | DEXTER | 813T1 | 2023-06-07 | Fail | Fail | 2023-07-14 | Yes
83914 | 2023-05-24 | 2023-06-05 | Solar | 999 | 885D1 | WILTON | 885T1 | 2023-06-07 | Fail | Pass | 2023-07-14
83916 | 2023-05-24 | 2023-06-05 | Solar | 999 | 885D1 | WILTON | 885T1 | 2023-06-07 | Fail | Fail | 2023-07-14 | Yes
83894 | 2023-05-22 | 2023-05-25 | Solar | 900 | 691D1 | BALDWIN | 691T1 | 2023-05-25 | Fail | Fail | 2023-06-21 | Yes
83856 | 2023-05-17 | 2023-05-22 | Solar | 154 | 274D1 | MAINE YANKEE | 274T2 | 2023-05-23 | Fail | Pass | 2023-07-20
83838 | 2023-05-16 | 2023-05-22 | Solar | 200 | 239D7 | PARK STREET | 239T2 | 2023-05-23 | Pass
83837 | 2023-05-15 | 2023-05-17 | Solar | 720 | 428D2 | LIVERMORE FALLS | 428T1 | 2023-05-18 | Pass
83829 | 2023-05-12 | 2023-05-15 | Solar | 995 | 412D3 | DEER RIPS | 412T4 | 2023-05-18 | Fail | Pass | 2023-06-06
83793 | 2023-05-09 | 2023-05-11 | Solar | 975 | 400D1 | ANDOVER | 400T1 | 2023-05-12 | Fail | Pass | 2023-06-20
83777 | 2023-05-08 | 2023-05-09 | Solar | 999 | 805D1 | BROOKS | 805T1 | 2023-05-10 | Fail | Fail | 2023-08-08 | Yes
83779 | 2023-05-08 | 2023-05-10 | Solar | 996 | 813D3 | DEXTER | 813T2 | 2023-05-12 | Fail | Fail | 2023-08-08 | Yes
83787 | 2023-05-08 | 2023-05-10 | Solar | 996 | 406D2 | BRIDGTON | 406T1 | 2023-05-17 | Fail | Fail | 2023-07-26 | Yes
83769 | 2023-05-05 | 2023-05-08 | Solar | 240 | 630D4 | GOOSEFARE | 630T1 | 2023-05-17 | Fail | Pass | 2023-06-22
83738 | 2023-05-04 | 2023-05-11 | Solar | 975 | 466D1 | RUMFORD INDUSTRIAL PARK | 466T1 | 2023-05-12 | Fail | Pass | 2023-06-01 | Yes
83720 | 2023-05-03 | 2023-05-25 | Solar | 1000 | 834D1 | MONSON | 834T1 | 2023-05-30 | Fail | Fail | 2023-06-22 | Yes
83685 | 2023-04-28 | 2023-05-01 | Solar | 324 | 858D1A | STURTEVANT | 858T1 | 2023-05-01 | Fail | Pass | 2023-05-03
83664 | 2023-04-27 | 2023-05-01 | Solar | 700 | 816D1 | EAST WILTON | 816T1 | 2023-05-02 | Fail | Pass | 2023-06-01
83668 | 2023-04-27 | 2023-05-01 | Solar | 975 | 233D2 | MANCHESTER | 233T1 | 2023-05-03 | Fail | Pass | 2023-05-11 | Yes
83670 | 2023-04-27 | 2023-05-01 | Solar | 975 | 262D1 | PUDDLEDOCK ROAD | 34 kV BUS 1 | 2023-05-09 | Fail | Pass | 2023-06-16
83611 | 2023-04-24 | 2023-05-03 | Solar | 120 | 617D3 | DUNSTAN | 617T1 | 2023-05-15 | Pass
83605 | 2023-04-21 | 2023-04-27 | Solar | 975 | 431D1 | MECHANIC FALLS | 431T2 | 2023-04-27 | Fail | Pass | 2023-06-05
83600 | 2023-04-20 | 2023-04-21 | Solar | 850 | 450D1 | SABATTUS | 450T1 | 2023-04-24 | Fail | Pass | 2023-06-21
83601 | 2023-04-20 | 2023-04-25 | Solar | 700 | 256D2 | WINTHROP | 256T1 | 2023-04-25 | Fail | Pass | 2023-05-11
83526 | 2023-04-12 | 2023-05-01 | Solar | 1000 | 821D3 | GUILFORD | 821T2 | 2023-05-02 | Fail | Fail | 2023-05-18 | Yes
83507 | 2023-04-11 | 2023-04-14 | Solar | 975 | 639D2 | NORTH WINDHAM | 639T2 | 2023-05-02 | Fail | Pass | 2023-05-23
83514 | 2023-04-11 | 2023-04-13 | Solar | 995 | 858D3 | STURTEVANT | 858T2 | 2023-04-18 | Fail | Pass | 2023-05-01
83474 | 2023-04-05 | 2023-04-07 | Solar | 999 | 605D1 | BIDDEFORD PUMPING STATION | 605T1 | 2023-05-03 | Pass | Pass | 2023-06-26
83455 | 2023-04-03 | 2023-04-18 | Solar | 999 | 602D3 | BASSETT | 602T1 | 2023-05-03 | Fail | Pass | 2023-06-23
83453 | 2023-03-31 | 2023-04-05 | Solar | 975 | 858D1A | STURTEVANT | 858T1 | 2023-04-05 | Fail | Fail | 2023-04-24 | Yes
83437 | 2023-03-28 | 2023-04-06 | Solar | 120 | 634D4 | MAY STREET | 634T1 | 2023-05-03 | Pass
83403 | 2023-03-27 | 2023-04-03 | Solar | 125 | 693D1 | SCARBOROUGH | 693T1 | 2023-04-05 | Pass |  |  | Yes
83401 | 2023-03-24 | 2023-03-29 | Solar | 250 | 436D6 | GREAT FALLS | 436T1 | 2023-03-30 | Fail | Pass | 2023-04-24 | Yes
83384 | 2023-03-23 | 2023-03-29 | Solar | 600 | 673D1 | BIDDEFORD INDUSTRIAL PARK | 673T2 | 2023-04-19 | Fail | Pass | 2023-06-02
83361 | 2023-03-21 | 2023-03-24 | Solar/Battery | 996 | 834D1 | MONSON | 834T1 | 2023-03-28 | Fail | Pass | 2023-05-16
83350 | 2023-03-20 | 2023-03-23 | Solar | 999 | 253D1 | WARREN | 253T1 | 2023-04-12 | Fail | Fail | 2023-05-11 | Yes
83328 | 2023-03-16 | 2023-03-20 | Solar | 720 | 653D5 | FORE RIVER | 653T1 | 2023-04-03 | Fail | Pass | 2023-05-01
83307 | 2023-03-14 | 2023-03-21 | Solar/Battery | 996 | 813D1 | DEXTER | 813T1 | 2023-03-22 | Fail | Pass | 2023-07-07
83298 | 2023-03-13 | 2023-03-16 | Solar | 120 | 200D1 | AUGUSTA K5 | 200T1 | 2023-03-16 | Pass
83253 | 2023-03-06 | 2023-03-15 | Solar | 120 | 656D1 | SANFORD INDUSTRIAL PARK | 656T1 | 2023-04-04 | Pass
83260 | 2023-03-06 | 2023-03-10 | Solar | 400 | 211D1 | BROWNS CROSSING | 211T1 | 2023-03-13 | Pass
83231 | 2023-03-02 | 2023-03-20 | Solar | 150 | 232D2 | LISBON FALLS | 232T2 | 2023-03-29 | Pass
83235 | 2023-03-02 | 2023-03-06 | Fuel Cell | 930 | 688D1 | KITTERY | 688T1 | 2023-03-28 | Pass |  |  | Yes
83229 | 2023-03-01 | 2023-03-03 | Fuel Cell | 600 | 420D1 | HOTEL ROAD | 420T2 | 2023-03-14 | Pass
83208 | 2023-02-24 | 2023-03-03 | Solar | 999 | 447D2 | RUMFORD | 447T4 | 2023-03-14 | Fail | Pass | 2023-04-18
83189 | 2023-02-22 | 2023-02-22 | Solar | 1500 | 612D1 | BUTLER'S CORNER | 612T1 | 2023-03-21 | Fail |  |  | Yes
83186 | 2023-02-21 | 2023-02-23 | Solar | 995 | 256D2 | WINTHROP | 256T1 | 2023-02-24 | Fail | Pass | 2023-03-23
83158 | 2023-02-16 | 2023-03-13 | Solar | 160 | 690D1 | HINCKLEY POND | 690T1 | 2023-03-23 | Pass |  |  | Yes
83159 | 2023-02-16 | 2023-03-01 | Solar | 120 | 255D2 | WEST STREET | 255T1 | 2023-03-23 | Fail |  |  | Yes
83131 | 2023-02-14 | 2023-02-21 | Solar | 240 | 621D2 | FACTORY ISLAND | 621T2 | 2023-03-07 | Pass
83095 | 2023-02-13 | 2023-02-24 | Solar | 300 | 239D7 | PARK STREET | 239T2 | 2023-03-16 | Pass
83116 | 2023-02-13 | 2023-02-22 | Solar | 133.2 | 650D4 | RIGBY | 650T2 | 2023-03-01 | Pass
83066 | 2023-02-09 | 2023-02-13 | Solar | 160 | 629D3 | KENNEBUNKPORT | 629T2 | 2023-03-07 | Pass
83040 | 2023-02-08 | 2023-02-23 | Solar | 999 | 837D2 | NEWPORT | 837T2 | 2023-03-07 | Fail | Pass | 2023-04-05
83025 | 2023-02-07 | 2023-02-09 | Solar | 995 | 256D2 | WINTHROP | 256T1 | 2023-02-23 | Fail | Pass | 2023-03-22
83038 | 2023-02-07 | 2023-02-09 | Solar | 100 | 447D4 | RUMFORD | 447T3 | 2023-02-24 | Pass
83018 | 2023-02-03 | 2023-02-09 | Solar | 300 | 620D1 | ELM STREET | 620T2 | 2023-02-28 | Fail | Pass | 2023-04-03
83014 | 2023-02-02 | 2023-02-13 | Solar | 200 | 630D2 | GOOSEFARE | 630T1 | 2023-03-07 | Pass
83016 | 2023-02-02 | 2023-03-03 | Solar | 240 | 630D4 | GOOSEFARE | 630T1 | 2023-04-04 | Fail |  |  | Yes
82985 | 2023-01-30 | 2023-02-09 | Solar | 200 | 656D2 | SANFORD INDUSTRIAL PARK | 656T1 | 2023-02-21 | Pass
82971 | 2023-01-27 | 2023-02-01 | Solar | 100 | 634D4 | MAY STREET | 634T1 | 2023-02-22 | Pass
82924 | 2023-01-20 | 2023-01-23 | Fuel Cell | 975 | 636D2 | MUSSEY ROAD | 636T1 | 2023-03-03 | Pass
82927 | 2023-01-20 | 2023-01-24 | Solar | 500 | 447D4 | RUMFORD | 447T3 | 2023-02-14 | Pass
82862 | 2023-01-06 | 2023-01-10 | Solar | 400 | 813D3 | DEXTER | 813T2 | 2023-01-13 | Pass |  |  | Yes
82873 | 2023-01-06 | 2023-01-11 | Solar | 360 | 650D4 | RIGBY | 650T2 | 2023-02-06 | Pass
82874 | 2023-01-06 | 2023-02-06 | Solar | 999 | 821D1 | GUILFORD | 821T1 | 2023-02-07 | Fail | Fail | 2023-03-02 | Yes
82822 | 2023-01-05 | 2023-01-09 | Solar | 145.92 | 251D1 | UNION | 251T1 | 2023-01-26 | Fail | Pass | 2023-02-01
82781 | 2022-12-28 | 2023-01-18 | Fuel Cell | 975 | 630D1 | GOOSEFARE | 630T1 | 2023-01-26 | Pass |  |  | Yes
82771 | 2022-12-22 | 2023-01-06 | Solar | 996 | 657D4 | SANFORD SWITCH | 657T1 | 2023-01-30 | Fail | Pass | 2023-04-18
82708 | 2022-12-14 | 2023-01-09 | Solar | 500 | 238D1 | MESSINA | 238T1 | 2023-01-11 | Fail | Pass | 2023-03-27
82709 | 2022-12-14 |  |  | 999 | 610D2 | BONNY EAGLE | 610T4 |  |  |  |  | Yes
82674 | 2022-12-13 | 2023-01-03 | Solar | 999 | 821D1 | GUILFORD | 821T1 | 2023-01-03 | Fail |  |  | Yes
82683 | 2022-12-13 | 2023-01-11 | Solar | 700 | 624D2 | FORT HILL | 624T1 | 2023-02-07 | Pass
82671 | 2022-12-08 | 2022-12-12 | Fuel Cell | 650 | 420D3 | HOTEL ROAD | 420T2 | 2023-01-16 | Pass
82669 | 2022-12-06 | 2022-12-23 | Solar | 975 | 239D7 | PARK STREET | 239T2 | 2023-01-12 | Fail | Fail | 2023-02-22 | Yes
82584 | 2022-11-29 | 2022-12-12 | Solar | 890 | 420D6 | HOTEL ROAD | 420T1 | 2022-12-13 | Fail | Pass | 2023-02-23 | Yes
82564 | 2022-11-23 | 2022-12-12 | Solar | 1950 | 693D1 | SCARBOROUGH | 693T1 | 2023-02-13 | Fail |  |  | Yes
82547 | 2022-11-21 | 2022-11-30 | Fuel Cell | 975 | 421D2 | CHALLENGER | 421T1 |  | Fail |  |  | Yes
82518 | 2022-11-16 | 2022-11-29 | Fuel Cell | 975 | 424D4 | LEWISTON LOWER | 424T3 | 2023-01-13 | Pass
82496 | 2022-11-14 | 2022-11-18 | Fuel Cell | 975 | 688D1 | KITTERY | 688T1 | 2023-01-15 | Fail |  |  | Yes
82499 | 2022-11-14 | 2022-11-29 | Solar | 500 | 233D2 | MANCHESTER | 233T1 | 2022-11-30 | Fail | Pass | 2023-05-01
82486 | 2022-11-07 | 2022-11-30 | Fuel Cell | 975 | 630D2 | GOOSEFARE | 630T1 | 2023-01-06 | Pass
82485 | 2022-11-05 | 2022-11-30 | Fuel Cell | 975 | 420D6 | HOTEL ROAD | 420T1 | 2023-01-09 | Pass
82455 | 2022-11-03 | 2022-12-05 | Solar | 100 | 250D2 | TOPSHAM | 250T2 | 2023-05-10 | Pass | Pass | 2023-02-13
82439 | 2022-11-01 | 2022-11-01 | Solar | 950 | 858D4 | STURTEVANT | 858T2 | 2022-11-01 | Pass
82404 | 2022-10-26 | 2022-11-15 | Solar | 750 | 445D1 | RAYMOND 115 KV | 445T1 | 2022-11-17 | Fail |  | 2023-06-21 | Yes
82373 | 2022-10-21 | 2022-11-01 | Solar | 104.16 | 245D2 | STICKNEYS CORNER | 245T1 | 2022-11-02 | Fail | Pass | 2023-02-01
82363 | 2022-10-20 | 2022-11-16 | Fuel Cell | 975 | 636D2 | MUSSEY ROAD | 636T1 | 2022-12-27 | Fail |  |  | Yes
82366 | 2022-10-20 | 2022-10-24 | Solar | 996 | 657D4 | SANFORD SWITCH | 657T1 | 2022-12-27 | Fail | Pass | 2023-04-18
82339 | 2022-10-18 | 2022-11-14 | Solar | 975 | 841D1 | PHILLIPS/STRONG | 841T1 | 2023-01-25 | Fail | Pass | 2023-02-23
82340 | 2022-10-18 | 2022-12-02 | Solar | 975 | 839D2 | OAKLAND | 839T1 | 2022-12-02 | Fail | Fail | 2023-03-30 | Yes
82322 | 2022-10-17 | 2022-10-19 | Solar | 995 | 667D1 | SOUTH SANFORD | 667T2 | 2022-12-01 | Fail | Pass | 2023-03-22 | Yes
82324 | 2022-10-17 | 2022-10-17 | Solar | 975 | 450D1 | SABATTUS | 450T1 | 2022-11-22 | Fail | Fail | 2023-01-23 | Yes
82261 | 2022-10-05 | 2022-11-01 | Solar | 950 | 858D4 | STURTEVANT | 858T2 | 2022-11-02 | Pass
82255 | 2022-10-04 | 2022-10-04 | Solar | 975 | 821D1 | GUILFORD | 821T1 | 2022-10-14 | Fail | Pass | 2023-02-07
82233 | 2022-09-27 | 2022-10-04 | Solar | 100 | 659D9 | SEWALL STREET | 659T2 | 2022-10-12 | Pass
82226 | 2022-09-23 | 2022-09-27 | Solar | 349.998 | 813D1 | DEXTER | 813T1 | 2022-09-28 | Pass |  |  | Yes
82201 | 2022-09-20 | 2022-09-30 | Solar | 390 | 261D3 | BATH 34 | 261T2 | 2022-10-06 | Fail | Pass | 2022-11-30
82202 | 2022-09-20 | 2022-12-02 | Solar | 996 | 407D1 | BRYANT POND | 407T1 | 2022-12-05 | Fail |  |  | Yes
82186 | 2022-09-15 | 2022-10-03 | Solar | 348 | 250D1 | TOPSHAM | 250T2 | 2022-10-03 | Fail |  |  | Yes
82151 | 2022-09-09 | 2022-09-09 | Solar | 160 | 213D3 | BRUNSWICK WEST SIDE | 213T1 | 2022-09-23 | Pass
82152 | 2022-09-09 | 2022-09-12 | Solar | 260 | 273D4 | BRUNSWICK HYDRO | 273T2 | 2022-10-04 | Fail | Pass | 2023-01-23
82143 | 2022-09-08 | 2022-09-30 | Solar | 228 | 860D1 | UNITY | 860T1 | 2023-03-09 | Fail |  |  | Yes
82084 | 2022-08-29 | 2022-09-09 | Solar | 1000 | 416D1 | GRAY | 416T2 | 2022-10-07 | Fail | Fail |  | Yes
82055 | 2022-08-25 | 2022-12-01 | Solar | 275 | 823D2 | HARRIS | 823T5 | 2023-02-24 | Pass
82053 | 2022-08-23 | 2022-08-23 | Solar | 1000 | 846D1 | PROSPECT | 846T1 | 2022-09-02 | Fail | Pass | 2022-11-11
82010 | 2022-08-15 | 2022-08-18 | Solar/Battery | 996 | 445D1 | RAYMOND 115 KV | 445T1 | 2022-08-22 | Fail | Fail | 2022-09-21 | Yes
82007 | 2022-08-12 | 2022-08-30 | Solar | 1875 | 272D4 | NORTH AUGUSTA | 272T1 | 2022-09-14 | Fail | Fail | 2022-11-08 | Yes
81972 | 2022-08-10 | 2022-08-17 | Solar | 975 | 246D2 | THOMASTON CREEK | 246T1 | 2022-09-09 | Fail | Fail | 2022-10-21 | Yes
81959 | 2022-08-08 | 2022-09-14 | Solar | 2000 | 431D2 | MECHANIC FALLS | 431T1 | 2022-09-13 | Fail | Fail |  | Yes
81960 | 2022-08-08 | 2022-09-28 | Solar | 749 | 860D2 | UNITY | 860T1 | 2022-10-05 | Fail | Fail | 2022-11-21 | Yes
81961 | 2022-08-08 | 2022-09-28 | Solar | 749 | 209D3 | BOOTHBAY HARBOR | 209T1 | 2022-09-30 |  |  |  | Yes
81963 | 2022-08-08 | 2022-08-08 | Solar | 749 | 250D1 | TOPSHAM | 250T2 | 2022-09-02 | Fail | Pass | 2022-11-02
81964 | 2022-08-08 | 2022-09-28 | Solar | 749 | 817D3 | FAIRFIELD | 817T1 | 2022-09-30 |  |  |  | Yes
81965 | 2022-08-08 | 2022-08-15 | Solar | 749 | 438D1 | PAPOOSE POND | Tap off of Transmission Line | 2022-09-12 | Fail | Pass | 2022-12-12
81966 | 2022-08-08 | 2022-08-15 | Solar | 749 | 850D2 | SEARSPORT | 850T1 | 2022-09-14 | Fail | Pass | 2022-12-13
81967 | 2022-08-08 | 2022-08-15 | Solar | 749 | 837D2 | NEWPORT | 837T2 | 2022-08-29 | Fail | Fail | 2023-01-16 | Yes
81968 | 2022-08-08 | 2022-08-15 | Solar | 749 | 861D9 | VASSALBORO | 861T1 | 2022-09-13 | Fail | Fail | 2022-11-06 | Yes
81956 | 2022-08-05 | 2022-08-11 | Solar | 725 | 412D3 | DEER RIPS | 412T4 | 2022-09-13 | Pass
81957 | 2022-08-05 | 2022-08-11 | Solar | 725 | 412D3 | DEER RIPS | 412T4 | 2022-09-26 | Fail | Fail | 2022-11-21 | Yes
81958 | 2022-08-05 | 2022-08-12 | Solar | 2000 | 602D2 | BASSETT | 602T1 | 2022-08-29 | Fail | Pass | 2022-11-02 | Yes
81947 | 2022-08-04 | 2022-08-15 | Solar | 153.6 | 251D1 | UNION | 251T1 | 2022-08-29 | Fail |  | 2022-10-10 | Yes
81955 | 2022-08-04 | 2022-08-11 | Solar | 450 | 811D1 | CORINNA | 811T1 | 2022-08-30 | Pass |  |  | Yes
81945 | 2022-08-03 | 2022-08-08 | Solar | 500 | 866D2 | WESTON | 866T2 | 2022-10-04 | Pass |  |  | Yes
81942 | 2022-08-02 | 2022-08-08 | Solar | 996 | 470D1 | SAND ROAD TAP | 470T1 | 2022-08-09 | Fail | Pass | 2022-09-27
81911 | 2022-07-29 | 2022-08-05 | Solar | 530 | 861D9 | VASSALBORO | 861T1 | 2022-08-31 | Fail | Pass | 2022-10-12 | Yes
81910 | 2022-07-27 | 2022-08-04 | Solar | 996 | 861D9 | VASSALBORO | 861T1 | 2022-08-11 | Fail | Fail | 2022-10-05 | Yes
81908 | 2022-07-26 | 2022-08-04 | Solar | 165 | 252D2 | WALDOBORO | 252T1 |  |  |  |  | Yes
81909 | 2022-07-26 | 2022-08-04 | Solar | 996 | 837D2 | NEWPORT | 837T2 | 2022-08-29 | Fail |  | 2022-10-03 | Yes
81849 | 2022-07-25 | 2022-08-01 | Solar | 996 | 438D1 | PAPOOSE POND | Tap off of Transmission Line | 2022-08-24 | Fail | Fail | 2022-10-10 | Yes
81850 | 2022-07-25 | 2022-08-12 | Solar | 996 | 850D2 | SEARSPORT | 850T1 | 2022-09-06 | Fail | Fail | 2022-10-17 | Yes
81851 | 2022-07-25 | 2022-08-25 | Solar | 2000 | 667D1 | SOUTH SANFORD | 667T2 | 2022-10-12 | Fail |  |  | Yes
81852 | 2022-07-25 |  | Solar | 1700 | 626D1 | HIGH STREET | 626T1 |  |  |  |  | Yes
81894 | 2022-07-25 | 2022-08-15 | Solar | 999 | 866D2 | WESTON | 866T2 | 2022-08-29 | Fail | Fail | 2022-09-21 | Yes
81895 | 2022-07-25 | 2022-08-15 | Solar | 400 | 454D2 | TURNER | 454T1 | 2022-08-25 | Pass
81896 | 2022-07-25 | 2022-08-01 | Solar | 730 | 412D3 | DEER RIPS | 412T4 | 2022-08-01 | Fail |  |  | Yes
81847 | 2022-07-21 |  |  | 210 | 638D2 | NORTH LIMINGTON | 638T1 |  |  |  |  | Yes
81848 | 2022-07-21 | 2022-07-21 | Solar | 850 | 412D3 | DEER RIPS | 412T4 | 2022-08-29 | Fail | Fail | 2022-10-17 | Yes
81817 | 2022-07-20 | 2022-07-27 | Solar | 1000 | 837D2 | NEWPORT | 837T2 | 2022-08-29 | Fail | Fail | 2022-10-10 | Yes
81819 | 2022-07-20 | 2022-07-27 | Solar | 999 | 821D3 | GUILFORD | 821T2 | 2022-09-13 | Fail | Pass | 2022-11-02
81816 | 2022-07-19 | 2022-07-25 | Solar | 996 | 860D2 | UNITY | 860T1 | 2022-08-02 | Fail |  | 2022-09-02 | Yes
81815 | 2022-07-18 | 2022-08-02 | Solar | 124 | 225D4 | FREEPORT | 225T1 | 2022-08-16 | Fail |  |  | Yes
81810 | 2022-07-15 | 2022-07-22 | Solar | 996 | 209D3 | BOOTHBAY HARBOR | 209T1 | 2022-08-18 | Fail | Pass | 2022-10-05
81811 | 2022-07-15 | 2022-07-22 | Solar | 996 | 250D1 | TOPSHAM | 250T2 | 2022-08-18 | Fail |  |  | Yes
81812 | 2022-07-15 | 2022-07-22 | Solar | 996 | 817D3 | FAIRFIELD | 817T1 | 2022-08-18 | Fail |  | 2022-09-07 | Yes
81754 | 2022-07-08 | 2022-07-12 | Solar | 190 | 457D2 | MONMOUTH | 457T2 | 2022-07-27 | Pass |  |  | Yes
81752 | 2022-07-01 | 2022-07-12 | Solar | 540 | 250D2 | TOPSHAM | 250T2 | 2022-07-25 | Fail | Pass | 2022-09-13
81680 | 2022-06-24 | 2022-07-08 | Solar | 466 | 255D2 | WEST STREET | 255T1 | 2022-08-01 | Pass
81653 | 2022-06-21 | 2022-06-27 | Solar | 115.2 | 470D1 | SAND ROAD TAP | 470T1 | 2022-07-08 | Pass
81675 | 2022-06-21 | 2022-06-27 | Solar | 990 | 431D1 | MECHANIC FALLS | 431T2 | 2022-07-08 | Fail |  |  | Yes
81676 | 2022-06-21 | 2022-06-29 | Solar | 875 | 412D3 | DEER RIPS | 412T4 | 2022-07-27 | Fail |  |  | Yes
81677 | 2022-06-21 | 2022-06-29 | Solar | 875 | 412D3 | DEER RIPS | 412T4 | 2022-07-27 | Fail |  |  | Yes
81678 | 2022-06-21 | 2022-06-29 | Solar | 1000 | 858D4 | STURTEVANT | 858T2 | 2022-08-01 | Fail |  |  | Yes
81679 | 2022-06-21 | 2022-06-29 | Solar | 1000 | 858D4 | STURTEVANT | 858T2 | 2022-08-01 | Fail |  |  | Yes
81628 | 2022-06-17 | 2022-06-24 | Solar | 244 | 839D2 | OAKLAND | 839T1 | 2022-07-09 | Pass |  |  | Yes
81512 | 2022-06-02 | 2022-06-08 | Solar | 975 | 852D1 | SHAWMUT | 852T3 | 2022-06-15 | Fail | Fail |  | Yes
81513 | 2022-06-02 | 2022-06-08 | Solar | 975 | 873D1 | COUNTY RD (RICE RIPS) | 873T1 | 2022-06-15 | Fail | Pass | 2022-09-01
81515 | 2022-06-02 | 2022-06-08 | Solar | 975 | 873D1 | COUNTY RD (RICE RIPS) | 873T1 | 2022-06-27 | Fail |  |  | Yes
81516 | 2022-06-02 | 2022-06-08 | Solar | 975 | 454D2 | TURNER | 454T1 | 2022-06-15 | Fail |  |  | Yes
81506 | 2022-05-31 | 2022-06-06 | Solar | 975 | 870D1 | WINSLOW | 870T4 | 2022-07-06 | Fail |  | 2022-10-11 | Yes
81508 | 2022-05-31 | 2022-06-06 | Solar | 975 | 853D1 | SKOWHEGAN NORTH SIDE | 853T1 | 2022-06-15 | Fail |  |  | Yes
81509 | 2022-05-31 | 2022-06-06 | Solar | 975 | 853D1 | SKOWHEGAN NORTH SIDE | 853T1 | 2022-06-15 | Fail |  |  | Yes
81511 | 2022-05-31 | 2022-06-06 | Solar | 350 | 866D2 | WESTON | 866T2 | 2022-07-19 | Pass
81489 | 2022-05-27 | 2022-05-31 | Solar | 475 | 412D3 | DEER RIPS | 412T4 | 2022-06-08 | Pass
81435 | 2022-05-26 | 2022-06-01 | Solar | 975 | 412D3 | DEER RIPS | 412T4 | 2022-06-08 | Fail |  |  | Yes
81465 | 2022-05-26 | 2022-06-01 | Solar | 900 | 255D2 | WEST STREET | 255T1 | 2022-06-15 | Fail |  |  | Yes
81413 | 2022-05-23 | 2022-05-24 | Solar | 975 | 870D1 | WINSLOW | 870T4 | 2022-06-08 | Fail |  |  | Yes
81409 | 2022-05-20 | 2022-05-27 | Solar | 200 | 237D1 | MCCOYS | 237T1 | 2022-06-17 | Pass |  |  | Yes
81396 | 2022-05-19 | 2022-05-23 | Solar | 337.5 | 603D2 | BERWICK | 603T1 | 2022-08-11 | Fail | Pass | 2022-10-31
81395 | 2022-05-17 | 2022-06-06 | Solar | 975 | 457D2 | MONMOUTH | 457T2 | 2022-06-08 | Fail |  |  | Yes
81393 | 2022-05-16 | 2022-05-31 | Solar | 125 | 647D1 | PRIDES CORNER | 647T2 | 2022-06-14 | Pass
81394 | 2022-05-16 | 2022-05-23 | Solar | 975 | 457D2 | MONMOUTH | 457T2 | 2022-06-10 | Fail | Pass | 2022-07-29
81270 | 2022-05-09 | 2022-05-13 | Solar | 104.1 | 430D1 | LOVELL | 430T1 |  |  |  |  | Yes
81265 | 2022-05-03 | 2022-05-09 | Solar | 975 | 839D2 | OAKLAND | 839T1 | 2022-05-26 | Fail |  |  | Yes
81267 | 2022-05-03 | 2022-07-14 | Solar | 975 | 839D2 | OAKLAND | 839T1 | 2022-05-26 | Fail |  |  | Yes
81262 | 2022-05-02 | 2022-05-09 | Solar | 975 | 663D2 | SOUTH BERWICK | 663T1 | 2022-06-22 | Fail |  |  | Yes
81264 | 2022-05-02 | 2022-05-09 | Solar | 150 | 821D1 | GUILFORD | 821T1 | 2022-08-30 | Pass
81490 | 2022-04-30 | 2022-05-05 | Solar | 800 | 263D1 | BOWMAN STREET | 34kV BUS 2 | 2022-06-15 | Pass | Pass | 2022-08-16
81259 | 2022-04-29 | 2022-04-29 | Solar | 975 | 638D2 | NORTH LIMINGTON | 638T1 | 2022-07-06 | Fail |  |  | Yes
81260 | 2022-04-29 | 2022-05-05 | Solar | 650 | 861D9 | VASSALBORO | 861T1 | 2022-06-02 | Pass |  |  | Yes
81257 | 2022-04-28 | 2022-05-05 | Solar | 999 | 638D1 | NORTH LIMINGTON | 638T1 |  |  |  |  | Yes
81258 | 2022-04-28 | 2022-05-16 | Solar | 975 | 638D2 | NORTH LIMINGTON | 638T1 | 2022-07-06 | Fail |  |  | Yes
81223 | 2022-04-25 | 2022-04-25 | Other | 350 | 435D1 | NORWAY | 435T2 | 2022-07-21 | Pass
81222 | 2022-04-21 | 2022-04-29 | Solar | 975 | 663D2 | SOUTH BERWICK | 663T1 | 2022-07-06 | Fail |  |  | Yes
81170 | 2022-04-20 | 2022-04-27 | Solar | 750 | 695D2 | LEBANON | 695T1 | 2022-05-05 | Fail |  |  | Yes
81171 | 2022-04-20 | 2022-04-25 | Solar | 850 | 631D1 | LAMBERT STREET | 631T1 | 2022-07-08 | Fail | Pass | 2022-08-18
81179 | 2022-04-20 | 2022-04-27 | Solar | 750 | 695D2 | LEBANON | 695T1 | 2022-05-26 | Fail |  |  | Yes
81200 | 2022-04-20 | 2022-04-27 | Solar | 975 | 841D1 | PHILLIPS/STRONG | 841T1 | 2022-05-19 | Fail | Pass | 2022-07-21
81201 | 2022-04-20 | 2022-04-27 | Solar | 975 | 457D1 | MONMOUTH | 457T1 | 2022-05-17 | Fail | Pass | 2022-08-02
81203 | 2022-04-20 | 2022-04-27 | Solar | 975 | 841D1 | PHILLIPS/STRONG | 841T1 | 2022-05-18 | Fail |  |  | Yes
81132 | 2022-04-13 | 2022-04-15 | Solar | 172 | 874D1 | BELFAST 115 | 874T2 | 2022-05-27 | Pass |  |  | Yes
81130 | 2022-04-03 | 2022-04-15 | Solar | 975 | 225D4 | FREEPORT | 225T1 | 2022-06-02 | Fail | Pass | 2022-08-03 | Yes
81019 | 2022-03-30 | 2022-04-07 | Solar | 975 | 225D4 | FREEPORT | 225T1 | 2022-04-08 | Fail |  |  | Yes
81015 | 2022-03-29 | 2022-04-04 | Solar | 650 | 861D9 | VASSALBORO | 861T1 | 2022-04-28 | Fail |  |  | Yes
81016 | 2022-03-29 | 2022-04-04 | Solar | 280 | 865D5 | WEST WATERVILLE | 865T2 | 2022-05-17 | Fail | Pass | 2022-06-27
81017 | 2022-03-29 | 2022-04-07 | Solar | 500 | 444D2 | RAYMOND 34 KV | 444T1 | 2022-04-25 | Fail | Pass | 2022-08-12 | Yes
81006 | 2022-03-25 | 2022-04-21 | Solar | 475 | 239D10 | PARK STREET | 239T5 | 2022-05-19 | Pass |  |  | Yes
80962 | 2022-03-22 | 2022-03-22 | Solar | 975 | 244D2 | SOUTH CHINA | 244T1 | 2022-04-19 | Fail |  |  | Yes
80971 | 2022-03-22 | 2022-03-29 | Solar | 975 | 244D2 | SOUTH CHINA | 244T1 | 2022-04-29 | Fail | Pass | 2022-07-29 | Yes
80892 | 2022-03-21 | 2022-03-25 | Solar | 975 | 239D10 | PARK STREET | 239T5 | 2022-05-17 | Pass
80977 | 2022-03-21 | 2022-03-31 | Solar | 2000 | 457D2 | MONMOUTH | 457T2 | 2022-04-21 | Fail |  |  | Yes
80842 | 2022-03-02 | 2022-03-17 | Solar | 975 | 450D1 | SABATTUS | 450T1 | 2022-04-15 | Fail |  |  | Yes
80841 | 2022-03-01 | 2022-03-08 | Solar | 1990 | 801D1 | ANSON | 801T1 | 2022-03-29 | Fail |  |  | Yes
80838 | 2022-02-28 | 2022-03-17 | Solar | 1992 | 806D2 | BUCKSPORT | 806T3 | 2022-03-30 | Fail | Pass | 2022-06-25 | Yes
80825 | 2022-02-24 | 2022-03-09 | Solar | 1999 | 233D2 | MANCHESTER | 233T1 | 2022-03-30 | Fail | Fail | 2022-05-17 | Yes
80807 | 2022-02-16 | 2022-02-23 | Solar | 975 | 817D3 | FAIRFIELD | 817T1 | 2022-03-03 | Fail |  |  | Yes
80808 | 2022-02-16 | 2022-02-23 | Solar | 975 | 861D8 | VASSALBORO | 861T1 | 2022-03-29 | Fail | Fail | 2022-05-19 | Yes
80726 | 2022-02-04 | 2022-02-09 | Solar | 975 | 853D1 | SKOWHEGAN NORTH SIDE | 853T1 | 2022-03-28 | Fail |  |  | Yes
80727 | 2022-02-04 | 2022-02-09 | Solar | 975 | 874D1 | BELFAST 115 | 874T2 | 2022-03-07 | Fail |  |  | Yes
80728 | 2022-02-04 | 2022-02-10 | Solar | 975 | 428D3 | LIVERMORE FALLS | 428T1 | 2022-03-04 | Fail | Fail | 2022-06-03 | Yes
80736 | 2022-02-04 | 2022-02-10 | Solar | 975 | 420D7 | HOTEL ROAD | 420T1 | 2022-03-28 | Pass
80737 | 2022-02-04 | 2022-02-09 | Solar | 975 | 420D4 | HOTEL ROAD | 420T1 | 2022-03-03 | Fail |  |  | Yes
80725 | 2022-02-03 | 2022-02-09 | Solar | 975 | 866D2 | WESTON | 866T2 | 2022-02-11 | Fail |  |  | Yes
80701 | 2022-01-31 | 2022-02-04 | Solar | 1750 | 850D1 | SEARSPORT | 850T1 | 2022-02-10 | Fail | Fail | 2022-04-18 | Yes
80677 | 2022-01-26 | 2022-02-02 | Solar | 200 | 693D2 | SCARBOROUGH | 693T1 | 2022-04-06 | Fail | Pass | 2022-05-23
80667 | 2022-01-25 | 2022-02-01 | Solar | 499 | 420D7 | HOTEL ROAD | 420T1 | 2022-02-10 | Pass
80656 | 2022-01-20 | 2022-01-27 | Solar | 200 | 650D1 | RIGBY | 650T1 | 2022-02-17 | Pass |  |  | Yes
80658 | 2022-01-20 | 2022-01-27 | Solar | 436 | 650D1 | RIGBY | 650T1 | 2022-02-10 | Fail | Pass | 2022-06-06 | Yes
80659 | 2022-01-20 | 2022-01-27 | Solar | 516 | 650D1 | RIGBY | 650T1 | 2022-02-17 | Pass
80609 | 2022-01-13 | 2022-01-20 | Solar | 1999 | 263D1 | BOWMAN STREET | 34kV BUS 2 | 2022-01-21 | Fail | Pass | 2022-05-16 | Yes
80605 | 2022-01-12 | 2022-01-31 | Solar | 1500 | 412D4 | DEER RIPS | 412T4 | 2022-02-10 | Fail | Fail | 2022-05-12 | Yes
80585 | 2022-01-04 | 2022-01-11 | Solar | 1000 | 861D9 | VASSALBORO | 861T1 | 2022-01-21 | Fail | Pass | 2022-06-20 | Yes