## Level 2 Online Report
Project # | App Received | Customer Notified Application Complete | Facility Type | AC kW | Circuit | Substation | Substation Transformer | Tech Screen Completed | Tech Screen Results | ESA Results | ESA Completed | Withdrawn
111618 | 2026-07-30 |  | Solar | 70
111581 | 2026-07-27 | 2026-07-30 | Solar | 120 | 620D1 | ELM STREET | 620T2 |  | Pending
111528 | 2026-07-22 | 2026-07-29 | Solar | 38 | 657D3 | SANFORD SWITCH | 657T1 |  | Pending
111535 | 2026-07-22 |  | Battery | 210 | 688D1 | KITTERY | 688T1
111497 | 2026-07-20 | 2026-07-27 | Solar | 120 | 611D1 | BRIGHTON AVENUE | 611T1 |  | Pending
111409 | 2026-07-09 | 2026-07-14 | Solar | 100 | 623D1 | FOREST AVENUE | 623T1 |  | Pending
111416 | 2026-07-09 | 2026-07-21 | Solar | 27.3 | 605D2 | BIDDEFORD PUMPING STATION | 605T1 |  | Pending
111210 | 2026-06-16 | 2026-06-26 | Solar | 60 | 225D4 | FREEPORT | 225T1 | 2026-07-20 | Fail |  |  | Yes
111181 | 2026-06-11 | 2026-06-29 | Solar | 83.328 | 431D2 | MECHANIC FALLS | 431T1 | 2026-07-21 | Fail | Pending
111168 | 2026-06-09 | 2026-06-16 | Solar | 27.26 | 431D2 | MECHANIC FALLS | 431T1 | 2026-06-24 | Pass
111055 | 2026-06-01 | 2026-06-02 | Solar | 30 | 209D1 | BOOTHBAY HARBOR | 209T1 | 2026-06-25 | Pass
111005 | 2026-05-22 | 2026-05-27 | Solar | 27.264 | 215D5 | CAPITOL STREET | 215T1 | 2026-06-16 | Pass
110936 | 2026-05-15 | 2026-06-16 | Solar | 26.96 | 605D1 | BIDDEFORD PUMPING STATION | 605T1 | 2026-07-08 | Fail
110895 | 2026-05-12 | 2026-05-20 | Solar | 100 | 602D3 | BASSETT | 602T1 | 2026-06-15 | Fail | Fail | 2026-07-30 | Yes
110875 | 2026-05-08 | 2026-05-08 | Solar | 114 | 808D1 | CARMEL | 808T1 | 2026-05-12 | Pass
110876 | 2026-05-08 | 2026-05-08 | Solar | 114 | 808D1 | CARMEL | 808T1 | 2026-05-12 | Pass
110864 | 2026-05-07 | 2026-05-15 | Solar | 80 | 225D4 | FREEPORT | 225T1 | 2026-05-15 | Fail | Pass | 2026-07-23
110843 | 2026-05-05 | 2026-05-19 | Solar | 38 | 690D3 | HINCKLEY POND | 690T1 | 2026-06-08 | Fail | Pending
110844 | 2026-05-05 | 2026-05-19 | Solar | 34.2 | 450D2 | SABATTUS | 450T1 | 2026-06-08 | Pass
110785 | 2026-04-27 | 2026-04-30 | Solar | 30 | 471D2 | LEEDS | 471T1 | 2026-05-15 | Fail | Pass | 2026-07-01
110774 | 2026-04-24 | 2026-04-28 | Solar | 46 | 644D2 | PLEASANT HILL | 644T2 | 2026-05-14 | Fail | Pass | 2026-07-09
110753 | 2026-04-22 | 2026-05-04 | Solar | 240 | 213D3 | BRUNSWICK WEST SIDE | 213T1 | 2026-05-26 | Fail | Pass | 2026-07-21
110719 | 2026-04-15 | 2026-04-28 | Solar | 115.2 | 208D2 | BOND BROOK | 208T1 | 2026-04-28 | Fail | Pass | 2026-06-15
110630 | 2026-04-06 | 2026-04-09 | Solar | 27.648 | 817D2 | FAIRFIELD | 817T2 | 2026-04-30 | Pass
110558 | 2026-03-27 | 2026-03-27 | Solar | 34.6 | 858D4 | STURTEVANT | 858T2 | 2026-04-03 | Fail | Pass | 2026-05-08
110462 | 2026-03-19 | 2026-04-13 | Solar | 132 | 421D2 | CHALLENGER | 421T1 | 2026-04-13 | Fail | Pass | 2026-05-15
110452 | 2026-03-18 | 2026-04-13 | Solar | 228 | 808D1 | CARMEL | 808T1 | 2026-05-01 | Pass |  |  | Yes
110407 | 2026-03-13 | 2026-03-25 | Solar | 27.3 | 631D3 | LAMBERT STREET | 631T2 | 2026-04-13 | Fail | Pass | 2026-06-03
110410 | 2026-03-13 | 2026-03-25 | Solar | 27.3 | 631D3 | LAMBERT STREET | 631T2 | 2026-04-13 | Fail | Pass | 2026-06-03
110411 | 2026-03-13 | 2026-03-25 | Solar | 34.6 | 631D3 | LAMBERT STREET | 631T2 | 2026-04-13 | Fail | Pass | 2026-06-03
110415 | 2026-03-13 | 2026-03-25 | Solar | 34.6 | 631D3 | LAMBERT STREET | 631T2 | 2026-04-13 | Fail | Pass | 2026-06-02
110360 | 2026-03-08 | 2026-03-16 | Solar | 30.4 | 431D1 | MECHANIC FALLS | 431T2 | 2026-04-02 | Fail |  |  | Yes
110358 | 2026-03-07 | 2026-03-23 | Solar | 31.15 | 273D5 | BRUNSWICK HYDRO | 273T2 | 2026-04-13 | Pass
110245 | 2026-02-20 | 2026-02-24 | Solar | 84.6 | 865D5 | WEST WATERVILLE | 865T2 | 2026-02-24 | Fail | Pass | 2026-04-02
110068 | 2026-01-30 | 2026-02-03 | Solar | 38 | 800D1 | LINCOLNVILLE | 800T1 | 2026-02-24 | Fail
110025 | 2026-01-23 | 2026-02-10 | Solar | 90 | 421D2 | CHALLENGER | 421T1 | 2026-03-12 | Fail |  |  | Yes
110026 | 2026-01-23 | 2026-02-05 | Solar | 45.6 | 209D3 | BOOTHBAY HARBOR | 209T1 | 2026-02-24 | Fail | Pass | 2026-04-16
109934 | 2026-01-09 | 2026-01-23 | Solar | 999.6 | 821D3 | GUILFORD | 821T2 | 2026-02-09 | Fail | Pass | 2026-04-03
109924 | 2026-01-08 | 2026-01-20 | Solar | 40 | 218D1 | WILLIAM F WYMAN OUTSIDE | 218T13 | 2026-02-02 | Fail | Pass | 2026-05-06
109844 | 2025-12-30 | 2026-01-16 | Solar | 50 | 223D1 | EDGECOMB | 223T1 | 2026-02-09 | Fail | Pass | 2026-05-13
109833 | 2025-12-29 | 2026-01-08 | Solar | 999 | 818D1 | FARMINGTON FALLS | 818T1 | 2026-01-20 | Fail |  |  | Yes
109822 | 2025-12-26 | 2026-01-05 | Solar | 750 | 428D2 | LIVERMORE FALLS | 428T1 | 2026-01-20 | Fail | Fail | 2026-03-03 | Yes
109808 | 2025-12-23 | 2026-01-12 | Solar | 999 | 246D1 | THOMASTON CREEK | 34KV | 2026-02-02 | Fail | Pass | 2026-03-20
109788 | 2025-12-19 | 2026-02-09 | Solar | 375 | 639D2 | NORTH WINDHAM | 639T2 | 2026-03-03 | Fail | Pending
109782 | 2025-12-18 | 2025-12-31 | Solar | 152.16 | 225D3 | FREEPORT | 225T2 | 2026-01-12 | Fail | Pass | 2026-03-03
109728 | 2025-12-12 | 2025-12-17 | Solar | 220 | 674D2 | WESTBROOK | 674T1 | 2026-01-17 | Fail | Pass | 2026-02-03
109730 | 2025-12-12 | 2025-12-17 | Solar | 300 | 674D1 | WESTBROOK | 674T1 | 2026-01-07 | Pass
109731 | 2025-12-12 | 2025-12-17 | Solar | 240 | 674D1 | WESTBROOK | 674T1 | 2026-01-07 | Pass
109689 | 2025-12-10 | 2025-12-30 | Solar | 999 | 837D2 | NEWPORT | 837T2 | 2026-01-12 | Fail | Pass | 2026-03-10
109670 | 2025-12-09 |  | Solar | 750 | 842D1 | PITTSFIELD | 842T1 |  |  |  |  | Yes
109671 | 2025-12-09 |  | Solar | 249 | 842D1 | PITTSFIELD | 842T1 |  |  |  |  | Yes
109648 | 2025-12-07 |  | Solar | 452.2 | [7 empty] | Yes
109651 | 2025-12-07 | 2025-12-10 | Solar | 999 | 824D1 | HARTLAND | 824T1 | 2026-01-05 | Fail |  |  | Yes
109644 | 2025-12-05 | 2025-12-09 | Solar | 34.6 | 634D3 | MAY STREET | 634T2 | 2025-12-29 | Pass
109649 | 2025-12-05 | 2025-12-09 | Solar | 152.16 | 232D2 | LISBON FALLS | 232T2 | 2025-12-29 | Fail | Pass | 2026-02-24
109634 | 2025-12-03 | 2025-12-05 | Solar | 80 | 687D1 | ELIOT | 687T1 | 2025-12-29 | Pass
109624 | 2025-12-02 | 2025-12-05 | Solar | 975 | 624D2 | FORT HILL | 624T1 | 2026-01-07 | Fail | Pass | 2026-03-23
109626 | 2025-12-02 | 2025-12-09 | Solar | 999 | 272D6 | NORTH AUGUSTA | 272T2 | 2025-12-30 | Fail |  |  | Yes
109602 | 2025-12-01 | 2025-12-08 | Solar | 50 | 653D2 | FORE RIVER | 653T2 | 2025-12-31 | Pass
109500 | 2025-11-20 | 2025-11-25 | Solar | 600 | 219D1 | DAMARISCOTTA MILLS | 219T1 | 2025-12-11 | Fail | Pass | 2026-02-13
109467 | 2025-11-18 | 2025-11-19 | Solar | 995 | 691D1 | BALDWIN | 691T1 | 2025-12-03 | Fail | Pass | 2025-12-31
109452 | 2025-11-17 | 2025-11-18 | Solar | 50 | 690D2 | HINCKLEY POND | 690T1 | 2025-12-09 | Pass
109422 | 2025-11-13 | 2025-11-18 | Solar | 100 | 650D1 | RIGBY | 650T1 | 2025-12-09 | Fail | Pass | 2026-01-30
109427 | 2025-11-13 | 2025-11-18 | Solar | 200 | 239D7 | PARK STREET | 239T2 | 2025-12-03 | Fail | Pass | 2026-01-16
109429 | 2025-11-13 | 2025-12-03 | Solar | 400 | 420D4 | HOTEL ROAD | 420T1 | 2025-12-26 | Fail | Pending
109390 | 2025-11-11 | 2025-11-17 | Solar | 70 | 435D3 | NORWAY | 435T2 | 2025-12-08 | Fail | Pass | 2026-02-04
109400 | 2025-11-11 | 2025-12-03 | Solar | 99.4 | 621D2 | FACTORY ISLAND | 621T2 | 2025-12-24 | Fail | Pass | 2026-03-02
109286 | 2025-11-05 | 2025-11-10 | Solar | 160 | 214D2 | CAMDEN | 214T2 | 2025-12-01 | Fail | Pass | 2026-01-16
109280 | 2025-11-04 | 2025-11-10 | Solar | 84.6 | 865D5 | WEST WATERVILLE | 865T2 | 2025-11-24 | Fail | Pass | 2026-01-12 | Yes
109255 | 2025-11-03 | 2025-11-13 | Solar | 167 | 692D1 | HIRAM TAP | 692T1 | 2025-12-05 | Fail | Pass | 2026-01-27
109257 | 2025-11-03 | 2025-11-13 | Solar | 167 | 692D1 | HIRAM TAP | 692T1 | 2025-12-05 | Fail | Fail | 2026-01-27 | Yes
109155 | 2025-10-27 | 2025-11-04 | Solar | 250 | 620D1 | ELM STREET | 620T2 | 2025-11-24 | Fail | Pass | 2026-01-14
109160 | 2025-10-27 | 2025-10-30 | Solar | 995 | 824D2 | HARTLAND | 824T1 | 2025-11-05 | Fail | Fail | 2025-12-18 | Yes
109134 | 2025-10-24 | 2025-11-20 | Solar | 31.68 | 817D2 | FAIRFIELD | 817T2 | 2025-12-16 | Pass |  |  | Yes
109131 | 2025-10-23 | 2025-10-30 | Solar | 45.6 | 255D1 | WEST STREET | 255T1 | 2025-11-05 | Fail | Pass | 2026-01-23
109086 | 2025-10-22 | 2025-10-23 | Solar | 167 | 885D1 | WILTON | 885T1 | 2025-11-11 | Fail | Fail | 2026-01-07 | Yes
109090 | 2025-10-22 | 2025-11-18 | Solar | 27.3 | 635D2 | MOSHERS | 635T2 | 2025-12-09 | Fail |  |  | Yes
109107 | 2025-10-22 | 2025-10-24 | Solar | 167 | 240D1 | RICHMOND | 240T1 | 2025-11-05 | Fail | Pass | 2025-12-23
109110 | 2025-10-22 | 2025-10-24 | Solar | 167 | 240D1 | RICHMOND | 240T1 | 2025-11-05 | Fail | Pass | 2025-12-23
108994 | 2025-10-15 | 2025-10-17 | Solar | 167 | 803D6 | BELFAST WEST SIDE | 34.5 kV Bus | 2025-11-04 | Fail | Fail | 2025-12-23 | Yes
108995 | 2025-10-15 | 2025-10-17 | Solar | 167 | 803D6 | BELFAST WEST SIDE | 34.5 kV Bus | 2025-11-04 | Fail | Fail | 2025-12-23 | Yes
108997 | 2025-10-15 | 2025-10-29 | Solar | 50 | 416D2 | GRAY | 416T1 | 2025-11-11 | Fail | Pass | 2026-01-05
108963 | 2025-10-14 | 2025-10-22 | Solar | 975 | 807D1 | BURNHAM | 807T1 | 2025-11-05 | Fail | Fail | 2025-12-23 | Yes
108978 | 2025-10-14 | 2025-10-15 | Solar | 975 | 808D3 | CARMEL TAP | 808T1 off transmission | 2025-11-05 | Fail | Fail | 2025-12-15 | Yes
108982 | 2025-10-14 | 2025-10-22 | Solar | 975 | 457D2 | MONMOUTH | 457T2 | 2025-11-05 | Fail | Fail | 2025-12-17 | Yes
108984 | 2025-10-14 | 2025-10-22 | Solar | 975 | 252D2 | WALDOBORO | 252T1 | 2025-11-04 | Fail | Pass | 2025-12-22
108908 | 2025-10-13 | 2025-10-20 | Solar | 167 | 435D3 | NORWAY | 435T2 | 2025-11-10 | Fail | Pass | 2025-12-29
108947 | 2025-10-13 | 2025-10-15 | Solar | 996 | 813D3 | DEXTER | 813T2 | 2025-11-05 | Fail | Pass | 2026-01-07
108896 | 2025-10-10 | 2025-10-15 | Solar | 45.12 | 232D1 | LISBON FALLS | 232T1 | 2025-11-04 | Fail | Pass | 2026-01-07
108898 | 2025-10-10 | 2025-10-13 | Solar | 167 | 244D2 | SOUTH CHINA | 244T1 | 2025-11-04 | Fail | Pass | 2025-12-18
108900 | 2025-10-10 | 2025-10-13 | Solar | 167 | 244D2 | SOUTH CHINA | 244T1 | 2025-11-04 | Fail | Fail | 2025-12-18 | Yes
108903 | 2025-10-10 | 2025-10-14 | Solar | 167 | 803D6 | BELFAST WEST SIDE | 34.5 kV Bus | 2025-11-04 | Fail | Fail | 2025-12-16 | Yes
108904 | 2025-10-10 | 2025-10-14 | Solar | 167 | 803D6 | BELFAST WEST SIDE | 34.5 kV Bus | 2025-11-04 | Fail | Fail | 2025-12-16 | Yes
108907 | 2025-10-10 | 2025-10-14 | Solar | 167 | 435D3 | NORWAY | 435T2 | 2025-11-04 | Fail | Pass | 2025-12-23
108910 | 2025-10-10 | 2025-10-22 | Solar | 999 | 687D1 | ELIOT | 687T1 | 2025-11-13 | Fail | Pass | 2026-01-23
108892 | 2025-10-09 | 2025-10-15 | Solar | 975 | 262D1 | PUDDLEDOCK ROAD | 34 kV BUS 1 | 2025-11-05 | Fail | Pass | 2025-12-24
108857 | 2025-10-07 | 2025-10-08 | Solar | 975 | 219D2 | DAMARISCOTTA MILLS | 219T1 | 2025-10-30 | Fail | Pass | 2025-12-16
108804 | 2025-10-06 | 2025-10-09 | Solar | 999 | 824D2 | HARTLAND | 824T1 | 2025-10-31 | Fail | Fail | 2025-12-17 | Yes
108832 | 2025-10-06 | 2025-11-20 | Solar | 40 | 251D1 | UNION | 251T1 | 2025-12-16 | Fail | Fail | 2026-02-02 | Yes
108789 | 2025-10-03 | 2025-10-07 | Solar | 175 | 435D3 | NORWAY | 435T2 | 2025-10-29 | Fail | Pass | 2026-02-04
108790 | 2025-10-03 | 2025-10-08 | Solar | 999 | 208D2 | BOND BROOK | 208T1 | 2025-10-30 | Fail | Pass | 2025-12-30
108792 | 2025-10-03 | 2025-10-09 | Solar | 999 | 873D1 | COUNTY ROAD | 873T1 | 2025-10-31 | Fail | Pass | 2025-12-17
108794 | 2025-10-03 | 2025-10-09 | Solar | 999 | 252D1 | WALDOBORO | 252T1 | 2025-10-31 | Fail | Fail | 2025-12-24 | Yes
108795 | 2025-10-03 | 2025-10-08 | Solar | 999 | 818D1 | FARMINGTON FALLS | 818T1 | 2025-10-30 | Fail | Pass | 2025-12-30
108719 | 2025-09-29 | 2025-10-03 | Solar | 975 | 438D1 | PAPOOSE POND | Tap off of Transmission Line | 2025-10-27 | Fail | Pass | 2025-12-16
108721 | 2025-09-29 | 2025-10-01 | Solar | 975 | 824D1 | HARTLAND | 824T1 | 2025-10-20 | Fail | Fail | 2025-12-02 | Yes
108723 | 2025-09-29 | 2025-10-01 | Solar | 975 | 824D2 | HARTLAND | 824T1 | 2025-10-20 | Fail | Fail | 2025-12-02 | Yes
108725 | 2025-09-29 | 2025-10-01 | Solar | 999 | 818D1 | FARMINGTON FALLS | 818T1 | 2025-10-23 | Fail |  |  | Yes
108726 | 2025-09-29 | 2025-10-03 | Solar | 999 | 210D1 | BRISTOL | 210T1 | 2025-10-27 | Fail | Pass | 2025-12-17
108691 | 2025-09-26 | 2025-09-30 | Solar | 375 | 810D1 | CLINTON | 810T1 | 2025-10-20 | Fail |  |  | Yes
108639 | 2025-09-25 | 2025-09-29 | Solar | 995 | 815D2 | DOVER | 815T2 | 2025-10-21 | Fail | Fail | 2025-12-12 | Yes
108641 | 2025-09-25 | 2025-09-29 | Solar | 375 | 210D2 | BRISTOL | 210T1 | 2025-10-20 | Fail |  |  | Yes
108651 | 2025-09-25 | 2025-09-30 | Solar | 975 | 624D1 | FORT HILL | 624T1 | 2025-10-20 | Fail | Pass | 2025-12-09
108655 | 2025-09-25 | 2025-09-29 | Solar | 500 | 632D2 | LIMERICK | 632T1 | 2025-10-21 | Fail | Fail | 2025-12-17 | Yes
108606 | 2025-09-23 | 2025-09-30 | Solar | 30 | 250D2 | TOPSHAM | 250T2 | 2025-10-20 | Fail |  |  | Yes
108610 | 2025-09-23 | 2025-09-29 | Solar | 975 | 428D2 | LIVERMORE FALLS | 428T1 | 2025-10-21 | Fail | Fail | 2025-12-08 | Yes
108582 | 2025-09-22 | 2025-10-03 | Solar | 167 | 244D2 | SOUTH CHINA | 244T1 | 2025-10-20 | Fail | Pass | 2025-12-08
108583 | 2025-09-22 | 2025-10-03 | Solar | 167 | 244D2 | SOUTH CHINA | 244T1 | 2025-10-20 | Fail | Fail | 2025-12-08 | Yes
108584 | 2025-09-22 | 2025-10-03 | Solar | 167 | 244D2 | SOUTH CHINA | 244T1 | 2025-10-20 | Fail |  |  | Yes
108587 | 2025-09-22 | 2025-09-25 | Solar | 995 | 671D1 | WATERBORO | 671T1 | 2025-10-17 | Fail | Fail | 2025-12-08 | Yes
108600 | 2025-09-22 | 2025-09-29 | Solar | 975 | 866D2 | WESTON HYDRO | 866T2 | 2025-10-20 | Fail | Pass | 2025-12-02
108554 | 2025-09-18 | 2025-11-13 | Solar | 33.6 | 250D1 | TOPSHAM | 250T2 | 2025-12-02 | Fail | Pass | 2026-03-23
108564 | 2025-09-18 | 2025-09-25 | Solar | 152.16 | 225D3 | FREEPORT | 225T2 | 2025-10-21 | Fail |  |  | Yes
108522 | 2025-09-16 | 2025-09-25 | Solar | 80 | 656D3 | SANFORD INDUSTRIAL PARK | 656T1 | 2025-10-17 | Fail | Pass | 2025-12-24
108422 | 2025-09-09 | 2025-09-19 | Solar | 220 | 412D1 | DEER RIPS | 412T2 | 2025-10-01 | Fail | Pass | 2025-12-16
108396 | 2025-09-08 | 2025-09-11 | Solar | 975 | 837D2 | NEWPORT | 837T2 | 2025-10-01 | Fail | Pass | 2025-11-13
108355 | 2025-09-05 | 2025-09-10 | Solar | 999 | 885D1 | WILTON | 885T1 | 2025-09-23 | Fail | Pass | 2025-10-15
108345 | 2025-09-04 | 2025-09-08 | Solar | 995 | 457D3 | MONMOUTH | 457T2 | 2025-09-16 | Fail | Pass | 2025-10-09
108348 | 2025-09-04 | 2025-09-11 | Solar | 150 | 250D1 | TOPSHAM | 250T2 | 2025-10-01 | Fail | Pass | 2025-12-11
108318 | 2025-09-03 | 2025-10-06 | Solar | 167 | 810D1 | CLINTON | 810T1 | 2025-10-28 | Fail | Fail | 2025-12-16 | Yes
108297 | 2025-09-02 | 2025-10-03 | Solar | 167 | 400D1 | ANDOVER | 400T1 | 2025-10-27 | Fail | Pass | 2025-12-16
108305 | 2025-09-02 | 2025-10-03 | Solar | 167 | 400D1 | ANDOVER | 400T1 | 2025-10-27 | Fail | Pass | 2025-12-16
108306 | 2025-09-02 | 2025-09-11 | Solar | 30.378 | 631D2 | LAMBERT STREET | 631T1 | 2025-09-18 | Fail | Pass | 2025-11-05
108240 | 2025-08-28 | 2025-09-08 | Solar | 995 | 827D2 | ATHENS | 827T1 | 2025-09-16 | Fail | Fail | 2025-10-29 | Yes
108250 | 2025-08-28 | 2025-09-29 | Solar | 27.3 | 214D2 | CAMDEN | 214T2 | 2025-10-21 | Pass
108257 | 2025-08-28 | 2025-09-16 | Solar | 30 | 206D1 | BATH NORTH END | 206T1 |  |  |  |  | Yes
108275 | 2025-08-28 | 2025-09-10 | Solar | 996 | 461D1 | LUDDEN LANE | 461T1 | 2025-09-23 | Fail | Pass | 2026-01-13
108223 | 2025-08-27 | 2025-09-26 | Solar | 167 | 250D2 | TOPSHAM | 250T2 | 2025-10-20 | Fail | Fail | 2025-12-16 | Yes
108150 | 2025-08-21 | 2025-09-05 | Solar | 995.004 | 813D3 | DEXTER | 813T2 | 2025-09-19 | Fail | Pass | 2025-11-26
108102 | 2025-08-19 | 2025-09-08 | Solar | 38 | 214D3 | CAMDEN | 214T1 | 2025-09-29 | Fail | Pass | 2025-11-20
108079 | 2025-08-18 | 2025-08-27 | Solar | 43.392 | 215D3 | CAPITOL STREET | 215T2 | 2025-09-17 | Fail | Pass | 2025-10-08
108039 | 2025-08-15 | 2025-09-05 | Solar | 996 | 419D1 | HIRAM HYDRO | 419T3 | 2025-09-22 | Fail |  |  | Yes
107972 | 2025-08-11 | 2025-08-29 | Solar | 150 | 438D1 | PAPOOSE POND | Tap off of Transmission Line | 2025-09-22 | Fail | Pass | 2025-10-30
107976 | 2025-08-11 | 2025-09-04 | Solar | 150 | 438D1 | PAPOOSE POND | Tap off of Transmission Line | 2025-09-23 | Fail | Pass | 2025-11-13
107945 | 2025-08-08 | 2025-09-09 | Solar | 975 | 617D2 | DUNSTAN | 617T1 | 2025-09-24 | Fail | Pass | 2025-11-18
107951 | 2025-08-08 | 2025-08-15 | Solar | 91.2 | 217D3 | COOKS CORNER | 34KV BUS 1 | 2025-09-05 | Fail | Pass | 2025-10-27
107891 | 2025-08-06 | 2025-08-14 | Solar | 37.6 | 858D2 | STURTEVANT | 858T1 | 2025-09-09 | Pass
107844 | 2025-08-04 | 2025-09-15 | Solar | 33 | 252D2 | WALDOBORO | 252T1 | 2025-10-03 | Fail |  |  | Yes
107846 | 2025-08-04 | 2025-08-22 | Solar | 34.2 | 251D1 | UNION | 251T1 | 2025-09-15 | Fail |  |  | Yes
107848 | 2025-08-04 |  | Solar | 26.4 | [7 empty] | Yes
107918 | 2025-08-04 | 2025-08-13 | Solar | 37.6 | 622D2 | FALMOUTH | 622T1 | 2025-08-25 | Fail | Pass | 2025-10-16
107805 | 2025-08-01 | 2025-08-25 | Solar | 45.6 | 659D13 | SEWALL STREET | 659T1 | 2025-09-09 | Pass |  |  | Yes
107769 | 2025-07-31 | 2025-08-13 | Solar | 50 | 424D2 | LEWISTON LOWER | 424T1 | 2025-09-03 | Fail | Pass | 2025-11-24
107757 | 2025-07-30 | 2025-08-13 | Solar | 50 | 424D2 | LEWISTON LOWER | 424T1 | 2025-09-03 | Fail | Pass | 2025-11-24
107716 | 2025-07-29 | 2025-08-14 | Solar | 80 | 623D1 | FOREST AVENUE | 623T1 | 2025-09-04 | Pass
107718 | 2025-07-29 |  | Solar | 25.675 | [7 empty] | Yes
107656 | 2025-07-25 | 2025-08-14 | Solar | 999 | 626D5 | HIGH STREET | 626T2 | 2025-09-03 | Fail | Pass | 2025-10-22
107560 | 2025-07-21 | 2025-08-05 | Solar | 40 | 685D2 | BOLT HILL | 685T1 | 2025-08-26 | Fail | Pass | 2025-10-20
107549 | 2025-07-20 | 2025-07-25 | Solar | 995 | 691D1 | BALDWIN | 691T1 | 2025-08-15 | Fail | Fail | 2025-10-03 | Yes
107509 | 2025-07-18 | 2025-07-23 | Solar | 80 | 630D4 | GOOSEFARE | 630T1 | 2025-08-14 | Fail | Pass | 2025-10-07
107430 | 2025-07-15 | 2025-07-23 | Solar | 150 | 437D2 | OXFORD | 437T1 | 2025-08-12 | Fail | Fail | 2025-09-26 | Yes
107434 | 2025-07-15 | 2025-07-22 | Solar | 150 | 435D3 | NORWAY | 435T2 | 2025-08-12 | Fail | Pass | 2025-09-04
107347 | 2025-07-10 | 2025-07-16 | Solar | 975 | 262D1 | PUDDLEDOCK ROAD | 34 kV BUS 1 | 2025-07-30 | Fail | Pass | 2025-09-02
107361 | 2025-07-10 | 2025-08-06 | Solar | 998.9 | 256D1 | WINTHROP | 256T2 | 2025-08-25 | Fail | Fail | 2025-10-22 | Yes
107304 | 2025-07-08 | 2025-07-15 | Solar | 233 | 225D4 | FREEPORT | 225T1 | 2025-07-23 | Fail | Pass | 2025-11-12
107262 | 2025-07-04 | 2025-08-28 | Solar | 999 | 272D6 | NORTH AUGUSTA | 272T2 | 2025-09-18 | Fail | Fail | 2025-11-17 | Yes
107197 | 2025-06-27 | 2025-07-01 | Solar | 34.2 |  |  |  | 2025-07-23 | Fail |  |  | Yes
107163 | 2025-06-26 | 2025-07-01 | Solar | 300 | 424D2 | LEWISTON LOWER | 424T1 | 2025-07-23 | Pass
107183 | 2025-06-26 | 2025-07-07 | Solar | 30 | 854D1 | SKOWHEGAN SOUTH SIDE | 854T1 | 2025-07-28 | Fail | Pass | 2025-09-15 | Yes
107124 | 2025-06-24 | 2025-07-01 | Solar | 67.3 | 217D3 | COOKS CORNER | 34KV BUS 1 | 2025-07-23 | Pass
107146 | 2025-06-24 | 2025-07-17 | Solar | 900 | 461D1 | LUDDEN LANE | 461T1 | 2025-08-05 | Fail |  |  | Yes
107055 | 2025-06-18 | 2025-07-15 | Solar | 34.6 | 621D2 | FACTORY ISLAND | 621T2 | 2025-08-05 | Pass
107059 | 2025-06-18 | 2025-06-19 | Solar | 150 | 855D1 | SOUTH WATERVILLE | 855T1 | 2025-07-01 | Fail | Fail | 2025-09-12 | Yes
107068 | 2025-06-18 | 2025-06-30 | Solar | 150 | 400D1 | ANDOVER | 400T1 | 2025-07-21 | Fail | Fail | 2025-08-28 | Yes
107032 | 2025-06-17 | 2025-08-26 | Solar | 125.4 | 421D2 | CHALLENGER | 421T1 | 2025-09-16 | Fail | Pass | 2025-12-16 | Yes
107009 | 2025-06-14 | 2025-07-10 | Solar | 34.2 | 403D2 | BETHEL | 403T1 | 2025-08-20 | Pass
106959 | 2025-06-11 | 2025-06-17 | Solar | 150 | 400D1 | ANDOVER | 400T1 | 2025-06-25 | Fail | Fail | 2025-08-06 | Yes
106961 | 2025-06-11 | 2025-06-18 | Solar | 50 | 659D13 | SEWALL STREET | 659T1 | 2025-07-08 | Pass
106946 | 2025-06-10 | 2025-07-24 | Solar | 37.2 | 233D2 | MANCHESTER | 233T1 | 2025-08-12 | Fail | Pass | 2025-10-07
106867 | 2025-06-04 | 2025-06-09 | Solar | 999 | 885D1 | WILTON | 885T1 | 2025-06-20 | Fail | Fail | 2025-07-14 | Yes
106886 | 2025-06-04 | 2025-06-11 | Solar | 34.2 | 817D2 | FAIRFIELD | 817T2 | 2025-06-25 | Pass
106887 | 2025-06-04 | 2025-07-09 | Solar | 36 | 870D1 | WINSLOW | 870T4 | 2025-07-30 | Fail |  |  | Yes
106888 | 2025-06-04 | 2025-06-18 | Solar | 33.112 | 821D1 | GUILFORD | 821T1 | 2025-06-25 | Fail | Pass | 2025-11-03 | Yes
106789 | 2025-05-29 | 2025-06-03 | Solar | 999 | 632D2 | LIMERICK | 632T1 | 2025-06-24 | Fail | Fail | 2025-08-28 | Yes
106744 | 2025-05-27 | 2025-06-03 | Solar | 60 | 850D1 | SEARSPORT | 850T1 | 2025-06-24 | Fail | Pass | 2025-08-14
106748 | 2025-05-27 | 2025-06-03 | Solar | 60 | 850D1 | SEARSPORT | 850T1 | 2025-06-24 | Fail | Pass | 2025-08-14
106772 | 2025-05-27 | 2025-06-05 | Solar | 996 | 272D2 | NORTH AUGUSTA | 272T1 | 2025-06-20 | Fail | Pass | 2025-08-07
106723 | 2025-05-23 | 2025-06-20 | Solar | 30 | 858D4 | STURTEVANT | 858T2 | 2025-07-10 | Fail | Pass | 2025-08-19
106583 | 2025-05-22 | 2025-06-09 | Solar | 41.8 | 270D2 | MEADOW ROAD | 270T2 | 2025-06-24 | Fail | Pass | 2025-08-25
106698 | 2025-05-22 | 2025-05-30 | Solar | 975 | 435D3 | NORWAY | 435T2 | 2025-06-09 | Fail | Pass | 2025-07-11
106699 | 2025-05-22 | 2025-05-28 | Solar | 29.568 |  |  |  | 2025-06-06 | Fail |  |  | Yes
106654 | 2025-05-20 | 2025-06-03 | Solar | 999 | 415D2 | FRYEBURG | 415T1 | 2025-06-09 | Fail | Pass | 2025-07-25
106519 | 2025-05-09 | 2025-05-14 | Solar | 30 | 435D2 | NORWAY | 435T2 | 2025-05-27 | Pass
106484 | 2025-05-07 | 2025-05-21 | Solar | 975 | 857D1 | THORNDIKE TAP | 857T1 | 2025-06-04 | Fail | Pass | 2025-08-05
106487 | 2025-05-07 | 2025-05-14 | Solar | 59.292 | 617D2 | DUNSTAN | 617T1 | 2025-06-05 | Fail | Pass | 2025-07-29
106413 | 2025-05-02 | 2025-05-07 | Solar | 30 | 815D2 | DOVER | 815T2 | 2025-05-27 | Fail | Pass | 2025-08-07
106422 | 2025-05-02 | 2025-05-08 | Solar | 38.8 | 806D2 | BUCKSPORT | 806T3 | 2025-05-28 | Fail | Pass | 2025-07-16
106392 | 2025-04-30 | 2025-05-09 | Solar | 300 | 800D1 | LINCOLNVILLE | 800T1 | 2025-06-02 | Fail | Pass | 2025-08-27
106395 | 2025-04-30 | 2025-05-09 | Solar | 840 | 817D3 | FAIRFIELD | 817T1 | 2025-05-28 | Fail |  |  | Yes
106396 | 2025-04-30 | 2025-05-09 | Solar | 440 | 416D3 | GRAY | 416T1 | 2025-06-02 | Fail | Pass | 2025-08-26
106397 | 2025-04-30 | 2025-05-09 | Solar | 320 | 431D3 | MECHANIC FALLS | 431T2 | 2025-06-02 | Pass
106391 | 2025-04-29 | 2025-05-09 | Solar | 360 | 803D6 | BELFAST WEST SIDE | 34.5 kV Bus | 2025-06-02 | Fail | Pass | 2025-08-26
106348 | 2025-04-25 | 2025-05-02 | Solar | 67.3 | 623D1 | FOREST AVENUE | 623T1 | 2025-05-14 | Pass
106272 | 2025-04-22 | 2025-05-01 | Solar | 152 | 423D2 | KIMBALL ROAD | 423T2 | 2025-05-20 | Fail | Fail |  | Yes
106276 | 2025-04-22 | 2025-05-01 | Solar | 50 | 663D2 | SOUTH BERWICK | 663T1 | 2025-05-21 | Fail | Pass | 2025-06-27
106220 | 2025-04-18 | 2025-04-24 | Solar | 440 | 246D3 | THOMASTON CREEK | 246T1 | 2025-05-13 | Fail | Fail | 2025-08-26 | Yes
106226 | 2025-04-18 | 2025-04-24 | Solar | 160 | 803D6 | BELFAST WEST SIDE | 34.5 kV Bus | 2025-05-13 | Fail | Pass | 2025-08-14
106231 | 2025-04-18 | 2025-04-24 | Solar | 320 | 678D2 | BAR MILLS | 678T4 | 2025-05-14 | Fail |  |  | Yes
106234 | 2025-04-18 | 2025-04-24 | Solar | 160 | 873D1 | COUNTY ROAD | 873T1 | 2025-05-13 | Fail |  |  | Yes
106242 | 2025-04-18 | 2025-04-23 | Solar | 995 | 692D1 | HIRAM TAP | 692T1 | 2025-05-06 | Fail | Pass | 2025-07-07
106244 | 2025-04-18 | 2025-04-24 | Solar | 995 | 857D1 | THORNDIKE TAP | 857T1 | 2025-05-13 | Fail | Pass | 2025-07-07
106179 | 2025-04-16 | 2025-04-21 | Solar | 152 | 409D1 | PARIS TAP | 409T1 | 2025-05-05 | Fail | Pass | 2025-06-27
106155 | 2025-04-15 | 2025-04-22 | Solar | 50 | 256D2 | WINTHROP | 256T1 | 2025-05-12 | Fail | Pass | 2025-07-02
106128 | 2025-04-14 | 2025-04-17 | Solar | 875 | 428D3 | LIVERMORE FALLS | 428T1 | 2025-05-05 | Fail | Fail | 2025-07-02 | Yes
106048 | 2025-04-08 | 2025-04-15 | Solar | 153.6 | 208D2 | BOND BROOK | 208T1 | 2025-04-21 | Fail | Pass | 2025-06-04 | Yes
105982 | 2025-04-03 | 2025-05-02 | Solar | 999 | 610D2 | BONNY EAGLE | 610T4 | 2025-05-16 | Fail | Pass | 2025-07-02
105997 | 2025-04-03 | 2025-04-17 | Solar | 136.8 | 219D2 | DAMARISCOTTA MILLS | 219T1 | 2025-05-05 | Fail | Pass | 2025-06-26
105948 | 2025-04-01 | 2025-04-09 | Solar | 67.3 | 412D2 | DEER RIPS | 412T2 | 2025-04-11 | Pass
105865 | 2025-03-26 | 2025-03-31 | Solar | 999 | 885D1 | WILTON | 885T1 | 2025-04-04 | Fail | Fail | 2025-05-13 | Yes
105843 | 2025-03-25 | 2025-04-15 | Solar | 56.52 | 800D1 | LINCOLNVILLE | 800T1 | 2025-04-21 | Fail | Pass | 2025-06-17
105845 | 2025-03-25 | 2025-04-25 | Solar | 80 | 854D2 | SKOWHEGAN SOUTH SIDE | 854T1 | 2025-05-13 | Fail | Pass | 2025-07-02
105847 | 2025-03-25 | 2025-04-25 | Solar | 80 | 854D2 | SKOWHEGAN SOUTH SIDE | 854T1 | 2025-05-13 | Fail | Pass | 2025-07-03
105830 | 2025-03-24 | 2025-03-27 | Solar | 999 | 449D2 | RILEY | 449T1 | 2025-03-28 | Fail | Pass | 2025-06-20
105827 | 2025-03-21 | 2025-03-28 | Solar | 150 | 435D4 | NORWAY | 435T2 | 2025-04-04 | Fail | Pass | 2025-05-13
105796 | 2025-03-19 | 2025-03-27 | Solar | 999 | 238D1 | MESSINA | 238T1 | 2025-03-28 | Fail |  |  | Yes
105753 | 2025-03-17 | 2025-03-25 | Solar | 34.2 | 200D3 | AUGUSTA K5 | 200T1 | 2025-03-28 | Fail | Pass | 2025-04-15
105773 | 2025-03-17 | 2025-03-19 | Solar | 999 | 860D1 | UNITY | 860T1 | 2025-03-25 | Fail |  |  | Yes
105734 | 2025-03-14 | 2025-03-19 | Solar | 31.7 | 618D2 | EAST DEERING | 618T2 | 2025-03-25 | Pass
105711 | 2025-03-12 | 2025-03-19 | Solar | 999 | 853D1 | SKOWHEGAN NORTH SIDE | 853T1 | 2025-03-25 | Fail |  |  | Yes
105713 | 2025-03-12 | 2025-03-24 | Solar | 33.93 | 605D2 | BIDDEFORD PUMPING STATION | 605T1 | 2025-04-04 | Pass
105681 | 2025-03-11 | 2025-03-19 | Solar | 999 | 467D1 | TURNER TAP | 34KV Tap off of Transmission Line | 2025-03-25 | Fail | Pass | 2025-04-23
105657 | 2025-03-07 | 2025-03-18 | Solar | 40 | 860D1 | UNITY | 860T1 | 2025-03-18 | Fail | Pass | 2025-05-28
105660 | 2025-03-07 | 2025-03-17 | Solar | 995 | 806D1 | BUCKSPORT | 806T5 | 2025-03-18 | Fail | Pass | 2025-04-04
105641 | 2025-03-06 | 2025-03-17 | Solar | 995 | 837D2 | NEWPORT | 837T2 | 2025-03-18 | Fail | Pass | 2025-04-03
105649 | 2025-03-06 |  | Solar | 990 | [7 empty] | Yes
105591 | 2025-03-03 | 2025-03-21 | Solar | 30 | 219D2 | DAMARISCOTTA MILLS | 219T1 | 2025-03-25 | Fail | Pass | 2025-04-15
105594 | 2025-03-03 | 2025-03-14 | Solar | 30 | 219D2 | DAMARISCOTTA MILLS | 219T1 | 2025-03-17 | Fail | Pass | 2025-04-15
105547 | 2025-02-25 | 2025-03-11 | Solar | 999 | 815D2 | DOVER | 815T2 |  | Fail |  |  | Yes
105548 | 2025-02-25 | 2025-03-12 | Solar | 999 | 638D1 | NORTH LIMINGTON | 638T1 | 2025-03-12 | Fail |  |  | Yes
105549 | 2025-02-25 | 2025-03-12 | Solar | 999 | 602D2 | BASSETT | 602T1 | 2025-03-12 | Fail |  |  | Yes
105550 | 2025-02-25 | 2025-03-11 | Solar | 999 | 602D2 | BASSETT | 602T1 | 2025-03-11 | Fail |  |  | Yes
105551 | 2025-02-25 | 2025-03-11 | Solar | 999 | 818D1 | FARMINGTON FALLS | 818T1 | 2025-03-11 | Fail |  |  | Yes
105534 | 2025-02-24 | 2025-02-26 | Solar | 27.3 | 261D4 | BATH | 261T2 | 2025-02-28 | Fail | Pass | 2025-04-01
105521 | 2025-02-21 | 2025-03-07 | Solar | 999 | 842D1 | PITTSFIELD | 842T1 | 2025-03-11 | Fail | Pass | 2025-04-24
105523 | 2025-02-21 | 2025-03-07 | Solar | 999 | 885D1 | WILTON | 885T1 | 2025-03-11 | Fail | Fail | 2025-05-28 | Yes
105506 | 2025-02-20 | 2025-03-06 | Solar | 84.6 | 647D1 | PRIDES CORNER | 647T2 | 2025-03-07 | Fail | Pass | 2025-03-31
105500 | 2025-02-19 | 2025-02-24 | Solar | 975 | 431D1 | MECHANIC FALLS | 431T2 | 2025-02-28 | Fail | Pass | 2025-04-18 | Yes
105474 | 2025-02-17 | 2025-02-19 | Solar | 26.6 | 423D1 | KIMBALL ROAD | 423T2 | 2025-02-28 | Fail |  |  | Yes
105454 | 2025-02-14 | 2025-02-18 | Solar | 969.4 | 813D1 | DEXTER | 813T1 | 2025-02-21 | Fail | Fail | 2025-03-20 | Yes
105424 | 2025-02-13 | 2025-02-17 | Solar | 200 | 810D1 | CLINTON | 810T1 | 2025-02-21 | Fail | Fail | 2025-03-13 | Yes
105405 | 2025-02-11 | 2025-02-12 | Solar | 995 | 431D1 | MECHANIC FALLS | 431T2 | 2025-02-14 | Fail | Pass | 2025-04-16
105319 | 2025-02-04 | 2025-02-05 | Solar | 34.6 | 674D1 | WESTBROOK | 674T1 | 2025-02-06 | Pass
105215 | 2025-01-24 | 2025-01-28 | Solar | 152 | 423D2 | KIMBALL ROAD | 423T2 | 2025-01-31 | Fail | Fail | 2025-02-27 | Yes
105216 | 2025-01-24 | 2025-02-04 | Solar | 999 | 860D1 | UNITY | 860T1 | 2025-02-06 | Fail |  |  | Yes
105198 | 2025-01-23 | 2025-02-11 | Solar | 999 | 808D3 | CARMEL TAP | 808T1 off transmission | 2025-02-18 | Fail |  |  | Yes
105204 | 2025-01-23 | 2025-01-27 | Solar | 996 | 813D1 | DEXTER | 813T1 | 2025-01-31 | Fail | Fail | 2025-02-20 | Yes
105196 | 2025-01-22 | 2025-01-23 | Solar | 34.6 | 650D4 | RIGBY | 650T2 | 2025-01-24 | Fail | Pass | 2025-03-07
105148 | 2025-01-16 | 2025-01-20 | Solar | 75.6 | 214D3 | CAMDEN | 214T1 | 2025-01-24 | Fail | Pass | 2025-02-27
105156 | 2025-01-16 | 2025-01-29 | Solar | 57 | 687D1 | ELIOT | 687T1 | 2025-01-31 | Pass |  |  | Yes
105158 | 2025-01-16 | 2025-01-20 | Solar | 995 | 850D1 | SEARSPORT | 850T1 | 2025-01-24 | Fail | Pass | 2025-02-14
105134 | 2025-01-15 | 2025-01-23 | Solar | 200 | 675D2 | WESTERN AVENUE | 675T1 | 2025-01-24 | Pass |  |  | Yes
105120 | 2025-01-14 | 2025-01-20 | Solar | 141.84 | 253D1 | WARREN | 253T1 | 2025-01-24 | Fail | Fail | 2025-03-17 | Yes
105123 | 2025-01-14 | 2025-01-22 | Solar | 93.6 | 676D1 | YORK BEACH | 676T1 | 2025-01-27 | Pass
105126 | 2025-01-14 | 2025-02-03 | Solar | 975 | 272D4 | NORTH AUGUSTA | 272T1 | 2025-02-06 | Fail | Pass | 2025-03-20
105085 | 2025-01-10 | 2025-01-16 | Solar | 43.2 | 693D1 | SCARBOROUGH | 693T1 | 2025-01-17 | Fail | Pass | 2025-03-07
105055 | 2025-01-08 | 2025-01-27 | Solar | 975 | 873D1 | COUNTY ROAD | 873T1 | 2025-02-03 | Fail |  |  | Yes
104986 | 2025-01-02 | 2025-01-10 | Solar | 30.8 | 217D3 | COOKS CORNER | 34KV BUS 1 | 2025-01-13 | Fail | Pass | 2025-02-14
104989 | 2025-01-02 | 2025-01-03 | Solar | 152 | 409D1 | PARIS TAP | 409T1 | 2025-01-03 | Fail | Fail | 2025-01-24 | Yes
104942 | 2024-12-20 |  | Solar | 152 | [7 empty] | Yes
104944 | 2024-12-20 | 2024-12-23 | Solar | 152 | 423D2 | KIMBALL ROAD | 423T2 | 2024-12-30 | Fail | Pass | 2025-01-22
104916 | 2024-12-18 | 2024-12-31 | Solar | 220 | 239D7 | PARK STREET | 239T2 | 2025-01-03 | Fail | Pass | 2025-01-30
104902 | 2024-12-17 | 2024-12-31 | Solar | 200 | 246D3 | THOMASTON CREEK | 246T1 | 2025-01-03 | Fail | Pass | 2025-02-11
104903 | 2024-12-17 | 2024-12-24 | Solar | 240 | 239D6 | PARK STREET | 239T2 | 2025-01-03 | Fail | Pass | 2025-02-19 | Yes
104904 | 2024-12-17 | 2024-12-31 | Solar | 100 | 239D5 | PARK STREET | 239T4 | 2025-01-03 | Fail | Pass | 2025-01-29
104874 | 2024-12-13 | 2024-12-18 | Solar | 40 | 435D3 | NORWAY | 435T2 | 2024-12-18 | Fail | Pass | 2025-01-08
104875 | 2024-12-13 | 2024-12-17 | Solar | 40 | 435D3 | NORWAY | 435T2 | 2024-12-18 | Fail | Pass | 2025-01-08
104846 | 2024-12-11 | 2024-12-27 | Solar | 34.2 | 639D3 | NORTH WINDHAM | 639T2 | 2024-12-27 | Fail | Pass | 2025-01-31
104849 | 2024-12-11 | 2024-12-27 | Solar | 25.2 | 250D1 | TOPSHAM | 250T2 | 2024-12-27 | Fail | Pass | 2025-03-06
104820 | 2024-12-10 | 2024-12-13 | Solar | 27.6 | 806D2 | BUCKSPORT | 806T3 | 2024-12-16 | Fail |  |  | Yes
104822 | 2024-12-10 | 2024-12-12 | Solar | 995 | 467D1 | TURNER TAP | 34KV Tap off of Transmission Line | 2024-12-18 | Fail | Pass | 2025-01-14
104646 | 2024-11-22 | 2024-11-25 | Solar | 37.2 | 219D2 | DAMARISCOTTA MILLS | 219T1 | 2024-11-26 | Fail | Pass | 2024-12-13
104658 | 2024-11-22 | 2024-12-13 | Solar | 680 | 674D1 | WESTBROOK | 674T1 | 2024-12-16 | Fail | Pass | 2025-02-06 | Yes
104659 | 2024-11-22 | 2024-12-13 | Solar | 400 | 674D1 | WESTBROOK | 674T1 | 2024-12-16 | Fail | Pass | 2025-05-29 | Yes
104661 | 2024-11-22 | 2024-12-17 | Solar | 600 | 232D2 | LISBON FALLS | 232T2 | 2024-12-18 | Fail | Pass | 2025-01-06
104636 | 2024-11-21 | 2024-12-13 | Solar | 150 | 647D2 | PRIDES CORNER | 647T2 | 2024-12-16 | Pass
104638 | 2024-11-21 | 2024-12-13 | Solar | 240 | 674D2 | WESTBROOK | 674T1 | 2024-12-16 | Fail | Pass | 2025-02-06 | Yes
104609 | 2024-11-20 | 2024-11-25 | Solar | 995 | 813D1 | DEXTER | 813T1 | 2024-11-26 | Fail |  |  | Yes
104613 | 2024-11-20 | 2024-11-25 | Solar | 999 | 431D1 | MECHANIC FALLS | 431T2 | 2024-11-26 | Fail | Fail | 2025-01-02 | Yes
104553 | 2024-11-15 | 2024-12-03 | Solar | 990 | 603D2 | BERWICK | 603T1 | 2024-12-03 | Fail | Pass | 2025-04-08 | Yes
104515 | 2024-11-13 | 2024-11-13 | Solar | 60 | 803D3 | BELFAST WEST SIDE | 803T2 | 2024-11-14 | Fail | Pass | 2024-12-16
104517 | 2024-11-13 | 2024-11-21 | Solar | 999 | 428D2 | LIVERMORE FALLS | 428T1 | 2024-11-21 | Fail | Pass | 2024-12-09
104498 | 2024-11-12 |  | Solar | 265.05 | [7 empty] | Yes
104424 | 2024-11-05 | 2024-11-13 | Solar | 995 | 885D1 | WILTON | 885T1 | 2024-11-13 | Fail | Pass | 2025-01-23
104283 | 2024-10-24 | 2024-11-15 | Solar | 30.72 | 451D2 | MIDDLE STREET | 451T2 | 2024-11-19 | Pass
104271 | 2024-10-23 | 2024-10-24 | Solar | 984.85 | 874D1 | BELFAST 115 | 874T2 | 2024-10-25 | Fail | Pass | 2024-11-12
104273 | 2024-10-23 | 2024-10-24 | Solar | 995 | 858D3 | STURTEVANT | 858T2 | 2024-10-25 | Fail | Pass | 2024-11-12
104262 | 2024-10-22 | 2024-11-05 | Solar | 999 | 850D2 | SEARSPORT | 850T1 | 2024-11-06 | Fail |  |  | Yes
104264 | 2024-10-22 | 2024-11-26 | Solar | 999 | 815D2 | DOVER | 815T2 | 2024-11-26 | Fail |  |  | Yes
104167 | 2024-10-15 | 2024-10-21 | Solar | 990 | 208D1 | BOND BROOK | 208T1 | 2024-10-22 | Fail | Pass | 2024-11-04
104121 | 2024-10-11 | 2024-10-11 | Solar | 37.6 | 850D1 | SEARSPORT | 850T1 | 2024-10-14 | Fail | Pass | 2024-10-28
104133 | 2024-10-11 | 2024-10-16 | Solar | 40 | 803D4 | BELFAST WEST SIDE | 803T1 | 2024-10-16 | Fail | Pass | 2024-11-11
104001 | 2024-10-02 | 2024-11-04 | Solar | 30 | 610D2 | BONNY EAGLE | 610T4 | 2024-11-05 | Pass
103994 | 2024-10-01 | 2024-10-18 | Solar | 29.6 | 837D1 | NEWPORT | 837T1 | 2024-10-21 | Fail | Pass | 2024-11-04
103912 | 2024-09-25 | 2024-09-25 | Solar | 153.6 | 219D2 | DAMARISCOTTA MILLS | 219T1 | 2024-09-26 | Fail | Pass | 2024-10-28
103900 | 2024-09-24 | 2024-09-25 | Solar | 38 | 860D2 | UNITY | 860T1 | 2024-09-26 | Fail | Pass | 2025-01-16
103885 | 2024-09-23 | 2024-10-01 | Solar | 975 | 624D2 | FORT HILL | 624T1 | 2024-10-02 | Fail |  |  | Yes
103844 | 2024-09-19 | 2024-09-24 | Solar | 975 | 272D4 | NORTH AUGUSTA | 272T1 | 2024-09-24 | Fail | Pass | 2024-10-17 | Yes
103822 | 2024-09-18 | 2024-09-30 | Solar | 34.6 | 611D3 | BRIGHTON AVENUE | 611T1 | 2024-10-02 | Pass
103812 | 2024-09-17 | 2024-09-27 | Solar | 44.6 | 120D1 | BANGOR HYDRO (EMERA) | Not Applicable | 2024-10-04 | Fail | Pass | 2024-11-22 | Yes
103741 | 2024-09-11 | 2024-09-17 | Solar | 45.6 | 416D3 | GRAY | 416T1 | 2024-09-17 | Pass
103708 | 2024-09-07 | 2024-09-19 | Solar | 50.11 | 607D5 | BISHOP STREET | 607T2 | 2024-10-03 | Pass
103692 | 2024-09-06 | 2024-09-10 | Solar | 40 | 435D3 | NORWAY | 435T2 | 2024-09-11 | Fail |  |  | Yes
103677 | 2024-09-05 | 2024-09-05 | Solar | 100 | 803D6 | BELFAST WEST SIDE | 34.5 kV Bus | 2024-09-10 | Fail | Pass | 2024-10-15
103683 | 2024-09-05 | 2024-09-10 | Solar | 40 | 435D3 | NORWAY | 435T2 | 2024-09-11 | Fail |  |  | Yes
103608 | 2024-08-30 |  | Solar | 4999 | [7 empty] | Yes
103599 | 2024-08-29 | 2024-09-16 | Solar | 999.6 | 842D1 | PITTSFIELD | 842T1 | 2024-09-16 | Fail | Pass | 2024-10-11
103560 | 2024-08-28 | 2024-09-04 | Solar | 45.6 | 207D2 | BLAIR ROAD | 207T1 | 2024-09-09 | Fail | Pass | 2024-10-03
103367 | 2024-08-14 | 2024-08-15 | Solar | 995 | 242D1 | SIDNEY | 242T1 | 2024-08-16 | Fail | Pass | 2024-09-25
103285 | 2024-08-06 | 2024-08-13 | Solar | 540 | 647D1 | PRIDES CORNER | 647T2 | 2024-08-13 | Fail | Pass | 2024-09-12
103291 | 2024-08-06 | 2024-08-16 | Solar | 125 | 647D1 | PRIDES CORNER | 647T2 | 2024-08-22 | Fail | Pass | 2024-09-16
103293 | 2024-08-06 | 2024-08-16 | Solar | 150 | 647D1 | PRIDES CORNER | 647T2 | 2024-08-22 | Fail | Pass | 2024-09-16
103196 | 2024-07-31 | 2024-08-14 | Solar | 80 | 232D1 | LISBON FALLS | 232T1 | 2024-08-16 | Fail | Pass | 2024-09-19
103125 | 2024-07-30 | 2024-08-06 | Solar | 994 | 454D1 | TURNER | 454T1 | 2024-08-07 | Fail | Pass | 2024-09-16 | Yes
103042 | 2024-07-24 | 2024-08-12 | Solar | 975 | 207D2 | BLAIR ROAD | 207T1 | 2024-08-13 | Fail | Fail | 2024-09-30 | Yes
103014 | 2024-07-23 | 2024-07-25 | Solar | 50 | 647D1 | PRIDES CORNER | 647T2 | 2024-07-26 |  |  |  | Yes
103016 | 2024-07-23 | 2024-07-25 | Solar | 75 | 647D1 | PRIDES CORNER | 647T2 | 2024-07-26 |  |  |  | Yes
103017 | 2024-07-23 | 2024-07-25 | Solar | 50 | 647D1 | PRIDES CORNER | 647T2 | 2024-07-26 |  |  |  | Yes
103019 | 2024-07-23 |  | Solar | 75 | [7 empty] | Yes
103021 | 2024-07-23 |  | Solar | 50 | [7 empty] | Yes
103022 | 2024-07-23 |  | Solar | 480 | [7 empty] | Yes
103024 | 2024-07-23 | 2024-07-26 | Solar | 480 | 437D1 | OXFORD | 437T1 | 2024-07-29 | Fail | Fail | 2024-08-12 | Yes
103027 | 2024-07-23 |  | Solar | 150 | 437D1 | OXFORD | 437T1 |  |  |  |  | Yes
103028 | 2024-07-23 |  | Solar | 72 | [7 empty] | Yes
103030 | 2024-07-23 | 2024-07-26 | Solar | 420 | 216D2 | CONY ROAD | 216T1 | 2024-07-29 | Fail | Fail | 2024-08-23 | Yes
102997 | 2024-07-22 | 2024-07-25 | Solar | 50 | 837D2 | NEWPORT | 837T2 | 2024-07-26 | Fail | Pass | 2024-09-06
102960 | 2024-07-18 | 2024-08-05 | Solar | 34.2 | 406D2 | BRIDGTON | 406T1 | 2024-08-07 | Pass
102896 | 2024-07-12 | 2024-07-30 | Solar | 975 | 634D1 | MAY STREET | 634T1 | 2024-08-16 | Fail | Fail | 2024-10-02 | Yes
102852 | 2024-07-11 | 2024-07-18 | Solar | 390 | 605D1 | BIDDEFORD PUMPING STATION | 605T1 | 2024-07-26 | Fail | Pass | 2024-08-28
102789 | 2024-07-08 | 2024-07-08 | Solar | 145.152 | 685D1 | BOLT HILL | 685T1 | 2024-07-10 | Pass
102756 | 2024-07-02 | 2024-07-10 | Solar | 995 | 874D1 | BELFAST 115 | 874T2 | 2024-07-12 | Fail | Fail | 2024-09-03 | Yes
102732 | 2024-07-01 | 2024-07-02 | Solar | 150 | 239D6 | PARK STREET | 239T2 | 2024-07-09 | Fail | Pass | 2024-08-05
102742 | 2024-07-01 | 2024-07-02 | Solar | 200 | 630D2 | GOOSEFARE | 630T1 | 2024-07-03 | Fail | Pass | 2024-08-06
102743 | 2024-07-01 |  | Solar | 50 | [7 empty] | Yes
102747 | 2024-07-01 | 2024-07-02 | Solar | 50 | 647D1 | PRIDES CORNER | 647T2 | 2024-07-08 | Fail | Pass | 2024-08-05
102748 | 2024-07-01 |  | Solar | 50 | [7 empty] | Yes
102659 | 2024-06-25 | 2024-06-26 | Solar | 975 | 810D1 | CLINTON | 810T1 | 2024-06-27 | Fail | Fail | 2024-08-12 | Yes
102613 | 2024-06-24 | 2024-06-26 | Solar | 720 | 656D1 | SANFORD INDUSTRIAL PARK | 656T1 | 2024-07-12 | Fail | Pass | 2024-08-28
102614 | 2024-06-24 | 2024-06-26 | Solar | 360 | 644D1 | PLEASANT HILL | 644T2 | 2024-06-28 | Pass
102616 | 2024-06-24 | 2024-06-28 | Solar | 660 | 635D2 | MOSHERS | 635T2 | 2024-07-02 | Fail | Pass | 2024-08-01
102617 | 2024-06-24 | 2024-06-28 | Solar | 100 | 693D2 | SCARBOROUGH | 693T1 | 2024-07-02 | Pass
102619 | 2024-06-24 | 2024-06-28 | Solar | 200 | 693D2 | SCARBOROUGH | 693T1 | 2024-07-02 | Pass
102620 | 2024-06-24 | 2024-06-28 | Solar | 50 | 693D2 | SCARBOROUGH | 693T1 | 2024-07-02 | Pass
102622 | 2024-06-24 | 2024-06-28 | Solar | 150 | 630D1 | GOOSEFARE | 630T1 | 2024-07-02 | Pass
102629 | 2024-06-24 | 2024-06-26 | Solar | 50 | 415D2 | FRYEBURG | 415T1 | 2024-06-26 | Fail | Pass | 2024-08-08
102552 | 2024-06-18 | 2024-06-25 | Solar | 50 | 650D4 | RIGBY | 650T2 | 2024-06-28 | Fail | Pass | 2024-07-23
102553 | 2024-06-18 | 2024-07-01 | Solar | 34.6 | 690D2 | HINCKLEY POND | 690T1 | 2024-07-02 | Pass
102492 | 2024-06-13 |  | Solar | 996 | [7 empty] | Yes
102467 | 2024-06-12 | 2024-06-17 | Solar | 34.2 | 685D2 | BOLT HILL | 685T1 | 2024-07-10 | Fail | Pass | 2024-08-28
102439 | 2024-06-10 | 2024-06-13 | Solar | 280 | 213D3 | BRUNSWICK WEST SIDE | 213T1 | 2024-06-24 | Pass |  |  | Yes
102349 | 2024-06-05 |  | Solar | 37.6 | 685D2 | BOLT HILL | 685T1 |  |  |  |  | Yes
102350 | 2024-06-05 |  | Solar | 27.6 | 685D2 | BOLT HILL | 685T1 |  |  |  |  | Yes
102351 | 2024-06-05 |  | Solar | 27.6 | 685D2 | BOLT HILL | 685T1 |  |  |  |  | Yes
102352 | 2024-06-05 |  | Solar | 37.6 | 685D2 | BOLT HILL | 685T1 |  |  |  |  | Yes
102358 | 2024-06-05 |  | Solar | 25.2 | 685D2 | BOLT HILL | 685T1 |  |  |  |  | Yes
102359 | 2024-06-05 |  | Solar | 27.6 | 685D2 | BOLT HILL | 685T1 |  |  |  |  | Yes
102360 | 2024-06-05 |  | Solar | 37.6 | 685D2 | BOLT HILL | 685T1 |  |  |  |  | Yes
102362 | 2024-06-05 |  | Solar | 27.6 | 685D2 | BOLT HILL | 685T1 |  |  |  |  | Yes
102364 | 2024-06-05 |  |  | 27.6 | 685D2 | BOLT HILL | 685T1 |  |  |  |  | Yes
102365 | 2024-06-05 |  | Solar | 27.6 | 685D2 | BOLT HILL | 685T1 |  |  |  |  | Yes
102366 | 2024-06-05 |  | Solar | 37.6 | 685D2 | BOLT HILL | 685T1 |  |  |  |  | Yes
102368 | 2024-06-05 |  | Solar | 27.6 | 685D2 | BOLT HILL | 685T1 |  |  |  |  | Yes
102369 | 2024-06-05 |  | Solar | 33.8 | 685D2 | BOLT HILL | 685T1 |  |  |  |  | Yes
102371 | 2024-06-05 |  | Solar | 31.4 | 685D2 | BOLT HILL | 685T1 |  |  |  |  | Yes
102372 | 2024-06-05 |  | Solar | 31.4 | 685D2 | BOLT HILL | 685T1 |  |  |  |  | Yes
102340 | 2024-06-04 | 2024-07-10 | Solar | 160 | 213D3 | BRUNSWICK WEST SIDE | 213T1 | 2024-07-12 | Fail | Pass | 2024-08-09
102272 | 2024-05-30 | 2024-06-12 | Solar | 975 | 450D1 | SABATTUS | 450T1 | 2024-06-13 | Pass | Pass | 2024-07-15 | Yes
102254 | 2024-05-29 |  | Solar | 30 | 685D2 | BOLT HILL | 685T1 |  |  |  |  | Yes
102255 | 2024-05-29 |  | Solar | 30 | 685D2 | BOLT HILL | 685T1 |  |  |  |  | Yes
102257 | 2024-05-29 |  | Solar | 37.6 | 685D2 | BOLT HILL | 685T1 |  |  |  |  | Yes
102240 | 2024-05-28 | 2024-06-11 | Solar | 30.4 | 663D2 | SOUTH BERWICK | 663T1 | 2024-07-03 | Fail | Pass | 2024-08-06
102178 | 2024-05-23 | 2024-05-29 | Solar/Battery | 996 | 444D3 | RAYMOND 34 KV | 444T1 | 2024-06-03 | Fail |  |  | Yes
102153 | 2024-05-22 | 2024-06-04 | Solar | 600 | 854D2 | SKOWHEGAN SOUTH SIDE | 854T1 | 2024-06-07 | Fail |  |  | Yes
102149 | 2024-05-21 | 2024-05-21 | Solar | 152 | 435D4 | NORWAY | 435T2 | 2024-05-22 | Fail | Pass | 2024-07-10
102120 | 2024-05-20 | 2024-05-20 | Solar | 38 | 650D4 | RIGBY | 650T2 | 2024-05-21 | Fail | Pass | 2024-06-21
102106 | 2024-05-17 | 2024-06-25 | Solar | 76.46 | 457D2 | MONMOUTH | 457T2 | 2024-06-27 | Fail |  |  | Yes
102032 | 2024-05-13 | 2024-05-13 | Solar | 25.986 | 633D1 | LOUDEN | 633T3 | 2024-05-20 | Fail | Pass | 2024-07-17
102000 | 2024-05-10 | 2024-05-22 | Wind | 225 | 806D2 | BUCKSPORT | 806T3 | 2024-05-31 | Fail | Pass | 2024-07-09
102005 | 2024-05-10 | 2024-05-23 | Solar | 999 | 263D1 | BOWMAN STREET | 34 kV BUS 2 | 2024-05-29 | Fail |  |  | Yes
101853 | 2024-04-30 | 2024-05-03 | Solar | 27.3 | 451D8 | MIDDLE STREET | 451T2 | 2024-05-08 | Pass
101855 | 2024-04-30 | 2024-05-01 | Solar | 84.6 | 451D8 | MIDDLE STREET | 451T2 | 2024-05-07 | Pass
101835 | 2024-04-29 | 2024-05-20 | Solar | 67.3 | 412D1 | DEER RIPS | 412T2 | 2024-05-21 | Fail | Pass | 2024-07-09
101765 | 2024-04-23 | 2024-05-15 | Solar | 999 | 821D3 | GUILFORD | 821T2 | 2024-05-28 | Fail | Pass | 2024-07-10 | Yes
101752 | 2024-04-22 | 2024-05-09 | Solar | 67.127 | 647D3 | PRIDES CORNER | 647T2 | 2024-05-17 | Pass
101733 | 2024-04-19 | 2024-05-01 | Solar | 67.3 | 630D1 | GOOSEFARE | 630T1 | 2024-05-09 | Pass
101713 | 2024-04-18 | 2024-05-07 | Solar | 975 | 674D2 | WESTBROOK | 674T1 | 2024-05-17 | Fail |  |  | Yes
101717 | 2024-04-18 | 2024-04-19 | Solar | 975 | 226D2 | GARDINER | 226T1 | 2024-04-22 | Fail | Pass | 2024-05-20
101658 | 2024-04-12 | 2024-04-18 | Solar | 153.6 | 219D2 | DAMARISCOTTA MILLS | 219T1 | 2024-05-08 | Fail |  |  | Yes
101603 | 2024-04-08 | 2024-04-17 | Solar | 250 | 412D4 | DEER RIPS | 412T4 | 2024-04-25 | Fail | Pass | 2024-06-24 | Yes
101605 | 2024-04-08 | 2024-04-09 | Solar | 34.2 | 214D1 | CAMDEN | 214T2 | 2024-04-12 | Fail | Pass | 2024-05-15
101569 | 2024-04-04 | 2024-04-23 | Solar | 999 | 602D3 | BASSETT | 602T1 | 2024-05-09 | Fail | Pass | 2024-06-28
101560 | 2024-04-03 | 2024-04-18 | Solar | 34.2 | 633D1 | LOUDEN | 633T3 | 2024-05-09 | Fail | Pass | 2024-07-15
101528 | 2024-04-01 | 2024-04-12 | Solar | 999 | 431D1 | MECHANIC FALLS | 431T2 | 2024-04-22 | Fail | Fail | 2024-06-19 | Yes
101501 | 2024-03-28 | 2024-04-02 | Solar | 45.6 | 447D4 | RUMFORD | 447T3 | 2024-04-03 | Fail | Pass | 2024-05-13
101504 | 2024-03-28 | 2024-04-02 | Solar | 999 | 252D1 | WALDOBORO | 252T1 | 2024-04-05 | Fail | Fail | 2024-05-21 | Yes
101442 | 2024-03-24 | 2024-04-01 | Solar | 41.4 | 837D1 | NEWPORT | 837T1 | 2024-04-02 | Fail | Pass | 2024-05-13
101353 | 2024-03-18 | 2024-03-25 | Solar | 120 | 630D1 | GOOSEFARE | 630T1 | 2024-04-12 | Pass
101333 | 2024-03-14 |  | Solar | 150 | 403D1 | BETHEL | 403T1 |  |  |  |  | Yes
101334 | 2024-03-14 |  | Solar | 200 | 858D2 | STURTEVANT | 858T1 |  |  |  |  | Yes
101262 | 2024-03-08 | 2024-03-14 | Solar | 152 | 423D2 | KIMBALL ROAD | 423T2 | 2024-03-18 | Fail | Pass | 2024-04-30
101264 | 2024-03-08 | 2024-03-12 | Solar | 40 | 803D3 | BELFAST WEST SIDE | 803T2 | 2024-03-18 | Fail | Pass | 2024-04-30
101251 | 2024-03-07 | 2024-03-08 | Solar | 780 | 612D1 | BUTLER'S CORNER | 612T1 | 2024-03-27 | Fail | Fail | 2024-05-21 | Yes
101211 | 2024-03-04 | 2024-03-15 | Solar | 34.2 | 860D1 | UNITY | 860T1 | 2024-03-15 | Fail | Pass | 2024-04-26
101145 | 2024-02-27 | 2024-02-28 | Solar | 999 | 457D2 | MONMOUTH | 457T2 | 2024-03-01 | Fail | Pass | 2024-04-23
101131 | 2024-02-26 | 2024-02-29 | Solar | 999 | 447D4 | RUMFORD | 447T3 | 2024-03-01 | Fail | Fail | 2024-05-01 | Yes
101137 | 2024-02-26 | 2024-03-08 | Solar | 975 | 230D2 | COOPERS MILLS ROAD | 230T2 | 2024-03-08 | Fail | Pass | 2024-05-01
101067 | 2024-02-21 | 2024-02-23 | Solar | 125 | 865D1 | WEST WATERVILLE | 865T1 | 2024-02-26 | Pass |  |  | Yes
101055 | 2024-02-20 | 2024-02-23 | Solar | 39.168 | 630D4 | GOOSEFARE | 630T1 | 2024-03-07 | Fail | Pass | 2024-04-30 | Yes
101037 | 2024-02-19 |  | Solar | 100 | 415D2 | FRYEBURG | 415T1 |  |  |  |  | Yes
100996 | 2024-02-14 | 2024-02-20 | Solar | 34.2 | 846D1 | PROSPECT | 846T1 | 2024-02-21 | Fail | Pass | 2024-05-03
100997 | 2024-02-14 | 2024-02-15 | Solar | 48 | 245D1 | STICKNEYS CORNER | 245T1 | 2024-02-21 | Fail | Pass | 2024-04-09
100989 | 2024-02-13 |  | Solar | 996 | [7 empty] | Yes
100949 | 2024-02-09 |  | Solar | 25.986 | 633D1 | LOUDEN | 633T3 |  |  |  |  | Yes
100958 | 2024-02-09 | 2024-02-12 | Solar | 68.4 | 200D3 | AUGUSTA K5 | 200T1 | 2024-02-12 | Fail | Pass | 2024-05-17
100963 | 2024-02-09 | 2024-02-12 | Solar | 115.2 | 216D3 | CONY ROAD | 216T1 | 2024-02-13 | Pass
100892 | 2024-02-02 | 2024-02-16 | Solar | 80 | 633D1 | LOUDEN | 633T3 | 2024-03-07 | Fail | Pass | 2024-06-17
100873 | 2024-02-01 | 2024-02-13 | Solar | 995 | 667D2 | SOUTH SANFORD | 667T2 | 2024-03-07 | Fail | Fail | 2024-05-06 | Yes
100859 | 2024-01-31 | 2024-02-02 | Solar | 38 | 214D4 | CAMDEN | 214T1 | 2024-02-21 | Fail | Pass | 2024-04-15
100862 | 2024-01-31 | 2024-02-08 | Solar | 150 | 233D1 | MANCHESTER | 233T1 | 2024-02-09 | Fail | Pass | 2024-03-25
100863 | 2024-01-31 | 2024-02-09 | Solar | 600 | 415D2 | FRYEBURG | 415T1 | 2024-02-16 | Fail | Fail | 2024-04-12 | Yes
100846 | 2024-01-30 | 2024-02-19 | Solar | 999 | 272D2 | NORTH AUGUSTA | 272T1 | 2024-02-20 | Fail | Pass | 2024-04-11
100821 | 2024-01-26 | 2024-03-04 | Solar | 999 | 632D1 | LIMERICK | 632T1 | 2024-03-07 | Fail | Fail | 2024-05-12 | Yes
100800 | 2024-01-25 | 2024-01-29 | Solar | 93.312 | 217D3 | COOKS CORNER | 34KV BUS 1 | 2024-02-16 | Pass
100801 | 2024-01-25 | 2024-02-06 | Solar | 50 | 644D1 | PLEASANT HILL | 644T2 | 2024-02-09 | Pass
100802 | 2024-01-25 | 2024-01-29 | Solar | 73.6 | 217D3 | COOKS CORNER | 34KV BUS 1 | 2024-03-05 | Pass
100803 | 2024-01-25 | 2024-02-02 | Solar | 999 | 246D3 | THOMASTON CREEK | 246T1 | 2024-02-21 | Fail | Fail | 2024-05-07 | Yes
100806 | 2024-01-25 | 2024-01-29 | Solar | 38.4 | 217D3 | COOKS CORNER | 34KV BUS 1 | 2024-03-05 | Pass
100812 | 2024-01-25 | 2024-02-13 | Solar | 30 | 630D2 | GOOSEFARE | 630T1 | 2024-03-07 | Fail |  |  | Yes
100814 | 2024-01-25 | 2024-02-07 | Solar | 233.3 | 620D4 | ELM STREET | 620T2 | 2024-02-09 | Fail | Pass | 2024-04-02
100792 | 2024-01-24 | 2024-02-23 | Solar | 999 | 467D1 | TURNER TAP | 34KV Tap off of Transmission Line | 2024-02-26 | Fail | Pass | 2024-04-24
100748 | 2024-01-19 | 2024-01-25 | Solar | 29 | 423D2 | KIMBALL ROAD | 423T2 | 2024-01-29 | Fail | Pass | 2024-03-25
100666 | 2024-01-12 | 2024-01-16 | Solar | 28.35 | 620D2 | ELM STREET | 620T3 | 2024-02-06 | Fail |  |  | Yes
100687 | 2024-01-12 | 2024-01-18 | Solar | 500 | 256D2 | WINTHROP | 256T1 | 2024-01-19 | Fail |  |  | Yes
100680 | 2024-01-11 | 2024-01-22 | Solar | 380 | 668D3 | SPRING STREET | 668T2 | 2024-02-05 | Pass |  |  | Yes
100681 | 2024-01-11 | 2024-01-22 | Solar | 999 | 685D2 | BOLT HILL | 685T1 | 2024-02-13 | Fail | Pass | 2024-04-12
100682 | 2024-01-11 | 2024-01-22 | Solar | 999 | 603D3 | BERWICK | 603T1 | 2024-02-22 | Fail | Fail | 2024-04-26 | Yes
100665 | 2024-01-10 | 2024-01-11 | Solar | 33.3 | 249D1 | TOPSHAM OLD | 249T1 | 2024-01-30 | Fail | Pass | 2024-03-25
100620 | 2024-01-05 | 2024-01-05 | Solar | 400 | 412D1 | DEER RIPS | 412T2 | 2024-01-09 | Fail | Pass | 2024-03-18
100622 | 2024-01-05 | 2024-01-08 | Solar | 30 | 635D2 | MOSHERS | 635T2 | 2024-01-13 | Fail |  |  | Yes
100623 | 2024-01-05 | 2024-01-08 | Solar | 720 | 412D1 | DEER RIPS | 412T2 | 2024-01-09 | Fail | Pass | 2024-03-11
100586 | 2024-01-02 | 2024-01-09 | Solar | 34.2 | 218D1 | WILLIAM F WYMAN OUTSIDE | 218T13 | 2024-01-13 | Fail | Pass | 2024-03-11
100587 | 2024-01-02 | 2024-01-11 | Solar | 34.6 | 225D4 | FREEPORT | 225T1 | 2024-01-29 | Fail | Pass | 2024-03-25
100571 | 2023-12-29 | 2024-01-16 | Solar | 750 | 200D3 | AUGUSTA K5 | 200T1 | 2024-01-16 | Fail | Pass | 2024-03-20 | Yes
100555 | 2023-12-28 |  | Solar | 25.986 | 633D1 | LOUDEN | 633T3 |  |  |  |  | Yes
100520 | 2023-12-22 | 2024-01-09 | Solar | 500 | 660D2 | SHAWS MILL ROAD | 660T1 | 2024-01-13 | Fail | Pass | 2024-02-15
100446 | 2023-12-15 | 2023-12-15 | Battery | 44 | 661D1 | PRATT & WHITNEY | 661T1 | 2024-01-09 | Fail |  |  | Yes
100461 | 2023-12-15 | 2024-01-10 | Solar | 999 | 818D2 | FARMINGTON FALLS | 818T1 | 2024-01-17 | Fail | Pass | 2024-04-11 | Yes
100433 | 2023-12-13 | 2024-01-02 | Solar | 54 | 219D2 | DAMARISCOTTA MILLS | 219T1 | 2024-01-16 | Fail | Pass | 2024-04-26
100388 | 2023-12-11 | 2023-12-15 | Solar | 350 | 421D2 | CHALLENGER | 421T1 | 2024-01-03 | Fail | Pass | 2024-02-21
100360 | 2023-12-08 |  | Solar | 999 | [7 empty] | Yes
100368 | 2023-12-08 | 2023-12-14 | Solar | 330 | 841D1 | PHILLIPS/STRONG | 841T1 | 2024-01-03 | Fail |  |  | Yes
100376 | 2023-12-08 | 2023-12-15 | Solar | 999 | 855D2 | SOUTH WATERVILLE | 855T1 | 2023-12-18 | Fail | Fail | 2024-02-08 | Yes
100379 | 2023-12-08 |  | Solar | 1000 | 632D1 | LIMERICK | 632T1 |  |  |  |  | Yes
100334 | 2023-12-07 | 2023-12-13 | Solar | 26.4 | 673D1 | BIDDEFORD INDUSTRIAL PARK | 673T2 | 2024-01-09 | Pass
100340 | 2023-12-07 | 2023-12-11 | Solar | 360 | 215D2 | CAPITOL STREET | 215T2 | 2023-12-11 | Fail | Pass | 2024-02-09
100354 | 2023-12-07 | 2024-01-08 | Solar | 999 | 632D1 | LIMERICK | 632T1 | 2024-02-01 | Fail | Fail | 2024-04-09 | Yes
100324 | 2023-12-06 | 2023-12-12 | Solar | 360 | 273D5 | BRUNSWICK HYDRO | 273T2 | 2024-01-02 | Pass |  |  | Yes
100307 | 2023-12-05 | 2023-12-06 | Solar | 540 | 249D2 | TOPSHAM OLD | 249T1 | 2023-12-27 | Fail | Pass | 2024-03-11
100280 | 2023-12-04 | 2024-01-09 | Solar | 34.8 | 636D1 | MUSSEY ROAD | 636T1 | 2024-01-13 | Pass
100256 | 2023-12-01 | 2023-12-04 | Solar | 68.4 | 240D1 | RICHMOND | 240T1 | 2023-12-06 | Fail | Pass | 2024-03-25
100263 | 2023-12-01 | 2024-01-10 | Solar | 900 | 818D1 | FARMINGTON FALLS | 818T1 | 2024-01-17 | Fail | Pass | 2024-03-18 | Yes
100265 | 2023-12-01 | 2023-12-06 | Solar | 240 | 865D1 | WEST WATERVILLE | 865T1 | 2023-12-06 | Fail | Pass | 2024-01-29
100266 | 2023-12-01 | 2023-12-06 | Solar | 400 | 639D2 | NORTH WINDHAM | 639T2 | 2023-12-11 | Fail | Pass | 2024-03-08
100267 | 2023-12-01 | 2023-12-06 | Solar | 240 | 681D3 | BRANCH BROOK | 681T3 | 2023-12-27 | Pass
100268 | 2023-12-01 | 2023-12-06 | Solar | 500 | 681D3 | BRANCH BROOK | 681T3 | 2023-12-26 | Pass
100245 | 2023-11-30 | 2023-12-07 | Solar | 120 | 249D1 | TOPSHAM OLD | 249T1 | 2023-12-29 | Fail | Pass | 2024-02-22
100251 | 2023-11-30 | 2023-12-07 | Solar | 100 | 249D1 | TOPSHAM OLD | 249T1 | 2024-01-02 | Fail | Pass | 2024-02-19
100252 | 2023-11-30 | 2024-01-17 | Solar | 1020 | 471D1 | LEEDS | 471T1 | 2024-01-23 | Fail | Fail | 2024-04-29 | Yes
100255 | 2023-11-30 | 2023-12-15 | Solar | 1020 | 873D1 | COUNTY ROAD | 873T1 | 2023-12-18 | Fail |  |  | Yes
100222 | 2023-11-29 | 2023-11-30 | Solar | 996 | 678D1 | BAR MILLS | 678T4 | 2023-12-26 | Fail | Fail | 2024-03-21 | Yes
100227 | 2023-11-29 | 2023-12-12 | Solar | 1020 | 450D2 | SABATTUS | 450T1 | 2023-12-26 | Fail | Fail | 2024-03-11 | Yes
100140 | 2023-11-27 | 2023-12-07 | Solar | 360 | 668D3 | SPRING STREET | 668T2 | 2023-12-11 | Pass
100119 | 2023-11-22 | 2023-11-29 | Solar | 996 | 453D1 | TRAP CORNER | 453T1 | 2023-12-05 | Fail |  |  | Yes
100126 | 2023-11-22 | 2023-12-06 | Solar | 360 | 233D1 | MANCHESTER | 233T1 | 2023-12-06 | Fail | Fail | 2024-02-20 | Yes
100128 | 2023-11-22 | 2023-12-07 | Solar | 420 | 213D4 | BRUNSWICK WEST SIDE | 213T2 | 2023-12-29 | Pass |  |  | Yes
100129 | 2023-11-22 | 2023-12-06 | Solar | 480 | 668D3 | SPRING STREET | 668T2 | 2023-12-11 | Fail |  |  | Yes
100075 | 2023-11-19 |  | Solar | 30 | 635D2 | MOSHERS | 635T2 |  |  |  |  | Yes
100091 | 2023-11-17 | 2023-11-27 | Solar | 975 | 461D1 | LUDDEN LANE | 461T1 | 2023-12-11 | Fail | Pass | 2024-02-12
100056 | 2023-11-16 | 2023-11-27 | Solar | 120 | 208D1 | BOND BROOK | 208T1 | 2023-11-27 | Fail |  |  | Yes
100057 | 2023-11-16 | 2023-11-27 | Solar | 120 | 453D1 | TRAP CORNER | 453T1 | 2023-11-28 | Fail |  |  | Yes
100000 | 2023-11-15 | 2023-11-27 | Solar | 994 | 210D1 | BRISTOL | 210T1 | 2023-12-18 | Fail | Pass | 2024-01-25 | Yes
100001 | 2023-11-15 | 2023-11-27 | Solar | 700 | 870D1 | WINSLOW | 870T4 | 2023-11-28 | Fail | Fail | 2024-01-02 | Yes
100002 | 2023-11-15 | 2023-11-22 | Solar | 994 | 454D1 | TURNER | 454T1 | 2023-11-28 | Fail | Fail | 2024-01-25 | Yes
100049 | 2023-11-15 | 2024-01-04 | Solar | 1020 | 858D2 | STURTEVANT | 858T1 | 2024-01-05 | Fail |  |  | Yes
85879 | 2023-11-13 | 2023-11-20 | Solar | 999 | 695D2 | LEBANON | 695T1 | 2023-12-13 | Fail | Fail | 2024-02-14 | Yes
85878 | 2023-11-12 | 2024-01-03 | Solar | 49.8 | 806D1 | BUCKSPORT | 806T5 | 2024-01-08 | Fail | Pass | 2024-03-12
85877 | 2023-11-10 | 2023-11-13 | Solar | 995 | 842D1 | PITTSFIELD | 842T1 | 2023-11-14 | Fail | Pass | 2023-12-08 | Yes
85876 | 2023-11-09 | 2023-12-06 | Solar | 100 | 803D5 | BELFAST WEST SIDE | 803T1 | 2023-12-29 | Fail | Pass | 2024-02-21
85862 | 2023-11-08 | 2023-11-15 | Solar | 150 | 233D1 | MANCHESTER | 233T1 | 2023-11-15 | Fail | Pass | 2024-01-02
85875 | 2023-11-08 | 2023-12-11 | Solar | 999 | 837D2 | NEWPORT | 837T2 | 2023-12-11 | Fail | Pass | 2024-01-17 | Yes
85873 | 2023-11-07 | 2023-11-20 | Solar | 50 | 245D1 | STICKNEYS CORNER | 245T1 | 2023-11-27 | Fail | Pass | 2024-01-10
85805 | 2023-11-03 | 2023-11-09 | Solar | 999 | 813D1 | DEXTER | 813T1 | 2023-11-17 | Fail | Pass | 2024-01-02
85807 | 2023-11-03 | 2023-11-09 | Solar | 999 | 256D2 | WINTHROP | 256T1 | 2023-11-10 | Fail | Pass | 2023-12-06
85736 | 2023-11-02 | 2023-11-02 | Solar | 999 | 471D2 | LEEDS | 471T1 | 2023-11-08 | Fail | Pass | 2024-01-02
85743 | 2023-11-02 | 2023-11-14 | Solar | 560 | 412D1 | DEER RIPS | 412T2 | 2023-11-17 | Fail | Pass | 2024-01-11 | Yes
85721 | 2023-11-01 | 2023-11-13 | Solar | 970 | 239D6 | PARK STREET | 239T2 | 2023-11-14 | Fail | Pass | 2024-01-17
85727 | 2023-11-01 | 2023-11-13 | Solar | 625 | 230D1 | COOPERS MILLS ROAD | 230T2 | 2023-11-13 | Fail | Pass | 2024-01-25
85695 | 2023-10-31 | 2023-11-13 | Solar | 300 | 865D5 | WEST WATERVILLE | 865T2 | 2023-11-14 | Fail | Pass | 2024-01-29
85703 | 2023-10-31 | 2023-11-03 | Solar | 975 | 421D2 | CHALLENGER | 421T1 | 2023-11-09 | Fail | Pass | 2023-12-06 | Yes
85662 | 2023-10-27 | 2023-11-13 | Solar | 68.4 | 874D1 | BELFAST 115 | 874T2 | 2023-11-14 | Fail | Pass | 2024-01-02
85663 | 2023-10-27 | 2023-11-03 | Solar | 600 | 612D2 | BUTLER'S CORNER | 612T1 | 2023-11-28 | Fail | Fail | 2024-02-14 | Yes
85622 | 2023-10-24 | 2023-11-13 | Solar | 152 | 423D2 | KIMBALL ROAD | 423T2 | 2023-11-14 | Fail | Pass | 2024-01-11
85623 | 2023-10-24 | 2023-11-14 | Solar | 62.5 | 213D3 | BRUNSWICK WEST SIDE | 213T1 | 2023-12-07 | Pass
85591 | 2023-10-23 | 2023-10-24 | Solar | 50 | 647D1 | PRIDES CORNER | 647T2 | 2023-11-02 | Pass
85588 | 2023-10-18 | 2023-10-24 | Solar | 600 | 865D1 | WEST WATERVILLE | 865T1 | 2023-10-25 | Pass
85484 | 2023-10-13 | 2023-10-18 | Solar | 975 | 447D1 | RUMFORD | 447T3 | 2023-10-30 | Pass
85488 | 2023-10-13 | 2023-10-19 | Solar | 500 | 208D1 | BOND BROOK | 208T1 | 2023-10-19 | Fail | Pass | 2023-11-27
85398 | 2023-10-10 | 2023-10-12 | Solar | 40.4 | 435D2 | NORWAY | 435T2 | 2023-10-13 | Pass
85378 | 2023-10-09 | 2023-10-13 | Solar | 34.2 | 211D1 | BROWNS CROSSING | 211T1 | 2023-10-13 | Fail |  |  | Yes
85264 | 2023-10-02 | 2023-10-13 | Solar | 32.8 | 225D3 | FREEPORT | 225T2 | 2023-11-03 | Pass
85283 | 2023-10-02 | 2023-10-09 | Other | 75 | 675D1 | WESTERN AVENUE | 675T1 | 2023-10-10 | Fail |  |  | Yes
85228 | 2023-09-28 | 2023-10-04 | Solar | 975 | 261D4 | BATH | 261T2 | 2023-10-26 | Fail | Fail | 2023-11-10 | Yes
85186 | 2023-09-26 | 2023-10-17 | Solar | 900 | 667D3 | SOUTH SANFORD | 667T1 | 2023-11-14 | Fail | Pass | 2024-01-24
85189 | 2023-09-26 | 2023-10-16 | Solar | 27 | 423D2 | KIMBALL ROAD | 423T2 | 2023-10-17 | Pass
85197 | 2023-09-26 | 2023-10-02 | Solar | 480 | 423D1 | KIMBALL ROAD | 423T2 | 2023-10-05 | Fail | Pass | 2023-11-10
85173 | 2023-09-25 | 2023-09-28 | Solar | 250 | 673D1 | BIDDEFORD INDUSTRIAL PARK | 673T2 | 2023-10-23 | Pass
85134 | 2023-09-22 | 2023-09-28 | Solar | 46.08 | 253D1 | WARREN | 253T1 | 2023-10-11 | Pass
85069 | 2023-09-15 | 2023-10-04 | Solar | 975 | 466D1 | RUMFORD INDUSTRIAL PARK | 466T1 | 2023-10-06 | Fail | Fail | 2023-11-10 | Yes
85041 | 2023-09-13 | 2023-09-27 | Solar | 994 | 263D1 | BOWMAN STREET | 34 kV BUS 2 | 2023-09-28 | Fail | Pass | 2023-10-25 | Yes
85031 | 2023-09-12 | 2023-10-12 | Solar | 1999 | 225D3 | FREEPORT | 225T2 | 2023-10-26 | Fail |  |  | Yes
85005 | 2023-09-11 | 2023-09-14 | Solar | 45.6 | 412D3 | DEER RIPS | 412T4 | 2023-09-14 | Fail |  |  | Yes
85012 | 2023-09-11 | 2023-09-18 | Solar | 1050 | 207D1 | BLAIR ROAD | 207T1 | 2023-09-19 | Fail | Fail | 2023-10-25 | Yes
84974 | 2023-09-08 | 2023-09-13 | Solar | 975 | 233D1 | MANCHESTER | 233T1 | 2023-09-13 | Fail | Pass | 2023-09-29
84979 | 2023-09-08 | 2023-09-13 | Solar | 975 | 219D2 | DAMARISCOTTA MILLS | 219T1 | 2023-09-19 | Fail | Pass | 2023-10-12
84902 | 2023-09-05 | 2023-09-12 | Other | 100 | 855D1 | SOUTH WATERVILLE | 855T1 | 2023-09-06 | Fail | Pass | 2023-10-12
84904 | 2023-09-05 | 2023-09-11 | Solar | 150 | 252D2 | WALDOBORO | 252T1 | 2023-09-15 | Fail | Pass | 2023-10-12
84908 | 2023-09-05 | 2023-09-11 | Solar | 34.6 | 674D1 | WESTBROOK | 674T1 | 2023-09-11 | Pass
84885 | 2023-08-31 | 2023-09-19 | Solar | 27.3 | 618D1 | EAST DEERING | 618T1 | 2023-09-29 | Fail | Fail | 2023-11-14 | Yes
84833 | 2023-08-29 | 2023-09-05 | Solar | 34.6 | 647D2 | PRIDES CORNER | 647T2 | 2023-09-11 | Pass
84769 | 2023-08-24 | 2023-08-28 | Solar | 25.2 | 274D1 | MAINE YANKEE | 274T2 | 2023-09-18 | Fail |  |  | Yes
84764 | 2023-08-23 | 2023-09-19 | Solar | 500 | 210D2 | BRISTOL | 210T1 | 2023-10-11 | Fail | Fail | 2023-12-08 | Yes
84691 | 2023-08-17 | 2023-08-25 | Solar | 144.48 | 667D1 | SOUTH SANFORD | 667T2 | 2023-08-31 | Fail | Pass | 2023-10-12
84683 | 2023-08-14 |  | Solar | 799.98 | 874D1 | BELFAST 115 | 874T2 |  |  |  |  | Yes
84684 | 2023-08-14 | 2023-08-28 | Solar | 100 | 239D7 | PARK STREET | 239T2 | 2023-08-31 | Pass
84618 | 2023-08-09 | 2023-08-10 | Solar | 999 | 412D1 | DEER RIPS | 412T2 | 2023-08-11 | Fail | Pass | 2023-09-28
84619 | 2023-08-09 | 2023-08-10 | Solar | 996 | 870D1 | WINSLOW | 870T4 | 2023-08-11 | Fail | Fail | 2023-09-14 | Yes
84757 | 2023-08-09 | 2023-09-08 | Solar | 999.6 | 808D3 | CARMEL TAP | 808T1 off transmission | 2023-09-26 | Pass
84609 | 2023-08-08 | 2023-08-21 | Solar | 999 | 821D1 | GUILFORD | 821T1 | 2023-08-22 | Fail | Pass | 2023-12-01
84616 | 2023-08-08 | 2023-08-25 | Solar | 36.288 | 239D9 | PARK STREET | 239T4 | 2023-08-31 | Pass
84554 | 2023-08-02 | 2023-08-22 | Solar | 30 | 821D1 | GUILFORD | 821T1 | 2023-08-22 | Fail |  |  | Yes
84547 | 2023-08-01 | 2023-08-04 | Solar | 999 | 412D4 | DEER RIPS | 412T4 | 2023-08-07 | Fail | Fail | 2023-10-25 | Yes
84553 | 2023-08-01 | 2023-08-04 | Solar | 999 | 412D4 | DEER RIPS | 412T4 | 2023-08-07 | Fail | Fail | 2023-10-25 | Yes
84449 | 2023-07-25 | 2023-07-26 | Solar | 76 | 252D2 | WALDOBORO | 252T1 | 2023-07-27 | Fail | Pass | 2023-10-12 | Yes
84450 | 2023-07-25 | 2023-07-27 | Solar | 996 | 695D2 | LEBANON | 695T1 | 2023-08-24 | Fail | Pass | 2023-10-12
84451 | 2023-07-25 | 2023-07-27 | Solar | 996 | 663D2 | SOUTH BERWICK | 663T1 | 2023-08-24 | Fail | Fail | 2023-10-12 | Yes
84452 | 2023-07-25 | 2023-07-27 | Solar | 996 | 225D4 | FREEPORT | 225T1 | 2023-08-17 | Fail | Fail | 2023-10-03 | Yes
84411 | 2023-07-20 | 2023-08-07 | Solar | 999 | 632D2 | LIMERICK | 632T1 | 2023-08-31 | Fail |  |  | Yes
84416 | 2023-07-20 | 2023-08-07 | Solar | 999 | 632D2 | LIMERICK | 632T1 | 2023-08-31 | Fail |  |  | Yes
84417 | 2023-07-20 | 2023-07-26 | Solar | 67.3 | 653D2 | FORE RIVER | 653T2 | 2023-08-01 | Pass
84390 | 2023-07-18 | 2023-07-20 | Solar | 83 | 611D1 | BRIGHTON AVENUE | 611T1 | 2023-07-25 | Pass |  |  | Yes
84392 | 2023-07-18 | 2023-08-21 | Solar | 200 | 607D1 | BISHOP STREET | 607T1 | 2023-09-08 | Pass |  |  | Yes
84387 | 2023-07-17 | 2023-07-26 | Solar | 40 | 645D1 | UNION STREET | 645T1 | 2023-08-01 | Pass
84389 | 2023-07-17 | 2023-07-26 | Solar | 975 | 232D2 | LISBON FALLS | 232T2 | 2023-08-11 | Fail | Fail | 2023-09-20 | Yes
84338 | 2023-07-13 | 2023-07-19 | Solar | 975 | 244D1 | SOUTH CHINA | 244T1 | 2023-07-19 | Fail | Fail | 2023-08-16 | Yes
84350 | 2023-07-13 | 2023-07-19 | Solar | 975 | 255D2 | WEST STREET | 255T1 | 2023-07-19 | Fail | Pass | 2023-08-23
84302 | 2023-07-10 | 2023-07-11 | Solar | 57 | 239D9 | PARK STREET | 239T4 | 2023-07-13 | Pass
84303 | 2023-07-10 | 2023-07-11 | Solar | 45.6 | 239D9 | PARK STREET | 239T4 | 2023-07-13 | Pass
84304 | 2023-07-10 | 2023-07-10 | Solar | 750 | 858D2 | STURTEVANT | 858T1 | 2023-07-13 | Pass
84290 | 2023-07-06 | 2023-07-10 | Solar | 975 | 808D1 | CARMEL | 808T1 | 2023-07-14 | Fail | Pass | 2023-08-31 | Yes
84276 | 2023-07-05 | 2023-07-21 | Solar | 999 | 837D1 | NEWPORT | 837T1 | 2023-07-24 | Fail | Pass | 2023-08-11
84277 | 2023-07-05 | 2023-07-21 | Solar | 999 | 837D1 | NEWPORT | 837T1 | 2023-07-24 | Fail | Pass | 2023-09-06 | Yes
84278 | 2023-07-05 | 2023-07-21 | Solar | 999 | 837D1 | NEWPORT | 837T1 | 2023-07-24 | Fail | Pass | 2023-09-06 | Yes
84279 | 2023-07-05 | 2023-07-21 | Solar | 999 | 837D1 | NEWPORT | 837T1 | 2023-07-24 | Fail | Fail | 2023-09-06 | Yes
84280 | 2023-07-05 | 2023-07-21 | Solar | 999 | 837D1 | NEWPORT | 837T1 | 2023-07-24 | Fail | Fail | 2023-09-06 | Yes
84272 | 2023-06-30 | 2023-07-05 | Solar | 825 | 253D1 | WARREN | 253T1 | 2023-07-06 | Fail | Pass | 2023-08-01
84231 | 2023-06-29 | 2023-07-10 | Solar | 996 | 461D1 | LUDDEN LANE | 461T1 | 2023-07-13 | Fail | Pass | 2023-08-11
84228 | 2023-06-28 | 2023-06-30 | Solar | 999 | 860D1 | UNITY | 860T1 | 2023-07-10 | Fail | Fail | 2023-08-30 | Yes
84229 | 2023-06-28 | 2023-07-05 | Solar | 67.3 | 659D13 | SEWALL STREET | 659T1 | 2023-07-10 | Pass
84222 | 2023-06-27 | 2023-07-05 | Solar | 120 | 678D1 | BAR MILLS | 678T4 | 2023-07-26 | Fail | Pass | 2023-09-11
84184 | 2023-06-23 | 2023-07-10 | Solar | 40 | 860D1 | UNITY | 860T1 | 2023-07-11 | Fail | Pass | 2023-11-10
84188 | 2023-06-23 | 2023-06-28 | Solar | 975 | 238D1 | MESSINA | 238T1 | 2023-07-20 | Fail | Fail | 2023-08-16 | Yes
84211 | 2023-06-23 | 2023-07-07 | Solar | 160 | 689D1 | BRAGDON COMMONS | 689T1 | 2023-07-26 | Fail | Pass | 2023-09-20
84154 | 2023-06-19 | 2023-07-13 | Solar | 36.4 | 406D3 | BRIDGTON | 406T1 | 2023-07-17 | Pass |  |  | Yes
84117 | 2023-06-16 | 2023-06-21 | Solar | 975 | 858D1B | STURTEVANT | 858T1 | 2023-07-06 | Fail | Pass | 2023-09-25
84104 | 2023-06-14 | 2023-07-05 | Solar | 1000 | 815D2 | DOVER | 815T2 | 2023-07-06 | Fail |  |  | Yes
84107 | 2023-06-14 | 2023-06-15 | Solar | 999 | 636D1 | MUSSEY ROAD | 636T1 | 2023-06-30 | Fail | Pass | 2023-08-08 | Yes
84070 | 2023-06-12 | 2023-06-15 | Solar | 975 | 860D2 | UNITY | 860T1 | 2023-06-29 | Fail | Pass | 2023-07-27
84071 | 2023-06-12 | 2023-06-14 | Solar | 975 | 858D1A | STURTEVANT | 858T1 | 2023-06-15 | Fail | Pass | 2023-07-18 | Yes
84066 | 2023-06-09 | 2023-06-12 | Solar | 995 | 471D1 | LEEDS | 471T1 | 2023-06-15 | Fail | Fail | 2023-07-10 | Yes
84068 | 2023-06-09 | 2023-06-13 | Solar | 875 | 253D1 | WARREN | 253T1 | 2023-06-28 | Fail |  |  | Yes
84024 | 2023-06-07 | 2023-06-13 | Solar | 975 | 431D1 | MECHANIC FALLS | 431T2 | 2023-06-15 | Fail | Pass | 2023-07-18
84026 | 2023-06-07 | 2023-06-12 | Solar | 33.06 | 803D4 | BELFAST WEST SIDE | 803T1 | 2023-06-14 | Pass
83991 | 2023-06-02 | 2023-06-08 | Solar | 160 | 852D1 | SHAWMUT | 852T3 | 2023-06-09 | Fail | Pass | 2023-07-25
84004 | 2023-06-02 | 2023-06-21 | Solar | 999 | 256D1 | WINTHROP | 256T2 | 2023-06-27 | Fail | Pass | 2023-08-16
83943 | 2023-05-26 | 2023-06-06 | Solar | 50 | 261D4 | BATH | 261T2 | 2023-06-07 | Pass
83944 | 2023-05-26 | 2023-06-01 | Solar | 975 | 639D2 | NORTH WINDHAM | 639T2 | 2023-06-07 | Fail | Pass | 2023-07-12 | Yes
83909 | 2023-05-24 | 2023-06-05 | Solar | 999 | 813D1 | DEXTER | 813T1 | 2023-06-07 | Fail | Fail | 2023-07-14 | Yes
83914 | 2023-05-24 | 2023-06-05 | Solar | 999 | 885D1 | WILTON | 885T1 | 2023-06-07 | Fail | Pass | 2023-07-14
83916 | 2023-05-24 | 2023-06-05 | Solar | 999 | 885D1 | WILTON | 885T1 | 2023-06-07 | Fail | Fail | 2023-07-14 | Yes
83894 | 2023-05-22 | 2023-05-25 | Solar | 900 | 691D1 | BALDWIN | 691T1 | 2023-05-25 | Fail | Fail | 2023-06-21 | Yes
83856 | 2023-05-17 | 2023-05-22 | Solar | 154 | 274D1 | MAINE YANKEE | 274T2 | 2023-05-23 | Fail | Pass | 2023-07-20
83838 | 2023-05-16 | 2023-05-22 | Solar | 200 | 239D7 | PARK STREET | 239T2 | 2023-05-23 | Pass
83837 | 2023-05-15 | 2023-05-17 | Solar | 720 | 428D2 | LIVERMORE FALLS | 428T1 | 2023-05-18 | Pass
83829 | 2023-05-12 | 2023-05-15 | Solar | 995 | 412D3 | DEER RIPS | 412T4 | 2023-05-18 | Fail | Pass | 2023-06-06
83798 | 2023-05-10 | 2023-05-12 | Solar | 29 | 629D1 | KENNEBUNKPORT | 629T1 | 2023-05-15 | Pass
83793 | 2023-05-09 | 2023-05-11 | Solar | 975 | 400D1 | ANDOVER | 400T1 | 2023-05-12 | Fail | Pass | 2023-06-20
83777 | 2023-05-08 | 2023-05-09 | Solar | 999 | 805D1 | BROOKS | 805T1 | 2023-05-10 | Fail | Fail | 2023-08-08 | Yes
83779 | 2023-05-08 | 2023-05-10 | Solar | 996 | 813D3 | DEXTER | 813T2 | 2023-05-12 | Fail | Fail | 2023-08-08 | Yes
83787 | 2023-05-08 | 2023-05-10 | Solar | 996 | 406D2 | BRIDGTON | 406T1 | 2023-05-17 | Fail | Fail | 2023-07-26 | Yes
83765 | 2023-05-05 | 2023-05-12 | Solar | 34 | 416D1 | GRAY | 416T2 | 2023-05-12 | Fail |  |  | Yes
83766 | 2023-05-05 | 2023-05-09 | Solar | 40 | 803D4 | BELFAST WEST SIDE | 803T1 | 2023-05-15 | Pass
83768 | 2023-05-05 | 2023-05-09 | Solar | 34.2 | 803D4 | BELFAST WEST SIDE | 803T1 | 2023-05-15 | Pass
83769 | 2023-05-05 | 2023-05-08 | Solar | 240 | 630D4 | GOOSEFARE | 630T1 | 2023-05-17 | Fail | Pass | 2023-06-22
83734 | 2023-05-04 | 2023-05-08 | Solar | 45.6 | 239D6 | PARK STREET | 239T2 | 2023-05-18 | Pass
83736 | 2023-05-04 | 2023-05-08 | Solar | 45.6 | 239D6 | PARK STREET | 239T2 | 2023-05-09 | Pass
83738 | 2023-05-04 | 2023-05-11 | Solar | 975 | 466D1 | RUMFORD INDUSTRIAL PARK | 466T1 | 2023-05-12 | Fail | Pass | 2023-06-01 | Yes
83720 | 2023-05-03 | 2023-05-25 | Solar | 1000 | 834D1 | MONSON | 834T1 | 2023-05-30 | Fail | Fail | 2023-06-22 | Yes
83707 | 2023-05-02 | 2023-05-08 | Solar | 34.2 | 605D1 | BIDDEFORD PUMPING STATION | 605T1 | 2023-05-12 | Pass
83685 | 2023-04-28 | 2023-05-01 | Solar | 324 | 858D1A | STURTEVANT | 858T1 | 2023-05-01 | Fail | Pass | 2023-05-03
83664 | 2023-04-27 | 2023-05-01 | Solar | 700 | 816D1 | EAST WILTON | 816T1 | 2023-05-02 | Fail | Pass | 2023-06-01
83668 | 2023-04-27 | 2023-05-01 | Solar | 975 | 233D2 | MANCHESTER | 233T1 | 2023-05-03 | Fail | Pass | 2023-05-11 | Yes
83670 | 2023-04-27 | 2023-05-01 | Solar | 975 | 262D1 | PUDDLEDOCK ROAD | 34 kV BUS 1 | 2023-05-09 | Fail | Pass | 2023-06-16
83611 | 2023-04-24 | 2023-05-03 | Solar | 120 | 617D3 | DUNSTAN | 617T1 | 2023-05-15 | Pass |  |  | Yes
83603 | 2023-04-21 | 2023-05-01 | Solar | 34.2 | 241D1 | SHEEPSCOT | 241T1 | 2023-05-03 | Fail | Pass | 2023-07-27
83605 | 2023-04-21 | 2023-04-27 | Solar | 975 | 431D1 | MECHANIC FALLS | 431T2 | 2023-04-27 | Fail | Pass | 2023-06-05
83600 | 2023-04-20 | 2023-04-21 | Solar | 850 | 450D1 | SABATTUS | 450T1 | 2023-04-24 | Fail | Pass | 2023-06-21
83601 | 2023-04-20 | 2023-04-25 | Solar | 700 | 256D2 | WINTHROP | 256T1 | 2023-04-25 | Fail | Pass | 2023-05-11
83577 | 2023-04-18 | 2023-04-25 | Solar | 34.2 | 805D1 | BROOKS | 805T1 | 2023-05-01 | Pass
83523 | 2023-04-12 | 2023-04-18 | Solar | 45 | 214D1 | CAMDEN | 214T2 | 2023-04-20 | Pass
83526 | 2023-04-12 | 2023-05-01 | Solar | 1000 | 821D3 | GUILFORD | 821T2 | 2023-05-02 | Fail | Fail | 2023-05-18 | Yes
83507 | 2023-04-11 | 2023-04-14 | Solar | 975 | 639D2 | NORTH WINDHAM | 639T2 | 2023-05-02 | Fail | Pass | 2023-05-23
83514 | 2023-04-11 | 2023-04-13 | Solar | 995 | 858D3 | STURTEVANT | 858T2 | 2023-04-18 | Fail | Pass | 2023-05-01
83489 | 2023-04-07 | 2023-04-18 | Solar | 30.4 | 800D1 | LINCOLNVILLE | 800T1 | 2023-04-19 | Fail | Pass | 2023-06-07
83474 | 2023-04-05 | 2023-04-07 | Solar | 999 | 605D1 | BIDDEFORD PUMPING STATION | 605T1 | 2023-05-03 | Pass | Pass | 2023-06-26
83455 | 2023-04-03 | 2023-04-18 | Solar | 999 | 602D3 | BASSETT | 602T1 | 2023-05-03 | Fail | Pass | 2023-06-23
83453 | 2023-03-31 | 2023-04-05 | Solar | 975 | 858D1A | STURTEVANT | 858T1 | 2023-04-05 | Fail | Fail | 2023-04-24 | Yes
83437 | 2023-03-28 | 2023-04-06 | Solar | 120 | 634D4 | MAY STREET | 634T1 | 2023-05-03 | Pass
83403 | 2023-03-27 | 2023-04-03 | Solar | 125 | 693D1 | SCARBOROUGH | 693T1 | 2023-04-05 | Pass |  |  | Yes
83406 | 2023-03-27 | 2023-04-03 | Solar | 61.44 | 861D9 | VASSALBORO | 861T1 | 2023-04-03 | Fail | Pass | 2023-05-12
83392 | 2023-03-24 | 2023-04-06 | Solar | 45.6 | 815D1 | DOVER | 815T1 | 2023-04-07 | Fail | Pass | 2023-05-12
83401 | 2023-03-24 | 2023-03-29 | Solar | 250 | 436D6 | GREAT FALLS | 436T1 | 2023-03-30 | Fail | Pass | 2023-04-24 | Yes
83384 | 2023-03-23 | 2023-03-29 | Solar | 600 | 673D1 | BIDDEFORD INDUSTRIAL PARK | 673T2 | 2023-04-19 | Fail | Pass | 2023-06-02 | Yes
83361 | 2023-03-21 | 2023-03-24 | Solar/Battery | 996 | 834D1 | MONSON | 834T1 | 2023-03-28 | Fail | Pass | 2023-05-16
83350 | 2023-03-20 | 2023-03-23 | Solar | 999 | 253D1 | WARREN | 253T1 | 2023-04-12 | Fail | Fail | 2023-05-11 | Yes
83328 | 2023-03-16 | 2023-03-20 | Solar | 720 | 653D5 | FORE RIVER | 653T1 | 2023-04-03 | Fail | Pass | 2023-05-01
83307 | 2023-03-14 | 2023-03-21 | Solar/Battery | 996 | 813D1 | DEXTER | 813T1 | 2023-03-22 | Fail | Pass | 2023-07-07
83298 | 2023-03-13 | 2023-03-16 | Solar | 120 | 200D1 | AUGUSTA K5 | 200T1 | 2023-03-16 | Pass
83253 | 2023-03-06 | 2023-03-15 | Solar | 120 | 656D1 | SANFORD INDUSTRIAL PARK | 656T1 | 2023-04-04 | Pass
83258 | 2023-03-06 | 2023-03-10 | Solar | 34.2 | 860D1 | UNITY | 860T1 | 2023-03-13 | Fail | Pass | 2023-04-28
83260 | 2023-03-06 | 2023-03-10 | Solar | 400 | 211D1 | BROWNS CROSSING | 211T1 | 2023-03-13 | Pass
83238 | 2023-03-03 | 2023-03-14 | Solar | 45.6 | 255D2 | WEST STREET | 255T1 | 2023-03-14 | Pass
83231 | 2023-03-02 | 2023-03-20 | Solar | 150 | 232D2 | LISBON FALLS | 232T2 | 2023-03-29 | Pass
83235 | 2023-03-02 | 2023-03-06 | Fuel Cell | 930 | 688D1 | KITTERY | 688T1 | 2023-03-28 | Pass |  |  | Yes
83229 | 2023-03-01 | 2023-03-03 | Fuel Cell | 600 | 420D1 | HOTEL ROAD | 420T2 | 2023-03-14 | Pass
83217 | 2023-02-28 | 2023-02-28 | Solar | 27.6 | 246D1 | THOMASTON CREEK | 34KV | 2023-03-20 | Fail |  |  | Yes
83218 | 2023-02-28 | 2023-03-13 | Solar | 34.2 | 634D4 | MAY STREET | 634T1 | 2023-04-04 | Pass
83208 | 2023-02-24 | 2023-03-03 | Solar | 999 | 447D2 | RUMFORD | 447T4 | 2023-03-14 | Fail | Pass | 2023-04-18
83189 | 2023-02-22 | 2023-02-22 | Solar | 1500 | 612D1 | BUTLER'S CORNER | 612T1 | 2023-03-21 | Fail |  |  | Yes
83186 | 2023-02-21 | 2023-02-23 | Solar | 995 | 256D2 | WINTHROP | 256T1 | 2023-02-24 | Fail | Pass | 2023-03-23
83158 | 2023-02-16 | 2023-03-13 | Solar | 160 | 690D1 | HINCKLEY POND | 690T1 | 2023-03-23 | Pass |  |  | Yes
83159 | 2023-02-16 | 2023-03-01 | Solar | 120 | 255D2 | WEST STREET | 255T1 | 2023-03-23 | Pass
83131 | 2023-02-14 | 2023-02-21 | Solar | 240 | 621D2 | FACTORY ISLAND | 621T2 | 2023-03-07 | Pass
83095 | 2023-02-13 | 2023-02-24 | Solar | 300 | 239D7 | PARK STREET | 239T2 | 2023-03-16 | Pass
83113 | 2023-02-13 | 2023-02-22 | Solar | 99.9 | 675D1 | WESTERN AVENUE | 675T1 | 2023-03-07 | Pass
83116 | 2023-02-13 | 2023-02-22 | Solar | 133.2 | 650D4 | RIGBY | 650T2 | 2023-03-01 | Pass
83066 | 2023-02-09 | 2023-02-13 | Solar | 160 | 629D3 | KENNEBUNKPORT | 629T2 | 2023-03-07 | Pass
83040 | 2023-02-08 | 2023-02-23 | Solar | 999 | 837D2 | NEWPORT | 837T2 | 2023-03-07 | Fail | Pass | 2023-04-05
83025 | 2023-02-07 | 2023-02-09 | Solar | 995 | 256D2 | WINTHROP | 256T1 | 2023-02-23 | Fail | Pass | 2023-03-22
83038 | 2023-02-07 | 2023-02-09 | Solar | 100 | 447D4 | RUMFORD | 447T3 | 2023-02-24 | Pass
83018 | 2023-02-03 | 2023-02-09 | Solar | 300 | 620D1 | ELM STREET | 620T2 | 2023-02-28 | Fail | Pass | 2023-04-03
83014 | 2023-02-02 | 2023-02-13 | Solar | 200 | 630D2 | GOOSEFARE | 630T1 | 2023-03-07 | Pass
83016 | 2023-02-02 | 2023-03-03 | Solar | 240 | 630D4 | GOOSEFARE | 630T1 | 2023-04-04 | Fail |  |  | Yes
82985 | 2023-01-30 | 2023-02-09 | Solar | 200 | 656D2 | SANFORD INDUSTRIAL PARK | 656T1 | 2023-02-21 | Pass
82971 | 2023-01-27 | 2023-02-01 | Solar | 100 | 634D4 | MAY STREET | 634T1 | 2023-02-22 | Pass
82924 | 2023-01-20 | 2023-01-23 | Fuel Cell | 975 | 636D2 | MUSSEY ROAD | 636T1 | 2023-03-03 | Pass
82927 | 2023-01-20 | 2023-01-24 | Solar | 500 | 447D4 | RUMFORD | 447T3 | 2023-02-14 | Pass
82884 | 2023-01-10 | 2023-01-19 | Solar | 50 | 618D3 | EAST DEERING | 618T2 | 2023-02-13 | Pass
82862 | 2023-01-06 | 2023-01-10 | Solar | 400 | 813D3 | DEXTER | 813T2 | 2023-01-13 | Pass |  |  | Yes
82873 | 2023-01-06 | 2023-01-11 | Solar | 360 | 650D4 | RIGBY | 650T2 | 2023-02-06 | Pass
82874 | 2023-01-06 | 2023-02-06 | Solar | 999 | 821D1 | GUILFORD | 821T1 | 2023-02-07 | Fail | Fail | 2023-03-02 | Yes
82822 | 2023-01-05 | 2023-01-09 | Solar | 145.92 | 251D1 | UNION | 251T1 | 2023-01-26 | Fail | Pass | 2023-02-01
82781 | 2022-12-28 | 2023-01-18 | Fuel Cell | 975 | 630D1 | GOOSEFARE | 630T1 | 2023-01-26 | Pass |  |  | Yes
82816 | 2022-12-28 | 2023-01-03 | Solar | 34.6 | 634D3 | MAY STREET | 634T2 | 2023-01-30 | Pass
82771 | 2022-12-22 | 2023-01-06 | Solar | 996 | 657D4 | SANFORD SWITCH | 657T1 | 2023-01-30 | Fail | Pass | 2023-04-18
82775 | 2022-12-22 | 2023-01-16 | Solar | 45 | 874D1 | BELFAST 115 | 874T2 | 2023-01-17 | Pass
82725 | 2022-12-19 | 2022-12-21 | Solar | 92.16 | 246D2 | THOMASTON CREEK | 246T1 | 2022-12-24 | Pass
82710 | 2022-12-15 | 2022-12-21 | Solar | 50 | 803D5 | BELFAST WEST SIDE | 803T1 | 2022-12-23 | Pass
82708 | 2022-12-14 | 2023-01-09 | Solar | 500 | 238D1 | MESSINA | 238T1 | 2023-01-11 | Fail | Pass | 2023-03-27
82709 | 2022-12-14 |  |  | 999 | 610D2 | BONNY EAGLE | 610T4 |  |  |  |  | Yes
82674 | 2022-12-13 | 2023-01-03 | Solar | 999 | 821D1 | GUILFORD | 821T1 | 2023-01-03 | Fail |  |  | Yes
82683 | 2022-12-13 | 2023-01-11 | Solar | 700 | 624D2 | FORT HILL | 624T1 | 2023-02-07 | Pass
82671 | 2022-12-08 | 2022-12-12 | Fuel Cell | 650 | 420D3 | HOTEL ROAD | 420T2 | 2023-01-16 | Pass
82670 | 2022-12-07 | 2023-01-31 | Solar | 30.8 | 245D1 | STICKNEYS CORNER | 245T1 | 2023-02-06 | Fail |  |  | Yes
82668 | 2022-12-06 | 2023-01-10 | Solar | 51.9 | 225D4 | FREEPORT | 225T1 | 2023-01-16 | Pass
82669 | 2022-12-06 | 2022-12-23 | Solar | 975 | 239D7 | PARK STREET | 239T2 | 2023-01-12 | Fail | Fail | 2023-02-22 | Yes
82584 | 2022-11-29 | 2022-12-12 | Solar | 890 | 420D6 | HOTEL ROAD | 420T1 | 2022-12-13 | Fail | Pass | 2023-02-23 | Yes
82578 | 2022-11-28 | 2023-01-12 | Solar | 26 | 860D1 | UNITY | 860T1 | 2022-12-14 | Pass
82577 | 2022-11-25 | 2022-12-14 | Solar | 27 | 860D1 | UNITY | 860T1 | 2022-12-14 | Pass | Pass
82564 | 2022-11-23 | 2022-12-12 | Solar | 1950 | 693D1 | SCARBOROUGH | 693T1 | 2023-02-13 | Fail |  |  | Yes
82576 | 2022-11-23 | 2022-12-14 | Solar | 34.2 | 808D1 | CARMEL | 808T1 | 2022-12-14 | Pass
82563 | 2022-11-22 | 2023-01-10 | Solar | 37.3332 | 250D2 | TOPSHAM | 250T2 | 2023-01-13 | Fail | Pass | 2023-04-13
82543 | 2022-11-21 | 2022-12-02 | Solar | 54 | 663D2 | SOUTH BERWICK | 663T1 | 2023-12-12 | Pass
82547 | 2022-11-21 | 2022-11-30 | Fuel Cell | 975 | 421D2 | CHALLENGER | 421T1 |  | Fail |  |  | Yes
82517 | 2022-11-16 | 2023-01-10 | Solar | 67.3 | 618D1 | EAST DEERING | 618T1 | 2023-02-08 | Pass
82518 | 2022-11-16 | 2022-11-29 | Fuel Cell | 975 | 424D4 | LEWISTON LOWER | 424T3 | 2023-01-13 | Pass
82496 | 2022-11-14 | 2022-11-18 | Fuel Cell | 975 | 688D1 | KITTERY | 688T1 | 2023-01-15 | Fail |  |  | Yes
82498 | 2022-11-14 | 2022-11-16 | Solar | 50 | 213D3 | BRUNSWICK WEST SIDE | 213T1 | 2022-11-17 | Pass
82499 | 2022-11-14 | 2022-11-29 | Solar | 500 | 233D2 | MANCHESTER | 233T1 | 2022-11-30 | Fail | Pass | 2023-05-01
82487 | 2022-11-10 | 2023-01-19 | Solar | 69.4 | 430D1 | LOVELL | 430T1 | 2023-01-30 | Pass
82486 | 2022-11-07 | 2022-11-30 | Fuel Cell | 975 | 630D2 | GOOSEFARE | 630T1 | 2023-01-06 | Pass
82485 | 2022-11-05 | 2022-11-30 | Fuel Cell | 975 | 420D6 | HOTEL ROAD | 420T1 | 2023-01-09 | Pass
82455 | 2022-11-03 | 2022-12-05 | Solar | 100 | 250D2 | TOPSHAM | 250T2 | 2023-05-10 | Pass | Pass | 2023-02-13
82439 | 2022-11-01 | 2022-11-01 | Solar | 950 | 858D4 | STURTEVANT | 858T2 | 2022-11-01 | Pass |  |  | Yes
82452 | 2022-11-01 | 2022-11-18 | Solar | 96 | 246D3 | THOMASTON CREEK | 246T1 | 2022-11-23 | Fail |  |  | Yes
82432 | 2022-10-28 | 2022-11-29 | Solar | 66 | 675D1 | WESTERN AVENUE | 675T1 | 2022-12-27 | Fail | Pass | 2023-03-20
82404 | 2022-10-26 | 2022-11-15 | Solar | 750 | 445D1 | RAYMOND 115 KV | 445T1 | 2022-11-17 | Fail |  | 2023-06-21 | Yes
82373 | 2022-10-21 | 2022-11-01 | Solar | 104.16 | 245D2 | STICKNEYS CORNER | 245T1 | 2022-11-02 | Fail | Pass | 2023-02-01
82363 | 2022-10-20 | 2022-11-16 | Fuel Cell | 975 | 636D2 | MUSSEY ROAD | 636T1 | 2022-12-27 | Fail |  |  | Yes
82366 | 2022-10-20 | 2022-10-24 | Solar | 996 | 657D4 | SANFORD SWITCH | 657T1 | 2022-12-27 | Fail | Pass | 2023-04-18
82339 | 2022-10-18 | 2022-11-14 | Solar | 975 | 841D1 | PHILLIPS/STRONG | 841T1 | 2023-01-25 | Fail | Pass | 2023-02-23
82340 | 2022-10-18 | 2022-12-02 | Solar | 975 | 839D2 | OAKLAND | 839T1 | 2022-12-02 | Fail | Fail | 2023-03-30 | Yes
82322 | 2022-10-17 | 2022-10-19 | Solar | 995 | 667D1 | SOUTH SANFORD | 667T2 | 2022-12-01 | Fail | Pass | 2023-03-22 | Yes
82324 | 2022-10-17 | 2022-10-17 | Solar | 975 | 450D1 | SABATTUS | 450T1 | 2022-11-22 | Fail | Fail | 2023-01-23 | Yes
82261 | 2022-10-05 | 2022-11-01 | Solar | 950 | 858D4 | STURTEVANT | 858T2 | 2022-11-02 | Pass
82255 | 2022-10-04 | 2022-10-04 | Solar | 975 | 821D1 | GUILFORD | 821T1 | 2022-10-14 | Fail | Pass | 2023-02-07
82254 | 2022-10-03 | 2022-10-20 | Solar | 35 | 605D1 | BIDDEFORD PUMPING STATION | 605T1 | 2022-12-09 | Fail | Pass | 2023-03-09
82233 | 2022-09-27 | 2022-10-04 | Solar | 100 | 659D9 | SEWALL STREET | 659T2 | 2022-10-12 | Pass
82226 | 2022-09-23 | 2022-09-27 | Solar | 349.998 | 813D1 | DEXTER | 813T1 | 2022-09-28 | Pass |  |  | Yes
82232 | 2022-09-23 | 2022-10-20 | Solar | 45.6 | 261D3 | BATH | 261T2 | 2022-10-24 | Pass
82219 | 2022-09-21 | 2022-09-30 | Solar | 33.3 | 659D9 | SEWALL STREET | 659T2 | 2022-10-13 | Pass
82201 | 2022-09-20 | 2022-09-30 | Solar | 390 | 261D3 | BATH | 261T2 | 2022-10-06 | Fail | Pass | 2022-11-30
82202 | 2022-09-20 | 2022-12-02 | Solar | 996 | 407D1 | BRYANT POND | 407T1 | 2022-12-05 | Fail |  |  | Yes
82186 | 2022-09-15 | 2022-10-03 | Solar | 348 | 250D1 | TOPSHAM | 250T2 | 2022-10-03 | Fail |  |  | Yes
82187 | 2022-09-15 | 2022-10-04 | Solar | 30.4 | 638D1 | NORTH LIMINGTON | 638T1 | 2022-10-13 | Pass
82151 | 2022-09-09 | 2022-09-09 | Solar | 160 | 213D3 | BRUNSWICK WEST SIDE | 213T1 | 2022-09-23 | Pass
82152 | 2022-09-09 | 2022-09-12 | Solar | 260 | 273D4 | BRUNSWICK HYDRO | 273T2 | 2022-10-04 | Fail | Pass | 2023-01-23
82143 | 2022-09-08 | 2022-09-30 | Solar | 228 | 860D1 | UNITY | 860T1 | 2023-03-09 | Fail |  |  | Yes
82122 | 2022-09-07 | 2022-10-24 | Solar | 46 | 695D2 | LEBANON | 695T1 | 2023-12-27 | Pass
82092 | 2022-08-30 | 2022-09-12 | Solar | 50 | 644D3 | PLEASANT HILL | 644T2 | 2022-10-14 | Pass
82071 | 2022-08-29 | 2022-08-29 | Solar | 32.8 | 620D4 | ELM STREET | 620T2 | 2022-09-08 | Pass
82084 | 2022-08-29 | 2022-09-09 | Solar | 1000 | 416D1 | GRAY | 416T2 | 2022-10-07 | Fail | Fail |  | Yes
82055 | 2022-08-25 | 2022-12-01 | Solar | 275 | 823D2 | HARRIS | 823T5 | 2023-02-24 | Pass
82051 | 2022-08-23 | 2022-08-26 | Solar | 34.2 | 800D1 | LINCOLNVILLE | 800T1 | 2022-09-02 | Fail | Pass | 2022-11-30
82053 | 2022-08-23 | 2022-08-23 | Solar | 1000 | 846D1 | PROSPECT | 846T1 | 2022-09-02 | Fail | Pass | 2022-11-11
82044 | 2022-08-22 | 2022-08-22 | Solar | 30 | 225D4 | FREEPORT | 225T1 | 2022-08-23 | Pass
82009 | 2022-08-15 | 2022-08-18 | Solar | 30 | 858D2 | STURTEVANT | 858T1 | 2022-08-22 | Pass
82010 | 2022-08-15 | 2022-08-18 | Solar/Battery | 996 | 445D1 | RAYMOND 115 KV | 445T1 | 2022-08-22 | Fail | Fail | 2022-09-21 | Yes
82011 | 2022-08-15 | 2022-08-18 | Solar | 38 | 420D7 | HOTEL ROAD | 420T1 | 2022-08-22 | Pass
82007 | 2022-08-12 | 2022-08-30 | Solar | 1875 | 272D4 | NORTH AUGUSTA | 272T1 | 2022-09-14 | Fail | Fail | 2022-11-08 | Yes
82008 | 2022-08-12 | 2022-08-19 | Solar | 34.6 | 204D1 | WASHINGTON ST (BATH) | 204T2 | 2022-09-14 | Pass
81972 | 2022-08-10 | 2022-08-17 | Solar | 975 | 246D2 | THOMASTON CREEK | 246T1 | 2022-09-09 | Fail | Fail | 2022-10-21 | Yes
81959 | 2022-08-08 | 2022-09-14 | Solar | 2000 | 431D2 | MECHANIC FALLS | 431T1 | 2022-09-13 | Fail | Fail |  | Yes
81960 | 2022-08-08 | 2022-09-28 | Solar | 749 | 860D2 | UNITY | 860T1 | 2022-10-05 | Fail | Fail | 2022-11-21 | Yes
81961 | 2022-08-08 | 2022-09-28 | Solar | 749 | 209D3 | BOOTHBAY HARBOR | 209T1 | 2022-09-30 |  |  |  | Yes
81962 | 2022-08-08 | 2022-08-15 | Solar | 42.8 | 216D2 | CONY ROAD | 216T1 | 2022-08-15 | Fail | Pass | 2022-12-02
81963 | 2022-08-08 | 2022-08-08 | Solar | 749 | 250D1 | TOPSHAM | 250T2 | 2022-09-02 | Fail | Pass | 2022-11-02
81964 | 2022-08-08 | 2022-09-28 | Solar | 749 | 817D3 | FAIRFIELD | 817T1 | 2022-09-30 |  |  |  | Yes
81965 | 2022-08-08 | 2022-08-15 | Solar | 749 | 438D1 | PAPOOSE POND | Tap off of Transmission Line | 2022-09-12 | Fail | Pass | 2022-12-12
81966 | 2022-08-08 | 2022-08-15 | Solar | 749 | 850D2 | SEARSPORT | 850T1 | 2022-09-14 | Fail | Pass | 2022-12-13
81967 | 2022-08-08 | 2022-08-15 | Solar | 749 | 837D2 | NEWPORT | 837T2 | 2022-08-29 | Fail | Fail | 2023-01-16 | Yes
81968 | 2022-08-08 | 2022-08-15 | Solar | 749 | 861D9 | VASSALBORO | 861T1 | 2022-09-13 | Fail | Fail | 2022-11-06 | Yes
81956 | 2022-08-05 | 2022-08-11 | Solar | 725 | 412D3 | DEER RIPS | 412T4 | 2022-09-13 | Pass
81957 | 2022-08-05 | 2022-08-11 | Solar | 725 | 412D3 | DEER RIPS | 412T4 | 2022-09-26 | Fail | Fail | 2022-11-21 | Yes
81958 | 2022-08-05 | 2022-08-12 | Solar | 2000 | 602D2 | BASSETT | 602T1 | 2022-08-29 | Fail | Pass | 2022-11-02 | Yes
81947 | 2022-08-04 | 2022-08-15 | Solar | 153.6 | 251D1 | UNION | 251T1 | 2022-08-29 | Fail |  | 2022-10-10 | Yes
81955 | 2022-08-04 | 2022-08-11 | Solar | 450 | 811D1 | CORINNA | 811T1 | 2022-08-30 | Pass |  |  | Yes
81945 | 2022-08-03 | 2022-08-08 | Solar | 500 | 866D2 | WESTON HYDRO | 866T2 | 2022-10-04 | Pass |  |  | Yes
81942 | 2022-08-02 | 2022-08-08 | Solar | 996 | 470D1 | SAND ROAD TAP | 470T1 | 2022-08-09 | Fail | Pass | 2022-09-27
81911 | 2022-07-29 | 2022-08-05 | Solar | 530 | 861D9 | VASSALBORO | 861T1 | 2022-08-31 | Fail | Pass | 2022-10-12 | Yes
81912 | 2022-07-29 | 2022-08-05 | Solar | 32.8 | 225D3 | FREEPORT | 225T2 | 2022-08-08 | Fail | Pass | 2022-11-07
81910 | 2022-07-27 | 2022-08-04 | Solar | 996 | 861D9 | VASSALBORO | 861T1 | 2022-08-11 | Fail | Fail | 2022-10-05 | Yes
81908 | 2022-07-26 | 2022-08-04 | Solar | 165 | 252D2 | WALDOBORO | 252T1 |  |  |  |  | Yes
81909 | 2022-07-26 | 2022-08-04 | Solar | 996 | 837D2 | NEWPORT | 837T2 | 2022-08-29 | Fail |  | 2022-10-03 | Yes
81849 | 2022-07-25 | 2022-08-01 | Solar | 996 | 438D1 | PAPOOSE POND | Tap off of Transmission Line | 2022-08-24 | Fail | Fail | 2022-10-10 | Yes
81850 | 2022-07-25 | 2022-08-12 | Solar | 996 | 850D2 | SEARSPORT | 850T1 | 2022-09-06 | Fail | Fail | 2022-10-17 | Yes
81851 | 2022-07-25 | 2022-08-25 | Solar | 2000 | 667D1 | SOUTH SANFORD | 667T2 | 2022-10-12 | Fail |  |  | Yes
81852 | 2022-07-25 |  | Solar | 1700 | 626D1 | HIGH STREET | 626T1 |  |  |  |  | Yes
81894 | 2022-07-25 | 2022-08-15 | Solar | 999 | 866D2 | WESTON HYDRO | 866T2 | 2022-08-29 | Fail | Fail | 2022-09-21 | Yes
81895 | 2022-07-25 | 2022-08-15 | Solar | 400 | 454D2 | TURNER | 454T1 | 2022-08-25 | Pass
81896 | 2022-07-25 | 2022-08-01 | Solar | 730 | 412D3 | DEER RIPS | 412T4 | 2022-08-01 | Fail |  |  | Yes
81847 | 2022-07-21 |  |  | 210 | 638D2 | NORTH LIMINGTON | 638T1 |  |  |  |  | Yes
81848 | 2022-07-21 | 2022-07-21 | Solar | 850 | 412D3 | DEER RIPS | 412T4 | 2022-08-29 | Fail | Fail | 2022-10-17 | Yes
81817 | 2022-07-20 | 2022-07-27 | Solar | 1000 | 837D2 | NEWPORT | 837T2 | 2022-08-29 | Fail | Fail | 2022-10-10 | Yes
81819 | 2022-07-20 | 2022-07-27 | Solar | 999 | 821D3 | GUILFORD | 821T2 | 2022-09-13 | Fail | Pass | 2022-11-02 | Yes
81816 | 2022-07-19 | 2022-07-25 | Solar | 996 | 860D2 | UNITY | 860T1 | 2022-08-02 | Fail |  | 2022-09-02 | Yes
81814 | 2022-07-18 | 2022-07-25 |  | 50 | 813D1 | DEXTER | 813T1 | 2022-07-26 | Pass
81815 | 2022-07-18 | 2022-08-02 | Solar | 124 | 225D4 | FREEPORT | 225T1 | 2022-08-16 | Fail |  |  | Yes
81813 | 2022-07-16 | 2022-07-27 | Solar | 30 | 412D4 | DEER RIPS | 412T4 | 2022-08-02 | Fail | Pass | 2023-01-09
81810 | 2022-07-15 | 2022-07-22 | Solar | 996 | 209D3 | BOOTHBAY HARBOR | 209T1 | 2022-08-18 | Fail | Pass | 2022-10-05
81811 | 2022-07-15 | 2022-07-22 | Solar | 996 | 250D1 | TOPSHAM | 250T2 | 2022-08-18 | Fail |  |  | Yes
81812 | 2022-07-15 | 2022-07-22 | Solar | 996 | 817D3 | FAIRFIELD | 817T1 | 2022-08-18 | Fail |  | 2022-09-07 | Yes
81755 | 2022-07-12 | 2022-07-12 | Solar | 34.2 | 213D2 | BRUNSWICK WEST SIDE | 213T2 | 2022-09-07 | Pass
81769 | 2022-07-12 | 2022-07-22 | Solar | 76 | 437D2 | OXFORD | 437T1 | 2022-08-01 | Fail | Pass | 2001-01-01
81754 | 2022-07-08 | 2022-07-12 | Solar | 190 | 457D2 | MONMOUTH | 457T2 | 2022-07-27 | Pass |  |  | Yes
81753 | 2022-07-05 | 2022-07-12 | Solar | 50 | 803D4 | BELFAST WEST SIDE | 803T1 | 2022-07-25 | Pass
81752 | 2022-07-01 | 2022-07-12 | Solar | 540 | 250D2 | TOPSHAM | 250T2 | 2022-07-25 | Fail | Pass | 2022-09-13
81681 | 2022-06-27 | 2022-06-28 | Solar | 26.3 | 620D3 | ELM STREET | 620T2 | 2022-08-03 | Pass
81680 | 2022-06-24 | 2022-07-08 | Solar | 466 | 255D2 | WEST STREET | 255T1 | 2022-08-01 | Pass
81652 | 2022-06-21 | 2022-06-24 | Solar | 80 | 693D1 | SCARBOROUGH | 693T1 | 2022-07-29 | Fail | Pass
81653 | 2022-06-21 | 2022-06-27 | Solar | 115.2 | 470D1 | SAND ROAD TAP | 470T1 | 2022-07-08 | Pass
81658 | 2022-06-21 | 2022-06-27 | Solar | 67.3 | 634D3 | MAY STREET | 634T2 | 2022-07-05 | Pass
81675 | 2022-06-21 | 2022-06-27 | Solar | 990 | 431D1 | MECHANIC FALLS | 431T2 | 2022-07-08 | Fail |  |  | Yes
81676 | 2022-06-21 | 2022-06-29 | Solar | 875 | 412D3 | DEER RIPS | 412T4 | 2022-07-27 | Fail |  |  | Yes
81677 | 2022-06-21 | 2022-06-29 | Solar | 875 | 412D3 | DEER RIPS | 412T4 | 2022-07-27 | Fail |  |  | Yes
81678 | 2022-06-21 | 2022-06-29 | Solar | 1000 | 858D4 | STURTEVANT | 858T2 | 2022-08-01 | Fail |  |  | Yes
81679 | 2022-06-21 | 2022-06-29 | Solar | 1000 | 858D4 | STURTEVANT | 858T2 | 2022-08-01 | Fail |  |  | Yes
81650 | 2022-06-20 | 2022-06-24 | Solar | 34.2 | 842D1 | PITTSFIELD | 842T1 | 2022-10-11 | Pass
81651 | 2022-06-20 | 2022-06-24 | Solar | 37.6 | 214D1 | CAMDEN | 214T2 | 2022-07-08 | Pass
81628 | 2022-06-17 | 2022-06-24 | Solar | 244 | 839D2 | OAKLAND | 839T1 | 2022-07-09 | Pass |  |  | Yes
81512 | 2022-06-02 | 2022-06-08 | Solar | 975 | 852D1 | SHAWMUT | 852T3 | 2022-06-15 | Fail | Fail |  | Yes
81513 | 2022-06-02 | 2022-06-08 | Solar | 975 | 873D1 | COUNTY ROAD | 873T1 | 2022-06-15 | Fail | Pass | 2022-09-01
81515 | 2022-06-02 | 2022-06-08 | Solar | 975 | 873D1 | COUNTY ROAD | 873T1 | 2022-06-27 | Fail |  |  | Yes
81516 | 2022-06-02 | 2022-06-08 | Solar | 975 | 454D2 | TURNER | 454T1 | 2022-06-15 | Fail |  |  | Yes
81506 | 2022-05-31 | 2022-06-06 | Solar | 975 | 870D1 | WINSLOW | 870T4 | 2022-07-06 | Fail |  | 2022-10-11 | Yes
81508 | 2022-05-31 | 2022-06-06 | Solar | 975 | 853D1 | SKOWHEGAN NORTH SIDE | 853T1 | 2022-06-15 | Fail |  |  | Yes
81509 | 2022-05-31 | 2022-06-06 | Solar | 975 | 853D1 | SKOWHEGAN NORTH SIDE | 853T1 | 2022-06-15 | Fail |  |  | Yes
81510 | 2022-05-31 | 2022-06-06 | Solar | 30 | 214D3 | CAMDEN | 214T1 | 2022-06-15 | Pass
81511 | 2022-05-31 | 2022-06-06 | Solar | 350 | 866D2 | WESTON HYDRO | 866T2 | 2022-07-19 | Pass
81489 | 2022-05-27 | 2022-05-31 | Solar | 475 | 412D3 | DEER RIPS | 412T4 | 2022-06-08 | Pass
81435 | 2022-05-26 | 2022-06-01 | Solar | 975 | 412D3 | DEER RIPS | 412T4 | 2022-06-08 | Fail |  |  | Yes
81462 | 2022-05-26 | 2022-06-06 | Solar | 50 | 636D1 | MUSSEY ROAD | 636T1 | 2022-08-11 | Pass
81465 | 2022-05-26 | 2022-06-01 | Solar | 900 | 255D2 | WEST STREET | 255T1 | 2022-06-15 | Fail |  |  | Yes
81486 | 2022-05-26 | 2022-06-01 | Solar | 49 | 675D3 | WESTERN AVENUE | 675T1 | 2022-06-15 | Pass
81413 | 2022-05-23 | 2022-05-24 | Solar | 975 | 870D1 | WINSLOW | 870T4 | 2022-06-08 | Fail |  |  | Yes
81434 | 2022-05-23 | 2022-05-31 | Solar | 30.72 | 634D1 | MAY STREET | 634T1 | 2022-07-08 | Pass
81409 | 2022-05-20 | 2022-05-27 | Solar | 200 | 237D1 | MCCOYS | 237T1 | 2022-06-17 | Pass |  |  | Yes
81411 | 2022-05-20 | 2022-06-20 | Solar | 63.954 | 219D2 | DAMARISCOTTA MILLS | 219T1 | 2022-07-21 | Pass
81396 | 2022-05-19 | 2022-05-23 | Solar | 337.5 | 603D2 | BERWICK | 603T1 | 2022-08-11 | Fail | Pass | 2022-10-31
81395 | 2022-05-17 | 2022-06-06 | Solar | 975 | 457D2 | MONMOUTH | 457T2 | 2022-06-08 | Fail |  |  | Yes
81393 | 2022-05-16 | 2022-05-31 | Solar | 125 | 647D1 | PRIDES CORNER | 647T2 | 2022-06-14 | Pass
81394 | 2022-05-16 | 2022-05-23 | Solar | 975 | 457D2 | MONMOUTH | 457T2 | 2022-06-10 | Fail | Pass | 2022-07-29
81392 | 2022-05-13 | 2022-05-18 | Solar | 84.6 | 644D4 | PLEASANT HILL | 644T3 | 2022-06-22 | Pass
81390 | 2022-05-12 | 2022-05-18 | Solar | 67 | 239D7 | PARK STREET | 239T2 | 2022-06-14 | Pass
81346 | 2022-05-10 | 2022-05-18 | Solar | 46.08 | 253D1 | WARREN | 253T1 | 2022-05-31 | Pass
81270 | 2022-05-09 | 2022-05-13 | Solar | 104.1 | 430D1 | LOVELL | 430T1 |  |  |  |  | Yes
81268 | 2022-05-04 | 2022-05-09 | Solar | 50 | 644D4 | PLEASANT HILL | 644T3 | 2022-07-08 | Pass
81265 | 2022-05-03 | 2022-05-09 | Solar | 975 | 839D2 | OAKLAND | 839T1 | 2022-05-26 | Fail |  |  | Yes
81267 | 2022-05-03 | 2022-07-14 | Solar | 975 | 839D2 | OAKLAND | 839T1 | 2022-05-26 | Fail |  |  | Yes
81261 | 2022-05-02 | 2022-05-09 | Solar | 34.2 | 668D5 | SPRING STREET | 668T2 | 2022-10-13 | Pass
81262 | 2022-05-02 | 2022-05-09 | Solar | 975 | 663D2 | SOUTH BERWICK | 663T1 | 2022-06-22 | Fail |  |  | Yes
81264 | 2022-05-02 | 2022-05-09 | Solar | 150 | 821D1 | GUILFORD | 821T1 | 2022-08-30 | Pass
81490 | 2022-04-30 | 2022-05-05 | Solar | 800 | 263D1 | BOWMAN STREET | 34 kV BUS 2 | 2022-06-15 | Fail | Pass | 2022-08-16
81259 | 2022-04-29 | 2022-04-29 | Solar | 975 | 638D2 | NORTH LIMINGTON | 638T1 | 2022-07-06 | Fail |  |  | Yes
81260 | 2022-04-29 | 2022-05-05 | Solar | 650 | 861D9 | VASSALBORO | 861T1 | 2022-06-02 | Pass |  |  | Yes
81257 | 2022-04-28 | 2022-05-05 | Solar | 999 | 638D1 | NORTH LIMINGTON | 638T1 |  |  |  |  | Yes
81258 | 2022-04-28 | 2022-05-16 | Solar | 975 | 638D2 | NORTH LIMINGTON | 638T1 | 2022-07-06 | Fail |  |  | Yes
81236 | 2022-04-27 | 2022-05-05 | Solar | 28.8 | 214D3 | CAMDEN | 214T1 | 2022-05-17 | Pass |  |  | Yes
81223 | 2022-04-25 | 2022-04-25 | Other | 350 | 435D1 | NORWAY | 435T2 | 2022-07-21 | Pass
81222 | 2022-04-21 | 2022-04-29 | Solar | 975 | 663D2 | SOUTH BERWICK | 663T1 | 2022-07-06 | Fail |  |  | Yes
81170 | 2022-04-20 | 2022-04-27 | Solar | 750 | 695D2 | LEBANON | 695T1 | 2022-05-05 | Fail |  |  | Yes
81171 | 2022-04-20 | 2022-04-25 | Solar | 850 | 631D1 | LAMBERT STREET | 631T1 | 2022-07-08 | Fail | Pass | 2022-08-18
81179 | 2022-04-20 | 2022-04-27 | Solar | 750 | 695D2 | LEBANON | 695T1 | 2022-05-26 | Fail |  |  | Yes
81198 | 2022-04-20 | 2022-04-27 | Solar | 30 | 450D1 | SABATTUS | 450T1 | 2022-04-27 | Pass
81200 | 2022-04-20 | 2022-04-27 | Solar | 975 | 841D1 | PHILLIPS/STRONG | 841T1 | 2022-05-19 | Fail | Pass | 2022-07-21
81201 | 2022-04-20 | 2022-04-27 | Solar | 975 | 457D1 | MONMOUTH | 457T1 | 2022-05-17 | Fail | Pass | 2022-08-02
81203 | 2022-04-20 | 2022-04-27 | Solar | 975 | 841D1 | PHILLIPS/STRONG | 841T1 | 2022-05-18 | Fail |  |  | Yes
81140 | 2022-04-14 | 2022-04-18 | Solar | 34.6 | 611D1 | BRIGHTON AVENUE | 611T1 | 2023-01-24 | Pass
81132 | 2022-04-13 | 2022-04-15 | Solar | 172 | 874D1 | BELFAST 115 | 874T2 | 2022-05-27 | Pass |  |  | Yes
81130 | 2022-04-03 | 2022-04-15 | Solar | 975 | 225D4 | FREEPORT | 225T1 | 2022-06-02 | Fail | Pass | 2022-08-03 | Yes
81019 | 2022-03-30 | 2022-04-07 | Solar | 975 | 225D4 | FREEPORT | 225T1 | 2022-04-08 | Fail |  |  | Yes
81015 | 2022-03-29 | 2022-04-04 | Solar | 650 | 861D9 | VASSALBORO | 861T1 | 2022-04-28 | Fail |  |  | Yes
81016 | 2022-03-29 | 2022-04-04 | Solar | 280 | 865D5 | WEST WATERVILLE | 865T2 | 2022-05-17 | Fail | Pass | 2022-06-27
81017 | 2022-03-29 | 2022-04-07 | Solar | 500 | 444D2 | RAYMOND 34 KV | 444T1 | 2022-04-25 | Fail | Pass | 2022-08-12 | Yes
81018 | 2022-03-29 | 2022-04-07 | Solar | 34.2 | 405D2 | FRYEBURG TAP | 405T1 | 2022-04-25 | Fail | Pass | 2022-07-18
81006 | 2022-03-25 | 2022-04-21 | Solar | 475 | 239D10 | PARK STREET | 239T5 | 2022-05-19 | Pass |  |  | Yes
81005 | 2022-03-24 | 2022-04-04 | Solar | 80 | 431D1 | MECHANIC FALLS | 431T2 | 2022-04-21 | Pass
80962 | 2022-03-22 | 2022-03-22 | Solar | 975 | 244D2 | SOUTH CHINA | 244T1 | 2022-04-19 | Fail |  |  | Yes
80971 | 2022-03-22 | 2022-03-29 | Solar | 975 | 244D2 | SOUTH CHINA | 244T1 | 2022-04-29 | Fail | Pass | 2022-07-29 | Yes
80871 | 2022-03-21 | 2022-03-22 | Solar | 33.8 | 240D1 | RICHMOND | 240T1 | 2022-04-26 | Fail | Pass | 2022-06-16
80892 | 2022-03-21 | 2022-03-25 | Solar | 975 | 239D10 | PARK STREET | 239T5 | 2022-05-17 | Pass
80977 | 2022-03-21 | 2022-03-31 | Solar | 2000 | 457D2 | MONMOUTH | 457T2 | 2022-04-21 | Fail |  |  | Yes
80842 | 2022-03-02 | 2022-03-17 | Solar | 975 | 450D1 | SABATTUS | 450T1 | 2022-04-15 | Fail |  |  | Yes
80841 | 2022-03-01 | 2022-03-08 | Solar | 1990 | 801D1 | ANSON | 801T1 | 2022-03-29 | Fail |  |  | Yes
80837 | 2022-02-28 | 2022-03-17 | Solar | 41.04 | 837D2 | NEWPORT | 837T2 | 2022-03-22 | Fail |  |  | Yes
80838 | 2022-02-28 | 2022-03-17 | Solar | 1992 | 806D2 | BUCKSPORT | 806T3 | 2022-03-30 | Fail | Pass | 2022-06-25 | Yes
80825 | 2022-02-24 | 2022-03-09 | Solar | 1999 | 233D2 | MANCHESTER | 233T1 | 2022-03-30 | Fail | Fail | 2022-05-17 | Yes
80809 | 2022-02-21 | 2022-08-24 | Solar | 53.9 | 860D1 | UNITY | 860T1 | 2022-02-25 | Fail |  | 2022-06-14 | Yes
80824 | 2022-02-21 | 2022-02-24 | Solar | 48 | 678D1 | BAR MILLS | 678T4 |  |  |  |  | Yes
80807 | 2022-02-16 | 2022-02-23 | Solar | 975 | 817D3 | FAIRFIELD | 817T1 | 2022-03-03 | Fail |  |  | Yes
80808 | 2022-02-16 | 2022-02-23 | Solar | 975 | 861D8 | VASSALBORO | 861T1 | 2022-03-29 | Fail | Fail | 2022-05-19 | Yes
80726 | 2022-02-04 | 2022-02-09 | Solar | 975 | 853D1 | SKOWHEGAN NORTH SIDE | 853T1 | 2022-03-28 | Fail |  |  | Yes
80727 | 2022-02-04 | 2022-02-09 | Solar | 975 | 874D1 | BELFAST 115 | 874T2 | 2022-03-07 | Fail |  |  | Yes
80728 | 2022-02-04 | 2022-02-10 | Solar | 975 | 428D3 | LIVERMORE FALLS | 428T1 | 2022-03-04 | Fail | Fail | 2022-06-03 | Yes
80736 | 2022-02-04 | 2022-02-10 | Solar | 975 | 420D7 | HOTEL ROAD | 420T1 | 2022-03-28 | Pass
80737 | 2022-02-04 | 2022-02-09 | Solar | 975 | 420D4 | HOTEL ROAD | 420T1 | 2022-03-03 | Fail |  |  | Yes
80725 | 2022-02-03 | 2022-02-09 | Solar | 975 | 866D2 | WESTON HYDRO | 866T2 | 2022-02-11 | Fail |  |  | Yes
80701 | 2022-01-31 | 2022-02-04 | Solar | 1750 | 850D1 | SEARSPORT | 850T1 | 2022-02-10 | Fail | Fail | 2022-04-18 | Yes
80677 | 2022-01-26 | 2022-02-02 | Solar | 200 | 693D2 | SCARBOROUGH | 693T1 | 2022-04-06 | Fail | Pass | 2022-05-23
80667 | 2022-01-25 | 2022-02-01 | Solar | 499 | 420D7 | HOTEL ROAD | 420T1 | 2022-02-10 | Pass
80655 | 2022-01-20 | 2022-01-27 | Solar | 36 | 650D1 | RIGBY | 650T1 | 2022-02-17 | Pass |  |  | Yes
80656 | 2022-01-20 | 2022-01-27 | Solar | 200 | 650D1 | RIGBY | 650T1 | 2022-02-17 | Pass |  |  | Yes
80657 | 2022-01-20 | 2022-01-27 | Solar | 72 | 650D1 | RIGBY | 650T1 | 2022-02-17 | Pass |  |  | Yes
80658 | 2022-01-20 | 2022-01-27 | Solar | 436 | 650D1 | RIGBY | 650T1 | 2022-02-10 | Fail | Pass | 2022-06-06 | Yes
80659 | 2022-01-20 | 2022-01-27 | Solar | 516 | 650D1 | RIGBY | 650T1 | 2022-02-17 | Pass |  |  | Yes
80609 | 2022-01-13 | 2022-01-20 | Solar | 1999 | 263D1 | BOWMAN STREET | 34 kV BUS 2 | 2022-01-21 | Fail | Pass | 2022-05-16 | Yes
80605 | 2022-01-12 | 2022-01-31 | Solar | 1500 | 412D4 | DEER RIPS | 412T4 | 2022-02-10 | Fail | Fail | 2022-05-12 | Yes
80644 | 2022-01-11 | 2022-01-27 | Solar | 72 | 668D4 | SPRING STREET | 668T4 | 2022-02-17 | Pass
80585 | 2022-01-04 | 2022-01-11 | Solar | 1000 | 861D9 | VASSALBORO | 861T1 | 2022-01-21 | Fail | Pass | 2022-06-20 | Yes

## Comments
Row 13 | AOR complete delayed waiting for manual payment | Kaiya Hoogkamp | 06/03/26 11:58 AM
Row 21 | 30016889302 was original account# | Nathan Lawrence | 07/30/26 11:25 AM
Row 22 | Application AOR delayed as customer needed to pay ombudsman fee | Kaiya Hoogkamp | 05/01/26 8:59 AM
Row 23 | *When we get the ESA back, request noti and field planner appt* | Kaiya Hoogkamp | 06/09/26 11:03 AM
Row 26 | ESA Started 4/13/2026 and Due 5/27/2026 | Kaiya Hoogkamp | 05/13/26 9:58 AM
Row 26 | Developer requested extension to get SLD back to us, moved timeline to 4/14/26 as a 1 time curtesy | Kaiya Hoogkamp | 04/09/26 7:29 AM
Row 27 | 4/9/26 provided extension to 4/15/26 while we review SDL and provide feedback so they can get the PE stamp | Kaiya Hoogkamp | 04/09/26 2:01 PM
Row 33 | Additional Cost Sharing Invoice: 910315847/920341256 | Kaiya Hoogkamp | 04/15/26 4:29 PM
Row 34 | 109280 - reapply of this project, moved POI | Kaiya Hoogkamp | 03/04/26 10:28 AM
Row 35 | Pending MPUC NEB Dispute resolution 3/6/2026 - NAL | Nathan Lawrence | 03/06/26 8:22 AM
Row 36 | Initial TS start date was 2/10/26, discovered updated SLD was required, new TS started 2/20/26 | Kaiya Hoogkamp | 03/12/26 2:29 PM
Row 38 | **ALERT RYLEY WHEN ESA IS COMPLETE PRIOR TO SENDING RESULTS*** | Kaiya Hoogkamp | 03/03/26 1:51 PM
Row 38 | invoice adjustment 910305208 | Kaiya Hoogkamp | 01/23/26 11:21 AM
Row 38 | 0910305207/920330192 duplicate invoice created for 81819 when trying to create ombudsman invoice for 109934 | Kaiya Hoogkamp | 01/23/26 11:16 AM
Row 39 | ESA delayed past original due date as we were waiting on an updated SLD from the developer before the study could be completed. | Kaiya Hoogkamp | 05/06/26 10:20 AM
Row 43 | 2/4/26 is marked as paid date for $1500 deposit, but there is no payment on the debtor. Will straight invoice | Kaiya Hoogkamp | 05/28/26 11:27 AM
Row 43 | followed up on IA and gave until 5/8/2026 before beginning 60 day cure process | Kaiya Hoogkamp | 05/06/26 2:24 PM
Row 44 | 1/12/26 developer requested additional time to gather SLD so we could deem the application complete. | Kaiya Hoogkamp | 01/15/26 7:55 AM
Row 48 | 5/22/2026 developer advised project should be completed in July 2027 | Kaiya Hoogkamp | 05/22/26 12:52 PM
Row 52 | duplicate application (109649) and has been withdrawn | Kaiya Hoogkamp | 01/30/26 1:15 PM
Row 53 | TS received from DP 1/5, sent to customer same day. | Nathan Lawrence | 04/06/26 12:15 PM
Row 53 | 1/5/25 project withdrew after failing ESA | Kaiya Hoogkamp | 01/05/26 11:21 AM
Row 54 | 5/21/2026 developer advised COC should be submitted in Fall 2026 | Kaiya Hoogkamp | 05/21/26 2:24 PM
Row 57 | 5/13/26 sent email requesting IA | Kaiya Hoogkamp | 05/13/26 9:42 AM
Row 59 | 12/31/2025 holding off on sending executable IA until we receive the $200 application payment | Kaiya Hoogkamp | 12/31/25 2:20 PM
Row 61 | $1000 refund draft: 0000002688 | Kaiya Hoogkamp | 12/10/25 9:49 AM
Row 61 | $2500 PIA cancelled (910299338/920324117) | Kaiya Hoogkamp | 12/09/25 9:31 AM
Row 62 | 5/21/2026 developer advised project start date August 2026, not sure of COC at this time | Kaiya Hoogkamp | 05/21/26 2:20 PM
Row 65 | 3/11/26 customer advised they are working on providing updated SLD so ESA can be completed. | Kaiya Hoogkamp | 03/11/26 3:51 PM
Row 67 | $11.90 application overpayment refund draft: 0000000164 | Kaiya Hoogkamp | 01/28/26 1:54 PM
Row 70 | 5/21/2026 developer advised no date to begin construction or COC at this time. | Kaiya Hoogkamp | 05/21/26 3:02 PM
Row 73 | Substation transformer upgrade required. ESA Study incomplete | Kaiya Hoogkamp | 04/15/26 3:49 PM
Row 74 | & 910296325/ 920320975 ($36.96). App invoice adjusted to $34.32 (910296870, 920321597) | Kaiya Hoogkamp | 11/20/25 10:27 AM
Row 74 | App invoice adjusted to $34.32 (910296870, | Kaiya Hoogkamp | 11/17/25 3:09 PM
Row 76 | 1/8/26 withdrawn due to ESA fail | Kaiya Hoogkamp | 01/08/26 9:48 AM
Row 78 | 5/21/2026 developer advised no date to begin construction or COC at this time. | Kaiya Hoogkamp | 05/21/26 3:02 PM
Row 79 | 5/21/2026 developer advised no date to begin construction or COC at this time. | Kaiya Hoogkamp | 05/21/26 2:57 PM
Row 80 | Partial ESA report, no estimates given. | BAILEY RODERICK | 07/15/26 10:04 AM
Row 80 | 11/6/25 Tech screen results sent late due to tech screen email being mislabeled in the subject line and missed. | Kaiya Hoogkamp | 11/06/25 2:53 PM
Row 81 | Partial ESA report, no estimates given. | BAILEY RODERICK | 07/15/26 10:03 AM
Row 82 | 5/21/2026 developer advised COC in June 2026 | Kaiya Hoogkamp | 05/21/26 2:43 PM
Row 87 | 5/21/2026 developer advised no date to begin construction or COC at this time. | Kaiya Hoogkamp | 05/21/26 2:56 PM
Row 88 | this developer also has a level 4 application at this location app # 657 | Denise Baker | 10/15/25 2:16 PM
Row 89 | 0000000924 ESA refund processed 5/1/2026 | Kaiya Hoogkamp | 05/01/26 2:55 PM
Row 90 | 5/21/2026 developer advised no date to begin construction or COC at this time. | Kaiya Hoogkamp | 05/21/26 2:52 PM
Row 92 | Partial ESA report, no 'Minor Modification' estimates given (FAIL >$30,000). | BAILEY RODERICK | 07/15/26 10:31 AM
Row 93 | Partial ESA report, no 'Minor Modification' estimates given (FAIL >$30,000). | BAILEY RODERICK | 07/15/26 10:31 AM
Row 94 | 5/21/2026 developer advised no date to begin construction or COC at this time. | Kaiya Hoogkamp | 05/21/26 2:55 PM
Row 95 | Original PIA $2500 (910297358/920322034) adjusted to $2490 to account for conversion from CAD to USD. | Kaiya Hoogkamp | 11/24/25 9:12 AM
Row 95 | $2098 application fee adjusted to $2098 due to $10 shortfall in wire payment conversion from CAD to USD. $10 waived per Ryley. Adj 910294011 | Sarah Glidden | 10/29/25 8:54 AM
Row 99 | Partial ESA report, no estimates given. | BAILEY RODERICK | 07/15/26 10:27 AM
Row 99 | 910317816 adjusted invoice to $0.00 | Kaiya Hoogkamp | 05/04/26 1:09 PM
Row 99 | ESA refund: 0000000198 ($1500) | Kaiya Hoogkamp | 02/04/26 4:17 PM
Row 100 | 5/6/26 left message at 207-743-8938, the main office, to have Joesph Galletta return signed IA | Kaiya Hoogkamp | 05/06/26 12:56 PM
Row 100 | 4/16/26 put into "cure" and given until 6/15/26 to return signed IA | Kaiya Hoogkamp | 04/27/26 1:02 PM
Row 100 | 4/13/26 called developer, phone does not pick up. Called customer at 207-743-8938 and left message to speak with Joseph Galletta, the GM who signed for the ESA, requesting returned signed IA. | Kaiya Hoogkamp | 04/13/26 11:00 AM
Row 101 | 12/23/2025 App withdrawn, failed ESA | Kaiya Hoogkamp | 12/23/25 3:04 PM
Row 101 | 0000002309 refund draft for $8 total | Kaiya Hoogkamp | 10/15/25 10:38 AM
Row 102 | 0000002309 refund draft for $8 total | Kaiya Hoogkamp | 10/15/25 10:39 AM
Row 103 | 0000002309 refund draft for $8 total | Kaiya Hoogkamp | 10/15/25 10:38 AM
Row 104 | ESA was restudied after initial FAIL. Updated ESA PASS dated 12/30/25. Sent to customer 1/13/26 | BAILEY RODERICK | 01/15/26 11:58 AM
Row 104 | 0000002309 refund draft for $8 total | Kaiya Hoogkamp | 10/15/25 10:38 AM
Row 106 | Partial ESA report, no estimates given. | BAILEY RODERICK | 07/15/26 10:28 AM
Row 107 | Partial ESA report, no estimates given. | BAILEY RODERICK | 07/15/26 10:28 AM
Row 108 | 0000002201 $4 refund draft for 108726 and 108725 over payment | Kaiya Hoogkamp | 10/02/25 8:16 AM
Row 113 | DO NOT EXECUTE IA without W-9 | Kaiya Hoogkamp | 12/19/25 12:41 PM
Row 117 | 5/21/2026 developer advised no date to begin construction or COC at this time. | Kaiya Hoogkamp | 05/21/26 2:49 PM
Row 117 | $1500 incorrect contract and PIA info 0120007896 PIA 0910293108/920317608. Sales admin has been emailed to remove payment type K and cancel PIA. I have cancelled the contract | Kaiya Hoogkamp | 10/22/25 3:44 PM
Row 118 | 12/8/2025 withdrawn due to ESA failure | Kaiya Hoogkamp | 12/08/25 1:07 PM
Row 120 | Partial ESA report, no estimates given. | BAILEY RODERICK | 07/15/26 10:28 AM
Row 120 | Derek will be out of office from 10/01 until 10/15 | Denise Baker | 09/25/25 12:54 PM
Row 122 | followed up on IA and gave until 5/8/2026 before beginning 60 day cure process | Kaiya Hoogkamp | 05/06/26 2:19 PM
Row 122 | invoice for $50.40 910292518 / 920317018 | Denise Baker | 10/20/25 1:56 PM
Row 122 | received 50.40 payment to complete the app fee | Denise Baker | 10/20/25 1:38 PM
Row 124 | Partial ESA report, no 'Minor Modification' estimates given (PASS < $30,000). | BAILEY RODERICK | 07/15/26 10:31 AM
Row 124 | 5/21/2026 developer advised aiming to have COC by November 2026 | Kaiya Hoogkamp | 05/21/26 2:16 PM
Row 127 | ESA Study charges $301.57 --fee was waived | Kaiya Hoogkamp | 06/01/26 3:25 PM
Row 128 | 0000000922 - refund draft | Kaiya Hoogkamp | 07/08/26 1:36 PM
Row 129 | 5/21/2026 developer advised aiming to have COC by end of 2026 | Kaiya Hoogkamp | 05/21/26 2:15 PM
Row 130 | Partial ESA report, no estimates given. | BAILEY RODERICK | 07/15/26 10:28 AM
Row 131 | 5/21/2026 developer advised no date to begin construction or COC at this time. | Kaiya Hoogkamp | 05/21/26 2:48 PM
Row 131 | 0000002082 refund for app overpayment | Kaiya Hoogkamp | 04/21/26 1:57 PM
Row 131 | Customer changed size of project after refund was issued. Total application fee is $434.00 received check # 0214233428 for addtion $30.00 manual invoice # 910287897/920312010 | Denise Baker | 09/24/25 9:51 AM
Row 131 | Refunded $2736.00 due to overpayment of app fee. Customer entered incorrect project size. Correct size was $404.00 app fee, but customer paid $3140.00 | Thomas Blanchard | 09/18/25 10:32 AM
Row 132 | 5/21/2026 developer advised no date to begin construction or COC at this time. | Kaiya Hoogkamp | 05/21/26 2:51 PM
Row 132 | Customer changed size of project after refund was issued. Total application fee is $434.00 received check # 0214233428 for addtion $30.00 manual invoice invoice # 910287899/920312008 | Denise Baker | 09/24/25 9:54 AM
Row 135 | 5/21/2026 developer advised COC by July 2026 | Kaiya Hoogkamp | 05/21/26 2:07 PM
Row 139 | ESA performed by Dante | Kaiya Hoogkamp | 09/25/25 2:01 PM
Row 141 | 0000000924 refund for ESA deposit run 5/1/2026 | Kaiya Hoogkamp | 05/01/26 2:56 PM
Row 143 | 5/21/2026 developer advised no date to begin construction or COC at this time. | Kaiya Hoogkamp | 05/21/26 2:46 PM
Row 144 | 5/21/2026 developer advised no date to begin construction or COC at this time. | Kaiya Hoogkamp | 05/21/26 2:47 PM
Row 145 | IA pending, as this is a microgrid | Kaiya Hoogkamp | 05/27/26 11:53 AM
Row 146 | 5/21/2026 developer advised aiming to have COC by end of 2026 | Kaiya Hoogkamp | 05/21/26 2:14 PM
Row 147 | 5/21/2026 developer advised aiming to have COC by end of 2026 | Kaiya Hoogkamp | 05/21/26 2:11 PM
Row 150 | 0000001943 $192.80 refund | Kaiya Hoogkamp | 08/27/25 8:52 AM
Row 150 | Ombudsman fee invoice adjusted $0.00:910282356 | Kaiya Hoogkamp | 08/21/25 8:36 AM
Row 150 | App invoice adjusted $0.00: 910282354 | Kaiya Hoogkamp | 08/21/25 8:35 AM
Row 153 | 5/21/2026 developer advised aiming to have COC in Spring of 2027 | Kaiya Hoogkamp | 05/21/26 1:41 PM
Row 154 | 5/21/2026 developer advised aiming to have COC in November 2026 | Kaiya Hoogkamp | 05/21/26 1:40 PM
Row 154 | Incorrect $1500 PIA that is cancelled: 910291285/920315762 | Kaiya Hoogkamp | 10/15/25 11:40 AM
Row 155 | 5/21/2026 developer advised the new building is under construction, hoping for COC in spring 2027 | Kaiya Hoogkamp | 05/21/26 1:37 PM
Row 156 | $192.14 refund (app fee & ombudsman fee) draft:0000001905 | Kaiya Hoogkamp | 08/21/25 9:19 AM
Row 156 | $0.00 invoice for ombudsman fee: 910282176 | Kaiya Hoogkamp | 08/20/25 11:02 AM
Row 156 | $0.00 invoice for app fee: 910282175 | Kaiya Hoogkamp | 08/20/25 11:00 AM
Row 160 | 5/21/2026 developer advised COC by August 2026 | Kaiya Hoogkamp | 05/21/26 1:33 PM
Row 162 | 5/21/2026 developer advised no in-service date currently | Kaiya Hoogkamp | 05/21/26 1:31 PM
Row 164 | Duplicate check payment app invoice for $102 : 0910290069/ 920314441. Adjusted to Zero $0: 910290075 | Kaiya Hoogkamp | 10/07/25 3:32 PM
Row 164 | Dante & Elisha are doing the ESA | Kaiya Hoogkamp | 09/24/25 12:07 PM
Row 170 | Project originally tariff, switched to kWh onsite load only on 9/17/2025 | Kaiya Hoogkamp | 03/18/26 10:18 AM
Row 170 | Original Acct# was 30016819978 | Nathan Lawrence | 02/13/26 2:58 PM
Row 175 | 0000001962 refund draft for $91.20 app fee overpayment | Kaiya Hoogkamp | 08/28/25 9:10 AM
Row 175 | 910283033 app invoice adjusted for $350.80 | Kaiya Hoogkamp | 08/26/25 3:08 PM
Row 175 | App is actually for 125.4 kW AC, not 171, refund of $91.20 is due | Kaiya Hoogkamp | 08/26/25 7:52 AM
Row 175 | Followed up on 7/7/2025 | Andrew Jackson | 07/07/25 2:44 PM
Row 176 | APP FEE WAIVED tech screen was incorrect, ESA did not need to be completed | Kaiya Hoogkamp | 06/04/26 12:58 PM
Row 176 | 120007766 contract cancelled | Kaiya Hoogkamp | 08/26/25 3:38 PM
Row 176 | 0000001941 - $1500 refund draft number for ESA deposit | Kaiya Hoogkamp | 08/26/25 3:33 PM
Row 176 | ESA canceled. TS fail was an error, updated to pass 8/20/25 - NAL. | Nathan Lawrence | 08/20/25 3:10 PM
Row 179 | $6 refund draft: 0000001897 | Kaiya Hoogkamp | 08/20/25 8:04 AM
Row 179 | $6 910277568/920301365 invoice adjusted to$0.00: 910281926 | Kaiya Hoogkamp | 08/19/25 11:03 AM
Row 182 | Followed up on 7/7 | Andrew Jackson | 07/07/25 2:37 PM
Row 188 | 120007812 - contract cancelled 9/17/25 | Kaiya Hoogkamp | 09/17/25 8:23 AM
Row 188 | $2500 ESA fee acidentally paid by developer. Removed payment type K. Contract: 0120007812 INV: 0910286550/920310623 | Kaiya Hoogkamp | 09/16/25 1:24 PM
Row 194 | 120007677 duplicate contract made in the portal, cancelled (7/1/2025). | Kaiya Hoogkamp | 07/01/25 10:02 AM
Row 194 | Followed up on AOR(Incomplete) 5/16/2025 | Andrew Jackson | 05/16/25 10:58 AM
Row 195 | $2500 incorrect contract and PIA info 0120007914 PIA 0910294121/ 920318670. Sales admin has been emailed to remove payment type K and cancel PIA. I have cancelled the contract | Kaiya Hoogkamp | 10/29/25 2:21 PM
Row 203 | Cost sharing invoice 910273462 / 920297110 adjusted to $0, because the project is a tariff project. ADJUSTED 910273516 | Kaiya Hoogkamp | 06/27/25 1:34 PM
Row 205 | looks to be cascading off site as well, should not have charged a cost sharing fee | Kaiya Hoogkamp | 03/18/26 10:42 AM
Row 212 | 07/18/25 received additional charge of $93.82 from Dante, however, the contract is complete | Kaiya Hoogkamp | 06/04/26 2:53 PM
Row 212 | 5/21/2026 developer advised no date to begin construction or COC at this time. | Kaiya Hoogkamp | 05/21/26 2:18 PM
Row 214 | no contract? | Kaiya Hoogkamp | 04/03/26 2:58 PM
Row 220 | 4/15/25 AOR complete LATE due to waiting for customer check | Kaiya Hoogkamp | 04/15/25 9:37 AM
Row 221 | 1 time exention for SLD tro 5/2/2025 | Kaiya Hoogkamp | 04/15/25 10:10 AM
Row 221 | AOR complete LATE due to customer delayed SLD | Kaiya Hoogkamp | 04/15/25 9:37 AM
Row 222 | 1 time exention for SLD tro 5/2/2025 | Kaiya Hoogkamp | 04/15/25 10:11 AM
Row 222 | AOR complete LATE due to customer delayed SLD | Kaiya Hoogkamp | 04/15/25 9:38 AM
Row 225 | 4/17/2025 Withdrawn | Kaiya Hoogkamp | 04/17/25 10:31 AM
Row 227 | 4/17/2025 Withdrawn | Kaiya Hoogkamp | 04/17/25 10:32 AM
Row 229 | 105711 | Kaiya Hoogkamp | 04/17/25 10:32 AM
Row 229 | Additional invoice created for remaining application payment balance, $1996.00 | Kaiya Hoogkamp | 03/18/25 9:23 AM
Row 231 | Additional invoice created for remaining application payment balance, $1996.00 | Kaiya Hoogkamp | 03/18/25 9:23 AM
Row 234 | 0000000922 refund for unused study funds | Kaiya Hoogkamp | 05/04/26 12:17 PM
Row 235 | Draft 0000000096 issued for ACH 2nd refund, as it seemed we re-pulled the $40.00 ombudsman fee. | Kaiya Hoogkamp | 01/19/26 12:38 PM
Row 235 | Draft 0000001119 refund issued via ACH on 5/2/2025 | Kaiya Hoogkamp | 05/02/25 8:37 AM
Row 235 | Adjusted Ombudsman fee invoice to $0.00 910265697 | Kaiya Hoogkamp | 05/01/25 9:28 AM
Row 235 | Adjusted app invoice to $0.00 910264462 | Kaiya Hoogkamp | 04/22/25 4:06 PM
Row 235 | 4/2/25 app withdrawn. | Kaiya Hoogkamp | 04/02/25 3:06 PM
Row 236 | 0000000989 refund for duplicate payment of $376.40 | Kaiya Hoogkamp | 05/11/26 2:58 PM
Row 238 | 3/19/25 Application withdrawn. Failed technical screen and will fail and ESA. Advised to proceed with level 4. | Kaiya Hoogkamp | 03/19/25 1:12 PM
Row 239 | DO NOT EXECUTE IA OR COC UNTIL OMBUDSMAN FEE IS PAID | Kaiya Hoogkamp | 05/07/25 11:45 AM
Row 240 | DO NOT EXECUTE IA OR COC UNTIL OMBUDSMAN FEE IS PAID | Kaiya Hoogkamp | 05/07/25 11:46 AM
Row 241 | 3/19/25 Application withdrawn. Failed technical screen and will fail and ESA. Advised to proceed with level 4. | Kaiya Hoogkamp | 03/19/25 12:55 PM
Row 242 | 3/19/25 Application withdrawn. Failed technical screen and will fail and ESA. Advised to proceed with level 4. | Kaiya Hoogkamp | 03/19/25 1:03 PM
Row 246 | 5/21/26 Developer advised building is under contruction, hoping to have COC submitted in August 2026 | Kaiya Hoogkamp | 05/21/26 1:29 PM
Row 249 | 2/26/25 emailed template to apply $1500 from previous ESA to this new PIA invoice | Kaiya Hoogkamp | 02/26/25 4:09 PM
Row 249 | If they go forward with the ESA we need to zero out previous ESA invoice and move funds to this new ESA | Kaiya Hoogkamp | 02/21/25 12:07 PM
Row 249 | Adjusted to $0.00 invoice 910253996 | Kaiya Hoogkamp | 02/18/25 1:12 PM
Row 249 | App fee is waived, previous project, 104609, could not be completed due to a level 4 study. We waived app fee and ESA fee (move fee from previous project to new project). | Kaiya Hoogkamp | 02/17/25 10:33 AM
Row 252 | 5/21/26 developer anticipates project to be installed in fall 2026, it is being installed on a new construction site. | Kaiya Hoogkamp | 05/21/26 10:26 AM
Row 254 | 2/13/25 customer submitted payment and it was received. Opening the project up instead of reapplication. | Kaiya Hoogkamp | 02/13/25 8:20 AM
Row 254 | 2/11/25 project withdrawn, failure to pay application fee and unresponsive to outreach. | Kaiya Hoogkamp | 02/11/25 9:15 AM
Row 255 | Application late past AOR complete date due to developer delay sending application payment. | Kaiya Hoogkamp | 02/11/25 3:05 PM
Row 255 | Developer provided documentation of wire that was sent on 2/10/2025, reopened the application. | Kaiya Hoogkamp | 02/11/25 2:59 PM
Row 255 | 2/11/25 project withdrawn, failure to pay application fee and unresponsive to outreach. | Kaiya Hoogkamp | 02/11/25 9:14 AM
Row 257 | 5/21/2026 developer advised system being installed in June 2026 | Kaiya Hoogkamp | 05/21/26 1:39 PM
Row 259 | 4/7/25 email for IA sent. 30 BD 5/20/2025 | Kaiya Hoogkamp | 04/07/25 9:11 AM
Row 263 | DO NOT EXECUTE COC UNTIL OMBUDSMAN FEE IS PAID | Kaiya Hoogkamp | 05/07/25 11:39 AM
Row 264 | 1/29/25 offered one time extention to 2/5/2025 waiting for wire payment. | Kaiya Hoogkamp | 01/29/25 3:52 PM
Row 265 | Waiting for check payment for ESA ($2500) | Kaiya Hoogkamp | 01/27/25 2:50 PM
Row 265 | Transformer upgrade taking place under Consumptions, NOTI 10301100550 | Nathan Lawrence | 01/22/25 1:55 PM
Row 266 | $48 refunded, they overpaid the application fee. Draft:0000001583 | Kaiya Hoogkamp | 07/02/25 2:13 PM
Row 266 | 0000000189 is the draft refund | Kaiya Hoogkamp | 05/16/25 9:31 AM
Row 266 | 4/16/25 application withdrawn. Project unresponsive to outreach after technical screen failure. | Kaiya Hoogkamp | 04/16/25 8:16 AM
Row 267 | 2 cost sharing invoices, portal amount was incorrectly $570.00, full amount is $770.00. Additional $200 check sent and invoice is: 910255902/920278885 | Kaiya Hoogkamp | 03/04/25 11:39 AM
Row 269 | The developer advised this project was submitted in error and is withdrawn. | Kaiya Hoogkamp | 12/23/24 11:49 AM
Row 270 | 5/21/2026 developer advised no in-service date currently | Kaiya Hoogkamp | 05/21/26 1:35 PM
Row 273 | credit memo to offset $187.64 (we are not invoicing the developer again). 910315724 | Kaiya Hoogkamp | 04/15/26 11:02 AM
Row 273 | $187.64 invoice 910266466/920289826 | Kaiya Hoogkamp | 05/07/25 9:24 AM
Row 273 | Additional $187.64 invoice received. Sent to workf flow 5/6/25. Per Dante "Project 104903 – the additional two hours were for a peer review. Its dated near the start of the month and on the other its dated at the end of the month so it must have been missed because it was split between the two invoices. " | Kaiya Hoogkamp | 05/06/25 10:21 AM
Row 273 | Original IA for incorrect $2500 910250371/ 920272691 Updated PIA to $1500 910250593/920272951 | Kaiya Hoogkamp | 01/21/25 3:17 PM
Row 281 | 4/7/25 email for IA sent. 30 BD 5/20/2025 | Kaiya Hoogkamp | 04/07/25 9:10 AM
Row 282 | Developer is proposing a utility owned 750 kVA Pad mounted transformer. This will exceed the $30,000 Level 2 Threshold and will need to go to a level 4 study. | Nathan Lawrence | 12/17/24 1:56 PM
Row 282 | AOR complete delayed due to customer, waiting for payment to be received. | Kaiya Hoogkamp | 12/13/24 10:41 AM
Row 283 | TS Failed due to costs for proposed upgrades. | Nathan Lawrence | 01/08/25 10:10 AM
Row 283 | AOR complete delayed due to customer, waiting for payment to be received. | Kaiya Hoogkamp | 12/13/24 10:42 AM
Row 284 | 4/15/26 developer requested to apply $998.88 refund from their ESA to be applied to their outstanding $27,679.89 balance for level 4 project 640 | Kaiya Hoogkamp | 04/15/26 11:20 AM
Row 284 | AOR complete delayed due to customer, waiting for payment to be received. | Kaiya Hoogkamp | 12/13/24 10:42 AM
Row 285 | AOR complete delayed due to customer, waiting for payment to be received. | Kaiya Hoogkamp | 12/13/24 10:41 AM
Row 286 | AOR complete delayed due to customer, waiting for payment to be received. | Kaiya Hoogkamp | 12/13/24 10:41 AM
Row 287 | ESA original amount deposit due was $1500 | Kaiya Hoogkamp | 06/04/25 12:19 PM
Row 287 | 12/4/2024 informed developer we needed to terminate ESA and withdraw project due to level 4 PRJ 308 being in study. | Kaiya Hoogkamp | 05/14/25 9:11 AM
Row 287 | terminated contract on 3/11/25 | Kaiya Hoogkamp | 03/11/25 1:21 PM
Row 288 | Withdrawn on 1/2/2025 | Kaiya Hoogkamp | 01/27/25 8:32 AM
Row 290 | 0000001980 $1540 draft refund | Kaiya Hoogkamp | 09/02/25 11:32 AM
Row 290 | Incorrectly paid cost sharing fee invoice ($1500) (910273263) adjusted to $0.00: 910282401 | Kaiya Hoogkamp | 08/21/25 11:40 AM
Row 290 | Ombudsman invoice (910273264) adjusted to $0.00: 910282398 | Kaiya Hoogkamp | 08/21/25 11:37 AM
Row 290 | Replaces old 2.80 kW AC 1.00 DC project at the same address from 2013 | Kaiya Hoogkamp | 11/14/24 2:50 PM
Row 292 | 12/2/2024 customer requested to withdraw, as they have not finalized the SLD. | Kaiya Hoogkamp | 12/02/24 11:47 AM
Row 293 | 2/25/2026 project delayed due to State of Maine Permitting. | Kaiya Hoogkamp | 02/25/26 2:41 PM
Row 294 | 6/12/26 project does not have an estimated COC date yet | Kaiya Hoogkamp | 06/12/26 12:22 PM
Row 295 | 2/25/2026 project delayed due to State of Maine Permitting. | Kaiya Hoogkamp | 02/25/26 2:43 PM
Row 296 | 2/25/2026 project delayed due to State of Maine Permitting. | Kaiya Hoogkamp | 02/25/26 2:43 PM
Row 297 | 11/7/24 application failed technical screen and was advised it would fail addtional screening. Application withdrew and will reapply as a level 4. | Kaiya Hoogkamp | 11/07/24 11:13 AM
Row 298 | 12/4/2024 customer has withdrawn and will apply as a level 4 | Kaiya Hoogkamp | 12/04/24 12:19 PM
Row 299 | 2 Noti invoices: $24,291.18 & $30670.53 | Nathan Lawrence | 07/16/26 2:49 PM
Row 302 | 10/18/2024 project requested extension to complete SLD, extened to 10/25/2024 | Kaiya Hoogkamp | 10/18/24 3:27 PM
Row 303 | waiving the $1.12 for ESA | Kaiya Hoogkamp | 02/10/26 8:47 AM
Row 304 | Application Fee waived, this is a resubmission for original application 101658 | Kaiya Hoogkamp | 09/25/24 12:11 PM
Row 310 | Tech Screen notes no xfrmr upgrade needed. Existing service - no NOTI created | Nathan Lawrence | 09/26/24 9:32 AM
Row 311 | 4/7/25 email for IA sent. 30 BD 5/20/2025 | Kaiya Hoogkamp | 04/07/25 8:47 AM
Row 311 | Invoice will need to be adjusted to zero once they pay invoice through the portal with DD once banking is verified | Kaiya Hoogkamp | 09/25/24 12:31 PM
Row 312 | 9/11/24 customer decided to withdraw after failing tech screen. | Kaiya Hoogkamp | 09/11/24 1:19 PM
Row 313 | Holding COC due to problems with the phone line. CMP cannot connect to the meter. | Nathan Lawrence | 03/11/25 1:32 PM
Row 314 | 9/11/24 customer decided to withdraw after failing tech screen. | Kaiya Hoogkamp | 09/11/24 1:29 PM
Row 315 | 9/3/2024 app withdrawn, it incorrectly applied as a level 2, it needs to be a level 4. Customer advised of this. | Kaiya Hoogkamp | 09/03/24 9:54 AM
Row 318 | 2/25/2026 project delayed due to State of Maine Permitting. | Kaiya Hoogkamp | 02/25/26 2:44 PM
Row 318 | MANUAL PORTAL APPLICATION | Kaiya Hoogkamp | 09/23/24 12:15 PM
Row 319 | Original projects 103022 ($1060) and 103021 ($200). $1060+$200 = $1260. The NEW app total is $1180. $1180 - $1260 = -$80 is due to the customer as a refund. | Kaiya Hoogkamp | 08/07/24 3:02 PM
Row 320 | Original projects 103019 ($250 payment valid) and 103017 (project went to tech screen). App total is $350. Minus the $250 availible = $100 due | Kaiya Hoogkamp | 08/07/24 2:54 PM
Row 321 | Original projects 103016 & 103014, both projects went through tech screen, so full app total of $400 is due | Kaiya Hoogkamp | 08/07/24 2:39 PM
Row 324 | 9/30/2024 ESA failed, project withdrawn | Kaiya Hoogkamp | 10/31/24 10:37 AM
Row 324 | 8/23/24 resent ESA for new signatures, with a date line added next to customer signature | Kaiya Hoogkamp | 08/23/24 11:41 AM
Row 325 | 8/6/24 withdrawn, project being combined. | Kaiya Hoogkamp | 08/06/24 3:17 PM
Row 326 | 8/6/24 withdrawn, project being combined. | Kaiya Hoogkamp | 08/06/24 3:14 PM
Row 327 | 8/6/24 withdrawn, project being combined. | Kaiya Hoogkamp | 08/06/24 3:20 PM
Row 328 | 8/6/24 withdrawn, project being combined. | Kaiya Hoogkamp | 08/06/24 3:22 PM
Row 329 | 8/6/24 withdrawn, project being combined. | Kaiya Hoogkamp | 08/06/24 3:10 PM
Row 330 | 8/6/24 withdrawn, project being combined. | Kaiya Hoogkamp | 08/06/24 3:13 PM
Row 331 | 8/12/2024 failed ESA, project withdrawn | Kaiya Hoogkamp | 08/12/24 3:17 PM
Row 332 | 8/6/24 withdrawn, project being combined. | Kaiya Hoogkamp | 08/12/24 3:19 PM
Row 333 | 8/6/24 withdrawn, project being combined. | Kaiya Hoogkamp | 10/15/24 1:49 PM
Row 334 | 8/23/2024 project withdrawn after failing ESA | Kaiya Hoogkamp | 10/15/24 1:48 PM
Row 336 | No task 24 on noti 10301113757. | Nathan Lawrence | 12/17/24 2:55 PM
Row 336 | 8/5/2024 AOR complete delayed due to waiting for additional $42 payment to complete the application. | Kaiya Hoogkamp | 08/05/24 8:55 AM
Row 337 | 10/2/2024 ESA failed and project withdrawn. | Kaiya Hoogkamp | 10/15/24 1:54 PM
Row 337 | 7/30 invoice adjustment to make it $2050, funds are on debtor. Need to wait for adjustment invoice before entering IT ticket to clear. 910231855 | Kaiya Hoogkamp | 09/12/24 3:21 PM
Row 338 | 8/28/2024 ESA failed, project withdrawn. | Kaiya Hoogkamp | 10/15/24 1:56 PM
Row 340 | 9/3/2024 ESA failed, project withdrawn. | Kaiya Hoogkamp | 10/15/24 1:57 PM
Row 341 | Kaiya Hoogkamp 4/7/25 email for IA sent. 30 BD 5/20/2025 | Kaiya Hoogkamp | 04/07/25 8:43 AM
Row 343 | 8/2/2024 project withdrawn | Kaiya Hoogkamp | 08/02/24 10:30 AM
Row 345 | 8/2/2024 project withdrawn | Kaiya Hoogkamp | 08/02/24 10:30 AM
Row 346 | 8/12/2024 project withdrawn, failed ESA | Kaiya Hoogkamp | 08/13/24 3:18 PM
Row 347 | 2/12/26 project confirmed they are still active | Kaiya Hoogkamp | 02/19/26 12:59 PM
Row 355 | SAP NOTI 10301085577 is paid, no Task 24 Date on NOTI. | Nathan Lawrence | 12/10/24 11:27 AM
Row 357 | 6/14/2024 customer advsied they are withdrawing and reapplying as a level 4. They did not mean to apply as a level 2. | Kaiya Hoogkamp | 06/14/24 10:33 AM
Row 358 | NOTI completed 10/17/24. | Nathan Lawrence | 10/17/24 2:34 PM
Row 359 | 2/12/26 project confirmed they are still active. | Kaiya Hoogkamp | 02/19/26 1:01 PM
Row 360 | 6/11/2024 customer requested to withdraw. | Kaiya Hoogkamp | 06/11/24 12:58 PM
Row 361 | 6/11/2024 customer requested to withdraw. | Kaiya Hoogkamp | 06/11/24 12:58 PM
Row 362 | 6/11/2024 customer requested to withdraw. | Kaiya Hoogkamp | 06/11/24 12:58 PM
Row 363 | 6/11/2024 customer requested to withdraw. | Kaiya Hoogkamp | 06/11/24 12:58 PM
Row 364 | 6/11/2024 customer requested to withdraw. | Kaiya Hoogkamp | 06/11/24 12:58 PM
Row 365 | 6/11/2024 customer requested to withdraw. | Kaiya Hoogkamp | 06/11/24 12:59 PM
Row 366 | 6/11/2024 customer requested to withdraw. | Kaiya Hoogkamp | 06/11/24 12:59 PM
Row 367 | 6/11/2024 customer requested to withdraw. | Kaiya Hoogkamp | 06/11/24 12:59 PM
Row 368 | 6/11/2024 customer requested to withdraw. | Kaiya Hoogkamp | 06/11/24 12:59 PM
Row 369 | 6/11/2024 customer requested to withdraw. | Kaiya Hoogkamp | 06/11/24 12:59 PM
Row 370 | 6/11/2024 customer requested to withdraw. | Kaiya Hoogkamp | 06/11/24 12:59 PM
Row 371 | 6/11/2024 customer requested to withdraw. | Kaiya Hoogkamp | 06/11/24 12:59 PM
Row 372 | 6/11/2024 customer requested to withdraw. | Kaiya Hoogkamp | 06/11/24 12:59 PM
Row 373 | 6/11/2024 customer requested to withdraw. | Kaiya Hoogkamp | 06/11/24 12:59 PM
Row 374 | 6/11/2024 customer requested to withdraw. | Kaiya Hoogkamp | 06/11/24 1:23 PM
Row 375 | Application delayed AOR complete due to customer waiting for PE stamp on their SLD | Kaiya Hoogkamp | 07/10/24 2:09 PM
Row 377 | 6/11/2024 customer requested to withdraw. | Kaiya Hoogkamp | 06/11/24 12:57 PM
Row 378 | 6/11/2024 customer requested to withdraw. | Kaiya Hoogkamp | 06/11/24 12:58 PM
Row 379 | 6/11/2024 customer requested to withdraw. | Kaiya Hoogkamp | 06/11/24 12:58 PM
Row 381 | 6/18/2024 customer confirmed they are withdrawing after failing technical screen and reapplying as a level 4. | Kaiya Hoogkamp | 06/18/24 10:22 AM
Row 382 | 6/10/24 customer failed technical screen and requested to withdraw | Kaiya Hoogkamp | 06/10/24 10:34 AM
Row 383 | 2/12/26 customer confirmed project still active, expected to be completed July 2026 | Kaiya Hoogkamp | 02/19/26 1:03 PM
Row 383 | kWh, No on-site load | Nathan Lawrence | 08/01/24 1:18 PM
Row 384 | Existing Service, no upgrades, no NOTI | Nathan Lawrence | 08/28/24 9:00 AM
Row 385 | 8/27/2024 customer requested to withdraw project | Kaiya Hoogkamp | 08/27/24 10:21 AM
Row 385 | 6/25/24 application deemed complete, SLD submitted from the developer. Delayed by developer waiting on a PE stamp. | Kaiya Hoogkamp | 06/25/24 8:59 AM
Row 385 | 6/3 customer has requested extention to deem AOR complete, they are awaiting the PE Stamped SLD | Kaiya Hoogkamp | 06/03/24 2:51 PM
Row 385 | Original project (74286) folder is in 2019 - level 2 folder | Kaiya Hoogkamp | 05/20/24 8:53 AM
Row 386 | No task 24 in SAP | Kaiya Hoogkamp | 12/17/24 2:57 PM
Row 388 | 7/16/2024 project emailed to confirm withdrawn after failing technical screen | Kaiya Hoogkamp | 07/17/24 8:25 AM
Row 393 | 5/9 application AOR complete delayed due to customer needing to get updated SLD/Site plan | Kaiya Hoogkamp | 05/09/24 10:51 AM
Row 395 | 6/5/2024 project failed tech screen and requested to withdraw and reapply as level 4. | Kaiya Hoogkamp | 10/15/24 2:11 PM
Row 397 | 120006528 terminated contract, ESA was never performed. | Kaiya Hoogkamp | 03/10/25 1:51 PM
Row 397 | 7/16/2024 application withdrawn as we cannot perform the level 2 ESA at this time. Refund has been issued. 0000001479 | Kaiya Hoogkamp | 07/16/24 3:34 PM
Row 398 | additional invoice balance 656.73 paid in full | Kaiya Hoogkamp | 04/30/26 10:06 AM
Row 398 | Additional ESA Invoice 910265922/920289270 for $656.73, additional study charges that were initially missed from Dante due to being out at the time. | Kaiya Hoogkamp | 05/02/25 11:49 AM
Row 399 | no task 24 in SAP | Kaiya Hoogkamp | 12/17/24 2:56 PM
Row 402 | 6/28/2024 ESA failed, project withdrawn. | Kaiya Hoogkamp | 10/15/24 2:14 PM
Row 403 | No NOTI - existing service, no upgrades. | Nathan Lawrence | 01/08/25 12:05 PM
Row 404 | 5/23/2024 ESA failed, project withdrawn. | Kaiya Hoogkamp | 10/15/24 2:15 PM
Row 407 | Withdrawn 4/5/2024 Customer did not respond to multiple outreach attempts to provide required documents and payment to deem application complete. | Kaiya Hoogkamp | 04/05/24 10:13 AM
Row 408 | Withdrawn 4/5/2024 Customer did not respond to multiple outreach attempts to provide required documents and payment to deem application complete. | Kaiya Hoogkamp | 04/05/24 10:18 AM
Row 409 | No on-site load | Nathan Lawrence | 08/19/24 12:46 PM
Row 411 | Debit memo to offset Credit memo: 910265865/920289224 | Kaiya Hoogkamp | 05/02/25 9:46 AM
Row 411 | credit memo created to offset invoice 910263066/920286135. Credit Memo is 910264738/920288363 | Kaiya Hoogkamp | 04/24/25 10:48 AM
Row 411 | 5/21/2024 ESA failed, project withdrawn. | Kaiya Hoogkamp | 10/15/24 2:18 PM
Row 413 | Refunded thru credit of 811.24 given to Level4 PRJ 820 per Tyler | Thomas Blanchard | 03/06/25 8:32 AM
Row 414 | 5/1/2024 project failed ESA and withdrawn. | Kaiya Hoogkamp | 10/15/24 2:20 PM
Row 416 | 4/5/2024 Refund processed in SAP. | Kaiya Hoogkamp | 04/05/24 10:55 AM
Row 416 | INC3492935 entered to open up refund for $1500 ESA payment. The developer paid for an ESA even though they passed technical screen. | Kaiya Hoogkamp | 04/05/24 10:44 AM
Row 416 | 4/3/24 Customer has withdrawn due to construction issues. | Kaiya Hoogkamp | 04/03/24 11:07 AM
Row 417 | 5/17/2024 customer requested the application to be withdrawn. It will be downsizing to a level 1. | Kaiya Hoogkamp | 05/17/24 10:22 AM
Row 418 | adjusted invoice 910253799 to $0.00 on 2/17/2025 | Kaiya Hoogkamp | 02/17/25 1:37 PM
Row 418 | 3/5/24 customer is withdrawing due to developer being no longer in business. Customer will apply again in the future with a new developer. | Kaiya Hoogkamp | 03/05/24 1:23 PM
Row 418 | 3/4/2024 emailed requesting update as today is day 10 | Kaiya Hoogkamp | 03/04/24 1:55 PM
Row 420 | no task 24 in SAP | Kaiya Hoogkamp | 12/17/24 2:55 PM
Row 421 | 2/28/24 customer requested to withdraw and have refund issued, project did not go to technical screen and refund will be issued. | Kaiya Hoogkamp | 02/29/24 9:29 AM
Row 422 | no task 24 in SAP | Kaiya Hoogkamp | 12/17/24 2:52 PM
Row 422 | 910214308 Invoice adjustment to zero as project cancelled. | Kaiya Hoogkamp | 03/11/24 10:24 AM
Row 422 | 2/29/2024 the customer is withdrawing, they will reapply when all needed equipment has been installed. | Kaiya Hoogkamp | 02/29/24 2:52 PM
Row 423 | 4/7/25 email for IA sent. 30 BD 5/20/2025 | Kaiya Hoogkamp | 04/07/25 8:50 AM
Row 425 | From ESS email: "Field Planner appointment scheduled on 11/5 @8;30 to upgrade the 10kva 1ph 120/240 pole mounted transformer to a 100kva,120/240 pole mounted with a 600amp,120/240,1ph CT KWH credit service. Job 10301134847 will not be needed and that notification will be cancelled." | Nathan Lawrence | 10/28/24 12:08 PM
Row 425 | 10301134847 canceled, is a duplicate | Nathan Lawrence | 10/28/24 12:07 PM
Row 425 | New BUAG: 30016347129 created 10/28/24 by customer care | Nathan Lawrence | 10/28/24 9:59 AM
Row 426 | 5/7/2024 project failed ESA and withdrawn. | Kaiya Hoogkamp | 10/15/24 2:26 PM
Row 427 | No task 24 in SAP | Kaiya Hoogkamp | 12/17/24 2:50 PM
Row 429 | project withdrawn as it failed ESA on 4/12/2024 | Kaiya Hoogkamp | 04/29/24 9:10 AM
Row 431 | 5/16/2024 project withdrew and reapplied as level 4. | Kaiya Hoogkamp | 09/13/24 3:21 PM
Row 431 | 3/4 application complete delayed by customer - applied for 1000 kW AC then informed us it was 999 kW AC. Required updated SLD & Site plan with the change. Requested updated documents on 2/23/24 and received them 3/4/2024 | Kaiya Hoogkamp | 03/04/24 3:09 PM
Row 431 | currently missing required deration letter. CANNOT issue IA without this documentation 3/4/2024 | Kaiya Hoogkamp | 03/04/24 2:28 PM
Row 432 | Cost Sharing invoice adjustment: 910254167 | Kaiya Hoogkamp | 02/19/25 12:06 PM
Row 434 | no task 24 in SAP | Kaiya Hoogkamp | 12/17/24 2:46 PM
Row 435 | Refund used as credit towards a Level4 invoice (PRJ820) per Tyler | Thomas Blanchard | 03/06/25 8:21 AM
Row 435 | 2/7/25 duplicate application fee of $2098 has been refunded. | Kaiya Hoogkamp | 02/07/25 8:22 AM
Row 435 | 5/7/2024 failed ESA, project withdrawn | Kaiya Hoogkamp | 08/26/24 2:39 PM
Row 437 | 3/11/2024 customer withdrew after technical screen failure. | Kaiya Hoogkamp | 03/11/24 1:48 PM
Row 439 | currently missing required deration letter. CANNOT issue IA without this documentation 3/4/2024 | Kaiya Hoogkamp | 03/04/24 1:27 PM
Row 440 | No task 24 in SAP | Kaiya Hoogkamp | 12/17/24 2:45 PM
Row 441 | 4/29/2024 withdrawn, project failed tech screen 2/14/2024 and project never responded with next steps. | Kaiya Hoogkamp | 04/29/24 9:12 AM
Row 442 | Refund request number: 0000001051 | Kaiya Hoogkamp | 05/14/25 8:51 AM
Row 442 | 4/19/2024 application withdrawn. | Kaiya Hoogkamp | 08/20/24 1:05 PM
Row 442 | 4/30/2024 refund reissued for $1152. Original amount to be refunded $1500 for ESA. However, there was an outstanding invoice for $348 on invoice 910212016/920232028. That has now been paid. | Kaiya Hoogkamp | 04/30/24 3:10 PM
Row 442 | 4/23 Refund updated to JUST the ESA fee of $1500. We will waive app fee if they reapply in the future. | Kaiya Hoogkamp | 04/23/24 12:31 PM
Row 442 | project withdrawn, cannot process ESA due to level 4 studies. | Kaiya Hoogkamp | 04/19/24 2:30 PM
Row 442 | 4/18/24 processed refuned for $2600 | Kaiya Hoogkamp | 04/18/24 3:28 PM
Row 442 | 910219227 invoice adjustment to adjust invoice to $0 in order to issue refund. We are refunding application and ESA fee due to project being unable to move forward due to level 4 applications. | Kaiya Hoogkamp | 04/16/24 3:26 PM
Row 442 | waiting to receive W-9 or email confirmation of financial responsiblity for the ESA before creating contract. Create the ESA in the portal | Kaiya Hoogkamp | 02/06/24 11:26 AM
Row 445 | 4/26/24 withdrawn after failing ESA | Kaiya Hoogkamp | 08/20/24 12:36 PM
Row 446 | 8/5/2024 emailed requesting signed IA due by 8/16/2024 or we will withdraw their application. | Kaiya Hoogkamp | 08/05/24 2:05 PM
Row 448 | 1/19/2024 withdrawn, failed tech screen. | Kaiya Hoogkamp | 03/21/24 11:58 AM
Row 450 | Cost Sharing Invoice: 910214986/920235274 | Kaiya Hoogkamp | 03/14/24 10:00 AM
Row 451 | IA Fully Executed for Tenant Change 10/4/2024 from Jaime Shaw to Benjamin Sholl. | Nathan Lawrence | 10/04/24 11:21 AM
Row 453 | Withdrawn 1/17/2024 after 10 business days bast and after not fully submitting app or payment and not responding to all outreach. | Kaiya Hoogkamp | 03/21/24 12:01 PM
Row 457 | 4/4/25 email for IA sent. 30 BD 5/19/2025 | Kaiya Hoogkamp | 04/04/25 3:53 PM
Row 458 | portal contract 120006228 PIA 910212543 / 920232559. Created and cancelled 2/23/24. Portal contract and "old way" contract both made. | Kaiya Hoogkamp | 02/23/24 2:04 PM
Row 459 | 1/3/24 withdrawn after not responding within the 10 business day deadline | Kaiya Hoogkamp | 03/21/24 12:51 PM
Row 460 | 5/17/2024 project failed technical screen and withdrew. | Kaiya Hoogkamp | 10/15/24 2:39 PM
Row 461 | 2/9/2024 project failed ESA and withdrawn. | Kaiya Hoogkamp | 10/15/24 2:38 PM
Row 462 | Withdrawn 1/3/2024 after customer did not provide required documentation within the required 10 days and after an extention was granted. | Kaiya Hoogkamp | 03/21/24 11:39 AM
Row 465 | 4/9/2024 project withdrawn as it failed ESA. | Kaiya Hoogkamp | 04/29/24 9:07 AM
Row 468 | Duplicate invoice created adjustment 910216436 | Kaiya Hoogkamp | 03/25/24 1:29 PM
Row 468 | Customer paid twice for cost sharing payment. Additional payment invoice adjusted to zero 910213645 / | Kaiya Hoogkamp | 03/05/24 10:37 AM
Row 469 | Brent tech screen, updated SS for original dates, tech screen returned on 12/6/2023, but needed new TS form filled out. Brent delayed filling out | Kaiya Hoogkamp | 09/09/24 1:43 PM
Row 469 | MEPS will be financially responsible for ESA. Use their debtor when creating ESA. Email confirming financial responsibility is in the project folder. | Kaiya Hoogkamp | 02/06/24 12:29 PM
Row 470 | 6/7/2024 project withdrew | Kaiya Hoogkamp | 06/07/24 3:25 PM
Row 470 | 2/6 emailed customer asking for W-9 for New Sharon Community Solar or an email confirming Genie Solar Energy is financially responsible for ESA before we can create contract and PIA | Kaiya Hoogkamp | 02/06/24 10:41 AM
Row 473 | Rick tech screen, originally on time, but, contained wrong project size in TS, delay from Rick for updated TS with correct project size caused delay sent to customer | Kaiya Hoogkamp | 09/09/24 1:49 PM
Row 477 | 4/29/2024 failed ESA, project withdrawn | Kaiya Hoogkamp | 06/18/24 3:02 PM
Row 477 | Developer submitted 4 applications for same size all at once during transition to new portal, payments and additional documents were not all submitted at the same time. There was numerous back and forth with customer to ensure we received payments, export control and new account creation caused delays with the customer. Developer has worked in good faith to keep us informed as they worked to get all required documentation and payment. | Kaiya Hoogkamp | 01/24/24 2:50 PM
Row 478 | Refund draft: 0000000989 | Kaiya Hoogkamp | 05/14/25 8:47 AM
Row 478 | 4/24/2024 withdrawn | Kaiya Hoogkamp | 10/22/24 11:52 AM
Row 478 | 4/23 Refund updated to JUST the ESA fee of $2500. We will waive app fee if they reapply in the future. | Kaiya Hoogkamp | 04/23/24 12:21 PM
Row 478 | project withdrawn as it cannot go through ESA due to level 4 studies. | Kaiya Hoogkamp | 04/19/24 2:20 PM
Row 478 | $4640 refund issued for app fee and ESA. Project withdrawn | Kaiya Hoogkamp | 04/19/24 2:20 PM
Row 478 | 910219232 invoice adjustment to adjust invoice to $0 in order to issue refund. We are refunding application and ESA fee due to project being unable to move forward due to level 4 applications. | Kaiya Hoogkamp | 04/16/24 3:20 PM
Row 479 | Withdrawn 3/22 due to failing ESA | Kaiya Hoogkamp | 04/30/24 10:27 AM
Row 480 | 3/12/2024 project failed ESA and was withdrawn. | Kaiya Hoogkamp | 10/15/24 2:32 PM
Row 482 | 1/22/24 customer requested to withdraw project. | Kaiya Hoogkamp | 02/27/24 12:00 PM
Row 483 | 2/22/2024 failed ESA | Kaiya Hoogkamp | 07/23/24 3:18 PM
Row 485 | 1/11/2024 customer withdrew after technical screen. | Kaiya Hoogkamp | 07/23/24 2:52 PM
Row 486 | 12/7/2023 project withdrew. | Kaiya Hoogkamp | 10/15/24 2:50 PM
Row 488 | Customer requested to withdraw on 1/4/2024 | Kaiya Hoogkamp | 05/07/24 10:57 AM
Row 488 | Refund issued in SAP | Kaiya Hoogkamp | 01/22/24 1:48 PM
Row 488 | Original contract 120005879 cancelled on 1/18/2024, customer withdrawn without doing ESA and PIA $1500 refunded. | Kaiya Hoogkamp | 01/18/24 11:33 AM
Row 488 | Duplicate contract 12000085887 created by Nate Lawrence was cancelled. No payment attached. | Kaiya Hoogkamp | 01/18/24 11:32 AM
Row 489 | 1/7/2024 customer requested to withdraw | Kaiya Hoogkamp | 05/22/24 9:09 AM
Row 491 | 1/2/2024 ESA failed, project withdrawn. | Kaiya Hoogkamp | 10/15/24 2:54 PM
Row 492 | 1/26/2024 project withdrawn after failing ESA | Kaiya Hoogkamp | 07/23/24 3:32 PM
Row 493 | 1/24/2024 customer has decided to withdraw the project. | Kaiya Hoogkamp | 02/27/24 1:21 PM
Row 494 | 2/20/2024 project failed ESA and withdrawn. | Kaiya Hoogkamp | 10/15/24 2:55 PM
Row 498 | No task 24 in SAP | Kaiya Hoogkamp | 12/17/24 2:40 PM
Row 499 | 5/16/2024 project requested to be withdrawn, project no longer viable. | Kaiya Hoogkamp | 10/15/24 2:57 PM
Row 500 | Adjusted invoice to $0.00 910266889 | Kaiya Hoogkamp | 05/09/25 8:26 AM
Row 500 | 5/1/2025 sent the additional invoice to the customer and developer. | Kaiya Hoogkamp | 05/01/25 10:51 AM
Row 500 | ESA Additional Amount $1125.84 Debit memo 910265603 | Kaiya Hoogkamp | 04/30/25 12:40 PM
Row 504 | $0.00 invoice 910269585 | Kaiya Hoogkamp | 05/30/25 8:05 AM
Row 504 | Zeroed out ESA invoice, we are waiving the cost, as the customer asked to hold off on study and never confirmed they wanted to continue with ESA. They did not send the deposit. | Kaiya Hoogkamp | 05/30/25 7:58 AM
Row 504 | 5/15/25 project withdrawn due to site feasibility | Kaiya Hoogkamp | 05/19/25 10:05 AM
Row 504 | 4/4/25 email for IA sent. 30 BD 5/19/2025 | Kaiya Hoogkamp | 04/04/25 3:43 PM
Row 504 | Customer has not paid ESA deposit. DO NOT issue COC until we receive payment | Kaiya Hoogkamp | 03/07/25 11:33 AM
Row 506 | original PIA 910202573/920222068 cancelled due to incorrect project name entered in description. Ticket INC3254016 entered to cancel. | Kaiya Hoogkamp | 12/05/23 1:45 PM
Row 508 | 1211/24 project requested to withdraw in favor of their level 4 project 599 | Kaiya Hoogkamp | 12/11/24 8:44 AM
Row 510 | 2/22/2024 project failed ESA and withdrew. | Kaiya Hoogkamp | 10/15/24 3:05 PM
Row 517 | Invoice adjustment issued to 910197534 to adjust 180.80 to 180. | Kaiya Hoogkamp | 10/12/23 9:21 AM
Row 518 | 10/19/2023 project withdrew. | Kaiya Hoogkamp | 10/15/24 3:06 PM
Row 520 | 10/16/2023 project withdrew. | Kaiya Hoogkamp | 10/15/24 3:07 PM
Row 521 | 1/31/2024 project failed ESA and withdrew. | Kaiya Hoogkamp | 10/15/24 3:09 PM
Row 524 | "Install 500 kVA Pad Mount Transformer." listed under "Estimated Cost to Interconnect". | Nathan Lawrence | 09/03/24 2:31 PM
Row 527 | 11/13/2023 project failed ESA and withdrew. | Kaiya Hoogkamp | 10/15/24 3:10 PM
Row 529 | 11/6/2023 project failed tech screen and withdrew. | Kaiya Hoogkamp | 10/15/24 3:17 PM
Row 530 | 10/17/2023 project withdrew. | Kaiya Hoogkamp | 10/15/24 3:23 PM
Row 531 | 10/25/2023 project failed ESA and withdrew. | Kaiya Hoogkamp | 10/15/24 3:18 PM
Row 533 | 910265923/920289271 paid on 5/29/25 | Kaiya Hoogkamp | 05/30/25 1:40 PM
Row 533 | additional ESA invioice: 910265923/920289271 | Kaiya Hoogkamp | 05/02/25 11:52 AM
Row 534 | Application was to update project size due to overgeneration. No equipment changes to the project. No COC needed per Ryley. | Nathan Lawrence | 07/09/26 12:07 PM
Row 534 | 2/11/2026 project is over 100 years old, does it still require COC? | Kaiya Hoogkamp | 05/20/26 3:36 PM
Row 537 | 11/21/2023 project failed ESA and withdrawn. | Kaiya Hoogkamp | 10/15/24 3:40 PM
Row 539 | 10/12/2023 project withdrew and downsized. | Kaiya Hoogkamp | 10/15/24 3:45 PM
Row 540 | 12/8/2023 application failed ESA. Project withdrawn. | Kaiya Hoogkamp | 06/24/24 11:53 AM
Row 542 | 9/8/2023 project unresponsive to outreach and withdrawn after 10 bd deadline. | Kaiya Hoogkamp | 10/15/24 3:48 PM
Row 543 | Has a related noti 10300727127 for customer building construction per Gary Ham | Nathan Lawrence | 07/30/24 8:36 AM
Row 545 | 9/14/2023 project failed ESA and project withdrawn. | Kaiya Hoogkamp | 10/16/24 7:40 AM
Row 549 | 9/11/2023 customer withdrew the project. | Kaiya Hoogkamp | 10/16/24 7:41 AM
Row 550 | 1/24/2024 customer withdrew project. | Kaiya Hoogkamp | 10/16/24 7:43 AM
Row 551 | 11/3/2023 project withdrew. | Kaiya Hoogkamp | 10/16/24 7:42 AM
Row 553 | Original PIA 910191401/920210205 was never cleared w/ payment and sales admin cleared 3/26/2024. Created new PIA 910223778/920244513 on 5/23/2024 to apply payment to. | Thomas Blanchard | 05/28/24 2:44 PM
Row 554 | 10/12/2023 project failed ESA and withdrew. | Kaiya Hoogkamp | 10/16/24 8:21 AM
Row 555 | 10/3/2023 project failed ESA and withdrew. | Kaiya Hoogkamp | 10/16/24 8:19 AM
Row 556 | Contract cancelled. | Kaiya Hoogkamp | 03/10/25 1:27 PM
Row 556 | 10/26/2023 project requested to withdraw | Kaiya Hoogkamp | 10/22/24 12:01 PM
Row 557 | ESA Cancelled | Kaiya Hoogkamp | 03/10/25 1:28 PM
Row 557 | 10/26/2023 customer withdrew project. | Kaiya Hoogkamp | 10/16/24 8:28 AM
Row 560 | 4/4/25 email for IA sent. 30 BD 5/19/2025 | Kaiya Hoogkamp | 04/04/25 3:28 PM
Row 561 | Noti was created in error, canceled 8/21/2023 | Nathan Lawrence | 09/06/24 8:39 AM
Row 562 | 9/20/2023 project failed ESA and withdrew. | Kaiya Hoogkamp | 10/16/24 8:30 AM
Row 563 | 8/16/23 withdrawn after project failed ESA | Kaiya Hoogkamp | 10/07/24 10:53 AM
Row 564 | 12/8/2025 they paid invoice 910266050/920289412 $140.73 | Kaiya Hoogkamp | 03/03/26 2:22 PM
Row 564 | Old Acct#: 30016568518 | Nathan Lawrence | 01/27/26 10:41 AM
Row 564 | 5/6/25 Sent additional ESA for study work | Kaiya Hoogkamp | 05/06/25 1:15 PM
Row 564 | Additional PIA for restudy work done Spring 2024 910266050/920289412 $140.73 | Kaiya Hoogkamp | 05/05/25 9:56 AM
Row 564 | Original developer Perennial Renewables LLC, sold to Madison Energy Infrastructure | Kaiya Hoogkamp | 11/26/24 12:58 PM
Row 565 | There is no task 24 in SAP | Kaiya Hoogkamp | 12/17/24 2:34 PM
Row 565 | South Array | Nathan Lawrence | 09/05/24 10:57 AM
Row 566 | No task 24 in SAP. | Kaiya Hoogkamp | 12/17/24 2:35 PM
Row 566 | North Array | Nathan Lawrence | 09/05/24 10:58 AM
Row 568 | 1/21/2025 customer withdrew | Kaiya Hoogkamp | 01/22/25 7:37 AM
Row 572 | 9/6/2023 project failed ESA and withdrew. | Kaiya Hoogkamp | 10/16/24 8:35 AM
Row 573 | 9/6/2023 project failed ESA and withdrew. | Kaiya Hoogkamp | 10/16/24 8:35 AM
Row 576 | 8/30/2023 project failed ESA and withdrew. | Kaiya Hoogkamp | 10/16/24 8:36 AM
Row 577 | No task 24 on noti 10301002401. | Nathan Lawrence | 12/17/24 2:54 PM
Row 580 | 8/16/2023 project failed ESA and withdrew. | Kaiya Hoogkamp | 10/16/24 8:37 AM
Row 582 | 1/8/2024 project withdrew. | Kaiya Hoogkamp | 10/16/24 8:38 AM
Row 584 | 9/2/2023 application withdrawn | Kaiya Hoogkamp | 10/18/24 11:48 AM
Row 588 | 7/30/2023 app failed ESA and withdrew | Kaiya Hoogkamp | 10/18/24 11:54 AM
Row 588 | TIN has been used for Acadia Energy, can I use that # | Jessie Ladaga | 06/16/23 12:55 PM
Row 589 | 6/30/2023 application withdrawn | Kaiya Hoogkamp | 10/18/24 11:49 AM
Row 590 | Can I use the Green Lantern #; emailed Christy | Jessie Ladaga | 06/16/23 12:45 PM
Row 592 | Debtor # extended | Jessie Ladaga | 06/16/23 10:45 AM
Row 593 | DEBTOR # CREATED | Jessie Ladaga | 06/29/23 12:52 PM
Row 594 | 2/12/26 project confirmed on hold | Kaiya Hoogkamp | 02/19/26 12:50 PM
Row 595 | noti is on debtor 932463 | Kaiya Hoogkamp | 08/28/25 9:54 AM
Row 596 | 9/21/2023 application withdrawn | Kaiya Hoogkamp | 10/18/24 12:01 PM
Row 597 | Invoice for NOTI 10301049886 paid 10/31/24 | Nathan Lawrence | 12/10/24 12:25 PM
Row 598 | 7/14/2023 app failed ESA and project withdrawn | Kaiya Hoogkamp | 10/18/24 12:00 PM
Row 599 | 6/25/2023 application withdrawn | Kaiya Hoogkamp | 10/18/24 12:02 PM
Row 599 | NH Solar Garden payment - confirmed via email - see email? is there a debtor #? is there a w9? | Jessie Ladaga | 06/14/23 5:34 PM
Row 600 | 5/21/26 Revision advised July 2026 as estimated project complete date and COC being sent | Kaiya Hoogkamp | 05/21/26 8:57 AM
Row 600 | this project failed tech screen in error and needs to be refunded the ESA charge- after rescreen on tech screen they passed. | William Dawe | 07/11/23 8:54 AM
Row 600 | this is on RE # - can i use 1289121? | Jessie Ladaga | 06/14/23 5:20 PM
Row 603 | additional charges found and billable per Portal | Staci Pellegrini | 03/13/24 1:05 PM
| Added charges of $246.68 to invoice on 3/20/24 | Thomas Blanchard | 03/21/24 7:38 AM
Row 603 | no debtor # created. Can i use 929103? W9 is lacking address. Sent email. | Jessie Ladaga | 06/14/23 4:31 PM
Row 603 | debtor # created | Jessie Ladaga | 06/14/23 4:23 PM
Row 603 | email sent requesting w9 | Jessie Ladaga | 05/19/23 11:33 AM
Row 605 | Original developer GREEN LANTERN DEVELOPMENT LLC, sold to Madison Energy Infrastructure | Kaiya Hoogkamp | 11/26/24 12:55 PM
Row 605 | Created new paid 910206445/920226265 ticket sent xfer 2500.00 to correct debtor | Staci Pellegrini | 01/08/24 12:32 PM
Row 605 | pia 910183424/920201756 was canceled by sales admin | Staci Pellegrini | 01/05/24 9:35 AM
Row 605 | Pia was cancel because the payment was on the original payee debtor 924257 / set itnow ticket move to 932591 and will xfer contract to me and then set up new pia to clear. | Staci Pellegrini | 01/05/24 9:33 AM
Row 605 | found debtor # = 932591 | Jessie Ladaga | 06/14/23 2:39 PM
Row 605 | requested w9 | Jessie Ladaga | 06/14/23 2:30 PM
Row 606 | 8/14/2023 application withdrawn | Kaiya Hoogkamp | 10/18/24 12:09 PM
Row 606 | w9 reques sent | Jessie Ladaga | 05/31/23 2:44 PM
Row 606 | Request for w9 was sent out by front end analysis on 5/12/2023 | Jessie Ladaga | 05/12/23 2:48 PM
Row 607 | 8/8/2023 app failed ESA and withdrew | Kaiya Hoogkamp | 10/18/24 12:05 PM
Row 607 | w9 request sent | Jessie Ladaga | 05/31/23 2:48 PM
Row 607 | w9 request sent on 5/12 with ESA | Jessie Ladaga | 05/12/23 2:49 PM
Row 608 | 7/26/23 project failed ESA and withdrawn. | Kaiya Hoogkamp | 09/05/24 10:25 AM
Row 609 | 8/3/2023 application withdrawn | Kaiya Hoogkamp | 10/18/24 12:13 PM
Row 612 | NO W9 REC;D THIS HAS A NOTI # 1508679 | Jessie Ladaga | 06/30/23 3:22 PM
Row 612 | sent a follow up email requesting w9 | Jessie Ladaga | 06/14/23 2:17 PM
Row 612 | w9 email request sent | Jessie Ladaga | 05/31/23 2:26 PM
Row 613 | No Task 24 on noti 10301016392. | Nathan Lawrence | 12/17/24 2:53 PM
Row 615 | 5/20/2024 project has withdrawn. | Kaiya Hoogkamp | 05/20/24 3:30 PM
Row 615 | has credit willo need to apply to balance on 83453 email sent to Kiaya | Staci Pellegrini | 01/04/24 2:52 PM
Row 615 | email sent requesting .pdf PIA (study about to kick off) | Jessie Ladaga | 05/12/23 1:49 PM
Row 616 | 6/22/2023 ESA failed, application withdrawn | Kaiya Hoogkamp | 10/18/24 12:15 PM
Row 616 | THIS WAS EXTENDED BY STACI | Jessie Ladaga | 06/14/23 3:49 PM
Row 616 | 1416460 = noti / can this be extended to use? | Jessie Ladaga | 06/14/23 2:07 PM
Row 618 | sent IT ticket | Jessie Ladaga | 05/11/23 9:34 AM
Row 619 | FBL5N review; ? | Jessie Ladaga | 05/17/23 3:00 PM
Row 619 | Sent IT | Jessie Ladaga | 05/15/23 9:20 AM
Row 620 | 10/19/2023 The project listed 83668 is in fact a cancelled project per conversation with developer just now- Ryan Darlow. | Kaiya Hoogkamp | 10/18/24 12:20 PM
Row 620 | to have contract 120005075 reassigned to me then closed out .incorrect debtor | Staci Pellegrini | 03/05/24 4:37 PM
Row 620 | Duplicate contract Pia created for Prj 83668 contract 120005075 debtor 928950 910179620/920197672 incorrect debtor payment 5/5 pa 8400015200 will need to be moved debtor 929226 and applied invoice 920198765 contract 120005124. sent email jess. | Staci Pellegrini | 06/14/23 2:46 PM
Row 620 | sent IT | Jessie Ladaga | 05/15/23 8:44 AM
Row 620 | cutomer has sent in confirmation of ESA payment | Jessie Ladaga | 05/10/23 4:23 PM
Row 620 | have w9 and debtor #, need signed ESA | Jessie Ladaga | 05/10/23 1:06 PM
Row 620 | W9 requested | Jessie Ladaga | 05/10/23 12:59 PM
Row 621 | Payment refund 896..58 was taken from prj 83670 and applied to level 4 prj balance prj 692 1/17/2024 | Staci Pellegrini | 04/26/24 11:30 AM
Row 623 | No Contractor charges yet 11/6 | Staci Pellegrini | 11/06/23 2:47 PM
Row 623 | Entered second IT ticket because ESA payment was not applied to invoice initally. The ticket is INC3048477. | Kaiya Hoogkamp | 08/28/23 11:22 AM
Row 623 | I called customer regarding payment on Rec Monitor since 7/14/2023 belongs to esa deposit /2075865680 | Staci Pellegrini | 08/15/23 3:36 PM
Row 623 | 1466464 - extended debtor # | Jessie Ladaga | 07/05/23 9:07 AM
Row 623 | w9 requested | Jessie Ladaga | 06/30/23 3:46 PM
Row 624 | Credit memo: 910266673 for $19.92 refund that is due | Kaiya Hoogkamp | 05/08/25 9:16 AM
Row 624 | 5/7/25 Sent contract to work flow | Kaiya Hoogkamp | 05/07/25 8:21 AM
Row 624 | New PIA 910266262/920289612 | Kaiya Hoogkamp | 05/06/25 9:42 AM
Row 624 | New Contract: 120007536 released on 5/6/25 | Kaiya Hoogkamp | 05/06/25 9:35 AM
Row 624 | Per Michelle and Brian and sales admin, because we cannot get the PIA to show on the contract, we need to cancel the contract and PIA and start over. 120005031 has been terminated | Kaiya Hoogkamp | 05/06/25 9:10 AM
Row 624 | 910266160/920289513 - new PIA created per Michelle in Sales Admin | Kaiya Hoogkamp | 05/05/25 3:04 PM
Row 624 | Original developer MECHANIC FALLS GLC SOLAR LLC, sold to Madison Energy Infrastructure | Kaiya Hoogkamp | 11/26/24 12:57 PM
Row 624 | INC3162470 ticket requesting payment | Kaiya Hoogkamp | 10/24/23 10:24 AM
Row 624 | Original PIA 910179625/920197692 was never cleared w/ payment and sales admin cleared 9/28/2023. Created new PIA 910199075/920218318 on 10/24/2023 to apply payment to. | Kaiya Hoogkamp | 10/24/23 10:19 AM
Row 625 | katie to create debtor # | Jessie Ladaga | 04/28/23 10:10 AM
Row 626 | old PIA that closed out 910178292/920196202 | Kaiya Hoogkamp | 11/01/23 3:11 PM
Row 626 | sent IT ticket | Jessie Ladaga | 05/12/23 4:07 PM
Row 626 | rec'd W9; found debtor; sent to Christy to fix spelling in SAP and confirm TIN's match | Jessie Ladaga | 04/26/23 12:14 PM
Row 629 | PAID IN FULL with PRJ 339 DG refund 1313.42 and a $290 open credit from prj 81817, (see emails) | Thomas Blanchard | 06/05/25 10:35 AM
Row 629 | 5/17/2023 app failed ESA and withdrawn | Kaiya Hoogkamp | 10/18/24 12:21 PM
Row 629 | pia was created by jess/ pia got cancelled due to no pmt being applied / found no confirmation of payment from the customerr via portal. I sent email to customer 11/11 to confirm if paid or not before we invoice | Staci Pellegrini | 01/11/24 11:36 AM
Row 629 | sent email to Sales Admin to have address updated Debtor # 923285 - office moved; sent W9 and IA for backup documentaiton | Jessie Ladaga | 06/14/23 12:22 PM
Row 629 | need to send email to update address-- speak with staci | Jessie Ladaga | 05/31/23 1:39 PM
Row 629 | debtor # reuqest sent | Jessie Ladaga | 05/10/23 12:52 PM
Row 630 | Original developer GREEN LANTERN DEVELOPMENT LLC, sold to Madison Energy Infrastructure | Kaiya Hoogkamp | 11/26/24 12:56 PM
Row 630 | Debtor creation requested | Jessie Ladaga | 05/09/23 2:38 PM
Row 631 | Former Customer Name: Glenn Walker, Former Developer Name: Acadia Energy, LLC | Nathan Lawrence | 03/24/26 9:23 AM
Row 631 | Kiaya created credit memo | Staci Pellegrini | 11/08/23 5:44 PM
Row 631 | sent email for OCR to place 2500 on 9003006 | Jessie Ladaga | 04/28/23 11:18 AM
Row 631 | sent KK a request to create debtor # | Jessie Ladaga | 04/26/23 1:13 PM
Row 632 | the Pia was canceled the payment is on sundog solar acct 922300 it now ticket to move 1/4/24 | Staci Pellegrini | 01/04/24 3:11 PM
Row 632 | Posting period closed for 5/25/23 date. Next Step? | Jessie Ladaga | 06/14/23 12:05 PM
Row 633 | Charges waived, contract closed on 5/7/2024 | Thomas Blanchard | 05/07/24 11:48 AM
Row 633 | PIA Had been preivously cancelled. Contract completed on 10/20/2023. We will not be billing the contractor charges as it was a pass. | Kaiya Hoogkamp | 10/20/23 11:11 AM
Row 633 | This was a tech screen fail in error, it was in fact a PASS but ESA was billed out. | Kaiya Hoogkamp | 10/20/23 11:08 AM
Row 634 | debtor # created | Jessie Ladaga | 05/15/23 2:24 PM
Row 634 | email sent requesting w9 | Jessie Ladaga | 05/10/23 10:52 AM
Row 635 | 4/27/2023 project failed ESA and withdrew | Kaiya Hoogkamp | 09/23/24 2:19 PM
Row 635 | sent request to KK to have # created | Jessie Ladaga | 04/26/23 1:38 PM
Row 637 | 4/23/2023 app withdrawn | Kaiya Hoogkamp | 10/18/24 12:23 PM
Row 638 | Creating a new PIA per Brian Turner as the old one got stuck in the system and was not retrievable. New PIA is 910220267/920240885 | Thomas Blanchard | 04/26/24 8:50 AM
Row 638 | requested transfer of $1500 from Debtor 1289121 to PIA 910212948, contract 120005077, debtor 1507097. Original payment was used on wrong project/debtor. | Thomas Blanchard | 02/27/24 12:50 PM
Row 638 | Payment details in project folder email 7/31/2023 payment 7/21/2023 1289121 2200004802 | Staci Pellegrini | 07/31/23 10:15 AM
Row 638 | I am having problems with this one, a few questions | Jessie Ladaga | 05/10/23 10:53 AM
Row 638 | No ESA created | Jessie Ladaga | 04/26/23 1:48 PM
Row 639 | 1449381 = NOTI | Jessie Ladaga | 07/05/23 9:36 AM
Row 639 | meeting with developer on 6/15 to review TS. Will know more about payment at that time. No contract or PIA created to date. | Jessie Ladaga | 06/14/23 11:41 AM
Row 639 | 5/17/2023; email sent (w9 request) | Jessie Ladaga | 05/17/23 4:52 PM
Row 639 | sent request for w9 to installer | Jessie Ladaga | 05/11/23 12:30 PM
Row 640 | April 3, 2024 developer requested withdraw | Kaiya Hoogkamp | 07/11/24 3:55 PM
Row 640 | completed refund 1/17/24 | Staci Pellegrini | 02/20/24 9:02 AM
Row 640 | sent invoices to customer 1/4/2024 this is credit back to the customer no other outstanding projects owed so i requested refund 0000000086 1/17/24 sap | Staci Pellegrini | 01/17/24 9:30 AM
Row 640 | Issue with customer name | Kristina Waterhouse | 04/03/23 2:39 PM
Row 641 | $ is still open on open cash draw as of 5/26 sent ITNOW ticket | Staci Pellegrini | 05/26/23 1:48 PM
Row 641 | 5/16/23 follow up email sent in RE of W9 | Jessie Ladaga | 05/17/23 4:39 PM
Row 641 | Put $2500 (paid on 5/15/2023) ESA fee on debtor 1568046, pending W-9 with Arundel Solar | Kaiya Hoogkamp | 05/16/23 2:44 PM
Row 641 | need w9 with ESA name, email request sent | Jessie Ladaga | 05/12/23 2:38 PM
Row 642 | Refund used towards outstanding novel invoice. | Kaiya Hoogkamp | 06/04/25 9:33 AM
Row 642 | debtor # request sent/ email attached | Jessie Ladaga | 05/10/23 6:23 PM
Row 642 | there is a fully exectued ESA | Jessie Ladaga | 05/10/23 10:22 AM
Row 642 | debtor # creation requested | Jessie Ladaga | 05/10/23 10:21 AM
Row 642 | No ESA - email sent requesting signed Agreement | Jessie Ladaga | 04/26/23 2:15 PM
Row 642 | Requested W9 4/4 | Kristina Waterhouse | 04/04/23 1:28 PM
Row 643 | 6/9/2023 application withdrew | Kaiya Hoogkamp | 10/22/24 12:10 PM
Row 643 | Chase Warren payment on 1289121; sent IT | Jessie Ladaga | 05/12/23 4:46 PM
Row 643 | After researching the project number was over written in error making info look incorrect. | Kristina Waterhouse | 05/04/23 1:52 PM
Row 643 | wrong project details on this ROW- updated cor | William Dawe | 05/04/23 9:54 AM
Row 643 | PIA sent to customer/developer (ReVision) | Jessie Ladaga | 04/26/23 2:51 PM
Row 643 | ESA uploaded; waiting on Christy to release from workfolow to release Contract | Jessie Ladaga | 04/24/23 1:26 PM
Row 643 | need CMP to sign ESA | Jessie Ladaga | 04/24/23 10:43 AM
Row 643 | reuqested katie to create debtor # | Jessie Ladaga | 04/17/23 12:27 PM
Row 644 | 120005064 completed on 2/27/2024 | Kaiya Hoogkamp | 02/27/24 12:33 PM
Row 644 | original contract 120005064 (created incorrectly on Revisions debtor) | Kaiya Hoogkamp | 10/24/23 9:39 AM
Row 644 | sent needed US mailing addy to Katie for # creation | Jessie Ladaga | 04/26/23 3:15 PM
Row 644 | katie to create debtor # | Jessie Ladaga | 04/17/23 12:31 PM
Row 645 | Additinal noti amount of $4547.11 was paid on 7/1/2025 | Kaiya Hoogkamp | 07/16/25 8:07 AM
Row 645 | Noti has additional invoice Follow up invoice sent 5/14/25 $4547.11 | Kaiya Hoogkamp | 06/30/25 10:16 AM
Row 645 | i can create the contract and not release | Jessie Ladaga | 05/10/23 4:25 PM
Row 645 | no signed ESA | Jessie Ladaga | 05/10/23 10:13 AM
Row 645 | Sent email requesting w9 | Jessie Ladaga | 05/09/23 12:16 PM
Row 646 | 4/4/25 email for IA sent. 30 BD 5/19/2025 | Kaiya Hoogkamp | 04/04/25 2:37 PM
Row 651 | Estimated in-service date is by end of 2026. Project has a waiver through Ch 313 pushing the construction deadline back until fall of 2027. | Nathan Lawrence | 02/23/26 4:26 PM
Row 652 | 9/26/25 Spoke with Peter on the phone, he confirmed to withdraw the project ((207)754-5025) | Kaiya Hoogkamp | 09/26/25 10:56 AM
Row 652 | 4/4/25 email for IA sent. 30 BD 5/19/2025 | Kaiya Hoogkamp | 04/04/25 2:46 PM
Row 654 | Customer withdraw request 4/5/23. Downsized and resubmitted as L1. | Nathan Lawrence | 10/15/24 3:33 PM
Row 656 | completed refund 1/17/24 sjp | Staci Pellegrini | 02/20/24 9:03 AM
Row 656 | sent invoices to customer 1/4/2024 this is credit back to the customer no other outstanding projects owed so i requested refund 0000000086 1/17/24 sap | Staci Pellegrini | 01/17/24 9:29 AM
Row 657 | Withdraw request from customer 3/21/23 after failed TS. | Nathan Lawrence | 10/15/24 3:28 PM
Row 658 | PIF | Thomas Blanchard | 05/29/24 11:06 AM
Row 658 | Moved 103.42 from Acadia refunded projects to this Acadia balance due. OK'd by Glenn Walker | Thomas Blanchard | 05/29/24 11:03 AM
Row 659 | 4/7/2025 app withdrawn | Kaiya Hoogkamp | 04/07/25 8:54 AM
Row 659 | 4/4/25 email for IA sent. 30 BD 5/19/2025 | Kaiya Hoogkamp | 04/04/25 2:44 PM
Row 660 | No COC needed for this project per Ryley and Sue Clary | Nathan Lawrence | 06/11/26 1:29 PM
Row 660 | formerly 30012680267 | Nathan Lawrence | 06/08/26 9:51 AM
Row 660 | 2/13/26 developer confirmed this project is not withdrawn and still active. Updating smarthsheets. This project is still active on CNEBA | Kaiya Hoogkamp | 02/19/26 10:44 AM
Row 660 | 2/13/26 sent follow up asking for COC, project is not withdrawn on CNEBA | Kaiya Hoogkamp | 02/13/26 9:39 AM
Row 660 | no documentation verifying withdrawal | Kaiya Hoogkamp | 10/22/24 12:13 PM
Row 664 | Noti 10300899161 CANC | Nathan Lawrence | 01/30/25 12:45 PM
Row 666 | cleared SAP | Jessie Ladaga | 05/11/23 1:08 PM
Row 666 | need to change/update name in contract, add ESA then release | Jessie Ladaga | 04/24/23 10:34 AM
Row 666 | Requested Katie created debtor | Jessie Ladaga | 04/17/23 12:17 PM
Row 666 | Requested debtor | Kristina Waterhouse | 04/04/23 1:20 PM
Row 667 | Moved 596.78 from Acadia refunded projects to this Acadia balance due. OK'd by Glenn Walker. PIF | Thomas Blanchard | 05/29/24 11:05 AM
Row 669 | contract reassigned to me | Staci Pellegrini | 09/26/23 2:15 PM
Row 669 | charges 1480.08/ 1500.00 will need to refund 19.92. | Staci Pellegrini | 09/26/23 2:03 PM
Row 669 | Created USM1 debtor | Kristina Waterhouse | 04/03/23 3:02 PM
Row 669 | Requested W9 4/3 | Kristina Waterhouse | 04/03/23 12:02 PM
Row 670 | Project changed from Tariff to kWh. Meters were swapped on 12/19. New meter# is G024406251, Noti# 500001427736 | Nathan Lawrence | 12/22/25 2:39 PM
Row 671 | Customer confirmed withdrawal 4/11/2023, resubmitted as a L4. | Nathan Lawrence | 10/15/24 6:07 PM
Row 677 | 12/5/2023 project withdrew due to wetlands and being unable to develop the land. | Kaiya Hoogkamp | 07/09/24 12:53 PM
Row 679 | 3/4/2024 the project failed ESA and is withdrawn. | Kaiya Hoogkamp | 07/09/24 1:00 PM
Row 679 | INC2871444 to move and clear PIA | Kristina Waterhouse | 05/31/23 2:19 PM
Row 679 | Requested debtor in SAP | Kristina Waterhouse | 04/26/23 11:30 AM
Row 679 | Emailed again for W9 request | Kristina Waterhouse | 04/25/23 1:51 PM
Row 679 | Requested W9 | Kristina Waterhouse | 04/04/23 2:22 PM
Row 680 | ESA amount 986.72, study fee was waived. | Kaiya Hoogkamp | 06/25/25 9:23 AM
Row 680 | ESA Fees waived! | Kristina Waterhouse | 04/05/23 2:59 PM
Row 681 | 8/23/2023 application withdrew | Kaiya Hoogkamp | 10/22/24 12:46 PM
Row 683 | Requested debtor in SAP | Kristina Waterhouse | 04/06/23 10:36 AM
Row 683 | Requested W9 | Kristina Waterhouse | 04/05/23 8:26 AM
Row 688 | Customer requested withdrawal 1/4/2023, downsized and resubmitted. | Nathan Lawrence | 10/15/24 6:02 PM
Row 689 | 2/1/2023 customer confirmed they wanted to withdraw | Kaiya Hoogkamp | 06/12/24 10:47 AM
Row 690 | 10300988531 CANC | Nathan Lawrence | 06/10/26 2:23 PM
Row 692 | 2/13/2026 emailed customer for update/confirmation if project is withdrawn | Kaiya Hoogkamp | 02/13/26 9:50 AM
Row 692 | no documentation confirming withdrawal | Kaiya Hoogkamp | 10/22/24 11:46 AM
Row 692 | Per emails the fees will be waived on this project. Requested Nate's approval. | Kristina Waterhouse | 04/27/23 7:52 AM
Row 692 | Request W9 | Kristina Waterhouse | 04/03/23 2:22 PM
Row 694 | Wthdrawal requested by customer 2/27/2023. | Nathan Lawrence | 10/15/24 5:56 PM
Row 694 | Submitted INC2876458 to open CM for refund | Kristina Waterhouse | 06/02/23 10:15 AM
Row 694 | Sent email requesting they confirm refund information | Kristina Waterhouse | 05/23/23 11:31 AM
Row 694 | Created debtor in SAP | Kristina Waterhouse | 05/04/23 10:02 AM
Row 694 | Followed up on W9 request | Kristina Waterhouse | 04/25/23 1:55 PM
Row 694 | W9 requested 4/3 | Kristina Waterhouse | 04/03/23 1:48 PM
Row 695 | Also terminated contract 120004858 | Kristina Waterhouse | 06/13/23 8:44 AM
Row 695 | Submitted INC2895073 to cancell PIA | Kristina Waterhouse | 06/13/23 8:44 AM
Row 695 | Waived per Nate 4/12/2023 | Kristina Waterhouse | 04/13/23 6:25 AM
Row 698 | 2/13/26 emailed customer for update | Kaiya Hoogkamp | 02/13/26 10:11 AM
Row 698 | no documentation confirming withdrawal | Kaiya Hoogkamp | 10/22/24 11:45 AM
Row 700 | Submitted INC2797202 to move and clear PIA | Kristina Waterhouse | 04/25/23 1:01 PM
Row 700 | Created debtor..... PIA is sitting on recon | Kristina Waterhouse | 04/12/23 2:09 PM
Row 700 | Requested W9 | Kristina Waterhouse | 04/06/23 11:14 AM
Row 701 | Missing signed IA BUT we do have a COC | Kaiya Hoogkamp | 10/28/24 1:39 PM
Row 701 | waiting on transfomrer upgrade noti sent 3/27/2023 | William Dawe | 03/31/23 12:13 PM
Row 701 | This should have been a pass tech screen per Will @katherine.white@cmpco.com @staci.pellegrini@cmpco.com | Kristina Waterhouse | 03/23/23 2:47 PM
Row 702 | Customer confirmed withdrawal 2/15/2023 after failed TS, resubmitted as L4. | Nathan Lawrence | 10/15/24 5:52 PM
Row 705 | 2/13/26 sent email for update to developer | Kaiya Hoogkamp | 02/13/26 10:28 AM
Row 705 | no documentation confirming withdrawal | Kaiya Hoogkamp | 10/22/24 11:44 AM
Row 707 | Project sold to Perennial September 2024. New IA sent 10/2/24. Awaiting letter of intent and updated assignement sheet - NAL 10/2/24. | Nathan Lawrence | 10/02/24 10:37 AM
Row 707 | sent IT ticket | Jessie Ladaga | 05/11/23 9:59 AM
Row 708 | 0000001772 $11.20 refund for overpayment of application fee | Kaiya Hoogkamp | 07/30/25 1:44 PM
Row 711 | paid 07-06-2023 | Helen Markham | 01/11/24 10:40 AM
Row 711 | reopend aplication due to the POI incorrect during screenings awaiting on DE for updated results | William Dawe | 05/08/23 10:41 AM
Row 711 | Might be waiving second set of ESA Charges?????? | Kristina Waterhouse | 05/08/23 10:27 AM
Row 711 | Requested USM1 debtor in SAP | Kristina Waterhouse | 05/08/23 10:19 AM
Row 711 | They replied that Goodwin Motors was not a valid DBA for "FRG, Inc"... responded that we need customer name to match on W9 | Kristina Waterhouse | 04/25/23 12:15 PM
Row 711 | Followed up on W9 request | Kristina Waterhouse | 04/12/23 7:20 AM
Row 711 | Requested W9 | Kristina Waterhouse | 04/07/23 1:13 PM
Row 713 | Customer confirmed project withdrawal 2/15/2023 after failed TS. | Nathan Lawrence | 10/15/24 5:48 PM
Row 714 | the full esa study 3206.84 which has been paid in full as of 4/21/2023 | Staci Pellegrini | 06/09/23 12:09 PM
Row 714 | sent ITNOW ticket INC2867479 to clear pmt with invoice within SAP | Staci Pellegrini | 05/30/23 8:50 AM
Row 714 | sent it now ticket to cancel the Pia 2500.00 to invoice in full pmt made by customer | Staci Pellegrini | 04/27/23 9:05 AM
Row 715 | Customer withdraw request 6/13/2023. | Nathan Lawrence | 10/15/24 5:42 PM
Row 715 | contract completed | Staci Pellegrini | 02/27/24 8:12 AM
Row 715 | INC3066209 entered ticket to cancel PIA | Kaiya Hoogkamp | 09/05/23 11:14 AM
Row 715 | released contract 9/5/2023 & Informed Christy prj is withdrawn, she will cancel | Kaiya Hoogkamp | 09/05/23 10:59 AM
Row 715 | Found that this should not have been invoiced per Will dated 6/13/23 This project 82404 withdrew before ESA. Contract and PIA will need to be canceled. | Staci Pellegrini | 06/14/23 11:54 AM
Row 715 | invoice sent to customer | Jessie Ladaga | 05/15/23 9:31 AM
Row 715 | waiting on invoice; then need to sent to developer | Jessie Ladaga | 05/11/23 12:49 PM
Row 715 | esa agreement sent on 5/8/2023 waiting on dev and signature | William Dawe | 05/08/23 2:32 PM
Row 715 | need to send invoice. no signed ESA as of 4/24/2023 | Jessie Ladaga | 04/24/23 2:46 PM
Row 716 | INC2889448 to clear payment | Kristina Waterhouse | 06/09/23 9:06 AM
Row 716 | INC2770901 to clear PIA | Kristina Waterhouse | 04/12/23 12:47 PM
Row 716 | Requested debtor in SAP | Kristina Waterhouse | 04/11/23 1:56 PM
Row 716 | Requested W9 | Kristina Waterhouse | 04/07/23 1:35 PM
Row 717 | Customer confirmed PRJ withdrawn 2/23/23. Replaced w/ 82924. | Nathan Lawrence | 10/15/24 4:00 PM
Row 718 | 1233.40 | Staci Pellegrini | 08/16/23 11:32 AM
Row 718 | Extended debtor to 90/90 | Kristina Waterhouse | 04/06/23 10:21 AM
Row 718 | Requested W9 | Kristina Waterhouse | 04/05/23 8:36 AM
Row 719 | Submitted INC2807753 to open CM 910178007 for refund | Kristina Waterhouse | 05/01/23 9:40 AM
Row 720 | Project withdrawn 5/11/23, failed ESA. | Nathan Lawrence | 10/15/24 3:57 PM
Row 720 | Submitted INC2770359 to move/clear PIA | Kristina Waterhouse | 04/12/23 10:17 AM
Row 720 | Katherine used this PIA for project 82255 | Kristina Waterhouse | 04/12/23 8:42 AM
Row 720 | Found PIA confirmation but don't see payment? | Kristina Waterhouse | 04/11/23 2:34 PM
Row 720 | Created debtor | Kristina Waterhouse | 04/07/23 2:05 PM
Row 720 | Requested W9 4/3 | Kristina Waterhouse | 04/03/23 12:11 PM
Row 721 | 4/10/2024 project withdrawn per customer request. They cannot receive permits required to build. | Kaiya Hoogkamp | 04/10/24 3:15 PM
Row 721 | remaining credit will need to be refunded | Staci Pellegrini | 10/06/23 8:45 AM
Row 721 | invoice created 3/9/2023 sjp | Staci Pellegrini | 03/09/23 11:31 AM
Row 722 | The invoice was paid using a bulk refund from other Level2 Novel projects that were owed a refund. (see attachment) | Thomas Blanchard | 06/17/25 10:06 AM
Row 722 | 1/26/2023 failed esa and withdrew | Kaiya Hoogkamp | 10/22/24 11:42 AM
Row 722 | can't find deposit | Kristina Waterhouse | 04/13/23 10:07 AM
Row 722 | extended debtor in SAP | Kristina Waterhouse | 04/11/23 2:41 PM
Row 724 | Submitted INC2836191 to clear old milestone. Changed contract amount and released. | Kristina Waterhouse | 05/15/23 11:51 AM
Row 724 | Sumbitted CM 910179847 to clear incorrect invoice. Then need to redo milestone. New PIA #1 910179850/920197922 INC2832601 to move money from old PIA New PIA #2 910179851/ INC2832623 to move money | Kristina Waterhouse | 05/12/23 9:27 AM
Row 724 | Katherine used the wrong PIA payment and dollar amount.... This project only had a PIA of $500. Submitted INC270359 to cancel PIA 910173793/920191452 | Kristina Waterhouse | 04/12/23 9:56 AM
Row 725 | Followed up on check - still not receieved. | Kristina Waterhouse | 06/22/23 12:41 PM
Row 725 | Check is in the mail 6/2/23 | Kristina Waterhouse | 06/06/23 7:09 AM
Row 725 | Extended debtor in SAP | Kristina Waterhouse | 04/12/23 10:43 AM
Row 725 | Requested W9 | Kristina Waterhouse | 04/11/23 2:56 PM
Row 727 | 10/21/2024 project requested withdrawal | Kaiya Hoogkamp | 10/22/24 11:41 AM
Row 730 | INC2873394 to clear payment | Kristina Waterhouse | 06/01/23 8:55 AM
Row 730 | INC2773312 to clear PIA | Kristina Waterhouse | 04/13/23 10:35 AM
Row 730 | Extended debtor in SAP | Kristina Waterhouse | 04/12/23 11:22 AM
Row 731 | Customer withdraw request 2/9/23 after failed TS. | Nathan Lawrence | 10/15/24 3:49 PM
Row 732 | 5/22/2023 customer confirmed withdrawing project | Kaiya Hoogkamp | 06/20/24 8:32 AM
Row 735 | Submitted INC2807736 to open credit memo for refund | Kristina Waterhouse | 05/01/23 9:32 AM
Row 735 | INC2773476 to clear PIA | Kristina Waterhouse | 04/13/23 11:31 AM
Row 735 | Emailed Christy.... debtors don't match W9 | Kristina Waterhouse | 04/12/23 11:39 AM
Row 736 | found email stating "I am writing to inform you that we do not plan to request further study for this project or to reapply as a level 4 interconnection project." from developer sent on 3/24/23. Project failed tech screen, assuming this is withdrawal confirmation. | Kaiya Hoogkamp | 02/13/26 11:04 AM
Row 736 | no documentation confirming withdrawal | Kaiya Hoogkamp | 10/22/24 11:40 AM
Row 737 | 1/31/2025 submitted refund for duplicate applicaiton payment $192. | Kaiya Hoogkamp | 01/31/25 3:25 PM
Row 737 | Sent email requesting refund information. | Kristina Waterhouse | 06/13/23 8:12 AM
Row 737 | INC2894905 to open payment for refund | Kristina Waterhouse | 06/13/23 8:08 AM
Row 740 | 2/22/2023 project failed ESA and withdrew. | Kaiya Hoogkamp | 10/16/24 8:42 AM
Row 740 | Can't find fully executed ESA | Kristina Waterhouse | 04/13/23 11:54 AM
Row 740 | Extended debtor in SAP | Kristina Waterhouse | 04/12/23 11:52 AM
Row 741 | IA for Tenant Change sent 10/3/24. Changed from "Moose River Lumber Co" to "Boundary Co". | Nathan Lawrence | 10/03/24 12:53 PM
Row 742 | Submitted INC2822008 to clear PIA | Kristina Waterhouse | 05/08/23 11:10 AM
Row 742 | Requested Debtor in SAP | Kristina Waterhouse | 05/04/23 10:14 AM
Row 742 | Followed up on W9 request | Kristina Waterhouse | 04/25/23 2:18 PM
Row 742 | Requested W9 | Kristina Waterhouse | 04/13/23 1:32 PM
Row 743 | 1/27/26 sent coordination study invoice | Kaiya Hoogkamp | 01/27/26 12:52 PM
Row 743 | Coordination Study Invoice $750.56, debtor: 929912 USS1: 9010513 Invoice: 910304932/920329898 | Kaiya Hoogkamp | 01/21/26 2:00 PM
Row 743 | Per Staci we have reassignment, new W9 and new IA so we are billing under Propspect Solar One LLC.... Extended USM1 in SAP | Kristina Waterhouse | 04/13/23 12:09 PM
Row 743 | The ESA is under VCP but customer is now Prospect Solar One LLC.... | Kristina Waterhouse | 04/12/23 12:09 PM
Row 745 | No Task 24 on noti 10300920873. | Nathan Lawrence | 12/17/24 2:43 PM
Row 746 | 2/9/2023 application withdrew | Kaiya Hoogkamp | 10/16/24 2:09 PM
Row 748 | 11/8/2022 project failed ESA and withdrew. | Kaiya Hoogkamp | 10/16/24 2:12 PM
Row 748 | Sent follow up email on refund info | Kristina Waterhouse | 06/02/23 10:58 AM
Row 748 | Sent follow up email for refund info. | Kristina Waterhouse | 05/22/23 7:40 AM
Row 748 | INC2836420 to open funds for refund and emailed customer for refund info | Kristina Waterhouse | 05/15/23 1:26 PM
Row 748 | Refund on straight invoice | Kristina Waterhouse | 04/13/23 1:41 PM
Row 749 | Old Acct# 30013303463 | Nathan Lawrence | 01/28/26 3:42 PM
Row 750 | 11/16/2022 project requested to withdraw. | Kaiya Hoogkamp | 10/16/24 2:13 PM
Row 750 | Emailed again for status on where the payment was moved | Kristina Waterhouse | 05/22/23 1:28 PM
Row 750 | This projects deposit was cleared to PRJ 81513. PRJ 81513's deposit went to consumption. Emailed Sales admin. | Kristina Waterhouse | 04/14/23 11:53 AM
Row 750 | Created debtor in SAP | Kristina Waterhouse | 04/13/23 2:22 PM
Row 750 | Requested W9 4/3 | Kristina Waterhouse | 04/03/23 1:47 PM
Row 751 | 4/14/2023 project withdrawn | Kaiya Hoogkamp | 10/16/24 2:23 PM
Row 751 | Submitted INC2871126 to clear PIA | Kristina Waterhouse | 05/31/23 12:24 PM
Row 751 | PRJ 81958's deposit is missing. PRJ 81959's deposit was cleared to 81958. Sent email to sales admin to track down payment. There is an uncleared 500 on debtor 931931 but it's just a bank recon and I can't find anything else tied to the doc #. | Kristina Waterhouse | 05/18/23 2:03 PM
| Treasurey was able to find the payment and release it to sundry. | Kristina Waterhouse | 05/25/23 2:03 PM
Row 751 | Requested debtor in SAP | Kristina Waterhouse | 05/04/23 10:59 AM
Row 751 | Requested W9 | Kristina Waterhouse | 04/14/23 1:04 PM
Row 752 | 12/7/2022 project failed ESA and withdrew. | Kaiya Hoogkamp | 10/16/24 2:22 PM
Row 753 | 10/13/2022 project withdrawn. | Kaiya Hoogkamp | 10/16/24 2:21 PM
Row 754 | 910318310/920343864 $500 debit memo created to clear PIA | Kaiya Hoogkamp | 05/07/26 12:41 PM
Row 754 | 4/4/25 email for IA sent. 30 BD 5/19/2025 | Kaiya Hoogkamp | 04/04/25 2:26 PM
Row 754 | Adjusted straight invoice w 910185253 | Kristina Waterhouse | 07/03/23 8:30 AM
Row 754 | Need to change the contract type to show guarantee | Kristina Waterhouse | 05/08/23 1:16 PM
Row 754 | Changed NOTI into USM1 | Kristina Waterhouse | 05/04/23 10:22 AM
Row 754 | Requested W9 | Kristina Waterhouse | 04/14/23 12:54 PM
Row 756 | 2/21/2023 application withdrawn. | Kaiya Hoogkamp | 10/16/24 2:20 PM
Row 757 | Invoice for NOTI 10300952863 paid 11/11/2024 | Nathan Lawrence | 12/10/24 12:26 PM
Row 757 | Updated ESA name to Rewild per ESA agreement | Kristina Waterhouse | 03/20/23 12:48 PM
Row 759 | 1/26/2023 failed ESA and project withdrew. | Kaiya Hoogkamp | 10/16/24 2:17 PM
Row 759 | INC2803382 to cancel Katherines old PIA 910174793, it was never paid | Kristina Waterhouse | 04/27/23 1:24 PM
Row 760 | ESA total Amount $3206.84, we waived the study fee due to original tech screen pass and then failure | Kaiya Hoogkamp | 06/25/25 2:46 PM
Row 760 | 9/6/2022 project failed ESA and withdrew. | Kaiya Hoogkamp | 10/16/24 2:15 PM
Row 762 | ESA Amount: $500, was paid 1/18/2023 | Kaiya Hoogkamp | 06/25/25 11:31 AM
Row 762 | ESA total Billed: $1850.1, ESA was waived due to original tech screen was a pass, when it should have failed. | Kaiya Hoogkamp | 06/25/25 11:29 AM
Row 762 | 11/21/2022 project failed ESA and withdrew. | Kaiya Hoogkamp | 10/16/24 2:29 PM
Row 762 | the PIA was refunded customer not charged because of mis communication and email accidentially sent stating it was Pass when it was not ... | Staci Pellegrini | 01/11/24 12:30 PM
Row 762 | PIA was refunded! | Kristina Waterhouse | 05/04/23 11:21 AM
Row 762 | Found my deposit but it's cleared to a DC?? | Kristina Waterhouse | 04/14/23 1:39 PM
Row 763 | $555.23 Paid 4/1/2026 | Kaiya Hoogkamp | 06/10/26 11:16 AM
Row 763 | 6/17/2025 Remaining balance is $555.23 | Kaiya Hoogkamp | 06/17/25 11:24 AM
Row 763 | Correct Debtor is 933090 | Kaiya Hoogkamp | 04/16/25 9:06 AM
Row 763 | ESA Contract 120007418 INVOICE: 910262401 | Kaiya Hoogkamp | 04/09/25 9:03 AM
Row 763 | Coordination Study Contract 12007402 INVOICE: 910262399 | Kaiya Hoogkamp | 04/09/25 8:55 AM
Row 763 | NEW $500 contract: 120007418 PIA 910258361/920281370 | Kaiya Hoogkamp | 03/18/25 10:20 AM
Row 763 | Credit memo created 3/11/25: 910256926/920280771 & released | Kaiya Hoogkamp | 03/11/25 1:46 PM
Row 763 | Second contract for coordination study ($3200): 120007402. PIA: 910256233/920279200 | Kaiya Hoogkamp | 03/05/25 3:56 PM
Row 763 | 4/11/2023 project withdrew. | Kaiya Hoogkamp | 10/16/24 2:25 PM
Row 763 | Helen followed up on outstanding bal 2/14/24 | Staci Pellegrini | 02/28/24 4:24 PM
Row 763 | invoice 910197050 created for $500.00 ESA this correct debtor. | Staci Pellegrini | 10/06/23 9:35 AM
Row 763 | Need to lower the contract amount... this is the one that's cleared to a straight invoice | Kristina Waterhouse | 05/25/23 2:16 PM
| because of this kristina's invoice will need to be cancel and rebilled correctly with a PIA | Staci Pellegrini | 09/20/23 10:39 AM
Row 763 | PRJ 81958's deposit is missing. PRJ 819589's deposit was cleared to 81958. Sent email to sales admin to track down payment. There is an uncleared 500 on debtor 931931 but it's just a bank recon and I can't find anything else tied to the doc #. | Kristina Waterhouse | 05/18/23 2:03 PM
| this 500.00 is actual on debtor 931931, had to cancel invoice on 931931 and have $500.00 pmt mvd 933090 | Staci Pellegrini | 09/20/23 10:39 AM
Row 763 | i canceled the straight invoice last week ( smartsheets down) uner 931931 910160414/920176842 (adj 0.00) and asked for money to be moved over 933090. | Staci Pellegrini | 09/20/23 10:37 AM
Row 763 | email sent to Kaiya and straight invoice will need to be canceled. and contract reset from no guarantee to a guarantee. | Staci Pellegrini | 08/22/23 4:38 PM
Row 763 | PIA payment is pa 8400040065 11/15/2022 500.00 sitting on 931931 and needs to be moved to 933090. | Staci Pellegrini | 08/22/23 4:37 PM
Row 763 | INC2871110 to cancel PIA... paid with straight invoice | Kristina Waterhouse | 05/31/23 12:25 PM
Row 763 | Requested debtor in SAP | Kristina Waterhouse | 05/04/23 11:00 AM
Row 764 | 10/19/2022 project failed ESA and withdrew. | Kaiya Hoogkamp | 10/16/24 2:31 PM
Row 764 | Sent follow up email on refund info. | Kristina Waterhouse | 05/22/23 7:36 AM
Row 764 | Sent email to confirm refund info | Kristina Waterhouse | 05/15/23 12:58 PM
Row 764 | Submitted INC2836298 to clear invoice and open 766.60 for refund | Kristina Waterhouse | 05/15/23 12:52 PM
Row 764 | Exteded debtor in SAP | Kristina Waterhouse | 05/04/23 11:45 AM
Row 765 | NEW invoice on debtor 924030. Invoice: 910267874/920291265 | Kaiya Hoogkamp | 05/15/25 9:28 AM
Row 765 | Invoice adjustment to $0, 910267871 | Kaiya Hoogkamp | 05/15/25 9:06 AM
Row 765 | The correct debtor is 924030 | Kaiya Hoogkamp | 05/15/25 8:23 AM
Row 765 | UPDATED Invoice for $1000: 910262692/920285786 | Kaiya Hoogkamp | 04/10/25 1:34 PM
Row 765 | 4/10/25 app invoice adjustment to $0.00 910262686 | Kaiya Hoogkamp | 04/10/25 1:27 PM
Row 766 | 10/10/2022 project failed ESA and withdrew. | Kaiya Hoogkamp | 10/16/24 2:32 PM
Row 767 | sent email Sachin 4/11 for W-9 | Staci Pellegrini | 04/11/23 9:57 AM
Row 768 | Original ESA Amount that was waived was $1850.10 | Kaiya Hoogkamp | 06/04/25 9:50 AM
Row 768 | ESA fee waived per Nate P 9/7/2022 due to tech screen actually being a failure, not a pass, and the ESA was required to be done. | Kaiya Hoogkamp | 06/04/25 9:48 AM
Row 769 | No Task 24 on noti 10300965727 | Nathan Lawrence | 12/17/24 2:41 PM
Row 769 | Submitted INC2882919 to clear the 2000 HB to the new invoice and leave 396.58 open for refund. | Kristina Waterhouse | 06/06/23 9:32 AM
Row 769 | Adjusted origianl deposit invoice | Kristina Waterhouse | 06/02/23 10:50 AM
Row 769 | Emailed for refund info | Kristina Waterhouse | 05/25/23 1:07 PM
Row 769 | Extended debtor in SAP | Kristina Waterhouse | 05/04/23 11:49 AM
Row 769 | Changed ESA name from Revision to Wolf's Neck Farm as it was listed incorrectly | Kristina Waterhouse | 03/20/23 12:48 PM
Row 770 | 9/28/2022 project failed ESA and withdrew | Kaiya Hoogkamp | 10/16/24 2:49 PM
Row 771 | 3/3/2023 application withdrawn. | Kaiya Hoogkamp | 10/16/24 2:59 PM
Row 772 | 10/10/2022 project failed ESA and withdrew | Kaiya Hoogkamp | 10/16/24 2:57 PM
Row 773 | 10/19/2023 failed ESA, application withdrew. | Kaiya Hoogkamp | 10/17/24 10:55 AM
Row 773 | Canceled Katherine's PIA - INC2802646 | Kristina Waterhouse | 04/27/23 9:33 AM
Row 773 | Cancelled Katherine's contract, cannot find PIA and this needs to be released. | Kristina Waterhouse | 04/25/23 9:38 AM
Row 774 | 10/19/2022 project failed ESA and withdrew. | Kaiya Hoogkamp | 10/17/24 10:51 AM
Row 775 | App invoice adjusted to $0.00 910297254 | Kaiya Hoogkamp | 11/19/25 10:35 AM
Row 775 | 2/9/2023 application withdrew. | Kaiya Hoogkamp | 10/17/24 10:50 AM
Row 776 | App invoice adjusted to $0.00 910297257 | Kaiya Hoogkamp | 11/19/25 10:38 AM
Row 776 | 2/9/2023 application withdrew. | Kaiya Hoogkamp | 10/17/24 10:36 AM
Row 777 | 7/15/2025 sent follow up for ESA invoice payment | Kaiya Hoogkamp | 07/15/25 8:43 AM
Row 777 | 9/23/2022 project failed ESA and withdrew. | Kaiya Hoogkamp | 10/17/24 10:29 AM
Row 777 | sent reminder email for payment 1/10/2024 | Helen Markham | 01/10/24 2:52 PM
Row 777 | No deposit required | Kristina Waterhouse | 05/04/23 11:29 AM
Row 779 | 9/26/2022 application withdrawn. | Kaiya Hoogkamp | 10/16/24 3:02 PM
Row 780 | 8/3/2022 application withdrew. | Kaiya Hoogkamp | 10/17/24 11:07 AM
Row 781 | 10/19/2022 failed ESA and withdrew. | Kaiya Hoogkamp | 10/17/24 10:59 AM
Row 781 | The Payment 500.00 Kristina used originated 922312 clearing doc 2200003472 | Staci Pellegrini | 01/10/24 1:29 PM
Row 781 | per Portal & SAP $500.00 was invoiced under 910160407 10/21/2022 and cleared. for 81848 | Staci Pellegrini | 10/17/23 8:01 AM
| debtor 922331 | Staci Pellegrini | 10/17/23 11:54 AM
Row 781 | INC2855649 to move payment and clear PIA | Kristina Waterhouse | 05/24/23 9:03 AM
Row 781 | Submitted INC2855572 to clear adjusted invoice | Kristina Waterhouse | 05/24/23 8:45 AM
Row 781 | Released CM.... will do milestone after so it doesn't get stuck in my WF | Kristina Waterhouse | 05/23/23 11:15 AM
Row 781 | CM 910180038 to clear incorrect invoice | Kristina Waterhouse | 05/15/23 11:59 AM
Row 781 | I found a deposit when I was about to send this out to the customer..... need to adjust invoice and redo with PIA. | Kristina Waterhouse | 05/15/23 10:18 AM
Row 782 | 1/17/2023 failed ESA, application withdrawn. | Kaiya Hoogkamp | 10/17/24 11:19 AM
Row 782 | INC2856078 to clear random HA/HT pair | Kristina Waterhouse | 05/24/23 10:42 AM
Row 782 | 910181237 to clear Katherine's incorrect invoice | Kristina Waterhouse | 05/24/23 10:18 AM
Row 782 | Submitted ticket # INC2807808 to clear PIA | Kristina Waterhouse | 05/01/23 10:36 AM
Row 782 | Submitted ticket INC2807806 to cancel hx invoice 910165985 which never had a payment cleared to it. | Kristina Waterhouse | 05/01/23 10:31 AM
Row 783 | Ticket to cancel old PIA was closed but never done.... submitted INC2932865 | Kristina Waterhouse | 06/30/23 10:11 AM
Row 783 | Emailed front end.... I don't think a deposit was paid on this one. | Kristina Waterhouse | 05/09/23 12:16 PM
Row 783 | Submitted ticket INC2807815 to cancel PIA INC2807815, it was never paid so we'll bill total charges on milestone | Kristina Waterhouse | 05/01/23 10:40 AM
Row 784 | 9/28/2022 failed ESA and withdrew | Kaiya Hoogkamp | 10/17/24 11:28 AM
Row 784 | Extended debtor in SAP | Kristina Waterhouse | 04/27/23 12:05 PM
Row 784 | Cancelled Katherine's old contract | Kristina Waterhouse | 04/25/23 9:41 AM
Row 786 | 8/8/2022 failed tech screen, no formal email requesting withdraw. | Kaiya Hoogkamp | 10/17/24 11:45 AM
Row 787 | Check mailed 6/13/23 | Kristina Waterhouse | 06/19/23 7:26 AM
Row 787 | Submitted INC2856595 to clear PIA | Kristina Waterhouse | 05/24/23 2:14 PM
Row 787 | Extended debtor in SAP | Kristina Waterhouse | 05/22/23 2:14 PM
Row 787 | Submitted INC2844557 to unblock debtor | Kristina Waterhouse | 05/18/23 12:53 PM
Row 787 | Requested W9 | Kristina Waterhouse | 05/15/23 1:39 PM
Row 789 | 9/12/2022 project withdrew | Kaiya Hoogkamp | 10/17/24 11:55 AM
Row 789 | Confirmed project never went to ESA | Kristina Waterhouse | 04/27/23 8:49 AM
Row 789 | Doesn't look like the ESA on this one was ever actually executed, project was withdrawn the same day the agreement was issued to the customer. | Kristina Waterhouse | 04/27/23 8:11 AM
Row 789 | Application was withdrawn 9/12/22.... we need to verify the study was not aleady started. | Kristina Waterhouse | 04/05/23 7:27 AM
Row 790 | 9/28/2022 failed ESA and withdrew. | Kaiya Hoogkamp | 10/17/24 11:49 AM
Row 790 | Submitted INC2802599 to cancel Katherine's old PIA | Kristina Waterhouse | 04/27/23 9:25 AM
Row 792 | paid 08/03/2023 | Helen Markham | 01/11/24 10:13 AM
Row 792 | Customer's app fee was sent to doubtful debt, email sent to see if we should bill this cost | Kristina Waterhouse | 05/26/23 1:30 PM
Row 792 | No dates on the ESA agreement. Emailed WIll and Jess to see if they can be added. | Kristina Waterhouse | 05/25/23 1:16 PM
Row 792 | Emailed Christy - there's a debtor that's starred out that could be the right one? | Kristina Waterhouse | 05/15/23 1:44 PM
Row 793 | 9/1/2022 application withdrawn. | Kaiya Hoogkamp | 10/17/24 12:22 PM
Row 795 | 500.00 Pia created ... need to bill remaining | Staci Pellegrini | 06/20/23 4:26 PM
Row 795 | 120004855 - cancelled contract | Kristina Waterhouse | 05/26/23 12:06 PM
Row 795 | Brian is going to cancel the PIA that katherine created on Revision ... as this needs to go on Oceanview instead. | Staci Pellegrini | 05/24/23 3:56 PM
Row 798 | INC2887911 to open 889.94 for refund. | Kristina Waterhouse | 06/08/23 10:19 AM
Row 798 | INC2874422 to clear PIA | Kristina Waterhouse | 06/01/23 2:10 PM
Row 798 | CONTRACTOR CHARGES | Staci Pellegrini | 04/18/23 4:16 PM
Row 801 | 7/25/2022 application withdrawn. | Kaiya Hoogkamp | 10/17/24 12:51 PM
Row 802 | 8/3/2022 application withdrawn | Kaiya Hoogkamp | 10/17/24 12:50 PM
Row 803 | 2/13/26 sent a follow up about withdrawal. | Kaiya Hoogkamp | 02/13/26 11:59 AM
Row 803 | no documentation verifying withdrawal. | Kaiya Hoogkamp | 10/17/24 12:39 PM
Row 804 | 2/10/2023 application withdrew | Kaiya Hoogkamp | 10/17/24 12:24 PM
Row 805 | 2/10/2023 application withdrawn. | Kaiya Hoogkamp | 10/17/24 12:23 PM
Row 807 | 0000001740 draft for refund fo $4.80 for an overpayment of their application fee | Kaiya Hoogkamp | 07/23/25 11:23 AM
Row 807 | 4/4/25 email for IA sent. 30 BD 5/19/2025 | Kaiya Hoogkamp | 04/04/25 2:06 PM
Row 808 | 12/6/2022 application withdrawn. | Kaiya Hoogkamp | 10/17/24 12:54 PM
Row 809 | 8/10/2022 application withdrawn. | Kaiya Hoogkamp | 10/17/24 12:57 PM
Row 809 | Created USS1 under NES | Kristina Waterhouse | 05/31/23 1:51 PM
Row 809 | Requested W9 | Kristina Waterhouse | 05/30/23 12:07 PM
Row 810 | Requested W9 | Kristina Waterhouse | 05/30/23 12:11 PM
Row 810 | This project used deposit meant for project 81972. Deposit meant for this project was sent to consumption.... emailed sales admin. | Kristina Waterhouse | 04/14/23 11:53 AM
Row 811 | 3/3/2023 application withdrawn | Kaiya Hoogkamp | 10/17/24 12:56 PM
Row 812 | 6/21/2022 application withdrawn | Kaiya Hoogkamp | 10/17/24 12:55 PM
Row 813 | 10/19/2022 application withdrawn | Kaiya Hoogkamp | 10/17/24 1:08 PM
Row 813 | Created USS1 under NES | Kristina Waterhouse | 05/31/23 1:51 PM
Row 813 | Requested W9 | Kristina Waterhouse | 05/30/23 12:04 PM
Row 814 | 6/17/2022 application withdrawn. | Kaiya Hoogkamp | 10/17/24 12:59 PM
Row 815 | 6/17/2022 application withdrawn | Kaiya Hoogkamp | 10/17/24 12:58 PM
Row 819 | 6/30/2022 application withdrawn | Kaiya Hoogkamp | 10/17/24 1:10 PM
Row 821 | 6/15/2022 application withdrawn | Kaiya Hoogkamp | 10/17/24 1:09 PM
Row 823 | 6/8/2022 application withdrawn | Kaiya Hoogkamp | 10/17/24 1:27 PM
Row 825 | 6/27/2022 application withdrawn | Kaiya Hoogkamp | 10/17/24 1:28 PM
Row 826 | 0000000913 refund draft for the $500.00 payment in advance deposit that was unused, refund processed 5/1/26 | Kaiya Hoogkamp | 05/01/26 10:17 AM
Row 826 | 4/4/25 email for IA sent. 30 BD 5/19/2025 | Kaiya Hoogkamp | 04/04/25 3:36 PM
Row 826 | 500.00 payment open cash dated 7/27/2023 from First National bank referencing Eva Frey | Staci Pellegrini | 09/01/23 7:43 AM
Row 826 | followed up on status of ESA | Kristina Waterhouse | 06/05/23 11:43 AM
Row 826 | Emailed Will and Jess.... records die after ESA sent to customer | Kristina Waterhouse | 05/30/23 12:38 PM
Row 826 | I don't see signed agreement or ESA results in portal | Kristina Waterhouse | 04/25/23 1:14 PM
Row 827 | Both the customer and developer paid the remaining ESA Balance of $486.70. Refunded the customer on 2/26/26 draft: 0000000370, debtor: 1341785 | Kaiya Hoogkamp | 02/26/26 11:01 AM
Row 827 | Extended debtor in SAP | Kristina Waterhouse | 06/02/23 12:29 PM
Row 827 | Receiced W9 naming Outlook Farm LLC as a DBA for Great Works Properties. There is a blocked debtor in SAP that matches by TIN. Submitted INC2876682 to have it unblocked. | Kristina Waterhouse | 06/02/23 12:09 PM
Row 827 | Emailed for updated assigment information and W9.... name in portal and on CMP account has been updated to Great Works Property Inc | Kristina Waterhouse | 05/31/23 11:19 AM
Row 828 | 6/8/2022 application withdrawn | Kaiya Hoogkamp | 10/17/24 1:30 PM
Row 829 | Old Account# 30013836017 | Nathan Lawrence | 07/25/24 3:42 PM
Row 830 | Ticket INC2812351 to clear payment | Kristina Waterhouse | 05/03/23 7:07 AM
Row 834 | confirmation of withdrawal sent on 12/23/2022 | Kaiya Hoogkamp | 02/13/26 12:20 PM
Row 834 | no documentation confirming the withdrawal date | Kaiya Hoogkamp | 10/17/24 1:57 PM
Row 836 | Sent email to check on status/withdrawal date 2/13/2026 | Kaiya Hoogkamp | 02/13/26 12:40 PM
Row 836 | no documentation confirming the project is withdrawn | Kaiya Hoogkamp | 10/17/24 2:33 PM
Row 837 | 6/30/2022 application withdrawn | Kaiya Hoogkamp | 10/17/24 2:16 PM
Row 838 | 7/2/26 emailed requesting payment for app invoice | Kaiya Hoogkamp | 07/02/26 2:02 PM
Row 838 | Doubtful debt cleared | Kaiya Hoogkamp | 04/14/23 3:23 PM
Row 839 | 4/9/2022 failed ESA and withdrew | Kaiya Hoogkamp | 10/17/24 2:39 PM
Row 839 | Adj invoicefrom 2994.64 to 2007.92 910207125 | Staci Pellegrini | 01/12/24 10:38 AM
Row 839 | Kristina has over billed 81262 she billed part of Auburn Penley Corner to this one invoice needs to be adj | Staci Pellegrini | 01/12/24 9:50 AM
Row 839 | They replied that they will update the name on the account to Novel... still has not been done. Sent follow up email. | Kristina Waterhouse | 05/30/23 12:00 PM
Row 839 | Requested W9 | Kristina Waterhouse | 05/24/23 1:09 PM
Row 840 | 8/30/2022 4:17:31 PM Jessie Roderick (U341040) ESA not needed. TS passed. DE revised. | Kristina Waterhouse | 03/21/23 12:32 PM
Row 841 | Charges in 12/22 but study was completed 8/22 | Kristina Waterhouse | 05/24/23 1:45 PM
Row 842 | 7/19/2022 application withdrawn | Kaiya Hoogkamp | 10/17/24 2:47 PM
Row 843 | 2/13/26 sent follow up on project status | Kaiya Hoogkamp | 02/13/26 12:56 PM
Row 843 | no documentation for withdrawal | Kaiya Hoogkamp | 10/17/24 2:45 PM
Row 844 | 2/13/26 sent follow up on project status | Kaiya Hoogkamp | 02/13/26 1:11 PM
Row 844 | no documentation regarding withdrawal | Kaiya Hoogkamp | 10/17/24 2:58 PM
Row 844 | cleared by doubtful debt | Kaiya Hoogkamp | 04/17/23 8:57 AM
Row 845 | 2/13/26 sent follow up on project status | Kaiya Hoogkamp | 02/13/26 1:07 PM
Row 845 | no documentation about withdrawal | Kaiya Hoogkamp | 10/17/24 2:55 PM
Row 848 | 2/9/2023 application withdrawn | Kaiya Hoogkamp | 10/17/24 3:03 PM
Row 849 | 8/9/2022 application withdrawn | Kaiya Hoogkamp | 10/17/24 3:16 PM
Row 850 | Per W9 refund needs to be issued on USM1 debtor 929912. Submitted INC2879510 to move payment to correct debtor. | Kristina Waterhouse | 06/05/23 7:51 AM
Row 850 | Sent follow up email | Kristina Waterhouse | 06/02/23 10:35 AM
Row 850 | Sent follow up email for refund info. | Kristina Waterhouse | 05/22/23 7:33 AM
Row 850 | Sent email requesting W9 and to confirm refund info | Kristina Waterhouse | 05/15/23 12:49 PM
Row 850 | Submitted INC2836270 to clear adjusted invoice and open funds for refund. | Kristina Waterhouse | 05/15/23 12:43 PM
Row 851 | 8/9/2022 application withdrawn. | Kaiya Hoogkamp | 10/17/24 3:12 PM
Row 853 | INC2812351 to clear payment | Kristina Waterhouse | 05/03/23 7:07 AM
Row 855 | no documentation confirming withdrawal | Kaiya Hoogkamp | 10/17/24 3:10 PM
Row 857 | 8/17/2022 customer withdrew project | Kaiya Hoogkamp | 05/22/24 9:53 AM
Row 858 | The invoice was paid using a bulk refund from other Level2 Novel projects that were owed a refund (see attachment) | Thomas Blanchard | 06/17/25 10:01 AM
Row 858 | 8/8/2022 application withdrew | Kaiya Hoogkamp | 10/17/24 3:19 PM
Row 858 | sent reminder email for payment 1/10/2024 | Helen Markham | 01/10/24 2:52 PM
Row 859 | 2/13/26 sent follow up on project status | Kaiya Hoogkamp | 02/13/26 1:14 PM
Row 859 | no documentation on withdrawal | Kaiya Hoogkamp | 10/17/24 3:23 PM
Row 860 | 8/2/2022 application withdrawn | Kaiya Hoogkamp | 10/17/24 3:30 PM
Row 861 | 2000.00 910154560 | Staci Pellegrini | 01/08/24 4:58 PM
Row 861 | revision 1289121 | Staci Pellegrini | 01/08/24 4:55 PM
Row 861 | $2000.00 esa deposit paid by revision 1489121.. remaining balance Kristina billed under 933140 | Staci Pellegrini | 01/08/24 4:54 PM
Row 861 | Requested debtor in SAP | Kristina Waterhouse | 05/12/23 1:26 PM
Row 862 | no documentation verifying withdrawal. | Kaiya Hoogkamp | 10/17/24 3:29 PM
Row 862 | Converted NOTI to USM1 and exteneded to 90/90 | Kristina Waterhouse | 05/30/23 1:14 PM
Row 862 | Followed up on W9 request | Kristina Waterhouse | 05/24/23 12:52 PM
Row 862 | Requested W9 | Kristina Waterhouse | 05/12/23 1:37 PM
Row 864 | 9/27/2022 application withdrawn | Kaiya Hoogkamp | 10/17/24 3:32 PM
Row 866 | 9/28/2022 application moved to level 4 and withdrawn as level 2. | Kaiya Hoogkamp | 10/17/24 3:42 PM
Row 867 | 10/10/2022 application withdrawn | Kaiya Hoogkamp | 10/17/24 3:41 PM
Row 867 | Submitted INC2833148 to clear adjusted invoice and open for refund | Kristina Waterhouse | 05/12/23 1:17 PM
Row 868 | CM 910182276 to clear incorrect invoice 910174017 on wrong debtor | Kristina Waterhouse | 06/05/23 12:38 PM
Row 868 | Extended debtor in SAP | Kristina Waterhouse | 05/31/23 11:51 AM
Row 870 | 4/26/2022 application withdrew | Kaiya Hoogkamp | 10/17/24 3:39 PM
Row 871 | 5/26/2022 application moved to level 4 and withdrawn as level 2. | Kaiya Hoogkamp | 10/17/24 3:44 PM
Row 872 | Sent follow up for status/confirmation of withdrawal 2/13/2026 | Kaiya Hoogkamp | 02/13/26 1:38 PM
Row 872 | no documentation verifying withdrawal. | Kaiya Hoogkamp | 10/17/24 3:45 PM
Row 873 | 2/13/2026 sent customer email regarding withdrawal | Kaiya Hoogkamp | 02/13/26 1:44 PM
Row 873 | no documentation verifying withdrawal | Kaiya Hoogkamp | 10/17/24 3:55 PM
Row 873 | transferred to doubtful debt to cleared | Kaiya Hoogkamp | 04/17/23 2:33 PM
Row 874 | no documentation confirming withdrawal | Kaiya Hoogkamp | 10/17/24 3:52 PM
Row 874 | paid 06/26/2023 | Helen Markham | 01/11/24 10:27 AM
Row 874 | sent itnow ticket to clear dd with credit memo | Staci Pellegrini | 01/08/24 4:43 PM
Row 874 | Original invoice is with doubtful debt, need to identify the process | Kristina Waterhouse | 07/03/23 9:36 AM
Row 874 | Requested extension to 90/90 in SAP | Kristina Waterhouse | 06/05/23 12:31 PM
Row 874 | Customer replied that they are in the process of this project changing from Penobscot Narrow Solar to Penobscot Narrow Solar I. Asked estimated time frame | Kristina Waterhouse | 05/23/23 1:37 PM
Row 874 | Requested W9 | Kristina Waterhouse | 05/12/23 12:23 PM
Row 875 | 5/26/2022 project failed ESA and withdrew | Kaiya Hoogkamp | 10/17/24 3:56 PM
Row 876 | no documentation confirming the project is withdrawn | Kaiya Hoogkamp | 10/18/24 11:08 AM
Row 877 | level 1 project | Kaiya Hoogkamp | 10/18/24 10:59 AM
Row 878 | 12/6/2022 application withdrawn | Kaiya Hoogkamp | 10/18/24 11:18 AM
Row 879 | 6/8/2022 application withdrawn | Kaiya Hoogkamp | 10/18/24 11:15 AM
Row 879 | sent reminder email for payment 1/10/2024 | Helen Markham | 01/10/24 2:53 PM
Row 879 | Sent email for charge clarification. Katherine had labeled some June charges for this project but the study had already been completed in May. Novel had multiple projects during this time period. | Kristina Waterhouse | 05/30/23 11:53 AM
Row 880 | 6/20/2022 application withdrawn | Kaiya Hoogkamp | 10/18/24 11:23 AM
Row 881 | 5/26/2022 application withdrawn | Kaiya Hoogkamp | 10/18/24 11:22 AM
Row 882 | 6/30/2022 application withdrawn. | Kaiya Hoogkamp | 10/18/24 11:21 AM
Row 884 | 4/5/2022 application withdrawn | Kaiya Hoogkamp | 10/18/24 11:20 AM
Row 885 | 9/14/2022 application withdrawn | Kaiya Hoogkamp | 10/18/24 11:25 AM
Row 886 | Project in default, not paid | Thomas Blanchard | 06/17/25 12:44 PM
Row 886 | 4/25/2022 app failed ESA and withdrawn | Kaiya Hoogkamp | 10/18/24 11:28 AM
Row 886 | sent email to dante to ask why charges are 6475.35 when est being 500.00 | Staci Pellegrini | 01/08/24 3:05 PM
Row 886 | We charged 500.00 flat fee 7/7/2022 910150282/920166049 | Staci Pellegrini | 01/08/24 1:12 PM
Row 886 | W-9 Received | Kaiya Hoogkamp | 10/10/23 7:41 AM
Row 886 | Emailed requesting W-9 in order to create final invoice | Kaiya Hoogkamp | 10/02/23 1:41 PM
Row 886 | Followed up on W9 request | Kristina Waterhouse | 06/21/23 8:24 AM
Row 886 | Requested W9 | Kristina Waterhouse | 06/05/23 11:42 AM
Row 886 | Requested W9 | Kristina Waterhouse | 05/26/23 9:18 AM
Row 887 | Sent email confirming refund information | Kristina Waterhouse | 05/23/23 8:46 AM
Row 887 | 910152320 920169118 7/28/2022 CREATED / ADJ 3/17/2023 920191690 2000.00 | Staci Pellegrini | 04/18/23 3:50 PM
Row 887 | REFUND NEEDED | Staci Pellegrini | 04/18/23 3:26 PM
Row 889 | 3/21/2025 project emailed they are withdrawing. | Kaiya Hoogkamp | 03/21/25 1:18 PM
Row 891 | 3/21/2025 project emailed they are withdrawing. | Kaiya Hoogkamp | 03/21/25 1:16 PM
Row 892 | orig inovice 2000.00 910155488 920171646 4/28/2022 debtor 910795 has been adj 0.00 910232840 due to inv kristina created listed here | Staci Pellegrini | 08/07/24 11:23 AM
Row 892 | Paid 07/28/2023 | Helen Markham | 01/11/24 10:29 AM
Row 892 | The hx invoice is with doubtful debt. Submitted INC2936503 to determine the correct process for adjusting this invoice | Kristina Waterhouse | 07/03/23 9:21 AM
Row 892 | Extended debtor in SAP | Kristina Waterhouse | 06/05/23 9:12 AM
Row 892 | Followed up again on W9 request | Kristina Waterhouse | 05/31/23 11:26 AM
Row 892 | Followed up on W9 request | Kristina Waterhouse | 05/23/23 1:13 PM
Row 892 | Requested W9 | Kristina Waterhouse | 05/11/23 1:59 PM
Row 894 | 910217346/920237740 - contract 120006275, balance $370.87 | Kaiya Hoogkamp | 03/17/26 2:51 PM
Row 894 | 6/3/2022 application withdrawn | Kaiya Hoogkamp | 10/18/24 11:31 AM
Row 894 | Prior invoice 0.00 due to pia found 2000.00 from 10/11/2022 6000.00 group pmt, Tom created new PIA NEW CONTRACT 120006275/ | Staci Pellegrini | 03/15/24 9:53 AM
Row 894 | 910185191 to clear Katherines old invoice | Kristina Waterhouse | 06/30/23 12:15 PM
Row 895 | Additional $164.45 was billed and paid by bulk payment on 7/7/2025. | Thomas Blanchard | 07/07/25 3:00 PM
Row 895 | The invoice was paid using a bulk refund from other Level2 Novel projects that were owed a refund (see attachment) | Thomas Blanchard | 06/17/25 9:58 AM
Row 895 | 5/18/2022 application failed ESA and withdrew | Kaiya Hoogkamp | 10/18/24 11:31 AM
Row 895 | New contract 120006269, PIA 910213705 | Thomas Blanchard | 03/06/24 9:46 AM
Row 895 | 120005192 prior contract from Kristina did not have 500.00 pai this has been canceled and 0.00 TOm to create an new contract and pia and invoice 3/5/24 | Staci Pellegrini | 03/05/24 11:33 AM
Row 895 | prior invoice 2096..78 has been 0.00 Helen located 500.00 pia that belongs to this contract this needs to be reinvoiced under a new contract. Details in project backup file | Staci Pellegrini | 03/05/24 11:25 AM
Row 895 | sent reminder email for payment 1/10/2024 | Helen Markham | 01/10/24 2:53 PM
Row 895 | I had already tried to adjust this.... verified all old invoices are correctly cleared and only invoice that is outstanding is the one for 2096.78 | Kristina Waterhouse | 06/30/23 12:10 PM
Row 895 | ORIGINAL INVOICE WAS AMENDED SO CREDIT CREDIT INVOICE WAS CREATED 910184660 | Staci Pellegrini | 06/26/23 12:46 PM
Row 895 | 6/26/2023 0.00 invoice created 9/15/2022 910156432/920172671 930085 was replaced w 120005192 invoice920200848 910182481 | Staci Pellegrini | 06/26/23 11:59 AM
Row 895 | 910183703 to clear Katherines unpaid straight invoice | Kristina Waterhouse | 06/16/23 12:11 PM
Row 897 | 9/30/2024 project withdrawn. | Kaiya Hoogkamp | 09/30/24 11:51 AM
Row 897 | sent reminder email for payment 1/10/2024 | Helen Markham | 01/10/24 2:54 PM